## Data Request Estimate
SDG&E Cost Estimate for TURN DR-02 Q5d
Revised 2/22/17 - RLS
All cost estimates are unloaded
Cost estimate for 350 kW infrastructure
New Electrical Service Cost Estimate for one site (without transformer costs)
CapEx | CapEx | O&M | O&M
Non-Labor | Labor | Non-Labor | Labor
19000 |  |  |  | Meter Pedestal @ $19,000 material
| 5000 |  |  | Meter Pedestal Installation @ $5,000 labor (*)
100 |  |  |  | Smart Meter @ $100
| 2000 |  |  | Traffic Control ($2,000 per job) (*)
| 26250 |  |  | Trench from xfrmr to pedestal (150') & refill/repair asphalt/conduit @$175/ft (*)
| 45000 |  |  | Trench from pedestal to chargers (300') & refill/repair asphalt/conduit @ $150/ft (*)
| 11250 |  |  | Wire & connectors - installation from xfrmr to pedestal and chargers (450 feet @ $25/foot) (*)
19100 | 89500 | 0 | 0 | Subtotal
1528 |  | 0 |  | 8% Tax
| 13425 |  |  | 15% Contractor Items Profit (*)
2865 | 13425 |  |  | 15% Contingency
23493 | 116350 | 0 | 0 | Total
Cost estimate for 350 kW infrastructure
Transformer & Installation Cost Estimate for one site
CapEx | CapEx | O&M | O&M
Non-Labor | Labor | Non-Labor | Labor
7500 | 6000 | 450 | 600 | 500 kVA transformer
| 23000 |  |  | Contractor Labor for installation (*)
7500 | 29000 | 450 | 600 | Subtotal
600 |  | 36 |  | 8% Tax
| 3450 |  |  | 15% Contractor Items Profit (*)
1125 | 4350 | 67.5 | 90 | 15% Contingency
9225 | 36800 | 553.5 | 690 | Total
Cost estimate for 350 kW infrastructure
Design / Permit Fees Cost Estimate for one site
CapEx | CapEx | O&M | O&M
Non-Labor | Labor | Non-Labor | Labor
| 25000 |  |  | Site Walks / Engineering / Design / Document Preparation (*)
| 1000 |  |  | Permit Fees
0 | 26000 | 0 | 0 | Subtotal
0 |  | 0 |  | 8% Tax
| 3750 |  |  | 15% Contractor Items Profit (*)
0 | 3900 | 0 | 0 | 15% Contingency
0 | 33650 | 0 | 0 | Total
32718 | 186800 | 553.5 | 690 | Totals
Total Capital: | 219518
Total O&M: | 1243.5
Grand Total: | 220761.5