## CalPA DR4-Q3 2020
HFTD - Strategic Undergrounding Capital Spend - 20201
Project | Services | Materials | Internal Labor & Expenses | Discounts & Other | 2020 Total | Mileage Energized
SUG Projects In-Service (2020)
C1030 Phase 1 | 5117907.2036 | 679912.6591 | 32003.6568 | -70542.1956 | 5759281.3239 | 5.9
Apollo C357 Job 1 and Job 2 | 1756620.935 | 294363.524 | 154565.4698 | -36779.82 | 2168770.1089 | 0.83
C221 Phase 1 | 790754.49 | 196117.58 | 1752.2058 | -136 | 988488.2758 | 0.53
C221 Phase 2 | 933394 | 57740.23 | 2004.29 | -9676.91 | 983461.61 | 0.9
C1021 Ext UG to Lilac HS | 506100.4636 | 294642.3242 | 674.7734 | -3781.0127 | 797636.5486 | 0.2
C75 DUG | 1830372.75 | 966322.16 | 21656.14 | -21990.46 | 2796360.59 | 6.8
C754 | 315541.88 | 12981.84 | 1789.88 | -5809.95 | 324503.65 | 0.3
Sub-total | 11250691.7223 | 2502080.3174 | 214446.4158 | -148716.3483 | 13818502.1072 | 15.46
[6 empty] | 15.58 | Provided in 2020 WMP Filing was 15.58 miles, which shows 0.12miles difference. This should be corrected to 15.5 miles
SUG Projects in Early Construction for 2021
C1242 M121221 UG CABLE UPGRADE | 43687.1 | 9047.81 | -257.09 | -2234.65 | 50243.17
C1030 PH. 2A PARADISE MTN RD UG | 14265.6 | 0 | 1293.07 | 0 | 15558.67
C1030 PH. 2B HELLHOLE CANYON UG | 1664276.26 | 0 | 1776.81 | -33009.09 | 1633043.98
C1030, DUG STRATEGIC UG - UG | 5865.7439 | 0 | 3389.6016 | 0 | 9255.3456
C1030, DUG STRATEGIC UG-SCADA | 0 | 0 | 149.2653 | 0 | 149.2653
C1458 PH 1 W VICTORIA DR UG | 361156.8281 | 579667.0834 | 3742.408 | 36.33 | 944602.6494
C1458 PH1 W VICTORIA DR UG KSW | 0 | 0 | 786.048 | 0 | 786.048
C1458 PH2 ADMINISTRATION WY UG | 1596 | 0 | 0 | -31.92 | 1564.08
C1458 PHASE 1 W VICTORIA DR UG | -4.5475e-13 | 0 | 0 | 0 | -4.5475e-13
C216 HFTD STRATEGIC UG HARRAHS | 5540 | 0 | 92.31 | 0 | 5632.31
C216 HFTD STRATEGIC UG HARRAHS UG | 9878 | 0 | 811.1 | -79.56 | 10609.54
C216 SUG HARRAHS PH1 SCADA | 0 | 0 | 981.55 | 0 | 981.55
C221 DUG PH1 DT JULIAN CON UG | 4809.38 | 0 | 0 | 0 | 4809.38
C221 DUG PH2 DUDLEYS OH | 11520.25 | 0 | 0 | 0 | 11520.25
C221 DUG PH4 SPENCER-HWY 79 UG | 2590 | 0 | 0 | 0 | 2590
C221: KEARNY SCADA WORK UG | 0 | 0 | -186.36 | 0 | -186.36
C358:DUG VIEJAS CASINO UG | 2877 | 0 | 117.29 | 0 | 2994.29
C441 DUG UG | 4225 | 0 | 23.46 | -84.5 | 4163.96
C442 DUG OH | 0 | 0 | 23.46 | 0 | 23.46
C445 DUG HFTD | 6473 | 0 | 129.23 | -15.96 | 6586.27
C445 DUG HFTD SCADA | 0 | 0 | 369.23 | 0 | 369.23
C448 DUG SCADA | 0 | 0 | 92.31 | 0 | 92.31
C448 DUG UG | 2407.8 | 0 | 0 | 0 | 2407.8
C79 HFTD TIER 3 UG PHASE 1 | 0 | 0 | 70.37 | 0 | 70.37
C79: DUG | 7358.91 | 0 | 105.77 | 0 | 7464.68
C79: DUG - UG SCADA | 0 | 0 | 184.62 | 0 | 184.62
Sub-total | 2148526.872 | 588714.8934 | 13694.4529 | -35419.35 | 2715516.8682
SUG Substation Projects
CAMERON STRATEGIC UNDERGROUNDIN | 97.5 | 0 | 2632.78 | -1.95 | 2728.33
DESCANSO C79 UNDERGROUNDING | 22712 | 0 | 4391.06 | -100.25 | 27002.81
GLENCLIFF 12KV STRATEGIC UNDERG | 1654.73 | 0 | 499.6204 | -6.04 | 2148.3104
RINCON SUBS CIR 216 OH TO UG CO | 228239.9025 | 265.04 | 6174.2398 | -1401.9182 | 233277.264
SANTA YSABEL SUBS-C221 & C222 | 31566.81 | 0 | 2403.3 | -32.03 | 33938.08
Sub-total | 284270.9425 | 265.04 | 16101.0002 | -1542.1882 | 299094.7944
SUG Engineering/Design, Internal Labor, and Project Support
Sub-total | 21570145.5414 | 17706.8943 | 331220.9498 | 97548.3493 | 22016621.7348
Grand Total | 35253635.0782 | 3108767.1451 | 575462.8186 | -88129.5372 | 38849735.5047
1Reflects CPUC jurisdiction costs only

## CalPA DR4-Q3 2021
SUG 2021 - Design and Construction Budget Updated
Year | Circuit Number | General Information | Status | # UG Miles | District | Civil | Electrical | Material | Total | Adjusted | Cost Per Mile | Notes
2021 | C1030 | Phase 2A (Paradise Mtn.) | In Construction | 5.997 |  | 8095950 | 4047975 | 1349325 | 13493250 | 9193250 | 1532974.8207 | Adjusted for charges in 2020, Civil is 18% done
2021 | C1030 | Phase 2B (Hell Hole Canyon) | In Construction | 4.45 |  | 6007500 | 3003750 | 1001250 | 10012500 | 10012500 | 2250000 | Civil is 85% done
2021 | C1030 | DUG Ph.1 Valley Center | In bid | 3.876 |  | 5232600 | 2616300 | 872100 | 8721000 | 8721000 | 2250000
2021 | C1458 | Quick Win PH.1A W. Victoria Rd | In Construction | 2.3 |  | 3105000 | 1552500 | 517500 | 5175000 | 3475000 | 1510869.5652 | Adjusted for Charges in 2020, 20% Civil Complete
2021 | C221 | DUG PH.2 (ST to Dudley's) | In Design | 0.41 |  | 553500 | 276750 | 92250 | 922500 | 922500 | 2250000
2021 | C221 | DUG PH.1 (Dwntn Julian Connection) | In Design | 1.674 |  | 2259900 | 1129950 | 376650 | 3766500 | 3766500 | 2250000
2021 | C221 | DUG PH.4 (Spencer Sch to Hwy 79) | In Design | 1.895 |  | 2558250 | 1279125 | 426375 | 4263750 | 4263750 | 2250000
2021 | C357 | Quick Win Job#3-- E. Victoria Rd (FIRM) | In Design | 0.1 |  | 135000 | 67500 | 22500 | 225000 | 225000 | 2250000
2021 | C445 | DUG | In Design | 3.2168 |  | 4342680 | 2171340 | 723780 | 7237800 | 7237800 | 2250000
2021 | C448 | DUG | In Design | 1.23 |  | 1660500 | 830250 | 276750 | 2767500 | 2767500 | 2250000
2021 | C79 | DUG - Oak Grove Drive | In Bid | 3.093 |  | 4175550 | 2087775 | 695925 | 6959250 | 6959250 | 2250000
2021 | C216 | DUG PH.1 to Rincon's Harrah's Casino | In Design | 3.11 | Project schedule with more uncertainty at the moment. | 4198500 | 2099250 | 699750 | 6997500 | 6997500 | 2250000
2021 | C1458 | Quick Win PH.1B Across Caltrans | In Design | 0.1 |  | 135000 | 67500 | 22500 | 225000 | 225000 | 2250000
2021 | C1458 | Quick Win PH.2 AL Elem School | In Design | 0.24 |  | 324000 | 162000 | 54000 | 540000 | 540000 | 2250000
2021 | C448 | Microgric Solution partnership w/ SUG | In Design | 0.82 |  | 1107000 | 553500 | 184500 | 1845000 | 1845000 | 2250000
|  |  |  | 28.2418 |  | 43890930 | 21945465 | 7315155 | 73151550 | 67151550 | 2377736.1925
Design
C210 | DUG |  |  | 4 |  |  |  |  | #REF! | #REF! | #REF!
C221 | DUG PH.3 (ST to Spencer Sch.)* |  |  | 2.9 |  |  |  |  | #REF! | #REF! | #REF!
C235 | DUG |  |  | 3.5 |  |  |  |  | #REF! | #REF! | #REF!
C355 | DUG |  |  | 2.2 |  |  |  |  | #REF! | #REF! | #REF!
C358* | DUG* |  |  | 2.5 |  |  |  |  | #REF! | #REF! | #REF!
C441 | DUG* |  |  | 4.9 |  |  |  |  | #REF! | #REF! | #REF!
C442 | DUG* |  |  | 3.1 |  |  |  |  | #REF! | #REF! | #REF!
C79 | Ph.1 Sherilton Valley* |  |  | 8.08 |  |  |  |  | #REF! | #REF! | #REF!
C908 | DUG |  |  | 3.6 |  |  |  |  | #REF! | #REF! | #REF!
|  |  |  | 34.78 |  |  |  |  | #REF! | #REF! | #REF!
[8 empty] | Total |  | #REF! | #REF!
|  |  |  | Line Energized Goal | 135
| Miles |  |  | 2020 | 30.2
Original Design | 75 | Original design plan |  | 2021 | 36
Addtl Design | 30 | To support 2022 80mi construction |  | 2022 | 68.8
Original Construction | 25 | Original Target miles
Early/Addtl Construction | 11 | Early construction to support 2022 80mi construction scope increase
Total Design | 105
Total Construction | 36
Cost/mile Unit Based on 2020 Actuals
Civil | 1350000 | 60% |  | 2250000 | Construction
Electrical | 675000 | 30% |  | 350000 | Design
Material | 225000 | 10% |  | 20% increase | Other Support
Design | 350000
Direct Cost | 2600000 | 100%
| Miles | Direct - $'s
Engineering & Design | 105 | 36750000
Construction | 36 | 72900000
Material | 36 | 8100000
117750000
Other |  | 2021 w/ 20% increase due to scope increase
Environmental |  | 315600
Land Services |  | 198000
Project Support |  | 885600
Substation Engineering |  | 2000000
Internal Labor |  | 600000
3999200
Direct Cost |  | 121749200 | 1493250 | Difference compare from 2/2/21 submittal: |  | 120255950
Note on C56: No increase; based on need

## CalPA DR4-Q3 2022
SUG 2022 - Design and Construction Budget Updated
Year | Circuit Number | General Information | Status | # UG Miles | District | Civil | Electrical | Material | Total | Adjusted | Cost Per Mile | Notes
2021 | C1030 | Phase 2A (Paradise Mtn.) | In Construction | 5.997 |  | 8095950 | 4047975 | 1349325 | 13493250 | 9193250 | 1532974.8207 | Adjusted for charges in 2020, Civil is 18% done
2021 | C1030 | Phase 2B (Hell Hole Canyon) | In Construction | 4.45 |  | 6007500 | 3003750 | 1001250 | 10012500 | 10012500 | 2250000 | Civil is 85% done
2021 | C1030 | DUG Ph.1 Valley Center | In bid | 3.876 |  | 5232600 | 2616300 | 872100 | 8721000 | 8721000 | 2250000
2021 | C1458 | Quick Win PH.1A W. Victoria Rd | In Construction | 2.3 |  | 3105000 | 1552500 | 517500 | 5175000 | 3475000 | 1510869.5652 | Adjusted for Charges in 2020, 20% Civil Complete
2021 | C221 | DUG PH.2 (ST to Dudley's) | In Design | 0.41 |  | 553500 | 276750 | 92250 | 922500 | 922500 | 2250000
2021 | C221 | DUG PH.1 (Dwntn Julian Connection) | In Design | 1.674 |  | 2259900 | 1129950 | 376650 | 3766500 | 3766500 | 2250000
2021 | C221 | DUG PH.4 (Spencer Sch to Hwy 79) | In Design | 1.895 |  | 2558250 | 1279125 | 426375 | 4263750 | 4263750 | 2250000
2021 | C357 | Quick Win Job#3-- E. Victoria Rd (FIRM) | In Design | 0.1 |  | 135000 | 67500 | 22500 | 225000 | 225000 | 2250000
2021 | C445 | DUG | In Design | 3.2168 |  | 4342680 | 2171340 | 723780 | 7237800 | 7237800 | 2250000
2021 | C448 | DUG | In Design | 1.23 |  | 1660500 | 830250 | 276750 | 2767500 | 2767500 | 2250000
2021 | C79 | DUG - Oak Grove Drive | In Bid | 3.093 |  | 4175550 | 2087775 | 695925 | 6959250 | 6959250 | 2250000
2021 | C216 | DUG PH.1 to Rincon's Harrah's Casino | In Design | 3.11 | Project schedule with more uncertainty at the moment. | 4198500 | 2099250 | 699750 | 6997500 | 6997500 | 2250000
2021 | C1458 | Quick Win PH.1B Across Caltrans | In Design | 0.1 |  | 135000 | 67500 | 22500 | 225000 | 225000 | 2250000
2021 | C1458 | Quick Win PH.2 AL Elem School | In Design | 0.24 |  | 324000 | 162000 | 54000 | 540000 | 540000 | 2250000
2021 | C448 | Microgric Solution partnership w/ SUG | In Design | 0.82 |  | 1107000 | 553500 | 184500 | 1845000 | 1845000 | 2250000
|  |  |  | 28.2418 |  | 43890930 | 21945465 | 7315155 | 73151550 | 67151550 | 2377736.1925
Design
C210 | DUG |  |  | 4 |  |  |  |  | #REF! | #REF! | #REF!
C221 | DUG PH.3 (ST to Spencer Sch.)* |  |  | 2.9 |  |  |  |  | #REF! | #REF! | #REF!
C235 | DUG |  |  | 3.5 |  |  |  |  | #REF! | #REF! | #REF!
C355 | DUG |  |  | 2.2 |  |  |  |  | #REF! | #REF! | #REF!
C358* | DUG* |  |  | 2.5 |  |  |  |  | #REF! | #REF! | #REF!
C441 | DUG* |  |  | 4.9 |  |  |  |  | #REF! | #REF! | #REF!
C442 | DUG* |  |  | 3.1 |  |  |  |  | #REF! | #REF! | #REF!
C79 | Ph.1 Sherilton Valley* |  |  | 8.08 |  |  |  |  | #REF! | #REF! | #REF!
C908 | DUG |  |  | 3.6 |  |  |  |  | #REF! | #REF! | #REF!
|  |  |  | 34.78 |  |  |  |  | #REF! | #REF! | #REF!
[8 empty] | Total |  | #REF! | #REF!
|  |  |  | Line Energized Goal | 135
| Miles |  |  | 2020 | 30.2
Original Design | 162.5 | To support 2023 125mi construction |  | 2021 | 70
Addtl Design | 0 | N/A |  | 2022 | 34.8
Original Construction | 70 | To support 2020-2022 135mi construction goal
Early/Addtl Construction | 0 | N/A
Total Design | 162.5
Total Construction | 70
Cost/mile Unit Based on 2020 Actuals
Civil | 1350000 | 60% |  | 2250000 | Construction
Electrical | 675000 | 30% |  | 350000 | Design
Material | 225000 | 10% |  | 40% increase | Other Support
Design | 350000
Direct Cost | 2600000 | 100%
| Miles | Direct - $'s
Engineering & Design | 162.5 | 56875000
Construction | 70 | 141750000
Material | 70 | 15750000
214375000
Other |  | 2021 w/ 40% increase due to scope increase
Environmental |  | 368200
Land Services |  | 231000
Project Support |  | 1033200
Substation Engineering |  | 2000000
Internal Labor |  | 700000
4332400
Total Direct Costs |  | 218707400 | 21508200 | Difference compare from 2/2/21 submittal: |  | 197199200
Note on C56: No increase; based on need