## Agg.Summary & Table
Aggregated Summary & Table Template
*Created to satisfy the summary/table requirements of the reporting
Holistic Energization Steps - Average, Median, and Standard Deviation Reporting Requirements
Requirement Number | Ruling Info | Additional Information | Source | Calendar Days |  |  | Business Days
|  |  |  | Average | Median | Standard Deviation | Average | Median | Standard Deviation
1 | Receiving application and Energizing the Electrical Service | End to End Cycle Time (Data Point: 1 to 8) | Data Sheet | 147.4205 | 114 | 119.9669 | 105.6408 | 82 | 85.7754
2 | Each step of energization process within IOU's direct Control | Steps 2, 4, 6, 7, & 8 only | Data Sheet | 13 | 13 | 64.6121 | 28.4864 | 9 | 46.1474
2 (continued) | Each step of energization process NOT within IOU's direct Control | Steps 1, 3, and 5 only | Data Sheet | 57.6903 | 15 | 118.9536 | 41.44 | 11 | 85.0029
% Reporting Requirements
Requirement Number | Ruling Info | Additional Information | Source
4 | % of energization projects deemed complete annually | % determination for projects completed end to end | Separate file (tracking amount of projects energized by end of year) | 62.21%
5 | % of energization projects meeting adopted average | % of projects meeting adopted average | Data Sheet | 64.28%
5 | % of energization projects meeting adopted maximum | % of projects meeting adopted maximum | Data Sheet | 84.57%
Energization Reporting Requirements (End-Use)
Requirement Number | Ruling Info | Additional Information | Source | Business Class
|  |  |  | Residential | Commercial | Agriculture | Rule 45 | MPUs
8 | Total number of different end-use project types requesting service | Sum | Separate file (tracking all the different end-use projects requesting service) | N/A | N/A | N/A | N/A | N/A
10 | Total number of energization project requests received annually broken down by end-use | Sum and aggregation | Separate file (tracking all service requests) | N/A | N/A | N/A | N/A | N/A
10.1 | Total number of energization project requests approved to start energization process annually broken down by end-use | Sum and aggregation | Separate file (tracking all service requests) | 12210 | 3131 | 8 | 47 | 5995
11 | Total number of energization project requests completed annually broken down by end-use | Sum and aggregation | Separate file (tracking all service requests) | 7948 | 1606 | 6 | 18 | 4134
Total (Sum) Reporting Requirements
Requirement Number | Ruling Info | Additional Information | Source | Total (Sum)
12 | Total number of applicants that did not result in viable utility-side energization infrastructure deployments and why | Sum and summary | Separate file (tracking all service requests) | 827
28 | Total number of projects requesting R16 only | Sum | Separate file (tracking all service requests) | 14370
29 | Total number of projects requesting R29/45 only | Sum | Separate file (tracking all service requests) | 47
30 | Total number of projects requesting R15 only | Sum | Separate file (tracking all service requests) | 689
31 | Total number of projects requesting R15 & R16 only | Sum | Separate file (tracking all service requests) | 262
32 | Total number of projects requesting R15 & R29/45 only | Sum | Separate file (tracking all service requests) | 28
42 | Total number of main panel upgrades completed | Sum | Data Sheet | 4134
Individual & Aggregated Energization Steps - Average, Median, and Standard Deviation Reporting Requirements
Requirement Number | Ruling Info | Additional Information | Source | Calendar Days |  |  | Business Days
|  |  |  | Average | Maximum | Standard Deviation | Average | Maximum | Standard Deviation
18 | Aggregated summary of average, standard deviation, and maximum for IOU controlled steps | Step 2 only | Data Sheet | 45.3196 | 714 | 69.3692 | 32.6501 | 510 | 49.5412
|  | Step 4 only | Data Sheet | 30.7247 | 527 | 46.4275 | 22.1256 | 375 | 33.4397
|  | Step 6 only | Data Sheet | 96.0714 | 461 | 103.2069 | 68.9 | 329 | 73.6569
|  | Step 7 only | Data Sheet | 28.2148 | 503 | 41.9807 | 20.3656 | 359 | 29.9918
|  | Step 8 only | Data Sheet | 2.7606 | 416 | 15.3129 | 2.2636 | 298 | 11.0236
|  | Steps 2, 4, 6, 7, & 8 only | Data Sheet | 39.4545 | 714 | 64.6121 | 28.4864 | 510 | 46.1474
19 | Aggregated summary of average, standard deviation, and maximum for Customer controlled steps | Step 1 only | Data Sheet | 60.9094 | 2916 | 136.2788 | 43.7702 | 2082 | 97.2756
|  | Step 3 only | Data Sheet | 52.1334 | 457 | 73.7846 | 37.3767 | 327 | 52.6959
|  | Step 5 only | Data Sheet | 75.3216 | 625 | 82.318 | 54.0459 | 447 | 58.8214
|  | Steps 1, 3, and 5 only | Data Sheet | 57.7435 | 2916 | 118.9536 | 41.44 | 2082 | 84.9535
Summary/List Reporting Requirements
Requirement Number | Ruling Info | Additional Information | Source | Summary List
15 | Identification of constraints to infrastructure deployment (materials, staffing, permitting, need for upstream DCU, etc.) | List of items | Separate file (identification of constraints | See Narrative File, Section IV
Section 10 Page 59 | IOU provide information describing how timelines they track align with energization targets adopted, uses current data reporting tools, providing more individualized narrative | Summary | N/A (Summary of what IOU uses) | See Narrative File, Section IV
Section 10 Page 59 | IOU provide narrative information if information collected in existing systems does not meet targets adopted in decision | Summary | N/A (Summary) | See Narrative File, Section IV
Section 12 Page 70 | IOU provide description of the ESJ (environmental and social justice) barriers within energization data collection and reporting efforts | Summary | N/A (Summary) | See Narrative File, Section IV
Section 12 Page 70 | IOU provide efforts to overcome ESJ (environmental and social justice) barriers and delays and steps for improvement | Summary | N/A (Summary) | See Narrative File, Section IV
Section 7.1 Page 27 | SCE note in first biannual data reporting regarding the outlier removal and excluding those data points | Summary | N/A (Summary) | See Narrative File, Section IV
Concurrent Steps Requirement
Requirement Number | Ruling Info | Additional Information | Source | Steps | Total (timing)
2.1 | If applicable, identify the steps and total timing of the energization process performed concurrently. | List steps and timing for steps completed concurrently | Data sheet | Steps 2, 3, 4, 5, 6, 7 | 132975

## Tariff Closed
Preliminary Project Information | [7 empty] | Site Capacity & Capacity Requested |  |  |  | Upstream Capacity |  |  |  | Customer Desired Energization Date vs Final Energization Date |  |  | Additional Capacity, Flexible Service Option, & Cancelled/Delayed Project Information | [10 empty] | Tariff Upgrade |  |  | Customer Elect and Customer Project Delay |  |  |  | Costing Components | [9 empty] | Step 1 Intake (Customer) | [6 empty] | Step 2: Engineering and Design (IOU) |  |  |  | Step 3: Customer Dependencies (Customer) |  |  |  | Step 4: Utility Dependencies (IOU) |  |  |  | Step 5: Project Site Readiness (Customer) |  |  |  | Step 6: Project Site Readiness (IOU) |  |  |  | Step 7: Construction (IOU) |  |  |  | Step 8: Service Energization (IOU) |  |  |  | Customer Controlled Steps |  | IOU Controlled Steps |  | IOU & Customer Controlled Steps |  | Concurrent Steps |  |  | Meeting/Exceeding Energization Targets
Project Identifier # (project #) | Tariff (R15, R16, R29/R45, Combo) | OH (Overhead) or UG (Underground) | Applicant or IOU Design | Business Class (requested end-use) | Community type: Disadvantage Community (DAC) Underserved Community Tribal Community | City Project is Located in (City) | AHJ (Authority Having Jurisdiction) for permitting based off Project's location (AHJ) | Total Site Capacity at Time of Customer's Application for Service (kW) | Total Site Capacity Requested (kW) | Additional Capacity (kW) installed for future electric load deployment (as applicable) | Capacity Request Category: <1MW 1MW to 2M >2MW | Project triggered for upstream capacity project (Yes/No) | Date IOU identifies the need for an upstream capacity project and alerts customer of need for upstream capacity project (Date) | Date IOU completes the upstream capacity project (Date) | Time to complete upstream capacity project (Calendar Days) | Customer Desired Energization Date (Date) | Difference from Customer Desired Energization Date and Final Energization Date (Calendar Days) | Difference from Customer Desired Energization Date and Final Energization Date (Business Days) | Did customer install additional capacity to support future load growth? (Yes or No) | Identify when in the energization process the customer requested a change in design or scope (Date) | Identify when in energization process the customer requested a change in design or scope (Energization Step) | Customer cancelled/delayed project (as needed) (Yes or No) | Customer elected to install additional capacity to anticipate associated future load growth as indicated on customer's application (Yes or No) | Estimated timing for when customer anticipates additional capacity necessary as indicated on customer's application (Date) | Total additional kW capacity for the necessary future upgrade as listed on customer's application (kW) | If full energization of applicant site not feasible in a timely manner, explanation whether load management/flexible service options were installed/utilized to provide applicant with timely service | Amount of load (kW) provided to applicant using flexible service options (kW) | At the time energization provided, remaining (or total) unserved load requested by the applicant (kW) | Estimate when full service will be provided to the applicant for customers using flexible service and/or receiving tiered load schedules (Date) | Date when need for R15/16/29/45 upgrade identified (Date) | Date when Planning Work started R15/16/29/45 upgrade (Date) | Date when Construction Work started R15/16/29/45 upgrade (Date) | For R15/16 tariffs, did customer elect to take on typical IOU completed scope and vice versa. (i.e. Applicant Design or Applicant Install) (N/A, Customer elected Applicant Design/Install/Both) | For R15/16 tariffs, did customer elect to take on typical IOU completed scope and vice versa. Indicate Applicant Design or Applicant Install (N/A, Customer elected, IOU elected) Specify energization steps. (List Energization Steps) | For R15/R16 tariffs, project was delayed due to customer requested change in design or change in project scope (Yes, No) | For R15/R16 tariffs, the time the project was delayed due to customer requested change in design or change in project scope (Calendar Days) | Total Cost ($$$) to Complete All Energization Requests | Total Staffing, Labor, and Material Cost ($$$ Capital and Expense) | Total upstream capacity project cost ($$$) | Project Costs ($$$) for all IOU equipment for upstream capacity projects, Electric Rule 15, Electric Rule 16, and Electric Rule 29/45. | Project Costs ($$$) for anything else IOU covers | Total Construction/Overhead Costs ($$$) | Customer Allowance ($$$) | Estimated Costs ($$$) at Time of Design | Actual Costs ($$$) at Time of Energization | Difference of Estimated and Actual Costs at Time of Energization ($$$) | IOU assigned account/project manager for initial application (within 10 days) (Yes/No) | Date of IOU rejection of application (Date) | IOU reason for rejection of application (Reason) | Step 1 - Data Point Start 1) Intake Start Date (Date) | Step 1 - Data Point End 2) Intake End (Date) | Step 1: Intake (Calendar Days) | Step 1: Intake (Business Days) | Step 2 - Data Point Start 2) Engineering and Design Start (Date) | Step 2 - Data Point End 3) Engineering and Design End (Date) | Step 2: Engineering and Design (Calendar Days) | Step 2: Engineering and Design (Business Days) | Step 3 - Data Point Start 3) Customer Dependencies Start (Date) | Step 3 - Data Point End 4) Customer Dependencies End (Date) | Step 3: Customer Dependencies (Calendar Days) | Step 3: Customer Dependencies (Business Days) | Step 4 - Data Point Start 4) Utility Dependencies Start (Date) | Step 4 - Data Point End 5) Utility Dependencies End (Date) | Step 4: Utility Dependencies (Calendar Days) | Step 4: Utility Dependencies (Business Days) | Step 5 - Data Point Start 5) Customer Site Readiness Start (Date) | Step 5 - Data Point End 6) Customer Site Readiness End (Date) | Step 5: Site Readiness (Calendar Days) | Step 5: Site Readiness (Business Days) | Step 6 - Data Point Start 6) IOU Site Readiness Start (Date) | Step 6 - Data Point End 7) Site Readiness IOU End (Date) | Step 6: Site Readiness (Calendar Days) | Step 6: Site Readiness (Business Days) | Step 7 - Data Point Start 7) Construction Start (Date) | Step 7 - Data Point End 8) Construction End (Date) | Step 7: Construction (Calendar Days) | Step 7: Construction (Business Days) | Step 8 - Data Point Start 8) Service Energization Start (Date) | Step 8 - Data Point End 9) Service Energization End (Date) | Step 8: Service Energization (Calendar Days) | Step : Service Energization (Business Days) | Customer Controlled Steps: Step 1 - Intake, Step 3 - Customer Dependencies, & Step 5 - Site Readiness (Customer) (Calendar Days) | Customer Controlled Steps: Step 1 - Intake, Step 3 - Customer Dependencies, & Step 5 - Site Readiness (Customer) (Business Days) | IOU Controlled Steps: Step 2 - Engineering & Design, Step 4 - Utility Dependencies, Step 6 - Site Readiness (IOU), Step 7 - Construction, Step 8 - Service Energization (Calendar Days) | IOU Controlled Steps: Step 2 - Engineering & Design, Step 4 - Utility Dependencies, Step 6 - Site Readiness (IOU), Step 7 - Construction, Step 8 - Service Energization (Business Days) | End to End Cycle Time (1 to 8) (Calendar Days) | End to End Cycle Time (1 to 8) (Business Days) | Energization Steps Completed Concurrently (Energization Step(s) Listed) | Total time for Energization Steps Completed Concurrently (Calendar Days) | Total time for Energization Steps Completed Concurrently (Business Days) | R15/R16/R29/R45 Energization Average meeting/exceeding Average Energization Target (Meeting/Exceeding) | R15/R16/R29/R45 Energization Maximum meeting/exceeding Maximum Energization Target (Meeting/Exceeding) | R15/R16/R29/R45 Energization Reasoning as to why exceeded average/maximum Energization Target (Reasoning) | Location of project exceeding the maximum energization target: Location (circuit level)
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-13 | -623 | -446 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | 2024-09-11 | IOU Designed & Installed | N/A | No | N/A | 17.81 | Unknown | Unknown | Unknown | Unknown | 17.81 | Unknown | 192.95 | 17.81 | 175.14 | Yes | N/A | N/A | 2024-07-29 | 2024-07-30 | 2 | 2 | 2024-07-30 | 2024-08-19 | 21 | 15 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-09-11 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2024-10-28 | 1900-02-16 | 34 | 2024-10-28 | 2024-10-28 | 1 | 1 | 26 | 20 | 70 | 50 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 125 | 125 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | 50 | 37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-23 | 2025-02-12 | IOU Designed & Installed | N/A | No | N/A | 1445.62 | 303.42 | Unknown | Unknown | Unknown | 1142.2 | 3981 | 1879.45 | 1445.62 | 433.83 | Yes | N/A | N/A | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-02-12 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-02-19 | 1900-01-07 | 6 | 2025-02-19 | 2025-02-19 | 1 | 1 | 22 | 16 | 10 | 8 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-12 | -564 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-29 | 2024-05-29 | IOU Designed & Installed | N/A | No | N/A | 596.19 | -6.22 | Unknown | Unknown | Unknown | 602.41 | 3981 | 774.05 | 596.19 | 177.86 | Yes | N/A | N/A | 2024-02-15 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-02-29 | 36 | 26 | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2024-05-29 | 91 | 65 | Unknown | 2024-05-22 | Unknown | Unknown | 2024-05-29 | 2024-06-27 | 1900-01-29 | 22 | 2024-06-27 | 2024-06-27 | 1 | 1 | 91 | 65 | 67 | 49 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-16 | -407 | -291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | 2024-08-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | -387.46 | -14.55 | Unknown | Unknown | -384 | 11.09 | Unknown | 1038.98 | -387.46 | 1426.44 | Yes | N/A | N/A | 2024-08-19 | 2024-09-03 | 16 | 12 | 2024-09-03 | 2024-08-26 | Unknown | Unknown | 2024-08-26 | 2024-12-12 | 109 | 79 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | 2025-04-04 | 2025-04-04 | 1 | 1 | 125 | 91 | 1 | 1 | 126 | 92 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-28 | 632 | 453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-20 | 2023-02-04 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 1101.51 | 263.34 | Unknown | 129.58 | 6.22 | 702.37 | 3981 | 522.8 | 1101.51 | -578.71 | Yes | N/A | N/A | 2023-01-20 | 2023-02-04 | 16 | 11 | 2023-02-04 | Unknown | Unknown | Unknown | 2023-02-01 | 2023-04-18 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-10-28 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-21 | 1900-01-24 | 19 | 2024-11-21 | 2024-11-21 | 1 | 1 | 199 | 142 | 26 | 20 | 225 | 162 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-15 | -184 | -133 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1479.54 | 2769.9 | Unknown | 44.49 | -2555 | 1220.15 | Unknown | 2554.89 | 1479.54 | 1075.35 | Yes | N/A | N/A | 2024-03-25 | 2024-03-25 | 1 | 1 | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | 269 | 192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-10 | 2022-02-24 | 2023-07-23 | IOU Designed & Installed | N/A | No | N/A | -1200.46 | 842.76 | Unknown | 175.92 | -2736 | 516.86 | Unknown | 2736.17 | -1200.46 | 3936.63 | Yes | N/A | N/A | 2022-02-10 | 2023-04-11 | 426 | 304 | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-23 | 2023-12-11 | 1900-05-21 | 101 | 2023-12-11 | 2023-12-11 | 1 | 1 | 426 | 304 | 143 | 102 | 569 | 406 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56 | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-28 | 259 | 186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | 2023-11-26 | IOU Designed & Installed | N/A | No | N/A | 1174.11 | -6.48 | Unknown | Unknown | 29.3 | 1151.29 | 15288 | 1742.36 | 1174.11 | 568.25 | Yes | N/A | N/A | 2023-06-07 | 2023-10-20 | 136 | 98 | 2023-10-20 | 2023-11-03 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2023-11-17 | 17 | 13 | 2023-11-03 | 2024-02-23 | 113 | 81 | Unknown | 2024-03-07 | Unknown | Unknown | 2023-11-26 | 2024-03-14 | 1900-04-19 | 79 | 2024-03-14 | 2024-03-13 | Unknown | Unknown | 249 | 179 | 142 | 103 | 391 | 282 | Steps 2,3,5,6,7 | 116 | 83 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 146.09 | Unknown | Unknown | Unknown | 3.51 | 142.58 | 3981 | 186.52 | 146.09 | 40.43 | Yes | N/A | N/A | 2024-07-25 | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-08-16 | 66 | 48 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-10-10 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-10-24 | 1900-01-14 | 11 | 2024-10-24 | 2024-10-23 | Unknown | Unknown | 56 | 40 | 81 | 59 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-10 | -18 | -15 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-06-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | -882.92 | -26.75 | Unknown | Unknown | -2284 | 1427.83 | Unknown | 1736.36 | -882.92 | 2619.28 | Yes | N/A | N/A | 2024-03-20 | 2024-04-19 | 31 | 23 | 2024-04-19 | 2024-09-11 | 146 | 104 | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-07-12 | 31 | 23 | 2024-09-11 | 2024-10-14 | 34 | 24 | Unknown | 2024-07-24 | Unknown | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | 2024-12-26 | 2024-12-23 | Unknown | Unknown | 65 | 47 | 177 | 127 | 242 | 174 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | -701 | -502 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-07-30 | 2024-07-31 | IOU Designed & Installed | N/A | No | N/A | 1265.58 | -24.52 | Unknown | Unknown | Unknown | 1290.1 | 3981 | 1397.06 | 1265.58 | 131.48 | Yes | N/A | N/A | 2024-07-30 | 2024-07-30 | 1 | 1 | 2024-07-30 | 2024-07-31 | 2 | 2 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-07-31 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-08-07 | 1900-01-07 | 6 | 2024-08-07 | 2024-08-07 | 1 | 1 | 3 | 3 | 11 | 9 | 14 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-09-16 | 972 | 695 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-21 | 2025-05-15 | IOU Designed & Installed | N/A | No | N/A | 3558.72 | 5503.36 | Unknown | 258.64 | -4608 | 2404.72 | Unknown | 4607.6 | 3558.72 | 1048.88 | Yes | N/A | N/A | 2025-04-21 | 2025-04-18 | Unknown | Unknown | 2025-04-18 | 2025-05-12 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-12 | 1 | 1 | 2025-05-15 | 2025-05-15 | 1899-12-31 | 1 | 2025-05-15 | 2025-05-15 | 1 | 1 | 0 | 0 | 28 | 20 | 28 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 135.1 | 135.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-13 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-09-23 | 2025-03-04 | IOU Designed & Installed | N/A | No | N/A | 6979.27 | 2348.78 | Unknown | 296.46 | -2409 | 6743.03 | 3981 | 3042.86 | 6979.27 | -3936.41 | Yes | N/A | N/A | 2024-08-12 | 2024-07-22 | Unknown | Unknown | 2024-07-22 | 2024-09-25 | 66 | 48 | 2024-09-25 | 2024-09-25 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2025-03-04 | 161 | 115 | Unknown | 2025-02-10 | Unknown | Unknown | 2025-03-04 | 2025-03-06 | 1900-01-02 | 3 | 2025-03-06 | 2025-03-06 | 1 | 1 | 162 | 116 | 70 | 52 | 232 | 168 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | 29 | 22 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-11-08 | 2025-04-30 | IOU Designed & Installed | N/A | No | N/A | 61837.86 | 16164.59 | Unknown | 1147.67 | 0.93 | 44524.67 | Unknown | 58908.19 | 61837.86 | -2929.67 | Yes | N/A | N/A | 2024-09-24 | 2024-09-24 | 1 | 1 | 2024-09-24 | 2025-03-10 | 168 | 120 | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2025-03-25 | 57 | 41 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-04-30 | 1899-12-31 | 1 | 2025-04-30 | 2025-04-30 | 1 | 1 | 1 | 1 | 227 | 163 | 228 | 164 | Steps 2,3,5,6,7 | 15 | 11 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VS 1107-G2 MSO (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-01 | 1125 | 804 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-10-04 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | 14112.43 | 7938.85 | Unknown | Unknown | -25696 | 31869.58 | Unknown | Not available | 14112.43 | Unknown | Yes | N/A | N/A | 2024-09-24 | 2024-10-23 | 30 | 22 | 2024-10-23 | 2024-10-24 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2025-03-11 | 139 | 99 | Unknown | 2025-03-25 | Unknown | Unknown | 2025-01-29 | 2025-02-03 | 1900-01-05 | 4 | 2025-02-03 | 2025-01-30 | Unknown | Unknown | 169 | 121 | 8 | 6 | 177 | 127 | Steps 2,3,5,6,7 | 55 | 39 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | POWAY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-26 | -472 | -338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-08 | 2024-03-26 | IOU Designed & Installed | N/A | No | N/A | 290.11 | -11.65 | Unknown | Unknown | Unknown | 301.76 | 3981 | 746.46 | 290.11 | 456.35 | Yes | N/A | N/A | 2024-03-08 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2024-03-08 | 101 | 73 | 2024-03-08 | Unknown | Unknown | Unknown | 2024-03-08 | 2024-03-13 | 6 | 4 | 2024-03-08 | 2024-03-26 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-04-11 | 1900-01-16 | 13 | 2024-04-11 | 2024-04-10 | Unknown | Unknown | 19 | 13 | 124 | 90 | 143 | 103 | Steps 2,3,5,6,7 | 5 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-13 | -137 | -98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-23 | 2024-11-04 | IOU Designed & Installed | N/A | No | N/A | 7469.65 | Unknown | Unknown | Unknown | Unknown | 7469.65 | Unknown | 978.04 | 7469.65 | -6491.61 | Yes | N/A | N/A | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-12-27 | 1900-02-22 | 40 | 2024-12-27 | 2024-12-27 | 1 | 1 | 1 | 1 | 55 | 41 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | -493 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-14 | 2025-03-26 | IOU Designed & Installed | N/A | No | N/A | 1619.88 | Unknown | Unknown | Unknown | Unknown | 1619.88 | 3981 | 1066.55 | 1619.88 | -553.33 | Yes | N/A | N/A | 2024-10-03 | 2024-11-01 | 30 | 22 | 2024-11-01 | 2025-02-24 | 116 | 82 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-05-06 | 1900-02-10 | 30 | 2025-05-06 | 2025-05-06 | 1 | 1 | 30 | 22 | 159 | 113 | 189 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | -487 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-13 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | 745.12 | Unknown | Unknown | Unknown | Unknown | 745.12 | 3981 | 1121.37 | 745.12 | 376.25 | Yes | N/A | N/A | 2024-08-07 | 2024-08-13 | 7 | 5 | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-10-21 | 70 | 50 | Unknown | 2024-10-08 | Unknown | Unknown | 2024-10-21 | 2024-10-28 | 1900-01-07 | 6 | 2024-10-28 | 2024-10-28 | 1 | 1 | 77 | 55 | 10 | 8 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-17 | -161 | -116 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-10-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 302.97 | Unknown | Unknown | Unknown | 10.43 | 292.54 | 0 | 781.31 | 302.97 | 478.34 | Yes | N/A | N/A | 2023-10-18 | 2024-02-16 | 122 | 88 | 2024-02-16 | 2024-02-23 | 8 | 6 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | Unknown | 2025-02-06 | Unknown | Unknown | 2025-02-06 | 2025-02-06 | 1 | 1 | 122 | 88 | 9 | 7 | 131 | 95 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BORREGO SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | -622 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-25 | 2024-04-29 | IOU Designed & Installed | N/A | No | N/A | 2352.59 | 740.04 | Unknown | Unknown | Unknown | 1612.55 | 3981 | 874.27 | 2352.59 | -1478.32 | Yes | N/A | N/A | 2024-03-25 | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2024-03-26 | 54 | 38 | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-04-29 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-05-17 | 1900-01-18 | 15 | 2024-05-17 | 2024-05-17 | 1 | 1 | 1 | 1 | 74 | 54 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | El Cajon | COUNTY OF SAN DIEGO-SOUTH of 56 | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-30 | 71 | 52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 112228.41 | 17813 | Unknown | Unknown | -3246.6 | 97662.01 | 2919 | 29136.49 | 112228.41 | -83091.92 | Yes | N/A | N/A | 2023-11-01 | 2023-11-01 | 1 | 1 | 2023-11-01 | 2024-09-16 | 321 | 229 | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-07-09 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2025-03-11 | 1900-06-10 | 116 | 2025-03-11 | 2025-03-11 | 1 | 1 | 1 | 1 | 514 | 368 | 515 | 369 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | PALA | CALTRANS, CALTRANS-NORTH of 56 | 700 | 700 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-13 | 399 | 286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-14 | 2022-02-23 | 2024-09-05 | IOU Designed & Installed | N/A | No | N/A | 113236.5 | 10942.97 | Unknown | Unknown | -2234.26 | 104527.79 | 0 | 36548.02 | 113236.5 | -76688.48 | Yes | N/A | N/A | 2021-04-14 | 2023-08-10 | 849 | 607 | 2023-08-10 | 2024-06-27 | 323 | 231 | 2023-08-31 | 2024-06-04 | 1 | 1 | 2023-04-25 | 2024-07-18 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-10-16 | 1900-02-10 | 30 | 2024-10-16 | 2024-10-16 | 1 | 1 | 850 | 608 | 384 | 276 | 1234 | 884 | Steps 2,3,5,6,7 | 707 | 505 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 140082.8 | 140082.8 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-05-31 | 54 | 39 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2024-03-01 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | 3281.2 | Unknown | Unknown | Unknown | 41.24 | 3239.96 | 3981 | 696.62 | 3281.2 | -2584.58 | Yes | N/A | N/A | 2023-05-30 | 2024-01-09 | 225 | 161 | 2024-01-09 | 2024-03-28 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-06-14 | 79 | 57 | Unknown | 2024-06-12 | Unknown | Unknown | 2024-06-17 | 2024-09-21 | 1900-04-06 | 70 | 2024-09-21 | 2024-07-24 | Unknown | Unknown | 304 | 218 | 177 | 128 | 481 | 346 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 1 | 1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-29 | -674 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-20 | 2025-05-27 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 435.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-20 | 2025-05-06 | Unknown | Unknown | 2025-05-06 | 2025-05-20 | 15 | 11 | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-05-27 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | 2025-06-24 | 1900-01-28 | 21 | 2025-06-24 | 2025-06-24 | 1 | 1 | 7 | 5 | 45 | 33 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | Escondido | ESCONDIDO | 290.15 | 290.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-28 | 145 | 104 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | 2024-02-05 | IOU Designed & Installed | N/A | No | N/A | 22404.94 | 4151.29 | Unknown | 1317.62 | 167.3 | 16768.73 | 16443.39 | 1822.17 | 22404.94 | -20582.77 | Yes | N/A | N/A | 2023-08-08 | 2023-02-27 | Unknown | Unknown | 2023-02-27 | 2023-08-28 | 183 | 131 | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | 2023-09-12 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-02-20 | 1900-01-15 | 12 | 2024-02-20 | 2024-02-20 | 1 | 1 | 0 | 0 | 220 | 158 | 220 | 158 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -673 | -482 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-13 | 2024-06-18 | IOU Designed & Installed | N/A | No | N/A | 820.68 | -17.63 | Unknown | Unknown | Unknown | 838.31 | Unknown | 1016.73 | 820.68 | 196.05 | Yes | N/A | N/A | 2024-06-13 | 2024-05-03 | Unknown | Unknown | 2024-05-03 | 2024-06-13 | 42 | 30 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-06-18 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-06-27 | 1900-01-09 | 8 | 2024-06-27 | 2024-06-27 | 1 | 1 | 6 | 4 | 53 | 39 | 59 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 9 | 7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-17 | 2023-05-08 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | 2349.84 | Unknown | Unknown | Unknown | Unknown | 2349.84 | Unknown | 2159.06 | 2349.84 | -190.78 | Yes | N/A | N/A | 2022-11-17 | 2023-08-22 | 279 | 199 | 2023-08-22 | 2023-09-08 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2023-10-24 | 1900-01-13 | 10 | 2023-10-24 | 2023-10-24 | 1 | 1 | 279 | 199 | 33 | 25 | 312 | 224 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 54.05 | 54.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | -106 | -77 | No | 2023-10-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2024-02-05 | 2024-04-25 | IOU Designed & Installed | N/A | Yes | 152 | 5.26 | -4.67 | Unknown | Unknown | Unknown | 9.93 | 3981 | 860.31 | 5.26 | 855.05 | Yes | N/A | N/A | 2023-10-25 | 2024-03-25 | 153 | 109 | 2024-03-25 | 2023-11-15 | Unknown | Unknown | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-04-25 | 81 | 59 | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-04-29 | 1900-01-04 | 3 | 2024-04-29 | 2024-05-01 | 3 | 3 | 234 | 168 | 8 | 6 | 242 | 174 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-27 | -682 | -488 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-01 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 582.25 | -11.7 | Unknown | Unknown | Unknown | 593.95 | 3981 | 1652.23 | 582.25 | 1069.98 | Yes | N/A | N/A | 2025-04-01 | 2025-03-30 | Unknown | Unknown | 2025-03-30 | 2025-04-01 | 3 | 2 | 2025-04-01 | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-23 | 23 | 17 | 2025-04-01 | 2025-05-12 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-14 | 1900-01-02 | 3 | 2025-05-14 | 2025-05-14 | 1 | 1 | 42 | 30 | 30 | 23 | 72 | 53 | Steps 2,3,5,6,7 | 22 | 16 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-02-21 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1766.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-16 | 2025-02-17 | 33 | 23 | 2025-02-17 | 2025-02-21 | 5 | 5 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-03-03 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-05-08 | 1900-03-07 | 49 | 2025-05-08 | 2025-05-08 | 1 | 1 | 44 | 30 | 73 | 55 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-21 | -555 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | 2024-01-18 | IOU Designed & Installed | N/A | No | N/A | 336.63 | -13.96 | Unknown | Unknown | Unknown | 350.59 | Unknown | 913.7 | 336.63 | 577.07 | Yes | N/A | N/A | 2023-12-20 | 2024-01-04 | 16 | 12 | 2024-01-04 | 2024-01-05 | 2 | 2 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-18 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-03-15 | 1900-02-26 | 42 | 2024-03-15 | 2024-03-15 | 1 | 1 | 31 | 23 | 61 | 45 | 92 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-30 | -682 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-16 | 2025-05-22 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | 112.67 | -0.31 | Unknown | Unknown | Unknown | 112.98 | Unknown | 1283.33 | 112.67 | 1170.66 | Yes | N/A | N/A | 2025-05-16 | 2025-05-21 | 6 | 4 | 2025-05-21 | 2025-05-29 | 9 | 7 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-09 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-17 | 1900-01-08 | 7 | 2025-06-17 | 2025-06-17 | 1 | 1 | 18 | 12 | 19 | 15 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Agricultural | N/A | VALLEY CENTER | COUNTY OF SAN DIEGO-NORTH of 56 | 150 | 150 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 213 | 152 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-16 | 2024-09-12 | IOU Designed & Installed | N/A | No | N/A | 35493.34 | 6817.28 | Unknown | Unknown | -10515.51 | 39191.57 | 63501.05 | 56004.72 | 35493.34 | 20511.38 | Yes | N/A | N/A | 2024-01-02 | 2024-01-05 | 4 | 4 | 2024-01-05 | 2024-09-04 | 244 | 174 | 2024-06-21 | 2024-08-02 | 43 | 31 | 2024-04-19 | 2024-09-03 | 31 | 21 | 2024-09-04 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | 2024-11-04 | 1900-02-22 | 38 | 2024-11-04 | 2024-09-30 | Unknown | Unknown | 47 | 35 | 329 | 233 | 376 | 268 | Steps 2,3,5,6,7 | 180 | 128 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 142 | 142 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -155 | -112 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | 2023-06-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 46.96 | Unknown | Unknown | Unknown | Unknown | 46.96 | 3981 | 899.68 | 46.96 | 852.72 | Yes | N/A | N/A | 2023-05-26 | 2023-06-09 | 15 | 11 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | 2024-08-28 | 2024-08-28 | 1 | 1 | 15 | 11 | 1 | 1 | 16 | 12 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-30 | 436 | 311 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-06-09 | 2023-07-07 | IOU Designed & Installed | N/A | No | N/A | 985.7 | 347.91 | Unknown | Unknown | Unknown | 637.79 | 3981 | 597.19 | 985.7 | -388.51 | Yes | N/A | N/A | 2023-06-09 | 2023-06-09 | 1 | 1 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2023-07-07 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | 2023-07-10 | 1900-01-03 | 2 | 2023-07-10 | 2023-07-10 | 1 | 1 | 30 | 22 | 5 | 3 | 35 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 47.34 | 47.34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -609 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-07-30 | 2024-10-25 | IOU Designed & Installed | N/A | No | N/A | 1470.06 | Unknown | Unknown | Unknown | Unknown | 1470.06 | Unknown | 449.58 | 1470.06 | -1020.48 | Yes | N/A | N/A | 2024-07-30 | 2024-08-06 | 8 | 6 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-10-25 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2024-10-30 | 1900-01-05 | 4 | 2024-10-30 | 2024-10-30 | 1 | 1 | 87 | 63 | 7 | 5 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-30 | -494 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2025-03-20 | 2025-04-10 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1910.82 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-09-27 | Unknown | Unknown | 2024-09-27 | 2025-03-20 | 175 | 125 | 2025-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-04-10 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-04-23 | 1900-01-13 | 10 | 2025-04-23 | 2025-04-23 | 1 | 1 | 22 | 16 | 190 | 136 | 212 | 152 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 133.05 | 133.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-01 | 462 | 331 | No | 2023-03-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | 2024-09-19 | IOU Designed & Installed | N/A | Yes | 557 | 3029.93 | 44.96 | Unknown | Unknown | 236.29 | 2748.68 | 3981 | 515.35 | 3029.93 | -2514.58 | Yes | N/A | N/A | 2023-03-31 | 2024-10-08 | 558 | 398 | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | 2024-09-19 | 539 | 385 | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-10-31 | 1900-02-11 | 31 | 2024-10-31 | 2024-11-05 | 6 | 4 | 1097 | 783 | 50 | 36 | 1147 | 819 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | -541 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-14 | 2025-03-14 | IOU Designed & Installed | N/A | No | N/A | 1655.48 | 303.12 | Unknown | 425.45 | Unknown | 926.91 | Unknown | 1361.38 | 1655.48 | -294.1 | Yes | N/A | N/A | 2025-03-13 | 2025-02-28 | Unknown | Unknown | 2025-02-28 | 2025-03-13 | 14 | 10 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-03-14 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-03-26 | 1900-01-12 | 9 | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 | 1 | 28 | 20 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | -615 | -440 | No | 2025-01-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-10 | 2025-04-18 | IOU Designed & Installed | N/A | Yes | 62 | 1008.26 | Unknown | Unknown | Unknown | Unknown | 1008.26 | 3981 | 1199.58 | 1008.26 | 191.32 | Yes | N/A | N/A | 2025-01-10 | 2025-03-12 | 62 | 44 | 2025-03-12 | 2025-03-14 | 3 | 3 | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-04-18 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-04-25 | 1900-01-07 | 6 | 2025-04-25 | 2025-04-25 | 1 | 1 | 161 | 115 | 12 | 10 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 19.5 | 19.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -422 | -303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 600.83 | -12.07 | Unknown | Unknown | Unknown | 612.9 | 3981 | 1274.08 | 600.83 | 673.25 | Yes | N/A | N/A | 2024-08-07 | 2024-08-13 | 7 | 5 | 2024-08-13 | 2024-08-19 | 7 | 5 | 2024-08-19 | Unknown | Unknown | Unknown | 2024-08-19 | 2024-08-27 | 9 | 7 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | 2025-05-05 | 2025-05-05 | 1 | 1 | 7 | 5 | 17 | 13 | 24 | 18 | Steps 2,3,5,6,7 | 8 | 6 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 327 | 327 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-15 | -400 | -287 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-02-23 | 2024-12-08 | IOU Designed & Installed | N/A | No | N/A | 9022.25 | 873.78 | Unknown | 4.21 | 53.7 | 8090.56 | 3981 | 912.82 | 9022.25 | -8109.43 | Yes | N/A | N/A | 2024-02-23 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-02-27 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-09-04 | 191 | 137 | Unknown | 2024-11-13 | Unknown | Unknown | 2024-12-08 | 2024-12-11 | 1900-01-03 | 3 | 2024-12-11 | 2024-12-11 | 1 | 1 | 191 | 137 | 11 | 8 | 202 | 145 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-27 | -540 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 475.46 | Unknown | Unknown | Unknown | 8.13 | 467.33 | 3981 | 1449.63 | 475.46 | 974.17 | Yes | N/A | N/A | 2024-11-19 | 2024-12-11 | 23 | 17 | 2024-12-11 | 2024-12-11 | 1 | 1 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2025-02-25 | 77 | 55 | Unknown | 2025-02-11 | Unknown | Unknown | 2025-02-25 | 2025-03-06 | 1900-01-09 | 8 | 2025-03-06 | 2025-03-05 | Unknown | Unknown | 100 | 72 | 11 | 9 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-09 | -344 | -247 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | 2372.03 | 386.31 | Unknown | 103.92 | Unknown | 1881.8 | Unknown | 1049.54 | 2372.03 | -1322.49 | Yes | N/A | N/A | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-17 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-09-30 | 1900-01-13 | 10 | 2024-09-30 | 2024-09-30 | 1 | 1 | 9 | 7 | 16 | 12 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | 237 | 170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-10-15 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | -182.4 | Unknown | Unknown | Unknown | -197 | 14.6 | Unknown | 196.69 | -182.4 | 379.09 | Yes | N/A | N/A | 2024-07-08 | 2024-10-16 | 101 | 73 | 2024-10-16 | 2025-03-21 | 157 | 113 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-04-18 | 29 | 21 | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-31 | 2025-04-09 | 1900-01-09 | 8 | 2025-04-09 | 2025-04-09 | 1 | 1 | 130 | 94 | 168 | 122 | 298 | 216 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-05 | -603 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 34.63 | Unknown | Unknown | Unknown | Unknown | 34.63 | Unknown | 1693.87 | 34.63 | 1659.24 | Yes | N/A | N/A | 2024-12-09 | 2024-12-23 | 15 | 11 | 2024-12-23 | 2025-01-02 | 11 | 9 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | 2025-03-12 | 2025-03-12 | 1 | 1 | 15 | 11 | 12 | 10 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 137 | 137 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-24 | 78 | 57 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-12-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 801.75 | -17.38 | Unknown | Unknown | Unknown | 819.13 | 3981 | 5036.78 | 801.75 | 4235.03 | Yes | N/A | N/A | 2023-05-22 | 2024-01-02 | 226 | 162 | 2024-01-02 | 2024-06-06 | 157 | 113 | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-02-15 | 15 | 11 | 2024-06-06 | 2024-06-12 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-07-11 | 1 | 1 | 233 | 167 | 173 | 125 | 406 | 292 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-15 | -667 | -478 | No | 2024-10-29 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | 2024-11-06 | IOU Designed & Installed | N/A | Yes | 8 | 102.39 | -1.5 | Unknown | Unknown | Unknown | 103.89 | Unknown | 1142.97 | 102.39 | 1040.58 | Yes | N/A | N/A | 2024-10-29 | 2024-11-06 | 9 | 7 | 2024-11-06 | 2024-10-23 | Unknown | Unknown | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2024-11-06 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-12-17 | 1900-02-10 | 30 | 2024-12-17 | 2024-12-17 | 1 | 1 | 11 | 9 | 43 | 31 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 8.05 | 8.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2029-01-10 | -2116 | -1513 | No | 2022-10-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-17 | 2022-08-17 | Unknown | IOU Designed & Installed | N/A | Yes | 119 | 888.57 | -8.07 | Unknown | Unknown | Unknown | 896.64 | 3241 | 1207.69 | 888.57 | 319.12 | Yes | N/A | N/A | 2022-08-17 | 2023-02-01 | 169 | 121 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | Unknown | Unknown | 2023-07-20 | 2023-03-27 | Unknown | Unknown | 169 | 121 | 0 | 0 | 169 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | -72 | -53 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-20 | 2024-01-04 | IOU Designed & Installed | N/A | No | N/A | 7.42 | -9.38 | Unknown | Unknown | Unknown | 16.8 | 7962 | 1036.44 | 7.42 | 1029.02 | Yes | N/A | N/A | 2023-09-20 | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-09-20 | 23 | 17 | 2023-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | 2024-01-04 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-19 | 1900-01-15 | 12 | 2024-01-19 | 2024-03-27 | 69 | 49 | 107 | 77 | 108 | 78 | 215 | 155 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-25 | -149 | -108 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2023-11-15 | IOU Designed & Installed | N/A | No | N/A | 1554.96 | 302.11 | Unknown | Unknown | 1.87 | 1250.98 | 3981 | 673.65 | 1554.96 | -881.31 | Yes | N/A | N/A | 2023-09-14 | 2023-05-03 | Unknown | Unknown | 2023-05-03 | 2023-09-26 | 147 | 105 | 2023-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-26 | 2023-11-15 | 51 | 37 | Unknown | 2023-11-06 | Unknown | Unknown | 2023-11-15 | 2023-11-28 | 1900-01-13 | 10 | 2023-11-28 | 2023-11-28 | 1 | 1 | 51 | 37 | 162 | 116 | 213 | 153 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-16 | -441 | -316 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | 2024-11-06 | IOU Designed & Installed | N/A | No | N/A | 2371.85 | 319.14 | Unknown | Unknown | Unknown | 2052.71 | 3941 | 190.44 | 2371.85 | -2181.41 | Yes | N/A | N/A | 2024-04-18 | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-09-20 | 208 | 150 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-11-06 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-12-02 | 1900-01-26 | 19 | 2024-12-02 | 2024-12-02 | 1 | 1 | 48 | 34 | 236 | 170 | 284 | 204 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12.05 | 12.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-02 | -609 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | 2024-07-24 | IOU Designed & Installed | N/A | No | N/A | 948.32 | Unknown | Unknown | Unknown | 11.69 | 936.63 | 3961 | 1422.94 | 948.32 | 474.62 | Yes | N/A | N/A | 2024-05-09 | 2024-04-12 | Unknown | Unknown | 2024-04-12 | 2024-06-17 | 67 | 47 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-07-24 | 41 | 29 | Unknown | 2024-07-22 | Unknown | Unknown | 2024-07-24 | 2024-08-02 | 1900-01-09 | 8 | 2024-08-02 | 2024-08-01 | Unknown | Unknown | 41 | 29 | 77 | 55 | 118 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | VISTA | NCTD-Trolly North of 56, VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-02 | 294 | 211 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-07-26 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 618538.74 | 36838.46 | Unknown | 177.06 | 3579.74 | 577943.48 | 0 | 232827.77 | 618538.74 | -385710.97 | Yes | N/A | N/A | 2024-02-14 | 2024-07-23 | 161 | 115 | 2024-07-23 | 2025-02-07 | 200 | 144 | 2024-09-16 | 2025-01-10 | 2 | 2 | 2024-08-29 | 2025-04-01 | 109 | 75 | 2025-02-07 | 2025-02-04 | Unknown | Unknown | 2025-04-18 | 2025-05-22 | 35 | 25 | 2025-03-05 | 2025-06-23 | 1900-04-20 | 79 | 2025-06-23 | 2025-06-23 | 1 | 1 | 163 | 117 | 456 | 324 | 619 | 441 | Steps 2,3,5,6,7 | 409 | 293 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-19 | -366 | -261 | No | 2024-08-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | 2025-04-15 | IOU Designed & Installed | N/A | Yes | 195 | -832.73 | 210.3 | Unknown | Unknown | -1617 | 573.97 | Unknown | 1501.47 | -832.73 | 2334.2 | Yes | N/A | N/A | 2024-08-07 | 2025-02-18 | 196 | 140 | 2025-02-18 | 2024-08-07 | Unknown | Unknown | 2024-08-07 | 2025-03-06 | 212 | 152 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-04-15 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-04-19 | 1900-01-04 | 4 | 2025-04-19 | 2025-04-18 | Unknown | Unknown | 449 | 321 | 5 | 4 | 454 | 325 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-05 | 101 | 72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-04-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1038.47 | 1629.98 | Unknown | 186.53 | -3559 | 704.02 | 0 | 3559.1 | -1038.47 | 4597.57 | Yes | N/A | N/A | 2023-04-26 | 2023-04-26 | 1 | 1 | 2023-04-26 | 2023-07-12 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 79 | 57 | 80 | 58 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 94.25 | 94.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-18 | -461 | -330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-19 | 2024-07-31 | IOU Designed & Installed | N/A | No | N/A | 4982.67 | 1864.96 | Unknown | 66.68 | 179.75 | 2871.28 | Unknown | 2841.57 | 4982.67 | -2141.1 | Yes | N/A | N/A | 2024-07-19 | 2024-07-15 | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-07-31 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2025-03-14 | 1900-08-14 | 163 | 2025-03-14 | 2025-03-14 | 1 | 1 | 13 | 9 | 228 | 164 | 241 | 173 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-28 | -18 | -14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-03 | 2023-04-20 | IOU Designed & Installed | N/A | No | N/A | 1119.03 | 344.78 | Unknown | 148.52 | 40.27 | 585.46 | 3981 | 722.58 | 1119.03 | -396.45 | Yes | N/A | N/A | 2023-02-28 | 2023-03-03 | 4 | 4 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | 2023-04-20 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | 2024-12-10 | 1901-08-23 | 429 | 2024-12-10 | 2024-12-10 | 1 | 1 | 53 | 39 | 602 | 430 | 655 | 469 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | -247 | -178 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-19 | 2024-05-13 | IOU Designed & Installed | N/A | No | N/A | -162.01 | 1374.12 | Unknown | 43.17 | -2441 | 861.7 | Unknown | 2420.65 | -162.01 | 2582.66 | Yes | N/A | N/A | 2024-03-19 | 2024-04-11 | 24 | 18 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-05-15 | 1900-01-02 | 3 | 2024-05-15 | 2024-05-15 | 1 | 1 | 24 | 18 | 4 | 4 | 28 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-25 | -520 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | 8.73 | Unknown | Unknown | Unknown | 1.08 | 7.65 | 3981 | 1956.25 | 8.73 | 1947.52 | Yes | N/A | N/A | 2024-12-09 | 2024-12-09 | 1 | 1 | 2024-12-09 | 2024-12-12 | 4 | 4 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-03-03 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-06-23 | 1900-04-22 | 81 | 2025-06-23 | 2025-06-23 | 1 | 1 | 83 | 59 | 118 | 86 | 201 | 145 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 375.5 | 375.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-29 | -9 | -8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-10 | 2023-04-13 | IOU Designed & Installed | N/A | No | N/A | 4777.03 | -22.29 | Unknown | Unknown | Unknown | 4799.32 | Unknown | 4118.64 | 4777.03 | -658.39 | Yes | N/A | N/A | 2023-02-08 | 2023-02-10 | 3 | 3 | 2023-02-10 | 2023-03-07 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | 2023-06-20 | 1900-03-09 | 49 | 2023-06-20 | 2023-06-20 | 1 | 1 | 3 | 3 | 96 | 68 | 99 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | -367 | -264 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | 2025-02-04 | IOU Designed & Installed | N/A | No | N/A | -1871.95 | Unknown | Unknown | Unknown | -1923 | 51.05 | Unknown | 1922.9 | -1871.95 | 3794.85 | Yes | N/A | N/A | 2024-08-07 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-10-17 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-08-29 | 10 | 8 | 2024-10-17 | 2025-01-27 | 103 | 73 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-02-25 | 1900-01-21 | 16 | 2025-02-25 | 2025-02-24 | Unknown | Unknown | 103 | 73 | 125 | 91 | 228 | 164 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | Dulzura | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-19 | 476 | 341 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | 2025-04-08 | IOU Designed & Installed | N/A | No | N/A | 16486.25 | 5518.78 | Unknown | 803.53 | -4736 | 14899.94 | 2469 | 12988.66 | 16486.25 | -3497.59 | Yes | N/A | N/A | 2022-12-07 | 2025-02-28 | 815 | 583 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | 2023-08-01 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-08 | 1899-12-31 | 1 | 2025-04-08 | 2025-04-08 | 1 | 1 | 815 | 583 | 16 | 12 | 831 | 595 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 29 | 29 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | -367 | -264 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 15.03 | Unknown | Unknown | Unknown | Unknown | 15.03 | 3981 | 769.25 | 15.03 | 754.22 | Yes | N/A | N/A | 2023-12-04 | 2023-12-07 | 4 | 4 | 2023-12-07 | 2023-12-07 | 1 | 1 | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | 2024-07-30 | 2024-07-30 | 1 | 1 | 4 | 4 | 2 | 2 | 6 | 6 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-04 | -375 | -268 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-04 | 2023-11-04 | 2024-02-07 | IOU Designed & Installed | N/A | No | N/A | 350.63 | -20 | Unknown | Unknown | Unknown | 370.63 | 3981 | 1002.6 | 350.63 | 651.97 | Yes | N/A | N/A | 2023-11-04 | 2023-11-04 | 1 | 0 | 2023-11-04 | 2023-11-04 | 1 | 0 | 2023-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-04 | 2024-02-07 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-03-14 | 1900-02-05 | 27 | 2024-03-14 | 2024-02-23 | Unknown | Unknown | 97 | 68 | 38 | 27 | 135 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-03 | -689 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-10-24 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 49.1 | -0.94 | Unknown | Unknown | Unknown | 50.04 | 3981 | 1532.76 | 49.1 | 1483.66 | Yes | N/A | N/A | 2024-10-24 | 2024-10-24 | 1 | 1 | 2024-10-24 | 2024-10-24 | 1 | 1 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-10-29 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-11-13 | 1900-01-15 | 12 | 2024-11-13 | 2024-11-13 | 1 | 1 | 7 | 5 | 18 | 14 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-26 | -271 | -195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 837.84 | Unknown | Unknown | Unknown | Unknown | 837.84 | 3981 | 769.32 | 837.84 | -68.52 | Yes | N/A | N/A | 2023-11-14 | 2023-08-04 | Unknown | Unknown | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | 2024-10-28 | Unknown | Unknown | 2024-10-28 | 2024-10-28 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-20 | -336 | -241 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-13 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 577.46 | -11.6 | Unknown | Unknown | Unknown | 589.06 | 3981 | 5394.34 | 577.46 | 4816.88 | Yes | N/A | N/A | 2024-12-13 | 2024-12-13 | 1 | 1 | 2024-12-13 | 2024-12-13 | 1 | 1 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2025-03-06 | 81 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-03-24 | 1900-01-18 | 13 | 2025-03-24 | 2025-03-21 | Unknown | Unknown | 82 | 60 | 20 | 14 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-07 | -291 | -209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-10-03 | 2023-10-31 | IOU Designed & Installed | N/A | No | N/A | -364.49 | 2396.1 | Unknown | 532.02 | -4329 | 1036.39 | Unknown | 4328.7 | -364.49 | 4693.19 | Yes | N/A | N/A | 2023-10-02 | 2023-09-29 | Unknown | Unknown | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2023-11-21 | 1900-01-21 | 16 | 2023-11-21 | 2023-11-21 | 1 | 1 | 0 | 0 | 23 | 17 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | -648 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 2025-06-16 | IOU Designed & Installed | N/A | No | N/A | 973.25 | Unknown | Unknown | Unknown | 6.09 | 967.16 | 3981 | 1216.19 | 973.25 | 242.94 | Yes | N/A | N/A | 2025-04-07 | 2025-04-01 | Unknown | Unknown | 2025-04-01 | 2025-04-17 | 17 | 13 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-06-16 | 61 | 43 | Unknown | 2025-05-30 | Unknown | Unknown | 2025-06-16 | 2025-06-16 | 1899-12-31 | 1 | 2025-06-16 | 2025-06-16 | 1 | 1 | 61 | 43 | 19 | 15 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 22.15 | 22.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-17 | -617 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2024-01-23 | 2024-01-30 | IOU Designed & Installed | N/A | No | N/A | 330.62 | -16.42 | Unknown | Unknown | Unknown | 347.04 | 3981 | 924.49 | 330.62 | 593.87 | Yes | N/A | N/A | 2023-12-15 | 2023-10-30 | Unknown | Unknown | 2023-10-30 | 2024-01-23 | 86 | 62 | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-01-30 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-02-08 | 1900-01-09 | 8 | 2024-02-08 | 2024-02-08 | 1 | 1 | 8 | 6 | 97 | 71 | 105 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-02 | -147 | -106 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-06-19 | 2024-10-30 | IOU Designed & Installed | N/A | No | N/A | 9417.76 | Unknown | Unknown | Unknown | 34.51 | 9383.25 | 19142 | 3475.95 | 9417.76 | -5941.81 | Yes | N/A | N/A | 2024-05-23 | 2024-06-19 | 28 | 20 | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | Unknown | Unknown | 2024-10-30 | 2024-12-06 | 1900-02-06 | 28 | 2024-12-06 | 2024-12-06 | 1 | 1 | 28 | 20 | 39 | 29 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 31.6 | Unknown | Unknown | Unknown | Unknown | 31.6 | 3981 | 1451.84 | 31.6 | 1420.24 | Yes | N/A | N/A | 2024-10-14 | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2024-10-14 | 6 | 4 | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2024-10-18 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-11-20 | 1900-02-02 | 24 | 2024-11-20 | 2024-11-20 | 1 | 1 | 5 | 5 | 41 | 29 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-21 | -236 | -170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-01 | 2024-04-25 | IOU Designed & Installed | N/A | No | N/A | 6135.22 | Unknown | Unknown | Unknown | -815 | 6950.22 | Unknown | 815.06 | 6135.22 | -5320.16 | Yes | N/A | N/A | 2024-02-01 | 2024-02-02 | 2 | 2 | 2024-02-02 | 2024-04-22 | 81 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-04-29 | 1900-01-04 | 3 | 2024-04-29 | 2024-04-29 | 1 | 1 | 2 | 2 | 87 | 61 | 89 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | -527 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-22 | 2023-09-18 | 2023-10-17 | IOU Designed & Installed | N/A | No | N/A | 0.17 | -4.67 | Unknown | Unknown | Unknown | 4.84 | 3981 | 844.72 | 0.17 | 844.55 | Yes | N/A | N/A | 2023-07-22 | 2023-09-18 | 59 | 41 | 2023-09-18 | 2023-09-18 | 1 | 1 | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | 2023-10-17 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2023-10-31 | 1900-01-14 | 11 | 2023-10-31 | 2023-10-31 | 1 | 1 | 89 | 63 | 17 | 13 | 106 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-28 | -95 | -69 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-05-03 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 11572.14 | 274.88 | Unknown | Unknown | 51.48 | 11245.78 | 367321 | 18029.64 | 11572.14 | 6457.5 | Yes | N/A | N/A | 2023-04-12 | 2023-06-05 | 55 | 39 | 2023-06-05 | 2023-10-11 | 129 | 93 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2024-07-29 | 293 | 209 | Unknown | 2024-07-16 | Unknown | Unknown | 2024-08-22 | 2024-09-24 | 1900-02-02 | 24 | 2024-09-24 | 2024-09-24 | 1 | 1 | 348 | 248 | 164 | 118 | 512 | 366 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-14 | -402 | -288 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | 2024-05-07 | IOU Designed & Installed | N/A | No | N/A | 1080.02 | 181.8 | Unknown | Unknown | 28.05 | 870.17 | 7962 | 1644.17 | 1080.02 | 564.15 | Yes | N/A | N/A | 2023-10-17 | 2023-08-08 | Unknown | Unknown | 2023-08-08 | 2023-12-11 | 126 | 90 | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2024-05-07 | 149 | 107 | Unknown | 2025-03-17 | Unknown | Unknown | 2024-05-07 | 2024-05-08 | 1900-01-01 | 2 | 2024-05-08 | 2024-05-08 | 1 | 1 | 149 | 107 | 129 | 93 | 278 | 200 | Steps 2,3,5,6,7 | 314 | 224 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 120.1 | 120.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-26 | 508 | 364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-20 | 2022-04-20 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | 14.1 | -11.64 | Unknown | Unknown | Unknown | 25.74 | 3241 | 982.38 | 14.1 | 968.28 | Yes | N/A | N/A | 2022-04-20 | 2024-06-28 | 801 | 573 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-04-20 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-07-18 | 1900-04-02 | 67 | 2024-07-18 | 2024-07-18 | 1 | 1 | 801 | 573 | 94 | 68 | 895 | 641 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | -692 | -495 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1203.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | Unknown | Unknown | 2025-05-09 | 2025-05-09 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-27 | 18 | 13 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 122.23 | 1942.88 | Unknown | 678.04 | -3371 | 872.31 | 0 | 3370.8 | 122.23 | 3248.57 | Yes | N/A | N/A | 2023-09-06 | 2023-08-25 | Unknown | Unknown | 2023-08-25 | 2023-09-19 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 27 | 19 | 27 | 19 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-08 | -631 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-07-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | -8.79 | -6.36 | Unknown | Unknown | Unknown | -2.43 | Unknown | 372.29 | -8.79 | 381.08 | Yes | N/A | N/A | 2023-07-26 | 2023-07-26 | 1 | 1 | 2023-07-26 | 2023-07-26 | 1 | 1 | 2023-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2023-08-16 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 98 | 98 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | -689 | -494 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2247.24 | Unknown | Unknown | Unknown | Unknown | 2247.24 | Unknown | 1052.38 | 2247.24 | -1194.86 | Yes | N/A | N/A | 2025-04-11 | 2025-04-28 | 18 | 12 | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | 2025-05-12 | 2025-05-12 | 1 | 1 | 18 | 12 | 1 | 1 | 19 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-14 | -459 | -328 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-03-08 | 2024-07-03 | IOU Designed & Installed | N/A | No | N/A | 15.28 | -11.78 | Unknown | Unknown | Unknown | 27.06 | Unknown | 865.17 | 15.28 | 849.89 | Yes | N/A | N/A | 2024-02-15 | 2024-02-28 | 14 | 10 | 2024-02-28 | 2024-03-08 | 10 | 8 | 2024-03-08 | 2024-06-10 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-07-03 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-07-15 | 1900-01-12 | 9 | 2024-07-15 | 2024-07-12 | Unknown | Unknown | 227 | 161 | 23 | 17 | 250 | 178 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-13 | 2 | 1 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-08-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4191.82 | 3273 | Unknown | 752.42 | -1186 | 1352.4 | Unknown | 1185.85 | 4191.82 | -3005.97 | Yes | N/A | N/A | 2023-08-10 | 2023-09-07 | 29 | 21 | 2023-09-07 | 2023-09-13 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 29 | 21 | 8 | 6 | 37 | 27 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -369 | -264 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-06-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 42.92 | Unknown | Unknown | Unknown | Unknown | 42.92 | Unknown | 1528.78 | 42.92 | 1485.86 | Yes | N/A | N/A | 2024-05-30 | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-06-28 | 66 | 48 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | 2025-02-26 | 2025-02-25 | Unknown | Unknown | 0 | 0 | 66 | 48 | 66 | 48 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-22 | -621 | -444 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-30 | 2024-11-30 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 64.46 | Unknown | Unknown | Unknown | Unknown | 64.46 | 3981 | 1534.24 | 64.46 | 1469.78 | Yes | N/A | N/A | 2024-11-30 | 2024-11-26 | Unknown | Unknown | 2024-11-26 | 2024-11-30 | 5 | 4 | 2024-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-30 | 2025-02-20 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-03-11 | 1900-01-19 | 14 | 2025-03-11 | 2025-03-11 | 1 | 1 | 83 | 59 | 26 | 19 | 109 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | -506 | -361 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 8771.17 | 880.82 | Unknown | 188.53 | 80.91 | 7620.91 | 3981 | 1262.92 | 8771.17 | -7508.25 | Yes | N/A | N/A | 2024-09-03 | 2024-10-15 | 43 | 31 | 2024-10-15 | 2024-10-15 | 1 | 1 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2025-02-25 | 134 | 96 | Unknown | 2025-01-17 | Unknown | Unknown | 2025-02-25 | 2025-02-28 | 1900-01-03 | 4 | 2025-02-28 | 2025-02-28 | 1 | 1 | 177 | 127 | 6 | 6 | 183 | 133 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 319.05 | 319.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-20 | 178 | 127 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-12-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3291.14 | -27.47 | Unknown | Unknown | 5.27 | 3313.34 | 3981 | 1192.16 | 3291.14 | -2098.98 | Yes | N/A | N/A | 2023-08-09 | 2024-01-03 | 148 | 106 | 2024-01-03 | 2024-04-30 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2024-12-19 | 234 | 168 | Unknown | 2024-12-03 | Unknown | Unknown | Unknown | 2024-12-23 | Unknown | Unknown | 2024-12-23 | 2025-01-14 | 23 | 17 | 382 | 274 | 142 | 102 | 524 | 376 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68.1 | 68.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-06 | 513 | 368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2025-01-15 | 2025-01-23 | IOU Designed & Installed | N/A | No | N/A | 26.5 | Unknown | Unknown | Unknown | Unknown | 26.5 | 3981 | 1191.75 | 26.5 | 1165.25 | Yes | N/A | N/A | 2023-10-30 | 2025-01-08 | 437 | 313 | 2025-01-08 | 2025-01-15 | 8 | 6 | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-01-23 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-02-03 | 1900-01-11 | 8 | 2025-02-03 | 2025-01-31 | Unknown | Unknown | 446 | 320 | 20 | 14 | 466 | 334 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 22 | 22 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | -609 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-08-05 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 2604.9 | 788.46 | Unknown | Unknown | Unknown | 1816.44 | 3981 | 1482.36 | 2604.9 | -1122.54 | Yes | N/A | N/A | 2024-07-24 | 2024-06-05 | Unknown | Unknown | 2024-06-05 | 2024-08-08 | 65 | 47 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-09-25 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-09-27 | 1900-01-02 | 3 | 2024-09-27 | 2024-09-27 | 1 | 1 | 49 | 35 | 69 | 51 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | -562 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-20 | 2022-05-20 | 2025-05-20 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 334432.17 | 46636.41 | Unknown | Unknown | -1027.91 | 288823.67 | 124630.27 | 155527.55 | 334432.17 | -178904.62 | Yes | N/A | N/A | 2022-05-20 | 2024-08-20 | 824 | 588 | 2024-08-20 | 2024-11-04 | 77 | 55 | 2024-09-24 | 2025-05-08 | 15 | 9 | 2024-09-09 | 2024-11-22 | 36 | 28 | 2024-12-27 | Unknown | Unknown | Unknown | 2024-12-27 | 2025-05-12 | 137 | 97 | 2025-05-20 | 2025-06-17 | 1900-01-28 | 21 | 2025-06-17 | 2025-06-17 | 1 | 1 | 839 | 597 | 280 | 202 | 1119 | 799 | Steps 2,3,5,6,7 | 282 | 202 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 111.05 | 111.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | -138 | -100 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-27 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 1878.83 | 871.47 | Unknown | 239.86 | -1593 | 2360.5 | 3981 | 4112.42 | 1878.83 | 2233.59 | Yes | N/A | N/A | 2024-08-09 | 2024-06-04 | Unknown | Unknown | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2024-11-14 | 1900-01-09 | 8 | 2024-11-14 | 2024-10-14 | Unknown | Unknown | 0 | 0 | 10 | 8 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-14 | -603 | -432 | No | 2023-03-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | Yes | 45 | 7.17 | -4.27 | Unknown | Unknown | Unknown | 11.44 | 3981 | 153.75 | 7.17 | 146.58 | Yes | N/A | N/A | 2023-03-31 | 2023-05-15 | 46 | 32 | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | Unknown | Unknown | 2023-06-22 | 2023-06-22 | 1 | 1 | 46 | 32 | 1 | 1 | 47 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 29 | 29 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-19 | 49 | 36 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-01-31 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 3302.55 | 243.81 | Unknown | Unknown | 186.95 | 2871.79 | 3885 | 862.23 | 3302.55 | -2440.32 | Yes | N/A | N/A | 2023-01-31 | 2023-03-22 | 51 | 37 | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | 2024-11-07 | 597 | 427 | Unknown | 2024-11-07 | Unknown | Unknown | 2024-11-07 | 2024-11-07 | 1899-12-31 | 1 | 2024-11-07 | 2024-11-07 | 1 | 1 | 648 | 464 | 2 | 2 | 650 | 466 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-22 | 171 | 123 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | 5080.38 | 1650.24 | Unknown | 15.27 | -1788.39 | 5203.26 | Unknown | 3658.2 | 5080.38 | -1422.18 | Yes | N/A | N/A | 2024-01-30 | 2024-08-28 | 212 | 152 | 2024-08-28 | 2024-11-19 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2025-05-30 | 193 | 139 | Unknown | 2025-03-14 | Unknown | Unknown | 2025-05-02 | 2025-06-11 | 1900-02-09 | 29 | 2025-06-11 | 2025-06-11 | 1 | 1 | 405 | 291 | 126 | 90 | 531 | 381 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-08 | 110 | 79 | No | 2024-02-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-16 | Unknown | IOU Designed & Installed | N/A | Yes | 404 | 317.25 | -6.38 | Unknown | Unknown | Unknown | 323.63 | Unknown | 1728.33 | 317.25 | 1411.08 | Yes | N/A | N/A | 2024-02-16 | 2025-03-26 | 405 | 289 | 2025-03-26 | 2024-02-16 | Unknown | Unknown | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | 2025-04-28 | 2025-04-28 | 1 | 1 | 405 | 289 | 1 | 1 | 406 | 290 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-12 | 25 | 20 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 4905.96 | Unknown | Unknown | Unknown | -1281 | 6186.96 | Unknown | 1281.33 | 4905.96 | -3624.63 | Yes | N/A | N/A | 2024-07-25 | 2024-07-25 | 1 | 1 | 2024-07-25 | 2024-08-13 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-09-06 | 1900-01-15 | 12 | 2024-09-06 | 2024-09-06 | 1 | 1 | 1 | 1 | 37 | 27 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 130 | 130 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-14 | -567 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-08-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 354.39 | -7.13 | Unknown | Unknown | Unknown | 361.52 | 13296 | 700.5 | 354.39 | 346.11 | Yes | N/A | N/A | 2024-06-27 | 2024-07-23 | 27 | 19 | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2024-10-24 | 1 | 1 | 27 | 19 | 1 | 1 | 28 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 113.05 | 113.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-08 | -537 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-30 | 2025-05-13 | IOU Designed & Installed | N/A | No | N/A | 975.8 | Unknown | Unknown | Unknown | Unknown | 975.8 | 3981 | 3968.21 | 975.8 | 2992.41 | Yes | N/A | N/A | 2024-12-10 | 2024-12-27 | 18 | 14 | 2024-12-27 | 2024-12-30 | 4 | 2 | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | 2025-05-13 | 135 | 97 | Unknown | 2025-05-12 | Unknown | Unknown | 2025-05-13 | 2025-05-20 | 1900-01-07 | 6 | 2025-05-20 | 2025-05-20 | 1 | 1 | 153 | 111 | 13 | 9 | 166 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-12 | -572 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 | 2024-07-26 | 2024-12-12 | IOU Designed & Installed | N/A | No | N/A | 1462.77 | Unknown | Unknown | Unknown | Unknown | 1462.77 | 3981 | 1122.44 | 1462.77 | -340.33 | Yes | N/A | N/A | 2024-07-26 | 2024-07-31 | 6 | 4 | 2024-07-31 | 2024-07-31 | 1 | 1 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-12-12 | 135 | 97 | Unknown | 2024-12-09 | Unknown | Unknown | 2024-12-12 | 2024-12-17 | 1900-01-05 | 4 | 2024-12-17 | 2024-12-17 | 1 | 1 | 141 | 101 | 8 | 6 | 149 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-10 | -694 | -497 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | 192.02 | -2.19 | Unknown | Unknown | Unknown | 194.21 | 3981 | 2006.72 | 192.02 | 1814.7 | Yes | N/A | N/A | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-03-03 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-18 | 1900-01-15 | 12 | 2025-03-18 | 2025-03-18 | 1 | 1 | 15 | 11 | 18 | 14 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-26 | -364 | -261 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2023-09-28 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 565.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-27 | 2023-09-26 | Unknown | Unknown | 2023-09-26 | 2023-09-27 | 2 | 2 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-09-28 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-09-28 | 1899-12-31 | 1 | 2023-09-28 | 2023-09-28 | 1 | 1 | 2 | 2 | 4 | 4 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-06 | -25 | -19 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-11-06 | 2024-02-20 | IOU Designed & Installed | N/A | No | N/A | 37047.62 | 11857.13 | Unknown | Unknown | 115.05 | 25075.44 | 118675 | 20126.69 | 37047.62 | -16920.93 | Yes | N/A | N/A | 2023-05-09 | 2023-08-15 | 99 | 71 | 2023-08-15 | 2023-11-27 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2024-02-15 | 81 | 59 | Unknown | 2023-12-07 | Unknown | Unknown | 2024-02-20 | 2024-03-12 | 1900-01-21 | 16 | 2024-03-12 | 2024-03-12 | 1 | 1 | 180 | 130 | 128 | 92 | 308 | 222 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | RAMONA | N/A | 143 | 143 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-11 | 14 | 11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2024-01-17 | 2024-07-01 | IOU Designed & Installed | N/A | No | N/A | 2926.42 | 1962.09 | Unknown | Unknown | -4828 | 5792.33 | Unknown | 8802.59 | 2926.42 | 5876.17 | Yes | N/A | N/A | 2023-11-20 | 2023-12-13 | 24 | 18 | 2023-12-13 | 2024-06-24 | 195 | 139 | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-06-21 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-07-25 | 1900-01-24 | 19 | 2024-07-25 | 2024-07-25 | 1 | 1 | 24 | 18 | 273 | 197 | 297 | 215 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | 457 | 328 | No | 2022-08-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-19 | 2022-08-19 | 2023-05-03 | IOU Designed & Installed | N/A | Yes | 248 | 836.18 | 344.6 | Unknown | Unknown | Unknown | 491.58 | 9723 | 901.14 | 836.18 | 64.96 | Yes | N/A | N/A | 2022-08-19 | 2023-04-24 | 249 | 177 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-08-19 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | 2023-05-04 | 1900-01-01 | 2 | 2023-05-04 | 2023-05-04 | 1 | 1 | 249 | 177 | 3 | 3 | 252 | 180 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 26.05 | 26.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-08 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | 2024-01-10 | IOU Designed & Installed | N/A | No | N/A | 548.73 | 193.22 | Unknown | Unknown | Unknown | 355.51 | 3981 | 893.27 | 548.73 | 344.54 | Yes | N/A | N/A | 2023-12-11 | 2023-12-11 | 1 | 1 | 2023-12-11 | 2023-12-11 | 1 | 1 | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2024-01-10 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-01-17 | 1900-01-07 | 6 | 2024-01-17 | 2024-01-17 | 1 | 1 | 32 | 24 | 10 | 8 | 42 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -626 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-06-27 | 2024-08-19 | IOU Designed & Installed | N/A | No | N/A | 536.62 | -10.2 | Unknown | Unknown | Unknown | 546.82 | 3981 | 1543.31 | 536.62 | 1006.69 | Yes | N/A | N/A | 2024-06-24 | 2024-05-17 | Unknown | Unknown | 2024-05-17 | 2024-06-27 | 42 | 30 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-08-19 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-08-21 | 1900-01-02 | 3 | 2024-08-21 | 2024-08-27 | 7 | 5 | 54 | 38 | 52 | 38 | 106 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-21 | -306 | -220 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | 2025-05-19 | IOU Designed & Installed | N/A | No | N/A | 1247.72 | 1229.96 | Unknown | 405.47 | -1389 | 1001.29 | Unknown | 1388.71 | 1247.72 | 140.99 | Yes | N/A | N/A | 2025-04-23 | 2025-04-22 | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | 2025-05-19 | 1899-12-31 | 1 | 2025-05-19 | 2025-05-19 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Residential | Underserved Community | Valley Center | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 408 | 291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-02 | 2022-09-02 | 2024-04-24 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 38326.91 | 9619.66 | Unknown | Unknown | -13365 | 42072.25 | 0 | 32551.79 | 38326.91 | -5775.12 | Yes | N/A | N/A | 2022-09-02 | 2023-02-15 | 167 | 119 | 2023-02-15 | 2023-05-09 | 84 | 60 | 2023-03-15 | 2023-04-27 | 25 | 17 | 2023-04-28 | 2024-04-30 | 17 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-13 | 1900-01-19 | 14 | 2024-05-13 | 2024-05-13 | 1 | 1 | 192 | 136 | 122 | 86 | 314 | 222 | Steps 2,3,5,6,7 | 55 | 39 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-22 | -231 | -166 | No | 2024-11-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-21 | 2024-12-13 | IOU Designed & Installed | N/A | Yes | 48 | 466.43 | Unknown | Unknown | Unknown | 6.5 | 459.93 | Unknown | 1620.18 | 466.43 | 1153.75 | Yes | N/A | N/A | 2024-11-21 | 2025-01-07 | 48 | 34 | 2025-01-07 | 2024-12-10 | Unknown | Unknown | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2024-12-13 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-02-03 | 1900-02-21 | 37 | 2025-02-03 | 2025-02-03 | 1 | 1 | 52 | 38 | 54 | 38 | 106 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-02 | -599 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 210.69 | 75.56 | Unknown | Unknown | Unknown | 135.13 | Unknown | 363.72 | 210.69 | 153.03 | Yes | N/A | N/A | 2023-03-23 | 2023-03-23 | 1 | 1 | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | Unknown | Unknown | 2023-06-14 | 2023-06-14 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-29 | -213 | -153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | 2023-11-21 | IOU Designed & Installed | N/A | No | N/A | -7.34 | -5.54 | Unknown | Unknown | Unknown | -1.8 | Unknown | 480.37 | -7.34 | 487.71 | Yes | N/A | N/A | 2023-09-22 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2023-09-22 | 85 | 61 | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2023-11-21 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2023-11-29 | 1900-01-08 | 7 | 2023-11-29 | 2023-11-29 | 1 | 1 | 61 | 43 | 95 | 69 | 156 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 95.75 | 95.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-10 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-20 | 2025-02-13 | IOU Designed & Installed | N/A | No | N/A | 3418.64 | 832.85 | Unknown | 245.44 | Unknown | 2340.35 | 7962 | 1962.61 | 3418.64 | -1456.03 | Yes | N/A | N/A | 2024-12-10 | 2024-12-20 | 11 | 9 | 2024-12-20 | 2024-12-20 | 1 | 1 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-02-13 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-04-02 | 1900-02-17 | 35 | 2025-04-02 | 2025-04-02 | 1 | 1 | 67 | 49 | 51 | 37 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-08 | -613 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2043.04 | -5.85 | Unknown | Unknown | 14.09 | 2034.8 | 3885 | 351.62 | 2043.04 | -1691.42 | Yes | N/A | N/A | 2023-03-21 | 2023-04-03 | 14 | 10 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | Unknown | Unknown | Unknown | 2023-06-06 | Unknown | Unknown | 2023-06-06 | 2023-06-06 | 1 | 1 | 14 | 10 | 1 | 1 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-20 | -490 | -351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | -394.69 | -14.5 | Unknown | Unknown | -395.23 | 15.04 | 3981 | 882.79 | -394.69 | 1277.48 | Yes | N/A | N/A | 2023-06-18 | 2023-06-19 | 2 | 1 | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | 2023-10-19 | 2 | 2 | 2023-09-18 | 2023-10-13 | 26 | 20 | Unknown | 2023-10-11 | Unknown | Unknown | 2023-10-13 | 2025-02-05 | 1901-04-26 | 344 | 2025-02-05 | 2023-10-19 | Unknown | Unknown | 28 | 21 | 484 | 346 | 512 | 367 | Steps 2,3,5,6,7 | 31 | 23 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-27 | -357 | -256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-29 | 2025-03-26 | IOU Designed & Installed | N/A | No | N/A | -1390.05 | -21.45 | Unknown | Unknown | -2645 | 1276.4 | Unknown | 2645.09 | -1390.05 | 4035.14 | Yes | N/A | N/A | 2024-04-29 | 2024-08-02 | 96 | 70 | 2024-08-02 | 2024-08-02 | 1 | 1 | 2024-08-02 | 2024-09-09 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2025-03-26 | 199 | 143 | Unknown | 2024-10-25 | Unknown | Unknown | 2025-03-26 | 2025-04-04 | 1900-01-09 | 8 | 2025-04-04 | 2025-04-04 | 1 | 1 | 334 | 240 | 12 | 10 | 346 | 250 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | LA JOLLA | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-08 | 359 | 256 | No | 2023-06-30 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-06-30 | 2024-06-11 | IOU Designed & Installed | N/A | Yes | 161 | 1054.34 | -25.24 | Unknown | Unknown | Unknown | 1079.58 | 3981 | 1037.17 | 1054.34 | -17.17 | Yes | N/A | N/A | 2023-06-30 | 2023-11-17 | 141 | 101 | 2023-11-17 | 2023-12-08 | 22 | 16 | 2023-12-08 | 2023-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2024-06-11 | 342 | 244 | Unknown | 2025-03-05 | Unknown | Unknown | 2024-06-11 | 2024-07-01 | 1900-01-20 | 15 | 2024-07-01 | 2024-07-01 | 1 | 1 | 483 | 345 | 44 | 32 | 527 | 377 | Steps 2,3,5,6,7 | 267 | 191 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | GUATAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-20 | -631 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-11 | 2025-05-30 | IOU Designed & Installed | N/A | No | N/A | 5138.99 | 1311.3 | Unknown | Unknown | Unknown | 3827.69 | Unknown | 2139.9 | 5138.99 | -2999.09 | Yes | N/A | N/A | 2025-04-01 | 2025-04-02 | 2 | 2 | 2025-04-02 | 2025-04-11 | 10 | 8 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-05-30 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-05-30 | 1899-12-31 | 1 | 2025-05-30 | 2025-05-30 | 1 | 1 | 52 | 38 | 12 | 10 | 64 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-11 | -582 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-05-22 | 2023-07-06 | IOU Designed & Installed | N/A | No | N/A | 961.12 | 488.48 | Unknown | 161.28 | Unknown | 311.36 | 3981 | 661.33 | 961.12 | -299.79 | Yes | N/A | N/A | 2023-04-12 | 2023-05-22 | 41 | 29 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | 2023-07-06 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-07-10 | 1900-01-04 | 3 | 2023-07-10 | 2023-07-10 | 1 | 1 | 86 | 62 | 6 | 4 | 92 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-17 | -223 | -160 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2023-12-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8.01 | Unknown | Unknown | Unknown | Unknown | 8.01 | 3961 | 163.83 | 8.01 | 155.82 | Yes | N/A | N/A | 2023-12-08 | 2023-12-11 | 4 | 2 | 2023-12-11 | 2024-02-16 | 68 | 50 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | Unknown | Unknown | 2025-02-06 | 2025-02-06 | 1 | 1 | 4 | 2 | 69 | 51 | 73 | 53 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-12 | -70 | -51 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-04 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 7151.51 | 2051.34 | Unknown | Unknown | -1741.66 | 6841.83 | Unknown | 1501.3 | 7151.51 | -5650.21 | Yes | N/A | N/A | 2024-04-04 | 2024-03-22 | Unknown | Unknown | 2024-03-22 | 2024-08-26 | 158 | 112 | 2024-07-19 | 2024-07-23 | 5 | 3 | 2024-07-23 | 2024-08-19 | 28 | 20 | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-10-03 | 1900-01-23 | 18 | 2024-10-03 | 2024-10-03 | 1 | 1 | 5 | 3 | 211 | 151 | 216 | 154 | Steps 2,3,5,6,7 | 38 | 26 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | RANCHITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | 2024-01-18 | IOU Designed & Installed | N/A | No | N/A | 2560.81 | 800.03 | Unknown | 235.84 | Unknown | 1524.94 | 3981 | 861.77 | 2560.81 | -1699.04 | Yes | N/A | N/A | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-01-18 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-02-01 | 1900-01-14 | 11 | 2024-02-01 | 2024-02-01 | 1 | 1 | 33 | 25 | 17 | 13 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-21 | -112 | -81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-10-04 | IOU Designed & Installed | N/A | No | N/A | 969.02 | 252.46 | Unknown | 235.5 | Unknown | 481.06 | 3981 | 695.96 | 969.02 | -273.06 | Yes | N/A | N/A | 2023-06-13 | 2023-06-14 | 2 | 2 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | 2023-10-04 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | 2023-11-01 | 1900-01-28 | 21 | 2023-11-01 | 2023-11-01 | 1 | 1 | 115 | 83 | 30 | 22 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-15 | -299 | -214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-09-28 | 2023-11-15 | IOU Designed & Installed | N/A | No | N/A | -888.57 | 1862.88 | Unknown | 908.84 | -4461 | 800.71 | Unknown | 4461.2 | -888.57 | 5349.77 | Yes | N/A | N/A | 2023-09-28 | 2023-09-28 | 1 | 1 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2023-11-21 | 1900-01-06 | 5 | 2023-11-21 | 2023-11-21 | 1 | 1 | 1 | 1 | 8 | 6 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | -122 | -88 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-16 | 2023-02-16 | 2024-08-04 | IOU Designed & Installed | N/A | No | N/A | 2433.11 | 319 | Unknown | 75.73 | 12.22 | 2026.16 | 3981 | 733.82 | 2433.11 | -1699.29 | Yes | N/A | N/A | 2023-02-16 | 2023-04-11 | 55 | 39 | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-11 | 2023-05-18 | 8 | 6 | 2023-07-03 | 2024-08-04 | 399 | 285 | Unknown | 2024-08-01 | Unknown | Unknown | 2024-08-04 | 2024-08-07 | 1900-01-03 | 3 | 2024-08-07 | 2024-08-07 | 1 | 1 | 454 | 324 | 13 | 10 | 467 | 334 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | 2032 | 1453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -0.93 | Unknown | Unknown | Unknown | Unknown | -0.93 | Unknown | 773.84 | -0.93 | 774.77 | Yes | N/A | N/A | 2023-11-28 | 2023-12-04 | 7 | 5 | 2023-12-04 | 2023-12-27 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2023-12-15 | 11 | 9 | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | Unknown | Unknown | 2024-07-24 | 2024-07-24 | 1 | 1 | 7 | 5 | 36 | 28 | 43 | 33 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-09-30 | 652 | 467 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 467.68 | -5.55 | Unknown | Unknown | 18.64 | 454.59 | 3981 | 374.92 | 467.68 | -92.76 | Yes | N/A | N/A | 2023-04-21 | 2023-04-21 | 1 | 1 | 2023-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | Unknown | Unknown | Unknown | Unknown | 2023-07-12 | Unknown | Unknown | Unknown | 2023-10-06 | Unknown | Unknown | 2023-10-06 | 2023-07-14 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | -524 | -375 | No | 2023-03-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-03-27 | 2023-08-17 | IOU Designed & Installed | N/A | Yes | 126 | 2825.47 | 729.96 | Unknown | Unknown | 53.28 | 2042.23 | 3981 | 655.07 | 2825.47 | -2170.4 | Yes | N/A | N/A | 2023-03-27 | 2023-07-31 | 127 | 91 | 2023-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | 2023-08-17 | 141 | 101 | Unknown | 2023-08-17 | Unknown | Unknown | 2023-08-17 | 2023-10-03 | 1900-02-16 | 34 | 2023-10-03 | 2023-08-21 | Unknown | Unknown | 268 | 192 | 48 | 34 | 316 | 226 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-10 | -556 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-05 | 2023-06-05 | 2023-07-20 | IOU Designed & Installed | N/A | No | N/A | 404.86 | 252.1 | Unknown | Unknown | Unknown | 152.76 | Unknown | 495.75 | 404.86 | 90.89 | Yes | N/A | N/A | 2023-05-05 | 2023-06-05 | 32 | 22 | 2023-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2023-07-20 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-08-04 | 1900-01-15 | 12 | 2023-08-04 | 2023-08-04 | 1 | 1 | 78 | 56 | 17 | 13 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-04 | -276 | -198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 7.18 | -6.4 | Unknown | Unknown | Unknown | 13.58 | 3981 | 1138.54 | 7.18 | 1131.36 | Yes | N/A | N/A | 2024-03-01 | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-03-08 | 10 | 8 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-04-03 | 1 | 1 | 0 | 0 | 11 | 9 | 11 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-07 | -242 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-27 | 2023-07-07 | IOU Designed & Installed | N/A | No | N/A | 56.81 | -9.36 | Unknown | Unknown | Unknown | 66.17 | 3981 | 1421.18 | 56.81 | 1364.37 | Yes | N/A | N/A | 2023-06-27 | 2023-05-02 | Unknown | Unknown | 2023-05-02 | 2023-06-28 | 58 | 42 | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-07-07 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | 2023-08-09 | 1900-02-02 | 24 | 2023-08-09 | 2023-08-09 | 1 | 1 | 10 | 8 | 93 | 67 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-15 | -135 | -98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | 2023-10-23 | IOU Designed & Installed | N/A | No | N/A | -7.21 | -5.29 | Unknown | Unknown | Unknown | -1.92 | Unknown | 581.84 | -7.21 | 589.05 | Yes | N/A | N/A | 2023-06-20 | 2023-03-31 | Unknown | Unknown | 2023-03-31 | 2023-07-05 | 97 | 69 | 2023-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-05 | 2023-10-23 | 111 | 79 | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2023-11-01 | 1900-01-09 | 8 | 2023-11-01 | 2023-11-01 | 1 | 1 | 111 | 79 | 108 | 78 | 219 | 157 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | -409 | -294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-23 | 2023-06-23 | 2023-08-03 | IOU Designed & Installed | N/A | No | N/A | 4042.68 | 108.37 | Unknown | Unknown | 2.03 | 3932.28 | Unknown | 9467.6 | 4042.68 | 5424.92 | Yes | N/A | N/A | 2023-06-23 | 2023-07-12 | 20 | 14 | 2023-07-12 | 2023-07-27 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-07-27 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-03 | 2023-08-21 | 1900-01-18 | 13 | 2023-08-21 | 2023-08-21 | 1 | 1 | 20 | 14 | 37 | 27 | 57 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-28 | -302 | -217 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | 2023-08-24 | IOU Designed & Installed | N/A | No | N/A | 5940.28 | Unknown | Unknown | Unknown | Unknown | 5940.28 | 3981 | 1095.86 | 5940.28 | -4844.42 | Yes | N/A | N/A | 2023-08-15 | 2023-08-17 | 3 | 3 | 2023-08-17 | 2023-08-17 | 1 | 1 | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2023-08-24 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | 2023-08-31 | 1900-01-07 | 6 | 2023-08-31 | 2023-08-31 | 1 | 1 | 11 | 9 | 10 | 8 | 21 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 234 | 234 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-31 | 154 | 111 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-06-16 | 2023-08-28 | IOU Designed & Installed | N/A | No | N/A | 8784.65 | 2399.28 | Unknown | 1217.63 | 159.52 | 5008.22 | 3981 | 1125.7 | 8784.65 | -7658.95 | Yes | N/A | N/A | 2023-05-18 | 2023-06-16 | 30 | 22 | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-08-28 | 74 | 52 | Unknown | 2023-08-11 | Unknown | Unknown | 2023-08-28 | 2023-11-10 | 1900-03-15 | 55 | 2023-11-10 | 2023-09-01 | Unknown | Unknown | 104 | 74 | 75 | 55 | 179 | 129 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-31 | -73 | -52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-11 | 2023-08-15 | 2024-01-17 | IOU Designed & Installed | N/A | No | N/A | 5.96 | -7.53 | Unknown | Unknown | Unknown | 13.49 | 3981 | 569.4 | 5.96 | 563.44 | Yes | N/A | N/A | 2023-08-11 | 2023-08-15 | 5 | 3 | 2023-08-15 | 2023-08-15 | 1 | 1 | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2024-01-17 | 156 | 112 | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | 2024-01-19 | 1900-01-02 | 3 | 2024-01-19 | 2024-01-18 | Unknown | Unknown | 161 | 115 | 4 | 4 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 306 | 306 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-11-22 | 935 | 670 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 1894.25 | Unknown | Unknown | Unknown | Unknown | 1894.25 | 3981 | 499.79 | 1894.25 | -1394.46 | Yes | N/A | N/A | 2023-11-06 | 2023-09-15 | Unknown | Unknown | 2023-09-15 | 2023-12-18 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-04-25 | 130 | 94 | Unknown | 2024-05-06 | Unknown | Unknown | 2024-06-06 | 2024-06-17 | 1900-01-11 | 8 | 2024-06-17 | 2024-06-14 | Unknown | Unknown | 130 | 94 | 107 | 75 | 237 | 169 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-30 | -5 | -5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-07-07 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | -2064.61 | 2060.32 | Unknown | 151.83 | -5153 | 876.24 | Unknown | 5152.97 | -2064.61 | 7217.58 | Yes | N/A | N/A | 2023-04-18 | 2023-06-23 | 67 | 49 | 2023-06-23 | 2023-08-01 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-03-25 | 1899-12-31 | 1 | 2024-03-25 | 2024-03-25 | 1 | 1 | 67 | 49 | 42 | 30 | 109 | 79 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | Encinitas | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-12 | 387 | 278 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-05-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1357.19 | Unknown | Unknown | Unknown | -2656 | 4013.19 | Unknown | 2656.22 | 1357.19 | 1299.03 | Yes | N/A | N/A | 2024-04-09 | 2024-06-12 | 65 | 47 | 2024-06-12 | 2024-08-14 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-08-15 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | 2024-10-03 | 2024-10-03 | 1 | 1 | 65 | 47 | 68 | 50 | 133 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | 692 | 495 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-18 | 2022-07-18 | 2024-10-15 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 2027625.22 | 652112.1 | Unknown | 757.24 | 16858.44 | 1357897.44 | 23808707 | 972026.64 | 2027625.22 | -1055598.58 | Yes | N/A | N/A | 2022-07-18 | 2024-05-15 | 668 | 478 | 2024-05-15 | 2024-09-24 | 133 | 95 | 2024-06-13 | 2024-11-05 | 9 | 7 | 2024-06-20 | 2024-08-14 | 43 | 31 | 2024-09-24 | Unknown | Unknown | Unknown | 2024-08-08 | 2024-09-16 | 40 | 28 | 2024-10-15 | 2025-01-21 | 1900-04-08 | 71 | 2025-01-21 | 2025-01-21 | 1 | 1 | 677 | 485 | 316 | 226 | 993 | 711 | Steps 2,3,5,6,7 | 241 | 171 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 122.05 | 122.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-11 | -528 | -377 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | 2025-02-06 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | 6841.8 | 702.53 | Unknown | 113.51 | -1461.07 | 7486.83 | Unknown | 1522.75 | 6841.8 | -5319.05 | Yes | N/A | N/A | 2025-01-27 | 2025-01-03 | Unknown | Unknown | 2025-01-03 | 2025-02-14 | 43 | 31 | 2025-02-14 | 2025-02-19 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-04-24 | 65 | 47 | Unknown | 2025-04-22 | Unknown | Unknown | 2025-04-24 | 2025-05-01 | 1900-01-07 | 6 | 2025-05-01 | 2025-05-01 | 1 | 1 | 71 | 51 | 52 | 38 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-26 | -602 | -431 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | 2024-03-29 | IOU Designed & Installed | N/A | No | N/A | 746.76 | 252.46 | Unknown | Unknown | Unknown | 494.3 | Unknown | 889.73 | 746.76 | 142.97 | Yes | N/A | N/A | 2024-02-20 | 2024-02-20 | 1 | 1 | 2024-02-20 | 2024-02-20 | 1 | 1 | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-03-29 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-04-03 | 1900-01-05 | 4 | 2024-04-03 | 2024-04-03 | 1 | 1 | 40 | 30 | 8 | 6 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-08 | -102 | -73 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-07-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1272.32 | -23.47 | Unknown | Unknown | Unknown | 1295.79 | 7962 | 760.23 | 1272.32 | -512.09 | Yes | N/A | N/A | 2023-05-12 | 2023-07-27 | 77 | 55 | 2023-07-27 | 2023-08-16 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-07-29 | 29 | 21 | 2023-08-16 | 2024-05-03 | 262 | 188 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2024-08-28 | Unknown | Unknown | 339 | 243 | 50 | 36 | 389 | 279 | Steps 2,3,5,6,7 | 348 | 248 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-31 | 421 | 302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-02-14 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | 20018.42 | Unknown | Unknown | Unknown | Unknown | 20018.42 | 7962 | 5324.4 | 20018.42 | -14694.02 | Yes | N/A | N/A | 2024-01-23 | 2024-01-30 | 8 | 6 | 2024-01-30 | 2024-03-08 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-09-30 | 207 | 147 | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-11-08 | 1900-01-28 | 21 | 2024-11-08 | 2024-10-25 | Unknown | Unknown | 215 | 153 | 68 | 50 | 283 | 203 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | 1800 | 1800 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-03-16 | 286 | 205 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | 2023-12-06 | IOU Designed & Installed | N/A | No | N/A | 1714.49 | 1957.75 | Unknown | 1330.25 | -2462 | 888.49 | Unknown | 2462.49 | 1714.49 | 748 | Yes | N/A | N/A | 2023-10-27 | 2023-10-27 | 1 | 1 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2024-03-04 | 1900-03-30 | 64 | 2024-03-04 | 2023-12-27 | Unknown | Unknown | 1 | 1 | 90 | 64 | 91 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 105.05 | 105.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-19 | -35 | -26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 194.36 | 54.87 | Unknown | Unknown | 4.15 | 135.34 | 3981 | 1189.69 | 194.36 | 995.33 | Yes | N/A | N/A | 2024-07-15 | 2024-10-24 | 102 | 74 | 2024-10-24 | 2024-10-28 | 5 | 3 | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | 2025-05-15 | 2025-05-15 | 1 | 1 | 102 | 74 | 6 | 4 | 108 | 78 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 659 | 659 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-16 | -579 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-03-15 | 2024-04-09 | IOU Designed & Installed | N/A | No | N/A | 17.93 | -10.58 | Unknown | Unknown | Unknown | 28.51 | 3981 | 1146.94 | 17.93 | 1129.01 | Yes | N/A | N/A | 2024-02-07 | 2024-02-08 | 2 | 2 | 2024-02-08 | 2024-03-15 | 37 | 27 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-04-09 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2024-04-16 | 1900-01-07 | 6 | 2024-04-16 | 2024-04-16 | 1 | 1 | 28 | 20 | 46 | 34 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 69.05 | 69.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -385 | -276 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2025-02-12 | IOU Designed & Installed | N/A | No | N/A | -117.83 | 136.43 | Unknown | Unknown | -711.89 | 457.63 | Unknown | 1552.12 | -117.83 | 1669.95 | Yes | N/A | N/A | 2024-08-27 | 2024-07-19 | Unknown | Unknown | 2024-07-19 | 2024-10-07 | 81 | 57 | 2024-10-07 | 2024-10-22 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2025-02-12 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-04-11 | 1900-02-27 | 43 | 2025-04-11 | 2025-04-11 | 1 | 1 | 130 | 94 | 141 | 101 | 271 | 195 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | RAMONA | 166.2 | 166.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | -171 | -122 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-06-07 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 17545.36 | 3953.45 | Unknown | Unknown | 20.74 | 13571.17 | 3981 | 1427.11 | 17545.36 | -16118.25 | Yes | N/A | N/A | 2024-06-07 | 2024-06-19 | 13 | 9 | 2024-06-19 | 2025-01-10 | 206 | 148 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-02-05 | 27 | 19 | Unknown | 2025-01-24 | Unknown | Unknown | 2025-03-17 | 2025-03-17 | 1899-12-31 | 1 | 2025-03-17 | 2025-03-14 | Unknown | Unknown | 40 | 28 | 207 | 149 | 247 | 177 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | -360 | -258 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-01 | 2024-11-06 | IOU Designed & Installed | N/A | No | N/A | 1692.09 | 461.24 | Unknown | 44.31 | Unknown | 1186.54 | Unknown | 1077.95 | 1692.09 | -614.14 | Yes | N/A | N/A | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2024-11-06 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-11-06 | 1899-12-31 | 1 | 2024-11-06 | 2024-11-06 | 1 | 1 | 7 | 5 | 3 | 3 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | -555 | -398 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-31 | 2025-01-10 | IOU Designed & Installed | N/A | No | N/A | -1247.68 | Unknown | Unknown | Unknown | -1276 | 28.32 | Unknown | 1022.61 | -1247.68 | 2270.29 | Yes | N/A | N/A | 2024-10-29 | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2024-10-31 | 8 | 6 | 2024-10-31 | 2024-12-20 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-01-10 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-01-29 | 1900-01-19 | 14 | 2025-01-29 | 2025-01-29 | 1 | 1 | 55 | 41 | 29 | 21 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 917.15 | 917.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | 507 | 364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 826.81 | -16.62 | Unknown | Unknown | Unknown | 843.43 | 47772 | 1383.46 | 826.81 | 556.65 | Yes | N/A | N/A | 2023-10-09 | 2023-09-11 | Unknown | Unknown | 2023-09-11 | 2023-11-14 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-11 | 10 | 8 | 2023-11-14 | 2025-05-15 | 549 | 393 | Unknown | 2025-05-05 | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-05-22 | Unknown | Unknown | 549 | 393 | 75 | 55 | 624 | 448 | Steps 2,3,5,6,7 | 514 | 368 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-27 | 358 | 257 | No | 2023-05-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-04 | Unknown | IOU Designed & Installed | N/A | Yes | 524 | 12.71 | Unknown | Unknown | Unknown | Unknown | 12.71 | Unknown | 3107.69 | 12.71 | 3094.98 | Yes | N/A | N/A | 2023-05-02 | 2024-10-07 | 525 | 375 | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-02-19 | 1 | 1 | 525 | 375 | 1 | 1 | 526 | 376 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-07-22 | 1342 | 959 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | 2023-06-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 821.49 | -16.86 | Unknown | Unknown | Unknown | 838.35 | 64281 | 610.29 | 821.49 | -211.2 | Yes | N/A | N/A | 2023-06-28 | 2023-08-22 | 56 | 40 | 2023-08-22 | 2024-02-26 | 189 | 135 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-02-12 | Unknown | Unknown | Unknown | 2024-03-12 | Unknown | Unknown | Unknown | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-03-25 | 1 | 1 | 56 | 40 | 190 | 136 | 246 | 176 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 931.05 | 931.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-06-20 | 2023-07-21 | IOU Designed & Installed | N/A | No | N/A | -3.16 | -6.17 | Unknown | Unknown | Unknown | 3.01 | 6481 | 901.71 | -3.16 | 904.87 | Yes | N/A | N/A | 2023-05-31 | 2023-06-20 | 21 | 15 | 2023-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | 2023-07-21 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2023-08-25 | 1900-02-04 | 26 | 2023-08-25 | 2023-08-25 | 1 | 1 | 53 | 39 | 37 | 27 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-23 | -225 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-02 | 2023-04-10 | IOU Designed & Installed | N/A | No | N/A | 461.76 | -13 | Unknown | Unknown | Unknown | 474.76 | Unknown | 670.08 | 461.76 | 208.32 | Yes | N/A | N/A | 2023-03-01 | 2023-03-02 | 2 | 2 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | 2023-04-10 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | 2023-06-12 | 1900-03-04 | 46 | 2023-06-12 | 2023-06-12 | 1 | 1 | 42 | 30 | 65 | 47 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 54 | 54 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-29 | 76 | 55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-10 | 2023-05-26 | IOU Designed & Installed | N/A | No | N/A | -3.36 | -9.92 | Unknown | Unknown | Unknown | 6.56 | Unknown | 893.62 | -3.36 | 896.98 | Yes | N/A | N/A | 2023-04-10 | 2023-04-10 | 1 | 1 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | 2023-05-26 | 47 | 35 | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | 2023-06-13 | 1900-01-18 | 13 | 2023-06-13 | 2023-06-13 | 1 | 1 | 48 | 36 | 20 | 14 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-12 | -188 | -135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-06-06 | IOU Designed & Installed | N/A | No | N/A | -2.6 | -5.02 | Unknown | Unknown | Unknown | 2.42 | Unknown | 670.08 | -2.6 | 672.68 | Yes | N/A | N/A | 2023-03-21 | 2023-03-22 | 2 | 2 | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | 2023-06-06 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | 2023-08-08 | 1900-03-04 | 46 | 2023-08-08 | 2023-08-08 | 1 | 1 | 79 | 57 | 65 | 47 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-23 | -435 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-12-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 648.46 | -9.99 | Unknown | Unknown | Unknown | 658.45 | Unknown | 483.59 | 648.46 | -164.87 | Yes | N/A | N/A | 2023-10-13 | 2023-10-03 | Unknown | Unknown | 2023-10-03 | 2023-12-05 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-10-18 | 6 | 4 | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 0 | 0 | 71 | 51 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-07 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-13 | 2024-07-13 | 2024-09-11 | IOU Designed & Installed | N/A | No | N/A | 29.01 | Unknown | Unknown | Unknown | Unknown | 29.01 | Unknown | 1436.95 | 29.01 | 1407.94 | Yes | N/A | N/A | 2024-07-13 | 2024-07-13 | 1 | 0 | 2024-07-13 | 2024-07-13 | 1 | 0 | 2024-07-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-13 | 2024-09-11 | 61 | 43 | Unknown | 2024-09-10 | Unknown | Unknown | 2024-09-11 | 2024-10-23 | 1900-02-11 | 31 | 2024-10-23 | 2024-10-23 | 1 | 1 | 62 | 43 | 45 | 32 | 107 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-03 | -432 | -309 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | 2024-05-16 | IOU Designed & Installed | N/A | No | N/A | 2.69 | -2.38 | Unknown | Unknown | Unknown | 5.07 | Unknown | 381.45 | 2.69 | 378.76 | Yes | N/A | N/A | 2024-02-15 | 2023-10-09 | Unknown | Unknown | 2023-10-09 | 2024-02-21 | 136 | 98 | 2024-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-05-16 | 86 | 62 | Unknown | 2024-05-20 | Unknown | Unknown | 2024-05-16 | 2024-05-28 | 1900-01-12 | 9 | 2024-05-28 | 2024-05-28 | 1 | 1 | 86 | 62 | 150 | 108 | 236 | 170 | Steps 2,3,5,6,7 | 4 | 2 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-31 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | -1772.87 | Unknown | Unknown | Unknown | -1797 | 24.13 | Unknown | 1652.05 | -1772.87 | 3424.92 | Yes | N/A | N/A | 2024-10-17 | 2024-12-02 | 47 | 33 | 2024-12-02 | 2024-10-17 | Unknown | Unknown | 2024-10-17 | 2024-12-04 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2025-01-28 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-03 | 1900-01-06 | 5 | 2025-02-03 | 2025-02-25 | 23 | 17 | 154 | 110 | 30 | 22 | 184 | 132 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | -412 | -295 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-01 | 2023-07-05 | 2023-08-03 | IOU Designed & Installed | N/A | No | N/A | 35.87 | Unknown | Unknown | Unknown | Unknown | 35.87 | Unknown | 270.38 | 35.87 | 234.51 | Yes | N/A | N/A | 2023-07-01 | 2023-07-18 | 18 | 12 | 2023-07-18 | 2023-07-20 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-03 | 2023-08-18 | 1900-01-15 | 12 | 2023-08-18 | 2023-08-18 | 1 | 1 | 18 | 12 | 20 | 16 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-16 | -617 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | 2025-02-06 | IOU Designed & Installed | N/A | No | N/A | 822.51 | 122.12 | Unknown | Unknown | Unknown | 700.39 | Unknown | 1716.42 | 822.51 | 893.91 | Yes | N/A | N/A | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-02-06 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-06 | 1899-12-31 | 1 | 2025-02-06 | 2025-02-06 | 1 | 1 | 31 | 23 | 3 | 3 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12.6 | 12.6 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-05 | -533 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | 2023-12-12 | IOU Designed & Installed | N/A | No | N/A | 0.56 | -7.62 | Unknown | Unknown | Unknown | 8.18 | 3241 | 767.68 | 0.56 | 767.12 | Yes | N/A | N/A | 2023-12-05 | 2023-11-30 | Unknown | Unknown | 2023-11-30 | 2023-12-05 | 6 | 4 | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2023-12-12 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2023-12-20 | 1900-01-08 | 7 | 2023-12-20 | 2023-12-20 | 1 | 1 | 8 | 6 | 16 | 12 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 26.46 | 26.46 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-30 | -506 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-02-01 | 2024-03-20 | IOU Designed & Installed | N/A | No | N/A | 2631.4 | -62.67 | Unknown | Unknown | Unknown | 2694.07 | 3981 | 1051.94 | 2631.4 | -1579.46 | Yes | N/A | N/A | 2024-01-19 | 2023-11-15 | Unknown | Unknown | 2023-11-15 | 2024-02-01 | 79 | 57 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-03-20 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-04-11 | 1900-01-22 | 17 | 2024-04-11 | 2024-04-11 | 1 | 1 | 49 | 35 | 103 | 75 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-09 | -421 | -302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-07 | 2024-05-13 | IOU Designed & Installed | N/A | No | N/A | 1372.37 | 431.7 | Unknown | Unknown | Unknown | 940.67 | Unknown | 842.18 | 1372.37 | -530.19 | Yes | N/A | N/A | 2023-11-07 | 2023-11-07 | 1 | 1 | 2023-11-07 | 2023-11-07 | 1 | 1 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2024-05-13 | 189 | 135 | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-05-14 | 1900-01-01 | 2 | 2024-05-14 | 2024-05-14 | 1 | 1 | 190 | 136 | 4 | 4 | 194 | 140 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | -637 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | 2025-03-14 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1732.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-02-27 | 1 | 1 | 2025-02-27 | 2025-02-27 | 1 | 1 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-03-14 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-04-24 | 1900-02-10 | 30 | 2025-04-24 | 2025-04-24 | 1 | 1 | 17 | 13 | 44 | 32 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-11 | 29 | 22 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 30.54 | -13.67 | Unknown | Unknown | Unknown | 44.21 | 3981 | 986.48 | 30.54 | 955.94 | Yes | N/A | N/A | 2023-09-11 | 2023-10-03 | 23 | 17 | 2023-10-03 | 2023-10-25 | 23 | 17 | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | Unknown | Unknown | 2024-05-13 | 2024-05-10 | Unknown | Unknown | 23 | 17 | 23 | 17 | 46 | 34 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-07 | -630 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | 2025-03-27 | IOU Designed & Installed | N/A | No | N/A | 356.45 | -7.15 | Unknown | Unknown | Unknown | 363.6 | Unknown | 1643.68 | 356.45 | 1287.23 | Yes | N/A | N/A | 2025-03-20 | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-21 | 17 | 13 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-03-27 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-17 | 1900-01-21 | 16 | 2025-04-17 | 2025-04-17 | 1 | 1 | 8 | 6 | 40 | 30 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | -503 | -360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-02-28 | 2025-04-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1793.54 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-04-23 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-05-14 | 1900-01-21 | 16 | 2025-05-14 | 2025-05-01 | Unknown | Unknown | 56 | 40 | 23 | 17 | 79 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-29 | 110 | 79 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2023-07-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1003.5 | -12.66 | Unknown | Unknown | 6.98 | 1009.18 | 3981 | 2023.67 | 1003.5 | 1020.17 | Yes | N/A | N/A | 2023-07-24 | 2023-08-11 | 19 | 15 | 2023-08-11 | 2023-08-14 | 4 | 2 | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | Unknown | Unknown | Unknown | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-07-17 | 1 | 1 | 19 | 15 | 5 | 3 | 24 | 18 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-03 | -583 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-02-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -10.21 | -7.4 | Unknown | Unknown | Unknown | -2.81 | Unknown | 351.99 | -10.21 | 362.2 | Yes | N/A | N/A | 2023-01-31 | 2023-01-31 | 1 | 1 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | Unknown | Unknown | 2023-03-31 | 2023-03-31 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-23 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | 0 | Unknown | Unknown | Unknown | Unknown | Unkonwn | 3981 | 2007.02 | Unknown | 2007.02 | Yes | N/A | N/A | 2024-07-23 | 2024-07-22 | Unknown | Unknown | 2024-07-22 | 2024-09-04 | 45 | 33 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-16 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-09-17 | 1900-01-01 | 2 | 2024-09-17 | 2024-09-17 | 1 | 1 | 13 | 9 | 48 | 36 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | 43 | 31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 796.8 | Unknown | Unknown | Unknown | Unknown | 796.8 | Unknown | 477.21 | 796.8 | -319.59 | Yes | N/A | N/A | 2024-10-22 | 2025-03-05 | 135 | 97 | 2025-03-05 | 2025-03-06 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-11-27 | 37 | 27 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 135 | 97 | 40 | 30 | 175 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | 628 | 449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-08-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 727.97 | -14.28 | Unknown | Unknown | Unknown | 742.25 | 7962 | 482.9 | 727.97 | -245.07 | Yes | N/A | N/A | 2023-08-21 | 2023-07-13 | Unknown | Unknown | 2023-07-13 | 2024-05-13 | 306 | 218 | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | Unknown | Unknown | Unknown | 2024-05-13 | 2024-11-06 | 178 | 128 | Unknown | 2024-10-15 | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-11-18 | Unknown | Unknown | 178 | 128 | 306 | 218 | 484 | 346 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-15 | -499 | -356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2023-11-07 | 2023-11-29 | IOU Designed & Installed | N/A | No | N/A | 926.64 | -24.7 | Unknown | Unknown | 9.21 | 942.13 | 3981 | 869.4 | 926.64 | -57.24 | Yes | N/A | N/A | 2023-10-24 | 2023-11-06 | 14 | 10 | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | Unknown | Unknown | Unknown | 2023-11-08 | 2023-11-29 | 22 | 16 | 2023-11-07 | 2023-11-29 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2024-02-02 | 1900-03-06 | 48 | 2024-02-02 | 2024-02-02 | 1 | 1 | 37 | 27 | 90 | 66 | 127 | 93 | Steps 2,3,5,6,7 | 22 | 16 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | -491 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 423.69 | Unknown | Unknown | Unknown | 18.5 | 405.19 | 3981 | 1115.82 | 423.69 | 692.13 | Yes | N/A | N/A | 2024-10-16 | 2024-09-19 | Unknown | Unknown | 2024-09-19 | 2024-10-24 | 36 | 26 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2025-03-05 | 133 | 95 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-05-08 | 1900-03-05 | 47 | 2025-05-08 | 2025-05-08 | 1 | 1 | 133 | 95 | 102 | 74 | 235 | 169 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JULIAN | COUNTY OF SAN DIEGO-NORTH of 56 | 59.05 | 59.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | -359 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | 2023-04-05 | 2024-03-17 | IOU Designed & Installed | N/A | No | N/A | 4806.29 | 1457.3 | Unknown | 366.04 | Unknown | 2982.95 | 3981 | 580.42 | 4806.29 | -4225.87 | Yes | N/A | N/A | 2023-04-05 | 2023-04-05 | 1 | 1 | 2023-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-05 | 2023-04-06 | 2 | 2 | 2023-04-19 | 2024-03-17 | 334 | 238 | Unknown | Unknown | Unknown | Unknown | 2024-03-17 | 2024-03-21 | 1900-01-04 | 4 | 2024-03-21 | 2024-03-21 | 1 | 1 | 335 | 239 | 8 | 7 | 343 | 246 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | N/A | ENCINITAS | N/A | 30000 | 30000 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-11-01 | 513 | 368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-12-01 | 2024-03-22 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 286.17 | 78.56 | Unknown | Unknown | -2197.67 | 2405.28 | 1786 | 3063.21 | 286.17 | 2777.04 | Yes | N/A | N/A | 2023-11-29 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2023-12-20 | 174 | 124 | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-02-28 | 1 | 1 | 2023-12-20 | 2024-03-13 | 85 | 61 | Unknown | 2024-03-18 | Unknown | Unknown | 2024-03-22 | 2024-03-28 | 1900-01-06 | 5 | 2024-03-28 | 2024-03-28 | 1 | 1 | 85 | 61 | 183 | 131 | 268 | 192 | Steps 2,3,5,6,7 | 70 | 50 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 106.75 | 106.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -591 | -423 | No | 2024-04-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-06-20 | IOU Designed & Installed | N/A | Yes | 34 | 697.6 | -12.84 | Unknown | Unknown | 2.61 | 707.83 | 3981 | 880.28 | 697.6 | 182.68 | Yes | N/A | N/A | 2024-04-25 | 2024-05-29 | 35 | 25 | 2024-05-29 | 2024-05-29 | 1 | 1 | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2024-06-20 | 44 | 32 | Unknown | 2024-06-20 | Unknown | Unknown | 2024-06-20 | 2024-07-10 | 1900-01-20 | 15 | 2024-07-10 | 2024-07-10 | 1 | 1 | 79 | 57 | 23 | 17 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | -453 | -325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-06-07 | 2024-07-19 | IOU Designed & Installed | N/A | No | N/A | 23.93 | Unknown | Unknown | Unknown | Unknown | 23.93 | Unknown | 1578.07 | 23.93 | 1554.14 | Yes | N/A | N/A | 2024-05-07 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-06-07 | 58 | 42 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-07-19 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-08-12 | 1900-01-24 | 17 | 2024-08-12 | 2024-08-12 | 1 | 1 | 43 | 31 | 84 | 60 | 127 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 30054.05 | 30054.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-02-07 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-18 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | 366.36 | -19.18 | Unknown | Unknown | Unknown | 385.54 | 3981 | 827.23 | 366.36 | 460.87 | Yes | N/A | N/A | 2023-04-10 | 2023-04-18 | 9 | 7 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | 2023-07-27 | 101 | 73 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-07-28 | 1900-01-01 | 2 | 2023-07-28 | 2023-07-28 | 1 | 1 | 110 | 80 | 3 | 3 | 113 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | -675 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-05 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 492.84 | -24.08 | Unknown | Unknown | Unknown | 516.92 | Unknown | 2023.98 | 492.84 | 1531.14 | Yes | N/A | N/A | 2025-02-27 | 2025-02-21 | Unknown | Unknown | 2025-02-21 | 2025-02-21 | 1 | 1 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-06 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-04-07 | 1900-02-01 | 23 | 2025-04-07 | 2025-04-07 | 1 | 1 | 2 | 2 | 35 | 25 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-29 | -176 | -127 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | 2024-12-26 | IOU Designed & Installed | N/A | No | N/A | 15506.39 | Unknown | Unknown | Unknown | 1.12 | 15505.27 | Unknown | 5099.08 | 15506.39 | -10407.31 | Yes | N/A | N/A | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | 2024-09-11 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-02-03 | 1900-02-08 | 28 | 2025-02-03 | 2025-02-03 | 1 | 1 | 1 | 1 | 83 | 59 | 84 | 60 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | -583 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-01-30 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | 7824.69 | 3799.07 | Unknown | Unknown | -2559.26 | 6584.88 | 3981 | 6738.34 | 7824.69 | -1086.35 | Yes | N/A | N/A | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | 2025-02-07 | 9 | 7 | 2025-02-07 | 2025-03-03 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-04-07 | 36 | 26 | Unknown | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-04-19 | 1900-01-12 | 10 | 2025-04-19 | 2025-04-17 | Unknown | Unknown | 62 | 44 | 22 | 17 | 84 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | -535 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-05 | 2023-11-01 | IOU Designed & Installed | N/A | No | N/A | 694.48 | -39.12 | Unknown | Unknown | 6.11 | 727.49 | 3981 | 783.8 | 694.48 | 89.32 | Yes | N/A | N/A | 2023-10-05 | 2023-11-01 | 28 | 20 | 2023-11-01 | 2023-11-01 | 1 | 1 | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2023-11-01 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2024-02-22 | 1900-04-23 | 82 | 2024-02-22 | 2024-02-22 | 1 | 1 | 29 | 21 | 116 | 84 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | -458 | -327 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -23.87 | -17.28 | Unknown | Unknown | Unknown | -6.59 | Unknown | 98.41 | -23.87 | 122.28 | Yes | N/A | N/A | 2023-03-09 | 2023-03-08 | Unknown | Unknown | 2023-03-08 | 2023-03-20 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | 2023-05-02 | 1 | 1 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | Unknown | Unknown | Unknown | 2023-10-05 | Unknown | Unknown | 2023-10-05 | 2023-10-05 | 1 | 1 | 0 | 0 | 15 | 11 | 15 | 11 | Steps 2,3,5,6,7 | 43 | 31 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 18.05 | 18.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-27 | 312 | 225 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2025-01-13 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 20520.06 | Unknown | Unknown | Unknown | 387.63 | 20132.43 | 27867 | 2505.41 | 20520.06 | -18014.65 | Yes | N/A | N/A | 2024-09-24 | 2025-01-10 | 109 | 79 | 2025-01-10 | 2025-02-05 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-04-04 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-07-03 | 1900-04-18 | 79 | 2025-07-03 | 2025-04-04 | Unknown | Unknown | 168 | 122 | 136 | 98 | 304 | 220 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 78 | 78 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-08 | -168 | -121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | 2023-06-15 | IOU Designed & Installed | N/A | No | N/A | 7302.06 | 1109.03 | Unknown | Unknown | 21.62 | 6171.41 | 3981 | 2025.41 | 7302.06 | -5276.65 | Yes | N/A | N/A | 2023-03-24 | 2023-04-17 | 25 | 17 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | 2023-06-15 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | 2023-08-24 | 1900-03-11 | 51 | 2023-08-24 | 2023-08-24 | 1 | 1 | 78 | 56 | 72 | 52 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 22.4 | 22.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | -421 | -301 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | 2024-12-05 | IOU Designed & Installed | N/A | No | N/A | 1881.12 | 420.74 | Unknown | Unknown | 16.03 | 1444.35 | 3981 | 1266.12 | 1881.12 | -615 | Yes | N/A | N/A | 2024-06-04 | 2024-05-29 | Unknown | Unknown | 2024-05-29 | 2024-06-06 | 9 | 7 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-12-05 | 183 | 131 | Unknown | 2025-01-14 | Unknown | Unknown | 2024-12-05 | 2025-01-17 | 1900-02-12 | 32 | 2025-01-17 | 2025-01-17 | 1 | 1 | 183 | 131 | 54 | 40 | 237 | 171 | Steps 2,3,5,6,7 | 40 | 28 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-28 | -667 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-19 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | -0.88 | Unknown | Unknown | Unknown | Unknown | -0.88 | 3981 | 1480.17 | -0.88 | 1481.05 | Yes | N/A | N/A | 2024-07-19 | 2024-05-31 | Unknown | Unknown | 2024-05-31 | 2024-07-19 | 50 | 36 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-07-22 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-07-30 | 1900-01-08 | 7 | 2024-07-30 | 2024-07-30 | 1 | 1 | 4 | 2 | 60 | 44 | 64 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 90.05 | 90.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-15 | -76 | -55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | 2024-02-27 | 2024-08-05 | IOU Designed & Installed | N/A | No | N/A | 45.17 | Unknown | Unknown | Unknown | 0.59 | 44.58 | 3981 | 929.57 | 45.17 | 884.4 | Yes | N/A | N/A | 2024-02-27 | 2024-01-04 | Unknown | Unknown | 2024-01-04 | 2024-02-27 | 55 | 39 | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-08-05 | 161 | 115 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2025-02-03 | 1900-07-01 | 131 | 2025-02-03 | 2025-01-29 | Unknown | Unknown | 161 | 115 | 238 | 170 | 399 | 285 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-02 | 497 | 356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-03 | 2024-12-08 | IOU Designed & Installed | N/A | No | N/A | 1559.27 | 307.91 | Unknown | Unknown | Unknown | 1251.36 | Unknown | 307.58 | 1559.27 | -1251.69 | Yes | N/A | N/A | 2024-05-03 | 2024-09-26 | 147 | 105 | 2024-09-26 | 2024-11-21 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-08 | 2024-12-11 | 1900-01-03 | 3 | 2024-12-11 | 2024-12-11 | 1 | 1 | 147 | 105 | 62 | 45 | 209 | 150 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | -225 | -161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | 2024-07-05 | IOU Designed & Installed | N/A | No | N/A | -8053.85 | 1765.91 | Unknown | Unknown | -10969 | 1149.24 | Unknown | 10969.08 | -8053.85 | 19022.93 | Yes | N/A | N/A | 2024-06-25 | 2024-06-25 | 1 | 1 | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | 2024-07-12 | 1900-01-07 | 6 | 2024-07-12 | 2024-07-12 | 1 | 1 | 1 | 1 | 9 | 7 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | -645 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | Unknown | 2024-10-02 | IOU Designed & Installed | N/A | No | N/A | 6.37 | Unknown | Unknown | Unknown | Unknown | 6.37 | 3981 | 1510.56 | 6.37 | 1504.19 | Yes | N/A | N/A | 2024-08-15 | 2024-08-15 | 1 | 1 | 2024-08-15 | 2024-08-15 | 1 | 1 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-10-02 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-11-01 | 1900-01-30 | 23 | 2024-11-01 | 2024-11-01 | 1 | 1 | 50 | 36 | 33 | 25 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-10 | -668 | -477 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-19 | 2024-06-24 | IOU Designed & Installed | N/A | No | N/A | 14.36 | -11.06 | Unknown | Unknown | Unknown | 25.42 | 3981 | 1493.31 | 14.36 | 1478.95 | Yes | N/A | N/A | 2024-06-19 | 2024-05-17 | Unknown | Unknown | 2024-05-17 | 2024-06-19 | 34 | 24 | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-06-24 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-07-11 | 1900-01-17 | 14 | 2024-07-11 | 2024-07-11 | 1 | 1 | 6 | 4 | 53 | 39 | 59 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | -464 | -333 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2023-05-25 | 2023-10-30 | IOU Designed & Installed | N/A | No | N/A | -6.25 | -4.59 | Unknown | Unknown | Unknown | -1.66 | 26990 | 319.87 | -6.25 | 326.12 | Yes | N/A | N/A | 2023-05-25 | 2023-05-25 | 1 | 1 | 2023-05-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-25 | 2023-10-30 | 159 | 113 | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2023-11-15 | 1900-01-16 | 13 | 2023-11-15 | 2023-11-15 | 1 | 1 | 160 | 114 | 18 | 14 | 178 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2030-12-31 | -2552 | -1823 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-11 | 2023-08-14 | 2023-12-12 | IOU Designed & Installed | N/A | No | N/A | 14292.18 | 1466.15 | Unknown | Unknown | -3050.71 | 15876.74 | Unknown | 1768.8 | 14292.18 | -12523.38 | Yes | N/A | N/A | 2023-08-11 | 2023-09-27 | 48 | 34 | 2023-09-27 | 2023-10-31 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2023-11-01 | 1 | 1 | 2023-12-06 | Unknown | Unknown | Unknown | 2023-12-06 | 2023-11-30 | Unknown | Unknown | 2023-12-12 | 2024-01-05 | 1900-01-24 | 19 | 2024-01-05 | 2024-01-05 | 1 | 1 | 48 | 34 | 62 | 46 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | National City | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-07-10 | 929 | 664 | No | 2020-10-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-10-23 | 2020-10-27 | 2023-12-18 | IOU Designed & Installed | N/A | Yes | 1011 | 36927.33 | 9679.15 | Unknown | Unknown | -501.21 | 27749.39 | 50220 | Not available | 36927.33 | Unknown | Yes | N/A | N/A | 2020-10-23 | 2023-04-25 | 915 | 653 | 2023-04-25 | 2021-06-16 | Unknown | Unknown | 2023-06-12 | 2023-06-13 | 2 | 2 | 2021-03-04 | 2023-07-11 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2023-10-24 | 16 | 12 | 2023-12-18 | 2024-01-25 | 1900-02-07 | 29 | 2024-01-25 | 2024-01-25 | 1 | 1 | 917 | 655 | 75 | 55 | 992 | 710 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-17 | -521 | -374 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-04 | 2024-04-02 | IOU Designed & Installed | N/A | No | N/A | -6.38 | -6.23 | Unknown | Unknown | Unknown | -0.15 | 3885 | 553.02 | -6.38 | 559.4 | Yes | N/A | N/A | 2024-03-04 | 2024-03-26 | 23 | 17 | 2024-03-26 | 2024-03-26 | 1 | 1 | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-04-02 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-05-14 | 1900-02-11 | 31 | 2024-05-14 | 2024-05-14 | 1 | 1 | 30 | 22 | 45 | 33 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | -695 | -498 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | Unknown | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 23.91 | Unknown | Unknown | Unknown | Unknown | 23.91 | 3981 | 1516.55 | 23.91 | 1492.64 | Yes | N/A | N/A | 2024-09-30 | 2024-09-30 | 1 | 1 | 2024-09-30 | 2024-09-30 | 1 | 1 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-10-01 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-16 | 1900-01-15 | 12 | 2024-10-16 | 2024-10-16 | 1 | 1 | 3 | 3 | 18 | 14 | 21 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-28 | -241 | -172 | No | 2024-02-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-03-19 | 2025-04-22 | IOU Designed & Installed | N/A | Yes | 219 | 1581.75 | Unknown | Unknown | Unknown | 27.77 | 1553.98 | 3981 | 797.46 | 1581.75 | -784.29 | Yes | N/A | N/A | 2024-02-26 | 2024-10-02 | 220 | 158 | 2024-10-02 | 2024-03-19 | Unknown | Unknown | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2025-04-22 | 400 | 286 | Unknown | 2025-04-10 | Unknown | Unknown | 2025-04-22 | 2025-05-01 | 1900-01-09 | 8 | 2025-05-01 | 2025-05-01 | 1 | 1 | 620 | 444 | 11 | 9 | 631 | 453 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-12 | 422 | 303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | 2024-11-04 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 17303 | 1831.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-14 | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-10-17 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2024-10-16 | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | 2024-11-04 | 2024-11-08 | 1900-01-04 | 5 | 2024-11-08 | 2024-11-07 | Unknown | Unknown | 0 | 0 | 133 | 97 | 133 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | CORONADO | 4.7 | 4.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-17 | -358 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-17 | 2025-02-12 | IOU Designed & Installed | N/A | No | N/A | 213.3 | -4.28 | Unknown | Unknown | Unknown | 217.58 | 3981 | 1203.96 | 213.3 | 990.66 | Yes | N/A | N/A | 2024-06-17 | 2024-06-17 | 1 | 1 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-02-11 | 16 | 12 | 2024-06-17 | 2025-02-12 | 241 | 173 | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-03-24 | 1900-02-09 | 29 | 2025-03-24 | 2025-03-24 | 1 | 1 | 242 | 174 | 58 | 42 | 300 | 216 | Steps 2,3,5,6,7 | 239 | 171 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-21 | -546 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-02-01 | 2024-04-04 | IOU Designed & Installed | N/A | No | N/A | 348.14 | -13.94 | Unknown | Unknown | Unknown | 362.08 | 3981 | 1007.5 | 348.14 | 659.36 | Yes | N/A | N/A | 2024-01-05 | 2023-10-26 | Unknown | Unknown | 2023-10-26 | 2024-02-01 | 99 | 71 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-04-04 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-04-24 | 1900-01-20 | 15 | 2024-04-24 | 2024-04-23 | Unknown | Unknown | 64 | 46 | 120 | 86 | 184 | 132 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-14 | -487 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-10 | 2023-11-06 | IOU Designed & Installed | N/A | No | N/A | 1501.68 | 826.84 | Unknown | 352.16 | -1909.77 | 2232.45 | Unknown | 1909.97 | 1501.68 | 408.29 | Yes | N/A | N/A | 2023-05-10 | 2023-06-21 | 43 | 31 | 2023-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | 2023-11-06 | 139 | 99 | Unknown | 2023-10-19 | Unknown | Unknown | 2023-11-06 | 2023-11-13 | 1900-01-07 | 6 | 2023-11-13 | 2023-11-13 | 1 | 1 | 182 | 130 | 9 | 7 | 191 | 137 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN YSIDRO | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | -386 | -276 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-10 | 2025-03-20 | IOU Designed & Installed | N/A | No | N/A | 5513.68 | 1456.66 | Unknown | 20.28 | 2.67 | 4034.07 | 11943 | 2039.78 | 5513.68 | -3473.9 | Yes | N/A | N/A | 2024-09-06 | 2024-09-10 | 5 | 3 | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2025-03-20 | 192 | 138 | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-05-02 | 1900-02-12 | 32 | 2025-05-02 | 2025-05-02 | 1 | 1 | 197 | 141 | 46 | 34 | 243 | 175 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 46 | 34 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-17 | 2023-05-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 11324.39 | Unknown | Unknown | Unknown | Unknown | 11324.39 | Unknown | 1225.94 | 11324.39 | -10098.45 | Yes | N/A | N/A | 2022-11-17 | 2023-09-26 | 314 | 224 | 2023-09-26 | 2023-10-04 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | Unknown | Unknown | 2023-11-30 | 2023-11-30 | 1 | 1 | 314 | 224 | 10 | 8 | 324 | 232 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-10 | -674 | -482 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-29 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 3.94 | Unknown | Unknown | Unknown | Unknown | 3.94 | 3981 | 118.25 | 3.94 | 114.31 | Yes | N/A | N/A | 2025-04-29 | 2025-05-02 | 4 | 4 | 2025-05-02 | 2025-05-02 | 1 | 1 | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | 2025-05-12 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-06-05 | 1900-01-24 | 19 | 2025-06-05 | 2025-06-05 | 1 | 1 | 12 | 10 | 27 | 21 | 39 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-20 | -191 | -138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | 2023-01-30 | 2023-03-14 | IOU Designed & Installed | N/A | No | N/A | 222.87 | -7.36 | Unknown | Unknown | 6.81 | 223.42 | Unknown | 763.27 | 222.87 | 540.4 | Yes | N/A | N/A | 2023-01-30 | 2023-02-02 | 4 | 4 | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-02 | 2023-03-14 | 41 | 29 | Unknown | 2023-03-09 | Unknown | Unknown | 2023-03-14 | 2023-06-12 | 1900-03-31 | 65 | 2023-06-12 | 2023-06-12 | 1 | 1 | 45 | 33 | 92 | 66 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-27 | -640 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | Unknown | 2024-11-12 | IOU Designed & Installed | N/A | No | N/A | 96.3 | -1.57 | Unknown | Unknown | Unknown | 97.87 | 3981 | 1546.09 | 96.3 | 1449.79 | Yes | N/A | N/A | 2024-10-10 | 2024-10-10 | 1 | 1 | 2024-10-10 | 2024-10-10 | 1 | 1 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-11-12 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2024-11-25 | 1900-01-13 | 10 | 2024-11-25 | 2024-11-25 | 1 | 1 | 35 | 25 | 16 | 12 | 51 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 137.05 | 137.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-15 | 115 | 84 | No | 2024-04-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-05-06 | 2025-02-04 | IOU Designed & Installed | N/A | Yes | 272 | 7558.19 | 1936.23 | Unknown | 299.32 | Unknown | 5322.64 | 3981 | 643.54 | 7558.19 | -6914.65 | Yes | N/A | N/A | 2024-04-25 | 2025-01-22 | 273 | 195 | 2025-01-22 | 2024-04-25 | Unknown | Unknown | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2025-02-04 | 275 | 197 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-02-05 | 1900-01-01 | 2 | 2025-02-05 | 2025-02-07 | 3 | 3 | 548 | 392 | 5 | 5 | 553 | 397 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 510.05 | 510.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-01 | 228 | 163 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-03 | Unknown | 2024-01-31 | IOU Designed & Installed | N/A | No | N/A | 81.95 | -6.56 | Unknown | Unknown | Unknown | 88.51 | 3981 | 1132.85 | 81.95 | 1050.9 | Yes | N/A | N/A | 2023-07-03 | 2023-04-24 | Unknown | Unknown | 2023-04-24 | 2023-07-07 | 75 | 55 | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-03 | 2024-01-31 | 213 | 153 | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-02-13 | 1900-01-13 | 10 | 2024-02-13 | 2024-02-14 | 2 | 2 | 213 | 153 | 91 | 67 | 304 | 220 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DESCANSO | N/A | 113.75 | 113.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | -130 | -95 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 5682.9 | 877.92 | Unknown | Unknown | 28.55 | 4776.43 | 3981 | 1064.65 | 5682.9 | -4618.25 | Yes | N/A | N/A | 2024-07-16 | 2024-07-02 | Unknown | Unknown | 2024-07-02 | 2024-08-14 | 44 | 32 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-09-23 | 41 | 29 | Unknown | 2024-09-18 | Unknown | Unknown | 2024-09-23 | 2024-09-23 | 1899-12-31 | 1 | 2024-09-23 | 2024-09-23 | 1 | 1 | 41 | 29 | 46 | 34 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | Fallbrook | N/A | 140082.8 | 140082.8 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-05-31 | 60 | 43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2024-03-01 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | -3968.64 | 5329.73 | Unknown | Unknown | -24720 | 15421.63 | 3048.33 | 20744.38 | -3968.64 | 24713.02 | Yes | N/A | N/A | 2023-10-10 | 2024-01-09 | 92 | 66 | 2024-01-09 | 2024-03-28 | 80 | 58 | 2024-03-01 | 2024-03-01 | 1 | 1 | 2024-03-29 | 2024-04-12 | 15 | 11 | 2024-03-28 | Unknown | Unknown | Unknown | 2024-05-13 | 2024-06-12 | 31 | 23 | 2024-06-17 | 2024-07-30 | 1900-02-12 | 32 | 2024-07-30 | 2024-07-30 | 1 | 1 | 93 | 67 | 171 | 125 | 264 | 192 | Steps 2,3,5,6,7 | 42 | 30 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | DANA POINT | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-07 | -216 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-09-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 34.69 | Unknown | Unknown | Unknown | Unknown | 34.69 | Unknown | 1638.3 | 34.69 | 1603.61 | Yes | N/A | N/A | 2024-08-22 | 2024-08-27 | 6 | 4 | 2024-08-27 | 2024-09-06 | 11 | 9 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | 2024-10-03 | 2024-10-03 | 1 | 1 | 6 | 4 | 12 | 10 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | 1169 | 836 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2023-11-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 753.93 | -27.34 | Unknown | Unknown | 3.76 | 777.51 | Unknown | 1908.08 | 753.93 | 1154.15 | Yes | N/A | N/A | 2023-11-02 | 2023-11-02 | 1 | 1 | 2023-11-02 | 2023-11-13 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | 2023-11-09 | 7 | 5 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 1 | 1 | 20 | 14 | 21 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-15 | -136 | -99 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | 2024-06-24 | IOU Designed & Installed | N/A | No | N/A | 12436.95 | Unknown | Unknown | Unknown | Unknown | 12436.95 | 350328 | 6411.36 | 12436.95 | -6025.59 | Yes | N/A | N/A | 2023-02-15 | 2023-02-15 | 1 | 1 | 2023-02-15 | 2023-03-20 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | 2024-07-05 | 474 | 340 | Unknown | 2024-06-20 | Unknown | Unknown | 2024-06-24 | 2024-07-08 | 1900-01-14 | 11 | 2024-07-08 | 2024-07-02 | Unknown | Unknown | 475 | 341 | 49 | 35 | 524 | 376 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-05 | -356 | -255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-25 | 2024-10-02 | IOU Designed & Installed | N/A | No | N/A | -431.62 | Unknown | Unknown | Unknown | -499 | 67.38 | 3981 | 1010.84 | -431.62 | 1442.46 | Yes | N/A | N/A | 2024-04-24 | 2024-04-25 | 2 | 2 | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-04-25 | 2024-04-29 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-10-02 | 125 | 89 | Unknown | 2024-10-02 | Unknown | Unknown | 2024-10-02 | 2024-10-16 | 1900-01-14 | 11 | 2024-10-16 | 2024-10-14 | Unknown | Unknown | 132 | 94 | 16 | 12 | 148 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | -521 | -374 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-06-13 | 2024-07-03 | IOU Designed & Installed | N/A | No | N/A | 18.25 | Unknown | Unknown | Unknown | Unknown | 18.25 | 3981 | 1704.08 | 18.25 | 1685.83 | Yes | N/A | N/A | 2024-05-07 | 2024-06-13 | 38 | 28 | 2024-06-13 | 2024-06-13 | 1 | 1 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-07-03 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-08-14 | 1900-02-11 | 31 | 2024-08-14 | 2024-08-13 | Unknown | Unknown | 59 | 43 | 44 | 32 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-05 | -114 | -83 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-02-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2.08 | -6.19 | Unknown | Unknown | Unknown | 4.11 | 3981 | 1170.39 | -2.08 | 1172.47 | Yes | N/A | N/A | 2023-01-25 | 2023-02-06 | 13 | 9 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | 2023-05-11 | Unknown | Unknown | Unknown | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2023-09-13 | 1 | 1 | 13 | 9 | 1 | 1 | 14 | 10 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 81 | 81 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-31 | -203 | -146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4.97 | -6.23 | Unknown | Unknown | Unknown | 11.2 | 3981 | 1030.83 | 4.97 | 1025.86 | Yes | N/A | N/A | 2023-11-27 | 2023-11-27 | 1 | 1 | 2023-11-27 | 2023-11-27 | 1 | 1 | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-01-10 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-24 | -629 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-14 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | 1452.45 | Unknown | Unknown | Unknown | 1.29 | 1451.16 | 3981 | 2874.97 | 1452.45 | 1422.52 | Yes | N/A | N/A | 2025-03-14 | 2025-03-28 | 15 | 11 | 2025-03-28 | 2025-04-04 | 8 | 6 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-24 | 21 | 15 | Unknown | 2025-05-07 | Unknown | Unknown | 2025-04-24 | 2025-05-05 | 1900-01-11 | 8 | 2025-05-05 | 2025-05-05 | 1 | 1 | 36 | 26 | 21 | 15 | 57 | 41 | Steps 2,3,5,6,7 | 13 | 9 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | BORREGO SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-03 | 67 | 48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-04-19 | 2024-01-02 | IOU Designed & Installed | N/A | No | N/A | 8669.88 | 350.69 | Unknown | Unknown | -987 | 9306.19 | 11680 | 2223.55 | 8669.88 | -6446.33 | Yes | N/A | N/A | 2023-02-17 | 2023-02-17 | 1 | 1 | 2023-02-17 | 2023-06-14 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2023-12-06 | 1 | 1 | 2023-06-14 | 2023-08-11 | 59 | 43 | Unknown | 2025-04-11 | Unknown | Unknown | 2024-01-02 | 2024-01-12 | 1900-01-10 | 9 | 2024-01-12 | 2024-01-09 | Unknown | Unknown | 60 | 44 | 130 | 94 | 190 | 138 | Steps 2,3,5,6,7 | 640 | 458 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-28 | 495 | 354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-02-28 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 42998.66 | 3227.18 | Unknown | 74.88 | -12818.1 | 52514.7 | 25593 | 15315.01 | 42998.66 | -27683.65 | Yes | N/A | N/A | 2023-01-25 | 2023-02-28 | 35 | 25 | 2023-02-28 | 2024-05-20 | 448 | 320 | 2023-08-23 | 2023-11-21 | 7 | 3 | 2023-07-17 | 2024-10-22 | 95 | 69 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2025-05-06 | 1900-07-27 | 149 | 2025-05-06 | 2025-05-06 | 1 | 1 | 42 | 28 | 753 | 539 | 795 | 567 | Steps 2,3,5,6,7 | 398 | 284 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -507 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | 2025-04-04 | IOU Designed & Installed | N/A | No | N/A | 1346.25 | -23.7 | Unknown | Unknown | 13.15 | 1356.8 | 3981 | 1180.79 | 1346.25 | -165.46 | Yes | N/A | N/A | 2024-12-11 | 2025-01-16 | 37 | 27 | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-04-04 | 79 | 57 | Unknown | 2025-03-21 | Unknown | Unknown | 2025-04-04 | 2025-04-10 | 1900-01-06 | 5 | 2025-04-10 | 2025-04-09 | Unknown | Unknown | 116 | 84 | 8 | 6 | 124 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-06 | -546 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-05-13 | 2024-08-01 | IOU Designed & Installed | N/A | No | N/A | -539.65 | -12.07 | Unknown | Unknown | -1194 | 666.42 | 3981 | 1767.45 | -539.65 | 2307.1 | Yes | N/A | N/A | 2024-04-04 | 2024-05-13 | 40 | 28 | 2024-05-13 | 2024-05-17 | 5 | 5 | 2024-05-17 | 2024-06-13 | 28 | 20 | 2024-05-17 | 2024-05-23 | 7 | 5 | 2024-06-13 | 2024-08-01 | 50 | 36 | Unknown | 2024-07-19 | Unknown | Unknown | 2024-08-01 | 2024-08-09 | 1900-01-08 | 7 | 2024-08-09 | 2024-08-09 | 1 | 1 | 118 | 84 | 22 | 18 | 140 | 102 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-18 | -251 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-06-28 | 2024-07-08 | IOU Designed & Installed | N/A | No | N/A | 823.28 | -9.69 | Unknown | Unknown | Unknown | 832.97 | 36349.88 | 1197.72 | 823.28 | 374.44 | Yes | N/A | N/A | 2024-06-28 | 2024-06-28 | 1 | 1 | 2024-06-28 | 2025-03-06 | 252 | 180 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-08 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-07-10 | 1900-01-02 | 3 | 2024-07-10 | 2024-07-10 | 1 | 1 | 12 | 8 | 256 | 184 | 268 | 192 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-03 | -601 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-11 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | -10.8 | -8.76 | Unknown | Unknown | Unknown | -2.04 | 3981 | 1386.04 | -10.8 | 1396.84 | Yes | N/A | N/A | 2024-04-03 | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-04-11 | 65 | 47 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-05-30 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-12 | 1900-01-13 | 10 | 2024-06-12 | 2024-06-12 | 1 | 1 | 50 | 36 | 80 | 58 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-01 | 483 | 346 | No | 2021-05-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-21 | 2021-04-21 | 2023-07-06 | IOU Designed & Installed | N/A | Yes | 666 | 166.08 | -25.87 | Unknown | Unknown | 15.28 | 176.67 | 3981 | 915.57 | 166.08 | 749.49 | Yes | N/A | N/A | 2021-04-21 | 2023-03-02 | 681 | 487 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-05-05 | 2023-07-06 | Unknown | Unknown | Unknown | 2023-07-06 | Unknown | Unknown | 2023-07-06 | 2023-07-28 | 1900-01-22 | 17 | 2023-07-28 | 2023-07-28 | 1 | 1 | 681 | 487 | 24 | 18 | 705 | 505 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | RAMONA | COUNTY OF SAN DIEGO-SOUTH of 56 | 96 | 96 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | -367 | -263 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2023-12-15 | 2024-11-03 | IOU Designed & Installed | N/A | No | N/A | 2467.63 | 667.2 | Unknown | 134.86 | Unknown | 1665.57 | 3981 | 921.4 | 2467.63 | -1546.23 | Yes | N/A | N/A | 2023-12-15 | 2023-12-15 | 1 | 1 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-10-02 | 7 | 5 | 2023-12-18 | 2024-11-03 | 322 | 230 | Unknown | Unknown | Unknown | Unknown | 2024-11-03 | 2024-11-13 | 1900-01-10 | 8 | 2024-11-13 | 2024-11-13 | 1 | 1 | 323 | 231 | 19 | 14 | 342 | 245 | Steps 2,3,5,6,7 | 289 | 207 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-13 | 124 | 89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-03-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 241.22 | 808.37 | Unknown | 109.24 | -1000 | 323.61 | 0 | 1000.28 | 241.22 | 759.06 | Yes | N/A | N/A | 2023-03-17 | 2023-04-07 | 22 | 16 | 2023-04-07 | 2023-04-13 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 22 | 16 | 8 | 6 | 30 | 22 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | N/A | SD 1190-B1 CMR PA17 PH2 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 595 | 426 | No | 2023-04-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-07-05 | 2024-10-16 | Customer elected Applicant Design | Step 2 Engineering & Design | Yes | 161 | 70676.53 | 2576.41 | Unknown | Unknown | 11909.19 | 56190.93 | 0 | 32171.55 | 70676.53 | -38504.98 | Yes | N/A | N/A | 2022-04-27 | 2023-08-27 | 488 | 348 | 2023-08-27 | 2024-02-29 | 187 | 134 | 2023-09-13 | 2024-04-08 | 164 | 118 | 2024-04-12 | 2024-05-05 | 24 | 16 | 2024-04-24 | Unknown | Unknown | Unknown | 2024-04-24 | 2024-10-15 | 175 | 125 | 2024-10-16 | 2024-11-04 | 1900-01-19 | 14 | 2024-11-04 | 2024-11-04 | 1 | 1 | 652 | 466 | 407 | 290 | 1059 | 756 | Steps 2,3,5,6,7 | 180 | 128 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-06 | -669 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-08 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 529.27 | -10.2 | Unknown | Unknown | Unknown | 539.47 | 3981 | 1621.83 | 529.27 | 1092.56 | Yes | N/A | N/A | 2025-01-07 | 2025-01-08 | 2 | 2 | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-30 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-05 | 1900-01-06 | 5 | 2025-02-05 | 2025-02-05 | 1 | 1 | 25 | 19 | 9 | 7 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | -119 | -86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-03-28 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | -127.79 | -11.61 | Unknown | Unknown | -552.66 | 436.48 | Unknown | 555.58 | -127.79 | 683.37 | Yes | N/A | N/A | 2023-02-09 | 2023-03-28 | 48 | 34 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | 2023-07-26 | 98 | 70 | Unknown | 2023-07-18 | Unknown | Unknown | 2023-07-26 | 2023-08-04 | 1900-01-09 | 8 | 2023-08-04 | 2023-08-04 | 1 | 1 | 146 | 104 | 11 | 9 | 157 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 1023.05 | 1023.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-05-09 | -606 | -434 | No | 2024-06-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | 2024-09-03 | IOU Designed & Installed | N/A | Yes | 41 | 1517.86 | Unknown | Unknown | Unknown | 7.02 | 1510.84 | 3981 | 1106.45 | 1517.86 | -411.41 | Yes | N/A | N/A | 2024-06-26 | 2024-08-06 | 42 | 30 | 2024-08-06 | 2024-07-03 | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-09-03 | 63 | 45 | Unknown | 2024-08-29 | Unknown | Unknown | 2024-09-03 | 2024-09-10 | 1900-01-07 | 6 | 2024-09-10 | 2024-09-10 | 1 | 1 | 105 | 75 | 9 | 7 | 114 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | -392 | -281 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2025-02-05 | 2025-04-03 | IOU Designed & Installed | N/A | No | N/A | -1397.48 | -20.58 | Unknown | Unknown | -2422 | 1045.1 | Unknown | 2421.53 | -1397.48 | 3819.01 | Yes | N/A | N/A | 2024-10-18 | 2025-02-05 | 111 | 79 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-04-03 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-21 | 1900-01-18 | 13 | 2025-04-21 | 2025-04-11 | Unknown | Unknown | 160 | 114 | 19 | 13 | 179 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 155.05 | 155.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-07 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | 2025-01-27 | 2025-02-06 | IOU Designed & Installed | N/A | No | N/A | 1960.2 | 486.31 | Unknown | Unknown | 0.24 | 1473.65 | 3981 | 1256.69 | 1960.2 | -703.51 | Yes | N/A | N/A | 2025-01-27 | 2025-01-15 | Unknown | Unknown | 2025-01-15 | 2025-01-27 | 13 | 9 | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-02-06 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-04-11 | 1900-03-05 | 47 | 2025-04-11 | 2025-04-11 | 1 | 1 | 11 | 9 | 79 | 57 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-23 | -162 | -117 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2163.69 | 353.76 | Unknown | 998.38 | 29.93 | 781.62 | 3981 | 2521.7 | 2163.69 | 358.01 | Yes | N/A | N/A | 2023-09-19 | 2023-09-08 | Unknown | Unknown | 2023-09-08 | 2023-10-13 | 36 | 26 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 0 | 0 | 37 | 27 | 37 | 27 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 22 | 22 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-04 | 2024-12-27 | IOU Designed & Installed | N/A | No | N/A | 484.83 | Unknown | Unknown | Unknown | Unknown | 484.83 | 3981 | 1190.83 | 484.83 | 706 | Yes | N/A | N/A | 2024-12-04 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-12-11 | 29 | 21 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2024-12-27 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-01-27 | 1900-01-31 | 22 | 2025-01-27 | 2025-01-27 | 1 | 1 | 17 | 13 | 62 | 44 | 79 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-27 | -615 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | Unknown | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 83.98 | -0.63 | Unknown | Unknown | Unknown | 84.61 | 3981 | 1611.19 | 83.98 | 1527.21 | Yes | N/A | N/A | 2024-08-05 | 2024-08-05 | 1 | 1 | 2024-08-05 | 2024-08-05 | 1 | 1 | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-08-14 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-09-19 | 1900-02-05 | 27 | 2024-09-19 | 2024-09-19 | 1 | 1 | 11 | 9 | 39 | 29 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | 1135 | 812 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 102748.68 | 30630.35 | Unknown | Unknown | -7805.45 | 79923.78 | 0 | 52333.83 | 102748.68 | -50414.85 | Yes | N/A | N/A | 2022-09-01 | 2023-12-11 | 467 | 333 | 2023-12-11 | 2024-05-07 | 149 | 107 | 2024-01-02 | 2025-03-20 | 7 | 3 | 2024-01-11 | 2024-05-24 | 35 | 25 | 2024-05-15 | Unknown | Unknown | Unknown | 2024-05-15 | 2025-02-26 | 288 | 206 | Unknown | 2025-03-12 | Unknown | Unknown | 2025-03-12 | 2025-03-12 | 1 | 1 | 474 | 336 | 473 | 339 | 947 | 675 | Steps 2,3,5,6,7 | 569 | 407 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-30 | -374 | -268 | No | 2023-03-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-11-21 | IOU Designed & Installed | N/A | Yes | 176 | 3696.17 | 1311.57 | Unknown | Unknown | Unknown | 2384.6 | 3981 | 737.55 | 3696.17 | -2958.62 | Yes | N/A | N/A | 2023-03-20 | 2023-09-12 | 177 | 127 | 2023-09-12 | 2023-09-12 | 1 | 1 | 2023-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | 2023-11-21 | 247 | 177 | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2023-11-22 | 1900-01-01 | 2 | 2023-11-22 | 2023-11-22 | 1 | 1 | 424 | 304 | 4 | 4 | 428 | 308 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-20 | -422 | -303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 11250.43 | 2827.99 | Unknown | 1371.37 | 277.96 | 6773.11 | 3981 | 1274.06 | 11250.43 | -9976.37 | Yes | N/A | N/A | 2023-02-14 | 2023-02-14 | 1 | 1 | 2023-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | Unknown | Unknown | 2023-07-26 | 2023-07-26 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-15 | 95 | 68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 731.31 | Unknown | Unknown | Unknown | Unknown | 731.31 | 3981 | 773.84 | 731.31 | 42.53 | Yes | N/A | N/A | 2024-07-16 | 2024-07-16 | 1 | 1 | 2024-07-16 | 2024-08-07 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-08-06 | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | 2024-09-18 | Unknown | Unknown | 2024-09-18 | 2024-09-18 | 1 | 1 | 1 | 1 | 24 | 18 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-25 | -301 | -216 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | 2024-09-27 | IOU Designed & Installed | N/A | No | N/A | -2608.2 | 2122.91 | Unknown | 511.81 | -6593 | 1350.08 | Unknown | 6593.3 | -2608.2 | 9201.5 | Yes | N/A | N/A | 2024-07-29 | 2024-09-17 | 51 | 37 | 2024-09-17 | 2024-09-18 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-09-27 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-09-27 | 1899-12-31 | 1 | 2024-09-27 | 2024-09-27 | 1 | 1 | 61 | 45 | 4 | 4 | 65 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-06 | -124 | -89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 709.71 | -11.15 | Unknown | Unknown | Unknown | 720.86 | 31848 | 1457.58 | 709.71 | 747.87 | Yes | N/A | N/A | 2024-08-16 | 2024-06-20 | Unknown | Unknown | 2024-06-20 | 2024-08-30 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-11-04 | 1 | 1 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | Unknown | Unknown | 2025-01-02 | 2025-01-02 | 1 | 1 | 0 | 0 | 74 | 54 | 74 | 54 | Steps 2,3,5,6,7 | 66 | 46 | Unknown | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 188.1 | 188.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-12 | -394 | -281 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-04-26 | 2023-12-12 | IOU Designed & Installed | N/A | No | N/A | 1883.71 | -7.48 | Unknown | Unknown | 75.13 | 1816.06 | 3981 | 931.44 | 1883.71 | -952.27 | Yes | N/A | N/A | 2023-04-26 | 2023-05-08 | 13 | 9 | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | 2023-05-12 | 5 | 5 | 2023-05-08 | 2023-12-12 | 219 | 157 | Unknown | 2023-12-01 | Unknown | Unknown | 2023-12-12 | 2023-12-15 | 1900-01-03 | 4 | 2023-12-15 | 2023-12-15 | 1 | 1 | 232 | 166 | 10 | 10 | 242 | 176 | Steps 2,3,5,6,7 | 4 | 4 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-12 | -508 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-09-24 | 2024-11-06 | IOU Designed & Installed | N/A | No | N/A | 0 | Unknown | Unknown | Unknown | Unknown | Unkonwn | 3241 | 1171.57 | Unknown | 1171.57 | Yes | N/A | N/A | 2024-05-14 | 2024-09-12 | 122 | 88 | 2024-09-12 | 2024-09-24 | 13 | 9 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-11-06 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-11-19 | 1900-01-13 | 10 | 2024-11-19 | 2024-11-20 | 2 | 2 | 166 | 120 | 29 | 21 | 195 | 141 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CHULA VISTA | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-17 | -594 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.94 | Unknown | Unknown | Unknown | 16.67 | -20.61 | 3981 | 1416.87 | -3.94 | 1420.81 | Yes | N/A | N/A | 2025-01-09 | 2025-01-23 | 15 | 11 | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | 2025-05-02 | 2025-05-02 | 1 | 1 | 15 | 11 | 2 | 2 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | -532 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | 2025-02-28 | IOU Designed & Installed | N/A | No | N/A | 504.77 | 128.54 | Unknown | Unknown | Unknown | 376.23 | Unknown | 2226.15 | 504.77 | 1721.38 | Yes | N/A | N/A | 2024-05-21 | 2024-06-25 | 36 | 26 | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2025-02-28 | 75 | 55 | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-03-05 | 1900-01-05 | 4 | 2025-03-05 | 2025-03-05 | 1 | 1 | 111 | 81 | 7 | 5 | 118 | 86 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-06 | 163 | 116 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-30 | 2024-08-29 | IOU Designed & Installed | N/A | No | N/A | 7167.06 | Unknown | Unknown | Unknown | 6.77 | 7160.29 | 122438 | 6604.47 | 7167.06 | -562.59 | Yes | N/A | N/A | 2023-06-29 | 2023-05-31 | Unknown | Unknown | 2023-05-31 | 2023-07-14 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | 2024-07-25 | 378 | 270 | Unknown | 2024-08-20 | Unknown | Unknown | 2024-08-29 | 2024-09-21 | 1900-01-23 | 17 | 2024-09-21 | 2024-09-16 | Unknown | Unknown | 378 | 270 | 69 | 50 | 447 | 320 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-28 | 252 | 181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-21 | 2023-02-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | -338.91 | -19.13 | Unknown | Unknown | -354 | 34.22 | 3981 | 987.55 | -338.91 | 1326.46 | Yes | N/A | N/A | 2022-06-21 | 2023-02-20 | 245 | 175 | 2023-02-20 | 2023-03-01 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | 2023-03-29 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | 2024-03-01 | 2024-01-05 | Unknown | Unknown | 245 | 175 | 11 | 9 | 256 | 184 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 168.05 | 168.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | -199 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | 2023-11-13 | IOU Designed & Installed | N/A | No | N/A | 4327.71 | 1319.69 | Unknown | 516.78 | 2.21 | 2489.03 | 3981 | 2039.96 | 4327.71 | -2287.75 | Yes | N/A | N/A | 2023-08-08 | 2023-09-11 | 35 | 25 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2023-11-13 | 60 | 42 | Unknown | 2023-10-18 | Unknown | Unknown | 2023-11-13 | 2023-11-14 | 1900-01-01 | 2 | 2023-11-14 | 2023-11-14 | 1 | 1 | 95 | 67 | 3 | 3 | 98 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-04 | -535 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-27 | 2023-10-16 | IOU Designed & Installed | N/A | No | N/A | 531.56 | 247.2 | Unknown | 117.92 | Unknown | 166.44 | 3961 | 153.83 | 531.56 | -377.73 | Yes | N/A | N/A | 2023-06-27 | 2023-08-31 | 66 | 48 | 2023-08-31 | 2023-08-31 | 1 | 1 | 2023-08-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | 2023-10-16 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2023-10-17 | 1900-01-01 | 2 | 2023-10-17 | 2023-10-17 | 1 | 1 | 113 | 81 | 4 | 4 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-06 | -197 | -141 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-30 | 2024-12-30 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | -1428.92 | 1061.76 | Unknown | Unknown | -3021 | 530.32 | Unknown | 3021.05 | -1428.92 | 4449.97 | Yes | N/A | N/A | 2024-12-30 | 2024-12-30 | 1 | 1 | 2024-12-30 | 2025-05-22 | 144 | 104 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | 2025-05-22 | 2025-05-22 | 1 | 1 | 2025-01-22 | 2025-05-23 | 1900-05-01 | 88 | 2025-05-23 | 2025-05-23 | 1 | 1 | 1 | 1 | 268 | 194 | 269 | 195 | Steps 2,3,5,6,7 | 120 | 86 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-06 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 31.8 | Unknown | Unknown | Unknown | Unknown | 31.8 | 3981 | 743.91 | 31.8 | 712.11 | Yes | N/A | N/A | 2024-04-24 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-04-24 | 70 | 50 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-07-23 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-07-25 | 1900-01-02 | 3 | 2024-07-25 | 2024-07-25 | 1 | 1 | 91 | 65 | 74 | 54 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | 48.1 | 48.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-13 | -664 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-21 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1708.48 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-02-03 | 1 | 1 | 2025-02-03 | 2025-02-21 | 19 | 15 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-02-26 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-03-21 | 1900-01-23 | 18 | 2025-03-21 | 2025-03-20 | Unknown | Unknown | 7 | 5 | 43 | 33 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R29/R45 | UG | IOU Design | Commercial | N/A | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-25 | 580 | 415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-28 | 2023-02-28 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | 102007.86 | 3843.07 | Unknown | Unknown | 401.59 | 97763.2 | 0 | 84951.99 | 102007.86 | -17055.87 | Yes | N/A | N/A | 2022-10-28 | 2023-02-28 | 124 | 88 | 2023-02-28 | 2024-08-06 | 526 | 376 | 2024-03-04 | 2024-07-17 | 25 | 19 | 2024-05-13 | 2024-08-20 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2025-01-29 | 115 | 83 | 2024-10-21 | 2025-03-27 | 1900-06-06 | 114 | 2025-03-27 | 2025-03-27 | 1 | 1 | 149 | 107 | 819 | 589 | 968 | 696 | Steps 2,3,5,6,7 | 320 | 230 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-31 | 503 | 360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-06 | 2023-05-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 261.32 | -27.37 | Unknown | Unknown | Unknown | 288.69 | 3981 | 2052.35 | 261.32 | 1791.03 | Yes | N/A | N/A | 2022-09-06 | 2023-07-31 | 329 | 235 | 2023-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | Unknown | Unknown | 2024-04-13 | Unknown | Unknown | Unknown | 2024-05-17 | Unknown | Unknown | 2024-05-17 | 2024-05-17 | 1 | 1 | 329 | 235 | 1 | 1 | 330 | 236 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | -579 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-15 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 1460.37 | 241.5 | Unknown | Unknown | Unknown | 1218.87 | Unknown | 1598.13 | 1460.37 | 137.76 | Yes | N/A | N/A | 2024-07-15 | 2024-05-31 | Unknown | Unknown | 2024-05-31 | 2024-07-16 | 47 | 33 | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-10-18 | 96 | 70 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-10-21 | 1900-01-03 | 2 | 2024-10-21 | 2024-10-21 | 1 | 1 | 96 | 70 | 52 | 36 | 148 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-07 | -206 | -148 | No | 2023-03-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2024-02-09 | IOU Designed & Installed | N/A | Yes | 315 | 1202.61 | 657.67 | Unknown | 41.38 | 1.46 | 502.1 | 3241 | 440.06 | 1202.61 | -762.55 | Yes | N/A | N/A | 2023-03-08 | 2024-01-17 | 316 | 226 | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | 2024-02-09 | 339 | 243 | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-02-14 | 1900-01-05 | 4 | 2024-02-14 | 2024-02-14 | 1 | 1 | 655 | 469 | 7 | 5 | 662 | 474 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | -546 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1772.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-08 | 2025-04-08 | 1 | 1 | 2025-04-08 | 2025-04-08 | 1 | 1 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-06-03 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-18 | 1900-01-15 | 12 | 2025-06-18 | 2025-06-18 | 1 | 1 | 58 | 42 | 18 | 14 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | LAGUNA NIGUEL | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-15 | -50 | -37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3772.64 | Unknown | Unknown | Unknown | 41.08 | 3731.56 | 3981 | 452.52 | 3772.64 | -3320.12 | Yes | N/A | N/A | 2024-06-06 | 2024-06-06 | 1 | 1 | 2024-06-06 | 2024-06-06 | 1 | 1 | 2024-06-06 | Unknown | Unknown | Unknown | 2024-06-27 | 2024-11-12 | 139 | 99 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | 2024-11-26 | Unknown | Unknown | 2024-11-26 | 2024-11-26 | 1 | 1 | 1 | 1 | 141 | 101 | 142 | 102 | Steps 2,3,5,6,7 | 159 | 113 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-18 | -850 | -608 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | -8.26 | -6.85 | Unknown | Unknown | Unknown | -1.41 | 3981 | 153.75 | -8.26 | 162.01 | Yes | N/A | N/A | 2023-03-24 | 2023-04-26 | 34 | 24 | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-26 | 2023-07-17 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-06-21 | Unknown | Unknown | 2023-06-21 | 2023-06-21 | 1 | 1 | 117 | 83 | 1 | 1 | 118 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-16 | -83 | -60 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-08-03 | 2024-01-19 | IOU Designed & Installed | N/A | No | N/A | 94.64 | -5.11 | Unknown | Unknown | 17.48 | 82.27 | 0 | 892.6 | 94.64 | 797.96 | Yes | N/A | N/A | 2023-07-05 | 2023-04-20 | Unknown | Unknown | 2023-04-20 | 2023-08-03 | 106 | 76 | 2023-08-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-03 | 2024-01-19 | 170 | 122 | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-12-23 | 1900-12-05 | 242 | 2024-12-23 | 2024-12-23 | 1 | 1 | 170 | 122 | 447 | 319 | 617 | 441 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-23 | -99 | -72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-09-05 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 11379.57 | Unknown | Unknown | Unknown | -1088.53 | 12468.1 | Unknown | 1270.22 | 11379.57 | -10109.35 | Yes | N/A | N/A | 2024-08-20 | 2024-08-20 | 1 | 1 | 2024-08-20 | 2024-10-17 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | 2024-10-29 | 2025-04-15 | 1900-06-17 | 121 | 2025-04-15 | 2025-04-15 | 1 | 1 | 1 | 1 | 229 | 165 | 230 | 166 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 424.05 | 424.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-24 | -38 | -29 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-21 | 2023-07-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 7.92 | -7.05 | Unknown | Unknown | Unknown | 14.97 | 3981 | 1971.06 | 7.92 | 1963.14 | Yes | N/A | N/A | 2023-07-21 | 2023-07-27 | 7 | 5 | 2023-07-27 | 2023-07-27 | 1 | 1 | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2024-04-16 | 1 | 1 | 7 | 5 | 2 | 2 | 9 | 7 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-15 | -286 | -205 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-17 | 2025-01-17 | 2025-04-04 | IOU Designed & Installed | N/A | No | N/A | 42632.79 | 11233.57 | Unknown | 887.58 | Unknown | 30511.64 | Unknown | 7258.91 | 42632.79 | -35373.88 | Yes | N/A | N/A | 2025-01-17 | 2025-02-06 | 21 | 15 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-04 | 1899-12-31 | 1 | 2025-04-04 | 2025-04-04 | 1 | 1 | 21 | 15 | 2 | 2 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FB 1048-J1 MDWOOD PA5A PH3B | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-08 | 586 | 419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-24 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 5342.28 | -29.41 | Unknown | Unknown | Unknown | 5371.69 | 3981 | Not available | 5342.28 | Unknown | Yes | N/A | N/A | 2024-01-23 | 2023-12-13 | Unknown | Unknown | 2023-12-13 | 2024-01-31 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | 2024-07-11 | 2024-07-16 | 1900-01-05 | 4 | 2024-07-16 | 2024-07-16 | 1 | 1 | 0 | 0 | 57 | 41 | 57 | 41 | Steps 2,3,5,6,7 | 84 | 60 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-09 | 184 | 131 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | 2024-07-17 | 2025-04-30 | IOU Designed & Installed | N/A | No | N/A | 94094.84 | 39499.8 | Unknown | Unknown | 3382.84 | 51212.2 | 3981 | 1177.26 | 94094.84 | -92917.58 | Yes | N/A | N/A | 2024-07-01 | 2024-05-29 | Unknown | Unknown | 2024-05-29 | 2024-07-17 | 50 | 36 | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2025-04-30 | 288 | 206 | Unknown | 2025-04-29 | Unknown | Unknown | 2025-04-30 | 2025-05-12 | 1900-01-12 | 9 | 2025-05-12 | 2025-05-12 | 1 | 1 | 288 | 206 | 64 | 46 | 352 | 252 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SANTA YSABEL | N/A | 35.05 | 35.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-27 | -520 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-07-11 | 2024-01-03 | IOU Designed & Installed | N/A | No | N/A | 1860.87 | 928.64 | Unknown | 222.28 | -1101 | 1810.95 | 3981 | 1896.46 | 1860.87 | 35.59 | Yes | N/A | N/A | 2023-06-30 | 2023-07-11 | 12 | 8 | 2023-07-11 | 2023-07-11 | 1 | 1 | 2023-07-11 | 2023-08-24 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | 2024-01-03 | 133 | 95 | Unknown | 2023-12-14 | Unknown | Unknown | 2024-01-03 | 2024-01-24 | 1900-01-21 | 16 | 2024-01-24 | 2024-01-24 | 1 | 1 | 190 | 136 | 24 | 18 | 214 | 154 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | -572 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-19 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 1279.44 | Unknown | Unknown | Unknown | 12.68 | 1266.76 | 3981 | 1210.59 | 1279.44 | -68.85 | Yes | N/A | N/A | 2024-06-17 | 2024-07-15 | 29 | 21 | 2024-07-15 | 2024-07-15 | 1 | 1 | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-10-23 | 101 | 73 | Unknown | 2024-10-21 | Unknown | Unknown | 2024-10-23 | 2024-11-05 | 1900-01-13 | 10 | 2024-11-05 | 2024-11-05 | 1 | 1 | 130 | 94 | 16 | 12 | 146 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 31.2 | 31.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | -378 | -271 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-01 | 2024-06-28 | IOU Designed & Installed | N/A | No | N/A | 40702.56 | 1830.26 | Unknown | Unknown | 38.53 | 38833.77 | Unknown | 15173.46 | 40702.56 | -25529.1 | Yes | N/A | N/A | 2024-02-01 | 2024-02-01 | 1 | 1 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | 2024-06-24 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-08-16 | 1900-02-18 | 36 | 2024-08-16 | 2024-08-16 | 1 | 1 | 1 | 1 | 74 | 54 | 75 | 55 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-04 | 65 | 48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 839.33 | -16.87 | Unknown | Unknown | Unknown | 856.2 | Unknown | 434.59 | 839.33 | -404.74 | Yes | N/A | N/A | 2024-08-20 | 2024-07-03 | Unknown | Unknown | 2024-07-03 | 2024-09-11 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-12-02 | 97 | 69 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | 2025-05-08 | 2025-05-08 | 1 | 1 | 0 | 0 | 169 | 121 | 169 | 121 | Steps 2,3,5,6,7 | 82 | 58 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-07 | -271 | -194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | -345.5 | Unknown | Unknown | Unknown | -993 | 647.5 | Unknown | 992.77 | -345.5 | 1338.27 | Yes | N/A | N/A | 2024-06-12 | 2024-07-11 | 30 | 22 | 2024-07-11 | 2024-07-11 | 1 | 1 | 2024-07-11 | 2024-07-15 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-08-09 | 1 | 1 | 35 | 25 | 2 | 2 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-06 | -645 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-04-08 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | 1318.27 | -26.49 | Unknown | Unknown | Unknown | 1344.76 | 3981 | 1637.77 | 1318.27 | 319.5 | Yes | N/A | N/A | 2025-03-26 | 2025-04-04 | 10 | 8 | 2025-04-04 | 2025-04-04 | 1 | 1 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-25 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-30 | 1900-02-04 | 26 | 2025-05-30 | 2025-05-30 | 1 | 1 | 28 | 22 | 38 | 28 | 66 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | -119 | -86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-04-17 | 2024-07-15 | IOU Designed & Installed | N/A | No | N/A | 2531.9 | Unknown | Unknown | Unknown | 55.96 | 2475.94 | 3981 | 716.26 | 2531.9 | -1815.64 | Yes | N/A | N/A | 2024-01-11 | 2024-04-17 | 98 | 70 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-11-06 | 1900-04-24 | 83 | 2024-11-06 | 2024-08-02 | Unknown | Unknown | 98 | 70 | 115 | 83 | 213 | 153 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-08 | 27 | 20 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-08 | 2025-03-14 | IOU Designed & Installed | N/A | No | N/A | 22913.05 | 2603.74 | Unknown | 329.15 | 180.08 | 19800.08 | Unknown | 21297.84 | 22913.05 | -1615.21 | Yes | N/A | N/A | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | 2025-02-21 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-02-27 | 15 | 11 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-05-05 | 1900-02-21 | 37 | 2025-05-05 | 2025-05-05 | 1 | 1 | 1 | 1 | 182 | 130 | 183 | 131 | Steps 2,3,5,6,7 | 6 | 4 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-06-21 | -437 | -313 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | 2024-04-04 | IOU Designed & Installed | N/A | No | N/A | 794.19 | -5.67 | Unknown | Unknown | 14.59 | 785.27 | 3981 | 1094.5 | 794.19 | 300.31 | Yes | N/A | N/A | 2023-11-06 | 2023-08-25 | Unknown | Unknown | 2023-08-25 | 2023-11-27 | 95 | 67 | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2024-04-04 | 130 | 94 | Unknown | 2024-03-29 | Unknown | Unknown | 2024-04-04 | 2024-04-10 | 1900-01-06 | 5 | 2024-04-10 | 2024-04-10 | 1 | 1 | 130 | 94 | 103 | 73 | 233 | 167 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | -548 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-07-18 | 2023-07-20 | IOU Designed & Installed | N/A | No | N/A | 380.45 | -13.48 | Unknown | Unknown | Unknown | 393.93 | Unknown | 855.66 | 380.45 | 475.21 | Yes | N/A | N/A | 2023-07-12 | 2023-07-18 | 7 | 5 | 2023-07-18 | 2023-07-18 | 1 | 1 | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-07-20 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-08-23 | 1900-02-03 | 25 | 2023-08-23 | 2023-08-23 | 1 | 1 | 10 | 8 | 37 | 27 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 208 | 208 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-13 | -361 | -258 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-17 | 2023-03-08 | 2023-09-07 | IOU Designed & Installed | N/A | No | N/A | 2974.02 | 382.68 | Unknown | Unknown | Unknown | 2591.34 | Unknown | 672.68 | 2974.02 | -2301.34 | Yes | N/A | N/A | 2023-01-17 | 2023-03-08 | 51 | 37 | 2023-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | 2023-09-07 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | 2023-10-18 | 1900-02-10 | 30 | 2023-10-18 | 2023-10-18 | 1 | 1 | 235 | 169 | 43 | 31 | 278 | 200 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-31 | 112 | 81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2023-10-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 390.73 | -15.62 | Unknown | Unknown | Unknown | 406.35 | 7962 | 591.2 | 390.73 | 200.47 | Yes | N/A | N/A | 2023-10-24 | 2023-10-06 | Unknown | Unknown | 2023-10-06 | 2023-11-15 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2023-11-21 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | Unknown | Unknown | 2024-02-16 | 2023-12-21 | Unknown | Unknown | 7 | 5 | 41 | 29 | 48 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 122 | 122 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | -551 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2023-05-25 | 2023-08-28 | IOU Designed & Installed | N/A | No | N/A | 1112.66 | -13.24 | Unknown | Unknown | 139.87 | 986.03 | 3981 | 726.78 | 1112.66 | -385.88 | Yes | N/A | N/A | 2023-05-25 | 2023-04-05 | Unknown | Unknown | 2023-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | 2023-08-28 | 64 | 46 | Unknown | 2023-08-24 | Unknown | Unknown | 2023-08-28 | 2024-10-08 | 1901-02-11 | 292 | 2024-10-08 | 2023-09-11 | Unknown | Unknown | 64 | 46 | 408 | 292 | 472 | 338 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 52 | 52 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-04 | -443 | -318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2024-08-29 | IOU Designed & Installed | N/A | No | N/A | 5224.48 | 767.56 | Unknown | 297.29 | 26.85 | 4132.78 | 3981 | 1422.56 | 5224.48 | -3801.92 | Yes | N/A | N/A | 2024-04-11 | 2024-01-03 | Unknown | Unknown | 2024-01-03 | 2024-05-03 | 122 | 88 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-08-29 | 119 | 85 | Unknown | 2024-08-26 | Unknown | Unknown | 2024-08-29 | 2024-09-17 | 1900-01-19 | 14 | 2024-09-17 | 2024-09-17 | 1 | 1 | 119 | 85 | 143 | 103 | 262 | 188 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-28 | -639 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-13 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | 821.38 | -18.28 | Unknown | Unknown | Unknown | 839.66 | Unknown | 1085.06 | 821.38 | 263.68 | Yes | N/A | N/A | 2024-05-09 | 2024-05-13 | 5 | 3 | 2024-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-05-14 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-06-27 | 1900-02-13 | 33 | 2024-06-27 | 2024-06-27 | 1 | 1 | 7 | 5 | 46 | 34 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 211.15 | 211.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-13 | -127 | -92 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | 2024-07-31 | IOU Designed & Installed | N/A | No | N/A | 715.72 | Unknown | Unknown | Unknown | 18.44 | 697.28 | 3981 | 1379.65 | 715.72 | 663.93 | Yes | N/A | N/A | 2023-11-29 | 2023-11-29 | 1 | 1 | 2023-11-29 | 2023-11-29 | 1 | 1 | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2024-07-31 | 246 | 176 | Unknown | 2024-07-17 | Unknown | Unknown | 2024-07-31 | 2024-08-08 | 1900-01-08 | 7 | 2024-08-08 | 2024-08-08 | 1 | 1 | 247 | 177 | 11 | 9 | 258 | 186 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-17 | 159 | 114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | 2024-09-20 | IOU Designed & Installed | N/A | No | N/A | 7192.55 | Unknown | Unknown | Unknown | Unknown | 7192.55 | Unknown | 1903.24 | 7192.55 | -5289.31 | Yes | N/A | N/A | 2024-07-03 | 2024-06-05 | Unknown | Unknown | 2024-06-05 | 2024-07-30 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | 2024-09-20 | 2024-10-23 | 1900-02-02 | 24 | 2024-10-23 | 2024-10-23 | 1 | 1 | 0 | 0 | 91 | 65 | 91 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2023-12-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 816.09 | -8.01 | Unknown | Unknown | Unknown | 824.1 | Unknown | 249.6 | 816.09 | -566.49 | Yes | N/A | N/A | 2023-12-15 | 2023-12-15 | 1 | 1 | 2023-12-15 | 2024-03-05 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-12 | 9 | 7 | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-04-24 | 1 | 1 | 1 | 1 | 92 | 66 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | -549 | -394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-07-03 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 671.37 | -12.92 | Unknown | Unknown | Unknown | 684.29 | 3981 | 1304.45 | 671.37 | 633.08 | Yes | N/A | N/A | 2024-06-13 | 2024-07-03 | 21 | 15 | 2024-07-03 | 2024-07-03 | 1 | 1 | 2024-07-03 | Unknown | Unknown | Unknown | 2024-07-03 | 2024-07-19 | 17 | 13 | 2024-07-03 | 2024-10-28 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-05 | 1900-01-08 | 7 | 2024-11-05 | 2024-11-05 | 1 | 1 | 139 | 99 | 28 | 22 | 167 | 121 | Steps 2,3,5,6,7 | 16 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 22.05 | 22.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-25 | -440 | -315 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-27 | 2024-10-28 | 2024-11-13 | IOU Designed & Installed | N/A | No | N/A | 38.87 | Unknown | Unknown | Unknown | Unknown | 38.87 | 3981 | 901.98 | 38.87 | 863.11 | Yes | N/A | N/A | 2024-10-27 | 2024-10-21 | Unknown | Unknown | 2024-10-21 | 2024-10-28 | 8 | 6 | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-13 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-12-13 | 1900-01-30 | 23 | 2024-12-13 | 2024-12-12 | Unknown | Unknown | 17 | 13 | 39 | 29 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | 45 | 45 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-11 | 698 | 499 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1148.77 | -19.38 | Unknown | Unknown | 21.75 | 1146.4 | 3981 | 1327.19 | 1148.77 | 178.42 | Yes | N/A | N/A | 2023-11-13 | 2023-11-20 | 8 | 6 | 2023-11-20 | 2023-11-27 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2023-11-28 | 9 | 7 | 2023-11-27 | 2023-05-02 | Unknown | Unknown | Unknown | 2023-12-15 | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-01-10 | Unknown | Unknown | 8 | 6 | 17 | 13 | 25 | 19 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 8.1 | 8.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | -349 | -250 | No | 2024-04-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-05-31 | Unknown | IOU Designed & Installed | N/A | Yes | 314 | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1107.93 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-11 | 2025-02-19 | 315 | 225 | 2025-02-19 | 2024-05-31 | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | 2025-04-01 | 2025-03-27 | Unknown | Unknown | 315 | 225 | 0 | 0 | 315 | 225 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | -172 | -124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1512.01 | 1499.3 | Unknown | 183.6 | -3773 | 578.09 | Unknown | 3773.45 | -1512.01 | 5285.46 | Yes | N/A | N/A | 2023-03-10 | 2023-04-25 | 47 | 33 | 2023-04-25 | 2023-09-05 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | Unknown | Unknown | Unknown | 2023-09-05 | 2023-09-05 | 1 | 1 | Unknown | 2023-09-05 | Unknown | Unknown | 2023-09-05 | 2023-09-05 | 1 | 1 | 47 | 33 | 136 | 98 | 183 | 131 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-20 | -346 | -248 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-11-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 97.19 | -1.25 | Unknown | Unknown | Unknown | 98.44 | Unknown | 1719.59 | 97.19 | 1622.4 | Yes | N/A | N/A | 2023-10-30 | 2023-11-27 | 29 | 21 | 2023-11-27 | 2023-11-30 | 4 | 4 | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2024-10-09 | 1 | 1 | 29 | 21 | 5 | 5 | 34 | 26 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-09 | -592 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | 2024-03-08 | IOU Designed & Installed | N/A | No | N/A | -13.38 | -14.24 | Unknown | Unknown | Unknown | 0.86 | 3941 | 499.18 | -13.38 | 512.56 | Yes | N/A | N/A | 2023-12-12 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | 2023-12-12 | 26 | 18 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2024-03-08 | 88 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-03-18 | 1900-01-10 | 7 | 2024-03-18 | 2024-03-27 | 10 | 8 | 88 | 64 | 47 | 33 | 135 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | -507 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | -8.3 | -6 | Unknown | Unknown | Unknown | -2.3 | Unknown | 98.66 | -8.3 | 106.96 | Yes | N/A | N/A | 2023-03-23 | 2023-03-31 | 9 | 7 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | Unknown | Unknown | 2023-09-19 | 2023-09-19 | 1 | 1 | 9 | 7 | 1 | 1 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | Rancho Santa Fe | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-03 | -270 | -194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-08-17 | 2023-10-21 | IOU Designed & Installed | N/A | No | N/A | -740.78 | 1979.28 | Unknown | 707.52 | -4278 | 850.42 | Unknown | 4277.9 | -740.78 | 5018.68 | Yes | N/A | N/A | 2023-08-10 | 2023-08-10 | 1 | 1 | 2023-08-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-21 | 2023-11-07 | 1900-01-17 | 12 | 2023-11-07 | 2023-11-07 | 1 | 1 | 1 | 1 | 19 | 13 | 20 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 144 | 144 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-18 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-06-03 | 2024-08-13 | IOU Designed & Installed | N/A | No | N/A | 17.03 | Unknown | Unknown | Unknown | Unknown | 17.03 | 3981 | 1313.08 | 17.03 | 1296.05 | Yes | N/A | N/A | 2024-05-21 | 2024-05-13 | Unknown | Unknown | 2024-05-13 | 2024-06-03 | 22 | 16 | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-08-13 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-08-21 | 1900-01-08 | 7 | 2024-08-21 | 2024-08-19 | Unknown | Unknown | 72 | 52 | 31 | 23 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | 897 | 641 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 130219.82 | 40693.98 | Unknown | 8334.85 | 1703.62 | 79487.37 | 1516747 | 85088.2 | 130219.82 | -45131.62 | Yes | N/A | N/A | 2023-05-08 | 2023-05-18 | 11 | 9 | 2023-05-18 | 2023-11-01 | 168 | 120 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2025-04-04 | 521 | 373 | Unknown | 2025-03-04 | Unknown | Unknown | Unknown | 2025-06-16 | Unknown | Unknown | 2025-06-16 | 2025-06-16 | 1 | 1 | 532 | 382 | 169 | 121 | 701 | 503 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-13 | -642 | -460 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-18 | 2025-04-30 | IOU Designed & Installed | N/A | No | N/A | -254.63 | Unknown | Unknown | Unknown | -1231 | 976.37 | Unknown | 1231.32 | -254.63 | 1485.95 | Yes | N/A | N/A | 2025-02-27 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-03-18 | 22 | 16 | 2025-03-18 | 2025-03-21 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-04-30 | 7 | 5 | Unknown | 2025-04-25 | Unknown | Unknown | 2025-04-30 | 2025-05-12 | 1900-01-12 | 9 | 2025-05-12 | 2025-05-12 | 1 | 1 | 11 | 9 | 36 | 26 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | 16.13 | 16.13 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-06 | 211 | 151 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-07-09 | 2025-05-05 | IOU Designed & Installed | N/A | No | N/A | -8410.73 | 12295.59 | Unknown | Unknown | -36934 | 16227.68 | 0 | 35314.95 | -8410.73 | 43725.68 | Yes | N/A | N/A | 2024-02-28 | 2024-04-01 | 34 | 24 | 2024-04-01 | 2024-11-25 | 239 | 171 | 2024-08-27 | 2024-08-28 | 2 | 2 | 2025-04-03 | 2025-04-04 | 2 | 2 | 2024-11-25 | 2025-03-19 | 115 | 83 | 2024-12-03 | 2025-04-03 | 122 | 88 | 2025-05-05 | 2025-05-05 | 1899-12-31 | 1 | 2025-05-05 | 2025-05-05 | 1 | 1 | 151 | 109 | 365 | 263 | 516 | 372 | Steps 2,3,5,6,7 | 326 | 234 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-20 | -616 | -441 | No | 2024-11-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-12-04 | 2025-01-02 | IOU Designed & Installed | N/A | Yes | 9 | 839.63 | -17.11 | Unknown | Unknown | Unknown | 856.74 | Unknown | 1890.33 | 839.63 | 1050.7 | Yes | N/A | N/A | 2024-11-25 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-12-04 | 22 | 16 | 2024-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | 2025-01-02 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-02-11 | 1900-02-09 | 29 | 2025-02-11 | 2025-02-11 | 1 | 1 | 30 | 22 | 64 | 46 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-05 | -548 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2024-11-01 | IOU Designed & Installed | N/A | No | N/A | 1941.48 | Unknown | Unknown | Unknown | 21.9 | 1919.58 | 3981 | 1270.48 | 1941.48 | -671 | Yes | N/A | N/A | 2024-07-02 | 2024-09-12 | 73 | 53 | 2024-09-12 | 2024-09-12 | 1 | 1 | 2024-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | 2024-11-01 | 51 | 37 | Unknown | 2024-11-01 | Unknown | Unknown | 2024-11-01 | 2024-12-04 | 1900-02-02 | 24 | 2024-12-04 | 2024-12-04 | 1 | 1 | 124 | 90 | 36 | 26 | 160 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -524 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-25 | 2024-11-12 | IOU Designed & Installed | N/A | No | N/A | 22.99 | Unknown | Unknown | Unknown | Unknown | 22.99 | 3981 | 1553.1 | 22.99 | 1530.11 | Yes | N/A | N/A | 2024-09-23 | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-09-25 | 21 | 15 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-11-12 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2024-12-12 | 1900-01-30 | 23 | 2024-12-12 | 2025-02-27 | 78 | 56 | 49 | 35 | 130 | 94 | 179 | 129 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-11 | -405 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-06-19 | 2023-08-10 | IOU Designed & Installed | N/A | No | N/A | 5087.94 | 1624.52 | Unknown | 2128.36 | Unknown | 1335.06 | 3981 | 1186.72 | 5087.94 | -3901.22 | Yes | N/A | N/A | 2023-03-13 | 2023-06-19 | 99 | 71 | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | 2023-08-10 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-10-03 | 1900-02-23 | 39 | 2023-10-03 | 2023-10-03 | 1 | 1 | 152 | 110 | 56 | 40 | 208 | 150 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-08 | 70 | 51 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-04-04 | 2024-04-03 | IOU Designed & Installed | N/A | No | N/A | 324.09 | -10.89 | Unknown | Unknown | Unknown | 334.98 | 3885 | 879.95 | 324.09 | 555.86 | Yes | N/A | N/A | 2023-03-28 | 2023-04-04 | 8 | 6 | 2023-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-04 | 2024-04-03 | 366 | 262 | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-04-18 | 1900-01-15 | 12 | 2024-04-18 | 2024-04-18 | 1 | 1 | 374 | 268 | 17 | 13 | 391 | 281 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-25 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-02 | 2025-05-30 | IOU Designed & Installed | N/A | No | N/A | 155.4 | Unknown | Unknown | Unknown | Unknown | 155.4 | 3981 | 1601.82 | 155.4 | 1446.42 | Yes | N/A | N/A | 2024-12-02 | 2024-12-02 | 1 | 1 | 2024-12-02 | 2024-12-02 | 1 | 1 | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2025-05-30 | 180 | 130 | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-26 | 1900-01-27 | 20 | 2025-06-26 | 2025-06-26 | 1 | 1 | 181 | 131 | 30 | 22 | 211 | 153 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | -473 | -338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | 2024-10-09 | IOU Designed & Installed | N/A | No | N/A | 432.22 | -7.6 | Unknown | Unknown | Unknown | 439.82 | 3981 | 1470.67 | 432.22 | 1038.45 | Yes | N/A | N/A | 2024-04-24 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-06-21 | 121 | 87 | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-10-09 | 111 | 79 | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-10-17 | 1900-01-08 | 7 | 2024-10-17 | 2024-10-16 | Unknown | Unknown | 111 | 79 | 130 | 94 | 241 | 173 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-30 | -232 | -167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-03-31 | IOU Designed & Installed | N/A | No | N/A | -4.54 | -13.36 | Unknown | Unknown | Unknown | 8.82 | Unknown | 341 | -4.54 | 345.54 | Yes | N/A | N/A | 2023-03-21 | 2023-03-21 | 1 | 1 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-03-31 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | 2023-06-12 | 1900-03-14 | 52 | 2023-06-12 | 2023-06-12 | 1 | 1 | 12 | 10 | 75 | 53 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 15.05 | 15.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -395 | -282 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 381.54 | Unknown | Unknown | Unknown | 2.37 | 379.17 | 3981 | 1318.64 | 381.54 | 937.1 | Yes | N/A | N/A | 2023-12-01 | 2023-12-04 | 4 | 2 | 2023-12-04 | 2024-01-17 | 45 | 33 | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-10-28 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-04 | 1900-01-07 | 6 | 2024-11-04 | 2024-10-31 | Unknown | Unknown | 12 | 8 | 53 | 39 | 65 | 47 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-11 | -553 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-01 | 2024-04-01 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 162.7 | Unknown | Unknown | Unknown | -776.43 | 939.13 | Unknown | 783.95 | 162.7 | 621.25 | Yes | N/A | N/A | 2024-04-01 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2025-03-06 | 379 | 271 | 2025-03-06 | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | 2024-07-22 | 69 | 49 | Unknown | 2024-07-10 | Unknown | Unknown | 2024-07-22 | 2024-08-07 | 1900-01-16 | 13 | 2024-08-07 | 2024-08-07 | 1 | 1 | 69 | 49 | 397 | 285 | 466 | 334 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 66.4 | 66.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | 332 | 239 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-06-07 | 2024-11-06 | IOU Designed & Installed | N/A | No | N/A | 538.64 | -10.2 | Unknown | Unknown | Unknown | 548.84 | 3981 | 1403.06 | 538.64 | 864.42 | Yes | N/A | N/A | 2024-06-07 | 2024-04-25 | Unknown | Unknown | 2024-04-25 | 2024-06-07 | 44 | 32 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-11-06 | 153 | 109 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-11-15 | 1900-01-09 | 8 | 2024-11-15 | 2025-02-27 | 105 | 75 | 153 | 109 | 159 | 115 | 312 | 224 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 148.1 | 148.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-19 | -189 | -136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 662.76 | 195.22 | Unknown | 72.9 | 6.52 | 388.12 | 3981 | 2501.87 | 662.76 | 1839.11 | Yes | N/A | N/A | 2023-10-16 | 2023-11-02 | 18 | 14 | 2023-11-02 | 2023-11-06 | 5 | 3 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 18 | 14 | 6 | 4 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | -474 | -340 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-13 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 1416.83 | -28.46 | Unknown | Unknown | Unknown | 1445.29 | 3981 | 1248.18 | 1416.83 | -168.65 | Yes | N/A | N/A | 2025-01-13 | 2025-01-07 | Unknown | Unknown | 2025-01-07 | 2025-01-13 | 7 | 5 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-04-01 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-21 | 1900-01-20 | 15 | 2025-04-21 | 2025-04-21 | 1 | 1 | 79 | 57 | 29 | 21 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-02 | 569 | 408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-03-18 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 32263.27 | 4169.29 | Unknown | 294.04 | 20.54 | 27779.4 | 0 | 35540.92 | 32263.27 | 3277.65 | Yes | N/A | N/A | 2024-01-08 | 2024-01-08 | 1 | 1 | 2024-01-08 | 2024-12-12 | 340 | 244 | 2024-03-22 | 2024-10-18 | 38 | 28 | 2024-11-22 | 2024-12-11 | 20 | 14 | 2024-12-12 | 2025-01-24 | 44 | 32 | Unknown | 2025-01-28 | Unknown | Unknown | 2025-02-05 | 2025-02-24 | 1900-01-19 | 14 | 2025-02-24 | 2025-02-21 | Unknown | Unknown | 83 | 61 | 380 | 272 | 463 | 333 | Steps 2,3,5,6,7 | 265 | 189 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | -705 | -504 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-10 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | -997.47 | -14.54 | Unknown | Unknown | -990 | 7.07 | Unknown | 989.55 | -997.47 | 1987.02 | Yes | N/A | N/A | 2023-07-10 | 2023-07-11 | 2 | 2 | 2023-07-11 | 2023-07-11 | 1 | 1 | 2023-07-11 | 2023-07-13 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | 2023-07-26 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-07-27 | 1900-01-01 | 2 | 2023-07-27 | 2023-07-27 | 1 | 1 | 19 | 15 | 4 | 4 | 23 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-20 | -278 | -200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | 2022-08-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.4 | -4.79 | Unknown | Unknown | Unknown | -0.61 | Unknown | 98.66 | -5.4 | 104.06 | Yes | N/A | N/A | 2022-08-31 | 2023-03-30 | 212 | 152 | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2023-10-16 | 1 | 1 | 212 | 152 | 1 | 1 | 213 | 153 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-10 | -207 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-31 | 2024-05-31 | IOU Designed & Installed | N/A | No | N/A | 1064.06 | -27 | Unknown | Unknown | Unknown | 1091.06 | 3981 | 1061.48 | 1064.06 | -2.58 | Yes | N/A | N/A | 2024-05-17 | 2024-05-21 | 5 | 3 | 2024-05-21 | 2024-05-31 | 11 | 9 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-05-31 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-06-17 | 1900-01-17 | 12 | 2024-06-17 | 2024-06-17 | 1 | 1 | 6 | 4 | 30 | 22 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | -312 | -224 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1376.78 | 2186.81 | Unknown | 572.65 | -5031 | 894.76 | Unknown | 5031.19 | -1376.78 | 6407.97 | Yes | N/A | N/A | 2023-03-10 | 2023-03-31 | 22 | 16 | 2023-03-31 | 2023-04-18 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | Unknown | Unknown | Unknown | 2023-04-18 | 2023-04-18 | 1 | 1 | Unknown | 2023-04-18 | Unknown | Unknown | 2023-04-18 | 2023-04-18 | 1 | 1 | 22 | 16 | 21 | 15 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-12 | -565 | -405 | No | 2024-10-30 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | 2025-01-10 | IOU Designed & Installed | N/A | Yes | 44 | 1523.07 | 315.42 | Unknown | Unknown | Unknown | 1207.65 | 3981 | 1807.05 | 1523.07 | 283.98 | Yes | N/A | N/A | 2024-10-30 | 2024-12-18 | 50 | 36 | 2024-12-18 | 2024-10-30 | Unknown | Unknown | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2025-01-10 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-02-24 | 1900-02-14 | 32 | 2025-02-24 | 2025-02-24 | 1 | 1 | 123 | 89 | 47 | 33 | 170 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-17 | -184 | -133 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 835.34 | 85.52 | Unknown | 34.76 | 9.27 | 705.79 | 0 | 913.81 | 835.34 | 78.47 | Yes | N/A | N/A | 2023-04-07 | 2023-04-10 | 4 | 2 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2024-04-16 | 1 | 1 | 4 | 2 | 1 | 1 | 5 | 3 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-06 | -455 | -326 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-15 | 2023-07-15 | 2023-08-30 | IOU Designed & Installed | N/A | No | N/A | 392.99 | 241.68 | Unknown | Unknown | Unknown | 151.31 | Unknown | 496.45 | 392.99 | 103.46 | Yes | N/A | N/A | 2023-07-15 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-15 | 2023-08-30 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-12-07 | 1900-04-09 | 72 | 2023-12-07 | 2023-12-07 | 1 | 1 | 47 | 33 | 101 | 73 | 148 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 13.4 | 13.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | -515 | -368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | 2023-04-24 | IOU Designed & Installed | N/A | No | N/A | 1175.16 | -9.79 | Unknown | Unknown | Unknown | 1184.95 | 3981 | 325.18 | 1175.16 | -849.98 | Yes | N/A | N/A | 2023-03-01 | 2023-03-06 | 6 | 4 | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-06 | 2023-04-24 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | 2023-08-09 | 1900-04-17 | 78 | 2023-08-09 | 2023-08-09 | 1 | 1 | 56 | 40 | 109 | 79 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-16 | -642 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2023-08-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 333.16 | -21.19 | Unknown | Unknown | Unknown | 354.35 | Unknown | 1723.56 | 333.16 | 1390.4 | Yes | N/A | N/A | 2023-08-01 | 2023-08-01 | 1 | 1 | 2023-08-01 | 2023-10-26 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 1 | 1 | 88 | 64 | 89 | 65 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | -584 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-29 | 2023-07-11 | IOU Designed & Installed | N/A | No | N/A | 1299.32 | -30.84 | Unknown | Unknown | Unknown | 1330.16 | Unknown | 270.38 | 1299.32 | -1028.94 | Yes | N/A | N/A | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | 2023-07-11 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | 2023-07-18 | 1900-01-07 | 6 | 2023-07-18 | 2023-07-18 | 1 | 1 | 14 | 10 | 10 | 8 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-09 | -412 | -295 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-02-28 | 2024-07-17 | IOU Designed & Installed | N/A | No | N/A | 299.59 | Unknown | Unknown | Unknown | 11.79 | 287.8 | 3981 | 1479.07 | 299.59 | 1179.48 | Yes | N/A | N/A | 2024-02-23 | 2024-03-21 | 28 | 20 | 2024-03-21 | 2024-04-05 | 16 | 12 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-07-17 | 104 | 74 | Unknown | 2024-07-01 | Unknown | Unknown | 2024-07-17 | 2024-09-23 | 1900-03-09 | 49 | 2024-09-23 | 2024-09-23 | 1 | 1 | 132 | 94 | 86 | 62 | 218 | 156 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | -332 | -238 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 26 | Unknown | Unknown | Unknown | Unknown | 26 | Unknown | 1529.38 | 26 | 1503.38 | Yes | N/A | N/A | 2024-11-14 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-11-14 | 7 | 5 | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-11-14 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-12-11 | 1900-01-27 | 20 | 2024-12-11 | 2024-12-11 | 1 | 1 | 1 | 1 | 36 | 26 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 72 | 72 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-28 | -436 | -313 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | 2024-01-02 | IOU Designed & Installed | N/A | No | N/A | 1803.79 | 257.62 | Unknown | Unknown | 29.31 | 1516.86 | 3941 | 644.56 | 1803.79 | -1159.23 | Yes | N/A | N/A | 2023-07-17 | 2023-04-03 | Unknown | Unknown | 2023-04-03 | 2023-08-11 | 131 | 95 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2024-01-02 | 145 | 103 | Unknown | 2023-12-18 | Unknown | Unknown | 2024-01-02 | 2024-01-17 | 1900-01-15 | 12 | 2024-01-17 | 2024-01-17 | 1 | 1 | 145 | 103 | 148 | 108 | 293 | 211 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 152 | 109 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-10-18 | 2023-11-16 | IOU Designed & Installed | N/A | No | N/A | 31.66 | -8.14 | Unknown | Unknown | 31.08 | 8.72 | 0 | 1417.05 | 31.66 | 1385.39 | Yes | N/A | N/A | 2023-10-18 | 2025-01-22 | 463 | 331 | 2025-01-22 | 2023-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2023-10-26 | 3 | 3 | 2023-10-23 | 2023-11-13 | 22 | 16 | Unknown | 2023-10-31 | Unknown | Unknown | 2023-11-16 | 2024-07-23 | 1900-09-07 | 179 | 2024-07-23 | 2023-11-22 | Unknown | Unknown | 485 | 347 | 254 | 182 | 739 | 529 | Steps 2,3,5,6,7 | 3 | 3 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-09 | -444 | -317 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-15 | 2023-10-15 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | 1185.08 | 245.01 | Unknown | 36.6 | Unknown | 903.47 | Unknown | 864.3 | 1185.08 | -320.78 | Yes | N/A | N/A | 2023-10-15 | 2023-10-15 | 1 | 0 | 2023-10-15 | 2023-10-15 | 1 | 0 | 2023-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-15 | 2024-03-14 | 152 | 109 | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-03-22 | 1900-01-08 | 7 | 2024-03-22 | 2024-03-22 | 1 | 1 | 153 | 109 | 11 | 8 | 164 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-09 | -446 | -319 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-02 | 2024-08-06 | IOU Designed & Installed | N/A | No | N/A | 20.28 | Unknown | Unknown | Unknown | Unknown | 20.28 | 3981 | 1532.34 | 20.28 | 1512.06 | Yes | N/A | N/A | 2024-08-02 | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-08-02 | 61 | 45 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-08-06 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-26 | 1900-01-20 | 15 | 2024-08-26 | 2024-08-20 | Unknown | Unknown | 5 | 3 | 82 | 60 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-02 | -110 | -80 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2210.37 | 426.33 | Unknown | Unknown | 11.31 | 1772.73 | 3981 | 2225.95 | 2210.37 | 15.58 | Yes | N/A | N/A | 2023-12-19 | 2024-02-16 | 60 | 44 | 2024-02-16 | 2024-02-16 | 1 | 1 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 60 | 44 | 2 | 2 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-02 | -96 | -69 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | 2024-05-16 | IOU Designed & Installed | N/A | No | N/A | 14468.46 | 5392.71 | Unknown | 9.77 | -437.85 | 9503.83 | Unknown | 734.32 | 14468.46 | -13734.14 | Yes | N/A | N/A | 2023-10-09 | 2024-01-03 | 87 | 63 | 2024-01-03 | 2024-01-03 | 1 | 1 | 2024-01-03 | 2024-03-01 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-05-16 | 77 | 55 | Unknown | 2024-05-08 | Unknown | Unknown | 2024-05-16 | 2024-09-28 | 1900-05-15 | 97 | 2024-09-28 | 2024-09-28 | 1 | 0 | 223 | 161 | 138 | 98 | 361 | 259 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-09 | -649 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-21 | 2025-03-25 | IOU Designed & Installed | N/A | No | N/A | 38.84 | Unknown | Unknown | Unknown | Unknown | 38.84 | 3981 | 1975.23 | 38.84 | 1936.39 | Yes | N/A | N/A | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-03-25 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-03-31 | 1900-01-06 | 5 | 2025-03-31 | 2025-03-31 | 1 | 1 | 6 | 4 | 9 | 7 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | -639 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-16 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | -15.29 | -12.42 | Unknown | Unknown | Unknown | -2.87 | Unknown | 694.06 | -15.29 | 709.35 | Yes | N/A | N/A | 2024-03-27 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-04-16 | 48 | 34 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-05-14 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-05-17 | 1900-01-03 | 4 | 2024-05-17 | 2024-05-17 | 1 | 1 | 29 | 21 | 53 | 39 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 53 | 53 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-02 | -628 | -449 | No | 2023-01-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-01-29 | 2023-03-12 | IOU Designed & Installed | N/A | Yes | 335 | 9.53 | -11.99 | Unknown | Unknown | Unknown | 21.52 | 3981 | 795.6 | 9.53 | 786.07 | Yes | N/A | N/A | 2023-01-18 | 2023-12-15 | 332 | 238 | 2023-12-15 | 2023-12-19 | 5 | 3 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-27 | 2023-03-12 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-03-12 | 2024-02-13 | 1900-12-04 | 242 | 2024-02-13 | 2024-02-13 | 1 | 1 | 346 | 248 | 345 | 246 | 691 | 494 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-27 | -212 | -151 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-14 | 2023-06-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 310.13 | Unknown | Unknown | Unknown | -625 | 935.13 | 0 | 625.49 | 310.13 | 315.36 | Yes | N/A | N/A | 2023-06-14 | 2023-06-14 | 1 | 1 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | Unknown | 2024-09-27 | Unknown | Unknown | 2024-09-27 | 2024-09-27 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-17 | -614 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-18 | 2025-03-18 | 2025-04-11 | IOU Designed & Installed | N/A | No | N/A | 417.43 | -8.39 | Unknown | Unknown | Unknown | 425.82 | Unknown | 2133.39 | 417.43 | 1715.96 | Yes | N/A | N/A | 2025-03-18 | 2025-03-18 | 1 | 1 | 2025-03-18 | 2025-03-18 | 1 | 1 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-04-11 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-05-13 | 1900-02-01 | 23 | 2025-05-13 | 2025-05-13 | 1 | 1 | 26 | 20 | 35 | 25 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-14 | -562 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-25 | 2023-07-28 | IOU Designed & Installed | N/A | No | N/A | -1.81 | -7.02 | Unknown | Unknown | Unknown | 5.21 | Unknown | 148.62 | -1.81 | 150.43 | Yes | N/A | N/A | 2023-04-25 | 2023-06-05 | 42 | 30 | 2023-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2023-07-28 | 54 | 40 | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2023-08-02 | 1900-01-05 | 4 | 2023-08-02 | 2023-08-02 | 1 | 1 | 96 | 70 | 7 | 5 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | 112 | 81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1169.49 | -21.66 | Unknown | Unknown | Unknown | 1191.15 | 3981 | 2064.21 | 1169.49 | 894.72 | Yes | N/A | N/A | 2024-02-01 | 2024-02-01 | 1 | 1 | 2024-02-01 | 2024-07-29 | 180 | 128 | 2024-06-06 | 2024-06-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-11-05 | 100 | 72 | Unknown | 2024-09-17 | Unknown | Unknown | Unknown | 2024-11-22 | Unknown | Unknown | 2024-11-22 | 2024-11-21 | Unknown | Unknown | 102 | 74 | 180 | 128 | 282 | 202 | Steps 2,3,5,6,7 | 53 | 37 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-31 | -707 | -506 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-05 | 2025-06-05 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1051.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-05 | 2025-06-05 | 1 | 1 | 2025-06-05 | 2025-06-05 | 1 | 1 | 2025-06-05 | Unknown | Unknown | Unknown | 2025-06-06 | 2025-06-19 | 14 | 10 | 2025-06-05 | 2025-06-23 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-23 | 1899-12-31 | 1 | 2025-06-23 | 2025-06-23 | 1 | 1 | 20 | 14 | 17 | 13 | 37 | 27 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 164 | 164 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-30 | 913 | 652 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-21 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 5423.62 | 119.91 | Unknown | 20.08 | Unknown | 5283.63 | 23886 | 7006.01 | 5423.62 | 1582.39 | Yes | N/A | N/A | 2024-02-21 | 2024-09-26 | 219 | 157 | 2024-09-26 | 2024-10-15 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2025-01-24 | 102 | 74 | Unknown | 2025-02-27 | Unknown | Unknown | 2025-03-17 | 2025-04-04 | 1900-01-18 | 15 | 2025-04-04 | 2025-03-31 | Unknown | Unknown | 321 | 231 | 39 | 29 | 360 | 260 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-18 | -598 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2024-02-07 | IOU Designed & Installed | N/A | No | N/A | -6.12 | -4.96 | Unknown | Unknown | Unknown | -1.16 | Unknown | 163.83 | -6.12 | 169.95 | Yes | N/A | N/A | 2024-01-09 | 2023-10-30 | Unknown | Unknown | 2023-10-30 | 2024-02-02 | 96 | 70 | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-02-07 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-02-28 | 1900-01-21 | 16 | 2024-02-28 | 2024-02-28 | 1 | 1 | 6 | 4 | 119 | 87 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-06 | 188 | 135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-01-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 635.4 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-16 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2024-01-30 | 63 | 45 | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | 2025-05-14 | 2025-05-13 | Unknown | Unknown | 0 | 0 | 63 | 45 | 63 | 45 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | -682 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-01-24 | 2025-01-24 | IOU Designed & Installed | N/A | No | N/A | 776.67 | -14.7 | Unknown | Unknown | Unknown | 791.37 | 3981 | 1683.99 | 776.67 | 907.32 | Yes | N/A | N/A | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-01-24 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-03-10 | 1900-02-14 | 32 | 2025-03-10 | 2025-03-10 | 1 | 1 | 2 | 2 | 48 | 34 | 50 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 138.1 | 138.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-13 | 0 | 1 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2023-09-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5.7 | -5.07 | Unknown | Unknown | Unknown | 10.77 | Unknown | 331.63 | 5.7 | 325.93 | Yes | N/A | N/A | 2023-07-24 | 2023-09-29 | 68 | 50 | 2023-09-29 | 2023-10-04 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | Unknown | Unknown | Unknown | 2024-06-13 | Unknown | Unknown | 2024-06-13 | 2024-06-13 | 1 | 1 | 68 | 50 | 7 | 5 | 75 | 55 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | Lakeside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | -144 | -104 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | 2024-10-06 | IOU Designed & Installed | N/A | No | N/A | -1615.43 | 606.24 | Unknown | 77.06 | -2721 | 422.27 | Unknown | 2720.93 | -1615.43 | 4336.36 | Yes | N/A | N/A | 2024-09-24 | 2024-09-25 | 2 | 2 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-06 | 2024-10-08 | 1900-01-02 | 2 | 2024-10-08 | 2024-10-08 | 1 | 1 | 2 | 2 | 4 | 3 | 6 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | -200 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | 2024-08-09 | IOU Designed & Installed | N/A | No | N/A | 6079.45 | 528.09 | Unknown | 166.87 | 6.86 | 5377.63 | 3981 | 808.64 | 6079.45 | -5270.81 | Yes | N/A | N/A | 2024-03-20 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2024-04-12 | 32 | 24 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-08-09 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-08-13 | 1900-01-04 | 3 | 2024-08-13 | 2024-08-13 | 1 | 1 | 120 | 86 | 38 | 28 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-22 | 21 | 16 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | 2024-12-13 | IOU Designed & Installed | N/A | No | N/A | 280.72 | 3084.57 | Unknown | 62.37 | -4324 | 1457.78 | Unknown | 4324.46 | 280.72 | 4043.74 | Yes | N/A | N/A | 2024-11-04 | 2024-11-01 | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2024-12-13 | 1899-12-31 | 1 | 2024-12-13 | 2024-12-13 | 1 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-20 | -163 | -118 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 15.43 | -11.93 | Unknown | Unknown | Unknown | 27.36 | 3981 | 2239.3 | 15.43 | 2223.87 | Yes | N/A | N/A | 2024-01-17 | 2024-01-04 | Unknown | Unknown | 2024-01-04 | 2024-01-26 | 23 | 17 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | Unknown | Unknown | Unknown | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2024-07-10 | 1 | 1 | 0 | 0 | 24 | 18 | 24 | 18 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | 2024-12-09 | IOU Designed & Installed | N/A | No | N/A | 1974.8 | Unknown | Unknown | Unknown | -1071 | 3045.8 | Unknown | 1071.13 | 1974.8 | -903.67 | Yes | N/A | N/A | 2024-09-19 | 2024-07-12 | Unknown | Unknown | 2024-07-12 | 2024-09-23 | 74 | 52 | 2024-09-23 | 2024-10-21 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-12-09 | 78 | 56 | Unknown | 2024-12-05 | Unknown | Unknown | 2024-12-09 | 2024-12-26 | 1900-01-17 | 14 | 2024-12-26 | 2024-12-26 | 1 | 1 | 107 | 77 | 93 | 67 | 200 | 144 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 80 | 80 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-20 | -263 | -188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2023-10-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1076.25 | Unknown | Unknown | Unknown | 14.92 | 1061.33 | 3981 | 1301.18 | 1076.25 | 224.93 | Yes | N/A | N/A | 2023-10-25 | 2023-08-11 | Unknown | Unknown | 2023-08-11 | 2024-01-11 | 154 | 110 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | 2024-11-04 | 2024-10-30 | Unknown | Unknown | 0 | 0 | 154 | 110 | 154 | 110 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 63.05 | 63.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-26 | -250 | -179 | No | 2024-01-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-03-01 | Unknown | IOU Designed & Installed | N/A | Yes | 348 | 659.53 | -12.43 | Unknown | Unknown | Unknown | 671.96 | 3981 | 961.53 | 659.53 | 302 | Yes | N/A | N/A | 2024-01-24 | 2025-01-06 | 349 | 249 | 2025-01-06 | 2024-03-01 | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-02-18 | 1 | 1 | 349 | 249 | 1 | 1 | 350 | 250 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | -115 | -84 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | 2023-09-20 | IOU Designed & Installed | N/A | No | N/A | 2529.11 | 3811.78 | Unknown | 967.8 | -3773 | 1522.53 | Unknown | 3773.45 | 2529.11 | 1244.34 | Yes | N/A | N/A | 2023-03-10 | 2023-03-17 | 8 | 6 | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | 2023-11-07 | 1900-02-17 | 35 | 2023-11-07 | 2023-11-07 | 1 | 1 | 8 | 6 | 50 | 36 | 58 | 42 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 115.4 | 115.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-01 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-04 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | 1013.09 | Unknown | Unknown | Unknown | Unknown | 1013.09 | 3981 | 1220.59 | 1013.09 | 207.5 | Yes | N/A | N/A | 2025-02-04 | 2025-03-06 | 31 | 23 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-05-20 | 76 | 54 | Unknown | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-05-22 | 1900-01-02 | 3 | 2025-05-22 | 2025-05-22 | 1 | 1 | 107 | 77 | 4 | 4 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-05 | -606 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | 2024-12-03 | IOU Designed & Installed | N/A | No | N/A | 37.96 | Unknown | Unknown | Unknown | Unknown | 37.96 | 3981 | 1598.54 | 37.96 | 1560.58 | Yes | N/A | N/A | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-12-03 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2025-01-07 | 1900-02-04 | 26 | 2025-01-07 | 2025-01-07 | 1 | 1 | 37 | 27 | 38 | 28 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | RANCHO SANTA FE | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-25 | -684 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-11 | 2025-01-03 | IOU Designed & Installed | N/A | No | N/A | 626.14 | Unknown | Unknown | Unknown | Unknown | 626.14 | Unknown | 499.14 | 626.14 | -127 | Yes | N/A | N/A | 2024-12-10 | 2024-12-06 | Unknown | Unknown | 2024-12-06 | 2024-12-13 | 8 | 6 | 2024-12-12 | 2024-12-13 | 2 | 2 | 2024-12-13 | 2025-01-24 | 43 | 31 | 2024-12-13 | 2025-01-03 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-01-10 | 1900-01-07 | 6 | 2025-01-10 | 2025-01-10 | 1 | 1 | 24 | 18 | 60 | 44 | 84 | 62 | Steps 2,3,5,6,7 | 43 | 31 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-28 | -568 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-17 | 2023-11-17 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 0.34 | -4.16 | Unknown | Unknown | Unknown | 4.5 | Unknown | 203.86 | 0.34 | 203.52 | Yes | N/A | N/A | 2023-11-17 | 2023-11-20 | 4 | 2 | 2023-11-20 | 2023-11-20 | 1 | 1 | 2023-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2023-12-04 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-08 | 1900-01-04 | 5 | 2023-12-08 | 2023-12-08 | 1 | 1 | 19 | 13 | 7 | 7 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-13 | -276 | -198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-15 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | 4378.22 | 308.78 | Unknown | 33.66 | -15995 | 20030.78 | Unknown | 17212.43 | 4378.22 | 12834.21 | Yes | N/A | N/A | 2025-01-15 | 2025-01-31 | 17 | 13 | 2025-01-31 | 2025-02-11 | 12 | 8 | 2025-02-03 | 2025-02-04 | 2 | 2 | 2025-01-31 | 2025-02-24 | 17 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-03-12 | 1900-01-14 | 11 | 2025-03-12 | 2025-03-12 | 1 | 1 | 19 | 15 | 45 | 29 | 64 | 44 | Steps 2,3,5,6,7 | 12 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -217 | -156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 162.95 | -3.08 | Unknown | Unknown | Unknown | 166.03 | Unknown | 466.88 | 162.95 | 303.93 | Yes | N/A | N/A | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | 2024-06-20 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-06-03 | 26 | 18 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | Unknown | Unknown | 2024-09-18 | 2024-09-18 | 1 | 1 | 2 | 2 | 78 | 56 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | DEL MAR | 311 | 311 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | -532 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-11-11 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 327.9 | -55.56 | Unknown | Unknown | -517.16 | 900.62 | 3981 | 2154.14 | 327.9 | 1826.24 | Yes | N/A | N/A | 2024-10-10 | 2024-11-06 | 28 | 20 | 2024-11-06 | 2024-11-13 | 8 | 6 | 2024-11-13 | 2024-12-11 | 29 | 21 | 2025-01-31 | 2025-03-20 | 49 | 35 | 2024-12-17 | 2025-01-22 | 37 | 27 | Unknown | 2025-01-15 | Unknown | Unknown | 2025-01-22 | 2025-04-04 | 1900-03-13 | 53 | 2025-04-04 | 2025-04-04 | 1 | 1 | 94 | 68 | 131 | 95 | 225 | 163 | Steps 2,3,5,6,7 | 93 | 67 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-28 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-03-13 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | 198.18 | -3 | Unknown | Unknown | Unknown | 201.18 | 3981 | 2336.74 | 198.18 | 2138.56 | Yes | N/A | N/A | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-02-28 | 2025-03-13 | 14 | 10 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-04-07 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-04-14 | 1900-01-07 | 6 | 2025-04-14 | 2025-05-02 | 19 | 15 | 27 | 19 | 41 | 31 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 218.3 | 218.3 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-19 | 16 | 13 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-08-01 | IOU Designed & Installed | N/A | No | N/A | 741.03 | -12.43 | Unknown | Unknown | 23.98 | 729.48 | 7962 | 362.2 | 741.03 | -378.83 | Yes | N/A | N/A | 2023-02-08 | 2023-02-03 | Unknown | Unknown | 2023-02-03 | 2023-02-17 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | 2023-05-03 | 2 | 2 | 2023-02-17 | 2023-07-27 | 161 | 115 | Unknown | 2023-07-26 | Unknown | Unknown | 2023-08-01 | 2023-10-16 | 1900-03-17 | 55 | 2023-10-16 | 2023-08-04 | Unknown | Unknown | 161 | 115 | 94 | 68 | 255 | 183 | Steps 2,3,5,6,7 | 75 | 53 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 422.05 | 422.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-24 | -315 | -226 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-30 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 17761.42 | Unknown | Unknown | Unknown | Unknown | 17761.42 | 3981 | 1073.63 | 17761.42 | -16687.79 | Yes | N/A | N/A | 2023-11-29 | 2023-11-29 | 1 | 1 | 2023-11-29 | 2023-11-30 | 2 | 2 | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2023-12-04 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-14 | 1900-01-10 | 9 | 2023-12-14 | 2023-12-14 | 1 | 1 | 6 | 4 | 14 | 12 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | -360 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 395.92 | -7.33 | Unknown | Unknown | 1.89 | 401.36 | 0 | 987.89 | 395.92 | 591.97 | Yes | N/A | N/A | 2024-02-14 | 2023-10-27 | Unknown | Unknown | 2023-10-27 | 2024-02-14 | 111 | 79 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-10-28 | 258 | 184 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-01 | 1900-01-04 | 5 | 2024-11-01 | 2024-11-01 | 1 | 1 | 258 | 184 | 117 | 85 | 375 | 269 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-07 | -477 | -342 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | 2024-12-17 | IOU Designed & Installed | N/A | No | N/A | 1040.3 | -20.4 | Unknown | Unknown | Unknown | 1060.7 | Unknown | 1530.59 | 1040.3 | 490.29 | Yes | N/A | N/A | 2024-10-09 | 2024-09-13 | Unknown | Unknown | 2024-09-13 | 2024-10-09 | 27 | 19 | 2024-10-09 | Unknown | Unknown | Unknown | 2024-10-10 | 2024-10-17 | 8 | 6 | 2024-10-09 | 2024-12-17 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-01-15 | 1900-01-29 | 22 | 2025-01-15 | 2025-01-15 | 1 | 1 | 70 | 50 | 66 | 48 | 136 | 98 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-05 | -478 | -342 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | 2024-02-27 | IOU Designed & Installed | N/A | No | N/A | 49.89 | -9.79 | Unknown | Unknown | Unknown | 59.68 | Unknown | 531.02 | 49.89 | 481.13 | Yes | N/A | N/A | 2023-11-13 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2023-11-17 | 127 | 91 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2024-02-27 | 103 | 73 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-14 | 1900-01-16 | 13 | 2024-03-14 | 2024-03-14 | 1 | 1 | 103 | 73 | 145 | 105 | 248 | 178 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-08 | 35 | 26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-07-07 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 6527.69 | -9.18 | Unknown | Unknown | Unknown | 6536.87 | Unknown | 462.82 | 6527.69 | -6064.87 | Yes | N/A | N/A | 2023-07-07 | 2023-05-22 | Unknown | Unknown | 2023-05-22 | 2023-08-02 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 0 | 0 | 74 | 54 | 74 | 54 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-18 | 64 | 47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-08-02 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | -1801.13 | Unknown | Unknown | Unknown | Unknown | -1801.13 | 3981 | 2611.94 | -1801.13 | 4413.07 | Yes | N/A | N/A | 2024-02-07 | 2024-05-24 | 108 | 78 | 2024-05-24 | 2024-08-21 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-08-23 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-10-10 | 1900-01-17 | 14 | 2024-10-10 | 2024-11-21 | 43 | 31 | 111 | 81 | 151 | 109 | 262 | 190 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | -220 | -159 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-04-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -7.89 | -5.71 | Unknown | Unknown | Unknown | -2.18 | Unknown | 352.77 | -7.89 | 360.66 | Yes | N/A | N/A | 2023-03-31 | 2023-04-03 | 4 | 2 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | Unknown | Unknown | 2023-06-06 | 2023-06-06 | 1 | 1 | 4 | 2 | 1 | 1 | 5 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-14 | -372 | -267 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-07-09 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 1279.08 | -17.82 | Unknown | Unknown | 11.96 | 1284.94 | 3981 | 1104.02 | 1279.08 | -175.06 | Yes | N/A | N/A | 2024-06-06 | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-07-09 | 77 | 55 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2025-03-18 | 253 | 181 | Unknown | 2025-03-03 | Unknown | Unknown | 2025-03-18 | 2025-04-07 | 1900-01-20 | 15 | 2025-04-07 | 2025-04-07 | 1 | 1 | 253 | 181 | 99 | 71 | 352 | 252 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | La Jolla | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-02 | 3 | 2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-20 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 17915.33 | 81.79 | Unknown | Unknown | 12.83 | 17820.71 | Unknown | 14897.12 | 17915.33 | -3018.21 | Yes | N/A | N/A | 2024-03-13 | 2024-03-06 | Unknown | Unknown | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-09-13 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-11-05 | 1900-02-25 | 41 | 2024-11-05 | 2024-11-05 | 1 | 1 | 0 | 0 | 82 | 60 | 82 | 60 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 24.35 | 24.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-01 | -431 | -309 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-24 | 2025-04-28 | IOU Designed & Installed | N/A | No | N/A | 451.21 | -1.57 | Unknown | Unknown | 19.55 | 433.23 | 3981 | 1188.89 | 451.21 | 737.68 | Yes | N/A | N/A | 2024-09-23 | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-10-16 | 69 | 49 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2025-04-28 | 195 | 139 | Unknown | 2025-05-05 | Unknown | Unknown | 2025-04-28 | 2025-05-09 | 1900-01-11 | 10 | 2025-05-09 | 2025-05-27 | 19 | 13 | 195 | 139 | 100 | 72 | 295 | 211 | Steps 2,3,5,6,7 | 7 | 5 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-06 | 9 | 8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | 1630.87 | -35.34 | Unknown | Unknown | Unknown | 1666.21 | 3981 | 781.27 | 1630.87 | -849.6 | Yes | N/A | N/A | 2023-09-13 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2023-09-14 | 63 | 45 | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-10-13 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-11-15 | 1900-02-02 | 24 | 2023-11-15 | 2023-11-15 | 1 | 1 | 30 | 22 | 98 | 70 | 128 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-11 | -329 | -236 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1689.15 | 739.5 | Unknown | Unknown | Unknown | 949.65 | Unknown | 1128.17 | 1689.15 | -560.98 | Yes | N/A | N/A | 2025-02-13 | 2025-02-13 | 1 | 1 | 2025-02-13 | 2025-02-13 | 1 | 1 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | 2025-03-19 | 2025-03-19 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-14 | -119 | -86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-04 | 2023-02-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 417.8 | -15.47 | Unknown | Unknown | Unknown | 433.27 | 26990 | 1396.44 | 417.8 | 978.64 | Yes | N/A | N/A | 2023-01-04 | 2023-02-27 | 55 | 39 | 2023-02-27 | Unknown | Unknown | Unknown | 2023-08-23 | 2024-03-12 | 25 | 17 | 2023-07-21 | 2024-03-13 | 79 | 59 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | Unknown | Unknown | 2024-06-17 | 2024-06-17 | 1 | 1 | 80 | 56 | 80 | 60 | 160 | 116 | Steps 2,3,5,6,7 | 352 | 250 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-25 | -568 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-25 | 2024-12-20 | IOU Designed & Installed | N/A | No | N/A | -900.01 | -13.2 | Unknown | Unknown | -1618 | 731.19 | Unknown | 1617.55 | -900.01 | 2517.56 | Yes | N/A | N/A | 2024-09-20 | 2024-09-25 | 6 | 4 | 2024-09-25 | 2024-09-25 | 1 | 1 | 2024-09-25 | 2024-12-11 | 25 | 19 | 2024-12-11 | 2024-12-23 | 13 | 9 | 2024-10-17 | 2024-12-20 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-01-03 | 1900-01-14 | 11 | 2025-01-03 | 2025-01-03 | 1 | 1 | 96 | 70 | 30 | 22 | 126 | 92 | Steps 2,3,5,6,7 | 67 | 47 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-21 | 68 | 50 | No | 2022-11-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-14 | 2022-11-14 | 2024-05-09 | IOU Designed & Installed | N/A | Yes | 511 | 516.84 | 306.13 | Unknown | Unknown | Unknown | 210.71 | Unknown | 693.46 | 516.84 | 176.62 | Yes | N/A | N/A | 2022-11-14 | 2024-04-08 | 512 | 366 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-11-14 | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-06-28 | 1900-02-19 | 37 | 2024-06-28 | 2024-06-28 | 1 | 1 | 512 | 366 | 52 | 38 | 564 | 404 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | N/A | 80 | 80 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-08 | 118 | 85 | No | 2022-09-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-20 | 2022-09-20 | 2023-10-01 | IOU Designed & Installed | N/A | Yes | 245 | 2265.57 | 1095.72 | Unknown | 235.84 | -859 | 1793.01 | 9066 | 1552.18 | 2265.57 | -713.39 | Yes | N/A | N/A | 2022-09-20 | 2023-05-23 | 246 | 176 | 2023-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-12-22 | 2023-10-01 | Unknown | Unknown | Unknown | 2023-07-17 | Unknown | Unknown | 2023-10-01 | 2023-10-04 | 1900-01-03 | 3 | 2023-10-04 | 2023-10-04 | 1 | 1 | 246 | 176 | 5 | 4 | 251 | 180 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | 102 | 102 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | 218 | 157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-03-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1942.69 | Unknown | Unknown | Unknown | Unknown | 1942.69 | 169731 | 24778.07 | 1942.69 | 22835.38 | Yes | N/A | N/A | 2024-01-12 | 2024-02-13 | 33 | 23 | 2024-02-13 | 2024-07-10 | 149 | 107 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2025-01-09 | 184 | 132 | Unknown | 2025-02-18 | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | 2025-03-10 | 2025-03-07 | Unknown | Unknown | 217 | 155 | 149 | 107 | 366 | 262 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-29 | -222 | -159 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-14 | 2024-04-24 | IOU Designed & Installed | N/A | No | N/A | -1446.97 | 1998.62 | Unknown | 274.44 | -4613 | 892.97 | Unknown | 4613.46 | -1446.97 | 6060.43 | Yes | N/A | N/A | 2024-03-14 | 2024-03-14 | 1 | 1 | 2024-03-14 | 2024-06-21 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | Unknown | Unknown | Unknown | 2024-06-21 | 2024-06-21 | 1 | 1 | 2024-04-24 | 2024-06-21 | 1900-02-27 | 43 | 2024-06-21 | 2024-06-21 | 1 | 1 | 1 | 1 | 161 | 117 | 162 | 118 | Steps 2,3,5,6,7 | 58 | 42 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-08 | 176 | 126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 13.38 | -11.88 | Unknown | Unknown | Unknown | 25.26 | Unknown | 1617.33 | 13.38 | 1603.95 | Yes | N/A | N/A | 2024-02-08 | 2024-02-22 | 15 | 11 | 2024-02-22 | 2024-03-20 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-03-19 | 21 | 15 | 2024-03-20 | Unknown | Unknown | Unknown | 2024-03-26 | 2024-03-27 | 2 | 2 | Unknown | 2024-04-01 | Unknown | Unknown | 2024-04-01 | 2024-04-01 | 1 | 1 | 15 | 11 | 52 | 38 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-12 | 80 | 58 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-10-24 | 2025-01-17 | IOU Designed & Installed | N/A | No | N/A | 3881.74 | 2852.25 | Unknown | 264.39 | -1730.79 | 2495.89 | Unknown | 1735.01 | 3881.74 | -2146.73 | Yes | N/A | N/A | 2024-04-22 | 2024-11-04 | 197 | 141 | 2024-11-04 | 2024-12-26 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-01-31 | 37 | 27 | Unknown | 2025-01-17 | Unknown | Unknown | 2025-01-17 | 2025-02-05 | 1900-01-19 | 14 | 2025-02-05 | 2025-04-02 | 57 | 41 | 234 | 168 | 130 | 94 | 364 | 262 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | -605 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 12.68 | Unknown | Unknown | Unknown | Unknown | 12.68 | Unknown | 1050.75 | 12.68 | 1038.07 | Yes | N/A | N/A | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-09-23 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-10-02 | 1900-01-09 | 8 | 2024-10-02 | 2024-10-02 | 1 | 1 | 43 | 31 | 12 | 10 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | -676 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-25 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 31.15 | -0.62 | Unknown | Unknown | Unknown | 31.77 | 3981 | 1670.23 | 31.15 | 1639.08 | Yes | N/A | N/A | 2025-02-25 | 2025-02-25 | 1 | 1 | 2025-02-25 | 2025-02-25 | 1 | 1 | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-17 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-04-01 | 1900-01-15 | 12 | 2025-04-01 | 2025-04-01 | 1 | 1 | 22 | 16 | 18 | 14 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | Oceanside | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-22 | 348 | 249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-22 | 2024-08-06 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 56292.79 | 18093.03 | Unknown | Unknown | 113.39 | 38086.37 | 685535 | 43405.85 | 56292.79 | -12886.94 | Yes | N/A | N/A | 2023-05-22 | 2023-08-31 | 102 | 74 | 2023-08-31 | 2024-07-10 | 315 | 225 | 2023-09-21 | 2024-07-17 | 235 | 169 | 2024-07-05 | 2024-07-22 | 16 | 8 | 2024-07-10 | Unknown | Unknown | Unknown | 2024-06-27 | 2024-07-29 | 33 | 23 | 2024-08-06 | 2024-09-04 | 1900-01-29 | 22 | 2024-09-04 | 2024-09-04 | 1 | 1 | 337 | 243 | 395 | 279 | 732 | 522 | Steps 2,3,5,6,7 | 317 | 225 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-26 | -216 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 169.08 | Unknown | Unknown | Unknown | -751.65 | 920.73 | Unknown | 759 | 169.08 | 589.92 | Yes | N/A | N/A | 2024-04-23 | 2024-03-11 | Unknown | Unknown | 2024-03-11 | 2024-05-03 | 54 | 40 | 2024-05-03 | 2024-05-17 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-07-11 | 53 | 39 | Unknown | 2024-07-01 | Unknown | Unknown | 2024-07-11 | 2024-07-25 | 1900-01-14 | 11 | 2024-07-25 | 2024-07-25 | 1 | 1 | 68 | 50 | 70 | 52 | 138 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community,Tribal Community | PAUMA VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-27 | 227 | 164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2024-01-30 | IOU Designed & Installed | N/A | No | N/A | 3466.23 | Unknown | Unknown | Unknown | Unknown | 3466.23 | 400 | 1981.02 | 3466.23 | -1485.21 | Yes | N/A | N/A | 2023-09-29 | 2023-09-29 | 1 | 1 | 2023-09-29 | 2024-01-02 | 96 | 68 | 2023-11-21 | 2023-11-21 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | 2024-01-12 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-02-13 | 1900-01-14 | 11 | 2024-02-13 | 2024-02-09 | Unknown | Unknown | 13 | 11 | 111 | 79 | 124 | 90 | Steps 2,3,5,6,7 | 42 | 30 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-21 | -268 | -192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-07-09 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | -1004.52 | 5310.54 | Unknown | Unknown | -8775 | 2459.94 | Unknown | 8775.12 | -1004.52 | 9779.64 | Yes | N/A | N/A | 2024-07-09 | 2024-07-09 | 1 | 1 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-09-26 | 1900-01-10 | 9 | 2024-09-26 | 2024-09-26 | 1 | 1 | 1 | 1 | 12 | 10 | 13 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | 47 | 34 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 181.61 | 108.06 | Unknown | Unknown | Unknown | 73.55 | 3981 | 192.83 | 181.61 | 11.22 | Yes | N/A | N/A | 2024-05-16 | 2024-06-17 | 33 | 23 | 2024-06-17 | 2024-06-20 | 4 | 4 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | 2025-03-19 | 2025-03-19 | 1 | 1 | 33 | 23 | 5 | 5 | 38 | 28 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -713 | -510 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | 2023-03-12 | IOU Designed & Installed | N/A | No | N/A | 2083.85 | 819.04 | Unknown | 88.1 | Unknown | 1176.71 | 3981 | 303.03 | 2083.85 | -1780.82 | Yes | N/A | N/A | 2023-03-01 | 2023-03-01 | 1 | 1 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-12 | 2023-04-19 | 1900-02-07 | 28 | 2023-04-19 | 2023-04-19 | 1 | 1 | 1 | 1 | 40 | 29 | 41 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 232.15 | 232.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | -171 | -124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | 2022-10-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 983.45 | 140.51 | Unknown | 103.04 | -344.07 | 1083.97 | 3981 | 1830.13 | 983.45 | 846.68 | Yes | N/A | N/A | 2022-08-31 | 2023-02-10 | 164 | 118 | 2023-02-10 | 2023-02-14 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-14 | 2023-11-28 | 288 | 206 | Unknown | 2023-12-15 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-01-29 | Unknown | Unknown | 452 | 324 | 5 | 3 | 457 | 327 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-13 | -58 | -43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-20 | 2023-07-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 270.38 | Unknown | Unknown | Yes | N/A | N/A | 2023-07-20 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2023-07-20 | 7 | 5 | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2024-12-17 | 1 | 1 | 0 | 0 | 8 | 6 | 8 | 6 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | -515 | -369 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-18 | 2025-03-11 | IOU Designed & Installed | N/A | No | N/A | 1239.84 | -39.83 | Unknown | Unknown | Unknown | 1279.67 | Unknown | 1703.1 | 1239.84 | 463.26 | Yes | N/A | N/A | 2024-09-17 | 2024-08-22 | Unknown | Unknown | 2024-08-22 | 2024-09-18 | 28 | 20 | 2024-09-18 | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-08 | 19 | 13 | 2024-09-19 | 2025-03-11 | 174 | 124 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-03-18 | 1900-01-07 | 6 | 2025-03-18 | 2025-03-18 | 1 | 1 | 174 | 124 | 56 | 40 | 230 | 164 | Steps 2,3,5,6,7 | 19 | 13 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -189 | -136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-07 | 2025-06-25 | IOU Designed & Installed | N/A | No | N/A | 1006.89 | Unknown | Unknown | Unknown | Unknown | 1006.89 | 2875.23 | 633.08 | 1006.89 | -373.81 | Yes | N/A | N/A | 2024-03-06 | 2024-03-06 | 1 | 1 | 2024-03-06 | 2024-10-11 | 220 | 158 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2025-06-02 | 235 | 167 | Unknown | 2025-06-12 | Unknown | Unknown | 2025-06-25 | 2025-06-25 | 1899-12-31 | 1 | 2025-06-25 | 2025-06-25 | 1 | 1 | 236 | 168 | 222 | 160 | 458 | 328 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 31 | 31 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-29 | -380 | -273 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 32.47 | Unknown | Unknown | Unknown | Unknown | 32.47 | 3981 | 952.51 | 32.47 | 920.04 | Yes | N/A | N/A | 2024-05-14 | 2024-05-14 | 1 | 1 | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | 2025-04-14 | 2025-04-14 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | VISTA | N/A | 138.05 | 138.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 80 | 57 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-14 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | 2346.17 | 402.48 | Unknown | 76.88 | 20.81 | 1846 | 3885 | 1076.25 | 2346.17 | -1269.92 | Yes | N/A | N/A | 2023-06-13 | 2023-07-10 | 28 | 20 | 2023-07-10 | 2023-07-24 | 15 | 11 | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | 2024-05-17 | 312 | 224 | Unknown | 2024-05-03 | Unknown | Unknown | 2024-05-17 | 2024-05-20 | 1900-01-03 | 2 | 2024-05-20 | 2024-05-20 | 1 | 1 | 340 | 244 | 20 | 14 | 360 | 258 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-22 | -424 | -303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | 2023-07-25 | IOU Designed & Installed | N/A | No | N/A | 187.05 | 116.47 | Unknown | Unknown | Unknown | 70.58 | Unknown | 363.72 | 187.05 | 176.67 | Yes | N/A | N/A | 2023-02-15 | 2023-02-15 | 1 | 1 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | 2023-07-25 | 161 | 115 | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2023-07-26 | 1900-01-01 | 2 | 2023-07-26 | 2023-07-26 | 1 | 1 | 162 | 116 | 3 | 3 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-27 | 36 | 27 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | 2024-01-26 | IOU Designed & Installed | N/A | No | N/A | 301.39 | 943.58 | Unknown | 265.32 | -2724 | 1816.49 | Unknown | 2540.73 | 301.39 | 2239.34 | Yes | N/A | N/A | 2023-12-19 | 2023-12-21 | 3 | 3 | 2023-12-21 | 2023-12-21 | 1 | 1 | 2023-12-21 | 2024-01-03 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-01-26 | 37 | 27 | Unknown | 2024-01-26 | Unknown | Unknown | 2024-01-26 | 2024-02-01 | 1900-01-06 | 5 | 2024-02-01 | 2024-02-01 | 1 | 1 | 54 | 40 | 9 | 7 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | -635 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-23 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 731 | -14.16 | Unknown | Unknown | Unknown | 745.16 | Unknown | 1682.72 | 731 | 951.72 | Yes | N/A | N/A | 2024-09-05 | 2024-09-17 | 13 | 9 | 2024-09-17 | 2024-09-23 | 7 | 5 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-10-18 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-10-25 | 1900-01-07 | 6 | 2024-10-25 | 2024-10-25 | 1 | 1 | 39 | 29 | 16 | 12 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | LA JOLLA | 127 | 127 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-10 | 150 | 107 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-07-19 | 2023-10-19 | IOU Designed & Installed | N/A | No | N/A | 5130.55 | 863.33 | Unknown | Unknown | -8317 | 12584.22 | 1877.49 | 10194.19 | 5130.55 | 5063.64 | Yes | N/A | N/A | 2023-06-08 | 2023-06-28 | 21 | 15 | 2023-06-28 | 2023-08-24 | 58 | 42 | 2023-07-06 | 2023-07-06 | 1 | 1 | 2023-08-07 | 2023-08-30 | 18 | 14 | 2023-08-24 | Unknown | Unknown | Unknown | 2023-09-26 | 2023-10-19 | 24 | 18 | 2023-10-19 | 2023-11-07 | 1900-01-19 | 14 | 2023-11-07 | 2023-11-07 | 1 | 1 | 22 | 16 | 121 | 89 | 143 | 105 | Steps 2,3,5,6,7 | 55 | 39 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-06 | -992 | -709 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 12.87 | -9.94 | Unknown | Unknown | Unknown | 22.81 | 3241 | 1093.92 | 12.87 | 1081.05 | Yes | N/A | N/A | 2024-06-26 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-06-26 | 70 | 50 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-07-02 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-18 | 1900-01-16 | 13 | 2024-07-18 | 2024-07-18 | 1 | 1 | 7 | 5 | 88 | 64 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 141.4 | 141.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | -512 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | 2024-05-06 | IOU Designed & Installed | N/A | No | N/A | 1052.62 | -7.74 | Unknown | Unknown | 6.32 | 1054.04 | 3981 | 737.9 | 1052.62 | -314.72 | Yes | N/A | N/A | 2024-01-23 | 2024-02-22 | 31 | 23 | 2024-02-22 | 2024-02-23 | 2 | 2 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-05-06 | 74 | 52 | Unknown | 2024-05-06 | Unknown | Unknown | 2024-05-06 | 2024-05-22 | 1900-01-16 | 13 | 2024-05-22 | 2024-05-22 | 1 | 1 | 105 | 75 | 20 | 16 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | -422 | -303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-08-15 | IOU Designed & Installed | N/A | No | N/A | 370.13 | -11.88 | Unknown | Unknown | Unknown | 382.01 | Unknown | 775.04 | 370.13 | 404.91 | Yes | N/A | N/A | 2023-03-21 | 2023-03-21 | 1 | 1 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-08-15 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2023-08-15 | 1899-12-31 | 1 | 2023-08-15 | 2023-08-15 | 1 | 1 | 149 | 107 | 2 | 2 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 19.35 | 19.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | -535 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-02-24 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | 75.73 | -1.56 | Unknown | Unknown | Unknown | 77.29 | 3981 | 1604.04 | 75.73 | 1528.31 | Yes | N/A | N/A | 2025-01-28 | 2025-02-24 | 28 | 20 | 2025-02-24 | 2025-02-24 | 1 | 1 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-05-20 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-06-03 | 1900-01-14 | 11 | 2025-06-03 | 2025-06-03 | 1 | 1 | 114 | 82 | 17 | 13 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -224 | -161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5191.65 | 1294.27 | Unknown | 688.44 | Unknown | 3208.94 | 3981 | 163.83 | 5191.65 | -5027.82 | Yes | N/A | N/A | 2024-01-29 | 2024-02-20 | 23 | 17 | 2024-02-20 | 2024-02-22 | 3 | 3 | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | 2024-05-30 | 2024-05-30 | 1 | 1 | 23 | 17 | 4 | 4 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-23 | -196 | -141 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | 2023-11-08 | IOU Designed & Installed | N/A | No | N/A | 2274.49 | 493.36 | Unknown | 162.32 | 4.47 | 1614.34 | 3981 | 971.87 | 2274.49 | -1302.62 | Yes | N/A | N/A | 2023-09-07 | 2023-09-14 | 8 | 6 | 2023-09-14 | 2023-09-15 | 2 | 2 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2023-11-08 | 55 | 39 | Unknown | 2023-11-06 | Unknown | Unknown | 2023-11-08 | 2023-11-09 | 1900-01-01 | 2 | 2023-11-09 | 2023-11-09 | 1 | 1 | 63 | 45 | 5 | 5 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-02 | 799 | 572 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-26 | 2023-04-05 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | 9469.02 | 352.45 | Unknown | Unknown | -1520.67 | 10637.24 | 0 | 1804.8 | 9469.02 | -7664.22 | Yes | N/A | N/A | 2022-10-26 | 2023-04-05 | 162 | 116 | 2023-04-05 | 2023-05-04 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | Unknown | Unknown | 2023-10-10 | 2024-01-30 | 1900-04-22 | 81 | 2024-01-30 | 2024-07-09 | 162 | 116 | 162 | 116 | 305 | 219 | 467 | 335 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-23 | 109 | 80 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.42 | -10.16 | Unknown | Unknown | Unknown | 6.74 | 8164 | 548.56 | -3.42 | 551.98 | Yes | N/A | N/A | 2023-04-10 | 2023-03-21 | Unknown | Unknown | 2023-03-21 | 2023-04-18 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | 2023-05-02 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-05-12 | Unknown | Unknown | 15 | 11 | 29 | 21 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 26.05 | 26.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-30 | -143 | -103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | 2024-05-20 | IOU Designed & Installed | N/A | No | N/A | -9.51 | -8.2 | Unknown | Unknown | Unknown | -1.31 | Unknown | 907.87 | -9.51 | 917.38 | Yes | N/A | N/A | 2024-01-30 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-01-30 | 21 | 15 | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-05-20 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-07-10 | 1900-02-20 | 38 | 2024-07-10 | 2024-07-10 | 1 | 1 | 112 | 80 | 74 | 54 | 186 | 134 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | -468 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-25 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | 1431.41 | Unknown | Unknown | Unknown | 12.7 | 1418.71 | 3981 | 1210.86 | 1431.41 | -220.55 | Yes | N/A | N/A | 2025-03-06 | 2025-03-28 | 23 | 17 | 2025-03-28 | 2025-04-03 | 7 | 5 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-06-03 | 62 | 44 | Unknown | 2025-05-28 | Unknown | Unknown | 2025-06-03 | 2025-06-06 | 1900-01-03 | 4 | 2025-06-06 | 2025-06-06 | 1 | 1 | 85 | 61 | 12 | 10 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-16 | -448 | -321 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2024-02-16 | IOU Designed & Installed | N/A | No | N/A | 1626.05 | -12.81 | Unknown | Unknown | 13.27 | 1625.59 | 3981 | 708.24 | 1626.05 | -917.81 | Yes | N/A | N/A | 2023-09-29 | 2023-10-24 | 26 | 18 | 2023-10-24 | 2023-10-26 | 3 | 3 | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2024-02-16 | 114 | 82 | Unknown | 2024-02-23 | Unknown | Unknown | 2024-02-16 | 2024-02-23 | 1900-01-07 | 6 | 2024-02-23 | 2024-02-23 | 1 | 1 | 140 | 100 | 12 | 10 | 152 | 110 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 69.05 | 69.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | -582 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-01-23 | 2023-03-28 | IOU Designed & Installed | N/A | No | N/A | 954.28 | 236.04 | Unknown | 155.78 | Unknown | 562.46 | Unknown | 183.65 | 954.28 | -770.63 | Yes | N/A | N/A | 2023-01-23 | 2023-03-08 | 45 | 33 | 2023-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | 2023-03-28 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | 2023-03-29 | 1900-01-01 | 2 | 2023-03-29 | 2023-03-29 | 1 | 1 | 66 | 48 | 3 | 3 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-03 | -365 | -262 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-16 | 2025-01-31 | IOU Designed & Installed | N/A | No | N/A | 301.77 | -26.52 | Unknown | Unknown | 1.78 | 326.51 | 3981 | 1842.81 | 301.77 | 1541.04 | Yes | N/A | N/A | 2025-01-14 | 2025-01-14 | 1 | 1 | 2025-01-14 | 2025-01-16 | 3 | 3 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-01-31 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-04-03 | 1900-03-03 | 45 | 2025-04-03 | 2025-04-03 | 1 | 1 | 17 | 13 | 67 | 49 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-29 | -368 | -264 | No | 2024-02-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-05 | 2024-11-25 | IOU Designed & Installed | N/A | Yes | 126 | 4352.23 | 723.24 | Unknown | 101.08 | 81.28 | 3446.63 | 3981 | 701.13 | 4352.23 | -3651.1 | Yes | N/A | N/A | 2024-02-05 | 2024-06-10 | 127 | 91 | 2024-06-10 | 2024-03-01 | Unknown | Unknown | 2024-03-01 | 2024-06-07 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-11-25 | 256 | 182 | Unknown | 2024-11-18 | Unknown | Unknown | 2024-11-25 | 2024-11-26 | 1900-01-01 | 2 | 2024-11-26 | 2024-11-26 | 1 | 1 | 482 | 344 | 3 | 3 | 485 | 347 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | 123 | 88 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-02-29 | 2024-03-22 | IOU Designed & Installed | N/A | No | N/A | 814.42 | -7.6 | Unknown | Unknown | Unknown | 822.02 | 0 | 608.85 | 814.42 | -205.57 | Yes | N/A | N/A | 2024-02-29 | 2024-02-29 | 1 | 1 | 2024-02-29 | 2024-03-20 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2025-02-10 | 1900-11-21 | 232 | 2025-02-10 | 2025-02-10 | 1 | 1 | 1 | 1 | 348 | 248 | 349 | 249 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | -178 | -129 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -12.4 | -8.99 | Unknown | Unknown | Unknown | -3.41 | Unknown | 311.78 | -12.4 | 324.18 | Yes | N/A | N/A | 2023-02-28 | 2023-02-28 | 1 | 1 | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | Unknown | Unknown | 2023-06-05 | 2023-06-05 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | -51 | -38 | No | 2023-07-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-24 | 2022-10-24 | 2024-05-20 | IOU Designed & Installed | N/A | Yes | 225 | 1017.22 | -7.74 | Unknown | Unknown | 84.06 | 940.9 | 36349.88 | 969.54 | 1017.22 | -47.68 | Yes | N/A | N/A | 2022-10-24 | 2024-03-12 | 506 | 362 | 2024-03-12 | 2024-03-12 | 1 | 1 | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2024-05-20 | 295 | 211 | Unknown | 2024-05-15 | Unknown | Unknown | 2024-05-20 | 2024-06-07 | 1900-01-18 | 15 | 2024-06-07 | 2024-06-11 | 5 | 3 | 801 | 573 | 25 | 19 | 826 | 592 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-03 | 341 | 244 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2705.38 | -55.09 | Unknown | Unknown | 28.06 | 2732.41 | 24469 | 575.54 | 2705.38 | -2129.84 | Yes | N/A | N/A | 2023-09-18 | 2023-09-07 | Unknown | Unknown | 2023-09-07 | 2023-10-06 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-10-06 | 8 | 6 | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-02-07 | 1 | 1 | 0 | 0 | 39 | 29 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-02 | -708 | -506 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | 2025-01-10 | IOU Designed & Installed | N/A | No | N/A | 77.79 | -1.5 | Unknown | Unknown | Unknown | 79.29 | 3981 | 1609.07 | 77.79 | 1531.28 | Yes | N/A | N/A | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-10 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-01-24 | 1900-01-14 | 11 | 2025-01-24 | 2025-01-24 | 1 | 1 | 3 | 3 | 17 | 13 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 2650 | 2650 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-07-21 | 57 | 41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | 2024-08-27 | IOU Designed & Installed | N/A | No | N/A | 16110.38 | 389.24 | Unknown | Unknown | 36.3 | 15684.84 | Unknown | 10131.82 | 16110.38 | -5978.56 | Yes | N/A | N/A | 2024-03-21 | 2024-03-21 | 1 | 1 | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-07-30 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-16 | 1900-01-20 | 15 | 2024-09-16 | 2024-09-16 | 1 | 1 | 1 | 1 | 58 | 42 | 59 | 43 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 690 | 495 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 74.54 | Unknown | Unknown | Unknown | -653 | 727.54 | Unknown | 547.66 | 74.54 | 473.12 | Yes | N/A | N/A | 2024-12-17 | 2024-05-31 | Unknown | Unknown | 2024-05-31 | 2025-01-09 | 224 | 160 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2024-12-12 | Unknown | Unknown | Unknown | 2025-01-29 | Unknown | Unknown | 2025-01-30 | 2025-02-10 | 1900-01-11 | 8 | 2025-02-10 | 2025-02-07 | Unknown | Unknown | 0 | 0 | 236 | 168 | 236 | 168 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-01 | -539 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-19 | 2024-11-25 | IOU Designed & Installed | N/A | No | N/A | 40.09 | Unknown | Unknown | Unknown | Unknown | 40.09 | 3981 | 283.36 | 40.09 | 243.27 | Yes | N/A | N/A | 2024-06-19 | 2024-06-13 | Unknown | Unknown | 2024-06-13 | 2024-09-24 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-09-24 | 1 | 1 | 2024-09-24 | 2024-11-15 | 53 | 39 | Unknown | 2024-11-25 | Unknown | Unknown | 2024-11-25 | 2024-12-12 | 1900-01-17 | 14 | 2024-12-12 | 2024-12-09 | Unknown | Unknown | 53 | 39 | 123 | 89 | 176 | 128 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-19 | -396 | -285 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-04-11 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 1275.86 | 352.3 | Unknown | Unknown | Unknown | 923.56 | 3981 | 1025.78 | 1275.86 | -250.08 | Yes | N/A | N/A | 2024-03-15 | 2024-04-11 | 28 | 20 | 2024-04-11 | 2024-04-11 | 1 | 1 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-10-29 | 202 | 144 | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-11-18 | 1900-01-20 | 15 | 2024-11-18 | 2024-11-18 | 1 | 1 | 230 | 164 | 23 | 17 | 253 | 181 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2020-12-31 | 1159 | 828 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-03 | 2022-01-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -12.52 | -10.14 | Unknown | Unknown | Unknown | -2.38 | Unknown | 993.46 | -12.52 | 1005.98 | Yes | N/A | N/A | 2022-01-03 | 2023-07-21 | 565 | 405 | 2023-07-21 | 2023-07-21 | 1 | 1 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-03-04 | 1 | 1 | 565 | 405 | 2 | 2 | 567 | 407 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | -677 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2025-01-02 | 2025-01-06 | IOU Designed & Installed | N/A | No | N/A | 49.77 | Unknown | Unknown | Unknown | Unknown | 49.77 | 3981 | 1376.98 | 49.77 | 1327.21 | Yes | N/A | N/A | 2024-12-18 | 2025-01-02 | 16 | 12 | 2025-01-02 | 2025-01-02 | 1 | 1 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-01-06 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-01-24 | 1900-01-18 | 15 | 2025-01-24 | 2025-01-24 | 1 | 1 | 21 | 15 | 21 | 17 | 42 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-23 | -411 | -294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-05-16 | 2023-08-02 | IOU Designed & Installed | N/A | No | N/A | 5241.68 | 350.69 | Unknown | Unknown | -1086 | 5976.99 | 3981 | 1489.17 | 5241.68 | -3752.51 | Yes | N/A | N/A | 2023-02-14 | 2023-05-04 | 80 | 58 | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | 2023-08-02 | 65 | 47 | Unknown | 2023-06-09 | Unknown | Unknown | 2023-08-02 | 2023-08-16 | 1900-01-14 | 11 | 2023-08-16 | 2023-08-09 | Unknown | Unknown | 145 | 105 | 15 | 11 | 160 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-13 | -17 | -13 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-28 | 2023-07-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2005.71 | -40.76 | Unknown | Unknown | 38.02 | 2008.45 | 15924 | 1481.48 | 2005.71 | -524.23 | Yes | N/A | N/A | 2023-07-28 | 2023-09-05 | 40 | 28 | 2023-09-05 | 2023-09-21 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | 2023-09-13 | 9 | 7 | 2023-09-21 | 2023-12-01 | 72 | 52 | Unknown | 2024-03-14 | Unknown | Unknown | Unknown | 2024-03-28 | Unknown | Unknown | 2024-03-28 | 2024-03-27 | Unknown | Unknown | 112 | 80 | 26 | 20 | 138 | 100 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 29.75 | 29.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | -547 | -392 | No | 2024-08-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-08 | 2025-01-07 | IOU Designed & Installed | N/A | Yes | 154 | 684.77 | Unknown | Unknown | Unknown | 10.88 | 673.89 | 3981 | 1106.45 | 684.77 | 421.68 | Yes | N/A | N/A | 2024-08-05 | 2025-01-06 | 155 | 111 | 2025-01-06 | 2024-09-13 | Unknown | Unknown | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2025-01-07 | 117 | 83 | Unknown | 2024-12-06 | Unknown | Unknown | 2025-01-07 | 2025-01-08 | 1900-01-01 | 2 | 2025-01-08 | 2025-01-08 | 1 | 1 | 272 | 194 | 3 | 3 | 275 | 197 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -554 | -397 | No | 2024-06-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | 2024-10-18 | IOU Designed & Installed | N/A | Yes | 41 | -170.05 | Unknown | Unknown | Unknown | 13.56 | -183.61 | 3981 | 1249.55 | -170.05 | 1419.6 | Yes | N/A | N/A | 2024-06-26 | 2024-08-06 | 42 | 30 | 2024-08-06 | 2024-07-08 | Unknown | Unknown | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-10-18 | 103 | 75 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-11-13 | 1900-01-26 | 19 | 2024-11-13 | 2024-11-13 | 1 | 1 | 145 | 105 | 28 | 20 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-11 | -501 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-14 | 2025-05-22 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1430.44 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-04 | 2024-11-11 | 8 | 6 | 2024-11-11 | 2024-11-14 | 4 | 4 | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2025-05-22 | 190 | 136 | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-05-28 | 1900-01-06 | 5 | 2025-05-28 | 2025-05-28 | 1 | 1 | 198 | 142 | 12 | 10 | 210 | 152 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-12 | -299 | -214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-13 | 2024-05-10 | IOU Designed & Installed | N/A | No | N/A | -6.33 | -5.14 | Unknown | Unknown | Unknown | -1.19 | Unknown | 163.83 | -6.33 | 170.16 | Yes | N/A | N/A | 2024-03-13 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2024-03-13 | 2 | 2 | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-05-10 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-05-17 | 1900-01-07 | 6 | 2024-05-17 | 2024-05-17 | 1 | 1 | 59 | 43 | 11 | 9 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-17 | -678 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | 2025-04-04 | IOU Designed & Installed | N/A | No | N/A | 46.63 | -0.94 | Unknown | Unknown | Unknown | 47.57 | Unknown | 1628.24 | 46.63 | 1581.61 | Yes | N/A | N/A | 2025-03-26 | 2025-03-27 | 2 | 2 | 2025-03-27 | 2025-04-02 | 7 | 5 | 2025-03-26 | 2025-04-02 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-04 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-05-08 | 1900-02-03 | 25 | 2025-05-08 | 2025-05-08 | 1 | 1 | 13 | 11 | 43 | 31 | 56 | 42 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 19.05 | 19.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-12 | -625 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | 2025-02-14 | IOU Designed & Installed | N/A | No | N/A | 453.2 | -8.05 | Unknown | Unknown | Unknown | 461.25 | 3981 | 2169.3 | 453.2 | 1716.1 | Yes | N/A | N/A | 2025-01-08 | 2024-12-30 | Unknown | Unknown | 2024-12-30 | 2025-01-08 | 10 | 8 | 2025-01-08 | Unknown | Unknown | Unknown | 2025-01-10 | 2025-02-06 | 28 | 20 | 2025-01-08 | 2025-02-14 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-02-25 | 1900-01-11 | 8 | 2025-02-25 | 2025-02-25 | 1 | 1 | 38 | 28 | 51 | 37 | 89 | 65 | Steps 2,3,5,6,7 | 29 | 21 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | -654 | -469 | No | 2024-10-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-11-05 | 2024-11-07 | IOU Designed & Installed | N/A | Yes | 168 | 25.17 | Unknown | Unknown | Unknown | Unknown | 25.17 | Unknown | 2153.82 | 25.17 | 2128.65 | Yes | N/A | N/A | 2024-10-10 | 2024-10-10 | 1 | 1 | 2024-10-10 | 2024-11-06 | 28 | 20 | 2024-11-06 | 2024-11-07 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-11-07 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-11-26 | 1900-01-19 | 14 | 2024-11-26 | 2024-11-26 | 1 | 1 | 5 | 5 | 49 | 35 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-22 | -321 | -230 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-08-28 | 2023-09-08 | IOU Designed & Installed | N/A | No | N/A | 1194.13 | 478.42 | Unknown | 235.84 | Unknown | 479.87 | 3885 | 936.4 | 1194.13 | -257.73 | Yes | N/A | N/A | 2023-08-28 | 2023-08-30 | 3 | 3 | 2023-08-30 | 2023-08-30 | 1 | 1 | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-09-08 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | 2023-10-06 | 1900-01-28 | 21 | 2023-10-06 | 2023-10-06 | 1 | 1 | 13 | 11 | 31 | 23 | 44 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-25 | 2024-08-02 | IOU Designed & Installed | N/A | No | N/A | 670.27 | -12.71 | Unknown | Unknown | Unknown | 682.98 | 3981 | 1452.85 | 670.27 | 782.58 | Yes | N/A | N/A | 2024-04-23 | 2024-05-01 | 9 | 7 | 2024-05-01 | 2024-06-06 | 37 | 27 | 2024-06-06 | Unknown | Unknown | Unknown | 2024-06-07 | 2024-06-14 | 8 | 6 | 2024-06-06 | 2024-08-02 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-08-09 | 1900-01-07 | 6 | 2024-08-09 | 2024-08-09 | 1 | 1 | 67 | 49 | 54 | 40 | 121 | 89 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-22 | -701 | -502 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-07 | 2025-05-07 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 344.78 | 83.66 | Unknown | Unknown | Unknown | 261.12 | 3981 | 1022.51 | 344.78 | 677.73 | Yes | N/A | N/A | 2025-05-07 | 2025-05-07 | 1 | 1 | 2025-05-07 | 2025-05-07 | 1 | 1 | 2025-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-05-12 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-21 | 1900-01-09 | 8 | 2025-05-21 | 2025-05-21 | 1 | 1 | 6 | 4 | 12 | 10 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-14 | -471 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | 2024-02-13 | IOU Designed & Installed | N/A | No | N/A | 5.8 | -5.19 | Unknown | Unknown | Unknown | 10.99 | 3241 | 625.94 | 5.8 | 620.14 | Yes | N/A | N/A | 2023-12-14 | 2023-08-08 | Unknown | Unknown | 2023-08-08 | 2023-12-14 | 129 | 93 | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2024-02-13 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-03-15 | 1900-01-31 | 24 | 2024-03-15 | 2024-02-29 | Unknown | Unknown | 61 | 43 | 161 | 117 | 222 | 160 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | -427 | -306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.69 | -13.7 | Unknown | Unknown | Unknown | 9.01 | Unknown | 681.81 | -4.69 | 686.5 | Yes | N/A | N/A | 2023-01-24 | 2023-02-09 | 17 | 13 | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | 2023-07-28 | 2023-07-28 | 1 | 1 | 17 | 13 | 1 | 1 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 10294.05 | 10294.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2027-01-13 | -632 | -453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-11 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | 12186.72 | 1829.58 | Unknown | Unknown | 2.94 | 10354.2 | 3981 | 1418.75 | 12186.72 | -10767.97 | Yes | N/A | N/A | 2025-02-11 | 2025-02-11 | 1 | 1 | 2025-02-11 | 2025-03-21 | 39 | 29 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-04-07 | 48 | 34 | Unknown | 2025-03-11 | Unknown | Unknown | 2025-04-07 | 2025-04-21 | 1900-01-14 | 11 | 2025-04-21 | 2025-04-21 | 1 | 1 | 49 | 35 | 55 | 41 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-26 | -578 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-13 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | 377.18 | -7.51 | Unknown | Unknown | Unknown | 384.69 | Unknown | 1546.72 | 377.18 | 1169.54 | Yes | N/A | N/A | 2024-11-05 | 2024-11-13 | 9 | 7 | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2025-01-15 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-02-25 | 1900-02-10 | 30 | 2025-02-25 | 2025-02-25 | 1 | 1 | 73 | 53 | 44 | 32 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-03 | 179 | 128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-02-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1067.76 | -20.25 | Unknown | Unknown | Unknown | 1088.01 | 19905 | 1544.71 | 1067.76 | 476.95 | Yes | N/A | N/A | 2024-01-19 | 2024-02-02 | 15 | 11 | 2024-02-02 | 2024-02-21 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-02-08 | 7 | 5 | 2024-02-21 | 2025-02-20 | 366 | 262 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | Unknown | Unknown | 2024-10-29 | 2024-10-29 | 1 | 1 | 381 | 273 | 28 | 20 | 409 | 293 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | -578 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2024-10-31 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | 12.74 | Unknown | Unknown | Unknown | Unknown | 12.74 | Unknown | 197.01 | 12.74 | 184.27 | Yes | N/A | N/A | 2024-10-31 | 2024-10-28 | Unknown | Unknown | 2024-10-28 | 2024-10-28 | 1 | 1 | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-02-19 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-03-18 | 1900-01-27 | 20 | 2025-03-18 | 2025-03-18 | 1 | 1 | 59 | 43 | 30 | 22 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | 124.2 | 124.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-06 | 120 | 87 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-14 | 2023-06-14 | 2023-09-19 | IOU Designed & Installed | N/A | No | N/A | 5313.94 | Unknown | Unknown | Unknown | Unknown | 5313.94 | Unknown | 772.96 | 5313.94 | -4540.98 | Yes | N/A | N/A | 2023-06-14 | 2023-06-14 | 1 | 1 | 2023-06-14 | 2023-06-28 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-10-04 | 1900-01-15 | 12 | 2023-10-04 | 2023-10-04 | 1 | 1 | 1 | 1 | 32 | 24 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-13 | -166 | -119 | No | 2024-03-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-25 | 2024-04-19 | IOU Designed & Installed | N/A | Yes | 65 | 714.41 | -44.02 | Unknown | Unknown | Unknown | 758.43 | Unknown | 937.89 | 714.41 | 223.48 | Yes | N/A | N/A | 2024-03-25 | 2024-05-29 | 66 | 48 | 2024-05-29 | 2024-03-25 | Unknown | Unknown | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-04-19 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2024-05-31 | 1900-02-11 | 31 | 2024-05-31 | 2024-05-31 | 1 | 1 | 92 | 68 | 44 | 32 | 136 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-08 | -498 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-04-23 | 2024-08-07 | IOU Designed & Installed | N/A | No | N/A | 1360.54 | -26.23 | Unknown | Unknown | Unknown | 1386.77 | 3981 | 1106.84 | 1360.54 | -253.7 | Yes | N/A | N/A | 2024-02-16 | 2024-04-23 | 68 | 48 | 2024-04-23 | 2024-04-23 | 1 | 1 | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-08-07 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-08-28 | 1900-01-21 | 16 | 2024-08-28 | 2024-08-28 | 1 | 1 | 175 | 125 | 24 | 18 | 199 | 143 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | -573 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-03 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | 549.78 | -6.4 | Unknown | Unknown | -744 | 1300.18 | Unknown | 744.39 | 549.78 | 194.61 | Yes | N/A | N/A | 2025-03-03 | 2025-02-26 | Unknown | Unknown | 2025-02-26 | 2025-03-31 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-05-23 | 54 | 40 | Unknown | 2025-05-15 | Unknown | Unknown | 2025-06-05 | 2025-06-06 | 1900-01-01 | 2 | 2025-06-06 | 2025-06-06 | 1 | 1 | 54 | 40 | 37 | 27 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-22 | -668 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-20 | 2025-05-20 | 2025-05-29 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1420.27 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-20 | 2025-05-13 | Unknown | Unknown | 2025-05-13 | 2025-05-20 | 8 | 6 | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-05-29 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-23 | 1900-01-25 | 18 | 2025-06-23 | 2025-06-23 | 1 | 1 | 10 | 8 | 35 | 25 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-29 | -594 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-10 | 2025-04-04 | IOU Designed & Installed | N/A | No | N/A | -240.59 | Unknown | Unknown | Unknown | -1170 | 929.41 | Unknown | 1170.27 | -240.59 | 1410.86 | Yes | N/A | N/A | 2025-01-10 | 2025-02-18 | 40 | 28 | 2025-02-18 | 2025-02-21 | 4 | 4 | 2025-02-21 | 2025-02-26 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-04-04 | 38 | 28 | Unknown | 2025-03-31 | Unknown | Unknown | 2025-04-04 | 2025-04-14 | 1900-01-10 | 7 | 2025-04-14 | 2025-04-14 | 1 | 1 | 84 | 60 | 16 | 12 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-07 | -106 | -77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2024-01-19 | 2024-03-26 | IOU Designed & Installed | N/A | No | N/A | 583.85 | -21.91 | Unknown | Unknown | Unknown | 605.76 | Unknown | 1094.85 | 583.85 | 511 | Yes | N/A | N/A | 2023-12-26 | 2023-10-11 | Unknown | Unknown | 2023-10-11 | 2024-01-19 | 101 | 73 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-03-26 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-04-23 | 1900-01-28 | 21 | 2024-04-23 | 2024-04-23 | 1 | 1 | 68 | 48 | 131 | 95 | 199 | 143 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 7.7 | 7.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-30 | -576 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | 2025-01-27 | 2025-05-19 | IOU Designed & Installed | N/A | No | N/A | 630.75 | 254.7 | Unknown | Unknown | Unknown | 376.05 | 3981 | 347.96 | 630.75 | -282.79 | Yes | N/A | N/A | 2025-01-27 | 2025-02-20 | 25 | 19 | 2025-02-20 | 2025-03-03 | 12 | 8 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-05-19 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | 2025-06-02 | 1900-01-14 | 11 | 2025-06-02 | 2025-06-02 | 1 | 1 | 103 | 75 | 28 | 20 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-12 | -20 | -15 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-12 | 2024-07-18 | IOU Designed & Installed | N/A | No | N/A | -925.58 | Unknown | Unknown | Unknown | -980 | 54.42 | Unknown | 979.6 | -925.58 | 1905.18 | Yes | N/A | N/A | 2024-07-12 | 2024-07-12 | 1 | 1 | 2024-07-12 | 2024-07-12 | 1 | 1 | 2024-07-12 | 2024-07-18 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-07-18 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-07-23 | 1900-01-05 | 4 | 2024-07-23 | 2024-07-23 | 1 | 1 | 15 | 11 | 8 | 6 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-16 | -1 | -2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2024-01-18 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | 2099.13 | Unknown | Unknown | Unknown | Unknown | 2099.13 | Unknown | 3502.69 | 2099.13 | 1403.56 | Yes | N/A | N/A | 2023-09-14 | 2024-01-18 | 127 | 91 | 2024-01-18 | 2024-01-18 | 1 | 1 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-01-22 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-02-15 | 1900-01-24 | 19 | 2024-02-15 | 2024-02-15 | 1 | 1 | 131 | 93 | 27 | 21 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | -407 | -291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | 2024-05-15 | 2024-12-11 | IOU Designed & Installed | N/A | No | N/A | 2874.48 | Unknown | Unknown | Unknown | 131.04 | 2743.44 | 3981 | 2116.24 | 2874.48 | -758.24 | Yes | N/A | N/A | 2024-05-13 | 2024-07-08 | 57 | 41 | 2024-07-08 | 2024-07-11 | 4 | 4 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-12-11 | 154 | 110 | Unknown | 2024-11-14 | Unknown | Unknown | 2024-12-11 | 2025-02-03 | 1900-02-23 | 39 | 2025-02-03 | 2025-01-31 | Unknown | Unknown | 211 | 151 | 59 | 43 | 270 | 194 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-27 | -542 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-17 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 945.98 | Unknown | Unknown | Unknown | Unknown | 945.98 | 3981 | 1144.44 | 945.98 | 198.46 | Yes | N/A | N/A | 2024-07-10 | 2024-07-11 | 2 | 2 | 2024-07-11 | 2024-07-17 | 7 | 5 | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-10-23 | 99 | 71 | Unknown | 2024-10-17 | Unknown | Unknown | 2024-10-23 | 2024-11-01 | 1900-01-09 | 8 | 2024-11-01 | 2024-11-01 | 1 | 1 | 101 | 73 | 18 | 14 | 119 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | -639 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | 2023-05-22 | IOU Designed & Installed | N/A | No | N/A | 2774.34 | 807.53 | Unknown | 250.92 | 4.7 | 1711.19 | 3981 | 665.8 | 2774.34 | -2108.54 | Yes | N/A | N/A | 2023-03-06 | 2023-04-25 | 51 | 37 | 2023-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-25 | 2023-05-22 | 28 | 20 | Unknown | 2023-05-17 | Unknown | Unknown | 2023-05-22 | 2023-05-25 | 1900-01-03 | 4 | 2023-05-25 | 2023-05-25 | 1 | 1 | 79 | 57 | 5 | 5 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-26 | 98 | 71 | No | 2023-02-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-10-03 | 2024-07-31 | IOU Designed & Installed | N/A | Yes | 532 | -1062.21 | Unknown | Unknown | Unknown | -1123 | 60.79 | 7962 | 2386.09 | -1062.21 | 3448.3 | Yes | N/A | N/A | 2023-02-17 | 2024-08-02 | 533 | 381 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-11-01 | 28 | 20 | 2023-12-18 | 2024-07-31 | 227 | 163 | Unknown | 2024-06-28 | Unknown | Unknown | 2024-07-31 | 2024-08-05 | 1900-01-05 | 4 | 2024-08-05 | 2024-08-02 | Unknown | Unknown | 760 | 544 | 34 | 24 | 794 | 568 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-19 | -478 | -343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-04-22 | 2024-04-23 | IOU Designed & Installed | N/A | No | N/A | 1220.84 | -35.17 | Unknown | Unknown | Unknown | 1256.01 | Unknown | 961.08 | 1220.84 | -259.76 | Yes | N/A | N/A | 2024-03-21 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-04-22 | 89 | 63 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-04-23 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-05-29 | 1900-02-05 | 27 | 2024-05-29 | 2024-05-29 | 1 | 1 | 2 | 2 | 127 | 91 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | -501 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-04-03 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 3.03 | Unknown | Unknown | Unknown | Unknown | 3.03 | Unknown | 534.57 | 3.03 | 531.54 | Yes | N/A | N/A | 2024-03-21 | 2024-04-03 | 14 | 10 | 2024-04-03 | 2024-04-03 | 1 | 1 | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-07-25 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-08-27 | 1900-02-02 | 24 | 2024-08-27 | 2024-08-27 | 1 | 1 | 128 | 92 | 36 | 26 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-16 | -376 | -269 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-20 | 2022-09-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 705.62 | -10.32 | Unknown | Unknown | Unknown | 715.94 | 3981 | 632.46 | 705.62 | -73.16 | Yes | N/A | N/A | 2022-09-20 | 2023-05-03 | 226 | 162 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | Unknown | Unknown | Unknown | 2023-07-06 | Unknown | Unknown | 2023-07-06 | 2023-07-06 | 1 | 1 | 226 | 162 | 1 | 1 | 227 | 163 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | El Cajon | COUNTY OF SAN DIEGO-SOUTH of 56 | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-11 | 413 | 296 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-08-14 | 2024-12-13 | IOU Designed & Installed | N/A | No | N/A | 80804.04 | 3559.75 | Unknown | Unknown | 359.77 | 76884.52 | Unknown | 45697.2 | 80804.04 | -35106.84 | Yes | N/A | N/A | 2024-06-18 | 2024-06-18 | 1 | 1 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-12-03 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-02-27 | 1900-03-17 | 55 | 2025-02-27 | 2025-02-27 | 1 | 1 | 1 | 1 | 127 | 91 | 128 | 92 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-15 | -541 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-29 | 2024-01-30 | IOU Designed & Installed | N/A | No | N/A | 2350.5 | 472.26 | Unknown | Unknown | Unknown | 1878.24 | 3981 | 1230.26 | 2350.5 | -1120.24 | Yes | N/A | N/A | 2024-01-10 | 2023-09-25 | Unknown | Unknown | 2023-09-25 | 2024-01-29 | 127 | 91 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-01-30 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-02-21 | 1900-01-22 | 17 | 2024-02-21 | 2024-02-21 | 1 | 1 | 2 | 2 | 151 | 109 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 267 | 192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-03-17 | 2024-05-03 | IOU Designed & Installed | N/A | No | N/A | 31254.47 | -19.4 | Unknown | Unknown | Unknown | 31273.87 | 3573507 | 57351.62 | 31254.47 | 26097.15 | Yes | N/A | N/A | 2023-03-17 | 2023-03-17 | 1 | 1 | 2023-03-17 | 2023-04-10 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | 2958465 | Unknown | Unknown | Unknown | 2023-11-03 | Unknown | Unknown | 2024-05-03 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-02-23 | Unknown | Unknown | 1 | 1 | 25 | 17 | 26 | 18 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 16.2 | 16.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | -594 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | 2024-11-13 | IOU Designed & Installed | N/A | No | N/A | 115.49 | -1.5 | Unknown | Unknown | Unknown | 116.99 | 3981 | 1946.94 | 115.49 | 1831.45 | Yes | N/A | N/A | 2024-08-08 | 2024-08-08 | 1 | 1 | 2024-08-08 | 2024-08-08 | 1 | 1 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-11-13 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-11-21 | 1900-01-08 | 7 | 2024-11-21 | 2024-11-21 | 1 | 1 | 99 | 71 | 11 | 9 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | EL CAJON | 168 | 168 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-02 | 284 | 203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-06-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 16706.36 | 7884.07 | Unknown | Unknown | -14629.89 | 23452.18 | 2557 | 24841.04 | 16706.36 | 8134.68 | Yes | N/A | N/A | 2023-03-27 | 2024-03-12 | 352 | 252 | 2024-03-12 | 2024-04-25 | 45 | 33 | 2024-03-06 | 2024-04-09 | 35 | 25 | 2023-08-31 | 2024-07-03 | 122 | 88 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | Unknown | Unknown | 2024-08-12 | 2024-08-12 | 1 | 1 | 387 | 277 | 168 | 122 | 555 | 399 | Steps 2,3,5,6,7 | 341 | 243 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-17 | -322 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-08-12 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | -5338.85 | 557.5 | Unknown | Unknown | -6279 | 382.65 | Unknown | 6279.48 | -5338.85 | 11618.33 | Yes | N/A | N/A | 2024-07-30 | 2024-07-30 | 1 | 1 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-08-29 | 1900-01-03 | 4 | 2024-08-29 | 2024-08-29 | 1 | 1 | 1 | 1 | 5 | 5 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-03 | -461 | -330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-28 | 2024-04-04 | IOU Designed & Installed | N/A | No | N/A | 6.05 | Unknown | Unknown | Unknown | Unknown | 6.05 | 3981 | 850.59 | 6.05 | 844.54 | Yes | N/A | N/A | 2024-03-07 | 2024-03-21 | 15 | 11 | 2024-03-21 | 2024-03-28 | 8 | 6 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-04-04 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-07-30 | 1900-04-27 | 84 | 2024-07-30 | 2024-07-30 | 1 | 1 | 23 | 17 | 127 | 91 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | Poway | POWAY | 139.05 | 139.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-30 | 80 | 57 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-07-13 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 47477.47 | 15045.34 | Unknown | Unknown | -13443.89 | 45876.02 | 2990.2 | 20183 | 47477.47 | -27294.47 | Yes | N/A | N/A | 2023-04-04 | 2023-06-30 | 88 | 64 | 2023-06-30 | 2024-03-26 | 271 | 193 | 2023-12-12 | 2024-02-16 | 7 | 7 | 2024-01-26 | 2024-10-04 | 64 | 46 | 2024-03-26 | Unknown | Unknown | Unknown | 2024-04-10 | 2024-10-09 | 183 | 131 | 2024-10-15 | 2024-11-18 | 1900-02-03 | 25 | 2024-11-18 | 2024-11-18 | 1 | 1 | 95 | 71 | 554 | 396 | 649 | 467 | Steps 2,3,5,6,7 | 318 | 228 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | -627 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-04 | 2025-01-03 | IOU Designed & Installed | N/A | No | N/A | 5545.15 | 992.86 | Unknown | Unknown | 2.74 | 4549.55 | 3981 | 1538.97 | 5545.15 | -4006.18 | Yes | N/A | N/A | 2024-12-04 | 2024-12-04 | 1 | 1 | 2024-12-04 | 2024-12-04 | 1 | 1 | 2024-12-04 | Unknown | Unknown | Unknown | 2024-12-05 | 2024-12-17 | 13 | 9 | 2024-12-04 | 2025-01-03 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-03-03 | 1900-02-28 | 42 | 2025-03-03 | 2025-03-03 | 1 | 1 | 32 | 24 | 75 | 53 | 107 | 77 | Steps 2,3,5,6,7 | 13 | 9 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 70280 | 70280 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-08 | 88 | 63 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-25 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 1490.96 | 420.6 | Unknown | Unknown | Unknown | 1070.36 | 3981 | 1747.12 | 1490.96 | 256.16 | Yes | N/A | N/A | 2024-09-17 | 2024-09-25 | 9 | 7 | 2024-09-25 | 2024-09-25 | 1 | 1 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-28 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-14 | 1900-01-17 | 14 | 2024-11-14 | 2024-11-04 | Unknown | Unknown | 43 | 31 | 19 | 15 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -65 | -48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-17 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | -1108 | Unknown | Unknown | Unknown | -1108 | Unkonwn | Unknown | 992.68 | -1108 | 2100.68 | Yes | N/A | N/A | 2024-09-13 | 2024-09-17 | 5 | 3 | 2024-09-17 | 2024-09-17 | 1 | 1 | 2024-09-17 | 2024-10-18 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-11-14 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-11-20 | 1900-01-06 | 5 | 2024-11-20 | 2024-11-20 | 1 | 1 | 65 | 47 | 9 | 7 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-05 | -604 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-29 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | -5.15 | -5.31 | Unknown | Unknown | Unknown | 0.16 | Unknown | 163.83 | -5.15 | 168.98 | Yes | N/A | N/A | 2024-03-18 | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2024-04-16 | 63 | 45 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-04-22 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-06-11 | 1900-02-19 | 37 | 2024-06-11 | 2024-06-11 | 1 | 1 | 7 | 5 | 115 | 83 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 502 | 359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | 2023-11-03 | 2024-08-14 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 16878.47 | 15278.33 | Unknown | Unknown | -113245.41 | 114845.55 | Unknown | 110029.5 | 16878.47 | 93151.03 | Yes | N/A | N/A | 2023-11-03 | 2024-02-27 | 117 | 83 | 2024-02-27 | 2024-05-30 | 94 | 68 | 2024-03-12 | 2024-04-01 | 21 | 15 | 2024-05-31 | 2024-06-21 | 22 | 16 | 2024-06-10 | Unknown | Unknown | Unknown | 2024-06-10 | 2024-08-02 | 54 | 40 | 2024-08-14 | 2024-10-15 | 1900-03-03 | 45 | 2024-10-15 | 2024-10-15 | 1 | 1 | 138 | 98 | 234 | 170 | 372 | 268 | Steps 2,3,5,6,7 | 90 | 66 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-22 | 220 | 157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -720.07 | Unknown | Unknown | Unknown | -837.87 | 117.8 | Unknown | 729.7 | -720.07 | 1449.77 | Yes | N/A | N/A | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | 2024-08-20 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | Unknown | Unknown | Unknown | 2025-01-28 | Unknown | Unknown | 2025-01-28 | 2025-01-28 | 1 | 1 | 21 | 15 | 2 | 2 | 23 | 17 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | -674 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | 116.62 | -1.5 | Unknown | Unknown | Unknown | 118.12 | 3981 | 1666.28 | 116.62 | 1549.66 | Yes | N/A | N/A | 2025-01-28 | 2025-01-24 | Unknown | Unknown | 2025-01-24 | 2025-01-28 | 5 | 3 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-03-03 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-18 | 1900-01-15 | 12 | 2025-03-18 | 2025-03-18 | 1 | 1 | 35 | 25 | 22 | 16 | 57 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Alpine | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-14 | -249 | -179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | 2024-10-05 | IOU Designed & Installed | N/A | No | N/A | -1568.21 | 303.12 | Unknown | 38.53 | -2121 | 211.14 | Unknown | 2120.56 | -1568.21 | 3688.77 | Yes | N/A | N/A | 2024-09-06 | 2024-09-09 | 4 | 2 | 2024-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-05 | 2024-10-08 | 1900-01-03 | 2 | 2024-10-08 | 2024-10-08 | 1 | 1 | 4 | 2 | 5 | 3 | 9 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Marcos | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-03 | -23 | -18 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-26 | 2023-01-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1034.02 | 1079.26 | Unknown | 290.43 | -2834 | 430.29 | Unknown | 2834.07 | -1034.02 | 3868.09 | Yes | N/A | N/A | 2023-01-26 | 2023-01-31 | 6 | 4 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 6 | 4 | 1 | 1 | 7 | 5 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-14 | 31 | 22 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-08-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -392.63 | 1408.66 | Unknown | 135.37 | -2566 | 629.34 | Unknown | 2565.77 | -392.63 | 2958.4 | Yes | N/A | N/A | 2023-07-17 | 2024-03-13 | 241 | 173 | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 241 | 173 | 1 | 1 | 242 | 174 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-06 | -282 | -201 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2023-10-26 | 2023-12-06 | IOU Designed & Installed | N/A | No | N/A | -916.7 | 1862.88 | Unknown | 866.01 | -4454 | 808.41 | Unknown | 4454.15 | -916.7 | 5370.85 | Yes | N/A | N/A | 2023-10-25 | 2023-11-01 | 8 | 6 | 2023-11-01 | 2023-12-29 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | Unknown | Unknown | Unknown | 2023-12-29 | 2023-12-29 | 1 | 1 | 2023-12-06 | 2023-12-29 | 1900-01-23 | 18 | 2023-12-29 | 2023-12-29 | 1 | 1 | 8 | 6 | 85 | 63 | 93 | 69 | Steps 2,3,5,6,7 | 23 | 17 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9611 | 9611 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-12-22 | -607 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | 983.22 | 359.19 | Unknown | Unknown | Unknown | 624.03 | 3981 | 814.57 | 983.22 | -168.65 | Yes | N/A | N/A | 2024-04-15 | 2023-12-29 | Unknown | Unknown | 2023-12-29 | 2024-04-15 | 109 | 77 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-04-22 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-04-24 | 1900-01-02 | 3 | 2024-04-24 | 2024-04-24 | 1 | 1 | 8 | 6 | 113 | 81 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-30 | -489 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 1287.69 | Unknown | Unknown | Unknown | 36.25 | 1251.44 | Unknown | 1484.41 | 1287.69 | 196.72 | Yes | N/A | N/A | 2024-09-27 | 2024-09-11 | Unknown | Unknown | 2024-09-11 | 2024-11-08 | 59 | 43 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | 2025-04-01 | 145 | 103 | Unknown | 2025-01-03 | Unknown | Unknown | 2025-04-01 | 2025-04-28 | 1900-01-27 | 20 | 2025-04-28 | 2025-04-28 | 1 | 1 | 145 | 103 | 88 | 64 | 233 | 167 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-11 | -149 | -106 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | 2024-01-26 | IOU Designed & Installed | N/A | No | N/A | -10.52 | -8.54 | Unknown | Unknown | Unknown | -1.98 | Unknown | 152.86 | -10.52 | 163.38 | Yes | N/A | N/A | 2023-10-31 | 2023-10-31 | 1 | 1 | 2023-10-31 | 2023-10-31 | 1 | 1 | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2024-01-26 | 88 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-03-15 | 1900-02-18 | 36 | 2024-03-15 | 2024-03-15 | 1 | 1 | 89 | 65 | 52 | 38 | 141 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | -289 | -208 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-12-04 | 2024-04-18 | IOU Designed & Installed | N/A | No | N/A | 579.42 | -13.11 | Unknown | Unknown | 11.2 | 581.33 | 3981 | 1001.51 | 579.42 | 422.09 | Yes | N/A | N/A | 2023-11-20 | 2023-08-23 | Unknown | Unknown | 2023-08-23 | 2023-12-04 | 104 | 74 | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2024-04-18 | 137 | 99 | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-10-16 | 1900-06-30 | 130 | 2024-10-16 | 2024-10-16 | 1 | 1 | 137 | 99 | 287 | 205 | 424 | 304 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | EN 1167-G2 | EN 1167-G2 | 244 | 244 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | 340 | 244 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-07-29 | 2024-11-20 | IOU Designed & Installed | N/A | No | N/A | 88668.03 | 22119.12 | Unknown | Unknown | -4134.25 | 70683.16 | 6559.49 | 26025.2 | 88668.03 | -62642.83 | Yes | N/A | N/A | 2023-01-23 | 2023-03-16 | 53 | 39 | 2023-03-16 | 2024-05-23 | 435 | 311 | 2023-08-14 | 2024-05-22 | 18 | 14 | 2023-10-20 | 2024-11-13 | 12 | 8 | 2024-05-31 | Unknown | Unknown | Unknown | 2024-05-31 | 2024-11-07 | 161 | 115 | 2024-11-20 | 2024-12-05 | 1900-01-15 | 12 | 2024-12-05 | 2024-12-05 | 1 | 1 | 71 | 53 | 625 | 447 | 696 | 500 | Steps 2,3,5,6,7 | 664 | 474 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-16 | -300 | -215 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-04-19 | 2023-10-16 | IOU Designed & Installed | N/A | No | N/A | 406.22 | 230.13 | Unknown | Unknown | Unknown | 176.09 | Unknown | 148.62 | 406.22 | -257.6 | Yes | N/A | N/A | 2023-04-19 | 2023-06-09 | 52 | 38 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2023-10-16 | 130 | 92 | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2024-03-22 | 1900-06-07 | 115 | 2024-03-22 | 2024-03-22 | 1 | 1 | 182 | 130 | 160 | 116 | 342 | 246 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-06 | 149 | 106 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -7.78 | -6.31 | Unknown | Unknown | Unknown | -1.47 | 26990 | 532.4 | -7.78 | 540.18 | Yes | N/A | N/A | 2023-09-14 | 2023-11-06 | 54 | 38 | 2023-11-06 | 2023-11-07 | 2 | 2 | 2023-10-05 | 2023-10-10 | 6 | 4 | 2023-09-26 | 2024-01-22 | 115 | 83 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-06-03 | 1 | 1 | 60 | 42 | 118 | 86 | 178 | 128 | Steps 2,3,5,6,7 | 123 | 87 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 86 | 86 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-12 | 89 | 64 | No | 2022-08-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-26 | 2022-08-29 | 2024-02-29 | IOU Designed & Installed | N/A | Yes | 249 | 274.26 | -18.82 | Unknown | Unknown | 9.3 | 283.78 | 3885 | 905.34 | 274.26 | 631.08 | Yes | N/A | N/A | 2022-08-26 | 2023-05-02 | 250 | 178 | 2023-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-08-29 | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2024-02-29 | 1899-12-31 | 1 | 2024-02-29 | 2023-10-09 | Unknown | Unknown | 250 | 178 | 1 | 1 | 251 | 179 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-04 | -142 | -103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-06-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1907.32 | 1912.19 | Unknown | 498.53 | -1417 | 913.6 | 0 | 1416.99 | 1907.32 | -490.33 | Yes | N/A | N/A | 2023-06-09 | 2023-06-09 | 1 | 1 | 2023-06-09 | 2023-07-12 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 35 | 25 | 36 | 26 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | -690 | -495 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-04 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | 1181.27 | -24.38 | Unknown | Unknown | Unknown | 1205.65 | 3981 | 1690.41 | 1181.27 | 509.14 | Yes | N/A | N/A | 2025-04-04 | 2025-04-04 | 1 | 1 | 2025-04-04 | 2025-04-04 | 1 | 1 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-07 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-05-05 | 1900-01-28 | 21 | 2025-05-05 | 2025-05-05 | 1 | 1 | 5 | 3 | 31 | 23 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | 12 | 9 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2023-05-25 | 2024-02-02 | IOU Designed & Installed | N/A | No | N/A | 6116.64 | -29.36 | Unknown | Unknown | -4129 | 10275 | Unknown | 3768.87 | 6116.64 | -2347.77 | Yes | N/A | N/A | 2023-05-25 | 2023-05-25 | 1 | 1 | 2023-05-25 | 2023-06-20 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | 2023-12-14 | 178 | 128 | Unknown | 2024-02-12 | Unknown | Unknown | 2024-02-02 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2024-01-24 | 1 | 1 | 179 | 129 | 28 | 20 | 207 | 149 | Steps 2,3,5,6,7 | 10 | 6 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-21 | -242 | -174 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-07-25 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | -2444.77 | 615.84 | Unknown | 142.41 | -3623 | 419.98 | Unknown | 3623.45 | -2444.77 | 6068.22 | Yes | N/A | N/A | 2024-07-25 | 2024-07-31 | 7 | 5 | 2024-07-31 | 2024-10-18 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | 2024-08-26 | 2024-10-22 | 1900-02-26 | 42 | 2024-10-22 | 2024-10-22 | 1 | 1 | 7 | 5 | 139 | 101 | 146 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-11 | -599 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-03-31 | 2025-05-09 | IOU Designed & Installed | N/A | No | N/A | 2278.56 | -9.73 | Unknown | Unknown | 2.94 | 2285.35 | 3981 | 1276.18 | 2278.56 | -1002.38 | Yes | N/A | N/A | 2025-03-31 | 2025-04-10 | 11 | 9 | 2025-04-10 | 2025-04-11 | 2 | 2 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-05-09 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-22 | 1900-01-13 | 10 | 2025-05-22 | 2025-05-22 | 1 | 1 | 40 | 30 | 17 | 13 | 57 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-13 | -543 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-04-12 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | -999.76 | Unknown | Unknown | Unknown | -1468 | 468.24 | Unknown | 1468.47 | -999.76 | 2468.23 | Yes | N/A | N/A | 2024-04-08 | 2024-06-13 | 67 | 49 | 2024-06-13 | 2024-07-03 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-08-19 | 1900-01-28 | 21 | 2024-08-19 | 2024-08-19 | 1 | 1 | 67 | 49 | 51 | 37 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 326.4 | 326.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-17 | -295 | -212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-17 | 2023-03-27 | IOU Designed & Installed | N/A | No | N/A | 719.56 | 236.04 | Unknown | 88.1 | Unknown | 395.42 | Unknown | 217.6 | 719.56 | -501.96 | Yes | N/A | N/A | 2023-02-15 | 2023-02-17 | 3 | 3 | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-17 | 2023-03-27 | 39 | 27 | Unknown | 2025-03-05 | Unknown | Unknown | 2023-03-27 | 2023-03-28 | 1900-01-01 | 2 | 2023-03-28 | 2023-03-28 | 1 | 1 | 42 | 30 | 3 | 3 | 45 | 33 | Steps 2,3,5,6,7 | 709 | 507 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | CALTRANS-Orange County | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-30 | -648 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3397.91 | -49.34 | Unknown | Unknown | Unknown | 3447.25 | 3981 | 1600.94 | 3397.91 | -1796.97 | Yes | N/A | N/A | 2024-12-09 | 2024-12-10 | 2 | 2 | 2024-12-10 | 2025-01-14 | 36 | 26 | 2025-01-14 | Unknown | Unknown | Unknown | 2025-01-14 | 2025-01-21 | 8 | 6 | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-02-20 | 1 | 1 | 2 | 2 | 45 | 33 | 47 | 35 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-06 | -570 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-18 | 2024-03-11 | IOU Designed & Installed | N/A | No | N/A | 11.53 | -10.26 | Unknown | Unknown | Unknown | 21.79 | Unknown | 874.63 | 11.53 | 863.1 | Yes | N/A | N/A | 2024-01-08 | 2024-01-18 | 11 | 9 | 2024-01-18 | 2024-01-18 | 1 | 1 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-03-11 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | 2024-03-15 | 1900-01-04 | 5 | 2024-03-15 | 2024-03-15 | 1 | 1 | 65 | 47 | 7 | 7 | 72 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-23 | -315 | -226 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-05 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | -3837.49 | 606.36 | Unknown | Unknown | -4860 | 416.15 | Unknown | 4860.48 | -3837.49 | 8697.97 | Yes | N/A | N/A | 2024-06-05 | 2024-06-05 | 1 | 1 | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-07-12 | 1900-01-03 | 4 | 2024-07-12 | 2024-07-12 | 1 | 1 | 1 | 1 | 5 | 5 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | Rancho Mission Viejo | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 50 | 37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-25 | 2022-01-25 | 2023-06-23 | IOU Designed & Installed | N/A | No | N/A | 148629.11 | 41365.9 | Unknown | Unknown | -45186.83 | 152450.04 | Unknown | 123559.36 | 148629.11 | -25069.75 | Yes | N/A | N/A | 2022-01-25 | 2023-02-17 | 389 | 279 | 2023-02-17 | 2023-05-23 | 96 | 68 | 2023-01-11 | 2023-04-14 | 44 | 32 | 2023-04-17 | 2023-04-24 | 8 | 6 | 2023-02-22 | Unknown | Unknown | Unknown | 2023-02-22 | 2023-06-12 | 111 | 79 | 2023-06-23 | 2023-07-21 | 1900-01-28 | 21 | 2023-07-21 | 2023-07-21 | 1 | 1 | 433 | 311 | 245 | 175 | 678 | 486 | Steps 2,3,5,6,7 | 61 | 43 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 93.05 | 93.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-22 | 94 | 67 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2024-01-26 | 2024-06-12 | IOU Designed & Installed | N/A | No | N/A | 11021.51 | 89.5 | Unknown | Unknown | -410.69 | 11342.7 | 0 | 533.25 | 11021.51 | -10488.26 | Yes | N/A | N/A | 2023-05-24 | 2023-08-29 | 98 | 70 | 2023-08-29 | 2024-04-17 | 233 | 167 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-09-24 | 1900-04-14 | 75 | 2024-09-24 | 2024-09-24 | 1 | 1 | 98 | 70 | 339 | 243 | 437 | 313 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-06 | -679 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-23 | 2025-05-30 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1304.82 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-23 | 2025-05-16 | Unknown | Unknown | 2025-05-16 | 2025-05-30 | 15 | 11 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-11 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-26 | 1900-01-15 | 12 | 2025-06-26 | 2025-06-26 | 1 | 1 | 13 | 9 | 32 | 24 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | Both | IOU Design | Commercial | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-10-31 | 1385 | 990 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-03 | 2022-08-03 | 2023-07-06 | IOU Designed & Installed | N/A | No | N/A | 77439.47 | 16352.26 | Unknown | Unknown | 109.23 | 60977.98 | Unknown | 70211.64 | 77439.47 | -7227.83 | Yes | N/A | N/A | 2022-08-03 | 2023-06-08 | 310 | 222 | 2023-06-08 | 2023-07-05 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2023-06-30 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-08-16 | 1900-02-10 | 30 | 2023-08-16 | 2023-08-16 | 1 | 1 | 310 | 222 | 93 | 67 | 403 | 289 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-31 | 598 | 429 | No | 2023-11-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | 2025-03-13 | IOU Designed & Installed | N/A | Yes | 463 | -392.6 | 28.2 | Unknown | Unknown | -501 | 80.2 | 3981 | 1532.96 | -392.6 | 1925.56 | Yes | N/A | N/A | 2023-11-09 | 2025-02-14 | 464 | 332 | 2025-02-14 | Unknown | Unknown | Unknown | 2024-09-24 | 2024-09-24 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | Unknown | Unknown | 2025-03-13 | 2025-03-21 | 1900-01-08 | 7 | 2025-03-21 | 2025-03-20 | Unknown | Unknown | 465 | 333 | 9 | 7 | 474 | 340 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | -464 | -333 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-10 | 2025-05-09 | IOU Designed & Installed | N/A | No | N/A | 1576.11 | Unknown | Unknown | Unknown | Unknown | 1576.11 | Unknown | 568.92 | 1576.11 | -1007.19 | Yes | N/A | N/A | 2024-09-05 | 2024-09-06 | 2 | 2 | 2024-09-06 | Unknown | Unknown | Unknown | 2024-10-17 | 2024-11-27 | 42 | 30 | 2024-09-19 | 2024-12-11 | 44 | 32 | 2025-01-07 | 2025-05-09 | 123 | 89 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-12 | 1900-01-03 | 2 | 2025-05-12 | 2025-05-12 | 1 | 1 | 167 | 121 | 49 | 35 | 216 | 156 | Steps 2,3,5,6,7 | 69 | 49 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-29 | -222 | -160 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-06-01 | 2023-10-06 | IOU Designed & Installed | N/A | No | N/A | 0.92 | -12.59 | Unknown | Unknown | Unknown | 13.51 | 3981 | 976.29 | 0.92 | 975.37 | Yes | N/A | N/A | 2023-06-01 | 2023-06-01 | 1 | 1 | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | 2023-10-06 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | 2023-12-05 | 1900-03-01 | 43 | 2023-12-05 | 2023-11-20 | Unknown | Unknown | 129 | 93 | 61 | 43 | 190 | 136 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | -584 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-02-26 | 2024-03-11 | IOU Designed & Installed | N/A | No | N/A | -25.04 | -12.39 | Unknown | Unknown | Unknown | -12.65 | 3981 | 983.09 | -25.04 | 1008.13 | Yes | N/A | N/A | 2024-01-19 | 2024-02-26 | 39 | 27 | 2024-02-26 | 2024-02-26 | 1 | 1 | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-03-11 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | 2024-03-20 | 1900-01-09 | 8 | 2024-03-20 | 2024-03-18 | Unknown | Unknown | 54 | 38 | 11 | 9 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-25 | -681 | -488 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-02-28 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | 44.85 | Unknown | Unknown | Unknown | Unknown | 44.85 | 3981 | 1665.51 | 44.85 | 1620.66 | Yes | N/A | N/A | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-04-09 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-15 | 1900-01-06 | 5 | 2025-04-15 | 2025-04-15 | 1 | 1 | 42 | 30 | 9 | 7 | 51 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LADERA RANCH | N/A | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-06 | -282 | -203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | 2023-11-26 | IOU Designed & Installed | N/A | No | N/A | 651.78 | 246.68 | Unknown | Unknown | Unknown | 405.1 | 3981 | 1031.49 | 651.78 | 379.71 | Yes | N/A | N/A | 2023-09-22 | 2023-09-25 | 4 | 2 | 2023-09-25 | 2023-09-25 | 1 | 1 | 2023-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | 2023-11-26 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2023-11-26 | 2023-11-29 | 1900-01-03 | 3 | 2023-11-29 | 2023-11-29 | 1 | 1 | 67 | 47 | 6 | 5 | 73 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Valley Center | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | 69 | 50 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 781.2 | 1931 | Unknown | 462.54 | -2516 | 903.66 | 0 | 2515.62 | 781.2 | 1734.42 | Yes | N/A | N/A | 2023-02-07 | 2023-02-08 | 2 | 2 | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | Unknown | Unknown | 2024-04-09 | 2024-04-09 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-06 | -476 | -341 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-10-28 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | 237.94 | Unknown | Unknown | Unknown | -824 | 1061.94 | Unknown | 688.95 | 237.94 | 451.01 | Yes | N/A | N/A | 2024-09-13 | 2024-10-28 | 46 | 32 | 2024-10-28 | 2024-10-28 | 1 | 1 | 2024-10-28 | 2024-12-06 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-03-03 | 88 | 62 | Unknown | 2025-02-26 | Unknown | Unknown | 2025-03-03 | 2025-03-17 | 1900-01-14 | 11 | 2025-03-17 | 2025-03-17 | 1 | 1 | 174 | 124 | 17 | 13 | 191 | 137 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 104 | 75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-06-06 | 2023-07-13 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 680.99 | Unknown | Unknown | Yes | N/A | N/A | 2023-03-30 | 2023-04-07 | 9 | 7 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | 2023-07-13 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | 2023-07-14 | 1900-01-01 | 2 | 2023-07-14 | 2023-07-14 | 1 | 1 | 47 | 35 | 3 | 3 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | -197 | -141 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.1 | -5.88 | Unknown | Unknown | Unknown | 0.78 | 3981 | 154.79 | -5.1 | 159.89 | Yes | N/A | N/A | 2023-02-28 | 2023-04-20 | 52 | 38 | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | Unknown | Unknown | 2024-05-24 | 2024-05-24 | 1 | 1 | 52 | 38 | 1 | 1 | 53 | 39 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | -586 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-06 | 2023-10-05 | IOU Designed & Installed | N/A | No | N/A | -4.65 | -3.4 | Unknown | Unknown | Unknown | -1.25 | Unknown | 480.37 | -4.65 | 485.02 | Yes | N/A | N/A | 2023-09-06 | 2023-06-07 | Unknown | Unknown | 2023-06-07 | 2023-09-06 | 92 | 66 | 2023-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | 2023-10-05 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-10-23 | 1900-01-18 | 13 | 2023-10-23 | 2023-10-23 | 1 | 1 | 30 | 22 | 112 | 80 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-27 | -639 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-15 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | 2207.75 | -69.88 | Unknown | Unknown | Unknown | 2277.63 | 3981 | 2105.82 | 2207.75 | -101.93 | Yes | N/A | N/A | 2025-01-15 | 2025-01-02 | Unknown | Unknown | 2025-01-02 | 2025-01-15 | 14 | 10 | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-01-29 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-03-28 | 1900-02-27 | 43 | 2025-03-28 | 2025-03-28 | 1 | 1 | 15 | 11 | 74 | 54 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 23 | 23 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | -291 | -209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 7962 | 835.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-04-25 | 2024-04-26 | 2 | 2 | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | 2025-05-28 | 2025-05-27 | Unknown | Unknown | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 57 | 57 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-17 | 515 | 368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-26 | 2024-05-02 | IOU Designed & Installed | N/A | No | N/A | 294.64 | -8.81 | Unknown | Unknown | 0.5 | 302.95 | 3981 | 1033.41 | 294.64 | 738.77 | Yes | N/A | N/A | 2024-02-08 | 2024-02-22 | 15 | 11 | 2024-02-22 | 2024-02-26 | 5 | 3 | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-05-02 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-07-23 | 1900-03-23 | 59 | 2024-07-23 | 2024-08-13 | 22 | 16 | 82 | 60 | 110 | 78 | 192 | 138 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-19 | -162 | -117 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 330.79 | Unknown | Unknown | Unknown | 14.49 | 316.3 | 3981 | 788.11 | 330.79 | 457.32 | Yes | N/A | N/A | 2024-03-27 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-04-16 | 55 | 39 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | Unknown | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-04-10 | 1 | 1 | 0 | 0 | 56 | 40 | 56 | 40 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-04 | 65 | 48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 213.45 | -4.29 | Unknown | Unknown | Unknown | 217.74 | Unknown | 498.17 | 213.45 | 284.72 | Yes | N/A | N/A | 2024-08-29 | 2024-07-03 | Unknown | Unknown | 2024-07-03 | 2025-04-14 | 286 | 204 | 2024-10-25 | 2024-10-28 | 4 | 2 | 2024-08-29 | 2024-12-02 | 94 | 68 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | 2025-05-08 | 2025-05-08 | 1 | 1 | 4 | 2 | 381 | 273 | 385 | 275 | Steps 2,3,5,6,7 | 231 | 163 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 159.05 | 159.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-11 | -563 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | -1143.67 | -6.07 | Unknown | Unknown | -1375 | 237.4 | Unknown | 1257.9 | -1143.67 | 2401.57 | Yes | N/A | N/A | 2024-05-09 | 2024-05-17 | 9 | 7 | 2024-05-17 | 2025-03-07 | 295 | 211 | 2025-03-07 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-17 | 32 | 22 | Unknown | 2024-06-12 | Unknown | Unknown | 2024-06-17 | 2024-06-28 | 1900-01-11 | 10 | 2024-06-28 | 2024-06-27 | Unknown | Unknown | 41 | 29 | 307 | 221 | 348 | 250 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-25 | -326 | -235 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-07 | 2023-11-30 | IOU Designed & Installed | N/A | No | N/A | -8675.61 | 4707.75 | Unknown | Unknown | -15266 | 1882.64 | Unknown | 15265.99 | -8675.61 | 23941.6 | Yes | N/A | N/A | 2023-11-07 | 2023-11-07 | 1 | 1 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2023-12-04 | 1900-01-04 | 3 | 2023-12-04 | 2023-12-04 | 1 | 1 | 1 | 1 | 6 | 4 | 7 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-16 | -214 | -153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-01-19 | 2025-01-19 | IOU Designed & Installed | N/A | No | N/A | 533.9 | -10.74 | Unknown | Unknown | Unknown | 544.64 | 3981 | 895.38 | 533.9 | 361.48 | Yes | N/A | N/A | 2024-01-16 | 2023-09-22 | Unknown | Unknown | 2023-09-22 | 2024-01-19 | 120 | 86 | 2024-01-19 | Unknown | Unknown | Unknown | 2024-12-17 | 2024-12-31 | 15 | 11 | 2024-01-19 | 2025-01-19 | 367 | 261 | Unknown | Unknown | Unknown | Unknown | 2025-01-19 | 2025-02-14 | 1900-01-26 | 20 | 2025-02-14 | 2025-02-14 | 1 | 1 | 367 | 261 | 163 | 118 | 530 | 379 | Steps 2,3,5,6,7 | 347 | 247 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-30 | 670 | 480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-20 | 2022-01-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 75915.44 | 11671.02 | Unknown | Unknown | Unknown | 64244.42 | 840935 | 24864.42 | 75915.44 | -51051.02 | Yes | N/A | N/A | 2022-01-20 | 2023-03-28 | 433 | 309 | 2023-03-28 | 2023-08-15 | 141 | 101 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | Unknown | Unknown | Unknown | 2024-04-01 | Unknown | Unknown | 2024-04-01 | 2024-03-30 | Unknown | Unknown | 433 | 309 | 141 | 101 | 574 | 410 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-28 | -136 | -99 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-03-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.92 | -5.71 | Unknown | Unknown | Unknown | 3.79 | 3981 | 658.28 | -1.92 | 660.2 | Yes | N/A | N/A | 2023-02-28 | 2023-03-28 | 29 | 21 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1 | 1 | 29 | 21 | 1 | 1 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8.4 | 8.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-30 | -682 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-29 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | 77.68 | Unknown | Unknown | Unknown | Unknown | 77.68 | 3981 | 1178.92 | 77.68 | 1101.24 | Yes | N/A | N/A | 2025-05-29 | 2025-05-09 | Unknown | Unknown | 2025-05-09 | 2025-05-29 | 21 | 15 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-10 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-17 | 1900-01-07 | 6 | 2025-06-17 | 2025-06-17 | 1 | 1 | 13 | 9 | 30 | 22 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-31 | 661 | 474 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2023-06-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8672.05 | 273.61 | Unknown | Unknown | Unknown | 8398.44 | 3981 | 1920.4 | 8672.05 | -6751.65 | Yes | N/A | N/A | 2023-05-24 | 2023-10-20 | 150 | 108 | 2023-10-20 | 2024-10-24 | 371 | 265 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | 2025-05-22 | 2025-05-22 | 1 | 1 | 150 | 108 | 372 | 266 | 522 | 374 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-19 | -157 | -114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2023-12-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 832.32 | 2509.02 | Unknown | 516.64 | -3363 | 1169.66 | Unknown | 3363.06 | 832.32 | 2530.74 | Yes | N/A | N/A | 2023-12-27 | 2023-12-26 | Unknown | Unknown | 2023-12-26 | 2024-01-30 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 37 | 27 | 37 | 27 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -346 | -249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-26 | 2024-02-10 | IOU Designed & Installed | N/A | No | N/A | 978.7 | 270.15 | Unknown | 134.36 | Unknown | 574.19 | Unknown | 297.38 | 978.7 | -681.32 | Yes | N/A | N/A | 2024-01-25 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2024-01-26 | 3 | 3 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-02-10 | 16 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-02-10 | 2024-02-13 | 1900-01-03 | 2 | 2024-02-13 | 2024-02-13 | 1 | 1 | 16 | 11 | 8 | 6 | 24 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | -539 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-06-06 | 2023-08-04 | IOU Designed & Installed | N/A | No | N/A | 447.68 | -6.36 | Unknown | Unknown | Unknown | 454.04 | 3981 | 633.01 | 447.68 | 185.33 | Yes | N/A | N/A | 2023-03-13 | 2023-06-06 | 86 | 62 | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | 2023-08-04 | 60 | 44 | Unknown | 2023-08-03 | Unknown | Unknown | 2023-08-04 | 2023-08-11 | 1900-01-07 | 6 | 2023-08-11 | 2023-08-11 | 1 | 1 | 146 | 106 | 9 | 7 | 155 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | -299 | -214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-23 | IOU Designed & Installed | N/A | No | N/A | -1.28 | -3.84 | Unknown | Unknown | Unknown | 2.56 | Unknown | 389.6 | -1.28 | 390.88 | Yes | N/A | N/A | 2023-03-14 | 2023-03-14 | 1 | 1 | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-14 | 2023-03-23 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | 2023-04-08 | 1900-01-16 | 12 | 2023-04-08 | 2023-04-08 | 1 | 0 | 11 | 9 | 18 | 12 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -241 | -172 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-26 | 2025-04-03 | IOU Designed & Installed | N/A | No | N/A | 106.52 | -18.48 | Unknown | Unknown | -1212.85 | 1337.85 | Unknown | 1213.62 | 106.52 | 1107.1 | Yes | N/A | N/A | 2024-02-07 | 2024-06-26 | 141 | 101 | 2024-06-26 | 2024-07-01 | 6 | 4 | 2024-07-01 | 2025-02-12 | 227 | 163 | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-04-03 | 51 | 37 | Unknown | 2025-03-18 | Unknown | Unknown | 2025-04-03 | 2025-04-03 | 1899-12-31 | 1 | 2025-04-03 | 2025-04-03 | 1 | 1 | 419 | 301 | 8 | 6 | 427 | 307 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | -535 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-29 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | 501.18 | -19.67 | Unknown | Unknown | Unknown | 520.85 | Unknown | 1163.84 | 501.18 | 662.66 | Yes | N/A | N/A | 2024-03-29 | 2023-12-08 | Unknown | Unknown | 2023-12-08 | 2024-03-29 | 113 | 81 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-04-22 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-06-10 | 1900-02-18 | 36 | 2024-06-10 | 2024-06-10 | 1 | 1 | 25 | 17 | 164 | 118 | 189 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | -443 | -318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 28.49 | Unknown | Unknown | Unknown | Unknown | 28.49 | 3981 | 1651.57 | 28.49 | 1623.08 | Yes | N/A | N/A | 2024-07-03 | 2024-06-05 | Unknown | Unknown | 2024-06-05 | 2024-07-03 | 29 | 21 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-08-26 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-09-10 | 1900-01-15 | 12 | 2024-09-10 | 2024-09-18 | 9 | 7 | 55 | 39 | 54 | 40 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-13 | -427 | -306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | 2024-04-09 | IOU Designed & Installed | N/A | No | N/A | 14.76 | -13.1 | Unknown | Unknown | Unknown | 27.86 | 3241 | 672.6 | 14.76 | 657.84 | Yes | N/A | N/A | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2024-04-09 | 156 | 112 | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2024-04-15 | 1900-01-06 | 5 | 2024-04-15 | 2024-04-12 | Unknown | Unknown | 157 | 113 | 8 | 6 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-24 | -696 | -498 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 30.57 | Unknown | Unknown | Unknown | Unknown | 30.57 | 3981 | 1573.37 | 30.57 | 1542.8 | Yes | N/A | N/A | 2024-10-30 | 2024-10-30 | 1 | 1 | 2024-10-30 | 2024-10-30 | 1 | 1 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2024-11-05 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2024-11-27 | 1900-01-22 | 17 | 2024-11-27 | 2024-11-27 | 1 | 1 | 8 | 6 | 25 | 19 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -436 | -313 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | -860.39 | Unknown | Unknown | Unknown | -919 | 58.61 | 3981 | 1713.05 | -860.39 | 2573.44 | Yes | N/A | N/A | 2024-07-03 | 2024-04-23 | Unknown | Unknown | 2024-04-23 | 2024-07-03 | 72 | 52 | 2024-07-03 | 2024-09-23 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2025-02-11 | 141 | 101 | Unknown | 2025-02-03 | Unknown | Unknown | 2025-02-11 | 2025-02-19 | 1900-01-08 | 7 | 2025-02-19 | 2025-02-19 | 1 | 1 | 224 | 160 | 82 | 60 | 306 | 220 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 449 | 449 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-20 | -453 | -324 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-08-01 | 2025-02-04 | IOU Designed & Installed | N/A | No | N/A | 47.13 | Unknown | Unknown | Unknown | Unknown | 47.13 | Unknown | 1770.12 | 47.13 | 1722.99 | Yes | N/A | N/A | 2024-07-02 | 2024-05-31 | Unknown | Unknown | 2024-05-31 | 2024-08-01 | 63 | 45 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2025-02-04 | 188 | 134 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-02-21 | 1900-01-17 | 14 | 2025-02-21 | 2025-02-21 | 1 | 1 | 188 | 134 | 82 | 60 | 270 | 194 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-06 | 100 | 71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 1417.03 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-18 | 2023-04-18 | 1 | 1 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community,Tribal Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-03-01 | 295 | 211 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-06-21 | 2024-12-19 | IOU Designed & Installed | N/A | No | N/A | 3150.12 | 1037.74 | Unknown | 13.65 | -1153.33 | 3252.06 | Unknown | 753.99 | 3150.12 | -2396.13 | Yes | N/A | N/A | 2024-06-21 | 2024-06-21 | 1 | 1 | 2024-06-21 | 2024-07-03 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-12-12 | 163 | 117 | Unknown | 2024-12-19 | Unknown | Unknown | 2024-12-19 | 2024-12-23 | 1900-01-04 | 3 | 2024-12-23 | 2024-12-21 | Unknown | Unknown | 164 | 118 | 18 | 12 | 182 | 130 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-12 | -356 | -255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-01-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 563.45 | -11.5 | Unknown | Unknown | -379 | 953.95 | Unknown | 489.06 | 563.45 | -74.39 | Yes | N/A | N/A | 2023-01-25 | 2023-02-12 | 19 | 13 | 2023-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-12 | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | Unknown | Unknown | Unknown | 2023-09-22 | Unknown | Unknown | 2023-09-22 | 2023-09-22 | 1 | 1 | 19 | 13 | 1 | 1 | 20 | 14 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-02 | -656 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-07-05 | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 669.72 | -12.92 | Unknown | Unknown | Unknown | 682.64 | 3981 | 1718.11 | 669.72 | 1048.39 | Yes | N/A | N/A | 2024-06-28 | 2024-06-05 | Unknown | Unknown | 2024-06-05 | 2024-07-05 | 31 | 23 | 2024-07-05 | Unknown | Unknown | Unknown | 2024-07-05 | 2024-07-19 | 15 | 11 | 2024-07-05 | 2024-08-14 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-08-15 | 1900-01-01 | 2 | 2024-08-15 | 2024-08-15 | 1 | 1 | 41 | 29 | 49 | 37 | 90 | 66 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-22 | -633 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-29 | 2024-05-03 | IOU Designed & Installed | N/A | No | N/A | 1279.66 | -39.19 | Unknown | Unknown | Unknown | 1318.85 | 3981 | 1215.67 | 1279.66 | -63.99 | Yes | N/A | N/A | 2024-04-17 | 2024-04-04 | Unknown | Unknown | 2024-04-04 | 2024-04-29 | 26 | 18 | 2024-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-05-03 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-05-30 | 1900-01-27 | 20 | 2024-05-30 | 2024-05-30 | 1 | 1 | 5 | 5 | 55 | 39 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-22 | -325 | -234 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | 2023-12-07 | IOU Designed & Installed | N/A | No | N/A | 1260.09 | -20.21 | Unknown | Unknown | 22.42 | 1257.88 | 3981 | 753.61 | 1260.09 | -506.48 | Yes | N/A | N/A | 2023-03-02 | 2023-07-31 | 152 | 108 | 2023-07-31 | 2023-08-22 | 23 | 17 | 2023-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2023-12-07 | 115 | 83 | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | 2024-02-27 | 1900-03-23 | 59 | 2024-02-27 | 2024-01-02 | Unknown | Unknown | 267 | 191 | 106 | 76 | 373 | 267 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 53 | 53 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-04 | 218 | 157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-02 | 2023-11-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3581.4 | Unknown | Unknown | Unknown | Unknown | 3581.4 | 58412 | 3004.66 | 3581.4 | -576.74 | Yes | N/A | N/A | 2022-11-02 | 2023-09-05 | 308 | 220 | 2023-09-05 | 2024-03-06 | 184 | 132 | 2023-11-10 | 2023-11-13 | 4 | 2 | 2024-10-18 | 2025-02-19 | 125 | 89 | 2024-03-06 | 2025-02-27 | 359 | 257 | Unknown | 2025-03-31 | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | 2025-04-15 | 2025-04-10 | Unknown | Unknown | 671 | 479 | 309 | 221 | 980 | 700 | Steps 2,3,5,6,7 | 467 | 333 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | -527 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-12 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1694.79 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2024-11-25 | Unknown | Unknown | 2024-11-25 | 2024-12-12 | 18 | 14 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-06-05 | 176 | 126 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-06-11 | 1900-01-06 | 5 | 2025-06-11 | 2025-06-11 | 1 | 1 | 176 | 126 | 26 | 20 | 202 | 146 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-07 | -572 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-29 | 2024-08-01 | IOU Designed & Installed | N/A | No | N/A | 659.06 | 190.31 | Unknown | Unknown | Unknown | 468.75 | 3981 | 1753.22 | 659.06 | 1094.16 | Yes | N/A | N/A | 2024-07-16 | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-07-31 | 59 | 43 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-08-01 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-09-12 | 1900-02-11 | 31 | 2024-09-12 | 2024-09-12 | 1 | 1 | 2 | 2 | 103 | 75 | 105 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 24 | 24 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | -573 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -745.12 | Unknown | Unknown | Unknown | -790 | 44.88 | 3981 | 1712.66 | -745.12 | 2457.78 | Yes | N/A | N/A | 2024-12-09 | 2025-01-10 | 33 | 25 | 2025-01-10 | 2025-01-16 | 7 | 5 | 2025-01-16 | 2025-02-07 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | 2025-02-21 | 2025-02-21 | 1 | 1 | 56 | 42 | 8 | 6 | 64 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-18 | -371 | -266 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | -11 | -7.96 | Unknown | Unknown | Unknown | -3.04 | Unknown | 363.72 | -11 | 374.72 | Yes | N/A | N/A | 2023-02-23 | 2023-02-23 | 1 | 1 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | Unknown | Unknown | 2023-10-13 | 2023-10-13 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | -631 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | Unknown | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 674.91 | -13.2 | Unknown | Unknown | Unknown | 688.11 | 3981 | 1558.29 | 674.91 | 883.38 | Yes | N/A | N/A | 2024-10-16 | 2024-10-17 | 2 | 2 | 2024-10-17 | 2024-10-17 | 1 | 1 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2024-10-18 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-10-31 | 1900-01-13 | 10 | 2024-10-31 | 2024-10-31 | 1 | 1 | 4 | 4 | 16 | 12 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-04 | -590 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | 2024-04-10 | IOU Designed & Installed | N/A | No | N/A | 6.03 | -5.36 | Unknown | Unknown | Unknown | 11.39 | 3981 | 952.79 | 6.03 | 946.76 | Yes | N/A | N/A | 2024-02-20 | 2024-02-22 | 3 | 3 | 2024-02-22 | 2024-02-23 | 2 | 2 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-04-10 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-04-23 | 1900-01-13 | 10 | 2024-04-23 | 2024-04-23 | 1 | 1 | 51 | 37 | 17 | 13 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | 600 | 430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 27.21 | Unknown | Unknown | Unknown | Unknown | 27.21 | Unknown | 423.67 | 27.21 | 396.46 | Yes | N/A | N/A | 2023-12-20 | 2023-12-20 | 1 | 1 | 2023-12-20 | 2024-02-09 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-06-20 | 133 | 95 | Unknown | 2024-06-28 | Unknown | Unknown | Unknown | 2024-08-26 | Unknown | Unknown | 2024-08-26 | 2024-08-23 | Unknown | Unknown | 134 | 96 | 52 | 38 | 186 | 134 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-24 | -383 | -274 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 4.03 | Unknown | Unknown | Unknown | Unknown | 4.03 | Unknown | 579.89 | 4.03 | 575.86 | Yes | N/A | N/A | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2025-01-30 | 156 | 112 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-06 | 1900-01-07 | 6 | 2025-02-06 | 2025-02-06 | 1 | 1 | 157 | 113 | 10 | 8 | 167 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-09 | 355 | 255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-30 | 2025-04-30 | 2025-05-30 | IOU Designed & Installed | N/A | No | N/A | -4259.33 | 416.72 | Unknown | Unknown | -5172 | 495.95 | Unknown | 5172.03 | -4259.33 | 9431.36 | Yes | N/A | N/A | 2025-04-30 | 2025-04-30 | 1 | 1 | 2025-04-30 | 2025-05-27 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | Unknown | 2025-05-27 | 2025-05-27 | 1 | 1 | 2025-05-30 | 2025-05-30 | 1899-12-31 | 1 | 2025-05-30 | 2025-05-30 | 1 | 1 | 1 | 1 | 31 | 23 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 26703 | 26703 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-12-31 | 176 | 127 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-13 | 2025-06-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 27867 | 750.86 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-03 | 2024-05-03 | 1 | 1 | 2024-05-03 | 2024-06-27 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2025-06-04 | 343 | 245 | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-06-25 | 1899-12-31 | 1 | 2025-06-25 | 2025-06-25 | 1 | 1 | 344 | 246 | 58 | 42 | 402 | 288 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 8664 | 8664 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-05-20 | -43 | -32 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 769.7 | -15.46 | Unknown | Unknown | Unknown | 785.16 | 15924 | 1190.82 | 769.7 | 421.12 | Yes | N/A | N/A | 2024-10-21 | 2024-10-21 | 1 | 1 | 2024-10-21 | 2024-10-29 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2025-04-07 | 161 | 115 | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | 2025-04-08 | 2025-04-07 | Unknown | Unknown | 162 | 116 | 9 | 7 | 171 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-16 | -280 | -201 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6.04 | Unknown | Unknown | Unknown | Unknown | 6.04 | 0 | 158.14 | 6.04 | 152.1 | Yes | N/A | N/A | 2023-10-09 | 2023-11-13 | 36 | 26 | 2023-11-13 | 2023-11-13 | 1 | 1 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2024-10-09 | 1 | 1 | 36 | 26 | 2 | 2 | 38 | 28 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-04-21 | 1322 | 945 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-09 | 2024-11-04 | IOU Designed & Installed | N/A | No | N/A | 46039.3 | 4990.52 | Unknown | Unknown | 5.88 | 41042.9 | 27454 | 20421.77 | 46039.3 | -25617.53 | Yes | N/A | N/A | 2024-09-09 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2024-10-10 | 213 | 153 | 2024-09-20 | 2024-09-25 | 6 | 4 | 2024-09-30 | 2024-10-09 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-12-03 | 1900-01-29 | 22 | 2024-12-03 | 2024-12-03 | 1 | 1 | 6 | 4 | 254 | 184 | 260 | 188 | Steps 2,3,5,6,7 | 20 | 14 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-16 | 96 | 69 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-31 | 2023-07-31 | 2024-08-05 | IOU Designed & Installed | N/A | No | N/A | 5190.22 | Unknown | Unknown | Unknown | 384.62 | 4805.6 | 3981 | 1376.79 | 5190.22 | -3813.43 | Yes | N/A | N/A | 2023-07-31 | 2023-05-30 | Unknown | Unknown | 2023-05-30 | 2023-08-04 | 67 | 49 | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | 2024-08-05 | 368 | 262 | Unknown | 2024-08-02 | Unknown | Unknown | 2024-08-05 | 2024-08-20 | 1900-01-15 | 12 | 2024-08-20 | 2024-08-20 | 1 | 1 | 368 | 262 | 84 | 62 | 452 | 324 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | 11.5 | 11.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-04 | -479 | -344 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 929.83 | 350.66 | Unknown | Unknown | Unknown | 579.17 | 3981 | 186.52 | 929.83 | -743.31 | Yes | N/A | N/A | 2024-08-22 | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-09-16 | 64 | 46 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2025-02-03 | 141 | 101 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-10 | 1900-01-07 | 6 | 2025-02-10 | 2025-02-10 | 1 | 1 | 141 | 101 | 73 | 53 | 214 | 154 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-17 | -635 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | 975.28 | -29.96 | Unknown | Unknown | Unknown | 1005.24 | Unknown | 517.33 | 975.28 | -457.95 | Yes | N/A | N/A | 2024-04-15 | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-04-15 | 48 | 34 | 2024-04-15 | Unknown | Unknown | Unknown | 2024-04-17 | 2024-05-08 | 22 | 16 | 2024-04-16 | 2024-04-17 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-04-22 | 1900-01-05 | 4 | 2024-04-22 | 2024-04-22 | 1 | 1 | 2 | 2 | 77 | 55 | 79 | 57 | Steps 2,3,5,6,7 | 22 | 16 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-08 | -138 | -99 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-02-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 30.69 | Unknown | Unknown | Unknown | Unknown | 30.69 | 7962 | 1052.36 | 30.69 | 1021.67 | Yes | N/A | N/A | 2024-01-29 | 2024-01-29 | 1 | 1 | 2024-01-29 | 2024-02-02 | 5 | 5 | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | Unknown | Unknown | 2024-08-23 | 2024-08-23 | 1 | 1 | 1 | 1 | 6 | 6 | 7 | 7 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | Both | Applicant Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-12 | -277 | -200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-11-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -3224.94 | 2082.66 | Unknown | 973.17 | -15652 | 9371.23 | Unknown | 16432.51 | -3224.94 | 19657.45 | Yes | N/A | N/A | 2024-04-25 | 2024-08-09 | 107 | 77 | 2024-08-09 | 2024-11-19 | 103 | 73 | 2024-08-21 | 2024-11-07 | 22 | 16 | 2024-09-09 | 2024-11-18 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-03-10 | 1900-04-15 | 76 | 2025-03-10 | 2025-03-10 | 1 | 1 | 129 | 93 | 233 | 167 | 362 | 260 | Steps 2,3,5,6,7 | 149 | 107 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-10 | -20 | -15 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-15 | 2024-08-16 | IOU Designed & Installed | N/A | No | N/A | 6409.35 | 1099.68 | Unknown | 882.59 | 4.15 | 4422.93 | 7962 | 2343.9 | 6409.35 | -4065.45 | Yes | N/A | N/A | 2023-11-15 | 2024-01-18 | 65 | 47 | 2024-01-18 | 2024-01-26 | 9 | 7 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-08-16 | 204 | 146 | Unknown | 2024-08-08 | Unknown | Unknown | 2024-08-16 | 2024-08-21 | 1900-01-05 | 4 | 2024-08-21 | 2024-08-21 | 1 | 1 | 269 | 193 | 16 | 12 | 285 | 205 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-07-11 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 878.82 | 253.74 | Unknown | Unknown | Unknown | 625.08 | Unknown | 1411.77 | 878.82 | 532.95 | Yes | N/A | N/A | 2024-06-27 | 2024-07-12 | 16 | 12 | 2024-07-12 | 2024-07-12 | 1 | 1 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-09-10 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-12 | 1900-01-02 | 3 | 2024-09-12 | 2024-09-12 | 1 | 1 | 77 | 55 | 5 | 5 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-05 | 411 | 294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-09-05 | 2025-02-07 | IOU Designed & Installed | N/A | No | N/A | 33.37 | Unknown | Unknown | Unknown | Unknown | 33.37 | 3981 | 1496.79 | 33.37 | 1463.42 | Yes | N/A | N/A | 2024-08-29 | 2024-08-27 | Unknown | Unknown | 2024-08-27 | 2024-09-05 | 10 | 8 | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2025-02-07 | 156 | 112 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-02-20 | 1900-01-13 | 10 | 2025-02-20 | 2025-02-19 | Unknown | Unknown | 156 | 112 | 24 | 18 | 180 | 130 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-29 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-13 | 2023-05-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -13.58 | -9.86 | Unknown | Unknown | Unknown | -3.72 | Unknown | 657 | -13.58 | 670.58 | Yes | N/A | N/A | 2023-04-13 | 2023-05-09 | 27 | 19 | 2023-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | Unknown | Unknown | 2023-06-22 | 2023-06-22 | 1 | 1 | 27 | 19 | 1 | 1 | 28 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | -599 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-08 | 2024-04-09 | IOU Designed & Installed | N/A | No | N/A | 91.74 | -14.24 | Unknown | Unknown | Unknown | 105.98 | 3981 | 1002.75 | 91.74 | 911.01 | Yes | N/A | N/A | 2024-03-27 | 2024-02-06 | Unknown | Unknown | 2024-02-06 | 2024-04-08 | 63 | 45 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | 2024-04-09 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2024-05-21 | 1900-02-11 | 31 | 2024-05-21 | 2024-05-21 | 1 | 1 | 2 | 2 | 107 | 77 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-31 | -199 | -142 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-07-24 | IOU Designed & Installed | N/A | No | N/A | 1129.72 | 577.54 | Unknown | 177.41 | Unknown | 374.77 | Unknown | 153.75 | 1129.72 | -975.97 | Yes | N/A | N/A | 2023-06-13 | 2023-06-14 | 2 | 2 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | 2023-07-24 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2023-09-14 | 1900-02-21 | 39 | 2023-09-14 | 2023-09-14 | 1 | 1 | 43 | 31 | 54 | 40 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-27 | -684 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-10 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | 2704.64 | 762.81 | Unknown | Unknown | Unknown | 1941.83 | 3981 | 1704.88 | 2704.64 | -999.76 | Yes | N/A | N/A | 2024-10-10 | 2024-10-10 | 1 | 1 | 2024-10-10 | 2024-10-10 | 1 | 1 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-10-11 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-11-12 | 1900-02-01 | 23 | 2024-11-12 | 2024-11-12 | 1 | 1 | 2 | 2 | 35 | 25 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-29 | -52 | -37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-10 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 731.28 | Unknown | Unknown | Unknown | 4.03 | 727.25 | 3241 | 1930.38 | 731.28 | 1199.1 | Yes | N/A | N/A | 2023-07-10 | 2023-07-10 | 1 | 1 | 2023-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | 2024-11-05 | 485 | 347 | Unknown | 2024-10-24 | Unknown | Unknown | 2024-11-05 | 2024-11-11 | 1900-01-06 | 5 | 2024-11-11 | 2024-11-07 | Unknown | Unknown | 486 | 348 | 7 | 5 | 493 | 353 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | N/A | SD 1169-J3 SKYLINE (E) | SD 1169-J3 SKYLINE (E) | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | 48 | 35 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2025-05-28 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 437966.54 | 123246.58 | Unknown | 7022.82 | 17147.39 | 290549.75 | 742892.7 | 151777.19 | 437966.54 | -286189.35 | Yes | N/A | N/A | 2023-02-13 | 2023-08-08 | 177 | 127 | 2023-08-08 | 2024-06-28 | 326 | 234 | 2023-08-30 | 2025-03-18 | 435 | 309 | 2023-04-28 | 2024-09-04 | 77 | 55 | 2024-06-28 | Unknown | Unknown | Unknown | 2024-07-17 | 2025-05-16 | 304 | 218 | 2025-05-28 | 2025-06-18 | 1900-01-21 | 16 | 2025-06-18 | 2025-06-18 | 1 | 1 | 612 | 436 | 730 | 524 | 1342 | 960 | Steps 2,3,5,6,7 | 1061 | 757 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 84.05 | 84.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-05 | -219 | -156 | No | 2023-12-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2024-01-16 | Unknown | IOU Designed & Installed | N/A | Yes | 236 | 41.2 | Unknown | Unknown | Unknown | Unknown | 41.2 | 3981 | 787.92 | 41.2 | 746.72 | Yes | N/A | N/A | 2023-12-21 | 2024-08-20 | 244 | 174 | 2024-08-20 | 2024-08-30 | 11 | 9 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | 2025-02-27 | 2025-02-28 | 2 | 2 | 244 | 174 | 13 | 11 | 257 | 185 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-10 | -168 | -121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-17 | 2022-11-17 | 2023-04-14 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 13872.97 | 796.96 | Unknown | 1621.44 | 0.79 | 11453.78 | Unknown | 7239.11 | 13872.97 | -6633.86 | Yes | N/A | N/A | 2022-11-17 | 2023-01-31 | 76 | 54 | 2023-01-31 | 2023-04-06 | 66 | 48 | 2023-01-31 | 2023-02-10 | 11 | 9 | 2023-04-06 | 2023-04-10 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | 2023-05-26 | 1900-02-11 | 31 | 2023-05-26 | 2023-05-26 | 1 | 1 | 87 | 63 | 115 | 83 | 202 | 146 | Steps 2,3,5,6,7 | 65 | 47 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 281 | 281 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | 285 | 204 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-06-18 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 3791.23 | Unknown | Unknown | Unknown | Unknown | 3791.23 | Unknown | 478.21 | 3791.23 | -3313.02 | Yes | N/A | N/A | 2024-04-30 | 2024-06-18 | 50 | 36 | 2024-06-18 | 2024-07-03 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-08-12 | 1900-01-20 | 15 | 2024-08-12 | 2024-08-12 | 1 | 1 | 50 | 36 | 38 | 28 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-21 | -470 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-18 | 2023-03-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1496.97 | -12.97 | Unknown | Unknown | Unknown | 1509.94 | Unknown | 699.6 | 1496.97 | -797.37 | Yes | N/A | N/A | 2023-03-18 | 2023-03-18 | 1 | 0 | 2023-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-08-09 | 1 | 1 | 1 | 0 | 1 | 1 | 2 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-24 | -527 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | 2024-04-01 | IOU Designed & Installed | N/A | No | N/A | -15.76 | -14.16 | Unknown | Unknown | Unknown | -1.6 | 3885 | 163.83 | -15.76 | 179.59 | Yes | N/A | N/A | 2023-12-05 | 2024-03-28 | 115 | 83 | 2024-03-28 | 2024-03-28 | 1 | 1 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-04-01 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-05-15 | 1900-02-13 | 33 | 2024-05-15 | 2024-05-15 | 1 | 1 | 120 | 86 | 47 | 35 | 167 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 97 | 97 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-30 | 224 | 161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-25 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | -11.02 | -9.01 | Unknown | Unknown | Unknown | -2.01 | Unknown | 31036.06 | -11.02 | 31047.08 | Yes | N/A | N/A | 2024-01-25 | 2023-12-06 | Unknown | Unknown | 2023-12-06 | 2024-01-25 | 51 | 37 | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-05-17 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-05-23 | 1900-01-06 | 5 | 2024-05-23 | 2024-09-10 | 111 | 79 | 114 | 82 | 169 | 121 | 283 | 203 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 158 | 158 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-13 | -688 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-25 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 37.93 | Unknown | Unknown | Unknown | Unknown | 37.93 | 3981 | 1405.34 | 37.93 | 1367.41 | Yes | N/A | N/A | 2024-06-20 | 2024-06-25 | 6 | 4 | 2024-06-25 | 2024-06-25 | 1 | 1 | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-02 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-25 | 1900-01-23 | 18 | 2024-07-25 | 2024-07-25 | 1 | 1 | 14 | 10 | 26 | 20 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-13 | -358 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-17 | 2024-06-18 | IOU Designed & Installed | N/A | No | N/A | -8.89 | -7.66 | Unknown | Unknown | Unknown | -1.23 | Unknown | 1841.48 | -8.89 | 1850.37 | Yes | N/A | N/A | 2024-06-17 | 2024-06-17 | 1 | 1 | 2024-06-17 | 2024-06-17 | 1 | 1 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-06-18 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-06-20 | 1900-01-02 | 3 | 2024-06-20 | 2024-06-20 | 1 | 1 | 3 | 3 | 5 | 5 | 8 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | 14.4 | 14.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-20 | -618 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 37.17 | Unknown | Unknown | Unknown | Unknown | 37.17 | 3981 | 1709.43 | 37.17 | 1672.26 | Yes | N/A | N/A | 2025-02-05 | 2025-02-27 | 23 | 17 | 2025-02-27 | 2025-03-03 | 5 | 3 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | 2025-04-11 | 2025-04-11 | 1 | 1 | 23 | 17 | 6 | 4 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-25 | -418 | -299 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 526.96 | -10.2 | Unknown | Unknown | Unknown | 537.16 | 3941 | 1397.69 | 526.96 | 870.73 | Yes | N/A | N/A | 2024-05-21 | 2024-04-02 | Unknown | Unknown | 2024-04-02 | 2024-05-21 | 50 | 36 | 2024-05-21 | Unknown | Unknown | Unknown | 2024-05-22 | 2024-05-31 | 10 | 8 | 2024-05-21 | 2025-01-27 | 252 | 180 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-01-31 | 1900-01-04 | 5 | 2025-01-31 | 2025-01-31 | 1 | 1 | 252 | 180 | 66 | 50 | 318 | 230 | Steps 2,3,5,6,7 | 10 | 8 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | -370 | -265 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-05-17 | 2024-10-16 | IOU Designed & Installed | N/A | No | N/A | 673.44 | -18.34 | Unknown | Unknown | 139.94 | 551.84 | 3981 | 1087.33 | 673.44 | 413.89 | Yes | N/A | N/A | 2024-02-15 | 2024-02-23 | 9 | 7 | 2024-02-23 | 2024-05-17 | 85 | 61 | 2024-05-17 | 2024-06-27 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-10-16 | 153 | 109 | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2025-06-05 | 1900-08-20 | 167 | 2025-06-05 | 2024-10-18 | Unknown | Unknown | 204 | 146 | 318 | 228 | 522 | 374 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 546 | 546 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | 352 | 252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1721.49 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-18 | 2024-10-16 | Unknown | Unknown | 2024-10-16 | 2024-10-18 | 3 | 3 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2024-12-17 | 1 | 1 | 0 | 0 | 4 | 4 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 88.05 | 88.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-15 | -14 | -11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-10-26 | 2023-11-07 | IOU Designed & Installed | N/A | No | N/A | 751.17 | -33.09 | Unknown | Unknown | Unknown | 784.26 | 3981 | 883.6 | 751.17 | 132.43 | Yes | N/A | N/A | 2023-10-23 | 2023-09-19 | Unknown | Unknown | 2023-09-19 | 2023-10-26 | 38 | 28 | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2023-11-07 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2023-12-01 | 1900-01-24 | 19 | 2023-12-01 | 2023-12-01 | 1 | 1 | 13 | 9 | 64 | 48 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-06 | -576 | -413 | No | 2024-09-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-17 | 2024-11-04 | IOU Designed & Installed | N/A | Yes | 56 | 19.92 | Unknown | Unknown | Unknown | Unknown | 19.92 | Unknown | 1489.11 | 19.92 | 1469.19 | Yes | N/A | N/A | 2024-09-06 | 2024-10-24 | 49 | 35 | 2024-10-24 | 2024-10-24 | 1 | 1 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-11-04 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-11-20 | 1900-01-16 | 13 | 2024-11-20 | 2025-01-07 | 49 | 35 | 98 | 70 | 67 | 49 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | -583 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-07-17 | 2024-08-13 | IOU Designed & Installed | N/A | No | N/A | 33.93 | Unknown | Unknown | Unknown | Unknown | 33.93 | 3981 | 1372.25 | 33.93 | 1338.32 | Yes | N/A | N/A | 2024-05-30 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-07-17 | 119 | 85 | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-08-13 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-08-26 | 1900-01-13 | 10 | 2024-08-26 | 2024-08-26 | 1 | 1 | 28 | 20 | 134 | 96 | 162 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | Chula Vista | Chula Vista | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | -14 | -11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | 2024-11-08 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 23926.19 | 1451.44 | Unknown | Unknown | 241.26 | 22233.49 | 307750 | 34124.19 | 23926.19 | 10198 | Yes | N/A | N/A | 2023-03-23 | 2023-09-29 | 191 | 137 | 2023-09-29 | 2024-05-16 | 231 | 165 | 2023-10-06 | 2024-05-14 | 21 | 13 | 2023-10-24 | 2024-05-22 | 17 | 13 | 2024-06-25 | Unknown | Unknown | Unknown | 2024-06-25 | 2024-10-08 | 106 | 76 | 2024-11-08 | 2024-12-18 | 1900-02-09 | 29 | 2024-12-18 | 2024-12-18 | 1 | 1 | 212 | 150 | 396 | 284 | 608 | 434 | Steps 2,3,5,6,7 | 426 | 304 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-02 | 5 | 4 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-03-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 43.28 | Unknown | Unknown | Unknown | Unknown | 43.28 | 3981 | 1021.96 | 43.28 | 978.68 | Yes | N/A | N/A | 2024-02-16 | 2024-03-06 | 20 | 14 | 2024-03-06 | 2024-11-04 | 244 | 174 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-03-29 | 11 | 9 | 2024-11-04 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-11-07 | Unknown | Unknown | 20 | 14 | 255 | 183 | 275 | 197 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 1 | 1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | -574 | -411 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | 2023-12-07 | IOU Designed & Installed | N/A | No | N/A | -13.12 | -10.81 | Unknown | Unknown | Unknown | -2.31 | Unknown | 158.14 | -13.12 | 171.26 | Yes | N/A | N/A | 2023-11-13 | 2023-07-21 | Unknown | Unknown | 2023-07-21 | 2023-11-16 | 119 | 85 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2023-12-07 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | 2023-12-15 | 1900-01-08 | 7 | 2023-12-15 | 2023-12-15 | 1 | 1 | 22 | 16 | 129 | 93 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 63.05 | 63.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-14 | -294 | -211 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1933.85 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-02-03 | 1 | 1 | 2025-02-03 | 2025-02-03 | 1 | 1 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-03-05 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-26 | 1900-01-21 | 16 | 2025-03-26 | 2025-03-26 | 1 | 1 | 32 | 24 | 24 | 18 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | -523 | -374 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-28 | 2024-04-10 | IOU Designed & Installed | N/A | No | N/A | 778.55 | 244.9 | Unknown | Unknown | Unknown | 533.65 | Unknown | 1007.09 | 778.55 | 228.54 | Yes | N/A | N/A | 2024-02-28 | 2023-11-03 | Unknown | Unknown | 2023-11-03 | 2024-02-28 | 118 | 84 | 2024-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-04-10 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-05-22 | 1900-02-11 | 31 | 2024-05-22 | 2024-05-22 | 1 | 1 | 43 | 31 | 162 | 116 | 205 | 147 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 175 | 126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-21 | 2022-09-21 | 2024-04-10 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 377190.76 | 79827.11 | Unknown | 1501.36 | 9294.57 | 286567.72 | 568548 | 228664.13 | 377190.76 | -148526.63 | Yes | N/A | N/A | 2022-09-21 | 2023-07-21 | 304 | 218 | 2023-07-21 | 2023-10-09 | 81 | 57 | 2023-05-24 | 2024-03-21 | 161 | 115 | 2023-05-02 | 2025-01-09 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2024-07-30 | 286 | 204 | 2024-04-10 | 2024-05-24 | 1900-02-13 | 33 | 2024-05-24 | 2024-05-24 | 1 | 1 | 465 | 333 | 539 | 385 | 1004 | 718 | Steps 2,3,5,6,7 | 573 | 409 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | -420 | -301 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-15 | 2023-07-15 | 2023-11-28 | IOU Designed & Installed | N/A | No | N/A | 0.74 | -9.57 | Unknown | Unknown | Unknown | 10.31 | 3981 | 893.06 | 0.74 | 892.32 | Yes | N/A | N/A | 2023-07-15 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-15 | 2023-11-28 | 137 | 97 | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2023-12-15 | 1900-01-17 | 14 | 2023-12-15 | 2023-12-15 | 1 | 1 | 137 | 97 | 19 | 15 | 156 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 448.05 | 448.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-27 | -338 | -243 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-05-15 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | -7.28 | -14.03 | Unknown | Unknown | Unknown | 6.75 | 3981 | 1060.44 | -7.28 | 1067.72 | Yes | N/A | N/A | 2023-01-18 | 2023-05-15 | 118 | 84 | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-15 | 2023-07-17 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-07-25 | 1900-01-08 | 7 | 2023-07-25 | 2023-07-25 | 1 | 1 | 182 | 130 | 10 | 8 | 192 | 138 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | -267 | -192 | No | 2025-03-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-24 | 2025-05-29 | IOU Designed & Installed | N/A | Yes | 14 | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1935.12 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-06 | 2025-04-02 | 28 | 20 | 2025-04-02 | 2025-04-07 | 6 | 4 | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-05-29 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-05 | 1900-01-07 | 6 | 2025-06-05 | 2025-06-04 | Unknown | Unknown | 81 | 59 | 14 | 10 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1044.05 | 1044.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-11-19 | -625 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 363 | 111.85 | Unknown | Unknown | Unknown | 251.15 | Unknown | 1716.42 | 363 | 1353.42 | Yes | N/A | N/A | 2025-01-08 | 2024-12-02 | Unknown | Unknown | 2024-12-02 | 2025-01-08 | 38 | 28 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-02-11 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-03-04 | 1900-01-21 | 16 | 2025-03-04 | 2025-03-04 | 1 | 1 | 34 | 24 | 61 | 45 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-20 | -243 | -174 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-24 | 2023-04-20 | IOU Designed & Installed | N/A | No | N/A | 746.01 | 378.08 | Unknown | 155.78 | Unknown | 212.15 | 0 | 351.99 | 746.01 | -394.02 | Yes | N/A | N/A | 2023-02-23 | 2023-02-24 | 2 | 2 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | 2023-04-20 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | 2024-03-22 | 1900-12-03 | 242 | 2024-03-22 | 2024-03-22 | 1 | 1 | 58 | 42 | 339 | 243 | 397 | 285 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-17 | -219 | -158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-20 | 2023-03-01 | 2023-05-08 | IOU Designed & Installed | N/A | No | N/A | -4.26 | -12.58 | Unknown | Unknown | Unknown | 8.32 | 3241 | 748.67 | -4.26 | 752.93 | Yes | N/A | N/A | 2023-02-20 | 2023-03-01 | 10 | 8 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | 2023-05-08 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | 2023-06-12 | 1900-02-04 | 26 | 2023-06-12 | 2023-06-12 | 1 | 1 | 79 | 57 | 37 | 27 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-16 | 75 | 54 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 446.52 | -36.07 | Unknown | Unknown | Unknown | 482.59 | 3981 | 2411.9 | 446.52 | 1965.38 | Yes | N/A | N/A | 2024-05-28 | 2024-05-07 | Unknown | Unknown | 2024-05-07 | 2025-02-21 | 291 | 209 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-20 | 22 | 16 | 2025-02-21 | 2025-01-28 | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-02 | 2025-04-01 | Unknown | Unknown | 0 | 0 | 313 | 225 | 313 | 225 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | -371 | -266 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1.04 | -13.88 | Unknown | Unknown | Unknown | 14.92 | 3981 | 630.18 | 1.04 | 629.14 | Yes | N/A | N/A | 2023-03-20 | 2023-03-20 | 1 | 1 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2024-02-02 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-24 | -270 | -193 | No | 2024-02-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-09 | Unknown | IOU Designed & Installed | N/A | Yes | 311 | 35.16 | Unknown | Unknown | Unknown | Unknown | 35.16 | Unknown | 976.88 | 35.16 | 941.72 | Yes | N/A | N/A | 2024-02-05 | 2024-12-12 | 312 | 224 | 2024-12-12 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | 2025-02-27 | 2025-02-27 | 1 | 1 | 312 | 224 | 1 | 1 | 313 | 225 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | El Cajon | COUNTY OF SAN DIEGO-SOUTH of 56, EL CAJON | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-15 | 339 | 242 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-02 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 38534.41 | 3675.28 | Unknown | Unknown | 41.52 | 34817.61 | Unknown | 12108.44 | 38534.41 | -26425.97 | Yes | N/A | N/A | 2024-01-02 | 2024-01-02 | 1 | 1 | 2024-01-02 | 2024-07-16 | 197 | 141 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-03-22 | 10 | 8 | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-08-19 | 1900-01-25 | 18 | 2024-08-19 | 2024-08-19 | 1 | 1 | 1 | 1 | 234 | 168 | 235 | 169 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | -532 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 872.84 | -7.82 | Unknown | Unknown | Unknown | 880.66 | Unknown | 412.77 | 872.84 | -460.07 | Yes | N/A | N/A | 2024-05-07 | 2024-05-15 | 9 | 7 | 2024-05-15 | 2024-06-13 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-07-15 | 33 | 23 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | Unknown | Unknown | 2024-06-21 | 2024-06-21 | 1 | 1 | 9 | 7 | 64 | 46 | 73 | 53 | Steps 2,3,5,6,7 | 32 | 22 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-18 | -705 | -504 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-12-14 | IOU Designed & Installed | N/A | No | N/A | 688.32 | -6.36 | Unknown | Unknown | 20.56 | 674.12 | 3981 | 200.79 | 688.32 | -487.53 | Yes | N/A | N/A | 2023-03-15 | 2023-04-03 | 20 | 14 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | 2023-12-14 | 256 | 184 | Unknown | 2023-11-09 | Unknown | Unknown | 2023-12-14 | 2023-12-14 | 1899-12-31 | 1 | 2023-12-14 | 2023-12-14 | 1 | 1 | 276 | 198 | 2 | 2 | 278 | 200 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-08 | -599 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-01 | 2023-09-01 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | 4560.07 | 1165.84 | Unknown | 622.8 | Unknown | 2771.43 | 3981 | 654.89 | 4560.07 | -3905.18 | Yes | N/A | N/A | 2023-09-01 | 2023-09-01 | 1 | 1 | 2023-09-01 | 2023-09-01 | 1 | 1 | 2023-09-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2023-10-11 | 41 | 29 | Unknown | 2023-10-09 | Unknown | Unknown | 2023-10-11 | 2023-10-18 | 1900-01-07 | 6 | 2023-10-18 | 2023-10-18 | 1 | 1 | 42 | 30 | 10 | 8 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 724.1 | 724.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-15 | 184 | 132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | 8160.36 | Unknown | Unknown | Unknown | 338.68 | 7821.68 | 3981 | 895.06 | 8160.36 | -7265.3 | Yes | N/A | N/A | 2023-02-02 | 2023-08-21 | 201 | 143 | 2023-08-21 | Unknown | Unknown | Unknown | 2023-08-21 | 2023-08-21 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2025-01-15 | 514 | 368 | Unknown | 2025-03-11 | Unknown | Unknown | 2025-01-15 | 2025-03-19 | 1900-03-04 | 46 | 2025-03-19 | 2025-03-18 | Unknown | Unknown | 716 | 512 | 64 | 46 | 780 | 558 | Steps 2,3,5,6,7 | 55 | 39 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 10.05 | 10.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-10 | -265 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-13 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 589.8 | -11.85 | Unknown | Unknown | Unknown | 601.65 | 7962 | 823.83 | 589.8 | 234.03 | Yes | N/A | N/A | 2024-05-08 | 2024-05-10 | 3 | 3 | 2024-05-10 | 2024-05-10 | 1 | 1 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2025-05-12 | 365 | 261 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-21 | 1900-01-09 | 8 | 2025-05-21 | 2025-05-21 | 1 | 1 | 368 | 264 | 12 | 10 | 380 | 274 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | 13 | 13 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-03 | -338 | -243 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-22 | 2025-06-20 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 91568.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-16 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2025-02-27 | 259 | 185 | 2024-07-22 | 2024-09-06 | 47 | 35 | 2025-02-21 | 2025-03-12 | 15 | 11 | 2025-02-27 | 2958465 | Unknown | Unknown | 2025-03-04 | 2025-06-16 | 105 | 75 | 2025-06-20 | 2025-06-30 | 1900-01-10 | 7 | 2025-06-30 | 2025-06-30 | 1 | 1 | 47 | 35 | 391 | 279 | 438 | 314 | Steps 2,3,5,6,7 | 233 | 167 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 242.35 | 242.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-03 | -344 | -247 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 21796 | Unknown | Unknown | Unknown | 6.45 | 21789.55 | 3981 | 1347.91 | 21796 | -20448.09 | Yes | N/A | N/A | 2024-01-24 | 2024-07-17 | 176 | 126 | 2024-07-17 | 2024-07-30 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | 2024-10-24 | 2024-10-24 | 1899-12-31 | 1 | 2024-10-24 | 2024-10-24 | 1 | 1 | 176 | 126 | 16 | 12 | 192 | 138 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-25 | -438 | -315 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-08 | 2024-02-05 | IOU Designed & Installed | N/A | No | N/A | 9.55 | -11.55 | Unknown | Unknown | Unknown | 21.1 | Unknown | 870.37 | 9.55 | 860.82 | Yes | N/A | N/A | 2024-01-04 | 2023-09-14 | Unknown | Unknown | 2023-09-14 | 2024-01-09 | 118 | 84 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-02-05 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-03-15 | 1900-02-08 | 30 | 2024-03-15 | 2024-02-12 | Unknown | Unknown | 29 | 21 | 158 | 114 | 187 | 135 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-30 | -597 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-19 | 2024-07-31 | IOU Designed & Installed | N/A | No | N/A | 7.63 | Unknown | Unknown | Unknown | Unknown | 7.63 | Unknown | 1049.43 | 7.63 | 1041.8 | Yes | N/A | N/A | 2024-07-19 | 2024-07-19 | 1 | 1 | 2024-07-19 | 2024-07-19 | 1 | 1 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-07-31 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-09-05 | 1900-02-05 | 27 | 2024-09-05 | 2024-09-10 | 6 | 4 | 14 | 10 | 44 | 32 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 531.05 | 531.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-25 | -640 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2120.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-03-27 | Unknown | Unknown | 2025-03-27 | 2025-04-07 | 12 | 8 | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-06-23 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-23 | 1899-12-31 | 1 | 2025-06-23 | 2025-06-23 | 1 | 1 | 78 | 56 | 14 | 10 | 92 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-12 | -624 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | 2023-12-18 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 208.9 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-18 | 2023-09-21 | Unknown | Unknown | 2023-09-21 | 2023-12-15 | 86 | 62 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2023-12-18 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2023-12-28 | 1900-01-10 | 9 | 2023-12-28 | 2023-12-28 | 1 | 1 | 1 | 1 | 98 | 72 | 99 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-31 | 703 | 502 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-11-21 | IOU Designed & Installed | N/A | No | N/A | 32.32 | Unknown | Unknown | Unknown | Unknown | 32.32 | 3281 | 1137.31 | 32.32 | 1104.99 | Yes | N/A | N/A | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-11-21 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-12-03 | 1900-01-12 | 9 | 2024-12-03 | 2024-12-03 | 1 | 1 | 2 | 2 | 15 | 11 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | -493 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-29 | 2025-03-10 | IOU Designed & Installed | N/A | No | N/A | 1082.11 | 253.74 | Unknown | Unknown | Unknown | 828.37 | 7962 | 1716.71 | 1082.11 | 634.6 | Yes | N/A | N/A | 2025-01-28 | 2025-01-29 | 2 | 2 | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-03-10 | 41 | 29 | Unknown | 2025-01-31 | Unknown | Unknown | 2025-03-10 | 2025-03-14 | 1900-01-04 | 5 | 2025-03-14 | 2025-03-12 | Unknown | Unknown | 43 | 31 | 6 | 6 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 515.05 | 515.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-10 | 2024-12-23 | IOU Designed & Installed | N/A | No | N/A | -1062.46 | Unknown | Unknown | Unknown | -1489 | 426.54 | Unknown | 1489.07 | -1062.46 | 2551.53 | Yes | N/A | N/A | 2024-09-09 | 2024-10-02 | 24 | 18 | 2024-10-02 | 2025-03-03 | 153 | 109 | 2025-03-03 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2024-12-23 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-01-17 | 1900-01-25 | 20 | 2025-01-17 | 2025-02-12 | 27 | 19 | 66 | 48 | 206 | 148 | 272 | 196 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-07 | 95 | 68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-06-02 | 2023-12-08 | IOU Designed & Installed | N/A | No | N/A | 2315.79 | 575.28 | Unknown | 641.52 | Unknown | 1098.99 | 3981 | 646.79 | 2315.79 | -1669 | Yes | N/A | N/A | 2023-06-02 | 2023-06-02 | 1 | 1 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | 2023-12-08 | 190 | 136 | Unknown | 2023-11-15 | Unknown | Unknown | 2023-12-08 | 2023-12-11 | 1900-01-03 | 2 | 2023-12-11 | 2023-12-11 | 1 | 1 | 191 | 137 | 5 | 3 | 196 | 140 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SD 1190-A2 CMR PA9 WO4 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 704 | 505 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-11 | 2025-04-04 | IOU Designed & Installed | N/A | No | N/A | 19745.85 | 4311.33 | Unknown | Unknown | -10649.81 | 26084.33 | 41330 | Not available | 19745.85 | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-09-11 | 2 | 2 | 2024-09-11 | 2024-09-11 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2025-04-09 | 211 | 151 | Unknown | 2025-04-17 | Unknown | Unknown | 2025-04-04 | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-02-21 | Unknown | Unknown | 213 | 153 | 1 | 1 | 214 | 154 | Steps 2,3,5,6,7 | 13 | 9 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 130.2 | 130.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-29 | -627 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 49.21 | Unknown | Unknown | Unknown | Unknown | 49.21 | 3941 | 1510.29 | 49.21 | 1461.08 | Yes | N/A | N/A | 2024-08-14 | 2024-07-24 | Unknown | Unknown | 2024-07-24 | 2024-08-14 | 22 | 16 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-10-01 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-09 | 1900-01-08 | 7 | 2024-10-09 | 2024-10-10 | 2 | 2 | 49 | 35 | 33 | 25 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | -493 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | 2025-05-05 | IOU Designed & Installed | N/A | No | N/A | 1284.99 | -8.08 | Unknown | Unknown | 31.79 | 1261.28 | 11943 | 1404.73 | 1284.99 | 119.74 | Yes | N/A | N/A | 2024-10-22 | 2024-09-27 | Unknown | Unknown | 2024-09-27 | 2024-11-15 | 50 | 36 | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2025-05-05 | 172 | 122 | Unknown | 2025-03-26 | Unknown | Unknown | 2025-05-05 | 2025-05-13 | 1900-01-08 | 7 | 2025-05-13 | 2025-05-13 | 1 | 1 | 172 | 122 | 60 | 44 | 232 | 166 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | -651 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-27 | 2024-11-27 | 2024-12-19 | IOU Designed & Installed | N/A | No | N/A | 1045.11 | -20.4 | Unknown | Unknown | Unknown | 1065.51 | 3241 | 1704.03 | 1045.11 | 658.92 | Yes | N/A | N/A | 2024-11-27 | 2024-11-27 | 1 | 1 | 2024-11-27 | 2024-11-27 | 1 | 1 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2024-12-19 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-01-10 | 1900-01-22 | 17 | 2025-01-10 | 2025-01-10 | 1 | 1 | 24 | 18 | 25 | 19 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | Oceanside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-05 | 33 | 24 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2025-01-15 | 2025-03-26 | IOU Designed & Installed | N/A | No | N/A | 3443.05 | Unknown | Unknown | Unknown | -5490 | 8933.05 | Unknown | 7335.28 | 3443.05 | 3892.23 | Yes | N/A | N/A | 2024-08-23 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2025-03-24 | 284 | 202 | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-03-17 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-04-07 | 1900-01-12 | 9 | 2025-04-07 | 2025-04-07 | 1 | 1 | 0 | 0 | 309 | 219 | 309 | 219 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-04 | 18 | 15 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | 2024-03-19 | IOU Designed & Installed | N/A | No | N/A | 4.12 | -3.66 | Unknown | Unknown | Unknown | 7.78 | Unknown | 308.87 | 4.12 | 304.75 | Yes | N/A | N/A | 2024-03-12 | 2024-03-12 | 1 | 1 | 2024-03-12 | 2024-03-12 | 1 | 1 | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-03-19 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-03-22 | 1900-01-03 | 4 | 2024-03-22 | 2024-03-22 | 1 | 1 | 9 | 7 | 6 | 6 | 15 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 101.4 | 101.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-16 | 219 | 158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | 12115.18 | 350.69 | Unknown | Unknown | Unknown | 11764.49 | 3981 | 3183.52 | 12115.18 | -8931.66 | Yes | N/A | N/A | 2023-12-12 | 2023-11-08 | Unknown | Unknown | 2023-11-08 | 2024-01-02 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-03-06 | 1 | 1 | 2024-01-02 | 2024-03-20 | 79 | 57 | Unknown | 2024-03-11 | Unknown | Unknown | 2024-03-14 | 2024-03-25 | 1900-01-11 | 8 | 2024-03-25 | 2024-03-22 | Unknown | Unknown | 79 | 57 | 69 | 49 | 148 | 106 | Steps 2,3,5,6,7 | 64 | 46 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-15 | -253 | -182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1093.28 | 1620.68 | Unknown | 195.2 | -3559 | 649.84 | Unknown | 3559.1 | -1093.28 | 4652.38 | Yes | N/A | N/A | 2023-05-19 | 2023-05-19 | 1 | 1 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | Unknown | Unknown | 2023-09-05 | 2023-09-05 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | -502 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-27 | 2023-07-18 | IOU Designed & Installed | N/A | No | N/A | -7.8 | -5.65 | Unknown | Unknown | Unknown | -2.15 | Unknown | 98.41 | -7.8 | 106.21 | Yes | N/A | N/A | 2023-02-15 | 2023-02-27 | 13 | 9 | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-27 | 2023-07-18 | 142 | 102 | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-07-18 | 1899-12-31 | 1 | 2023-07-18 | 2023-07-18 | 1 | 1 | 155 | 111 | 2 | 2 | 157 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-08 | 9 | 8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 178.51 | -3.58 | Unknown | Unknown | Unknown | 182.09 | 3981 | 1742.23 | 178.51 | 1563.72 | Yes | N/A | N/A | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | 2025-02-21 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-01-01 | 41 | 29 | 2025-02-21 | 2025-04-04 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | 2025-04-18 | 2025-04-17 | Unknown | Unknown | 44 | 32 | 154 | 110 | 198 | 142 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | -630 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-26 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | 296.2 | -5.95 | Unknown | Unknown | Unknown | 302.15 | 3981 | 2151.13 | 296.2 | 1854.93 | Yes | N/A | N/A | 2025-02-27 | 2025-03-18 | 20 | 14 | 2025-03-18 | 2025-03-26 | 9 | 7 | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-05-06 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-22 | 1900-01-16 | 13 | 2025-05-22 | 2025-05-22 | 1 | 1 | 62 | 44 | 27 | 21 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Residential | Underserved Community | Oceanside | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | 219 | 158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-08-12 | 2021-08-12 | 2024-04-15 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 16032.04 | 2627.28 | Unknown | Unknown | -752.86 | 14157.62 | 65179 | 25643.36 | 16032.04 | 9611.32 | Yes | N/A | N/A | 2021-08-12 | 2023-05-03 | 630 | 450 | 2023-05-03 | 2023-11-30 | 212 | 152 | 2023-06-30 | 2023-11-27 | 109 | 77 | 2023-11-29 | 2023-11-30 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2024-04-10 | 122 | 88 | 2024-04-15 | 2024-06-07 | 1900-02-22 | 40 | 2024-06-07 | 2024-06-07 | 1 | 1 | 739 | 527 | 391 | 283 | 1130 | 810 | Steps 2,3,5,6,7 | 153 | 109 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 411.05 | 411.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-13 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | 1499.17 | 382.05 | Unknown | Unknown | Unknown | 1117.12 | Unknown | 3879.99 | 1499.17 | 2380.82 | Yes | N/A | N/A | 2024-12-13 | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2024-12-17 | 27 | 19 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-04-24 | 129 | 93 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-04-24 | 1899-12-31 | 1 | 2025-04-24 | 2025-04-24 | 1 | 1 | 129 | 93 | 29 | 21 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | 55 | 55 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-27 | -464 | -332 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | 2025-03-10 | IOU Designed & Installed | N/A | No | N/A | 43887.67 | 10978.9 | Unknown | 2538.41 | Unknown | 30370.36 | Unknown | 66227.13 | 43887.67 | 22339.46 | Yes | N/A | N/A | 2024-12-11 | 2024-12-18 | 8 | 6 | 2024-12-18 | 2025-01-07 | 21 | 15 | 2024-12-19 | 2025-01-06 | 19 | 13 | 2024-12-18 | 2025-02-07 | 37 | 29 | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-03-20 | 1900-01-10 | 9 | 2025-03-20 | 2025-03-20 | 1 | 1 | 27 | 19 | 70 | 54 | 97 | 73 | Steps 2,3,5,6,7 | 69 | 49 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-31 | -903 | -646 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 431.85 | -6.22 | Unknown | Unknown | 31.07 | 407 | Unknown | 431.96 | 431.85 | 0.11 | Yes | N/A | N/A | 2023-03-02 | 2023-03-02 | 1 | 1 | 2023-03-02 | 2023-03-10 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | 2023-03-21 | 15 | 11 | 2023-03-10 | 2023-06-13 | 96 | 68 | Unknown | 2023-04-11 | Unknown | Unknown | Unknown | 2023-09-11 | Unknown | Unknown | 2023-09-11 | 2023-07-12 | Unknown | Unknown | 97 | 69 | 24 | 18 | 121 | 87 | Steps 2,3,5,6,7 | 11 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-13 | 124 | 89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2454.95 | 3904.42 | Unknown | 881 | -3985 | 1654.53 | 0 | 3985.38 | 2454.95 | 1530.43 | Yes | N/A | N/A | 2023-03-24 | 2023-03-23 | Unknown | Unknown | 2023-03-23 | 2023-04-14 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 24 | 18 | 24 | 18 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-09 | -305 | -219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-09 | 2023-04-29 | IOU Designed & Installed | N/A | No | N/A | -9.7 | -7.74 | Unknown | Unknown | Unknown | -1.96 | 3981 | 639.68 | -9.7 | 649.38 | Yes | N/A | N/A | 2023-03-09 | 2023-03-09 | 1 | 1 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | 2023-04-29 | 52 | 37 | Unknown | Unknown | Unknown | Unknown | 2023-04-29 | 2023-08-16 | 1900-04-19 | 78 | 2023-08-16 | 2023-05-09 | Unknown | Unknown | 53 | 38 | 110 | 78 | 163 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 16.2 | 16.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-28 | 249 | 178 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | 2024-02-27 | IOU Designed & Installed | N/A | No | N/A | 343.42 | -9.75 | Unknown | Unknown | Unknown | 353.17 | 11943 | 872.51 | 343.42 | 529.09 | Yes | N/A | N/A | 2023-09-12 | 2023-09-12 | 1 | 1 | 2023-09-12 | 2023-10-27 | 46 | 34 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2024-02-27 | 124 | 88 | Unknown | 2024-02-26 | Unknown | Unknown | 2024-02-27 | 2024-04-03 | 1900-02-05 | 27 | 2024-04-03 | 2024-04-02 | Unknown | Unknown | 125 | 89 | 83 | 61 | 208 | 150 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 369.05 | 369.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | -479 | -344 | No | 2024-10-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2024-10-31 | 2025-04-23 | IOU Designed & Installed | N/A | Yes | 147 | 6200.66 | 659.28 | Unknown | 113.51 | 61.26 | 5366.61 | 3981 | 2882.59 | 6200.66 | -3318.07 | Yes | N/A | N/A | 2024-10-31 | 2025-03-14 | 135 | 97 | 2025-03-14 | 2025-03-27 | 14 | 10 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-04-23 | 128 | 92 | Unknown | 2025-04-22 | Unknown | Unknown | 2025-04-23 | 2025-04-29 | 1900-01-06 | 5 | 2025-04-29 | 2025-04-29 | 1 | 1 | 263 | 189 | 22 | 16 | 285 | 205 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 154.1 | 154.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | -148 | -107 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-07-23 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 904.81 | Unknown | Unknown | Unknown | Unknown | 904.81 | 7962 | 418.5 | 904.81 | -486.31 | Yes | N/A | N/A | 2023-07-13 | 2023-07-17 | 5 | 3 | 2023-07-17 | 2023-07-23 | 7 | 5 | 2023-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-23 | 2024-10-15 | 451 | 322 | Unknown | 2024-10-14 | Unknown | Unknown | 2024-10-15 | 2024-10-31 | 1900-01-16 | 13 | 2024-10-31 | 2024-10-24 | Unknown | Unknown | 456 | 325 | 24 | 18 | 480 | 343 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-31 | -676 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 834.85 | -51.91 | Unknown | Unknown | Unknown | 886.76 | 3981 | 1844.55 | 834.85 | 1009.7 | Yes | N/A | N/A | 2025-01-29 | 2025-01-28 | Unknown | Unknown | 2025-01-28 | 2025-01-31 | 4 | 4 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-03-26 | 1 | 1 | 0 | 0 | 5 | 5 | 5 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 139.05 | 139.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-21 | -351 | -252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-02-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -370.49 | -30.05 | Unknown | Unknown | -684 | 343.56 | 3981 | 3387.87 | -370.49 | 3758.36 | Yes | N/A | N/A | 2023-01-31 | 2023-05-25 | 115 | 83 | 2023-05-25 | 2023-08-10 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-11-29 | 64 | 46 | 2023-08-10 | 2023-11-14 | 97 | 69 | Unknown | 2023-11-29 | Unknown | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2023-12-06 | Unknown | Unknown | 212 | 152 | 142 | 102 | 354 | 254 | Steps 2,3,5,6,7 | 111 | 79 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 80.05 | 80.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-24 | -28 | -21 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2024-03-05 | IOU Designed & Installed | N/A | No | N/A | 282.15 | -14.02 | Unknown | Unknown | Unknown | 296.17 | 3981 | 1086.74 | 282.15 | 804.59 | Yes | N/A | N/A | 2023-09-27 | 2023-09-27 | 1 | 1 | 2023-09-27 | 2023-10-03 | 7 | 5 | 2023-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2024-03-05 | 155 | 111 | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | 2024-03-27 | 1900-01-22 | 17 | 2024-03-27 | 2024-03-27 | 1 | 1 | 156 | 112 | 31 | 23 | 187 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-06 | -304 | -218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-03 | 2025-01-03 | 2025-01-13 | IOU Designed & Installed | N/A | No | N/A | 94.9 | -1.26 | Unknown | Unknown | Unknown | 96.16 | 3981 | 1229.12 | 94.9 | 1134.22 | Yes | N/A | N/A | 2025-01-03 | 2025-01-03 | 1 | 1 | 2025-01-03 | 2025-01-03 | 1 | 1 | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-01-13 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-02-05 | 1900-01-23 | 18 | 2025-02-05 | 2025-02-05 | 1 | 1 | 12 | 8 | 26 | 20 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | CORONADO | 144 | 144 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-19 | -172 | -123 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-23 | 2025-02-21 | IOU Designed & Installed | N/A | No | N/A | 2738.72 | 388.59 | Unknown | Unknown | Unknown | 2350.13 | Unknown | 1752.85 | 2738.72 | -985.87 | Yes | N/A | N/A | 2024-10-23 | 2024-08-28 | Unknown | Unknown | 2024-08-28 | 2024-10-24 | 58 | 42 | 2024-10-24 | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-06 | 14 | 10 | 2024-10-23 | 2025-02-21 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-02-28 | 1900-01-07 | 6 | 2025-02-28 | 2025-02-28 | 1 | 1 | 122 | 88 | 81 | 59 | 203 | 147 | Steps 2,3,5,6,7 | 14 | 10 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-12 | -658 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-10 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1637.77 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-04-10 | 4 | 4 | 2025-04-10 | 2025-04-10 | 1 | 1 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-04-25 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-23 | 1900-01-28 | 21 | 2025-05-23 | 2025-05-23 | 1 | 1 | 20 | 16 | 31 | 23 | 51 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | 346 | 249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2025-01-28 | 2025-05-29 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 23886 | 73.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-07 | 2024-11-12 | 6 | 4 | 2024-11-12 | 2025-03-05 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-19 | 22 | 16 | 2025-03-05 | 2025-05-14 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-18 | 1900-01-20 | 15 | 2025-06-18 | 2025-06-12 | Unknown | Unknown | 77 | 55 | 157 | 113 | 234 | 168 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | -658 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-25 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | 4757.64 | 583.26 | Unknown | 204.56 | Unknown | 3969.82 | Unknown | 2127.8 | 4757.64 | -2629.84 | Yes | N/A | N/A | 2025-02-25 | 2025-02-25 | 1 | 1 | 2025-02-25 | 2025-03-07 | 11 | 9 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-03-31 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-04 | 1900-01-04 | 5 | 2025-04-04 | 2025-04-04 | 1 | 1 | 26 | 18 | 17 | 15 | 43 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-18 | -453 | -325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | 4906.11 | 609.85 | Unknown | Unknown | 8.8 | 4287.46 | 3981 | 817.4 | 4906.11 | -4088.71 | Yes | N/A | N/A | 2023-03-15 | 2023-05-01 | 48 | 34 | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | 2023-10-11 | 164 | 118 | Unknown | 2023-10-11 | Unknown | Unknown | 2023-10-11 | 2023-10-23 | 1900-01-12 | 9 | 2023-10-23 | 2023-10-23 | 1 | 1 | 212 | 152 | 14 | 10 | 226 | 162 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | -566 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-01 | 2024-08-16 | IOU Designed & Installed | N/A | No | N/A | 1676.74 | 511.75 | Unknown | Unknown | Unknown | 1164.99 | 3981 | 833.15 | 1676.74 | -843.59 | Yes | N/A | N/A | 2024-05-01 | 2024-05-01 | 1 | 1 | 2024-05-01 | 2024-05-01 | 1 | 1 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-08-16 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-09-27 | 1900-02-11 | 31 | 2024-09-27 | 2024-09-27 | 1 | 1 | 109 | 79 | 45 | 33 | 154 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-22 | -617 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-09-26 | 2024-12-09 | IOU Designed & Installed | N/A | No | N/A | 1093.74 | Unknown | Unknown | Unknown | Unknown | 1093.74 | 3981 | 1376.2 | 1093.74 | 282.46 | Yes | N/A | N/A | 2024-09-16 | 2024-09-26 | 11 | 9 | 2024-09-26 | 2024-09-26 | 1 | 1 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-12-09 | 75 | 53 | Unknown | 2024-12-06 | Unknown | Unknown | 2024-12-09 | 2024-12-13 | 1900-01-04 | 5 | 2024-12-13 | 2024-12-13 | 1 | 1 | 86 | 62 | 7 | 7 | 93 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-31 | 398 | 285 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | 2023-05-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -23.39 | -16.96 | Unknown | Unknown | Unknown | -6.43 | Unknown | 743.75 | -23.39 | 767.14 | Yes | N/A | N/A | 2023-05-08 | 2023-05-16 | 9 | 7 | 2023-05-16 | 2023-06-05 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2024-02-02 | 1 | 1 | 9 | 7 | 22 | 16 | 31 | 23 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | -667 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | Unknown | 2024-09-12 | IOU Designed & Installed | N/A | No | N/A | 2022.33 | -40.08 | Unknown | Unknown | Unknown | 2062.41 | 3981 | 1546.95 | 2022.33 | -475.38 | Yes | N/A | N/A | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-09-12 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | 2024-10-14 | 1900-02-01 | 23 | 2024-10-14 | 2024-10-14 | 1 | 1 | 19 | 15 | 35 | 25 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 11.5 | 11.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-18 | -666 | -477 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | 2024-08-08 | IOU Designed & Installed | N/A | No | N/A | 1098.22 | -15.3 | Unknown | Unknown | Unknown | 1113.52 | 3981 | 1171.09 | 1098.22 | 72.87 | Yes | N/A | N/A | 2024-07-23 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-07-25 | 21 | 15 | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-08-08 | 15 | 11 | Unknown | 2024-08-05 | Unknown | Unknown | 2024-08-08 | 2024-08-21 | 1900-01-13 | 10 | 2024-08-21 | 2024-08-21 | 1 | 1 | 15 | 11 | 36 | 26 | 51 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 2.35 | 2.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-25 | -490 | -351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-09-30 | 2024-11-06 | IOU Designed & Installed | N/A | No | N/A | 123.42 | -1.87 | Unknown | Unknown | Unknown | 125.29 | 3981 | 1843.47 | 123.42 | 1720.05 | Yes | N/A | N/A | 2024-08-12 | 2024-08-05 | Unknown | Unknown | 2024-08-05 | 2024-09-30 | 57 | 41 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-11-06 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-11-21 | 1900-01-15 | 12 | 2024-11-21 | 2024-11-20 | Unknown | Unknown | 38 | 28 | 73 | 53 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 10.75 | 10.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-01 | -484 | -346 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.47 | -27.06 | Unknown | Unknown | Unknown | 20.59 | Unknown | 1489.11 | -6.47 | 1495.58 | Yes | N/A | N/A | 2024-08-28 | 2024-08-29 | 2 | 2 | 2024-08-29 | 2024-08-30 | 2 | 2 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | 2025-04-04 | 2025-04-04 | 1 | 1 | 2 | 2 | 3 | 3 | 5 | 5 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | -56 | -41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-20 | 2023-12-28 | IOU Designed & Installed | N/A | No | N/A | -610.35 | -14.55 | Unknown | Unknown | -1118 | 522.2 | 3981 | 1629.08 | -610.35 | 2239.43 | Yes | N/A | N/A | 2023-10-17 | 2023-10-20 | 4 | 4 | 2023-10-20 | 2023-10-20 | 1 | 1 | 2023-10-20 | 2023-11-01 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2023-12-28 | 58 | 42 | Unknown | 2023-12-06 | Unknown | Unknown | 2023-12-28 | 2024-01-08 | 1900-01-11 | 8 | 2024-01-08 | 2024-01-05 | Unknown | Unknown | 75 | 55 | 13 | 9 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | -74 | -55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2023-12-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 3216.09 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-07 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 63.05 | 63.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | -437 | -314 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-04 | 2024-04-24 | IOU Designed & Installed | N/A | No | N/A | 1254.06 | -10.92 | Unknown | Unknown | 7.88 | 1257.1 | 3981 | 729.47 | 1254.06 | -524.59 | Yes | N/A | N/A | 2024-01-03 | 2024-01-29 | 27 | 19 | 2024-01-29 | 2024-01-29 | 1 | 1 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-04-24 | 87 | 63 | Unknown | 2024-04-15 | Unknown | Unknown | 2024-04-24 | 2024-05-21 | 1900-01-27 | 20 | 2024-05-21 | 2024-05-21 | 1 | 1 | 114 | 82 | 30 | 22 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA MESA | N/A | 311 | 311 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-01 | 769 | 550 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-18 | 2024-01-18 | IOU Designed & Installed | N/A | No | N/A | 14661.94 | -110.68 | Unknown | Unknown | Unknown | 14772.62 | 3981 | 378.5 | 14661.94 | -14283.44 | Yes | N/A | N/A | 2023-09-14 | 2023-09-18 | 5 | 3 | 2023-09-18 | 2023-09-20 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | 2024-01-10 | 113 | 81 | Unknown | 2024-01-09 | Unknown | Unknown | 2024-01-18 | 2024-02-15 | 1900-01-28 | 21 | 2024-02-15 | 2024-02-09 | Unknown | Unknown | 118 | 84 | 32 | 24 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-06 | -79 | -58 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | 2023-07-28 | IOU Designed & Installed | N/A | No | N/A | 562.19 | 64.29 | Unknown | Unknown | Unknown | 497.9 | Unknown | 149.62 | 562.19 | -412.57 | Yes | N/A | N/A | 2023-03-06 | 2023-04-21 | 47 | 35 | 2023-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | 2023-07-28 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2023-09-18 | 1900-02-21 | 37 | 2023-09-18 | 2023-09-18 | 1 | 1 | 146 | 106 | 54 | 38 | 200 | 144 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-23 | -413 | -296 | No | 2024-08-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-13 | 2025-06-04 | IOU Designed & Installed | N/A | Yes | 264 | 634.65 | -12.76 | Unknown | Unknown | Unknown | 647.41 | Unknown | 1951.15 | 634.65 | 1316.5 | Yes | N/A | N/A | 2024-08-07 | 2025-04-28 | 265 | 189 | 2025-04-28 | 2024-08-16 | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | 2024-08-14 | 2024-09-13 | 31 | 23 | 2024-08-16 | 2025-06-04 | 293 | 209 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-06-05 | 1900-01-01 | 2 | 2025-06-05 | 2025-06-05 | 1 | 1 | 558 | 398 | 34 | 26 | 592 | 424 | Steps 2,3,5,6,7 | 28 | 20 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-23 | -680 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-08-12 | 2024-08-16 | IOU Designed & Installed | N/A | No | N/A | 1163.17 | -22.7 | Unknown | Unknown | Unknown | 1185.87 | Unknown | 1654.49 | 1163.17 | 491.32 | Yes | N/A | N/A | 2024-08-12 | 2024-08-07 | Unknown | Unknown | 2024-08-07 | 2024-08-12 | 6 | 4 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-08-16 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-09-11 | 1900-01-26 | 19 | 2024-09-11 | 2024-09-11 | 1 | 1 | 5 | 5 | 34 | 24 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-03 | -250 | -179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | 2023-04-18 | IOU Designed & Installed | N/A | No | N/A | 59.94 | -11.49 | Unknown | Unknown | 0.33 | 71.1 | 3981 | 765.48 | 59.94 | 705.54 | Yes | N/A | N/A | 2023-03-31 | 2023-03-31 | 1 | 1 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | 2023-04-18 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | 2023-06-12 | 1900-02-24 | 40 | 2023-06-12 | 2023-04-28 | Unknown | Unknown | 20 | 14 | 56 | 40 | 76 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-21 | -406 | -291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2223.91 | -13.57 | Unknown | Unknown | 19.87 | 2217.61 | 3981 | 865.34 | 2223.91 | -1358.57 | Yes | N/A | N/A | 2024-04-10 | 2024-04-25 | 16 | 12 | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | Unknown | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-07-11 | 1 | 1 | 16 | 12 | 2 | 2 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-14 | -155 | -112 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-08-29 | IOU Designed & Installed | N/A | No | N/A | -7.09 | -13.97 | Unknown | Unknown | Unknown | 6.88 | 3885 | 851.34 | -7.09 | 858.43 | Yes | N/A | N/A | 2023-03-28 | 2023-03-29 | 2 | 2 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | 2023-08-29 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2023-09-12 | 1900-01-14 | 11 | 2023-09-12 | 2023-09-12 | 1 | 1 | 156 | 112 | 16 | 12 | 172 | 124 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-09 | -537 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-03 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | -6.61 | -4.78 | Unknown | Unknown | Unknown | -1.83 | 3981 | 341 | -6.61 | 347.61 | Yes | N/A | N/A | 2023-03-03 | 2023-03-03 | 1 | 1 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | 2023-07-17 | 137 | 97 | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-06-21 | Unknown | Unknown | 2023-06-21 | 2023-06-21 | 1 | 1 | 138 | 98 | 1 | 1 | 139 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 62.35 | 62.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-29 | -525 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-01-24 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 1863.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-24 | 2024-01-20 | Unknown | Unknown | 2024-01-20 | 2025-01-24 | 371 | 265 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-04-25 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-22 | 1900-01-27 | 20 | 2025-05-22 | 2025-05-22 | 1 | 1 | 92 | 66 | 400 | 286 | 492 | 352 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-18 | -525 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2024-01-19 | 2024-03-21 | IOU Designed & Installed | N/A | No | N/A | 6.26 | -5.54 | Unknown | Unknown | Unknown | 11.8 | Unknown | 909.4 | 6.26 | 903.14 | Yes | N/A | N/A | 2023-12-26 | 2023-10-11 | Unknown | Unknown | 2023-10-11 | 2024-01-19 | 101 | 73 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-03-21 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-04-11 | 1900-01-21 | 16 | 2024-04-11 | 2024-04-11 | 1 | 1 | 63 | 45 | 124 | 90 | 187 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | 7.7 | 7.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-03 | -380 | -271 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-05 | 2024-04-05 | 2024-07-08 | IOU Designed & Installed | N/A | No | N/A | 5051.67 | 1304.19 | Unknown | Unknown | Unknown | 3747.48 | 7962 | 1048.42 | 5051.67 | -4003.25 | Yes | N/A | N/A | 2024-04-05 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-07-05 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | 2024-05-02 | 25 | 19 | 2024-07-05 | 2024-07-05 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-07-19 | 1900-01-11 | 10 | 2024-07-19 | 2024-07-19 | 1 | 1 | 1 | 1 | 132 | 98 | 133 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-30 | -225 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2025-01-30 | 2025-04-17 | IOU Designed & Installed | N/A | No | N/A | 32983.48 | 6886.13 | Unknown | 380.51 | 67.41 | 25649.43 | Unknown | 24308.95 | 32983.48 | -8674.53 | Yes | N/A | N/A | 2024-12-16 | 2024-12-02 | Unknown | Unknown | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-04-02 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-05-19 | 1900-02-01 | 23 | 2025-05-19 | 2025-05-19 | 1 | 1 | 0 | 0 | 73 | 53 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-23 | 178 | 127 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | 2023-08-24 | 2024-07-26 | IOU Designed & Installed | N/A | No | N/A | 56527.15 | 16890.86 | Unknown | 23.78 | 3.18 | 39609.33 | 0 | 18922.92 | 56527.15 | -37604.23 | Yes | N/A | N/A | 2023-08-18 | 2023-08-18 | 1 | 1 | 2023-08-18 | 2024-07-05 | 323 | 231 | Unknown | Unknown | Unknown | Unknown | 2023-11-11 | 2024-07-16 | 18 | 12 | 2024-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-08-19 | 1900-01-24 | 17 | 2024-08-19 | 2024-08-19 | 1 | 1 | 1 | 1 | 367 | 261 | 368 | 262 | Steps 2,3,5,6,7 | 11 | 7 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 62.05 | 62.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-20 | -596 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-10-09 | 2023-10-17 | IOU Designed & Installed | N/A | No | N/A | 673.46 | 370.8 | Unknown | 65.07 | Unknown | 237.59 | 3241 | 1139.92 | 673.46 | 466.46 | Yes | N/A | N/A | 2023-09-26 | 2023-10-09 | 14 | 10 | 2023-10-09 | 2023-10-09 | 1 | 1 | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2023-10-17 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2023-11-02 | 1900-01-16 | 13 | 2023-11-02 | 2023-11-02 | 1 | 1 | 23 | 17 | 19 | 15 | 42 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -624 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2024-09-03 | 2024-11-13 | IOU Designed & Installed | N/A | No | N/A | 2947.97 | 509.4 | Unknown | 81.15 | Unknown | 2357.42 | 3981 | 1289.22 | 2947.97 | -1658.75 | Yes | N/A | N/A | 2024-08-23 | 2024-09-03 | 12 | 8 | 2024-09-03 | 2024-09-03 | 1 | 1 | 2024-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-11-13 | 72 | 52 | Unknown | 2024-11-12 | Unknown | Unknown | 2024-11-13 | 2024-11-19 | 1900-01-06 | 5 | 2024-11-19 | 2024-11-19 | 1 | 1 | 84 | 60 | 9 | 7 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | -37 | -28 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | 2025-04-23 | IOU Designed & Installed | N/A | No | N/A | 15299.55 | -7.1 | Unknown | Unknown | 7.98 | 15298.67 | 457179 | 27655.16 | 15299.55 | 12355.61 | Yes | N/A | N/A | 2024-09-25 | 2024-09-25 | 1 | 1 | 2024-09-25 | 2025-01-13 | 111 | 79 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-11-07 | 1 | 1 | 2025-01-13 | 2025-04-04 | 82 | 60 | Unknown | 2025-04-07 | Unknown | Unknown | 2025-04-23 | 2025-05-05 | 1900-01-12 | 9 | 2025-05-05 | 2025-04-28 | Unknown | Unknown | 83 | 61 | 125 | 89 | 208 | 150 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 20.5 | 20.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | -681 | -488 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2024-11-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 11.52 | Unknown | Unknown | Unknown | Unknown | 11.52 | Unknown | 606.18 | 11.52 | 594.66 | Yes | N/A | N/A | 2024-11-08 | 2024-11-08 | 1 | 1 | 2024-11-08 | 2024-11-08 | 1 | 1 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-11-20 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-17 | -443 | -318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | 2025-01-14 | IOU Designed & Installed | N/A | No | N/A | 1509.22 | Unknown | Unknown | Unknown | 5.34 | 1503.88 | 3981 | 1150.65 | 1509.22 | -358.57 | Yes | N/A | N/A | 2024-10-17 | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2024-11-15 | 52 | 38 | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2025-01-14 | 61 | 43 | Unknown | 2025-01-14 | Unknown | Unknown | 2025-01-14 | 2025-01-29 | 1900-01-15 | 12 | 2025-01-29 | 2025-01-29 | 1 | 1 | 61 | 43 | 69 | 51 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-02 | -468 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 132.78 | -5.16 | Unknown | Unknown | 6.28 | 131.66 | Unknown | 1133.2 | 132.78 | 1000.42 | Yes | N/A | N/A | 2023-08-04 | 2023-05-16 | Unknown | Unknown | 2023-05-16 | 2023-08-16 | 93 | 67 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-20 | Unknown | Unknown | 2024-01-20 | 2024-01-20 | 1 | 0 | 0 | 0 | 94 | 67 | 94 | 67 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-23 | -632 | -453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-04 | 2024-06-07 | IOU Designed & Installed | N/A | No | N/A | 3.88 | Unknown | Unknown | Unknown | Unknown | 3.88 | Unknown | 1457.03 | 3.88 | 1453.15 | Yes | N/A | N/A | 2024-06-03 | 2024-04-25 | Unknown | Unknown | 2024-04-25 | 2024-06-04 | 41 | 29 | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-06-07 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-07-30 | 1900-02-22 | 38 | 2024-07-30 | 2024-07-30 | 1 | 1 | 4 | 4 | 96 | 68 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-06 | 74 | 53 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2023-08-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | -847.38 | 2092.02 | Unknown | 483.9 | -4278 | 854.7 | 0 | 4277.9 | -847.38 | 5125.28 | Yes | N/A | N/A | 2023-08-01 | 2023-08-15 | 15 | 11 | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | Unknown | Unknown | 2024-09-18 | 2024-09-18 | 1 | 1 | 15 | 11 | 1 | 1 | 16 | 12 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 585 | 420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-26 | 2024-10-17 | IOU Designed & Installed | N/A | No | N/A | 3985.5 | Unknown | Unknown | Unknown | -1125 | 5110.5 | Unknown | 962.51 | 3985.5 | -3022.99 | Yes | N/A | N/A | 2024-02-15 | 2024-02-15 | 1 | 1 | 2024-02-15 | 2024-05-09 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-09-24 | 139 | 99 | Unknown | 2024-09-12 | Unknown | Unknown | 2024-10-17 | 2024-11-14 | 1900-01-28 | 21 | 2024-11-14 | 2024-10-25 | Unknown | Unknown | 140 | 100 | 114 | 82 | 254 | 182 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Vista | N/A | 117.05 | 117.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -150 | -108 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2024-03-25 | 2024-08-08 | IOU Designed & Installed | N/A | No | N/A | 30060.41 | 3920.89 | Unknown | Unknown | -19298.38 | 45437.9 | 1602 | 23432.16 | 30060.41 | -6628.25 | Yes | N/A | N/A | 2023-12-05 | 2024-02-02 | 60 | 44 | 2024-02-02 | 2024-07-02 | 152 | 108 | 2024-04-29 | 2024-06-20 | 5 | 3 | 2024-06-21 | 2024-06-27 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-09-04 | 1900-01-27 | 20 | 2024-09-04 | 2024-09-04 | 1 | 1 | 65 | 47 | 188 | 134 | 253 | 181 | Steps 2,3,5,6,7 | 64 | 46 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 147.05 | 147.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-29 | 267 | 191 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-04-13 | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | 8322.79 | Unknown | Unknown | Unknown | 6.77 | 8316.02 | 3981 | 726.48 | 8322.79 | -7596.31 | Yes | N/A | N/A | 2023-01-24 | 2023-04-12 | 79 | 57 | 2023-04-12 | 2023-08-14 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | 2024-06-12 | 281 | 201 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | 2024-09-03 | 2024-09-21 | 1900-01-18 | 14 | 2024-09-21 | 2024-09-21 | 1 | 0 | 79 | 57 | 426 | 304 | 505 | 361 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-16 | -532 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-20 | 2024-01-29 | IOU Designed & Installed | N/A | No | N/A | 977.54 | 315.58 | Unknown | Unknown | Unknown | 661.96 | 3241 | 674.57 | 977.54 | -302.97 | Yes | N/A | N/A | 2023-10-20 | 2023-10-20 | 1 | 1 | 2023-10-20 | 2023-10-20 | 1 | 1 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2024-01-29 | 102 | 72 | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-01-31 | 1900-01-02 | 3 | 2024-01-31 | 2024-01-31 | 1 | 1 | 103 | 73 | 5 | 5 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 119.2 | 119.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | -271 | -194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-07-09 | 2024-11-18 | IOU Designed & Installed | N/A | No | N/A | 55.64 | -0.63 | Unknown | Unknown | Unknown | 56.27 | 3981 | 1624.42 | 55.64 | 1568.78 | Yes | N/A | N/A | 2024-06-11 | 2024-06-25 | 15 | 11 | 2024-06-25 | 2024-07-09 | 15 | 11 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-11-18 | 133 | 95 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-12-06 | 1900-01-18 | 15 | 2024-12-06 | 2024-12-04 | Unknown | Unknown | 148 | 106 | 34 | 26 | 182 | 132 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | -293 | -210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-30 | 2024-06-12 | IOU Designed & Installed | N/A | No | N/A | 696.85 | 1880.88 | Unknown | 263.22 | -2292 | 844.75 | Unknown | 2291.63 | 696.85 | 1594.78 | Yes | N/A | N/A | 2024-04-23 | 2024-04-22 | Unknown | Unknown | 2024-04-22 | 2024-06-21 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | Unknown | Unknown | Unknown | 2024-06-21 | 2024-06-21 | 1 | 1 | 2024-06-12 | 2024-06-21 | 1900-01-09 | 8 | 2024-06-21 | 2024-06-21 | 1 | 1 | 0 | 0 | 73 | 55 | 73 | 55 | Steps 2,3,5,6,7 | 9 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-16 | -333 | -238 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | 2024-12-10 | IOU Designed & Installed | N/A | No | N/A | 20.03 | Unknown | Unknown | Unknown | Unknown | 20.03 | 3941 | 852.62 | 20.03 | 832.59 | Yes | N/A | N/A | 2024-01-11 | 2023-12-20 | Unknown | Unknown | 2023-12-20 | 2024-01-11 | 23 | 17 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-12-10 | 335 | 239 | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2024-12-18 | 1900-01-08 | 7 | 2024-12-18 | 2024-12-18 | 1 | 1 | 335 | 239 | 33 | 25 | 368 | 264 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 96 | 96 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-29 | -255 | -182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-12 | 2025-01-10 | IOU Designed & Installed | N/A | No | N/A | 1285.24 | Unknown | Unknown | Unknown | 27.22 | 1258.02 | 3981 | 1526.53 | 1285.24 | 241.29 | Yes | N/A | N/A | 2024-01-04 | 2024-07-15 | 194 | 138 | 2024-07-15 | 2024-07-15 | 1 | 1 | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2025-01-10 | 178 | 128 | Unknown | 2024-11-19 | Unknown | Unknown | 2025-01-10 | 2025-01-17 | 1900-01-07 | 6 | 2025-01-17 | 2025-01-17 | 1 | 1 | 372 | 266 | 10 | 8 | 382 | 274 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-13 | 7 | 6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-03 | 2023-03-01 | 2023-04-07 | IOU Designed & Installed | N/A | No | N/A | 9783.34 | Unknown | Unknown | Unknown | Unknown | 9783.34 | 0 | 1505.53 | 9783.34 | -8277.81 | Yes | N/A | N/A | 2022-05-03 | 2023-05-08 | 371 | 265 | 2023-05-08 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | 2023-03-21 | 2 | 2 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-04-20 | 1900-01-13 | 10 | 2023-04-20 | 2023-04-20 | 1 | 1 | 371 | 265 | 17 | 13 | 388 | 278 | Steps 2,3,5,6,7 | 1 | 1 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Commercial | Underserved Community | San Marcos | SAN MARCOS | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-01 | 726 | 519 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 35692.7 | 10781.28 | Unknown | Unknown | -25228 | 50139.42 | 4735.84 | 63447.13 | 35692.7 | 27754.43 | Yes | N/A | N/A | 2023-03-08 | 2023-03-03 | Unknown | Unknown | 2023-03-03 | 2023-09-22 | 204 | 146 | 2023-05-24 | 2023-06-01 | 9 | 7 | 2023-07-11 | 2025-07-07 | 56 | 42 | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-09-26 | 1 | 1 | 9 | 7 | 261 | 189 | 270 | 196 | Steps 2,3,5,6,7 | 775 | 553 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 73.1 | 73.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-29 | -565 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-05 | 2024-03-01 | IOU Designed & Installed | N/A | No | N/A | 5.83 | -5.21 | Unknown | Unknown | Unknown | 11.04 | Unknown | 970.67 | 5.83 | 964.84 | Yes | N/A | N/A | 2024-02-02 | 2024-02-05 | 4 | 2 | 2024-02-05 | 2024-02-05 | 1 | 1 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-03-01 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-03-15 | 1900-01-14 | 11 | 2024-03-15 | 2024-03-13 | Unknown | Unknown | 30 | 22 | 16 | 12 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-26 | -537 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-21 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | 656.27 | Unknown | Unknown | Unknown | 5.63 | 650.64 | 3621 | 790.36 | 656.27 | 134.09 | Yes | N/A | N/A | 2024-03-12 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | 2024-03-21 | 43 | 31 | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-07-16 | 118 | 84 | Unknown | 2024-07-08 | Unknown | Unknown | 2024-07-16 | 2024-08-07 | 1900-01-22 | 17 | 2024-08-07 | 2024-08-07 | 1 | 1 | 118 | 84 | 67 | 49 | 185 | 133 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JULIAN | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -666 | -477 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-24 | 2024-06-25 | IOU Designed & Installed | N/A | No | N/A | 4082.82 | 1274.36 | Unknown | Unknown | Unknown | 2808.46 | 3981 | 1149.69 | 4082.82 | -2933.13 | Yes | N/A | N/A | 2024-06-14 | 2024-05-23 | Unknown | Unknown | 2024-05-23 | 2024-06-24 | 33 | 23 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-06-25 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-18 | 1900-01-23 | 18 | 2024-07-18 | 2024-07-18 | 1 | 1 | 2 | 2 | 58 | 42 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | -1068 | -765 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-10 | 2024-04-11 | IOU Designed & Installed | N/A | No | N/A | -19.22 | -15.62 | Unknown | Unknown | Unknown | -3.6 | Unknown | 534.57 | -19.22 | 553.79 | Yes | N/A | N/A | 2024-04-10 | 2024-04-10 | 1 | 1 | 2024-04-10 | 2024-04-10 | 1 | 1 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-04-11 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-04-22 | 1900-01-11 | 8 | 2024-04-22 | 2024-04-22 | 1 | 1 | 3 | 3 | 14 | 10 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | -381 | -274 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-22 | 2025-01-06 | IOU Designed & Installed | N/A | No | N/A | -3734.31 | 630.6 | Unknown | 39.38 | -4836 | 431.71 | Unknown | 4835.97 | -3734.31 | 8570.28 | Yes | N/A | N/A | 2024-11-22 | 2024-11-19 | Unknown | Unknown | 2024-11-19 | 2025-01-03 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-01-06 | 4 | 2 | 2025-01-03 | 2025-01-03 | 1 | 1 | 2025-01-06 | 2025-01-06 | 1899-12-31 | 1 | 2025-01-06 | 2025-01-06 | 1 | 1 | 4 | 2 | 49 | 37 | 53 | 39 | Steps 2,3,5,6,7 | 3 | 1 | Meeting | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Residential | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -240 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-20 | 2022-12-20 | 2025-04-23 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 84945.82 | 8964.16 | Unknown | Unknown | 116.37 | 75865.29 | 417425 | 40628.94 | 84945.82 | -44316.88 | Yes | N/A | N/A | 2022-12-20 | 2023-05-01 | 133 | 95 | 2023-05-01 | 2024-01-10 | 255 | 183 | 2023-05-09 | 2024-01-02 | 92 | 66 | 2023-04-26 | 2024-01-25 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-05-05 | 1900-01-12 | 9 | 2025-05-05 | 2025-05-05 | 1 | 1 | 225 | 161 | 301 | 217 | 526 | 378 | Steps 2,3,5,6,7 | 497 | 355 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-17 | -670 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-16 | 2025-05-08 | IOU Designed & Installed | N/A | No | N/A | 494.25 | -10.2 | Unknown | Unknown | Unknown | 504.45 | Unknown | 1029.34 | 494.25 | 535.09 | Yes | N/A | N/A | 2025-04-01 | 2025-04-08 | 8 | 6 | 2025-04-08 | 2025-04-15 | 8 | 6 | 2025-04-15 | Unknown | Unknown | Unknown | 2025-04-16 | 2025-04-21 | 6 | 4 | 2025-04-16 | 2025-05-08 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-05-16 | 1900-01-08 | 7 | 2025-05-16 | 2025-05-16 | 1 | 1 | 31 | 23 | 24 | 18 | 55 | 41 | Steps 2,3,5,6,7 | 5 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | -614 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | Unknown | 2024-11-11 | IOU Designed & Installed | N/A | No | N/A | 73.14 | -1.5 | Unknown | Unknown | 0.53 | 74.11 | 3981 | 1546.72 | 73.14 | 1473.58 | Yes | N/A | N/A | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-11-11 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2025-02-07 | 1900-03-29 | 65 | 2025-02-07 | 2025-02-07 | 1 | 1 | 21 | 15 | 91 | 67 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-23 | -267 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-06-08 | 2023-09-27 | IOU Designed & Installed | N/A | No | N/A | 19917.41 | 498.08 | Unknown | 235.16 | Unknown | 19184.17 | 9596 | 4517.85 | 19917.41 | -15399.56 | Yes | N/A | N/A | 2023-06-08 | 2023-06-22 | 15 | 11 | 2023-06-22 | 2023-06-27 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-27 | 2023-09-22 | 88 | 64 | Unknown | 2023-08-24 | Unknown | Unknown | 2023-09-27 | 2023-10-03 | 1900-01-06 | 5 | 2023-10-03 | 2023-09-30 | Unknown | Unknown | 103 | 75 | 13 | 9 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 109.05 | 109.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 10 | 7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 409.31 | -18.39 | Unknown | Unknown | 3.01 | 424.69 | 3981 | 1875.17 | 409.31 | 1465.86 | Yes | N/A | N/A | 2023-02-09 | 2023-03-02 | 22 | 16 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | Unknown | Unknown | Unknown | 2023-09-14 | Unknown | Unknown | 2023-09-14 | 2023-12-11 | 89 | 63 | 22 | 16 | 89 | 63 | 111 | 79 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-01 | 825 | 590 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-17 | 2023-08-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 19905 | 364.1 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-17 | 2023-09-15 | 30 | 22 | 2023-09-15 | 2023-10-19 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2024-08-23 | 310 | 222 | Unknown | 2024-08-08 | Unknown | Unknown | Unknown | 2024-09-03 | Unknown | Unknown | 2024-09-03 | 2024-09-03 | 1 | 1 | 340 | 244 | 36 | 26 | 376 | 270 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-08 | -344 | -247 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | 7127.74 | 1545.99 | Unknown | 299.48 | 26.89 | 5255.38 | 3981 | 1191.8 | 7127.74 | -5935.94 | Yes | N/A | N/A | 2024-04-17 | 2024-06-21 | 66 | 48 | 2024-06-21 | 2024-08-01 | 42 | 30 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2025-01-15 | 168 | 120 | Unknown | 2025-01-15 | Unknown | Unknown | 2025-01-15 | 2025-01-29 | 1900-01-14 | 11 | 2025-01-29 | 2025-01-29 | 1 | 1 | 234 | 168 | 58 | 42 | 292 | 210 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-30 | -293 | -210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-27 | 2025-04-12 | IOU Designed & Installed | N/A | No | N/A | -1986.11 | 3729.32 | Unknown | 229.74 | -7567 | 1621.83 | Unknown | 7567.27 | -1986.11 | 9553.38 | Yes | N/A | N/A | 2025-03-14 | 2025-03-13 | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-12 | 2025-04-13 | 1900-01-01 | 0 | 2025-04-13 | 2025-04-12 | Unknown | Unknown | 0 | 0 | 2 | 0 | 2 | 0 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8.4 | 8.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-30 | -688 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-29 | 2025-06-02 | IOU Designed & Installed | N/A | No | N/A | 678.38 | Unknown | Unknown | Unknown | Unknown | 678.38 | 3981 | 1339.45 | 678.38 | 661.07 | Yes | N/A | N/A | 2025-05-29 | 2025-05-09 | Unknown | Unknown | 2025-05-09 | 2025-05-29 | 21 | 15 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-02 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-06-11 | 1900-01-09 | 8 | 2025-06-11 | 2025-06-11 | 1 | 1 | 5 | 3 | 32 | 24 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-22 | 325 | 232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-17 | 2023-01-10 | 2024-05-10 | IOU Designed & Installed | N/A | No | N/A | 11759.51 | 2174.55 | Unknown | Unknown | 2.27 | 9582.69 | 3981 | 628.41 | 11759.51 | -11131.1 | Yes | N/A | N/A | 2022-11-17 | 2024-02-23 | 464 | 332 | 2024-02-23 | 2024-02-23 | 1 | 1 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-05-10 | 78 | 56 | Unknown | 2024-05-09 | Unknown | Unknown | 2024-05-10 | 2024-05-16 | 1900-01-06 | 5 | 2024-05-16 | 2024-08-12 | 89 | 63 | 542 | 388 | 97 | 69 | 639 | 457 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | -586 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 586.36 | -11.7 | Unknown | Unknown | 5.6 | 592.46 | Unknown | 1742.63 | 586.36 | 1156.27 | Yes | N/A | N/A | 2024-10-15 | 2024-10-14 | Unknown | Unknown | 2024-10-14 | 2024-10-15 | 2 | 2 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-11-07 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2025-02-07 | 1900-04-02 | 67 | 2025-02-07 | 2025-02-07 | 1 | 1 | 24 | 18 | 96 | 70 | 120 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-09 | -388 | -279 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-21 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | 2838.12 | 319.76 | Unknown | 16.21 | 32.14 | 2470.01 | 3981 | 1212.23 | 2838.12 | -1625.89 | Yes | N/A | N/A | 2024-08-16 | 2024-08-23 | 8 | 6 | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2025-03-03 | 193 | 137 | Unknown | 2025-02-28 | Unknown | Unknown | 2025-03-03 | 2025-03-17 | 1900-01-14 | 11 | 2025-03-17 | 2025-03-17 | 1 | 1 | 201 | 143 | 17 | 13 | 218 | 156 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | 88 | 63 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2024-09-11 | 2025-05-15 | IOU Designed & Installed | N/A | No | N/A | 3157.31 | 89.02 | Unknown | Unknown | 14.83 | 3053.46 | Unknown | 17173.56 | 3157.31 | 14016.25 | Yes | N/A | N/A | 2024-08-23 | 2024-08-22 | Unknown | Unknown | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-05-06 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-06-17 | 1900-02-02 | 24 | 2025-06-17 | 2025-06-17 | 1 | 1 | 0 | 0 | 78 | 56 | 78 | 56 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 164 | 164 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -415 | -298 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-28 | 2025-06-14 | IOU Designed & Installed | N/A | No | N/A | -691.86 | -7.6 | Unknown | Unknown | -2435.55 | 1751.29 | 0 | 2851.72 | -691.86 | 3543.58 | Yes | N/A | N/A | 2024-02-15 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2025-05-15 | 477 | 341 | 2025-06-04 | 2025-06-04 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-05-29 | 15 | 11 | Unknown | 2025-06-10 | Unknown | Unknown | 2025-06-14 | 2025-06-17 | 1900-01-03 | 2 | 2025-06-17 | 2025-06-16 | Unknown | Unknown | 16 | 12 | 481 | 343 | 497 | 355 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-16 | 117 | 85 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-22 | 2024-09-24 | IOU Designed & Installed | N/A | No | N/A | 884.89 | Unknown | Unknown | Unknown | 10.88 | 874.01 | 0 | 1982.72 | 884.89 | 1097.83 | Yes | N/A | N/A | 2023-08-22 | 2023-06-19 | Unknown | Unknown | 2023-06-19 | 2023-08-25 | 68 | 50 | 2023-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-25 | 2024-09-24 | 397 | 283 | Unknown | 2024-08-15 | Unknown | Unknown | 2024-09-24 | 2024-10-11 | 1900-01-17 | 14 | 2024-10-11 | 2024-10-11 | 1 | 1 | 397 | 283 | 87 | 65 | 484 | 348 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-02 | 151 | 109 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-08-23 | IOU Designed & Installed | N/A | No | N/A | -4.35 | -8.54 | Unknown | Unknown | Unknown | 4.19 | 3981 | 663.56 | -4.35 | 667.91 | Yes | N/A | N/A | 2023-02-07 | 2023-02-08 | 2 | 2 | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | 2023-08-17 | 68 | 50 | 2023-02-08 | 2023-08-23 | 197 | 141 | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | 2023-09-05 | 1900-01-13 | 10 | 2023-09-05 | 2023-08-31 | Unknown | Unknown | 199 | 143 | 82 | 60 | 281 | 203 | Steps 2,3,5,6,7 | 190 | 136 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-14 | -230 | -165 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-09-29 | 2023-11-08 | IOU Designed & Installed | N/A | No | N/A | 0.48 | -6.8 | Unknown | Unknown | Unknown | 7.28 | 3281 | 851.2 | 0.48 | 850.72 | Yes | N/A | N/A | 2023-09-28 | 2023-09-29 | 2 | 2 | 2023-09-29 | 2023-09-29 | 1 | 1 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-11-08 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2023-11-27 | 1900-01-19 | 14 | 2023-11-27 | 2023-11-27 | 1 | 1 | 43 | 31 | 22 | 16 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-25 | -503 | -360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | 2024-09-05 | IOU Designed & Installed | N/A | No | N/A | 425.28 | 251.36 | Unknown | Unknown | Unknown | 173.92 | 3981 | 163.83 | 425.28 | -261.45 | Yes | N/A | N/A | 2024-04-16 | 2024-04-16 | 1 | 1 | 2024-04-16 | 2024-04-22 | 7 | 5 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-09-05 | 137 | 99 | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2024-09-10 | 1900-01-05 | 4 | 2024-09-10 | 2024-09-09 | Unknown | Unknown | 138 | 100 | 13 | 9 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-04 | -162 | -117 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-19 | 2023-10-03 | IOU Designed & Installed | N/A | No | N/A | 497.28 | -13.94 | Unknown | Unknown | Unknown | 511.22 | Unknown | 836.31 | 497.28 | 339.03 | Yes | N/A | N/A | 2023-06-19 | 2023-06-19 | 1 | 1 | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | 2023-10-03 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-10-25 | 1900-01-22 | 17 | 2023-10-25 | 2023-10-25 | 1 | 1 | 108 | 78 | 24 | 18 | 132 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-05 | 133 | 96 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-05-15 | 2023-05-30 | IOU Designed & Installed | N/A | No | N/A | -4.47 | -3.62 | Unknown | Unknown | Unknown | -0.85 | 0 | 495.75 | -4.47 | 500.22 | Yes | N/A | N/A | 2023-03-20 | 2023-03-31 | 12 | 10 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-15 | 2023-05-30 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | 2024-06-17 | 1901-01-19 | 275 | 2024-06-17 | 2024-06-17 | 1 | 1 | 28 | 22 | 386 | 276 | 414 | 298 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -521 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-21 | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | 2097.27 | 182.33 | Unknown | Unknown | 27.41 | 1887.53 | 3941 | 273.91 | 2097.27 | -1823.36 | Yes | N/A | N/A | 2024-05-17 | 2024-03-18 | Unknown | Unknown | 2024-03-18 | 2024-05-31 | 75 | 55 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-09-17 | 110 | 78 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-09-18 | 1900-01-01 | 2 | 2024-09-18 | 2024-09-18 | 1 | 1 | 110 | 78 | 78 | 58 | 188 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | -365 | -260 | No | 2024-08-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2025-03-04 | IOU Designed & Installed | N/A | Yes | 182 | 988.25 | -10.2 | Unknown | Unknown | 33.69 | 964.76 | 3981 | 196.44 | 988.25 | -791.81 | Yes | N/A | N/A | 2024-08-27 | 2025-02-25 | 183 | 131 | 2025-02-25 | 2024-10-03 | Unknown | Unknown | 2024-10-03 | 2025-02-26 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-03-04 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-05-31 | 1900-03-29 | 64 | 2025-05-31 | 2025-05-31 | 1 | 0 | 337 | 241 | 90 | 64 | 427 | 305 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-20 | -548 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-22 | 2024-03-13 | IOU Designed & Installed | N/A | No | N/A | 560.62 | -6.36 | Unknown | Unknown | Unknown | 566.98 | 3981 | 805.64 | 560.62 | 245.02 | Yes | N/A | N/A | 2024-01-08 | 2024-01-22 | 15 | 11 | 2024-01-22 | 2024-01-22 | 1 | 1 | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-03-13 | 52 | 38 | Unknown | 2024-03-25 | Unknown | Unknown | 2024-03-13 | 2024-03-21 | 1900-01-08 | 7 | 2024-03-21 | 2024-03-21 | 1 | 1 | 67 | 49 | 11 | 9 | 78 | 58 | Steps 2,3,5,6,7 | 12 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-15 | -380 | -271 | No | 2024-04-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-19 | 2024-04-29 | Unknown | IOU Designed & Installed | N/A | Yes | 154 | 4.88 | Unknown | Unknown | Unknown | Unknown | 4.88 | 3981 | 496.14 | 4.88 | 491.26 | Yes | N/A | N/A | 2024-04-19 | 2024-09-06 | 141 | 101 | 2024-09-06 | 2024-09-20 | 15 | 11 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | 2025-02-28 | 2025-02-28 | 1 | 1 | 141 | 101 | 16 | 12 | 157 | 113 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 12000 | 12000 | Not Available | >2MW | No | N/A | N/A | N/A | 2027-03-03 | -657 | -470 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1864.89 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-03 | 2025-04-18 | 16 | 12 | 2025-04-18 | 2025-04-21 | 4 | 2 | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | 2025-05-15 | 2025-05-15 | 1 | 1 | 16 | 12 | 5 | 3 | 21 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-30 | 300 | 215 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-03-16 | 2023-06-05 | IOU Designed & Installed | N/A | No | N/A | 2614.52 | -77.61 | Unknown | Unknown | 8.36 | 2683.77 | Unknown | 812.25 | 2614.52 | -1802.27 | Yes | N/A | N/A | 2023-03-16 | 2023-03-16 | 1 | 1 | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-16 | 2023-06-05 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2023-09-26 | 1900-04-23 | 82 | 2023-09-26 | 2023-09-26 | 1 | 1 | 83 | 59 | 115 | 83 | 198 | 142 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 139 | 139 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-27 | -164 | -118 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-02-22 | 2023-07-21 | IOU Designed & Installed | N/A | No | N/A | 21165.91 | 414.93 | Unknown | 413.46 | 41.69 | 20295.83 | 3981 | 2366.23 | 21165.91 | -18799.68 | Yes | N/A | N/A | 2023-02-22 | 2023-04-28 | 66 | 48 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | 2023-07-21 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2023-08-16 | 1900-01-26 | 19 | 2023-08-16 | 2023-08-16 | 1 | 1 | 151 | 109 | 28 | 20 | 179 | 129 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 150 | 107 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-03 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 952.27 | Unknown | Unknown | Unknown | 4.38 | 947.89 | 3981 | 1252.95 | 952.27 | 300.68 | Yes | N/A | N/A | 2024-05-03 | 2024-03-18 | Unknown | Unknown | 2024-03-18 | 2024-05-23 | 67 | 49 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-07-11 | 50 | 36 | Unknown | 2024-07-08 | Unknown | Unknown | 2024-07-11 | 2024-07-29 | 1900-01-18 | 13 | 2024-07-29 | 2024-07-29 | 1 | 1 | 50 | 36 | 87 | 63 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-09 | -46 | -35 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2025-02-19 | 2025-03-24 | IOU Designed & Installed | N/A | No | N/A | 622.92 | 800.68 | Unknown | 78.02 | -668 | 412.22 | Unknown | 668.2 | 622.92 | 45.28 | Yes | N/A | N/A | 2024-10-24 | 2025-03-04 | 132 | 94 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1899-12-31 | 1 | 2025-03-24 | 2025-03-24 | 1 | 1 | 132 | 94 | 2 | 2 | 134 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-11-04 | 539 | 386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2024-04-17 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 8287.24 | 300.29 | Unknown | Unknown | -6917 | 14903.95 | 2875.23 | 9741.59 | 8287.24 | 1454.35 | Yes | N/A | N/A | 2023-02-09 | 2023-03-15 | 35 | 25 | 2023-03-15 | 2023-09-14 | 184 | 132 | 2023-03-21 | 2023-06-21 | 93 | 67 | 2023-07-26 | 2023-08-30 | 35 | 25 | 2023-09-14 | 2024-04-10 | 210 | 150 | 2023-09-19 | 2024-04-08 | 203 | 145 | 2024-04-17 | 2024-04-30 | 1900-01-13 | 10 | 2024-04-30 | 2024-04-26 | Unknown | Unknown | 338 | 242 | 436 | 312 | 774 | 554 | Steps 2,3,5,6,7 | 381 | 273 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | Lemon Grove | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-02 | 428 | 306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 86.72 | -16.22 | Unknown | Unknown | 86.19 | 16.75 | Unknown | 6210.94 | 86.72 | 6124.22 | Yes | N/A | N/A | 2023-08-08 | 2023-10-05 | 59 | 43 | 2023-10-05 | 2023-10-05 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2024-08-03 | 1 | 0 | 59 | 43 | 2 | 1 | 61 | 44 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | Lakeside | COUNTY OF SAN DIEGO-NORTH of 56 | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-19 | -230 | -165 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-08 | 2024-07-17 | IOU Designed & Installed | N/A | No | N/A | 3819.22 | Unknown | Unknown | Unknown | -1609 | 5428.22 | Unknown | 1224.06 | 3819.22 | -2595.16 | Yes | N/A | N/A | 2024-05-07 | 2024-05-07 | 1 | 1 | 2024-05-07 | 2024-07-11 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-07-10 | 9 | 7 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-08-01 | 1900-01-15 | 12 | 2024-08-01 | 2024-08-01 | 1 | 1 | 1 | 1 | 92 | 68 | 93 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Carlsbad | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-27 | 284 | 203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2023-12-15 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 5313.49 | Unknown | Unknown | Unknown | -2763 | 8076.49 | 0 | 3027.89 | 5313.49 | -2285.6 | Yes | N/A | N/A | 2023-12-15 | 2023-03-17 | Unknown | Unknown | 2023-03-17 | 2025-02-27 | 714 | 510 | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-04-10 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-04-07 | 1900-01-21 | 16 | 2025-04-07 | 2025-04-07 | 1 | 1 | 0 | 0 | 745 | 533 | 745 | 533 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-23 | 1 | 2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-12 | 2024-07-17 | IOU Designed & Installed | N/A | No | N/A | 906.96 | 278.11 | Unknown | Unknown | Unknown | 628.85 | 3981 | 807.18 | 906.96 | -99.78 | Yes | N/A | N/A | 2024-07-12 | 2024-07-03 | Unknown | Unknown | 2024-07-03 | 2024-07-12 | 10 | 8 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-07-17 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-07-24 | 1900-01-07 | 6 | 2024-07-24 | 2024-07-24 | 1 | 1 | 6 | 4 | 19 | 15 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-02 | -216 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-20 | 2023-09-27 | IOU Designed & Installed | N/A | No | N/A | 42.75 | -6.65 | Unknown | Unknown | Unknown | 49.4 | Unknown | 731.61 | 42.75 | 688.86 | Yes | N/A | N/A | 2023-07-18 | 2023-05-10 | Unknown | Unknown | 2023-05-10 | 2023-07-20 | 72 | 52 | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-09-27 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-09-29 | 1900-01-02 | 3 | 2023-09-29 | 2023-09-29 | 1 | 1 | 70 | 50 | 76 | 56 | 146 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | -675 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-11 | 2024-11-04 | IOU Designed & Installed | N/A | No | N/A | 1.62 | Unknown | Unknown | Unknown | Unknown | 1.62 | Unknown | 197.01 | 1.62 | 195.39 | Yes | N/A | N/A | 2024-10-10 | 2024-10-21 | 12 | 8 | 2024-10-21 | 2024-11-01 | 12 | 10 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2024-11-04 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-11-19 | 1900-01-15 | 12 | 2024-11-19 | 2024-11-19 | 1 | 1 | 16 | 10 | 29 | 23 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-05 | -197 | -142 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-17 | 2023-08-17 | 2023-09-14 | IOU Designed & Installed | N/A | No | N/A | -5.95 | -5.14 | Unknown | Unknown | Unknown | -0.81 | Unknown | 153.83 | -5.95 | 159.78 | Yes | N/A | N/A | 2023-08-17 | 2023-04-13 | Unknown | Unknown | 2023-04-13 | 2023-08-28 | 138 | 98 | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2023-09-14 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-09-21 | 1900-01-07 | 6 | 2023-09-21 | 2023-09-21 | 1 | 1 | 18 | 14 | 147 | 105 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-29 | -534 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | 2024-05-07 | IOU Designed & Installed | N/A | No | N/A | 1451.32 | 244.9 | Unknown | Unknown | 12.54 | 1193.88 | Unknown | 1078.66 | 1451.32 | -372.66 | Yes | N/A | N/A | 2024-03-18 | 2023-12-12 | Unknown | Unknown | 2023-12-12 | 2024-04-30 | 141 | 101 | 2024-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2024-05-07 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-06-13 | 1900-02-06 | 28 | 2024-06-13 | 2024-06-13 | 1 | 1 | 8 | 6 | 180 | 130 | 188 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-13 | -112 | -81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.78 | -3.59 | Unknown | Unknown | Unknown | -0.19 | 3961 | 153.83 | -3.78 | 157.61 | Yes | N/A | N/A | 2023-03-31 | 2023-08-17 | 140 | 100 | 2023-08-17 | 2023-08-17 | 1 | 1 | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | Unknown | Unknown | 2023-10-24 | 2023-10-24 | 1 | 1 | 140 | 100 | 2 | 2 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 179 | 179 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-18 | -445 | -320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-12-14 | 2024-04-12 | IOU Designed & Installed | N/A | No | N/A | 628.93 | -11.44 | Unknown | Unknown | Unknown | 640.37 | 3981 | 742.97 | 628.93 | 114.04 | Yes | N/A | N/A | 2023-11-29 | 2023-12-06 | 8 | 6 | 2023-12-06 | 2023-12-14 | 9 | 7 | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2024-04-12 | 121 | 87 | Unknown | 2024-04-08 | Unknown | Unknown | 2024-04-12 | 2024-04-29 | 1900-01-17 | 12 | 2024-04-29 | 2024-04-29 | 1 | 1 | 129 | 93 | 28 | 20 | 157 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 124 | 124 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-20 | 99 | 72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-06-12 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 50.41 | Unknown | Unknown | Unknown | Unknown | 50.41 | Unknown | 1550.18 | 50.41 | 1499.77 | Yes | N/A | N/A | 2024-05-17 | 2024-04-22 | Unknown | Unknown | 2024-04-22 | 2024-06-12 | 52 | 38 | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-09-10 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-10-01 | 1900-01-21 | 16 | 2024-10-01 | 2024-09-27 | Unknown | Unknown | 91 | 65 | 74 | 54 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-23 | -496 | -355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | -4.77 | -9.35 | Unknown | Unknown | Unknown | 4.58 | 3981 | 960.53 | -4.77 | 965.3 | Yes | N/A | N/A | 2023-05-16 | 2023-05-16 | 1 | 1 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | 2023-07-27 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-09-15 | 1900-02-19 | 37 | 2023-09-15 | 2023-09-15 | 1 | 1 | 74 | 54 | 52 | 38 | 126 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-18 | -200 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-08-28 | 2024-09-27 | IOU Designed & Installed | N/A | No | N/A | 879.33 | 253.74 | Unknown | Unknown | Unknown | 625.59 | 3941 | 812.97 | 879.33 | -66.36 | Yes | N/A | N/A | 2023-08-28 | 2023-08-28 | 1 | 1 | 2023-08-28 | 2023-08-28 | 1 | 1 | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2024-09-27 | 397 | 285 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-09-30 | 1900-01-03 | 2 | 2024-09-30 | 2024-09-30 | 1 | 1 | 398 | 286 | 6 | 4 | 404 | 290 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-30 | 286 | 205 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-13 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 27525.79 | Unknown | Unknown | Unknown | -1303 | 28828.79 | Unknown | 1303.14 | 27525.79 | -26222.65 | Yes | N/A | N/A | 2025-01-13 | 2025-01-13 | 1 | 1 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-03-12 | 1900-02-18 | 36 | 2025-03-12 | 2025-03-12 | 1 | 1 | 1 | 1 | 51 | 37 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-30 | -622 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | 2024-12-02 | IOU Designed & Installed | N/A | No | N/A | 23.81 | Unknown | Unknown | Unknown | Unknown | 23.81 | Unknown | 1773.98 | 23.81 | 1750.17 | Yes | N/A | N/A | 2024-11-25 | 2024-10-28 | Unknown | Unknown | 2024-10-28 | 2024-11-25 | 29 | 21 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-02 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2025-01-16 | 1900-02-14 | 34 | 2025-01-16 | 2025-01-16 | 1 | 1 | 8 | 6 | 76 | 56 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 27.05 | 27.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-11 | -309 | -222 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1750.38 | Unknown | Unknown | Unknown | 71.44 | 1678.94 | 3981 | 1187.82 | 1750.38 | -562.56 | Yes | N/A | N/A | 2024-02-16 | 2024-04-09 | 54 | 38 | 2024-04-09 | 2024-04-12 | 4 | 4 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | 2025-02-05 | 2025-02-05 | 1 | 1 | 54 | 38 | 5 | 5 | 59 | 43 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-10-01 | -856 | -613 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1450.15 | -3.88 | Unknown | Unknown | Unknown | 1454.03 | Unknown | 1137.09 | 1450.15 | -313.06 | Yes | N/A | N/A | 2025-03-11 | 2025-03-12 | 2 | 2 | 2025-03-12 | 2025-05-21 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-25 | 18 | 14 | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | Unknown | Unknown | 2025-05-28 | 2025-05-28 | 1 | 1 | 2 | 2 | 90 | 66 | 92 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | 263 | 188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 21206.55 | -21.26 | Unknown | 19.09 | 7.46 | 21201.26 | 3981 | 1557.6 | 21206.55 | -19648.95 | Yes | N/A | N/A | 2024-10-15 | 2024-10-16 | 2 | 2 | 2024-10-16 | 2025-02-12 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-04-18 | 66 | 48 | Unknown | 2025-03-25 | Unknown | Unknown | 2025-04-02 | 2025-05-05 | 1900-02-02 | 24 | 2025-05-05 | 2025-05-05 | 1 | 1 | 68 | 50 | 155 | 111 | 223 | 161 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 78 | 78 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-21 | -695 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | 2025-04-11 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1063.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-03-31 | Unknown | Unknown | 2025-03-31 | 2025-04-10 | 11 | 9 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-04-11 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-04-25 | 1900-01-14 | 11 | 2025-04-25 | 2025-04-25 | 1 | 1 | 2 | 2 | 27 | 21 | 29 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | -308 | -221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | 2024-01-19 | IOU Designed & Installed | N/A | No | N/A | -1259.54 | 1736.9 | Unknown | 96.98 | -3961 | 867.58 | Unknown | 3961.28 | -1259.54 | 5220.82 | Yes | N/A | N/A | 2023-12-12 | 2023-12-12 | 1 | 1 | 2023-12-12 | 2024-02-01 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-01-26 | Unknown | Unknown | 2024-02-01 | 2024-02-01 | 1 | 1 | 2024-01-19 | 2024-02-21 | 1900-02-02 | 24 | 2024-02-21 | 2024-01-26 | Unknown | Unknown | 1 | 1 | 87 | 63 | 88 | 64 | Steps 2,3,5,6,7 | 13 | 9 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | ES 1110-F5 DIXON TL REARR (E) | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | 111 | 80 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-06-01 | 2025-01-16 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 1691.51 | 5036.43 | Unknown | 1659 | -31749.59 | 26745.67 | 0 | 38234.76 | 1691.51 | 36543.25 | Yes | N/A | N/A | 2023-06-01 | 2024-01-26 | 240 | 172 | 2024-01-26 | 2024-11-06 | 286 | 204 | 2024-02-21 | 2024-10-24 | 121 | 85 | 2024-02-27 | 2024-12-04 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | Unknown | Unknown | 2025-01-16 | 2025-01-29 | 1900-01-13 | 10 | 2025-01-29 | 2025-01-29 | 1 | 1 | 361 | 257 | 347 | 249 | 708 | 506 | Steps 2,3,5,6,7 | 499 | 357 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | -669 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-17 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | 2777.28 | 482.65 | Unknown | 26.6 | Unknown | 2268.03 | 3981 | 1670.08 | 2777.28 | -1107.2 | Yes | N/A | N/A | 2024-06-17 | 2024-06-17 | 1 | 1 | 2024-06-17 | 2024-06-17 | 1 | 1 | 2024-06-17 | Unknown | Unknown | Unknown | 2024-06-18 | 2024-07-12 | 25 | 19 | 2024-06-17 | 2024-07-16 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-08-06 | 1900-01-21 | 16 | 2024-08-06 | 2024-08-06 | 1 | 1 | 31 | 23 | 49 | 37 | 80 | 60 | Steps 2,3,5,6,7 | 25 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Lakeside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-08 | 1 | 2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2023-08-01 | 2023-08-07 | IOU Designed & Installed | N/A | No | N/A | 138.91 | 581.2 | Unknown | 321.6 | -1150 | 386.11 | Unknown | 1150.07 | 138.91 | 1011.16 | Yes | N/A | N/A | 2023-08-01 | 2023-08-01 | 1 | 1 | 2023-08-01 | 2023-08-03 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-07 | 2023-08-09 | 1900-01-02 | 3 | 2023-08-09 | 2023-08-09 | 1 | 1 | 1 | 1 | 7 | 7 | 8 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -225 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 919.77 | 266.07 | Unknown | Unknown | 3.01 | 650.69 | 3981 | 2289.49 | 919.77 | 1369.72 | Yes | N/A | N/A | 2024-04-30 | 2024-03-13 | Unknown | Unknown | 2024-03-13 | 2024-05-17 | 66 | 48 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | 2024-07-18 | 2024-07-18 | 1 | 1 | 0 | 0 | 67 | 49 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-20 | -72 | -53 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 997.92 | 293.14 | Unknown | 109.36 | 10.48 | 584.94 | 3981 | 1995.03 | 997.92 | 997.11 | Yes | N/A | N/A | 2023-10-17 | 2023-10-27 | 11 | 9 | 2023-10-27 | 2023-10-27 | 1 | 1 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | Unknown | Unknown | Unknown | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2024-07-10 | 1 | 1 | 11 | 9 | 2 | 2 | 13 | 11 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-25 | -562 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | 2024-12-16 | IOU Designed & Installed | N/A | No | N/A | 83.85 | -1.56 | Unknown | Unknown | Unknown | 85.41 | Unknown | 1658.03 | 83.85 | 1574.18 | Yes | N/A | N/A | 2024-10-14 | 2024-10-24 | 11 | 9 | 2024-10-24 | 2024-11-06 | 14 | 10 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-12-16 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2025-01-09 | 1900-01-24 | 19 | 2025-01-09 | 2025-01-09 | 1 | 1 | 52 | 38 | 40 | 30 | 92 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 6.75 | 6.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-17 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-07-26 | 2024-09-27 | IOU Designed & Installed | N/A | No | N/A | 36.16 | Unknown | Unknown | Unknown | Unknown | 36.16 | 3981 | 1431.9 | 36.16 | 1395.74 | Yes | N/A | N/A | 2024-07-09 | 2024-07-23 | 15 | 11 | 2024-07-23 | 2024-07-26 | 4 | 4 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-09-27 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-10-18 | 1900-01-21 | 16 | 2024-10-18 | 2024-10-17 | Unknown | Unknown | 79 | 57 | 26 | 20 | 105 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-26 | -669 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-04-08 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | 31.11 | -0.63 | Unknown | Unknown | Unknown | 31.74 | 3981 | 1898.7 | 31.11 | 1867.59 | Yes | N/A | N/A | 2025-03-17 | 2025-03-28 | 12 | 10 | 2025-03-28 | 2025-04-08 | 12 | 8 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-25 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-04-28 | 1900-01-03 | 2 | 2025-04-28 | 2025-04-28 | 1 | 1 | 30 | 24 | 17 | 11 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | -492 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-12-19 | 2025-06-04 | IOU Designed & Installed | N/A | No | N/A | 605.93 | Unknown | Unknown | Unknown | Unknown | 605.93 | 3981 | 2326.9 | 605.93 | 1720.97 | Yes | N/A | N/A | 2024-11-19 | 2024-11-19 | 1 | 1 | 2024-11-19 | 2024-12-19 | 31 | 23 | 2024-12-19 | Unknown | Unknown | Unknown | 2024-12-20 | 2024-12-27 | 8 | 6 | 2024-12-19 | 2025-06-04 | 168 | 120 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-06-25 | 1900-01-21 | 16 | 2025-06-25 | 2025-06-25 | 1 | 1 | 169 | 121 | 62 | 46 | 231 | 167 | Steps 2,3,5,6,7 | 8 | 6 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-15 | -203 | -146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-01-26 | 2024-04-10 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -23875.18 | 691.03 | Unknown | Unknown | -30213 | 5646.79 | Unknown | 30212.98 | -23875.18 | 54088.16 | Yes | N/A | N/A | 2024-01-26 | 2024-01-28 | 3 | 1 | 2024-01-28 | 2024-02-28 | 32 | 23 | 2024-02-09 | 2024-02-13 | 5 | 3 | 2024-02-28 | 2024-03-11 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-04-26 | 1900-01-16 | 13 | 2024-04-26 | 2024-04-26 | 1 | 1 | 8 | 4 | 63 | 46 | 71 | 50 | Steps 2,3,5,6,7 | 19 | 13 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ALPINE | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-05 | -82 | -59 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | 2023-11-28 | IOU Designed & Installed | N/A | No | N/A | -27.46 | -13.74 | Unknown | Unknown | Unknown | -13.72 | Unknown | 839.77 | -27.46 | 867.23 | Yes | N/A | N/A | 2023-11-21 | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-11-21 | 105 | 75 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2023-11-28 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2024-03-15 | 1900-04-18 | 79 | 2024-03-15 | 2024-03-15 | 1 | 1 | 8 | 6 | 215 | 155 | 223 | 161 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 72.45 | 72.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-08 | -374 | -267 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-24 | 2023-09-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 832.67 | -6.32 | Unknown | Unknown | 16.07 | 822.92 | 3981 | 1207.17 | 832.67 | 374.5 | Yes | N/A | N/A | 2023-09-24 | 2023-10-11 | 18 | 13 | 2023-10-11 | 2023-10-11 | 1 | 1 | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | Unknown | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | 2024-05-30 | 2024-05-30 | 1 | 1 | 18 | 13 | 2 | 2 | 20 | 15 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | Poway | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | -337 | -241 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | 2023-03-21 | IOU Designed & Installed | N/A | No | N/A | 1130.96 | 1544.88 | Unknown | 352.4 | -1734 | 967.68 | Unknown | 1734.25 | 1130.96 | 603.29 | Yes | N/A | N/A | 2023-03-06 | 2023-03-06 | 1 | 1 | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-03-24 | 1900-01-03 | 4 | 2023-03-24 | 2023-03-24 | 1 | 1 | 1 | 1 | 5 | 5 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-13 | -529 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | 2023-08-01 | IOU Designed & Installed | N/A | No | N/A | -1043.56 | -20.29 | Unknown | Unknown | -2005 | 981.73 | Unknown | 2005.18 | -1043.56 | 3048.74 | Yes | N/A | N/A | 2023-03-02 | 2023-03-29 | 28 | 20 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | 2023-08-01 | 86 | 62 | Unknown | 2023-06-21 | Unknown | Unknown | 2023-08-01 | 2023-08-03 | 1900-01-02 | 3 | 2023-08-03 | 2023-08-03 | 1 | 1 | 114 | 82 | 4 | 4 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 77.05 | 77.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -254 | -182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | 1828.78 | -14.18 | Unknown | Unknown | 10.57 | 1832.39 | 3981 | 734.32 | 1828.78 | -1094.46 | Yes | N/A | N/A | 2023-09-11 | 2023-06-26 | Unknown | Unknown | 2023-06-26 | 2023-12-13 | 171 | 123 | 2023-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2024-05-17 | 232 | 166 | Unknown | 2024-05-16 | Unknown | Unknown | 2024-05-17 | 2024-05-28 | 1900-01-11 | 8 | 2024-05-28 | 2024-05-23 | Unknown | Unknown | 232 | 166 | 183 | 131 | 415 | 297 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | -548 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | 2023-09-06 | IOU Designed & Installed | N/A | No | N/A | 2243.09 | -12.61 | Unknown | Unknown | 8.27 | 2247.43 | Unknown | 1906.87 | 2243.09 | -336.22 | Yes | N/A | N/A | 2023-06-20 | 2023-07-19 | 30 | 22 | 2023-07-19 | 2025-03-06 | 597 | 427 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | 2023-09-06 | 50 | 36 | Unknown | 2023-09-11 | Unknown | Unknown | 2023-09-06 | 2023-09-14 | 1900-01-08 | 7 | 2023-09-14 | 2023-09-14 | 1 | 1 | 80 | 58 | 607 | 435 | 687 | 493 | Steps 2,3,5,6,7 | 5 | 3 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -306 | -219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 280472.87 | 83815.45 | Unknown | Unknown | 8791.31 | 187866.11 | 2090656.42 | 146338.18 | 280472.87 | -134134.69 | Yes | N/A | N/A | 2023-01-24 | 2023-07-10 | 168 | 120 | 2023-07-10 | 2024-03-13 | 248 | 178 | 2023-07-18 | 2024-05-08 | 34 | 26 | 2024-02-28 | 2024-04-08 | 41 | 29 | 2024-03-26 | Unknown | Unknown | Unknown | 2024-03-26 | 2024-11-07 | 227 | 163 | Unknown | 2025-02-28 | Unknown | Unknown | 2025-02-28 | 2025-02-28 | 1 | 1 | 202 | 146 | 517 | 371 | 719 | 517 | Steps 2,3,5,6,7 | 322 | 230 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | -386 | -277 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | 2023-09-05 | IOU Designed & Installed | N/A | No | N/A | 2201.23 | 490.43 | Unknown | 199.63 | 16.82 | 1494.35 | 3981 | 642.19 | 2201.23 | -1559.04 | Yes | N/A | N/A | 2023-01-24 | 2023-07-31 | 189 | 135 | 2023-07-31 | 2023-07-31 | 1 | 1 | 2023-07-31 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-09-05 | 152 | 108 | Unknown | 2023-09-07 | Unknown | Unknown | 2023-09-05 | 2023-09-13 | 1900-01-08 | 7 | 2023-09-13 | 2023-09-13 | 1 | 1 | 341 | 243 | 11 | 9 | 352 | 252 | Steps 2,3,5,6,7 | 2 | 2 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | -671 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-24 | 2025-01-08 | IOU Designed & Installed | N/A | No | N/A | 1208.16 | -23.4 | Unknown | Unknown | 2.82 | 1228.74 | 0 | 760.32 | 1208.16 | -447.84 | Yes | N/A | N/A | 2023-02-17 | 2023-02-24 | 8 | 6 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | 2025-01-08 | 685 | 489 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-29 | 1900-01-21 | 16 | 2025-01-29 | 2025-01-29 | 1 | 1 | 693 | 495 | 23 | 17 | 716 | 512 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-07 | -670 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 30.43 | Unknown | Unknown | Unknown | Unknown | 30.43 | Unknown | 1809.55 | 30.43 | 1779.12 | Yes | N/A | N/A | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | 2025-03-06 | 17 | 13 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-04-02 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-08 | 1900-01-06 | 5 | 2025-04-08 | 2025-04-08 | 1 | 1 | 29 | 21 | 25 | 19 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 617 | 617 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | -525 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | 333.38 | -6.7 | Unknown | Unknown | Unknown | 340.08 | 3981 | 2461.78 | 333.38 | 2128.4 | Yes | N/A | N/A | 2024-12-17 | 2025-02-19 | 65 | 47 | 2025-02-19 | 2025-04-30 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-07 | 12 | 8 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-12 | 1900-01-01 | 2 | 2025-06-12 | 2025-06-12 | 1 | 1 | 65 | 47 | 86 | 62 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-25 | -488 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 28.07 | Unknown | Unknown | Unknown | Unknown | 28.07 | 3981 | 918.94 | 28.07 | 890.87 | Yes | N/A | N/A | 2024-11-04 | 2024-11-04 | 1 | 1 | 2024-11-04 | 2024-11-04 | 1 | 1 | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2025-03-05 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-24 | 1900-01-19 | 14 | 2025-03-24 | 2025-03-24 | 1 | 1 | 123 | 89 | 22 | 16 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 91.05 | 91.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | -367 | -264 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | 2024-05-29 | IOU Designed & Installed | N/A | No | N/A | 13.12 | -11.64 | Unknown | Unknown | Unknown | 24.76 | 3981 | 927.67 | 13.12 | 914.55 | Yes | N/A | N/A | 2024-01-29 | 2024-04-23 | 86 | 62 | 2024-04-23 | 2024-04-26 | 4 | 4 | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2024-05-29 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-07-09 | 1900-02-10 | 30 | 2024-07-09 | 2024-07-09 | 1 | 1 | 120 | 86 | 47 | 35 | 167 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 99 | 99 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-11 | -655 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-07-19 | 2023-07-24 | IOU Designed & Installed | N/A | No | N/A | -2.81 | -5.41 | Unknown | Unknown | Unknown | 2.6 | 6481 | 663.74 | -2.81 | 666.55 | Yes | N/A | N/A | 2023-07-19 | 2023-07-19 | 1 | 1 | 2023-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-07-24 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2023-07-26 | 1900-01-02 | 3 | 2023-07-26 | 2023-07-26 | 1 | 1 | 6 | 4 | 4 | 4 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-20 | -212 | -152 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-02-08 | 2023-06-16 | IOU Designed & Installed | N/A | No | N/A | -4.52 | -13.42 | Unknown | Unknown | Unknown | 8.9 | Unknown | 680.85 | -4.52 | 685.37 | Yes | N/A | N/A | 2023-01-25 | 2023-02-08 | 15 | 11 | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | 2023-06-16 | 129 | 93 | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-06-22 | 1900-01-06 | 5 | 2023-06-22 | 2023-06-22 | 1 | 1 | 144 | 104 | 8 | 6 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -379 | -271 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 16.82 | Unknown | Unknown | Unknown | Unknown | 16.82 | Unknown | 1050.75 | 16.82 | 1033.93 | Yes | N/A | N/A | 2024-08-20 | 2024-08-20 | 1 | 1 | 2024-08-20 | 2024-08-20 | 1 | 1 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | Unknown | Unknown | 2025-02-07 | 2025-02-07 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-05 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-05-09 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | 1654.83 | 516.8 | Unknown | Unknown | Unknown | 1138.03 | Unknown | 1009.78 | 1654.83 | -645.05 | Yes | N/A | N/A | 2024-04-23 | 2024-03-08 | Unknown | Unknown | 2024-03-08 | 2024-05-09 | 63 | 45 | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-05-14 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-05-30 | 1900-01-16 | 13 | 2024-05-30 | 2024-05-30 | 1 | 1 | 6 | 4 | 81 | 59 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-17 | -512 | -366 | No | 2022-12-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-12 | 2022-12-12 | 2023-02-24 | IOU Designed & Installed | N/A | Yes | 93 | 1258.56 | 114.5 | Unknown | 44.05 | 224.37 | 875.64 | 3981 | 454.56 | 1258.56 | -804 | Yes | N/A | N/A | 2022-12-12 | 2023-03-15 | 94 | 68 | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-30 | 2023-02-24 | Unknown | Unknown | Unknown | 2023-02-22 | Unknown | Unknown | 2023-02-24 | 2025-07-18 | 1902-05-25 | 626 | 2025-07-18 | 2023-03-24 | Unknown | Unknown | 94 | 68 | 876 | 626 | 970 | 694 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12.05 | 12.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | -582 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-18 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 852.93 | 253.74 | Unknown | Unknown | Unknown | 599.19 | 3981 | 1573.97 | 852.93 | 721.04 | Yes | N/A | N/A | 2024-09-18 | 2024-08-06 | Unknown | Unknown | 2024-08-06 | 2024-09-18 | 44 | 32 | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-10-15 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-10-28 | 1900-01-13 | 10 | 2024-10-28 | 2024-10-25 | Unknown | Unknown | 28 | 20 | 58 | 42 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 1737.1 | 1737.1 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-01-10 | -457 | -328 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-08-21 | IOU Designed & Installed | N/A | No | N/A | 1053.12 | 231.47 | Unknown | Unknown | Unknown | 821.65 | 3981 | 995.15 | 1053.12 | -57.97 | Yes | N/A | N/A | 2023-06-21 | 2023-06-21 | 1 | 1 | 2023-06-21 | 2023-06-21 | 1 | 1 | 2023-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-08-21 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2023-10-11 | 1900-02-20 | 38 | 2023-10-11 | 2023-10-11 | 1 | 1 | 62 | 44 | 54 | 40 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-05 | -693 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | 2024-01-30 | IOU Designed & Installed | N/A | No | N/A | 4.78 | -5.8 | Unknown | Unknown | Unknown | 10.58 | Unknown | 297.38 | 4.78 | 292.6 | Yes | N/A | N/A | 2024-01-30 | 2024-01-26 | Unknown | Unknown | 2024-01-26 | 2024-01-30 | 5 | 3 | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-01-30 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-02-12 | 1900-01-13 | 10 | 2024-02-12 | 2024-02-12 | 1 | 1 | 1 | 1 | 20 | 14 | 21 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | 52 | 52 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-10 | 355 | 254 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-03-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | -7.03 | -20.68 | Unknown | Unknown | Unknown | 13.65 | Unknown | 611.41 | -7.03 | 618.44 | Yes | N/A | N/A | 2023-03-16 | 2023-03-20 | 5 | 3 | 2023-03-20 | 2023-03-23 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | 5 | 3 | 5 | 5 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | DANA POINT | COUNTY OF ORANGE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-02 | 497 | 356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | 2024-12-08 | IOU Designed & Installed | N/A | No | N/A | 1559.27 | 307.91 | Unknown | Unknown | Unknown | 1251.36 | Unknown | 307.58 | 1559.27 | -1251.69 | Yes | N/A | N/A | 2024-04-18 | 2024-09-26 | 162 | 116 | 2024-09-26 | 2024-11-21 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-08-13 | 103 | 73 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-08 | 2024-12-11 | 1900-01-03 | 3 | 2024-12-11 | 2024-12-11 | 1 | 1 | 162 | 116 | 165 | 118 | 327 | 234 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-12 | -487 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-02 | 2024-04-24 | IOU Designed & Installed | N/A | No | N/A | 4.72 | -4.16 | Unknown | Unknown | Unknown | 8.88 | Unknown | 1654.88 | 4.72 | 1650.16 | Yes | N/A | N/A | 2024-01-02 | 2023-10-17 | Unknown | Unknown | 2023-10-17 | 2024-01-26 | 102 | 74 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-04-24 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-13 | 1900-01-19 | 14 | 2024-05-13 | 2024-05-13 | 1 | 1 | 90 | 64 | 123 | 89 | 213 | 153 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-09 | -364 | -261 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-02 | 2024-11-25 | IOU Designed & Installed | N/A | No | N/A | 1240.32 | 118.61 | Unknown | Unknown | Unknown | 1121.71 | 0 | 1558.35 | 1240.32 | 318.03 | Yes | N/A | N/A | 2024-08-01 | 2024-04-15 | Unknown | Unknown | 2024-04-15 | 2024-08-02 | 110 | 80 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-11-25 | 116 | 82 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-04-10 | 1900-05-16 | 99 | 2025-04-10 | 2025-04-10 | 1 | 1 | 116 | 82 | 248 | 180 | 364 | 262 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-11 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | -19.86 | -16.14 | Unknown | Unknown | Unknown | -3.72 | 3981 | 742.24 | -19.86 | 762.1 | Yes | N/A | N/A | 2024-04-02 | 2024-01-23 | Unknown | Unknown | 2024-01-23 | 2024-04-02 | 71 | 51 | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-04-22 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-06-03 | 1900-02-11 | 31 | 2024-06-03 | 2024-06-03 | 1 | 1 | 21 | 15 | 115 | 83 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Fallbrook | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-25 | 61 | 44 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 447.69 | 1720.87 | Unknown | 392.04 | -2516 | 850.78 | 0 | 2515.62 | 447.69 | 2067.93 | Yes | N/A | N/A | 2023-02-09 | 2023-02-22 | 14 | 10 | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | Unknown | Unknown | 2024-03-26 | 2024-03-26 | 1 | 1 | 14 | 10 | 1 | 1 | 15 | 11 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 119 | 119 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-01 | -399 | -286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-02-07 | 2024-08-19 | IOU Designed & Installed | N/A | No | N/A | 3650.34 | 1248.7 | Unknown | Unknown | 12.45 | 2389.19 | 3981 | 2988.79 | 3650.34 | -661.55 | Yes | N/A | N/A | 2024-01-17 | 2024-02-07 | 22 | 16 | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-08-19 | 194 | 138 | Unknown | 2024-06-25 | Unknown | Unknown | 2024-08-19 | 2024-08-28 | 1900-01-09 | 8 | 2024-08-28 | 2024-08-28 | 1 | 1 | 216 | 154 | 11 | 9 | 227 | 163 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-06 | -12 | -9 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | 2024-09-12 | IOU Designed & Installed | N/A | No | N/A | -1455.86 | 1777.18 | Unknown | 317.61 | -4360 | 809.35 | Unknown | 4360.34 | -1455.86 | 5816.2 | Yes | N/A | N/A | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | 2024-09-24 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | Unknown | Unknown | Unknown | 2024-09-24 | 2024-09-24 | 1 | 1 | 2024-09-12 | 2024-09-24 | 1900-01-12 | 9 | 2024-09-24 | 2024-09-24 | 1 | 1 | 1 | 1 | 70 | 50 | 71 | 51 | Steps 2,3,5,6,7 | 12 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-20 | -232 | -167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1087.59 | 285.65 | Unknown | 149.52 | 14.59 | 637.83 | 3981 | 712.73 | 1087.59 | -374.86 | Yes | N/A | N/A | 2024-01-25 | 2024-01-11 | Unknown | Unknown | 2024-01-11 | 2024-02-06 | 27 | 19 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | Unknown | Unknown | 2024-05-02 | 2024-05-02 | 1 | 1 | 0 | 0 | 28 | 20 | 28 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | -708 | -506 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 1754.19 | 461.24 | Unknown | 44.31 | Unknown | 1248.64 | 3981 | 1526.87 | 1754.19 | -227.32 | Yes | N/A | N/A | 2024-10-30 | 2024-10-28 | Unknown | Unknown | 2024-10-28 | 2024-10-30 | 3 | 3 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2024-10-31 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-06 | 1900-01-06 | 5 | 2024-11-06 | 2024-11-08 | 3 | 3 | 2 | 2 | 13 | 11 | 15 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-24 | -708 | -507 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | Unknown | 2024-10-07 | IOU Designed & Installed | N/A | No | N/A | 28.28 | Unknown | Unknown | Unknown | Unknown | 28.28 | 3981 | 1644.8 | 28.28 | 1616.52 | Yes | N/A | N/A | 2024-09-27 | 2024-09-27 | 1 | 1 | 2024-09-27 | 2024-09-27 | 1 | 1 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-10-07 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-16 | 1900-01-09 | 8 | 2024-10-16 | 2024-10-16 | 1 | 1 | 12 | 8 | 12 | 10 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-10 | -664 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 14.73 | Unknown | Unknown | Unknown | Unknown | 14.73 | 3981 | 1853.67 | 14.73 | 1838.94 | Yes | N/A | N/A | 2025-02-25 | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-02-25 | 2 | 2 | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | Unknown | Unknown | 2025-04-17 | 2025-04-17 | 1 | 1 | 0 | 0 | 3 | 3 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-NORTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-22 | -327 | -235 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-01-19 | 2024-12-16 | IOU Designed & Installed | N/A | No | N/A | 14000.5 | 320.97 | Unknown | Unknown | 150.22 | 13529.31 | 19086 | 15129.61 | 14000.5 | 1129.11 | Yes | N/A | N/A | 2024-01-19 | 2024-05-23 | 126 | 90 | 2024-05-23 | 2024-09-19 | 120 | 86 | 2024-05-31 | 2024-07-11 | 21 | 15 | 2024-06-05 | 2024-09-11 | 45 | 33 | 2024-09-19 | 2024-11-14 | 57 | 41 | 2024-09-24 | 2024-10-29 | 36 | 26 | 2024-12-16 | 2025-02-13 | 1900-02-28 | 44 | 2025-02-13 | 2024-12-30 | Unknown | Unknown | 204 | 146 | 261 | 189 | 465 | 335 | Steps 2,3,5,6,7 | 198 | 142 | Unknown | Meeting | Not Available | N/A
| R15 | Both | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-10 | -85 | -62 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-10-25 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | 139306.35 | 11959.37 | Unknown | Unknown | 4060.2 | 123286.78 | 412667 | 45858.56 | 139306.35 | -93447.79 | Yes | N/A | N/A | 2023-07-18 | 2023-10-23 | 98 | 70 | 2023-10-23 | 2024-05-14 | 205 | 147 | 2023-10-30 | 2024-05-03 | 35 | 25 | 2023-11-30 | 2025-03-31 | 133 | 93 | 2024-08-26 | Unknown | Unknown | Unknown | 2024-08-26 | 2025-03-26 | 213 | 153 | 2024-10-11 | 2025-03-17 | 1900-06-06 | 112 | 2025-03-17 | 2025-03-17 | 1 | 1 | 133 | 95 | 710 | 506 | 843 | 601 | Steps 2,3,5,6,7 | 735 | 525 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-02 | -458 | -329 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-07 | 2024-08-16 | IOU Designed & Installed | N/A | No | N/A | 610.39 | 380.61 | Unknown | Unknown | Unknown | 229.78 | Unknown | 158.37 | 610.39 | -452.02 | Yes | N/A | N/A | 2024-03-07 | 2024-01-22 | Unknown | Unknown | 2024-01-22 | 2024-03-07 | 46 | 34 | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-08-16 | 163 | 117 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-10-01 | 1900-02-15 | 33 | 2024-10-01 | 2024-10-01 | 1 | 1 | 163 | 117 | 94 | 68 | 257 | 185 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | -223 | -160 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-13 | 2024-04-07 | IOU Designed & Installed | N/A | No | N/A | -1049.75 | 510.06 | Unknown | 114.85 | -2034 | 359.34 | Unknown | 2034.2 | -1049.75 | 3083.95 | Yes | N/A | N/A | 2024-03-08 | 2024-03-08 | 1 | 1 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-07 | 2024-07-15 | 1900-04-09 | 71 | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 101 | 72 | 102 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-25 | -322 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2023-07-25 | 2023-08-18 | IOU Designed & Installed | N/A | No | N/A | 4911.9 | 596.59 | Unknown | 2220.65 | 20.29 | 2074.37 | 3981 | 676.57 | 4911.9 | -4235.33 | Yes | N/A | N/A | 2023-07-25 | 2023-07-25 | 1 | 1 | 2023-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2023-08-18 | 25 | 19 | Unknown | 2023-08-29 | Unknown | Unknown | 2023-08-18 | 2023-09-07 | 1900-01-20 | 15 | 2023-09-07 | 2023-09-07 | 1 | 1 | 26 | 20 | 22 | 16 | 48 | 36 | Steps 2,3,5,6,7 | 11 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-28 | 29 | 22 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-10 | 2024-03-07 | IOU Designed & Installed | N/A | No | N/A | -772.07 | -10.59 | Unknown | Unknown | -784 | 22.52 | Unknown | 783.72 | -772.07 | 1555.79 | Yes | N/A | N/A | 2024-01-10 | 2024-01-10 | 1 | 1 | 2024-01-10 | 2024-01-23 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-03-28 | 1900-01-21 | 16 | 2024-03-28 | 2024-03-28 | 1 | 1 | 1 | 1 | 37 | 27 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | -533 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-20 | 2024-01-19 | IOU Designed & Installed | N/A | No | N/A | -6.56 | -10.09 | Unknown | Unknown | Unknown | 3.53 | 3961 | 694.33 | -6.56 | 700.89 | Yes | N/A | N/A | 2023-10-20 | 2023-10-17 | Unknown | Unknown | 2023-10-17 | 2023-10-20 | 4 | 4 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2024-01-19 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-01-25 | 1900-01-06 | 5 | 2024-01-25 | 2024-01-25 | 1 | 1 | 92 | 66 | 12 | 10 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | -520 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-08-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 581.27 | -14.16 | Unknown | Unknown | 0.62 | 594.81 | 3981 | 791.94 | 581.27 | 210.67 | Yes | N/A | N/A | 2023-08-10 | 2023-05-12 | Unknown | Unknown | 2023-05-12 | 2023-08-18 | 99 | 71 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | Unknown | Unknown | 2023-11-28 | 2023-11-28 | 1 | 1 | 0 | 0 | 100 | 72 | 100 | 72 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-31 | -686 | -491 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | 2024-10-07 | IOU Designed & Installed | N/A | No | N/A | 55.95 | Unknown | Unknown | Unknown | Unknown | 55.95 | Unknown | 3486.39 | 55.95 | 3430.44 | Yes | N/A | N/A | 2024-10-01 | 2024-10-01 | 1 | 1 | 2024-10-01 | 2024-10-01 | 1 | 1 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-07 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-14 | 1900-01-07 | 6 | 2024-10-14 | 2024-10-14 | 1 | 1 | 8 | 6 | 10 | 8 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-16 | 213 | 153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-03 | 2024-12-19 | IOU Designed & Installed | N/A | No | N/A | 1096.16 | Unknown | Unknown | Unknown | 44.17 | 1051.99 | 2781 | 632.46 | 1096.16 | -463.7 | Yes | N/A | N/A | 2023-05-03 | 2023-05-22 | 20 | 14 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | 2024-12-19 | 578 | 414 | Unknown | 2024-12-18 | Unknown | Unknown | 2024-12-19 | 2025-01-15 | 1900-01-27 | 20 | 2025-01-15 | 2025-01-15 | 1 | 1 | 598 | 428 | 29 | 21 | 627 | 449 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 18 | 18 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-10 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 21.83 | Unknown | Unknown | Unknown | Unknown | 21.83 | 3981 | 2485.18 | 21.83 | 2463.35 | Yes | N/A | N/A | 2024-11-22 | 2024-11-25 | 4 | 2 | 2024-11-25 | 2025-01-13 | 50 | 36 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-02-18 | Unknown | Unknown | 4 | 2 | 50 | 36 | 54 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 180 | 180 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | -304 | -219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-23 | 2024-09-19 | IOU Designed & Installed | N/A | No | N/A | 49.85 | Unknown | Unknown | Unknown | Unknown | 49.85 | Unknown | 1310.11 | 49.85 | 1260.26 | Yes | N/A | N/A | 2024-08-16 | 2024-07-31 | Unknown | Unknown | 2024-07-31 | 2024-08-23 | 24 | 18 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-19 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-09-23 | 1900-01-04 | 3 | 2024-09-23 | 2024-09-23 | 1 | 1 | 16 | 12 | 30 | 22 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | -499 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1173.25 | Unknown | Unknown | Unknown | -863 | 2036.25 | Unknown | 862.55 | 1173.25 | -310.7 | Yes | N/A | N/A | 2025-01-07 | 2025-01-07 | 1 | 1 | 2025-01-07 | 2025-01-07 | 1 | 1 | 2025-01-07 | 2025-01-10 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-02 | 2025-04-02 | 1 | 1 | 5 | 5 | 2 | 2 | 7 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | -228 | -164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-02-07 | 2025-05-09 | IOU Designed & Installed | N/A | No | N/A | 1871.22 | Unknown | Unknown | Unknown | 5.93 | 1865.29 | 3981 | 1456.53 | 1871.22 | -414.69 | Yes | N/A | N/A | 2025-01-30 | 2025-04-08 | 69 | 49 | 2025-04-08 | 2025-04-09 | 2 | 2 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-05-09 | 31 | 23 | Unknown | 2025-05-07 | Unknown | Unknown | 2025-05-09 | 2025-05-27 | 1900-01-18 | 13 | 2025-05-27 | 2025-05-27 | 1 | 1 | 100 | 72 | 22 | 16 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | -544 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | 2024-11-20 | IOU Designed & Installed | N/A | No | N/A | 1944.52 | Unknown | Unknown | Unknown | Unknown | 1944.52 | 3981 | 1207.98 | 1944.52 | -736.54 | Yes | N/A | N/A | 2024-08-05 | 2024-06-07 | Unknown | Unknown | 2024-06-07 | 2024-08-05 | 60 | 42 | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-11-20 | 108 | 78 | Unknown | 2024-11-13 | Unknown | Unknown | 2024-11-20 | 2024-12-02 | 1900-01-12 | 9 | 2024-12-02 | 2024-12-02 | 1 | 1 | 108 | 78 | 74 | 52 | 182 | 130 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 1973.25 | 1973.25 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-06-28 | 411 | 294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-10-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 13 | Unknown | Unknown | Unknown | Unknown | 13 | 0 | 364.73 | 13 | 351.73 | Yes | N/A | N/A | 2023-06-30 | 2023-08-01 | 33 | 23 | 2023-08-01 | 2023-10-12 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | Unknown | Unknown | 2024-08-12 | 2024-08-12 | 1 | 1 | 33 | 23 | 74 | 54 | 107 | 77 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-04 | -664 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-18 | 2025-05-07 | IOU Designed & Installed | N/A | No | N/A | 2.92 | Unknown | Unknown | Unknown | Unknown | 2.92 | Unknown | 196.59 | 2.92 | 193.67 | Yes | N/A | N/A | 2025-03-14 | 2025-04-09 | 27 | 19 | 2025-04-09 | 2025-04-15 | 7 | 5 | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-05-07 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-05-09 | 1900-01-02 | 3 | 2025-05-09 | 2025-05-09 | 1 | 1 | 50 | 36 | 11 | 9 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-12-07 | -1370 | -979 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | 2024-01-08 | IOU Designed & Installed | N/A | No | N/A | 2.29 | -2.9 | Unknown | Unknown | Unknown | 5.19 | Unknown | 1023.03 | 2.29 | 1020.74 | Yes | N/A | N/A | 2023-12-11 | 2023-12-07 | Unknown | Unknown | 2023-12-07 | 2023-12-11 | 5 | 3 | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2024-01-08 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-03-07 | 1900-02-28 | 44 | 2024-03-07 | 2024-03-07 | 1 | 1 | 29 | 21 | 66 | 48 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 6.7 | 6.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-23 | -610 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-10 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 2289.37 | 149.26 | Unknown | Unknown | Unknown | 2140.11 | 3941 | 1039 | 2289.37 | -1250.37 | Yes | N/A | N/A | 2024-04-10 | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-04-10 | 64 | 46 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-04-15 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-05-23 | 1900-02-07 | 29 | 2024-05-23 | 2024-05-23 | 1 | 1 | 6 | 4 | 104 | 76 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | -550 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-09-13 | IOU Designed & Installed | N/A | No | N/A | 1545.59 | -30.56 | Unknown | Unknown | Unknown | 1576.15 | 3981 | 1589.99 | 1545.59 | 44.4 | Yes | N/A | N/A | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-13 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-10-07 | 1900-01-24 | 17 | 2024-10-07 | 2024-10-07 | 1 | 1 | 19 | 15 | 27 | 19 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | -678 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-31 | 2024-08-05 | IOU Designed & Installed | N/A | No | N/A | 4.44 | Unknown | Unknown | Unknown | Unknown | 4.44 | 3981 | 985.1 | 4.44 | 980.66 | Yes | N/A | N/A | 2024-07-18 | 2024-07-16 | Unknown | Unknown | 2024-07-16 | 2024-07-31 | 16 | 12 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-08-05 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-08-30 | 1900-01-25 | 20 | 2024-08-30 | 2024-08-30 | 1 | 1 | 6 | 4 | 43 | 33 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | POWAY | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | -448 | -321 | No | 2023-09-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | 2024-04-24 | IOU Designed & Installed | N/A | Yes | 184 | 1524.55 | -25.61 | Unknown | Unknown | 30.55 | 1519.61 | 3885 | 479.59 | 1524.55 | -1044.96 | Yes | N/A | N/A | 2023-09-18 | 2024-03-20 | 185 | 133 | 2024-03-20 | 2024-03-20 | 1 | 1 | 2024-03-20 | Unknown | Unknown | Unknown | 2024-02-08 | 2024-02-13 | 6 | 4 | 2024-03-12 | 2024-04-24 | 44 | 32 | Unknown | 2024-04-22 | Unknown | Unknown | 2024-04-24 | 2024-05-03 | 1900-01-09 | 8 | 2024-05-03 | 2024-05-02 | Unknown | Unknown | 229 | 165 | 17 | 13 | 246 | 178 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-27 | -663 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-09 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | 2170.08 | 505.96 | Unknown | Unknown | Unknown | 1664.12 | 3981 | 1038.42 | 2170.08 | -1131.66 | Yes | N/A | N/A | 2025-04-02 | 2025-03-17 | Unknown | Unknown | 2025-03-17 | 2025-04-09 | 24 | 18 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-24 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-05 | 1900-01-11 | 8 | 2025-05-05 | 2025-05-05 | 1 | 1 | 16 | 12 | 37 | 27 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-03 | -625 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 32.88 | Unknown | Unknown | Unknown | Unknown | 32.88 | 3941 | 1395.84 | 32.88 | 1362.96 | Yes | N/A | N/A | 2024-08-20 | 2024-07-26 | Unknown | Unknown | 2024-07-26 | 2024-08-20 | 26 | 18 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-09-09 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2024-09-12 | 1900-01-03 | 4 | 2024-09-12 | 2024-09-16 | 5 | 3 | 21 | 15 | 35 | 25 | 56 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 311.05 | 311.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | -430 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-06 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 1764.69 | 502.72 | Unknown | 15.54 | Unknown | 1246.43 | 3981 | 848.3 | 1764.69 | -916.39 | Yes | N/A | N/A | 2024-03-06 | 2024-03-11 | 6 | 4 | 2024-03-11 | 2024-03-19 | 9 | 7 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-10-01 | 197 | 141 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-04 | 1900-01-03 | 4 | 2024-10-04 | 2024-10-03 | Unknown | Unknown | 203 | 145 | 13 | 11 | 216 | 156 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 404 | 289 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | 2024-04-24 | IOU Designed & Installed | N/A | No | N/A | 5677.59 | Unknown | Unknown | Unknown | -612 | 6289.59 | 0 | 611.58 | 5677.59 | -5066.01 | Yes | N/A | N/A | 2023-03-22 | 2023-04-07 | 17 | 13 | 2023-04-07 | 2023-05-09 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-09 | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | Unknown | Unknown | 2024-04-24 | 2024-05-09 | 1900-01-15 | 12 | 2024-05-09 | 2024-05-09 | 1 | 1 | 17 | 13 | 50 | 36 | 67 | 49 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | 269 | 193 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-10-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 113.07 | -47.88 | Unknown | Unknown | -1261 | 1421.95 | 7962 | 1619.13 | 113.07 | 1506.06 | Yes | N/A | N/A | 2023-08-30 | 2023-10-27 | 59 | 43 | 2023-10-27 | 2024-05-02 | 189 | 135 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-06-11 | 41 | 29 | Unknown | 2024-06-12 | Unknown | Unknown | Unknown | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-06-26 | Unknown | Unknown | 100 | 72 | 189 | 135 | 289 | 207 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-22 | 179 | 128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-08 | 2023-11-29 | IOU Designed & Installed | N/A | No | N/A | 0.74 | -9.57 | Unknown | Unknown | Unknown | 10.31 | 3981 | 848.6 | 0.74 | 847.86 | Yes | N/A | N/A | 2023-09-08 | 2023-07-26 | Unknown | Unknown | 2023-07-26 | 2023-09-08 | 45 | 33 | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | 2023-11-29 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2024-02-13 | 1900-03-17 | 55 | 2024-02-13 | 2023-12-18 | Unknown | Unknown | 83 | 59 | 122 | 88 | 205 | 147 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-01 | 357 | 256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-31 | 2024-07-20 | IOU Designed & Installed | N/A | No | N/A | 10410.48 | 3579.02 | Unknown | 12.43 | 462.34 | 6356.69 | 40815 | 24872.91 | 10410.48 | 14462.43 | Yes | N/A | N/A | 2023-05-30 | 2023-05-08 | Unknown | Unknown | 2023-05-08 | 2023-10-12 | 158 | 114 | 2023-08-14 | Unknown | Unknown | Unknown | 2023-09-29 | 2023-10-17 | 12 | 6 | 2023-10-12 | 2024-06-28 | 261 | 187 | Unknown | 2024-07-10 | Unknown | Unknown | 2024-07-20 | 2025-02-21 | 1900-08-04 | 155 | 2025-02-21 | 2024-07-23 | Unknown | Unknown | 261 | 187 | 387 | 275 | 648 | 462 | Steps 2,3,5,6,7 | 64 | 46 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 54 | 54 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-22 | -429 | -308 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-19 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 11336.61 | Unknown | Unknown | Unknown | Unknown | 11336.61 | 3981 | 1723.82 | 11336.61 | -9612.79 | Yes | N/A | N/A | 2024-07-19 | 2024-07-12 | Unknown | Unknown | 2024-07-12 | 2024-07-19 | 8 | 6 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-07-29 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-19 | 1900-01-21 | 16 | 2024-08-19 | 2024-08-19 | 1 | 1 | 11 | 7 | 31 | 23 | 42 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | N/A | Irvine | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-20 | -205 | -148 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-02-27 | 2024-03-15 | IOU Designed & Installed | N/A | No | N/A | 41331.32 | 6212.4 | Unknown | Unknown | 17.62 | 35101.3 | 25594 | 9570.74 | 41331.32 | -31760.58 | Yes | N/A | N/A | 2023-01-23 | 2023-02-27 | 36 | 26 | 2023-02-27 | 2023-12-08 | 285 | 205 | 2023-07-06 | 2024-04-23 | 24 | 18 | 2023-06-05 | 2024-03-18 | -19 | -17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-02-28 | 1 | 1 | 60 | 44 | 267 | 189 | 327 | 233 | Steps 2,3,5,6,7 | 478 | 342 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | Dana Point | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-29 | 307 | 220 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-10-30 | 2024-06-20 | IOU Designed & Installed | N/A | No | N/A | 32403.91 | 3049.14 | Unknown | Unknown | 43.38 | 29311.39 | 116978 | 10466.67 | 32403.91 | -21937.24 | Yes | N/A | N/A | 2023-07-11 | 2023-07-11 | 1 | 1 | 2023-07-11 | Unknown | Unknown | Unknown | 2023-08-22 | 2023-08-23 | 2 | 2 | 2023-11-10 | 2023-11-17 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-08-01 | 1900-02-11 | 31 | 2024-08-01 | 2024-08-01 | 1 | 1 | 3 | 3 | 52 | 38 | 55 | 41 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-11 | -438 | -314 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -278.23 | Unknown | Unknown | Unknown | -906.81 | 628.58 | Unknown | 1196.22 | -278.23 | 1474.45 | Yes | N/A | N/A | 2024-10-21 | 2024-10-16 | Unknown | Unknown | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | 2025-04-29 | 2025-04-29 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-14 | -706 | -505 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-02-28 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | 635.57 | -11.7 | Unknown | Unknown | Unknown | 647.27 | 3981 | 1700.87 | 635.57 | 1065.3 | Yes | N/A | N/A | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-03-03 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-10 | 1900-01-07 | 6 | 2025-03-10 | 2025-03-10 | 1 | 1 | 5 | 3 | 10 | 8 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-20 | 24 | 19 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2024-02-01 | IOU Designed & Installed | N/A | No | N/A | -5.53 | -5.48 | Unknown | Unknown | Unknown | -0.05 | Unknown | 158.79 | -5.53 | 164.32 | Yes | N/A | N/A | 2023-09-14 | 2024-01-09 | 118 | 84 | 2024-01-09 | 2024-01-09 | 1 | 1 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-02-01 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-03-15 | 1900-02-12 | 32 | 2024-03-15 | 2024-03-15 | 1 | 1 | 142 | 102 | 46 | 34 | 188 | 136 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-22 | -387 | -278 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1614.41 | -28.59 | Unknown | Unknown | 30 | 1613 | 3981 | 1093.04 | 1614.41 | -521.37 | Yes | N/A | N/A | 2024-05-21 | 2024-05-30 | 10 | 8 | 2024-05-30 | 2024-06-06 | 8 | 6 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | 2025-03-31 | 2025-03-31 | 1 | 1 | 10 | 8 | 9 | 7 | 19 | 15 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-24 | -654 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-30 | 2024-06-26 | IOU Designed & Installed | N/A | No | N/A | 76.05 | -12.11 | Unknown | Unknown | Unknown | 88.16 | Unknown | 1578.07 | 76.05 | 1502.02 | Yes | N/A | N/A | 2024-05-21 | 2024-04-29 | Unknown | Unknown | 2024-04-29 | 2024-05-30 | 32 | 24 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-26 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-07-09 | 1900-01-13 | 10 | 2024-07-09 | 2024-07-09 | 1 | 1 | 28 | 20 | 47 | 35 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | -206 | -148 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | 30811.68 | Unknown | Unknown | Unknown | Unknown | 30811.68 | 3901360 | 45109.39 | 30811.68 | 14297.71 | Yes | N/A | N/A | 2023-12-12 | 2024-04-08 | 119 | 85 | 2024-04-08 | 2024-04-22 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2958465 | Unknown | Unknown | Unknown | 2024-07-10 | Unknown | Unknown | 2024-07-16 | 2024-08-01 | 1900-01-16 | 13 | 2024-08-01 | 2024-07-21 | Unknown | Unknown | 119 | 85 | 32 | 24 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 88.05 | 88.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | -667 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-09 | 2025-05-21 | IOU Designed & Installed | N/A | No | N/A | 77.72 | Unknown | Unknown | Unknown | Unknown | 77.72 | 3981 | 1578.52 | 77.72 | 1500.8 | Yes | N/A | N/A | 2025-04-09 | 2025-04-09 | 1 | 1 | 2025-04-09 | 2025-04-09 | 1 | 1 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-05-21 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-06-03 | 1900-01-13 | 10 | 2025-06-03 | 2025-06-03 | 1 | 1 | 44 | 32 | 16 | 12 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-08 | -147 | -106 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-30 | 2022-11-30 | 2024-01-17 | IOU Designed & Installed | N/A | No | N/A | 492.03 | -11.97 | Unknown | Unknown | 13.64 | 490.36 | 3981 | 768.86 | 492.03 | 276.83 | Yes | N/A | N/A | 2022-11-30 | 2023-10-10 | 315 | 225 | 2023-10-10 | 2023-10-24 | 15 | 11 | 2023-10-24 | Unknown | Unknown | Unknown | 2023-10-24 | 2023-10-31 | 8 | 6 | 2023-10-24 | 2024-01-17 | 86 | 62 | Unknown | 2023-12-19 | Unknown | Unknown | 2024-01-17 | 2024-03-14 | 1900-02-26 | 42 | 2024-03-14 | 2024-03-14 | 1 | 1 | 401 | 287 | 82 | 60 | 483 | 347 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-13 | -185 | -132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-05 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 15.3 | Unknown | Unknown | Unknown | Unknown | 15.3 | 3981 | 192.95 | 15.3 | 177.65 | Yes | N/A | N/A | 2024-01-05 | 2024-08-07 | 216 | 154 | 2024-08-07 | 2024-08-07 | 1 | 1 | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2025-04-02 | 239 | 171 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-11 | 1900-01-09 | 8 | 2025-04-11 | 2025-04-11 | 1 | 1 | 455 | 325 | 12 | 10 | 467 | 335 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-24 | 52 | 37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-07-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 2852.6 | Unknown | Unknown | Yes | N/A | N/A | 2023-06-08 | 2023-07-18 | 41 | 29 | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 41 | 29 | 1 | 1 | 42 | 30 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-29 | -457 | -326 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | 2024-03-21 | IOU Designed & Installed | N/A | No | N/A | 1175.05 | 378.69 | Unknown | 36.6 | Unknown | 759.76 | 3981 | 932.85 | 1175.05 | -242.2 | Yes | N/A | N/A | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2024-03-21 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-03-29 | 1900-01-08 | 7 | 2024-03-29 | 2024-03-29 | 1 | 1 | 128 | 92 | 11 | 9 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-12-31 | 1485 | 1062 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-10-12 | 2024-01-20 | IOU Designed & Installed | N/A | No | N/A | 26027.45 | 9163.8 | Unknown | 972.3 | 96.18 | 15795.17 | Unknown | 5191.34 | 26027.45 | -20836.11 | Yes | N/A | N/A | 2023-08-09 | 2023-10-13 | 66 | 48 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | Unknown | Unknown | 2024-01-20 | 2024-01-24 | 1900-01-04 | 3 | 2024-01-24 | 2024-01-24 | 1 | 1 | 66 | 48 | 6 | 4 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | Oceanside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | 195 | 140 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-04-22 | 2025-06-13 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | Not available | Unknown | Unknown | Yes | N/A | N/A | 2024-04-22 | 2024-03-26 | Unknown | Unknown | 2024-03-26 | 2024-05-30 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2025-09-04 | 463 | 331 | Unknown | 2025-09-03 | Unknown | Unknown | 2025-06-13 | 2025-06-15 | 1900-01-02 | 1 | 2025-06-15 | 2025-06-14 | Unknown | Unknown | 463 | 331 | 69 | 49 | 532 | 380 | Steps 2,3,5,6,7 | 82 | 58 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-12 | -660 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-30 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 25.24 | Unknown | Unknown | Unknown | Unknown | 25.24 | 3981 | 1701.92 | 25.24 | 1676.68 | Yes | N/A | N/A | 2024-10-29 | 2024-09-24 | Unknown | Unknown | 2024-09-24 | 2024-10-30 | 37 | 27 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2024-11-15 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-11-21 | 1900-01-06 | 5 | 2024-11-21 | 2024-11-21 | 1 | 1 | 17 | 13 | 45 | 33 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-22 | 111 | 80 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | 2024-05-20 | IOU Designed & Installed | N/A | No | N/A | -2080.1 | -18.59 | Unknown | Unknown | -2101 | 39.49 | Unknown | 2201.73 | -2080.1 | 4281.83 | Yes | N/A | N/A | 2023-11-16 | 2023-10-30 | Unknown | Unknown | 2023-10-30 | 2024-02-01 | 95 | 69 | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-05-20 | 1 | 1 | 2024-02-01 | 2024-06-24 | 145 | 103 | Unknown | 2024-05-20 | Unknown | Unknown | 2024-05-20 | 2024-07-11 | 1900-02-21 | 39 | 2024-07-11 | 2024-07-11 | 1 | 1 | 145 | 103 | 150 | 110 | 295 | 213 | Steps 2,3,5,6,7 | 109 | 77 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 105.05 | 105.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-28 | -237 | -170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2650.7 | 120.84 | Unknown | Unknown | 4.24 | 2525.62 | 3981 | 2377.83 | 2650.7 | -272.87 | Yes | N/A | N/A | 2024-07-02 | 2024-06-28 | Unknown | Unknown | 2024-06-28 | 2024-07-25 | 28 | 20 | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | 2024-10-03 | 2024-10-03 | 1 | 1 | 0 | 0 | 29 | 21 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | 183 | 132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 681.59 | -0.31 | Unknown | Unknown | 9.24 | 672.66 | 7962 | 829.51 | 681.59 | 147.92 | Yes | N/A | N/A | 2024-03-15 | 2024-03-15 | 1 | 1 | 2024-03-15 | 2024-06-18 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-06-07 | 1 | 1 | 2024-06-18 | 2024-06-11 | Unknown | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | Unknown | 2024-08-02 | Unknown | Unknown | 2024-08-02 | 2024-08-01 | Unknown | Unknown | 1 | 1 | 97 | 69 | 98 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-22 | -395 | -284 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-03 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 1393.33 | -28 | Unknown | Unknown | Unknown | 1421.33 | 3981 | 1324.88 | 1393.33 | -68.45 | Yes | N/A | N/A | 2024-06-03 | 2024-06-03 | 1 | 1 | 2024-06-03 | 2024-06-03 | 1 | 1 | 2024-06-03 | Unknown | Unknown | Unknown | 2024-06-04 | 2025-01-16 | 66 | 46 | 2024-06-03 | 2025-04-01 | 303 | 217 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-22 | 1900-01-21 | 16 | 2025-04-22 | 2025-04-22 | 1 | 1 | 304 | 218 | 90 | 64 | 394 | 282 | Steps 2,3,5,6,7 | 227 | 163 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-04 | -676 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | Unknown | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 26.84 | Unknown | Unknown | Unknown | Unknown | 26.84 | 3981 | 1524.05 | 26.84 | 1497.21 | Yes | N/A | N/A | 2024-08-07 | 2024-08-07 | 1 | 1 | 2024-08-07 | 2024-08-07 | 1 | 1 | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-09-09 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2024-09-27 | 1900-01-18 | 15 | 2024-09-27 | 2024-09-27 | 1 | 1 | 35 | 25 | 21 | 17 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | RAMONA | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -216 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-15 | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 2025.06 | 483.36 | Unknown | 329.94 | Unknown | 1211.76 | 3981 | 964.2 | 2025.06 | -1060.86 | Yes | N/A | N/A | 2024-03-15 | 2023-04-10 | Unknown | Unknown | 2023-04-10 | 2024-03-25 | 351 | 251 | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-08-14 | 143 | 103 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-08-28 | 1900-01-14 | 11 | 2024-08-28 | 2024-08-28 | 1 | 1 | 143 | 103 | 367 | 263 | 510 | 366 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | Both | IOU Design | Residential | Underserved Community | Imperial Beach | IMPERIAL BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-05 | 306 | 219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-11-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1119.7 | 162.24 | Unknown | Unknown | 6.63 | 950.83 | 15924 | 3486.73 | 1119.7 | 2367.03 | Yes | N/A | N/A | 2023-10-04 | 2023-10-04 | 1 | 1 | 2023-10-04 | 2024-04-24 | 204 | 146 | 2024-02-01 | 2024-05-06 | 13 | 7 | 2024-02-02 | 2024-04-11 | 63 | 43 | 2024-04-24 | Unknown | Unknown | Unknown | 2024-04-24 | 2024-04-24 | 1 | 1 | Unknown | 2024-05-06 | Unknown | Unknown | 2024-05-06 | 2024-05-06 | 1 | 1 | 14 | 8 | 269 | 191 | 283 | 199 | Steps 2,3,5,6,7 | 177 | 125 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | 46.4 | 46.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-02 | 275 | 198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | 2023-05-26 | 2024-09-05 | IOU Designed & Installed | N/A | No | N/A | 9671.75 | 272.1 | Unknown | Unknown | -1086 | 10485.65 | 3981 | 1537.51 | 9671.75 | -8134.24 | Yes | N/A | N/A | 2023-05-26 | 2023-05-26 | 1 | 1 | 2023-05-26 | 2024-07-25 | 427 | 305 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-08-26 | 33 | 23 | Unknown | 2024-08-13 | Unknown | Unknown | 2024-09-05 | 2024-10-16 | 1900-02-10 | 30 | 2024-10-16 | 2024-10-03 | Unknown | Unknown | 34 | 24 | 469 | 335 | 503 | 359 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | -338 | -243 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 450.35 | -15.79 | Unknown | Unknown | -732 | 1198.14 | Unknown | 732.21 | 450.35 | 281.86 | Yes | N/A | N/A | 2023-04-21 | 2023-10-02 | 165 | 117 | 2023-10-02 | 2023-10-27 | 26 | 20 | 2023-10-27 | 2023-11-22 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | Unknown | 2024-04-23 | Unknown | Unknown | 2024-04-23 | 2024-04-23 | 1 | 1 | 192 | 136 | 27 | 21 | 219 | 157 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | -571 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | 2025-04-04 | IOU Designed & Installed | N/A | No | N/A | 214.37 | Unknown | Unknown | Unknown | -1125.66 | 1340.03 | Unknown | 1127.49 | 214.37 | 913.12 | Yes | N/A | N/A | 2025-01-07 | 2025-01-16 | 10 | 8 | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | 2025-03-19 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-04-04 | 15 | 11 | Unknown | 2025-04-03 | Unknown | Unknown | 2025-04-04 | 2025-04-28 | 1900-01-24 | 17 | 2025-04-28 | 2025-04-28 | 1 | 1 | 88 | 64 | 27 | 19 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 168.1 | 168.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-07 | -363 | -260 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-01 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | -8.3 | -7.18 | Unknown | Unknown | Unknown | -1.12 | Unknown | 534.53 | -8.3 | 542.83 | Yes | N/A | N/A | 2024-02-01 | 2024-02-01 | 1 | 1 | 2024-02-01 | 2024-02-01 | 1 | 1 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-06-10 | 131 | 93 | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-07-09 | 1900-01-29 | 22 | 2024-07-09 | 2024-07-09 | 1 | 1 | 132 | 94 | 32 | 24 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-12 | -655 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | 2025-02-07 | 2025-02-12 | IOU Designed & Installed | N/A | No | N/A | 2613.15 | 659.82 | Unknown | 104.66 | Unknown | 1848.67 | 3981 | 1657.35 | 2613.15 | -955.8 | Yes | N/A | N/A | 2025-01-27 | 2024-12-18 | Unknown | Unknown | 2024-12-18 | 2025-02-07 | 52 | 38 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-02-12 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-02-25 | 1900-01-13 | 10 | 2025-02-25 | 2025-02-25 | 1 | 1 | 6 | 4 | 67 | 49 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-03 | -277 | -200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1385.09 | -13.61 | Unknown | Unknown | Unknown | 1398.7 | 3981 | 897.18 | 1385.09 | -487.91 | Yes | N/A | N/A | 2024-02-20 | 2024-02-20 | 1 | 1 | 2024-02-20 | 2024-02-20 | 1 | 1 | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | Unknown | Unknown | 2024-04-01 | 2024-04-01 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-04 | -264 | -189 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-10 | 2024-02-09 | IOU Designed & Installed | N/A | No | N/A | -4.27 | -5.83 | Unknown | Unknown | Unknown | 1.56 | Unknown | 163.83 | -4.27 | 168.1 | Yes | N/A | N/A | 2024-01-10 | 2023-12-19 | Unknown | Unknown | 2023-12-19 | 2024-02-02 | 46 | 34 | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-02-09 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-03-15 | 1900-02-04 | 26 | 2024-03-15 | 2024-03-15 | 1 | 1 | 8 | 6 | 83 | 61 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-31 | 466 | 335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 25597.13 | 5248.41 | Unknown | 89.47 | -5556.72 | 25815.97 | 3981 | 9484.68 | 25597.13 | -16112.45 | Yes | N/A | N/A | 2023-08-02 | 2023-08-01 | Unknown | Unknown | 2023-08-01 | 2023-10-20 | 81 | 59 | 2023-08-03 | 2023-10-19 | 73 | 53 | 2023-10-20 | 2023-11-06 | 18 | 12 | 2023-10-20 | 2024-11-04 | 382 | 272 | 2023-11-08 | 2024-09-19 | 317 | 227 | Unknown | 2024-12-04 | Unknown | Unknown | 2024-12-04 | 2024-11-08 | Unknown | Unknown | 455 | 325 | 416 | 298 | 871 | 623 | Steps 2,3,5,6,7 | 457 | 325 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 146 | 146 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-31 | -107 | -78 | No | 2021-12-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-09 | 2021-12-09 | Unknown | IOU Designed & Installed | N/A | Yes | 503 | -780.07 | -12.03 | Unknown | Unknown | -776 | 7.96 | 3885 | 1522.03 | -780.07 | 2302.1 | Yes | N/A | N/A | 2021-12-09 | 2023-04-26 | 504 | 360 | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-05-25 | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-05-16 | Unknown | Unknown | 504 | 360 | 0 | 0 | 504 | 360 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | 94.05 | 94.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-31 | 30 | 22 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-12 | 2024-03-20 | IOU Designed & Installed | N/A | No | N/A | 1016.43 | -22.44 | Unknown | Unknown | Unknown | 1038.87 | 3981 | 855.07 | 1016.43 | -161.36 | Yes | N/A | N/A | 2023-04-11 | 2023-04-12 | 2 | 2 | 2023-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-12 | 2024-03-20 | 344 | 246 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-04-15 | 1900-01-26 | 19 | 2024-04-15 | 2024-04-30 | 16 | 12 | 346 | 248 | 43 | 31 | 389 | 279 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 94.05 | 94.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-11 | -161 | -116 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2024-09-26 | 2025-03-14 | IOU Designed & Installed | N/A | No | N/A | -4.34 | -18.02 | Unknown | Unknown | Unknown | 13.68 | Unknown | 1471.06 | -4.34 | 1475.4 | Yes | N/A | N/A | 2023-12-27 | 2024-09-26 | 275 | 197 | 2024-09-26 | 2024-09-26 | 1 | 1 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2025-03-14 | 170 | 122 | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-04-03 | 1900-01-20 | 15 | 2025-04-03 | 2025-04-03 | 1 | 1 | 445 | 319 | 23 | 17 | 468 | 336 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-03 | -166 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-17 | 2023-02-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.96 | -5.65 | Unknown | Unknown | Unknown | -1.31 | 3981 | 633.51 | -6.96 | 640.47 | Yes | N/A | N/A | 2023-01-17 | 2023-02-01 | 16 | 12 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | Unknown | Unknown | 2024-05-21 | 2024-05-21 | 1 | 1 | 16 | 12 | 1 | 1 | 17 | 13 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | -229 | -164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 5335.19 | 606.24 | Unknown | Unknown | 158.21 | 4570.74 | 3981 | 481.5 | 5335.19 | -4853.69 | Yes | N/A | N/A | 2024-02-08 | 2023-10-11 | Unknown | Unknown | 2023-10-11 | 2024-03-01 | 143 | 103 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-07-22 | 144 | 102 | Unknown | 2024-08-02 | Unknown | Unknown | 2024-07-22 | 2024-09-13 | 1900-02-22 | 40 | 2024-09-13 | 2024-09-13 | 1 | 1 | 144 | 102 | 198 | 144 | 342 | 246 | Steps 2,3,5,6,7 | 11 | 9 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-14 | -582 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-23 | 2025-03-28 | IOU Designed & Installed | N/A | No | N/A | 676.14 | -12.92 | Unknown | Unknown | Unknown | 689.06 | 3981 | 1105.45 | 676.14 | 429.31 | Yes | N/A | N/A | 2024-12-10 | 2024-12-24 | 15 | 11 | 2024-12-24 | 2025-01-02 | 10 | 8 | 2025-01-02 | Unknown | Unknown | Unknown | 2025-01-03 | 2025-02-20 | 49 | 35 | 2025-01-02 | 2025-03-28 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-11 | 1900-01-14 | 11 | 2025-04-11 | 2025-04-11 | 1 | 1 | 101 | 73 | 75 | 55 | 176 | 128 | Steps 2,3,5,6,7 | 49 | 35 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 42.05 | 42.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-11 | -19 | -14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | 2025-02-14 | IOU Designed & Installed | N/A | No | N/A | -798.4 | -2.19 | Unknown | Unknown | -998 | 201.79 | 3981 | 1721.03 | -798.4 | 2519.43 | Yes | N/A | N/A | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | 2024-03-08 | 82 | 60 | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2025-02-14 | 352 | 252 | Unknown | 2024-12-05 | Unknown | Unknown | 2025-02-14 | 2025-02-24 | 1900-01-10 | 7 | 2025-02-24 | 2025-02-20 | Unknown | Unknown | 435 | 313 | 12 | 8 | 447 | 321 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | 2024-06-14 | IOU Designed & Installed | N/A | No | N/A | 1884.12 | -5.46 | Unknown | Unknown | 47.57 | 1842.01 | 3981 | 660.02 | 1884.12 | -1224.1 | Yes | N/A | N/A | 2024-03-11 | 2024-04-22 | 43 | 31 | 2024-04-22 | 2024-04-23 | 2 | 2 | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-06-14 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-06-28 | 1900-01-14 | 11 | 2024-06-28 | 2024-06-27 | Unknown | Unknown | 96 | 70 | 17 | 13 | 113 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-14 | -549 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-02-21 | 2023-06-13 | IOU Designed & Installed | N/A | No | N/A | 256.01 | 174.71 | Unknown | Unknown | Unknown | 81.3 | Unknown | 272.8 | 256.01 | 16.79 | Yes | N/A | N/A | 2023-02-21 | 2023-03-22 | 30 | 22 | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | 2023-06-13 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | 2023-06-14 | 1900-01-01 | 2 | 2023-06-14 | 2023-06-14 | 1 | 1 | 114 | 82 | 3 | 3 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-04 | -466 | -333 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-08-13 | 2024-09-13 | IOU Designed & Installed | N/A | No | N/A | 35.64 | Unknown | Unknown | Unknown | Unknown | 35.64 | 3981 | 1508.11 | 35.64 | 1472.47 | Yes | N/A | N/A | 2024-02-23 | 2024-08-13 | 173 | 123 | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-09-13 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-09-26 | 1900-01-13 | 10 | 2024-09-26 | 2024-09-25 | Unknown | Unknown | 205 | 147 | 15 | 11 | 220 | 158 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 106.05 | 106.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-07 | -640 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 335.77 | 66.98 | Unknown | 63.34 | 4.33 | 201.12 | 3981 | 1208.79 | 335.77 | 873.02 | Yes | N/A | N/A | 2024-09-24 | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-10-03 | 17 | 13 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | 2024-12-06 | 2024-12-06 | 1 | 1 | 0 | 0 | 18 | 14 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | SAN CLEMENTE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | 299 | 214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2025-01-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1043.53 | -20.46 | Unknown | Unknown | -1038.65 | 15.58 | Unknown | 933.94 | -1043.53 | 1977.47 | Yes | N/A | N/A | 2023-08-23 | 2025-01-21 | 518 | 370 | 2025-01-21 | 2025-01-30 | 10 | 8 | 2025-01-30 | 2025-02-18 | 20 | 14 | 2025-03-27 | 2025-03-31 | 5 | 3 | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | 2025-03-27 | 2025-03-27 | 1 | 1 | 538 | 384 | 16 | 12 | 554 | 396 | Steps 2,3,5,6,7 | 41 | 29 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 111 | 111 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-14 | -63 | -46 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | Unknown | 2023-11-09 | IOU Designed & Installed | N/A | No | N/A | 444.85 | -18.77 | Unknown | Unknown | Unknown | 463.62 | 3981 | 928.64 | 444.85 | 483.79 | Yes | N/A | N/A | 2023-05-03 | 2023-05-03 | 1 | 1 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | 2023-11-09 | 191 | 137 | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-12-13 | 1900-02-03 | 25 | 2023-12-13 | 2023-12-13 | 1 | 1 | 192 | 138 | 36 | 26 | 228 | 164 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | -613 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-04 | 2025-06-02 | IOU Designed & Installed | N/A | No | N/A | 1090.07 | Unknown | Unknown | Unknown | Unknown | 1090.07 | 3981 | 1247.58 | 1090.07 | 157.51 | Yes | N/A | N/A | 2025-02-27 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-03-04 | 8 | 6 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-06-02 | 91 | 65 | Unknown | 2025-06-02 | Unknown | Unknown | 2025-06-02 | 2025-06-09 | 1900-01-07 | 6 | 2025-06-09 | 2025-06-09 | 1 | 1 | 91 | 65 | 17 | 13 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 86.05 | 86.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-05 | -217 | -156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-01 | 2024-03-22 | IOU Designed & Installed | N/A | No | N/A | 2272.22 | 612.39 | Unknown | 359.4 | Unknown | 1300.43 | 3981 | 1103.51 | 2272.22 | -1168.71 | Yes | N/A | N/A | 2024-02-01 | 2024-02-02 | 2 | 2 | 2024-02-02 | 2024-02-02 | 1 | 1 | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-03-22 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-04-02 | 1900-01-11 | 8 | 2024-04-02 | 2024-04-02 | 1 | 1 | 52 | 38 | 14 | 10 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 156.05 | 156.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-16 | -548 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | 2023-12-01 | 2024-01-03 | IOU Designed & Installed | N/A | No | N/A | 324 | -8.2 | Unknown | Unknown | Unknown | 332.2 | Unknown | 950 | 324 | 626 | Yes | N/A | N/A | 2023-11-30 | 2023-12-01 | 2 | 2 | 2023-12-01 | 2023-12-01 | 1 | 1 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2024-01-03 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2024-02-15 | 1900-02-12 | 32 | 2024-02-15 | 2024-02-15 | 1 | 1 | 36 | 26 | 46 | 34 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | 138 | 138 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-26 | 302 | 216 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-05-31 | 2024-11-27 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 107405.96 | 38207.84 | Unknown | 2764.29 | 1913.33 | 64520.5 | 962753 | 41695.91 | 107405.96 | -65710.05 | Yes | N/A | N/A | 2023-05-31 | 2023-07-28 | 59 | 43 | 2023-07-28 | 2023-12-08 | 134 | 96 | 2023-08-07 | 2023-12-06 | 6 | 4 | 2024-11-06 | 2024-11-07 | 2 | 2 | 2023-12-08 | Unknown | Unknown | Unknown | 2023-12-18 | 2024-10-16 | 304 | 218 | 2024-11-27 | 2025-03-24 | 1900-04-27 | 84 | 2025-03-24 | 2025-03-24 | 1 | 1 | 65 | 47 | 559 | 401 | 624 | 448 | Steps 2,3,5,6,7 | 458 | 328 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-18 | 216 | 155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-16 | 2023-02-23 | 2024-05-29 | IOU Designed & Installed | N/A | No | N/A | 5551.69 | Unknown | Unknown | Unknown | Unknown | 5551.69 | 3981 | 1312.69 | 5551.69 | -4239 | Yes | N/A | N/A | 2023-02-16 | 2023-03-28 | 41 | 29 | 2023-03-28 | 2024-04-19 | 389 | 279 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2024-04-23 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-06-25 | 1900-01-27 | 20 | 2024-06-25 | 2024-06-21 | Unknown | Unknown | 46 | 32 | 417 | 299 | 463 | 331 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | SANTEE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 412 | 295 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-23 | 2022-06-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2472.25 | -29.68 | Unknown | Unknown | 180.65 | 2321.28 | 0 | 454.81 | 2472.25 | -2017.44 | Yes | N/A | N/A | 2022-06-23 | 2023-03-13 | 264 | 188 | 2023-03-13 | 2023-03-21 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-02-25 | 2023-03-08 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | Unknown | Unknown | Unknown | 2024-08-05 | Unknown | Unknown | 2024-08-05 | 2024-08-01 | Unknown | Unknown | 264 | 188 | 21 | 15 | 285 | 203 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-08 | -599 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-05-06 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 739.02 | -5.61 | Unknown | Unknown | Unknown | 744.63 | 3981 | 778.36 | 739.02 | 39.34 | Yes | N/A | N/A | 2024-04-15 | 2024-05-06 | 22 | 16 | 2024-05-06 | 2024-05-06 | 1 | 1 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-07-11 | 67 | 49 | Unknown | 2024-06-26 | Unknown | Unknown | 2024-07-11 | 2024-07-17 | 1900-01-06 | 5 | 2024-07-17 | 2024-07-17 | 1 | 1 | 89 | 65 | 9 | 7 | 98 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-10 | -525 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-12-01 | 2024-01-03 | IOU Designed & Installed | N/A | No | N/A | -9.5 | -7.71 | Unknown | Unknown | Unknown | -1.79 | Unknown | 158.79 | -9.5 | 168.29 | Yes | N/A | N/A | 2023-11-28 | 2023-07-27 | Unknown | Unknown | 2023-07-27 | 2023-12-01 | 128 | 92 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2024-01-03 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2024-02-01 | 1900-01-29 | 22 | 2024-02-01 | 2024-02-01 | 1 | 1 | 34 | 24 | 159 | 115 | 193 | 139 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 105 | 76 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-14 | 2023-06-14 | 2023-09-28 | IOU Designed & Installed | N/A | No | N/A | 4738.32 | -22.05 | Unknown | Unknown | 505.09 | 4255.28 | Unknown | 1928.72 | 4738.32 | -2809.6 | Yes | N/A | N/A | 2023-06-14 | 2023-08-16 | 64 | 46 | 2023-08-16 | 2023-08-28 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-06-24 | 2023-09-26 | 45 | 31 | 2023-08-28 | 2023-09-20 | 24 | 18 | Unknown | 2023-09-07 | Unknown | Unknown | 2023-09-28 | 2024-04-08 | 1900-07-12 | 138 | 2024-04-08 | 2023-09-29 | Unknown | Unknown | 88 | 64 | 252 | 178 | 340 | 242 | Steps 2,3,5,6,7 | 29 | 21 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-05-15 | 586 | 420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -235.28 | Unknown | Unknown | Unknown | -739 | 503.72 | 3981 | 1702.69 | -235.28 | 1937.97 | Yes | N/A | N/A | 2024-05-06 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-05-31 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2024-09-12 | 2 | 2 | 2024-05-31 | 2024-11-21 | 175 | 125 | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | 2024-12-30 | Unknown | Unknown | 2024-12-30 | 2024-12-21 | Unknown | Unknown | 175 | 125 | 33 | 25 | 208 | 150 | Steps 2,3,5,6,7 | 104 | 74 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | Chula Vista | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-12 | 122 | 89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-18 | 2024-11-27 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 164160.91 | 16276.38 | Unknown | 2627.18 | 19144.71 | 126112.64 | 0 | 73602.91 | 164160.91 | -90558 | Yes | N/A | N/A | 2023-07-18 | 2023-10-11 | 86 | 62 | 2023-10-11 | 2024-02-13 | 126 | 90 | 2023-10-26 | 2024-12-17 | 106 | 76 | 2023-08-25 | 2025-01-16 | 234 | 168 | 2024-02-29 | Unknown | Unknown | Unknown | 2024-02-29 | 2024-11-07 | 253 | 181 | 2024-11-27 | 2025-03-14 | 1900-04-17 | 78 | 2025-03-14 | 2025-03-14 | 1 | 1 | 192 | 138 | 722 | 518 | 914 | 656 | Steps 2,3,5,6,7 | 912 | 650 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-20 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-22 | 2025-05-09 | IOU Designed & Installed | N/A | No | N/A | 1201.68 | -24.15 | Unknown | Unknown | Unknown | 1225.83 | 3981 | 1840.62 | 1201.68 | 638.94 | Yes | N/A | N/A | 2024-11-19 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-11-22 | 15 | 11 | 2024-11-22 | Unknown | Unknown | Unknown | 2024-12-03 | 2024-12-18 | 16 | 12 | 2024-11-22 | 2025-05-09 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-21 | 1900-01-12 | 9 | 2025-05-21 | 2025-05-21 | 1 | 1 | 169 | 121 | 45 | 33 | 214 | 154 | Steps 2,3,5,6,7 | 26 | 18 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | -280 | -201 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-03-08 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 3773.45 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-13 | 2023-02-13 | 1 | 1 | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | 2023-04-07 | 1900-01-30 | 23 | 2023-04-07 | 2023-04-07 | 1 | 1 | 1 | 1 | 32 | 24 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 838 | 838 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-21 | -238 | -171 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 18020.14 | Unknown | Unknown | Unknown | Unknown | 18020.14 | 3981 | 1023.84 | 18020.14 | -16996.3 | Yes | N/A | N/A | 2023-12-05 | 2023-09-19 | Unknown | Unknown | 2023-09-19 | 2024-03-20 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-05-14 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-12-03 | 1900-02-04 | 26 | 2024-12-03 | 2024-12-26 | 24 | 18 | 56 | 40 | 244 | 176 | 300 | 216 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-07 | -429 | -306 | No | 2024-10-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | 2025-03-31 | IOU Designed & Installed | N/A | Yes | 14 | 2599.87 | 539.52 | Unknown | 163.63 | 27.35 | 1869.37 | 31848 | 308.65 | 2599.87 | -2291.22 | Yes | N/A | N/A | 2024-10-16 | 2024-10-17 | 2 | 2 | 2024-10-17 | 2024-11-01 | 16 | 12 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2025-03-31 | 151 | 107 | Unknown | 2025-04-04 | Unknown | Unknown | 2025-03-31 | 2025-04-04 | 1900-01-04 | 5 | 2025-04-04 | 2025-04-04 | 1 | 1 | 153 | 109 | 22 | 18 | 175 | 127 | Steps 2,3,5,6,7 | 4 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-28 | -596 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | 2024-08-27 | IOU Designed & Installed | N/A | No | N/A | 2258.41 | Unknown | Unknown | Unknown | 16.3 | 2242.11 | 3981 | 1120.15 | 2258.41 | -1138.26 | Yes | N/A | N/A | 2024-06-06 | 2024-07-08 | 33 | 23 | 2024-07-08 | 2024-07-09 | 2 | 2 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-08-27 | 50 | 36 | Unknown | 2024-08-23 | Unknown | Unknown | 2024-08-27 | 2024-09-09 | 1900-01-13 | 10 | 2024-09-09 | 2024-09-09 | 1 | 1 | 83 | 59 | 17 | 13 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-22 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | 2025-01-10 | IOU Designed & Installed | N/A | No | N/A | 444.43 | -8.14 | Unknown | Unknown | Unknown | 452.57 | 3981 | 1651.64 | 444.43 | 1207.21 | Yes | N/A | N/A | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-10 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-02-25 | 1900-02-15 | 33 | 2025-02-25 | 2025-02-25 | 1 | 1 | 3 | 3 | 49 | 35 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | COTO DE CAZA | N/A | 191 | 191 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-23 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-12 | 2025-06-12 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 257.6 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-12 | 2025-06-03 | Unknown | Unknown | 2025-06-03 | 2025-06-12 | 10 | 8 | 2025-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-06-23 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-24 | 1900-01-01 | 2 | 2025-06-24 | 2025-06-24 | 1 | 1 | 12 | 8 | 13 | 11 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | PAUMA VALLEY | N/A | 440 | 440 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | -22 | -16 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-06-01 | 2023-11-07 | IOU Designed & Installed | N/A | No | N/A | 4113.7 | Unknown | Unknown | Unknown | 71.32 | 4042.38 | 125578 | 1992.71 | 4113.7 | -2120.99 | Yes | N/A | N/A | 2023-05-31 | 2023-04-28 | Unknown | Unknown | 2023-04-28 | 2023-10-06 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | 2023-10-27 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2024-02-23 | 1900-04-18 | 79 | 2024-02-23 | 2024-02-23 | 1 | 1 | 22 | 16 | 272 | 196 | 294 | 212 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | 13 | 13 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-21 | -682 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-27 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | 1201.68 | -24.15 | Unknown | Unknown | Unknown | 1225.83 | 3981 | 1919.87 | 1201.68 | 718.19 | Yes | N/A | N/A | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-17 | 21 | 15 | 2025-03-27 | 2025-04-25 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-08 | 1900-01-13 | 10 | 2025-05-08 | 2025-05-08 | 1 | 1 | 31 | 23 | 37 | 27 | 68 | 50 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-12 | -191 | -138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-08-31 | 2023-10-02 | IOU Designed & Installed | N/A | No | N/A | 451.75 | -5.85 | Unknown | Unknown | Unknown | 457.6 | 3981 | 670.34 | 451.75 | 218.59 | Yes | N/A | N/A | 2023-08-31 | 2023-08-30 | Unknown | Unknown | 2023-08-30 | 2023-09-05 | 7 | 5 | 2023-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | 2023-10-02 | 26 | 18 | Unknown | 2023-09-29 | Unknown | Unknown | 2023-10-02 | 2023-10-04 | 1900-01-02 | 3 | 2023-10-04 | 2023-10-04 | 1 | 1 | 26 | 18 | 11 | 9 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-15 | -224 | -161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-02-04 | 2025-06-02 | IOU Designed & Installed | N/A | No | N/A | 1208.98 | Unknown | Unknown | Unknown | -1191.67 | 2400.65 | Unknown | 1207.66 | 1208.98 | -1.32 | Yes | N/A | N/A | 2025-01-30 | 2025-02-13 | 15 | 11 | 2025-02-13 | 2025-02-14 | 2 | 2 | 2025-02-14 | 2025-04-21 | 67 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-06-02 | 53 | 37 | Unknown | 2025-05-16 | Unknown | Unknown | 2025-06-02 | 2025-06-05 | 1900-01-03 | 4 | 2025-06-05 | 2025-06-05 | 1 | 1 | 135 | 95 | 7 | 7 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-24 | -257 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1732.48 | 630.26 | Unknown | 88.44 | -2753 | 301.82 | Unknown | 2753.5 | -1732.48 | 4485.98 | Yes | N/A | N/A | 2023-09-06 | 2023-09-06 | 1 | 1 | 2023-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-05 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2024-01-11 | IOU Designed & Installed | N/A | No | N/A | -6.18 | -4.99 | Unknown | Unknown | Unknown | -1.19 | 3981 | 816.35 | -6.18 | 822.53 | Yes | N/A | N/A | 2023-09-27 | 2023-10-20 | 24 | 18 | 2023-10-20 | 2023-10-20 | 1 | 1 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2024-01-11 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-02-27 | 1900-02-16 | 34 | 2024-02-27 | 2024-02-27 | 1 | 1 | 108 | 78 | 50 | 36 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 25.05 | 25.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | -528 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2025-01-09 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 6454.49 | 1504.21 | Unknown | 417.28 | 52.66 | 4480.34 | 3981 | 2047.97 | 6454.49 | -4406.52 | Yes | N/A | N/A | 2024-10-09 | 2025-01-06 | 90 | 64 | 2025-01-06 | 2025-01-10 | 5 | 5 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-03-05 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-04-01 | 1900-01-27 | 20 | 2025-04-01 | 2025-04-01 | 1 | 1 | 145 | 103 | 34 | 26 | 179 | 129 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 100.05 | 100.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-13 | -607 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-07-09 | 2024-09-04 | IOU Designed & Installed | N/A | No | N/A | 903.7 | -17.61 | Unknown | Unknown | Unknown | 921.31 | Unknown | 1625.1 | 903.7 | 721.4 | Yes | N/A | N/A | 2024-06-27 | 2024-07-09 | 13 | 9 | 2024-07-09 | 2024-07-09 | 1 | 1 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-09-04 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-13 | 1900-01-09 | 8 | 2024-09-13 | 2024-09-13 | 1 | 1 | 71 | 51 | 12 | 10 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-05 | -604 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-07-07 | 2023-08-10 | IOU Designed & Installed | N/A | No | N/A | -7.08 | -13.71 | Unknown | Unknown | Unknown | 6.63 | Unknown | 865.19 | -7.08 | 872.27 | Yes | N/A | N/A | 2023-07-07 | 2023-07-07 | 1 | 1 | 2023-07-07 | 2023-07-07 | 1 | 1 | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | 2023-08-10 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-08-10 | 1899-12-31 | 1 | 2023-08-10 | 2023-08-10 | 1 | 1 | 36 | 26 | 3 | 3 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-20 | -398 | -285 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-24 | 2023-07-21 | IOU Designed & Installed | N/A | No | N/A | 2409.54 | -64.56 | Unknown | Unknown | Unknown | 2474.1 | 3885 | 922.23 | 2409.54 | -1487.31 | Yes | N/A | N/A | 2023-02-23 | 2023-02-24 | 2 | 2 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | 2023-07-21 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2023-09-18 | 1900-02-28 | 42 | 2023-09-18 | 2023-09-18 | 1 | 1 | 150 | 108 | 61 | 43 | 211 | 151 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-10 | 422 | 303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 466.02 | Unknown | Unknown | Unknown | Unknown | 466.02 | 3662 | 278.3 | 466.02 | -187.72 | Yes | N/A | N/A | 2023-02-01 | 2023-02-01 | 1 | 1 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | Unknown | Unknown | 2023-10-10 | 2023-10-06 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | -398 | -285 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-05-06 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | 3703.95 | 781.39 | Unknown | 105.49 | 46.59 | 2770.48 | 3961 | 53129.16 | 3703.95 | 49425.21 | Yes | N/A | N/A | 2024-01-12 | 2024-05-02 | 112 | 80 | 2024-05-02 | 2024-05-06 | 5 | 3 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-09-16 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-12-19 | 1900-04-04 | 69 | 2024-12-19 | 2024-09-20 | Unknown | Unknown | 246 | 176 | 100 | 72 | 346 | 248 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 84.05 | 84.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-17 | -456 | -327 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-06 | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | 4.44 | Unknown | Unknown | Unknown | Unknown | 4.44 | Unknown | 1050.75 | 4.44 | 1046.31 | Yes | N/A | N/A | 2024-09-06 | 2024-09-06 | 1 | 1 | 2024-09-06 | 2024-09-06 | 1 | 1 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-17 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-10-01 | 1900-01-14 | 11 | 2024-10-01 | 2025-03-18 | 169 | 121 | 13 | 9 | 185 | 133 | 198 | 142 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 138.05 | 138.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | -415 | -298 | No | 2023-06-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-19 | 2024-02-28 | IOU Designed & Installed | N/A | Yes | 151 | 1706.86 | -14 | Unknown | Unknown | 104.14 | 1616.72 | 3981 | 778.43 | 1706.86 | -928.43 | Yes | N/A | N/A | 2023-06-19 | 2023-11-16 | 151 | 109 | 2023-11-16 | 2023-11-17 | 2 | 2 | 2023-10-09 | 2023-10-09 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-08-26 | 2024-02-28 | 187 | 133 | Unknown | 2024-01-31 | Unknown | Unknown | 2024-02-28 | 2024-03-12 | 1900-01-13 | 10 | 2024-03-12 | 2024-03-12 | 1 | 1 | 339 | 243 | 17 | 13 | 356 | 256 | Steps 2,3,5,6,7 | 39 | 29 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-07 | -291 | -209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-10-05 | 2023-11-01 | IOU Designed & Installed | N/A | No | N/A | 72.94 | 2537.84 | Unknown | 766.48 | -4329 | 1097.62 | Unknown | 4328.7 | 72.94 | 4255.76 | Yes | N/A | N/A | 2023-10-02 | 2023-09-26 | Unknown | Unknown | 2023-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2023-11-21 | 1900-01-20 | 15 | 2023-11-21 | 2023-11-21 | 1 | 1 | 0 | 0 | 22 | 16 | 22 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | -428 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | 2025-06-16 | IOU Designed & Installed | N/A | No | N/A | 2630.17 | 513.12 | Unknown | Unknown | 24.61 | 2092.44 | 3941 | 1167.15 | 2630.17 | -1463.02 | Yes | N/A | N/A | 2024-10-09 | 2024-10-30 | 22 | 16 | 2024-10-30 | 2024-11-22 | 24 | 18 | 2024-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-06-16 | 207 | 147 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-06-17 | 1900-01-01 | 2 | 2025-06-17 | 2025-06-17 | 1 | 1 | 229 | 163 | 27 | 21 | 256 | 184 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-20 | -355 | -255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8.63 | Unknown | Unknown | Unknown | Unknown | 8.63 | 0 | 158.79 | 8.63 | 150.16 | Yes | N/A | N/A | 2023-12-18 | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2023-12-19 | 83 | 59 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | 2024-09-30 | 2024-09-30 | 1 | 1 | 0 | 0 | 84 | 60 | 84 | 60 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | -640 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | Unknown | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 1309.9 | 379.36 | Unknown | Unknown | Unknown | 930.54 | 3981 | 1703.27 | 1309.9 | 393.37 | Yes | N/A | N/A | 2024-08-16 | 2024-08-16 | 1 | 1 | 2024-08-16 | 2024-08-16 | 1 | 1 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-09-09 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2024-10-22 | 1900-02-12 | 32 | 2024-10-22 | 2024-10-22 | 1 | 1 | 26 | 18 | 46 | 34 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 11.4 | 11.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-27 | -590 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-23 | 2024-08-01 | IOU Designed & Installed | N/A | No | N/A | 329.6 | Unknown | Unknown | Unknown | 4.16 | 325.44 | 3981 | 1030.39 | 329.6 | 700.79 | Yes | N/A | N/A | 2024-05-06 | 2024-05-23 | 18 | 14 | 2024-05-23 | 2024-06-07 | 16 | 12 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-08-01 | 56 | 40 | Unknown | 2024-07-25 | Unknown | Unknown | 2024-08-01 | 2024-08-14 | 1900-01-13 | 10 | 2024-08-14 | 2024-08-14 | 1 | 1 | 74 | 54 | 31 | 23 | 105 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 93 | 93 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | -344 | -247 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-06-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3241 | 1067.01 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-07 | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-06-07 | 75 | 55 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | 2025-05-05 | 2025-05-01 | Unknown | Unknown | 0 | 0 | 75 | 55 | 75 | 55 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-13 | -369 | -264 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-13 | 2024-12-20 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2072.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-12 | 2024-12-03 | Unknown | Unknown | 2024-12-03 | 2024-12-13 | 11 | 9 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2024-12-20 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-05-09 | 1900-05-20 | 101 | 2025-05-09 | 2025-05-09 | 1 | 1 | 8 | 6 | 153 | 111 | 161 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | -594 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-05-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 427.75 | -9.26 | Unknown | Unknown | Unknown | 437.01 | 3981 | 646.79 | 427.75 | 219.04 | Yes | N/A | N/A | 2023-04-12 | 2023-05-08 | 27 | 19 | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | Unknown | Unknown | Unknown | 2023-06-26 | Unknown | Unknown | 2023-06-26 | 2023-06-26 | 1 | 1 | 27 | 19 | 1 | 1 | 28 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-16 | 767 | 548 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1474.91 | Unknown | Unknown | Unknown | -347.65 | 1822.56 | 0 | 407.5 | 1474.91 | -1067.41 | Yes | N/A | N/A | 2023-07-05 | 2023-07-05 | 1 | 1 | 2023-07-05 | 2023-08-16 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-08-25 | 2023-08-25 | 1 | 1 | 2023-08-16 | 2025-03-28 | 591 | 423 | Unknown | 2025-04-15 | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | 2025-04-22 | 2025-04-21 | Unknown | Unknown | 592 | 424 | 44 | 32 | 636 | 456 | Steps 2,3,5,6,7 | 9 | 7 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-23 | -481 | -345 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | 2024-03-20 | IOU Designed & Installed | N/A | No | N/A | 485.96 | 292.29 | Unknown | Unknown | Unknown | 193.67 | Unknown | 163.83 | 485.96 | -322.13 | Yes | N/A | N/A | 2024-02-08 | 2023-10-17 | Unknown | Unknown | 2023-10-17 | 2024-03-14 | 150 | 108 | 2024-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-03-20 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-04-29 | 1900-02-09 | 29 | 2024-04-29 | 2024-04-29 | 1 | 1 | 7 | 5 | 192 | 138 | 199 | 143 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | 241.05 | 241.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-09 | -554 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-02 | 2024-01-31 | IOU Designed & Installed | N/A | No | N/A | 1170.03 | 402.84 | Unknown | Unknown | Unknown | 767.19 | Unknown | 369.83 | 1170.03 | -800.2 | Yes | N/A | N/A | 2024-01-02 | 2023-10-20 | Unknown | Unknown | 2023-10-20 | 2024-01-10 | 83 | 59 | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-01-31 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-02-02 | 1900-01-02 | 3 | 2024-02-02 | 2024-02-02 | 1 | 1 | 22 | 16 | 87 | 63 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 111.05 | 111.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-18 | -594 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2025-01-09 | 2025-03-28 | IOU Designed & Installed | N/A | No | N/A | 2140.17 | 509.4 | Unknown | 128.91 | Unknown | 1501.86 | 3981 | 1411.63 | 2140.17 | -728.54 | Yes | N/A | N/A | 2024-12-17 | 2025-01-09 | 24 | 18 | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-03-28 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-03 | 1900-01-06 | 5 | 2025-04-03 | 2025-04-03 | 1 | 1 | 103 | 75 | 9 | 7 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -243 | -175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-02-28 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2826.37 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-28 | 2025-03-05 | 6 | 4 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-23 | 1899-12-31 | 1 | 2025-06-23 | 2025-06-23 | 1 | 1 | 6 | 4 | 2 | 2 | 8 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 74.05 | 74.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-26 | -512 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2024-01-12 | IOU Designed & Installed | N/A | No | N/A | 1141.75 | -18.65 | Unknown | Unknown | 4.61 | 1155.79 | 3281 | 1070.99 | 1141.75 | -70.76 | Yes | N/A | N/A | 2023-09-27 | 2023-11-06 | 41 | 29 | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2024-01-12 | 68 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | 2024-01-31 | 1900-01-19 | 14 | 2024-01-31 | 2024-01-31 | 1 | 1 | 109 | 79 | 22 | 16 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-21 | -530 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-23 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | 515.94 | Unknown | Unknown | Unknown | 16.19 | 499.75 | 3981 | 1237.55 | 515.94 | 721.61 | Yes | N/A | N/A | 2024-10-21 | 2024-11-06 | 17 | 13 | 2024-11-06 | 2024-11-06 | 1 | 1 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2025-03-31 | 146 | 104 | Unknown | 2025-03-28 | Unknown | Unknown | 2025-03-31 | 2025-04-09 | 1900-01-09 | 8 | 2025-04-09 | 2025-04-09 | 1 | 1 | 163 | 117 | 12 | 10 | 175 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 339.05 | 339.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | 151 | 108 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-23 | 2023-06-26 | 2025-05-08 | IOU Designed & Installed | N/A | No | N/A | 103547.01 | 4173.64 | Unknown | 34.46 | 396.08 | 98942.83 | 0 | 32767.96 | 103547.01 | -70779.05 | Yes | N/A | N/A | 2023-06-23 | 2023-06-27 | 5 | 3 | 2023-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | 2025-04-07 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-06-30 | 1900-02-22 | 38 | 2025-06-30 | 2025-06-30 | 1 | 1 | 5 | 3 | 74 | 52 | 79 | 55 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-03 | -91 | -66 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-17 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 14828.2 | Unknown | Unknown | Unknown | -1331 | 16159.2 | Unknown | 1331.23 | 14828.2 | -13496.97 | Yes | N/A | N/A | 2024-07-17 | 2024-07-17 | 1 | 1 | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-09-03 | 1900-02-04 | 26 | 2024-09-03 | 2024-09-03 | 1 | 1 | 1 | 1 | 37 | 27 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-09 | -464 | -331 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-20 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | 23.58 | Unknown | Unknown | Unknown | Unknown | 23.58 | 3981 | 830.88 | 23.58 | 807.3 | Yes | N/A | N/A | 2023-12-14 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | 2023-12-20 | 34 | 24 | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-07-16 | 210 | 150 | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-08-02 | 1900-01-17 | 14 | 2024-08-02 | 2024-08-02 | 1 | 1 | 210 | 150 | 53 | 39 | 263 | 189 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-19 | -421 | -302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-18 | 2024-04-18 | IOU Designed & Installed | N/A | No | N/A | 1803.72 | -9.55 | Unknown | Unknown | 19.74 | 1793.53 | 3981 | 867.56 | 1803.72 | -936.16 | Yes | N/A | N/A | 2023-11-15 | 2024-03-04 | 111 | 79 | 2024-03-04 | 2024-03-05 | 2 | 2 | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | 2024-04-18 | 45 | 33 | Unknown | 2024-04-11 | Unknown | Unknown | 2024-04-18 | 2024-04-24 | 1900-01-06 | 5 | 2024-04-24 | 2024-04-24 | 1 | 1 | 156 | 112 | 10 | 8 | 166 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-15 | -173 | -124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-31 | 2025-06-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2096.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-05-14 | 64 | 46 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-06-25 | 1899-12-31 | 1 | 2025-06-25 | 2025-06-25 | 1 | 1 | 64 | 46 | 2 | 2 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-22 | 1 | 2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | 2024-09-30 | IOU Designed & Installed | N/A | No | N/A | -1697.68 | Unknown | Unknown | Unknown | -1750 | 52.32 | Unknown | 1634.68 | -1697.68 | 3332.36 | Yes | N/A | N/A | 2024-08-05 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-08-05 | 53 | 37 | 2024-08-05 | 2024-08-20 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-09-30 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-10-25 | 1900-01-25 | 20 | 2024-10-25 | 2024-10-23 | Unknown | Unknown | 58 | 42 | 79 | 57 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-09 | -563 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 23.59 | Unknown | Unknown | Unknown | Unknown | 23.59 | 3941 | 1387.54 | 23.59 | 1363.95 | Yes | N/A | N/A | 2024-07-02 | 2024-05-29 | Unknown | Unknown | 2024-05-29 | 2024-07-02 | 35 | 25 | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-09-06 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-16 | 1900-01-10 | 7 | 2024-09-16 | 2024-09-23 | 8 | 6 | 67 | 49 | 54 | 38 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-13 | -227 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | 2024-04-29 | 2024-05-24 | IOU Designed & Installed | N/A | No | N/A | 5.06 | -4.5 | Unknown | Unknown | Unknown | 9.56 | 3981 | 818.11 | 5.06 | 813.05 | Yes | N/A | N/A | 2024-04-26 | 2024-04-29 | 4 | 2 | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-05-24 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-07-09 | 1900-02-15 | 33 | 2024-07-09 | 2024-05-31 | Unknown | Unknown | 28 | 20 | 48 | 34 | 76 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-14 | -75 | -55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-25 | 2024-07-01 | IOU Designed & Installed | N/A | No | N/A | 11779.32 | 2226.8 | Unknown | Unknown | -900.98 | 10453.5 | Unknown | 697.45 | 11779.32 | -11081.87 | Yes | N/A | N/A | 2023-09-21 | 2023-09-11 | Unknown | Unknown | 2023-09-11 | 2023-10-06 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | Unknown | Unknown | 2024-07-01 | 2024-07-01 | 1899-12-31 | 1 | 2024-07-01 | 2024-07-01 | 1 | 1 | 0 | 0 | 28 | 22 | 28 | 22 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-27 | -275 | -196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-06-20 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 1641.38 | Unknown | Unknown | Unknown | 14.32 | 1627.06 | 3981 | 1096.7 | 1641.38 | -544.68 | Yes | N/A | N/A | 2024-05-02 | 2024-04-25 | Unknown | Unknown | 2024-04-25 | 2024-05-03 | 9 | 7 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-10-18 | 99 | 71 | Unknown | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-10-25 | 1900-01-07 | 6 | 2024-10-25 | 2024-10-25 | 1 | 1 | 99 | 71 | 18 | 14 | 117 | 85 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | -693 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6.61 | Unknown | Unknown | Unknown | Unknown | 6.61 | 3981 | 197.01 | 6.61 | 190.4 | Yes | N/A | N/A | 2024-10-29 | 2024-10-31 | 3 | 3 | 2024-10-31 | 2024-10-31 | 1 | 1 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | Unknown | Unknown | 2024-12-04 | 2024-12-04 | 1 | 1 | 3 | 3 | 2 | 2 | 5 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | -41 | -30 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-04 | 2024-01-21 | IOU Designed & Installed | N/A | No | N/A | 2102.92 | 565.68 | Unknown | 320.5 | Unknown | 1216.74 | 3981 | 942.77 | 2102.92 | -1160.15 | Yes | N/A | N/A | 2023-05-03 | 2023-05-05 | 3 | 3 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | 2024-01-21 | 262 | 186 | Unknown | Unknown | Unknown | Unknown | 2024-01-21 | 2024-01-25 | 1900-01-04 | 4 | 2024-01-25 | 2024-01-25 | 1 | 1 | 265 | 189 | 6 | 5 | 271 | 194 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-19 | -572 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-30 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 29.24 | Unknown | Unknown | Unknown | Unknown | 29.24 | 3981 | 1552.93 | 29.24 | 1523.69 | Yes | N/A | N/A | 2024-10-28 | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2024-10-30 | 22 | 16 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2025-02-10 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-19 | 1900-01-09 | 8 | 2025-02-19 | 2025-02-24 | 6 | 4 | 104 | 74 | 38 | 28 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-20 | -154 | -111 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | Unknown | 2023-08-29 | IOU Designed & Installed | N/A | No | N/A | 1105.52 | -11.09 | Unknown | Unknown | 8.24 | 1108.37 | 3981 | 2210.72 | 1105.52 | 1105.2 | Yes | N/A | N/A | 2023-04-25 | 2023-05-17 | 23 | 17 | 2023-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-25 | 2023-08-29 | 127 | 91 | Unknown | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-09-19 | 1900-01-21 | 16 | 2023-09-19 | 2023-09-19 | 1 | 1 | 150 | 108 | 23 | 17 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-16 | -610 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2024-05-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 97.05 | -1.57 | Unknown | Unknown | 0.4 | 98.22 | 3981 | 1474.62 | 97.05 | 1377.57 | Yes | N/A | N/A | 2024-05-22 | 2024-05-22 | 1 | 1 | 2024-05-22 | 2024-05-22 | 1 | 1 | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | Unknown | Unknown | 2024-09-13 | 2024-09-13 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | Rancho Mission Viejo | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-09-01 | 309 | 222 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-21 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | 28193.34 | 2218.05 | Unknown | Unknown | 2627.37 | 23347.92 | 3981 | Not available | 28193.34 | Unknown | Yes | N/A | N/A | 2023-04-21 | 2023-06-28 | 69 | 49 | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | Unknown | Unknown | 2023-07-26 | 2024-09-23 | 1901-03-01 | 304 | 2024-09-23 | 2023-07-07 | Unknown | Unknown | 69 | 49 | 426 | 304 | 495 | 353 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | -608 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | 2024-12-12 | IOU Designed & Installed | N/A | No | N/A | 2702.59 | 872.89 | Unknown | 163.18 | Unknown | 1666.52 | 3981 | 1522 | 2702.59 | -1180.59 | Yes | N/A | N/A | 2024-11-14 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-12-12 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-01-17 | 1900-02-05 | 27 | 2025-01-17 | 2025-01-17 | 1 | 1 | 29 | 21 | 38 | 28 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -218 | -157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 453.87 | -8.87 | Unknown | Unknown | Unknown | 462.74 | Unknown | 466.88 | 453.87 | 13.01 | Yes | N/A | N/A | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | 2024-06-18 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-06-05 | 28 | 20 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-09-17 | 1 | 1 | 2 | 2 | 78 | 56 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-06 | -658 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | -10.4 | -8.38 | Unknown | Unknown | Unknown | -2.02 | Unknown | 154.79 | -10.4 | 165.19 | Yes | N/A | N/A | 2023-03-30 | 2023-04-13 | 15 | 11 | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 15 | 11 | 1 | 1 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 224 | 161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-28 | 2022-11-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1042.48 | -17.09 | Unknown | Unknown | 65.94 | 993.63 | Unknown | 1752.46 | 1042.48 | 709.98 | Yes | N/A | N/A | 2022-11-28 | 2023-06-19 | 204 | 146 | 2023-06-19 | 2023-07-05 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-04-13 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2024-02-02 | 1 | 1 | 204 | 146 | 26 | 20 | 230 | 166 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-13 | -486 | -347 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-07-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 837.81 | 254.76 | Unknown | 60.47 | -645.96 | 1168.54 | Unknown | 650.23 | 837.81 | -187.58 | Yes | N/A | N/A | 2023-07-07 | 2023-07-21 | 15 | 11 | 2023-07-21 | 2023-07-21 | 1 | 1 | 2023-07-21 | 2023-10-30 | 102 | 72 | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | Unknown | Unknown | Unknown | 2023-12-14 | Unknown | Unknown | 2023-12-14 | 2023-12-14 | 1 | 1 | 117 | 83 | 2 | 2 | 119 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 117.05 | 117.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-23 | -303 | -217 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-03-26 | 2024-10-17 | IOU Designed & Installed | N/A | No | N/A | 1276.79 | Unknown | Unknown | Unknown | 40.71 | 1236.08 | 3981 | 1265.31 | 1276.79 | -11.48 | Yes | N/A | N/A | 2024-03-26 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2024-04-12 | 80 | 58 | 2024-04-12 | 2024-07-22 | 102 | 72 | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-10-17 | 189 | 135 | Unknown | 2024-08-19 | Unknown | Unknown | 2024-10-17 | 2024-10-22 | 1900-01-05 | 4 | 2024-10-22 | 2024-10-24 | 3 | 3 | 291 | 207 | 89 | 65 | 380 | 272 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | 217.1 | 217.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-15 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-11-08 | 2024-12-03 | IOU Designed & Installed | N/A | No | N/A | -1112.47 | Unknown | Unknown | Unknown | -1176 | 63.53 | 3981 | 2638.18 | -1112.47 | 3750.65 | Yes | N/A | N/A | 2024-11-06 | 2024-10-21 | Unknown | Unknown | 2024-10-21 | 2024-11-08 | 19 | 15 | 2024-11-08 | 2024-11-18 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-12-03 | 16 | 12 | Unknown | 2024-11-27 | Unknown | Unknown | 2024-12-03 | 2024-12-05 | 1900-01-02 | 3 | 2024-12-05 | 2024-12-05 | 1 | 1 | 27 | 19 | 23 | 19 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | -885 | -633 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | 2023-06-06 | IOU Designed & Installed | N/A | No | N/A | 4341.68 | 115.45 | Unknown | 50.62 | Unknown | 4175.61 | Unknown | 216.32 | 4341.68 | -4125.36 | Yes | N/A | N/A | 2023-02-15 | 2023-03-27 | 41 | 29 | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-27 | 2023-06-06 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | 2023-06-07 | 1900-01-01 | 2 | 2023-06-07 | 2023-06-07 | 1 | 1 | 113 | 81 | 3 | 3 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-29 | -480 | -344 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | 2023-06-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 733.8 | -10.57 | Unknown | Unknown | -515.6 | 1259.97 | Unknown | 546.11 | 733.8 | -187.69 | Yes | N/A | N/A | 2023-06-05 | 2023-07-09 | 35 | 25 | 2023-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | Unknown | 2023-12-05 | Unknown | Unknown | 2023-12-05 | 2023-12-05 | 1 | 1 | 35 | 25 | 1 | 1 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-06 | -449 | -322 | No | 2023-02-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-01 | Unknown | IOU Designed & Installed | N/A | Yes | 107 | -17.35 | -12.56 | Unknown | Unknown | Unknown | -4.79 | Unknown | 311.78 | -17.35 | 329.13 | Yes | N/A | N/A | 2023-02-01 | 2023-05-19 | 108 | 78 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | Unknown | Unknown | 2023-06-15 | 2023-06-15 | 1 | 1 | 108 | 78 | 1 | 1 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-03 | -242 | -174 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-06 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 3582.5 | 734.4 | Unknown | Unknown | -557.49 | 3405.59 | Unknown | 656.49 | 3582.5 | -2926.01 | Yes | N/A | N/A | 2023-09-06 | 2023-10-19 | 44 | 32 | 2023-10-19 | 2023-10-20 | 2 | 2 | 2023-10-20 | 2024-01-11 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2024-08-28 | 315 | 225 | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-09-03 | 1900-01-06 | 5 | 2024-09-03 | 2024-09-03 | 1 | 1 | 443 | 317 | 10 | 8 | 453 | 325 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-03 | 557 | 398 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-29 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | 12730.05 | 599.05 | Unknown | 45.99 | Unknown | 12085.01 | Unknown | 2219.03 | 12730.05 | -10511.02 | Yes | N/A | N/A | 2024-03-29 | 2023-10-05 | Unknown | Unknown | 2023-10-05 | 2024-04-05 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-05-13 | 1900-01-26 | 19 | 2024-05-13 | 2024-05-13 | 1 | 1 | 0 | 0 | 212 | 152 | 212 | 152 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | DANA POINT | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | 41 | 30 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-06-17 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | -1603.69 | 9005.39 | Unknown | Unknown | -22866 | 12256.92 | 0 | 25313.46 | -1603.69 | 26917.15 | Yes | N/A | N/A | 2024-06-07 | 2024-06-07 | 1 | 1 | 2024-06-07 | 2025-03-18 | 285 | 203 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2025-02-21 | 21 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-06-10 | 1900-02-08 | 28 | 2025-06-10 | 2025-06-10 | 1 | 1 | 1 | 1 | 347 | 249 | 348 | 250 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-NORTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-16 | -602 | -431 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-03 | 2024-05-24 | IOU Designed & Installed | N/A | No | N/A | 21349.39 | 5946.74 | Unknown | 1077.57 | 97.89 | 14227.19 | Unknown | 1039.76 | 21349.39 | -20309.63 | Yes | N/A | N/A | 2024-04-02 | 2024-04-18 | 17 | 13 | 2024-04-18 | 2024-04-18 | 1 | 1 | 2024-04-18 | Unknown | Unknown | Unknown | 2024-04-18 | 2024-04-22 | 5 | 3 | 2024-04-18 | 2024-05-24 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-06-24 | 1900-01-31 | 22 | 2024-06-24 | 2024-06-24 | 1 | 1 | 54 | 40 | 39 | 27 | 93 | 67 | Steps 2,3,5,6,7 | 4 | 2 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | CB 1106-D5 (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-15 | 284 | 203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-06-21 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 5817.57 | 273.47 | Unknown | Unknown | 338.38 | 5205.72 | Unknown | 4446.49 | 5817.57 | -1371.08 | Yes | N/A | N/A | 2024-01-11 | 2024-06-07 | 149 | 107 | 2024-06-07 | 2024-11-06 | 153 | 109 | 2024-06-21 | 2024-10-29 | 131 | 93 | 2024-10-30 | 2024-11-06 | 8 | 6 | 2024-12-19 | Unknown | Unknown | Unknown | 2024-12-19 | 2025-02-24 | 68 | 48 | 2025-03-17 | 2025-03-26 | 1900-01-09 | 8 | 2025-03-26 | 2025-03-26 | 1 | 1 | 280 | 200 | 240 | 172 | 520 | 372 | Steps 2,3,5,6,7 | 138 | 98 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-31 | 245 | 176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | 2023-09-19 | IOU Designed & Installed | N/A | No | N/A | 4697.66 | -40.98 | Unknown | Unknown | Unknown | 4738.64 | 3981 | 1066.92 | 4697.66 | -3630.74 | Yes | N/A | N/A | 2023-05-19 | 2023-05-19 | 1 | 1 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | 2023-07-17 | 8 | 6 | 2023-07-10 | 2023-09-19 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-10-04 | 1900-01-15 | 12 | 2023-10-04 | 2023-10-03 | Unknown | Unknown | 73 | 53 | 24 | 18 | 97 | 71 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | COUNTY OF SAN DIEGO-NORTH of 56 | 12.45 | 12.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-05 | -472 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1607.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-12 | 2024-07-12 | Unknown | Unknown | 2024-07-12 | 2024-08-19 | 39 | 27 | 2024-08-19 | Unknown | Unknown | Unknown | 2024-08-23 | 2024-08-30 | 8 | 6 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | 2025-03-21 | 2025-03-20 | Unknown | Unknown | 0 | 0 | 47 | 33 | 47 | 33 | Steps 2,3,5,6,7 | 7 | 5 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | -158 | -115 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12.38 | Unknown | Unknown | Unknown | Unknown | 12.38 | Unknown | 449.58 | 12.38 | 437.2 | Yes | N/A | N/A | 2024-09-05 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2024-12-13 | 101 | 73 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 0 | 0 | 102 | 74 | 102 | 74 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | Carlsbad | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-07 | 161 | 116 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2023-12-07 | 2023-12-12 | IOU Designed & Installed | N/A | No | N/A | -1025.45 | 1115 | Unknown | 842.08 | -3778 | 795.47 | Unknown | 3778.06 | -1025.45 | 4803.51 | Yes | N/A | N/A | 2023-12-07 | 2023-12-07 | 1 | 1 | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2023-12-15 | 1900-01-03 | 4 | 2023-12-15 | 2023-12-15 | 1 | 1 | 1 | 1 | 5 | 5 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 102.4 | 102.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | 2024-12-02 | IOU Designed & Installed | N/A | No | N/A | 2362.26 | 628.4 | Unknown | Unknown | Unknown | 1733.86 | 3981 | 1619.31 | 2362.26 | -742.95 | Yes | N/A | N/A | 2024-11-05 | 2024-11-05 | 1 | 1 | 2024-11-05 | 2024-11-05 | 1 | 1 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2024-12-02 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2024-12-20 | 1900-01-18 | 15 | 2024-12-20 | 2024-12-20 | 1 | 1 | 29 | 21 | 21 | 17 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | -618 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-14 | 2023-04-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.83 | -11.31 | Unknown | Unknown | Unknown | 7.48 | 3981 | 727.47 | -3.83 | 731.3 | Yes | N/A | N/A | 2023-04-14 | 2023-05-01 | 18 | 12 | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-12 | Unknown | Unknown | 2023-07-12 | 2023-07-12 | 1 | 1 | 18 | 12 | 1 | 1 | 19 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | 87 | 87 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-12 | -492 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-05 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 1342.83 | Unknown | Unknown | Unknown | 4.46 | 1338.37 | 3981 | 1080.07 | 1342.83 | -262.76 | Yes | N/A | N/A | 2024-06-05 | 2024-06-12 | 8 | 6 | 2024-06-12 | 2024-06-20 | 9 | 7 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-07-25 | 30 | 22 | Unknown | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-08-07 | 1900-01-13 | 10 | 2024-08-07 | 2024-08-07 | 1 | 1 | 38 | 28 | 24 | 18 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | -596 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | 2025-03-12 | IOU Designed & Installed | N/A | No | N/A | 911.75 | -11.21 | Unknown | Unknown | 15.35 | 907.61 | 3981 | 1221.31 | 911.75 | 309.56 | Yes | N/A | N/A | 2024-12-05 | 2024-11-26 | Unknown | Unknown | 2024-11-26 | 2024-12-11 | 16 | 12 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2025-03-12 | 92 | 66 | Unknown | 2025-02-20 | Unknown | Unknown | 2025-03-12 | 2025-04-02 | 1900-01-21 | 16 | 2025-04-02 | 2025-04-02 | 1 | 1 | 92 | 66 | 39 | 29 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-30 | 162 | 117 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 614.64 | -11.16 | Unknown | Unknown | Unknown | 625.8 | 3981 | 1695.25 | 614.64 | 1080.61 | Yes | N/A | N/A | 2025-01-22 | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2025-01-28 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-11 | 21 | 15 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | Unknown | Unknown | 2025-03-11 | 2025-03-11 | 1 | 1 | 0 | 0 | 119 | 85 | 119 | 85 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 15.4 | 15.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-13 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | 2024-04-01 | IOU Designed & Installed | N/A | No | N/A | -4.94 | -4.96 | Unknown | Unknown | Unknown | 0.02 | Unknown | 158.79 | -4.94 | 163.73 | Yes | N/A | N/A | 2023-11-27 | 2023-07-21 | Unknown | Unknown | 2023-07-21 | 2023-12-15 | 148 | 106 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2024-04-01 | 109 | 77 | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-05-06 | 1900-02-04 | 26 | 2024-05-06 | 2024-05-06 | 1 | 1 | 109 | 77 | 185 | 133 | 294 | 210 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-03-18 | 1427 | 1020 | No | 2019-10-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2019-10-05 | 2019-10-05 | 2024-02-12 | IOU Designed & Installed | N/A | Yes | 1567 | 1060.7 | 281.3 | Unknown | Unknown | Unknown | 779.4 | Unknown | 153.49 | 1060.7 | -907.21 | Yes | N/A | N/A | 2019-10-05 | 2024-01-19 | 1568 | 1120 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2019-11-07 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-02-13 | 1900-01-01 | 2 | 2024-02-13 | 2024-02-13 | 1 | 1 | 1568 | 1120 | 3 | 3 | 1571 | 1123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-09 | -659 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-25 | 2024-10-28 | 2024-12-19 | IOU Designed & Installed | N/A | No | N/A | 2701.87 | 157.05 | Unknown | Unknown | Unknown | 2544.82 | 3981 | 1481.99 | 2701.87 | -1219.88 | Yes | N/A | N/A | 2024-10-25 | 2024-10-28 | 4 | 2 | 2024-10-28 | 2024-10-28 | 1 | 1 | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-12-19 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2024-12-19 | 1899-12-31 | 1 | 2024-12-19 | 2024-12-19 | 1 | 1 | 57 | 41 | 3 | 3 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-19 | -120 | -87 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2283.96 | Unknown | Unknown | Unknown | Unknown | 2283.96 | 3981 | 902.73 | 2283.96 | -1381.23 | Yes | N/A | N/A | 2024-07-18 | 2024-07-19 | 2 | 2 | 2024-07-19 | 2024-07-19 | 1 | 1 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-02-19 | 1 | 1 | 2 | 2 | 2 | 2 | 4 | 4 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 705.05 | 705.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-06 | -594 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-21 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 2414.7 | Unknown | Unknown | Unknown | 7.86 | 2406.84 | 3981 | 1376.32 | 2414.7 | -1038.38 | Yes | N/A | N/A | 2025-01-21 | 2025-01-09 | Unknown | Unknown | 2025-01-09 | 2025-01-23 | 15 | 11 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-05-12 | 110 | 78 | Unknown | 2025-04-23 | Unknown | Unknown | 2025-05-12 | 2025-05-22 | 1900-01-10 | 9 | 2025-05-22 | 2025-05-22 | 1 | 1 | 110 | 78 | 27 | 21 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-23 | 167 | 120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 963.02 | -27.69 | Unknown | Unknown | Unknown | 990.71 | Unknown | 223 | 963.02 | -740.02 | Yes | N/A | N/A | 2024-02-02 | 2024-03-26 | 54 | 38 | 2024-03-26 | 2024-05-20 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-07-12 | 31 | 23 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | 2024-08-08 | 2024-08-08 | 1 | 1 | 54 | 38 | 88 | 64 | 142 | 102 | Steps 2,3,5,6,7 | 53 | 39 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | 1872 | 1339 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-11-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 667.6 | -19.43 | Unknown | Unknown | Unknown | 687.03 | Unknown | 105.49 | 667.6 | -562.11 | Yes | N/A | N/A | 2023-10-10 | 2023-10-11 | 2 | 2 | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-02-15 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -684 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-07-22 | 2024-07-24 | IOU Designed & Installed | N/A | No | N/A | 1350.76 | 468.5 | Unknown | Unknown | Unknown | 882.26 | 3981 | 1447.53 | 1350.76 | 96.77 | Yes | N/A | N/A | 2024-07-22 | 2024-07-22 | 1 | 1 | 2024-07-22 | 2024-07-22 | 1 | 1 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-07-24 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-08-16 | 1900-01-23 | 18 | 2024-08-16 | 2024-08-16 | 1 | 1 | 3 | 3 | 26 | 20 | 29 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-18 | -337 | -242 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2024-12-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 394.56 | -7.76 | Unknown | Unknown | Unknown | 402.32 | Unknown | 1906.67 | 394.56 | 1512.11 | Yes | N/A | N/A | 2024-12-18 | 2024-12-12 | Unknown | Unknown | 2024-12-12 | 2025-02-19 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-01-25 | 23 | 16 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | 2025-03-18 | 2025-03-18 | 1 | 1 | 0 | 0 | 94 | 67 | 94 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-13 | -425 | -304 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 9.98 | -8.83 | Unknown | Unknown | Unknown | 18.81 | 3981 | 854.03 | 9.98 | 844.05 | Yes | N/A | N/A | 2023-09-29 | 2023-07-23 | Unknown | Unknown | 2023-07-23 | 2023-10-12 | 82 | 59 | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-05-14 | 1 | 1 | 0 | 0 | 83 | 60 | 83 | 60 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 189.05 | 189.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-10 | -372 | -267 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | 2024-06-24 | IOU Designed & Installed | N/A | No | N/A | 2472.53 | 493.36 | Unknown | 49.84 | Unknown | 1929.33 | 3981 | 655.96 | 2472.53 | -1816.57 | Yes | N/A | N/A | 2024-02-15 | 2024-02-15 | 1 | 1 | 2024-02-15 | 2024-02-15 | 1 | 1 | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-06-24 | 126 | 90 | Unknown | 2024-06-10 | Unknown | Unknown | 2024-06-24 | 2024-07-03 | 1900-01-09 | 8 | 2024-07-03 | 2024-07-03 | 1 | 1 | 127 | 91 | 12 | 10 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-06 | -549 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-03-28 | 2024-05-07 | IOU Designed & Installed | N/A | No | N/A | -8.43 | -6.83 | Unknown | Unknown | Unknown | -1.6 | Unknown | Not available | -8.43 | Unknown | Yes | N/A | N/A | 2024-03-26 | 2023-12-13 | Unknown | Unknown | 2023-12-13 | 2024-04-01 | 111 | 79 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-05-07 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-06-05 | 1900-01-29 | 22 | 2024-06-05 | 2024-06-05 | 1 | 1 | 37 | 27 | 142 | 102 | 179 | 129 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 22.05 | 22.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | 167 | 120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-11 | 2024-01-24 | IOU Designed & Installed | N/A | No | N/A | 4.73 | -5.76 | Unknown | Unknown | Unknown | 10.49 | 3941 | 211.5 | 4.73 | 206.77 | Yes | N/A | N/A | 2023-07-11 | 2023-05-05 | Unknown | Unknown | 2023-05-05 | 2023-07-11 | 68 | 48 | 2023-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | 2024-01-24 | 198 | 142 | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-02-16 | 1900-01-23 | 18 | 2024-02-16 | 2024-02-15 | Unknown | Unknown | 198 | 142 | 92 | 66 | 290 | 208 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-22 | 339 | 242 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | 2024-02-27 | 2024-08-06 | IOU Designed & Installed | N/A | No | N/A | 5196.7 | Unknown | Unknown | Unknown | Unknown | 5196.7 | 359426 | 5296.29 | 5196.7 | 99.59 | Yes | N/A | N/A | 2024-02-27 | 2024-03-23 | 26 | 19 | 2024-03-23 | 2024-06-04 | 74 | 52 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-07-23 | 50 | 36 | Unknown | 2024-07-29 | Unknown | Unknown | 2024-08-06 | 2024-09-04 | 1900-01-29 | 22 | 2024-09-04 | 2024-08-26 | Unknown | Unknown | 76 | 55 | 104 | 74 | 180 | 129 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 176.05 | 176.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-06 | -79 | -58 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2023-05-25 | 2023-07-05 | IOU Designed & Installed | N/A | No | N/A | -469.15 | -24.15 | Unknown | Unknown | -461 | 16 | 3885 | 1020.71 | -469.15 | 1489.86 | Yes | N/A | N/A | 2023-05-25 | 2023-05-25 | 1 | 1 | 2023-05-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | 2023-07-05 | 35 | 25 | Unknown | 2023-06-30 | Unknown | Unknown | 2023-07-05 | 2023-07-19 | 1900-01-14 | 11 | 2023-07-19 | 2023-07-19 | 1 | 1 | 36 | 26 | 16 | 12 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-09-07 | 1047 | 750 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2019-09-16 | 2019-09-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 579.06 | -6.85 | Unknown | Unknown | 11.35 | 574.56 | 7962 | 583.57 | 579.06 | 4.51 | Yes | N/A | N/A | 2019-09-16 | 2023-02-16 | 1250 | 894 | 2023-02-16 | 2023-02-27 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-27 | 2023-06-13 | 107 | 77 | Unknown | 2023-06-22 | Unknown | Unknown | Unknown | 2023-09-29 | Unknown | Unknown | 2023-09-29 | 2023-07-21 | Unknown | Unknown | 1357 | 971 | 12 | 8 | 1369 | 979 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 52 | 52 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-19 | 137 | 98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-12 | 2023-05-12 | 2025-04-21 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1894.3 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-12 | 2023-05-12 | 1 | 1 | 2023-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2025-04-21 | 496 | 354 | Unknown | 2025-04-10 | Unknown | Unknown | 2025-04-21 | 2025-05-05 | 1900-01-14 | 11 | 2025-05-05 | 2025-05-05 | 1 | 1 | 497 | 355 | 16 | 12 | 513 | 367 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-07 | -389 | -278 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2024-02-07 | 2024-08-13 | IOU Designed & Installed | N/A | No | N/A | 369.47 | 120.84 | Unknown | Unknown | Unknown | 248.63 | 3981 | 992.24 | 369.47 | 622.77 | Yes | N/A | N/A | 2023-12-15 | 2023-12-05 | Unknown | Unknown | 2023-12-05 | 2024-02-07 | 65 | 47 | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-08-13 | 189 | 135 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-08-14 | 1900-01-01 | 2 | 2024-08-14 | 2024-08-14 | 1 | 1 | 189 | 135 | 68 | 50 | 257 | 185 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-11-12 | 1359 | 972 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-24 | 2023-10-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 30181.68 | 11291.24 | Unknown | Unknown | Unknown | 18890.44 | 0 | 22907.05 | 30181.68 | -7274.63 | Yes | N/A | N/A | 2021-10-24 | 2023-09-01 | 678 | 485 | 2023-09-01 | 2023-10-25 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | 2024-05-29 | 218 | 156 | Unknown | 2024-06-24 | Unknown | Unknown | Unknown | 2024-08-05 | Unknown | Unknown | 2024-08-05 | 2024-08-02 | Unknown | Unknown | 896 | 641 | 55 | 39 | 951 | 680 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-19 | -529 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2025-02-19 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 1934.01 | Unknown | Unknown | Unknown | 6.6 | 1927.41 | 3981 | 1305.81 | 1934.01 | -628.2 | Yes | N/A | N/A | 2024-11-13 | 2025-02-18 | 98 | 70 | 2025-02-18 | 2025-02-24 | 7 | 5 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-04-02 | 38 | 28 | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-02 | 2025-04-08 | 1900-01-06 | 5 | 2025-04-08 | 2025-04-08 | 1 | 1 | 136 | 98 | 15 | 11 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN MARCOS | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-15 | 224 | 161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-26 | 2024-06-21 | IOU Designed & Installed | N/A | No | N/A | 785.94 | -2.89 | Unknown | Unknown | Unknown | 788.83 | 3981 | 383.06 | 785.94 | -402.88 | Yes | N/A | N/A | 2024-02-15 | 2024-02-15 | 1 | 1 | 2024-02-15 | 2024-03-15 | 30 | 22 | 2024-04-15 | 2024-04-15 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-06-13 | 91 | 65 | Unknown | 2024-06-19 | Unknown | Unknown | 2024-06-21 | 2024-06-27 | 1900-01-06 | 5 | 2024-06-27 | 2024-06-26 | Unknown | Unknown | 93 | 67 | 37 | 27 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-19 | -174 | -125 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 2270.26 | 2450.5 | Unknown | 83.55 | -1403 | 1139.21 | Unknown | 1403.24 | 2270.26 | -867.02 | Yes | N/A | N/A | 2024-05-15 | 2024-05-29 | 15 | 11 | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-09-26 | 1900-01-03 | 4 | 2024-09-26 | 2024-09-26 | 1 | 1 | 15 | 11 | 5 | 5 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-11 | -508 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-06 | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 845.1 | Unknown | Unknown | Unknown | Unknown | 845.1 | 3981 | 1109.05 | 845.1 | 263.95 | Yes | N/A | N/A | 2024-06-03 | 2024-05-16 | Unknown | Unknown | 2024-05-16 | 2025-03-06 | 295 | 211 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-08-14 | 70 | 50 | Unknown | 2024-08-09 | Unknown | Unknown | 2024-08-14 | 2024-08-21 | 1900-01-07 | 6 | 2024-08-21 | 2024-08-21 | 1 | 1 | 70 | 50 | 304 | 218 | 374 | 268 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | -574 | -411 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-10-15 | 2025-01-08 | IOU Designed & Installed | N/A | No | N/A | 500.73 | -10.2 | Unknown | Unknown | Unknown | 510.93 | Unknown | 1462.19 | 500.73 | 961.46 | Yes | N/A | N/A | 2024-09-11 | 2024-10-08 | 28 | 20 | 2024-10-08 | 2024-10-15 | 8 | 6 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2025-01-08 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-22 | 1900-01-14 | 11 | 2025-01-22 | 2025-01-22 | 1 | 1 | 114 | 82 | 24 | 18 | 138 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | -691 | -494 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-09 | 2024-08-27 | IOU Designed & Installed | N/A | No | N/A | 1793.62 | 517.88 | Unknown | Unknown | Unknown | 1275.74 | 3981 | 1521.7 | 1793.62 | -271.92 | Yes | N/A | N/A | 2024-08-09 | 2024-08-09 | 1 | 1 | 2024-08-09 | 2024-08-09 | 1 | 1 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-08-27 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-06 | 1900-01-10 | 9 | 2024-09-06 | 2024-09-06 | 1 | 1 | 20 | 14 | 13 | 11 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 520.05 | 520.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-12 | -584 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-12-18 | 2024-12-23 | IOU Designed & Installed | N/A | No | N/A | 1091.38 | 253.74 | Unknown | 80.45 | Unknown | 757.19 | 3981 | 1697.79 | 1091.38 | 606.41 | Yes | N/A | N/A | 2024-10-10 | 2024-12-10 | 62 | 44 | 2024-12-10 | 2024-12-18 | 9 | 7 | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2024-12-23 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-02-05 | 1900-02-13 | 33 | 2025-02-05 | 2025-02-05 | 1 | 1 | 68 | 48 | 55 | 41 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-20 | -489 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-03-21 | 2023-06-15 | IOU Designed & Installed | N/A | No | N/A | -3.36 | -9.92 | Unknown | Unknown | Unknown | 6.56 | 3981 | 952.55 | -3.36 | 955.91 | Yes | N/A | N/A | 2023-03-13 | 2023-03-23 | 11 | 9 | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | 2023-06-15 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | 2023-09-19 | 1900-04-06 | 69 | 2023-09-19 | 2023-09-19 | 1 | 1 | 96 | 70 | 98 | 70 | 194 | 140 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 124.05 | 124.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-15 | -466 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-18 | 2024-03-22 | IOU Designed & Installed | N/A | No | N/A | 843.05 | 493.36 | Unknown | 9.1 | Unknown | 340.59 | Unknown | 163.83 | 843.05 | -679.22 | Yes | N/A | N/A | 2024-03-12 | 2024-02-05 | Unknown | Unknown | 2024-02-05 | 2024-03-18 | 43 | 31 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | 2024-03-22 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-05-06 | 1900-02-14 | 32 | 2024-05-06 | 2024-05-06 | 1 | 1 | 5 | 5 | 90 | 64 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | -201 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-06-30 | IOU Designed & Installed | N/A | No | N/A | 924.43 | -14.7 | Unknown | Unknown | -319.39 | 1258.52 | Unknown | 934.84 | 924.43 | 10.41 | Yes | N/A | N/A | 2023-03-20 | 2023-03-29 | 10 | 8 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | 2023-06-30 | 45 | 33 | Unknown | 2023-06-20 | Unknown | Unknown | 2023-06-30 | 2023-07-14 | 1900-01-14 | 11 | 2023-07-14 | 2023-07-14 | 1 | 1 | 55 | 41 | 16 | 12 | 71 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-06 | -429 | -306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-06-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.87 | -3.59 | Unknown | Unknown | Unknown | 1.72 | Unknown | 429.05 | -1.87 | 430.92 | Yes | N/A | N/A | 2023-05-30 | 2023-05-31 | 2 | 2 | 2023-05-31 | 2023-07-18 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2024-02-02 | 1 | 1 | 2 | 2 | 50 | 36 | 52 | 38 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-07 | -578 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2023-11-28 | IOU Designed & Installed | N/A | No | N/A | 723.25 | 442.68 | Unknown | Unknown | Unknown | 280.57 | Unknown | 158.14 | 723.25 | -565.11 | Yes | N/A | N/A | 2023-09-29 | 2023-10-31 | 33 | 23 | 2023-10-31 | 2023-10-31 | 1 | 1 | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2023-11-28 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2023-12-07 | 1900-01-09 | 8 | 2023-12-07 | 2023-12-07 | 1 | 1 | 62 | 44 | 12 | 10 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-01 | 566 | 405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-02-23 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 561.47 | -4.06 | Unknown | Unknown | 20.62 | 544.91 | 6691 | 605.22 | 561.47 | 43.75 | Yes | N/A | N/A | 2024-02-23 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-05-03 | 81 | 59 | 2024-02-27 | 2024-03-12 | 15 | 11 | 2024-02-23 | 2024-03-20 | 14 | 10 | 2024-05-03 | 2024-06-05 | 34 | 24 | Unknown | 2024-05-17 | Unknown | Unknown | 2024-06-10 | 2024-06-20 | 1900-01-10 | 9 | 2024-06-20 | 2024-06-19 | Unknown | Unknown | 49 | 35 | 106 | 78 | 155 | 113 | Steps 2,3,5,6,7 | 84 | 60 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-17 | -559 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-24 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1736.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-21 | 4 | 4 | 2025-02-21 | 2025-02-24 | 4 | 2 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-06-03 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-06 | 1900-01-03 | 4 | 2025-06-06 | 2025-06-06 | 1 | 1 | 104 | 76 | 9 | 7 | 113 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | 415 | 298 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-18 | 2022-07-18 | 2024-04-11 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -4702.81 | 111.67 | Unknown | Unknown | -13330 | 8515.52 | Unknown | 13330.49 | -4702.81 | 18033.3 | Yes | N/A | N/A | 2022-07-18 | 2023-09-06 | 416 | 298 | 2023-09-06 | 2024-04-03 | 211 | 151 | 2023-09-19 | 2024-04-03 | 31 | 23 | 2023-10-17 | 2024-04-01 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-04-19 | 1900-01-08 | 7 | 2024-04-19 | 2024-04-19 | 1 | 1 | 447 | 321 | 231 | 167 | 678 | 488 | Steps 2,3,5,6,7 | 366 | 262 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | 391 | 280 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-23 | 2024-11-22 | IOU Designed & Installed | N/A | No | N/A | -1924.72 | 623.21 | Unknown | 753.67 | -3555 | 253.4 | Unknown | 3555.08 | -1924.72 | 5479.8 | Yes | N/A | N/A | 2024-10-23 | 2024-10-30 | 8 | 6 | 2024-10-30 | 2024-11-18 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2024-11-26 | 1900-01-04 | 3 | 2024-11-26 | 2024-11-26 | 1 | 1 | 8 | 6 | 26 | 18 | 34 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | -558 | -399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | 2025-06-19 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 3270.19 | Unknown | Unknown | Unknown | Unknown | 3270.19 | 3981 | Not available | 3270.19 | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-10-22 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2025-09-09 | 323 | 231 | Unknown | 2025-06-02 | Unknown | Unknown | 2025-06-19 | 2025-06-21 | 1900-01-02 | 2 | 2025-06-21 | 2025-06-21 | 1 | 0 | 323 | 231 | 52 | 36 | 375 | 267 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-12 | -443 | -318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-12 | 2024-05-06 | IOU Designed & Installed | N/A | No | N/A | 19.47 | -17.28 | Unknown | Unknown | Unknown | 36.75 | Unknown | 788.38 | 19.47 | 768.91 | Yes | N/A | N/A | 2024-01-02 | 2024-01-12 | 11 | 9 | 2024-01-12 | 2024-01-12 | 1 | 1 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | 2024-05-06 | 116 | 82 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-06-26 | 1900-02-20 | 38 | 2024-06-26 | 2024-06-26 | 1 | 1 | 127 | 91 | 54 | 40 | 181 | 131 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 56.75 | 56.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-31 | -292 | -209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 33.96 | Unknown | Unknown | Unknown | Unknown | 33.96 | 3981 | 724.9 | 33.96 | 690.94 | Yes | N/A | N/A | 2023-10-13 | 2023-10-13 | 1 | 1 | 2023-10-13 | 2023-10-13 | 1 | 1 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-11-12 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-26 | -693 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | 2024-09-27 | IOU Designed & Installed | N/A | No | N/A | 656.09 | 377.04 | Unknown | 11.65 | Unknown | 267.4 | Unknown | 197.01 | 656.09 | -459.08 | Yes | N/A | N/A | 2024-09-23 | 2024-09-26 | 4 | 4 | 2024-09-26 | 2024-09-26 | 1 | 1 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-09-27 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-10-02 | 1900-01-05 | 4 | 2024-10-02 | 2024-10-02 | 1 | 1 | 6 | 6 | 8 | 6 | 14 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-20 | -373 | -267 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-06-24 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 12481 | 511.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-24 | 2024-06-20 | Unknown | Unknown | 2024-06-20 | 2024-06-24 | 5 | 3 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2025-06-11 | 353 | 253 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-12 | 1900-01-01 | 2 | 2025-06-12 | 2025-06-12 | 1 | 1 | 353 | 253 | 8 | 6 | 361 | 259 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-05 | -478 | -343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-08-30 | 2024-01-24 | IOU Designed & Installed | N/A | No | N/A | -10.68 | -9.61 | Unknown | Unknown | Unknown | -1.07 | Unknown | 153.83 | -10.68 | 164.51 | Yes | N/A | N/A | 2023-08-30 | 2023-09-13 | 15 | 11 | 2023-09-13 | 2023-09-18 | 6 | 4 | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | 2024-01-24 | 129 | 93 | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-02-13 | 1900-01-20 | 15 | 2024-02-13 | 2024-02-13 | 1 | 1 | 144 | 104 | 28 | 20 | 172 | 124 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | -492 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-05-15 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 1303.45 | Unknown | Unknown | Unknown | 124.22 | 1179.23 | 3981 | 1085.08 | 1303.45 | -218.37 | Yes | N/A | N/A | 2024-05-15 | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-05-31 | 68 | 50 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-08-28 | 91 | 65 | Unknown | 2024-08-19 | Unknown | Unknown | 2024-08-28 | 2025-05-08 | 1900-09-10 | 182 | 2025-05-08 | 2024-11-04 | Unknown | Unknown | 91 | 65 | 322 | 232 | 413 | 297 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | San Marcos | SAN MARCOS | 375.5 | 375.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-29 | 319 | 228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-03-24 | 2024-04-26 | IOU Designed & Installed | N/A | No | N/A | -3343.46 | 3298.42 | Unknown | Unknown | -24006 | 17364.12 | 0 | 24006.29 | -3343.46 | 27349.75 | Yes | N/A | N/A | 2023-01-24 | 2024-05-21 | 484 | 346 | 2024-05-21 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | 2024-04-23 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2024-05-13 | 1900-01-17 | 12 | 2024-05-13 | 2024-05-13 | 1 | 1 | 484 | 346 | 88 | 62 | 572 | 408 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | -675 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-01 | 2024-12-04 | IOU Designed & Installed | N/A | No | N/A | 3284.59 | 517.97 | Unknown | 75.37 | Unknown | 2691.25 | 3981 | 1658.05 | 3284.59 | -1626.54 | Yes | N/A | N/A | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | Unknown | Unknown | Unknown | 2024-11-04 | 2024-11-20 | 17 | 13 | 2024-11-01 | 2024-12-04 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | 2024-12-04 | 1899-12-31 | 1 | 2024-12-04 | 2024-12-04 | 1 | 1 | 35 | 25 | 20 | 16 | 55 | 41 | Steps 2,3,5,6,7 | 19 | 13 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | Encinitas | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-20 | -10 | -9 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-08-21 | 2023-09-22 | IOU Designed & Installed | N/A | No | N/A | -2886.84 | Unknown | Unknown | Unknown | -4800 | 1913.16 | Unknown | 4799.99 | -2886.84 | 7686.83 | Yes | N/A | N/A | 2023-06-30 | 2023-08-21 | 53 | 37 | 2023-08-21 | 2023-09-21 | 32 | 24 | 2023-09-11 | 2023-09-20 | 10 | 8 | 2023-09-21 | 2023-09-21 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2023-10-10 | 1900-01-18 | 13 | 2023-10-10 | 2023-10-10 | 1 | 1 | 63 | 45 | 53 | 39 | 116 | 84 | Steps 2,3,5,6,7 | 10 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-25 | -601 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | 2024-05-13 | 2024-06-25 | IOU Designed & Installed | N/A | No | N/A | 28.35 | Unknown | Unknown | Unknown | Unknown | 28.35 | Unknown | 842.51 | 28.35 | 814.16 | Yes | N/A | N/A | 2024-05-13 | 2024-05-13 | 1 | 1 | 2024-05-13 | 2024-05-15 | 3 | 3 | 2024-05-15 | 2024-07-19 | 2 | 2 | 2024-07-16 | 2024-07-25 | 10 | 8 | 2024-05-15 | 2024-06-25 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-08-01 | 1900-02-06 | 28 | 2024-08-01 | 2024-08-01 | 1 | 1 | 45 | 33 | 52 | 40 | 97 | 73 | Steps 2,3,5,6,7 | 74 | 54 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-11 | -125 | -90 | No | 2022-05-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-25 | 2022-05-28 | 2023-11-20 | IOU Designed & Installed | N/A | Yes | 307 | 0.64 | -8.54 | Unknown | Unknown | Unknown | 9.18 | 3981 | 727.49 | 0.64 | 726.85 | Yes | N/A | N/A | 2022-05-25 | 2023-03-28 | 308 | 220 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-05-28 | 2023-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2023-12-08 | 1900-01-18 | 15 | 2023-12-08 | 2023-12-08 | 1 | 1 | 308 | 220 | 20 | 16 | 328 | 236 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 13588.3 | 13588.3 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-01 | 65 | 48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-08-05 | 2024-11-13 | IOU Designed & Installed | N/A | No | N/A | 1816.21 | Unknown | Unknown | Unknown | 56.69 | 1759.52 | 3981 | 1082.67 | 1816.21 | -733.54 | Yes | N/A | N/A | 2024-07-23 | 2024-08-19 | 28 | 20 | 2024-08-19 | 2024-08-19 | 1 | 1 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-11-13 | 87 | 63 | Unknown | 2024-10-31 | Unknown | Unknown | 2024-11-13 | 2024-12-09 | 1900-01-26 | 19 | 2024-12-09 | 2024-12-05 | Unknown | Unknown | 115 | 83 | 28 | 20 | 143 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | -618 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 105.94 | -1.5 | Unknown | Unknown | Unknown | 107.44 | 3981 | 2308.3 | 105.94 | 2202.36 | Yes | N/A | N/A | 2025-01-07 | 2025-01-24 | 18 | 14 | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-04-02 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-09 | 1900-01-07 | 6 | 2025-04-09 | 2025-04-07 | Unknown | Unknown | 87 | 63 | 9 | 7 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 42.05 | 42.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-22 | -125 | -90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | 2024-04-30 | IOU Designed & Installed | N/A | No | N/A | 1761.81 | -11.7 | Unknown | Unknown | 32.53 | 1740.98 | 3981 | 1193.44 | 1761.81 | -568.37 | Yes | N/A | N/A | 2023-12-14 | 2023-11-14 | Unknown | Unknown | 2023-11-14 | 2024-02-20 | 99 | 71 | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-04-30 | 71 | 51 | Unknown | 2024-04-30 | Unknown | Unknown | 2024-04-30 | 2024-05-10 | 1900-01-10 | 9 | 2024-05-10 | 2024-05-20 | 11 | 7 | 71 | 51 | 121 | 87 | 192 | 138 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-31 | 472 | 339 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | 2024-02-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 944.15 | -17.9 | Unknown | Unknown | 1.07 | 960.98 | 25672.6 | 1506.38 | 944.15 | 562.23 | Yes | N/A | N/A | 2024-02-13 | 2023-12-25 | Unknown | Unknown | 2023-12-25 | 2024-09-24 | 275 | 197 | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-03-29 | 18 | 14 | 2024-09-24 | 2025-07-16 | 296 | 212 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-02-14 | Unknown | Unknown | 296 | 212 | 293 | 211 | 589 | 423 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 136.4 | 136.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-08 | -572 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-22 | 2023-08-10 | IOU Designed & Installed | N/A | No | N/A | 4677.15 | 1591.93 | Unknown | 314.82 | Unknown | 2770.4 | 3981 | 656.47 | 4677.15 | -4020.68 | Yes | N/A | N/A | 2023-06-07 | 2023-06-07 | 1 | 1 | 2023-06-07 | Unknown | Unknown | Unknown | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-08-10 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-08-14 | 1900-01-04 | 3 | 2023-08-14 | 2023-08-14 | 1 | 1 | 51 | 37 | 6 | 4 | 57 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-04 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 28.02 | Unknown | Unknown | Unknown | Unknown | 28.02 | Unknown | 1722.48 | 28.02 | 1694.46 | Yes | N/A | N/A | 2024-05-08 | 2024-03-13 | Unknown | Unknown | 2024-03-13 | 2024-05-31 | 80 | 58 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-06-03 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-07-23 | 1900-02-19 | 37 | 2024-07-23 | 2024-07-23 | 1 | 1 | 4 | 2 | 132 | 96 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-15 | -506 | -361 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-11 | 2025-06-19 | IOU Designed & Installed | N/A | No | N/A | 1006.88 | Unknown | Unknown | Unknown | Unknown | 1006.88 | 3981 | 1213.62 | 1006.88 | 206.74 | Yes | N/A | N/A | 2024-12-05 | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-12-11 | 22 | 16 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2025-06-19 | 191 | 137 | Unknown | 2025-06-18 | Unknown | Unknown | 2025-06-19 | 2025-06-27 | 1900-01-08 | 7 | 2025-06-27 | 2025-06-27 | 1 | 1 | 191 | 137 | 32 | 24 | 223 | 161 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | 9 | 6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-10-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4985.23 | -17.49 | Unknown | Unknown | -5109 | 141.26 | Unknown | 3087.11 | -4985.23 | 8072.34 | Yes | N/A | N/A | 2023-09-26 | 2023-09-21 | Unknown | Unknown | 2023-09-21 | 2023-11-13 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-05-08 | 51 | 37 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | 2024-06-10 | 2024-06-10 | 1 | 1 | 0 | 0 | 106 | 76 | 106 | 76 | Steps 2,3,5,6,7 | 177 | 127 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-30 | -221 | -160 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | 2024-10-16 | IOU Designed & Installed | N/A | No | N/A | 1034.59 | 317.18 | Unknown | Unknown | Unknown | 717.41 | Unknown | 1859.14 | 1034.59 | 824.55 | Yes | N/A | N/A | 2024-09-17 | 2024-09-17 | 1 | 1 | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-10-16 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-21 | 1900-01-05 | 4 | 2024-10-21 | 2024-10-21 | 1 | 1 | 31 | 23 | 7 | 5 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | 93 | 68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | 2023-01-31 | 2023-04-27 | IOU Designed & Installed | N/A | No | N/A | 482.07 | -16.56 | Unknown | Unknown | 21.46 | 477.17 | 3981 | 781.25 | 482.07 | 299.18 | Yes | N/A | N/A | 2023-01-30 | 2023-01-31 | 2 | 2 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-31 | 2023-04-27 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | 2023-10-17 | 1900-06-22 | 124 | 2023-10-17 | 2023-05-05 | Unknown | Unknown | 89 | 65 | 174 | 124 | 263 | 189 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | 79.05 | 79.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-23 | -536 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1865.6 | 1250.97 | Unknown | 838.7 | -4869.57 | 4645.5 | 3981 | 9044.38 | 1865.6 | 7178.78 | Yes | N/A | N/A | 2024-09-16 | 2024-08-28 | Unknown | Unknown | 2024-08-28 | 2025-01-08 | 134 | 96 | 2024-12-16 | 2024-12-16 | 1 | 1 | 2024-10-21 | 2025-02-28 | 11 | 9 | 2025-01-08 | 2025-03-03 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | 2025-04-03 | 2025-03-05 | Unknown | Unknown | 56 | 40 | 145 | 105 | 201 | 145 | Steps 2,3,5,6,7 | 130 | 94 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-03-18 | 946 | 677 | No | 2019-09-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2019-09-26 | 2019-09-26 | Unknown | IOU Designed & Installed | N/A | Yes | 1281 | 26.22 | Unknown | Unknown | Unknown | 26.22 | Unkonwn | 3241 | 479.08 | 26.22 | 452.86 | Yes | N/A | N/A | 2019-09-26 | 2023-03-30 | 1282 | 916 | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2020-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-10-20 | Unknown | Unknown | 2022-10-20 | 2022-10-20 | Unknown | Unknown | 1282 | 916 | 0 | 0 | 1282 | 916 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-19 | -96 | -70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1680.32 | 1401.66 | Unknown | Unknown | -3712 | 630.02 | Unknown | 3711.73 | -1680.32 | 5392.05 | Yes | N/A | N/A | 2023-11-21 | 2023-11-21 | 1 | 1 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 17910 | 17910 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-04-20 | -543 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-14 | 2023-10-20 | IOU Designed & Installed | N/A | No | N/A | 2044.9 | 432.24 | Unknown | Unknown | 1.86 | 1610.8 | 3961 | 986.6 | 2044.9 | -1058.3 | Yes | N/A | N/A | 2023-08-14 | 2023-09-08 | 26 | 20 | 2023-09-08 | 2023-09-08 | 1 | 1 | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | 2023-10-20 | 43 | 31 | Unknown | 2023-10-11 | Unknown | Unknown | 2023-10-20 | 2023-10-25 | 1900-01-05 | 4 | 2023-10-25 | 2023-10-25 | 1 | 1 | 69 | 51 | 8 | 6 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-16 | -246 | -176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 192.64 | 50.72 | Unknown | Unknown | 1.75 | 140.17 | 3981 | 596.87 | 192.64 | 404.23 | Yes | N/A | N/A | 2023-12-19 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2024-01-02 | 35 | 25 | 2024-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 0 | 0 | 36 | 26 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | 111.05 | 111.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-13 | -501 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-11-22 | IOU Designed & Installed | N/A | No | N/A | 1050.51 | -10.35 | Unknown | Unknown | 10.37 | 1050.49 | 3981 | 1414.08 | 1050.51 | 363.57 | Yes | N/A | N/A | 2023-04-20 | 2023-05-25 | 36 | 26 | 2023-05-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-25 | 2023-11-22 | 182 | 130 | Unknown | 2023-11-08 | Unknown | Unknown | 2023-11-22 | 2023-11-29 | 1900-01-07 | 6 | 2023-11-29 | 2023-11-29 | 1 | 1 | 218 | 156 | 9 | 7 | 227 | 163 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-11 | -152 | -109 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | 2024-03-09 | IOU Designed & Installed | N/A | No | N/A | 1747.68 | 469.06 | Unknown | 254 | Unknown | 1024.62 | 3981 | 2134.05 | 1747.68 | 386.37 | Yes | N/A | N/A | 2023-09-11 | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-11-13 | 84 | 60 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2024-03-09 | 118 | 85 | Unknown | 2024-01-10 | Unknown | Unknown | 2024-03-09 | 2024-03-12 | 1900-01-03 | 2 | 2024-03-12 | 2024-03-12 | 1 | 1 | 118 | 85 | 89 | 63 | 207 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-05-31 | 2024-06-26 | IOU Designed & Installed | N/A | No | N/A | 25.47 | Unknown | Unknown | Unknown | Unknown | 25.47 | 3981 | 1339.95 | 25.47 | 1314.48 | Yes | N/A | N/A | 2024-05-31 | 2024-02-23 | Unknown | Unknown | 2024-02-23 | 2024-05-31 | 99 | 71 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-06-26 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-07-23 | 1900-01-27 | 20 | 2024-07-23 | 2024-07-23 | 1 | 1 | 27 | 19 | 128 | 92 | 155 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-06 | -150 | -107 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | 2024-05-06 | IOU Designed & Installed | N/A | No | N/A | 1622.49 | 454.77 | Unknown | 160.29 | Unknown | 1007.43 | 3981 | 746.54 | 1622.49 | -875.95 | Yes | N/A | N/A | 2023-02-02 | 2023-02-02 | 1 | 1 | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-02 | 2024-05-06 | 460 | 328 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-05-09 | 1900-01-03 | 4 | 2024-05-09 | 2024-05-09 | 1 | 1 | 461 | 329 | 5 | 5 | 466 | 334 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Residential | N/A | SB 1187-G1 Solana hlnds (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 611 | 437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | 2025-05-14 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 29010.85 | 12672.54 | Unknown | Unknown | 90.82 | 16247.49 | 127267 | 19427.9 | 29010.85 | -9582.95 | Yes | N/A | N/A | 2023-03-23 | 2024-01-31 | 315 | 225 | 2024-01-31 | 2024-07-31 | 183 | 131 | 2024-02-01 | 2024-05-20 | 110 | 78 | 2025-05-15 | 2025-05-16 | 2 | 2 | 2024-07-31 | Unknown | Unknown | Unknown | 2024-12-19 | 2025-05-13 | 146 | 104 | 2025-05-14 | 2025-06-17 | 1900-02-03 | 25 | 2025-06-17 | 2025-06-17 | 1 | 1 | 425 | 303 | 367 | 263 | 792 | 566 | Steps 2,3,5,6,7 | 470 | 336 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-06 | 653 | 468 | No | 2021-06-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-14 | 2021-06-14 | Unknown | IOU Designed & Installed | N/A | Yes | 777 | -7.84 | -5.68 | Unknown | Unknown | Unknown | -2.16 | 3885 | 453.49 | -7.84 | 461.33 | Yes | N/A | N/A | 2021-06-14 | 2024-01-18 | 949 | 679 | 2024-01-18 | 2023-07-31 | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | Unknown | Unknown | 2024-01-19 | 2024-01-19 | 1 | 1 | 949 | 679 | 1 | 1 | 950 | 680 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | -310 | -223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-03-24 | 2025-05-07 | IOU Designed & Installed | N/A | No | N/A | -2240.66 | 315.3 | Unknown | Unknown | -2768 | 212.04 | Unknown | 2768.14 | -2240.66 | 5008.8 | Yes | N/A | N/A | 2025-03-24 | 2025-03-24 | 1 | 1 | 2025-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-05-07 | 1899-12-31 | 1 | 2025-05-07 | 2025-05-07 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 7.05 | 7.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | -140 | -101 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-03-13 | 2025-05-22 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1974.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-23 | 2025-03-13 | 50 | 36 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-05-22 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-06-30 | 1900-02-08 | 28 | 2025-06-30 | 2025-06-05 | Unknown | Unknown | 121 | 87 | 40 | 28 | 161 | 115 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-08 | 357 | 256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-19 | 2023-04-24 | 2023-12-11 | IOU Designed & Installed | N/A | No | N/A | 82966.49 | 23982.34 | Unknown | Unknown | 197.22 | 58786.93 | 45804 | 38102.78 | 82966.49 | -44863.71 | Yes | N/A | N/A | 2022-10-19 | 2023-04-13 | 177 | 127 | 2023-04-13 | 2023-08-29 | 139 | 99 | 2023-05-24 | 2023-09-07 | 65 | 45 | 2023-05-11 | 2023-10-10 | 52 | 38 | 2023-08-29 | Unknown | Unknown | Unknown | 2023-09-08 | 2023-12-04 | 88 | 62 | 2023-12-11 | 2024-01-31 | 1900-02-20 | 38 | 2024-01-31 | 2024-01-31 | 1 | 1 | 242 | 172 | 332 | 238 | 574 | 410 | Steps 2,3,5,6,7 | 258 | 184 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | 376 | 269 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 2361.77 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-06-05 | Unknown | Unknown | 2024-06-05 | 2025-01-24 | 234 | 168 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-10 | 4 | 4 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | 2025-06-18 | 2025-06-18 | 1 | 1 | 0 | 0 | 239 | 173 | 239 | 173 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | -280 | -201 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | 2023-10-27 | IOU Designed & Installed | N/A | No | N/A | -16.78 | -13.4 | Unknown | Unknown | Unknown | -3.38 | Unknown | 153.22 | -16.78 | 170 | Yes | N/A | N/A | 2023-10-13 | 2023-09-12 | Unknown | Unknown | 2023-09-12 | 2023-10-13 | 32 | 24 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-10-27 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2023-11-09 | 1900-01-13 | 10 | 2023-11-09 | 2023-11-09 | 1 | 1 | 15 | 11 | 47 | 35 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-02 | -690 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 61.23 | Unknown | Unknown | Unknown | Unknown | 61.23 | Unknown | 1587.8 | 61.23 | 1526.57 | Yes | N/A | N/A | 2025-03-17 | 2025-03-06 | Unknown | Unknown | 2025-03-06 | 2025-03-17 | 12 | 8 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | 2025-04-11 | 2025-04-11 | 1 | 1 | 0 | 0 | 13 | 9 | 13 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-06 | -221 | -158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 640.97 | Unknown | Unknown | Unknown | 5.44 | 635.53 | 3981 | 1136.34 | 640.97 | 495.37 | Yes | N/A | N/A | 2024-06-26 | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-07-22 | 69 | 49 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-08-26 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-09-27 | 1900-02-01 | 25 | 2024-09-27 | 2024-09-27 | 1 | 1 | 55 | 39 | 103 | 75 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-20 | -633 | -453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-17 | 2023-12-15 | IOU Designed & Installed | N/A | No | N/A | 1447.12 | 489.8 | Unknown | Unknown | Unknown | 957.32 | 3981 | 207.39 | 1447.12 | -1239.73 | Yes | N/A | N/A | 2023-11-09 | 2023-11-16 | 8 | 6 | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-11-16 | Unknown | Unknown | Unknown | 2023-11-17 | 2023-11-21 | 5 | 3 | 2023-11-21 | 2023-12-15 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2023-12-27 | 1900-01-12 | 9 | 2023-12-27 | 2023-12-27 | 1 | 1 | 33 | 25 | 20 | 14 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 19.05 | 19.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-26 | -432 | -309 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-16 | 2025-06-17 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2620.81 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-07 | 2025-04-01 | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-06-17 | 63 | 45 | Unknown | 2025-06-17 | Unknown | Unknown | 2025-06-17 | 2025-06-20 | 1900-01-03 | 4 | 2025-06-20 | 2025-06-20 | 1 | 1 | 63 | 45 | 5 | 5 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | -281 | -201 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-02-14 | 2025-02-28 | IOU Designed & Installed | N/A | No | N/A | -6.73 | -28.12 | Unknown | Unknown | Unknown | 21.39 | 3981 | 1803.73 | -6.73 | 1810.46 | Yes | N/A | N/A | 2025-01-30 | 2025-01-27 | Unknown | Unknown | 2025-01-27 | 2025-02-14 | 19 | 15 | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-02-28 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-04-04 | 1900-02-04 | 26 | 2025-04-04 | 2025-04-04 | 1 | 1 | 15 | 11 | 56 | 42 | 71 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-07 | -682 | -488 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | -6.62 | -12.85 | Unknown | Unknown | Unknown | 6.23 | Unknown | 827.92 | -6.62 | 834.54 | Yes | N/A | N/A | 2023-06-13 | 2023-06-13 | 1 | 1 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | 2023-07-26 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-07-26 | 1899-12-31 | 1 | 2023-07-26 | 2023-07-26 | 1 | 1 | 45 | 33 | 2 | 2 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 142 | 142 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | 593 | 424 | No | 2023-05-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-05-19 | Unknown | IOU Designed & Installed | N/A | Yes | 301 | 10.65 | Unknown | Unknown | Unknown | Unknown | 10.65 | 6481 | 479.76 | 10.65 | 469.11 | Yes | N/A | N/A | 2023-05-15 | 2024-03-11 | 302 | 216 | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | 2024-10-15 | 2024-10-14 | Unknown | Unknown | 302 | 216 | 0 | 0 | 302 | 216 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | -664 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-04 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | 30.19 | Unknown | Unknown | Unknown | Unknown | 30.19 | Unknown | 1465.07 | 30.19 | 1434.88 | Yes | N/A | N/A | 2024-09-03 | 2024-09-03 | 1 | 1 | 2024-09-03 | 2024-09-04 | 2 | 2 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-10-08 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-17 | 1900-01-09 | 8 | 2024-10-17 | 2024-10-17 | 1 | 1 | 36 | 26 | 13 | 11 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 100 | 100 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-19 | -210 | -151 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8.46 | Unknown | Unknown | Unknown | Unknown | 8.46 | Unknown | 74.16 | 8.46 | 65.7 | Yes | N/A | N/A | 2024-05-17 | 2024-06-07 | 22 | 16 | 2024-06-07 | 2024-06-07 | 1 | 1 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-08-21 | 1 | 1 | 22 | 16 | 2 | 2 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-21 | -155 | -112 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-22 | 2023-01-31 | 2023-06-13 | IOU Designed & Installed | N/A | No | N/A | 780.63 | -25.5 | Unknown | Unknown | Unknown | 806.13 | 3981 | 1378.49 | 780.63 | 597.86 | Yes | N/A | N/A | 2022-12-22 | 2023-04-28 | 128 | 92 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | 2023-06-13 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | 2023-06-19 | 1900-01-06 | 5 | 2023-06-19 | 2023-06-19 | 1 | 1 | 134 | 96 | 8 | 6 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-04 | -584 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-28 | 2023-08-23 | IOU Designed & Installed | N/A | No | N/A | 662.71 | -10.4 | Unknown | Unknown | 1.79 | 671.32 | Unknown | 1194.58 | 662.71 | 531.87 | Yes | N/A | N/A | 2023-06-19 | 2023-07-18 | 30 | 22 | 2023-07-18 | 2023-07-18 | 1 | 1 | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-08-23 | 37 | 27 | Unknown | 2023-08-15 | Unknown | Unknown | 2023-08-23 | 2023-08-29 | 1900-01-06 | 5 | 2023-08-29 | 2023-08-29 | 1 | 1 | 67 | 49 | 9 | 7 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-03 | 49 | 35 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1828.78 | 6834.94 | Unknown | 629.66 | -8832 | 3196.18 | Unknown | 8832.31 | 1828.78 | 7003.53 | Yes | N/A | N/A | 2024-06-26 | 2024-06-18 | Unknown | Unknown | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-21 | Unknown | Unknown | 2024-09-21 | 2024-09-21 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Ysidro | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | 135 | 97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-05-09 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | 14134.49 | 6094.56 | Unknown | Unknown | -237.33 | 8277.26 | 185050 | 31333.21 | 14134.49 | 17198.72 | Yes | N/A | N/A | 2024-04-17 | 2024-03-18 | Unknown | Unknown | 2024-03-18 | Unknown | Unknown | Unknown | 2025-02-06 | 2025-03-03 | 26 | 18 | 2025-04-02 | 2025-04-21 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-06-10 | 1900-02-08 | 28 | 2025-06-10 | 2025-06-10 | 1 | 1 | 26 | 18 | 61 | 43 | 87 | 61 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 29 | 29 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-23 | -77 | -56 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | 2023-05-01 | 2023-11-16 | IOU Designed & Installed | N/A | No | N/A | 1243.05 | -18.88 | Unknown | Unknown | 3.09 | 1258.84 | 3981 | 1948.06 | 1243.05 | 705.01 | Yes | N/A | N/A | 2023-05-01 | 2023-06-16 | 47 | 35 | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | 2023-11-16 | 155 | 111 | Unknown | 2023-11-15 | Unknown | Unknown | 2023-11-16 | 2023-12-08 | 1900-01-22 | 17 | 2023-12-08 | 2023-12-08 | 1 | 1 | 202 | 146 | 24 | 18 | 226 | 164 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-30 | -353 | -254 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-30 | 2023-05-30 | IOU Designed & Installed | N/A | No | N/A | -3 | -8.83 | Unknown | Unknown | Unknown | 5.83 | 3941 | 526.05 | -3 | 529.05 | Yes | N/A | N/A | 2023-05-30 | 2023-05-30 | 1 | 1 | 2023-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | 2023-05-30 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | 2023-06-12 | 1900-01-13 | 10 | 2023-06-12 | 2023-06-12 | 1 | 1 | 2 | 2 | 15 | 11 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 193.05 | 193.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-31 | -540 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-09-13 | 2025-01-14 | IOU Designed & Installed | N/A | No | N/A | 33.93 | Unknown | Unknown | Unknown | Unknown | 33.93 | 3981 | 1605.16 | 33.93 | 1571.23 | Yes | N/A | N/A | 2024-08-21 | 2024-08-08 | Unknown | Unknown | 2024-08-08 | 2024-09-13 | 37 | 27 | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2025-01-14 | 124 | 88 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-02-06 | 1900-01-23 | 18 | 2025-02-06 | 2025-02-06 | 1 | 1 | 124 | 88 | 62 | 46 | 186 | 134 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 138.05 | 138.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | -638 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-21 | 2024-01-25 | IOU Designed & Installed | N/A | No | N/A | -5.9 | -4.78 | Unknown | Unknown | Unknown | -1.12 | Unknown | 515.81 | -5.9 | 521.71 | Yes | N/A | N/A | 2023-12-20 | 2023-12-21 | 2 | 2 | 2023-12-21 | 2023-12-21 | 1 | 1 | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-01-25 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-02-16 | 1900-01-22 | 17 | 2024-02-16 | 2024-02-16 | 1 | 1 | 38 | 28 | 25 | 19 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-03 | -632 | -453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-03 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1982.5 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-01 | 2025-03-19 | Unknown | Unknown | 2025-03-19 | 2025-04-03 | 16 | 12 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-05-12 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-06-09 | 1900-01-28 | 21 | 2025-06-09 | 2025-06-09 | 1 | 1 | 40 | 28 | 46 | 34 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 141.05 | 141.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-26 | -436 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2023-12-26 | 2024-05-09 | IOU Designed & Installed | N/A | No | N/A | 2143.92 | -12.98 | Unknown | Unknown | 38.19 | 2118.71 | 3981 | 1021.73 | 2143.92 | -1122.19 | Yes | N/A | N/A | 2023-12-26 | 2023-08-23 | Unknown | Unknown | 2023-08-23 | 2024-01-11 | 142 | 102 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-05-09 | 120 | 86 | Unknown | 2024-05-08 | Unknown | Unknown | 2024-05-09 | 2024-05-17 | 1900-01-08 | 7 | 2024-05-17 | 2024-05-16 | Unknown | Unknown | 120 | 86 | 151 | 109 | 271 | 195 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-18 | 916 | 655 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-24 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 24375.95 | 1762.66 | Unknown | Unknown | -7116.2 | 29729.49 | 6482 | 13751.89 | 24375.95 | -10624.06 | Yes | N/A | N/A | 2023-10-10 | 2023-08-30 | Unknown | Unknown | 2023-08-30 | 2024-02-16 | 171 | 123 | 2024-01-09 | 2024-02-09 | 15 | 13 | 2024-02-09 | 2024-08-09 | 4 | 0 | 2024-02-16 | 2024-12-05 | 294 | 210 | 2024-03-12 | 2024-10-25 | 228 | 164 | 2024-10-28 | 2025-03-14 | 1900-05-17 | 100 | 2025-03-14 | 2024-11-19 | Unknown | Unknown | 309 | 223 | 541 | 387 | 850 | 610 | Steps 2,3,5,6,7 | 481 | 345 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | 158.05 | 158.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | -70 | -51 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | 2024-09-19 | IOU Designed & Installed | N/A | No | N/A | 603.77 | 409.4 | Unknown | Unknown | -738 | 932.37 | 3241 | 1345.73 | 603.77 | 741.96 | Yes | N/A | N/A | 2023-03-31 | 2023-03-31 | 1 | 1 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2024-09-19 | 310 | 222 | Unknown | 2024-08-19 | Unknown | Unknown | 2024-09-19 | 2024-09-20 | 1900-01-01 | 2 | 2024-09-20 | 2024-09-20 | 1 | 1 | 311 | 223 | 3 | 3 | 314 | 226 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-03 | -298 | -214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-17 | 2025-01-17 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 4.71 | Unknown | Unknown | Unknown | Unknown | 4.71 | 3981 | 1545.38 | 4.71 | 1540.67 | Yes | N/A | N/A | 2025-01-17 | 2025-01-16 | Unknown | Unknown | 2025-01-16 | 2025-01-17 | 2 | 2 | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | 2025-01-27 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-03-11 | 1900-02-12 | 32 | 2025-03-11 | 2025-03-11 | 1 | 1 | 11 | 7 | 47 | 35 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | -518 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | 2023-11-16 | IOU Designed & Installed | N/A | No | N/A | 2606.29 | 511.35 | Unknown | Unknown | 16.13 | 2078.81 | 3981 | 661.64 | 2606.29 | -1944.65 | Yes | N/A | N/A | 2023-06-20 | 2023-06-19 | Unknown | Unknown | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2023-11-16 | 112 | 80 | Unknown | 2023-10-20 | Unknown | Unknown | 2023-11-16 | 2023-11-30 | 1900-01-14 | 11 | 2023-11-30 | 2023-11-29 | Unknown | Unknown | 112 | 80 | 15 | 11 | 127 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-08 | -487 | -348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-15 | 2023-08-01 | IOU Designed & Installed | N/A | No | N/A | -4.87 | -9.4 | Unknown | Unknown | Unknown | 4.53 | 3981 | 332.93 | -4.87 | 337.8 | Yes | N/A | N/A | 2023-03-06 | 2023-03-15 | 10 | 8 | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-16 | 2023-08-01 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-08-10 | 1900-01-09 | 8 | 2023-08-10 | 2023-08-09 | Unknown | Unknown | 149 | 107 | 10 | 8 | 159 | 115 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -12 | -9 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 313.42 | -32.51 | Unknown | Unknown | Unknown | 345.93 | 0 | 468.05 | 313.42 | 154.63 | Yes | N/A | N/A | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | 2025-03-19 | 323 | 231 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-13 | 28 | 20 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | 2025-04-11 | 2025-04-11 | 1 | 1 | 2 | 2 | 352 | 252 | 354 | 254 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | 522 | 522 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | 216 | 155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-08 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | 19936.08 | 3945.39 | Unknown | 3573.57 | 109.4 | 12307.72 | 0 | 18963.09 | 19936.08 | -972.99 | Yes | N/A | N/A | 2025-01-07 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | 2025-04-07 | 508 | 362 | 2024-04-23 | 2024-04-24 | 2 | 2 | 2025-01-31 | 2025-04-04 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-05-05 | 1900-01-28 | 21 | 2025-05-05 | 2025-05-05 | 1 | 1 | 2 | 2 | 602 | 430 | 604 | 432 | Steps 2,3,5,6,7 | 349 | 249 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-12 | -412 | -295 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-27 | 2023-07-27 | 2023-10-05 | IOU Designed & Installed | N/A | No | N/A | 689.32 | -10.92 | Unknown | Unknown | 10 | 690.24 | 3981 | 646.94 | 689.32 | -42.38 | Yes | N/A | N/A | 2023-07-27 | 2023-08-17 | 22 | 16 | 2023-08-17 | 2023-08-17 | 1 | 1 | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2023-10-05 | 50 | 36 | Unknown | 2023-10-04 | Unknown | Unknown | 2023-10-05 | 2023-11-27 | 1900-02-22 | 38 | 2023-11-27 | 2023-11-27 | 1 | 1 | 72 | 52 | 56 | 40 | 128 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-10 | -606 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | 2024-05-03 | IOU Designed & Installed | N/A | No | N/A | -12.64 | -10.27 | Unknown | Unknown | Unknown | -2.37 | Unknown | 917.98 | -12.64 | 930.62 | Yes | N/A | N/A | 2024-04-18 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-04-18 | 66 | 48 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-05-03 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-06-14 | 1900-02-11 | 31 | 2024-06-14 | 2024-06-14 | 1 | 1 | 16 | 12 | 110 | 80 | 126 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | 100 | 100 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-23 | -680 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 10.83 | Unknown | Unknown | Unknown | Unknown | 10.83 | Unknown | 1849.18 | 10.83 | 1838.35 | Yes | N/A | N/A | 2025-01-13 | 2024-12-27 | Unknown | Unknown | 2024-12-27 | 2025-01-14 | 19 | 13 | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | 2025-02-11 | 2025-02-11 | 1 | 1 | 0 | 0 | 20 | 14 | 20 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-11 | -519 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 851.02 | Unknown | Unknown | Unknown | -83.36 | 934.38 | Unknown | 278.35 | 851.02 | -572.67 | Yes | N/A | N/A | 2024-08-13 | 2024-09-05 | 24 | 18 | 2024-09-05 | 2024-09-05 | 1 | 1 | 2024-09-05 | 2024-12-31 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | 2025-01-09 | 2025-01-08 | Unknown | Unknown | 142 | 102 | 1 | 1 | 143 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | 40 | 29 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 629.3 | Unknown | Unknown | Unknown | Unknown | 629.3 | 29816 | 2953.86 | 629.3 | 2324.56 | Yes | N/A | N/A | 2024-10-07 | 2024-09-11 | Unknown | Unknown | 2024-09-11 | 2025-01-23 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | 2025-02-26 | 2025-02-26 | 1 | 1 | 0 | 0 | 136 | 98 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-15 | -221 | -159 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | 2023-08-30 | 2023-09-24 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 3557.66 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-24 | 2023-08-24 | 1 | 1 | 2023-08-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-24 | 2023-11-07 | 1900-02-13 | 32 | 2023-11-07 | 2023-11-07 | 1 | 1 | 1 | 1 | 46 | 33 | 47 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 31 | 31 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-18 | -585 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-07-26 | 2023-08-08 | IOU Designed & Installed | N/A | No | N/A | -6.2 | -11.96 | Unknown | Unknown | Unknown | 5.76 | 11943 | 911.81 | -6.2 | 918.01 | Yes | N/A | N/A | 2023-07-26 | 2023-04-04 | Unknown | Unknown | 2023-04-04 | 2023-07-26 | 114 | 82 | 2023-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-08-08 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | 2023-08-11 | 1900-01-03 | 4 | 2023-08-11 | 2023-08-11 | 1 | 1 | 14 | 10 | 119 | 87 | 133 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | OCEANSIDE | N/A | 20.1 | 20.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-17 | 624 | 447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-04-02 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -201.31 | Unknown | Unknown | Unknown | -260 | 58.69 | 258 | 462.26 | -201.31 | 663.57 | Yes | N/A | N/A | 2024-01-31 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2024-05-08 | 314 | 224 | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2025-01-14 | 259 | 185 | 2024-05-08 | 2024-12-19 | 226 | 162 | Unknown | 2025-01-14 | Unknown | Unknown | Unknown | 2025-01-28 | Unknown | Unknown | 2025-01-28 | 2025-04-01 | 64 | 46 | 226 | 162 | 637 | 455 | 863 | 617 | Steps 2,3,5,6,7 | 251 | 179 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-26 | -611 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-13 | 2024-10-13 | 2024-12-03 | IOU Designed & Installed | N/A | No | N/A | 39.15 | Unknown | Unknown | Unknown | Unknown | 39.15 | 3981 | 1498.54 | 39.15 | 1459.39 | Yes | N/A | N/A | 2024-10-13 | 2024-10-10 | Unknown | Unknown | 2024-10-10 | 2024-10-13 | 4 | 2 | 2024-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-13 | 2024-12-03 | 52 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2025-01-23 | 1900-02-20 | 38 | 2025-01-23 | 2025-01-23 | 1 | 1 | 52 | 37 | 57 | 41 | 109 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-18 | -251 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | Unknown | 2023-05-22 | IOU Designed & Installed | N/A | No | N/A | -3.72 | -10.95 | Unknown | Unknown | Unknown | 7.23 | 3981 | 941.91 | -3.72 | 945.63 | Yes | N/A | N/A | 2023-05-09 | 2023-05-09 | 1 | 1 | 2023-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-09 | 2023-05-22 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | 2023-06-12 | 1900-01-21 | 16 | 2023-06-12 | 2023-06-12 | 1 | 1 | 15 | 11 | 23 | 17 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -219 | -158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 13.59 | -12.04 | Unknown | Unknown | Unknown | 25.63 | 3981 | 881.94 | 13.59 | 868.35 | Yes | N/A | N/A | 2023-03-08 | 2023-11-27 | 265 | 189 | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2024-06-25 | Unknown | Unknown | 265 | 189 | 0 | 0 | 265 | 189 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | LA MESA | LA MESA | 8610 | 8610 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-01-17 | 76 | 55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-18 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | -17164.31 | 356.59 | Unknown | 41.64 | -18922 | 1359.46 | 0 | 18921.69 | -17164.31 | 36086 | Yes | N/A | N/A | 2024-03-06 | 2024-03-06 | 1 | 1 | 2024-03-06 | 2024-10-17 | 226 | 162 | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-10-24 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-03 | 1900-01-03 | 4 | 2025-04-03 | 2025-04-03 | 1 | 1 | 1 | 1 | 304 | 220 | 305 | 221 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-18 | 391 | 280 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-27 | 2023-11-17 | IOU Designed & Installed | N/A | No | N/A | 25323.93 | 6627.97 | Unknown | Unknown | Unknown | 18695.96 | Unknown | 1091.09 | 25323.93 | -24232.84 | Yes | N/A | N/A | 2023-10-20 | 2023-11-06 | 18 | 12 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2023-11-02 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2023-12-14 | 1900-01-27 | 20 | 2023-12-14 | 2023-12-14 | 1 | 1 | 18 | 12 | 36 | 26 | 54 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | -645 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-10-04 | 2025-02-14 | IOU Designed & Installed | N/A | No | N/A | -1139.97 | 265.74 | Unknown | Unknown | -2276 | 870.29 | Unknown | Not available | -1139.97 | Unknown | Yes | N/A | N/A | 2024-06-25 | 2024-07-09 | 15 | 11 | 2024-07-09 | 2024-07-09 | 1 | 1 | 2024-07-09 | 2025-01-02 | 178 | 128 | 2024-10-09 | 2024-10-25 | 17 | 13 | 2025-01-06 | 2025-02-14 | 40 | 30 | Unknown | 2025-02-03 | Unknown | Unknown | 2025-02-14 | 2025-02-24 | 1900-01-10 | 7 | 2025-02-24 | 2025-02-24 | 1 | 1 | 233 | 169 | 30 | 22 | 263 | 191 | Steps 2,3,5,6,7 | 85 | 61 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | -649 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | 2024-01-18 | IOU Designed & Installed | N/A | No | N/A | 14.86 | -18.79 | Unknown | Unknown | Unknown | 33.65 | Unknown | 1065.88 | 14.86 | 1051.02 | Yes | N/A | N/A | 2023-12-19 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | 2023-12-19 | 33 | 23 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-01-18 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-01-29 | 1900-01-11 | 8 | 2024-01-29 | 2024-01-29 | 1 | 1 | 31 | 23 | 46 | 32 | 77 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | CORONADO | 136 | 136 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | 17 | 13 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2024-05-02 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | -1637.96 | Unknown | Unknown | Unknown | -2021 | 383.04 | 0 | 1883.55 | -1637.96 | 3521.51 | Yes | N/A | N/A | 2023-11-20 | 2024-03-21 | 123 | 89 | 2024-03-21 | 2024-11-08 | 233 | 167 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-07-24 | 16 | 12 | 2024-11-08 | 2025-05-14 | 188 | 134 | Unknown | 2025-03-06 | Unknown | Unknown | 2025-06-18 | 2025-06-19 | 1900-01-01 | 2 | 2025-06-19 | 2025-06-18 | Unknown | Unknown | 311 | 223 | 251 | 181 | 562 | 404 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Underserved Community | Escondido | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | 450 | 323 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-03-16 | 2024-09-26 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -15637.71 | 799.13 | Unknown | Unknown | -34009 | 17572.16 | 0 | 34872.83 | -15637.71 | 50510.54 | Yes | N/A | N/A | 2023-03-16 | 2023-06-29 | 106 | 76 | 2023-06-29 | 2023-10-31 | 125 | 89 | 2023-07-14 | 2023-09-08 | 57 | 41 | 2023-05-03 | 2024-05-22 | 44 | 32 | 2023-10-31 | Unknown | Unknown | Unknown | 2023-11-08 | 2024-09-17 | 315 | 225 | 2024-09-26 | 2025-03-26 | 1900-06-30 | 130 | 2025-03-26 | 2025-03-26 | 1 | 1 | 163 | 117 | 667 | 477 | 830 | 594 | Steps 2,3,5,6,7 | 441 | 315 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-23 | -6 | -5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2218.73 | -8.96 | Unknown | Unknown | -2680 | 470.23 | Unknown | 2191.82 | -2218.73 | 4410.55 | Yes | N/A | N/A | 2024-03-27 | 2024-03-27 | 1 | 1 | 2024-03-27 | 2024-08-30 | 157 | 113 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-12 | 27 | 19 | 2024-08-30 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | 2024-10-17 | 2024-10-17 | 1 | 1 | 1 | 1 | 185 | 133 | 186 | 134 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 632.1 | 632.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | -269 | -194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-15 | 2024-09-11 | IOU Designed & Installed | N/A | No | N/A | 1357.33 | 378.72 | Unknown | Unknown | Unknown | 978.61 | 7962 | 957.71 | 1357.33 | -399.62 | Yes | N/A | N/A | 2023-11-15 | 2023-08-23 | Unknown | Unknown | 2023-08-23 | 2024-03-01 | 192 | 138 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-09-11 | 195 | 139 | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2024-10-28 | 1900-02-16 | 34 | 2024-10-28 | 2024-10-28 | 1 | 1 | 195 | 139 | 241 | 173 | 436 | 312 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | 786 | 562 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-04 | 2022-03-04 | 2025-02-10 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 86306.34 | 17338.82 | Unknown | 1817.79 | -3768.61 | 70918.34 | 1846219.9 | 71614.78 | 86306.34 | -14691.56 | Yes | N/A | N/A | 2022-03-04 | 2023-02-01 | 335 | 239 | 2023-02-01 | 2023-10-05 | 247 | 177 | 2023-02-02 | 2024-12-11 | 158 | 112 | 2023-09-27 | 2023-10-10 | 14 | 10 | 2024-09-20 | Unknown | Unknown | Unknown | 2024-09-20 | 2025-01-06 | 109 | 77 | 2025-02-10 | 2025-02-25 | 1900-01-15 | 12 | 2025-02-25 | 2025-02-25 | 1 | 1 | 493 | 351 | 387 | 277 | 880 | 628 | Steps 2,3,5,6,7 | 686 | 490 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 80.2 | 80.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-19 | -185 | -134 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2024-11-11 | 2025-06-16 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 863.32 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-08 | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2024-11-11 | 19 | 13 | 2024-11-11 | 2025-06-17 | 219 | 157 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-06-16 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-06-17 | 1900-01-01 | 2 | 2025-06-17 | 2025-06-17 | 1 | 1 | 220 | 158 | 22 | 16 | 242 | 174 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-30 | -652 | -467 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-11-06 | 2024-12-10 | IOU Designed & Installed | N/A | No | N/A | 524.64 | -10.2 | Unknown | Unknown | Unknown | 534.84 | 3981 | 1534.53 | 524.64 | 1009.89 | Yes | N/A | N/A | 2024-10-28 | 2024-10-28 | 1 | 1 | 2024-10-28 | 2024-11-06 | 10 | 8 | 2024-11-06 | Unknown | Unknown | Unknown | 2024-11-08 | 2024-11-18 | 11 | 7 | 2024-11-06 | 2024-12-10 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2024-12-17 | 1900-01-07 | 6 | 2024-12-17 | 2024-12-17 | 1 | 1 | 36 | 26 | 30 | 22 | 66 | 48 | Steps 2,3,5,6,7 | 12 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | 1129 | 808 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1777.67 | -15.35 | Unknown | Unknown | 6.4 | 1786.62 | 111453 | 3213.58 | 1777.67 | 1435.91 | Yes | N/A | N/A | 2023-06-13 | 2023-06-28 | 16 | 12 | 2023-06-28 | 2023-07-03 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-06-27 | 5 | 3 | 2023-07-03 | 2024-12-10 | 527 | 377 | Unknown | 2025-02-18 | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-06 | 2 | 2 | 543 | 389 | 13 | 9 | 556 | 398 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | -389 | -278 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-08 | 2025-04-14 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1651.66 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-05 | 2024-10-21 | 78 | 56 | 2024-10-21 | 2024-10-23 | 3 | 3 | 2024-10-23 | 2025-04-14 | 174 | 124 | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | 2025-04-14 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | 2025-05-09 | 1900-01-25 | 20 | 2025-05-09 | 2025-05-07 | Unknown | Unknown | 253 | 181 | 29 | 23 | 282 | 204 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Residential | Underserved Community | Escondido | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-16 | 449 | 322 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-03 | 2022-05-03 | 2024-02-26 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 71102.7 | 21310.49 | Unknown | Unknown | -56790.92 | 106583.13 | Unknown | 58753.28 | 71102.7 | -12349.42 | Yes | N/A | N/A | 2022-05-03 | 2023-08-30 | 485 | 347 | 2023-08-30 | 2024-02-05 | 160 | 114 | 2023-11-01 | 2024-01-30 | 46 | 32 | 2023-11-20 | 2024-02-20 | 27 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-04-09 | 1900-02-12 | 32 | 2024-04-09 | 2024-04-09 | 1 | 1 | 531 | 379 | 232 | 168 | 763 | 547 | Steps 2,3,5,6,7 | 167 | 119 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 79.05 | 79.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-19 | -127 | -92 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-09-28 | 2023-11-20 | IOU Designed & Installed | N/A | No | N/A | -7.71 | -5.81 | Unknown | Unknown | Unknown | -1.9 | Unknown | 500.87 | -7.71 | 508.58 | Yes | N/A | N/A | 2023-09-28 | 2023-09-28 | 1 | 1 | 2023-09-28 | 2023-09-28 | 1 | 1 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-11-20 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2024-03-14 | 1900-04-25 | 84 | 2024-03-14 | 2024-03-14 | 1 | 1 | 55 | 39 | 118 | 86 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -389 | -279 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-04-11 | 2024-01-05 | IOU Designed & Installed | N/A | No | N/A | 2.44 | -3.08 | Unknown | Unknown | Unknown | 5.52 | Unknown | 255.53 | 2.44 | 253.09 | Yes | N/A | N/A | 2023-03-27 | 2023-04-11 | 16 | 12 | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | 2023-12-11 | 67 | 49 | 2024-01-04 | 2024-01-05 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-01-09 | 1900-01-04 | 3 | 2024-01-09 | 2024-01-09 | 1 | 1 | 18 | 14 | 73 | 53 | 91 | 67 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-24 | -509 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-02-26 | 2024-03-13 | IOU Designed & Installed | N/A | No | N/A | -7.16 | -5.82 | Unknown | Unknown | Unknown | -1.34 | 3961 | 163.83 | -7.16 | 170.99 | Yes | N/A | N/A | 2024-02-26 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-02-26 | 18 | 12 | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-03-13 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-04-02 | 1900-01-20 | 15 | 2024-04-02 | 2024-04-02 | 1 | 1 | 17 | 13 | 40 | 28 | 57 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | -829 | -594 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 230.94 | -2.1 | Unknown | Unknown | Unknown | 233.04 | Unknown | 799.36 | 230.94 | 568.42 | Yes | N/A | N/A | 2023-02-17 | 2023-02-21 | 5 | 3 | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | 5 | 3 | 1 | 1 | 6 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-20 | -142 | -102 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-06-09 | 2023-10-31 | IOU Designed & Installed | N/A | No | N/A | 995 | -29.87 | Unknown | Unknown | Unknown | 1024.87 | 3981 | 789.8 | 995 | -205.2 | Yes | N/A | N/A | 2023-06-09 | 2023-06-09 | 1 | 1 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2023-10-31 | 145 | 103 | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2023-11-30 | 1900-01-30 | 23 | 2023-11-30 | 2023-11-30 | 1 | 1 | 146 | 104 | 32 | 24 | 178 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-25 | -211 | -152 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 316.05 | Unknown | Unknown | Unknown | 3.66 | 312.39 | 3981 | 1013.42 | 316.05 | 697.37 | Yes | N/A | N/A | 2024-05-17 | 2024-06-10 | 25 | 17 | 2024-06-10 | 2024-06-10 | 1 | 1 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | Unknown | Unknown | 2024-08-26 | 2024-08-26 | 1 | 1 | 25 | 17 | 2 | 2 | 27 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-02 | 478 | 343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-09-11 | 2024-11-11 | IOU Designed & Installed | N/A | No | N/A | 46008.18 | 4823.39 | Unknown | Unknown | 725.52 | 40459.27 | 569574.2 | 33217.96 | 46008.18 | -12790.22 | Yes | N/A | N/A | 2023-04-28 | 2023-09-19 | 145 | 103 | 2023-09-19 | 2024-04-17 | 212 | 152 | 2023-12-12 | Unknown | Unknown | Unknown | 2024-02-07 | 2024-04-15 | 21 | 15 | 2024-04-17 | Unknown | Unknown | Unknown | 2024-06-06 | 2024-10-24 | 141 | 101 | 2024-11-11 | 2025-04-24 | 1900-06-13 | 119 | 2025-04-24 | 2025-04-24 | 1 | 1 | 145 | 103 | 540 | 388 | 685 | 491 | Steps 2,3,5,6,7 | 127 | 91 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BONSALL | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -81 | -59 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | 2024-10-02 | IOU Designed & Installed | N/A | No | N/A | 17329.25 | 93.64 | Unknown | Unknown | Unknown | 17235.61 | Unknown | 3092.84 | 17329.25 | -14236.41 | Yes | N/A | N/A | 2024-08-16 | 2024-08-20 | 5 | 3 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-10 | 5 | 3 | 2024-09-04 | 2024-10-02 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-11-12 | 1900-02-10 | 30 | 2024-11-12 | 2024-11-12 | 1 | 1 | 34 | 24 | 48 | 34 | 82 | 58 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-10 | -476 | -341 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-05-19 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | -4.65 | -3.4 | Unknown | Unknown | Unknown | -1.25 | Unknown | 495.75 | -4.65 | 500.4 | Yes | N/A | N/A | 2023-04-12 | 2023-05-19 | 38 | 28 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2023-10-13 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-10-23 | 1900-01-10 | 7 | 2023-10-23 | 2023-10-23 | 1 | 1 | 186 | 134 | 12 | 8 | 198 | 142 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Marcos | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -202 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-10 | 2022-08-10 | 2023-06-21 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -2206.62 | Unknown | Unknown | Unknown | -25084 | 22877.38 | 0 | 23437.57 | -2206.62 | 25644.19 | Yes | N/A | N/A | 2022-08-10 | 2023-02-08 | 183 | 131 | 2023-02-08 | 2023-06-19 | 132 | 94 | 2023-02-28 | 2024-05-01 | 20 | 16 | 2023-03-28 | 2024-05-08 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | 2024-06-21 | 1901-01-01 | 263 | 2024-06-21 | 2024-06-21 | 1 | 1 | 203 | 147 | 596 | 426 | 799 | 573 | Steps 2,3,5,6,7 | 511 | 365 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-14 | -472 | -338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-02 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | -1704.42 | Unknown | Unknown | Unknown | -1768 | 63.58 | Unknown | 1767.57 | -1704.42 | 3471.99 | Yes | N/A | N/A | 2024-05-02 | 2024-02-23 | Unknown | Unknown | 2024-02-23 | 2024-09-03 | 194 | 138 | 2024-09-03 | 2024-09-05 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2024-10-23 | 49 | 35 | Unknown | 2024-10-23 | Unknown | Unknown | 2024-10-23 | 2024-11-01 | 1900-01-09 | 8 | 2024-11-01 | 2024-10-30 | Unknown | Unknown | 52 | 38 | 204 | 146 | 256 | 184 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-22 | -451 | -322 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | 2024-03-11 | IOU Designed & Installed | N/A | No | N/A | 796.75 | -11.62 | Unknown | Unknown | 18.13 | 790.24 | 3981 | 998.47 | 796.75 | 201.72 | Yes | N/A | N/A | 2023-09-11 | 2023-09-22 | 12 | 10 | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2024-03-11 | 167 | 119 | Unknown | 2024-03-27 | Unknown | Unknown | 2024-03-11 | 2024-03-28 | 1900-01-17 | 14 | 2024-03-28 | 2024-03-28 | 1 | 1 | 179 | 129 | 19 | 15 | 198 | 144 | Steps 2,3,5,6,7 | 16 | 12 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | Oceanside | OCEANSIDE | 20.1 | 20.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-17 | 452 | 325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-11 | 2023-07-25 | 2024-08-30 | IOU Designed & Installed | N/A | No | N/A | 24311.44 | 1083.73 | Unknown | Unknown | 1017.47 | 22210.24 | 24400.52 | 22213.52 | 24311.44 | -2097.92 | Yes | N/A | N/A | 2023-01-11 | 2023-02-24 | 45 | 33 | 2023-02-24 | 2024-01-10 | 321 | 229 | 2023-06-29 | 2024-04-10 | 204 | 146 | 2023-12-19 | 2024-01-23 | 17 | 13 | 2024-01-25 | Unknown | Unknown | Unknown | 2024-01-25 | 2024-08-14 | 203 | 145 | 2024-08-30 | 2024-10-11 | 1900-02-11 | 31 | 2024-10-11 | 2024-10-11 | 1 | 1 | 249 | 179 | 585 | 419 | 834 | 598 | Steps 2,3,5,6,7 | 308 | 220 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-04 | 357 | 256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12.95 | Unknown | Unknown | Unknown | Unknown | 12.95 | 1656 | 376.62 | 12.95 | 363.67 | Yes | N/A | N/A | 2023-12-13 | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-12-15 | 124 | 90 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | 2024-07-29 | 2024-07-26 | Unknown | Unknown | 0 | 0 | 124 | 90 | 124 | 90 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-30 | -609 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-27 | 2025-04-18 | IOU Designed & Installed | N/A | No | N/A | 781.17 | 513.12 | Unknown | 111.21 | -1219 | 1375.84 | Unknown | 1073.03 | 781.17 | 291.86 | Yes | N/A | N/A | 2025-02-10 | 2025-02-13 | 4 | 4 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-04-18 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-04-30 | 1900-01-12 | 9 | 2025-04-30 | 2025-04-30 | 1 | 1 | 5 | 5 | 14 | 10 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 39.55 | 39.55 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-08 | -346 | -248 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-24 | 2023-09-24 | 2024-03-07 | IOU Designed & Installed | N/A | No | N/A | 579.32 | -21.43 | Unknown | Unknown | -720.42 | 1321.17 | Unknown | 733.95 | 579.32 | 154.63 | Yes | N/A | N/A | 2023-09-24 | 2023-10-12 | 19 | 14 | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | 2023-11-20 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2024-03-07 | 109 | 79 | Unknown | 2024-03-06 | Unknown | Unknown | 2024-03-07 | 2024-03-27 | 1900-01-20 | 15 | 2024-03-27 | 2024-03-27 | 1 | 1 | 168 | 121 | 23 | 17 | 191 | 138 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | -1045 | -748 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-07 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | 535.21 | 176.49 | Unknown | Unknown | Unknown | 358.72 | Unknown | 307.58 | 535.21 | -227.63 | Yes | N/A | N/A | 2024-05-06 | 2024-05-07 | 2 | 2 | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-05-14 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-05-15 | 1900-01-01 | 2 | 2024-05-15 | 2024-05-15 | 1 | 1 | 10 | 8 | 3 | 3 | 13 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | -850 | -608 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | 1364.58 | 215.64 | Unknown | Unknown | Unknown | 1148.94 | Unknown | 351.99 | 1364.58 | -1012.59 | Yes | N/A | N/A | 2023-03-08 | 2023-03-08 | 1 | 1 | 2023-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | 2023-07-17 | 132 | 94 | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-07-19 | 1900-01-02 | 3 | 2023-07-19 | 2023-07-19 | 1 | 1 | 133 | 95 | 4 | 4 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | -671 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2025-01-10 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 31.63 | Unknown | Unknown | Unknown | Unknown | 31.63 | 3981 | 2269.61 | 31.63 | 2237.98 | Yes | N/A | N/A | 2024-12-17 | 2025-01-10 | 25 | 19 | 2025-01-10 | 2025-01-10 | 1 | 1 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-01-27 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-01-31 | 1900-01-04 | 5 | 2025-01-31 | 2025-01-30 | Unknown | Unknown | 43 | 31 | 6 | 6 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-12 | 93 | 68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 407.12 | -50.53 | Unknown | Unknown | -852 | 1309.65 | 0 | 851.98 | 407.12 | 444.86 | Yes | N/A | N/A | 2023-02-15 | 2023-02-15 | 1 | 1 | 2023-02-15 | 2023-04-07 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 1 | 1 | 53 | 39 | 54 | 40 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | 316 | 316 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-27 | 739 | 530 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-10-13 | 2025-03-26 | IOU Designed & Installed | N/A | No | N/A | 21587.2 | 1944.53 | Unknown | Unknown | 62.51 | 19580.16 | 203207 | 35165.07 | 21587.2 | 13577.87 | Yes | N/A | N/A | 2023-08-02 | 2023-10-13 | 73 | 53 | 2023-10-13 | 2024-03-28 | 168 | 120 | 2024-01-17 | Unknown | Unknown | Unknown | 2024-02-28 | 2024-04-03 | 27 | 19 | 2024-03-28 | Unknown | Unknown | Unknown | 2024-10-29 | 2025-03-21 | 144 | 104 | 2025-03-26 | 2025-04-04 | 1900-01-09 | 8 | 2025-04-04 | 2025-04-04 | 1 | 1 | 73 | 53 | 350 | 252 | 423 | 305 | Steps 2,3,5,6,7 | 77 | 55 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | -497 | -356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3421.65 | 153.28 | Unknown | Unknown | 25.55 | 3242.82 | 3981 | 1389.7 | 3421.65 | -2031.95 | Yes | N/A | N/A | 2024-08-07 | 2024-07-24 | Unknown | Unknown | 2024-07-24 | 2024-09-25 | 64 | 46 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | 2025-02-26 | 2025-02-26 | 1 | 1 | 0 | 0 | 65 | 47 | 65 | 47 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-13 | -206 | -149 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 647.51 | -19.5 | Unknown | Unknown | Unknown | 667.01 | 3981 | 676.18 | 647.51 | 28.67 | Yes | N/A | N/A | 2023-03-30 | 2023-03-30 | 1 | 1 | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-04-30 | 16 | 12 | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | Unknown | Unknown | 2024-05-21 | 2024-05-21 | 1 | 1 | 1 | 1 | 17 | 13 | 18 | 14 | Steps 2,3,5,6,7 | 397 | 283 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | 45.45 | 45.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-13 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-09-10 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 67.11 | -0.94 | Unknown | Unknown | Unknown | 68.05 | 3981 | 1436.66 | 67.11 | 1369.55 | Yes | N/A | N/A | 2024-08-29 | 2024-09-10 | 13 | 9 | 2024-09-10 | 2024-09-12 | 3 | 3 | 2024-09-12 | 2024-09-20 | 2 | 2 | 2024-09-12 | 2024-09-19 | 8 | 6 | 2024-09-12 | 2024-10-01 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-09 | 1900-01-08 | 7 | 2024-10-09 | 2024-10-09 | 1 | 1 | 35 | 25 | 21 | 17 | 56 | 42 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | -101 | -74 | No | 2023-03-29 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-03-29 | 2023-08-23 | IOU Designed & Installed | N/A | Yes | 110 | 49.62 | -13.84 | Unknown | Unknown | 56.7 | 6.76 | 3981 | 775.04 | 49.62 | 725.42 | Yes | N/A | N/A | 2023-03-29 | 2023-07-17 | 111 | 79 | 2023-07-17 | 2023-07-17 | 1 | 1 | 2023-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | 2023-08-23 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | 2024-10-08 | 1901-02-16 | 295 | 2024-10-08 | 2024-10-08 | 1 | 1 | 258 | 184 | 415 | 297 | 673 | 481 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | -683 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | 2023-11-20 | IOU Designed & Installed | N/A | No | N/A | 1757.73 | 531.82 | Unknown | 108.46 | Unknown | 1117.45 | 3961 | 1044.32 | 1757.73 | -713.41 | Yes | N/A | N/A | 2023-11-01 | 2023-11-20 | 20 | 14 | 2023-11-20 | 2023-11-20 | 1 | 1 | 2023-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2023-11-20 | 1 | 1 | Unknown | 2023-11-21 | Unknown | Unknown | 2023-11-20 | 2023-11-21 | 1900-01-01 | 2 | 2023-11-21 | 2023-11-21 | 1 | 1 | 21 | 15 | 4 | 4 | 25 | 19 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | -633 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 2281.32 | 489.8 | Unknown | Unknown | Unknown | 1791.52 | Unknown | 585.33 | 2281.32 | -1695.99 | Yes | N/A | N/A | 2024-05-08 | 2024-05-17 | 10 | 8 | 2024-05-17 | 2024-05-17 | 1 | 1 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-03 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-06-04 | 1900-01-01 | 2 | 2024-06-04 | 2024-06-04 | 1 | 1 | 28 | 20 | 4 | 4 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | -530 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-04-08 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 3586.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-04-07 | 27 | 19 | 2025-04-07 | 2025-04-08 | 2 | 2 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-05-06 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-12 | 1900-01-06 | 5 | 2025-05-12 | 2025-05-09 | Unknown | Unknown | 56 | 40 | 9 | 7 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | -524 | -375 | No | 2023-01-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-28 | 2023-01-28 | Unknown | IOU Designed & Installed | N/A | Yes | 26 | 1421.09 | -12.9 | Unknown | Unknown | Unknown | 1433.99 | Unknown | 699.6 | 1421.09 | -721.49 | Yes | N/A | N/A | 2023-01-28 | 2023-02-23 | 27 | 19 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | Unknown | Unknown | 2023-05-05 | 2023-05-05 | 1 | 1 | 27 | 19 | 1 | 1 | 28 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-30 | -655 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-24 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 53.14 | Unknown | Unknown | Unknown | Unknown | 53.14 | Unknown | 1553.1 | 53.14 | 1499.96 | Yes | N/A | N/A | 2024-09-23 | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-09-24 | 20 | 14 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-10-10 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-11-13 | 1900-02-03 | 25 | 2024-11-13 | 2024-11-13 | 1 | 1 | 17 | 13 | 56 | 40 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-02 | -641 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-23 | 2025-03-28 | IOU Designed & Installed | N/A | No | N/A | -7.08 | -29.67 | Unknown | Unknown | Unknown | 22.59 | Unknown | 1788.14 | -7.08 | 1795.22 | Yes | N/A | N/A | 2025-01-15 | 2025-01-23 | 9 | 7 | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-03-28 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-01 | 1900-01-04 | 3 | 2025-04-01 | 2025-04-01 | 1 | 1 | 74 | 54 | 7 | 5 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | -232 | -167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1302.34 | 1102.52 | Unknown | 283.57 | -688 | 604.25 | Unknown | 687.72 | 1302.34 | -614.62 | Yes | N/A | N/A | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-02-21 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-24 | -425 | -304 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-08-26 | 2024-01-09 | IOU Designed & Installed | N/A | No | N/A | 7.53 | -9.48 | Unknown | Unknown | Unknown | 17.01 | 11943 | 936.07 | 7.53 | 928.54 | Yes | N/A | N/A | 2023-08-25 | 2023-08-26 | 2 | 1 | 2023-08-26 | 2023-08-26 | 1 | 0 | 2023-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-26 | 2024-01-09 | 137 | 97 | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-01-24 | 1900-01-15 | 12 | 2024-01-24 | 2024-01-24 | 1 | 1 | 139 | 98 | 18 | 13 | 157 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 106.05 | 106.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | 405 | 290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-10-08 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 8319.92 | 1976.73 | Unknown | Unknown | 17.84 | 6325.35 | 3981 | 1372.47 | 8319.92 | -6947.45 | Yes | N/A | N/A | 2024-03-26 | 2024-05-14 | 50 | 36 | 2024-05-14 | 2024-11-06 | 177 | 127 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2025-03-28 | 143 | 103 | Unknown | 2025-03-04 | Unknown | Unknown | 2025-03-18 | 2025-04-09 | 1900-01-22 | 17 | 2025-04-09 | 2025-04-04 | Unknown | Unknown | 193 | 139 | 200 | 144 | 393 | 283 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CMR PA6 WO1 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 809 | 580 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-11 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 34187 | Not available | Unknown | Unknown | Yes | N/A | N/A | 2024-09-11 | 2024-09-11 | 1 | 1 | 2024-09-11 | 2024-09-13 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2025-06-13 | 274 | 196 | Unknown | 2025-07-03 | Unknown | Unknown | 2025-06-11 | 2025-07-03 | 1900-01-22 | 17 | 2025-07-03 | 2025-06-06 | Unknown | Unknown | 275 | 197 | 26 | 20 | 301 | 217 | Steps 2,3,5,6,7 | 22 | 16 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 82.05 | 82.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-31 | -191 | -138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | -411.66 | -1.88 | Unknown | Unknown | -505 | 95.22 | 7010.18 | 1741.01 | -411.66 | 2152.67 | Yes | N/A | N/A | 2024-01-17 | 2023-11-08 | Unknown | Unknown | 2023-11-08 | 2024-01-31 | 85 | 61 | 2024-01-31 | 2024-09-30 | 244 | 174 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-04-23 | 1 | 1 | 244 | 174 | 86 | 62 | 330 | 236 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-18 | -402 | -288 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | 2023-05-04 | 2023-11-27 | IOU Designed & Installed | N/A | No | N/A | 17671.35 | 7252.62 | Unknown | Unknown | 8.22 | 10410.51 | 3981 | 2250.24 | 17671.35 | -15421.11 | Yes | N/A | N/A | 2023-05-04 | 2023-05-04 | 1 | 1 | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | 2023-11-27 | 208 | 148 | Unknown | 2023-11-17 | Unknown | Unknown | 2023-11-27 | 2023-12-13 | 1900-01-16 | 13 | 2023-12-13 | 2023-12-13 | 1 | 1 | 209 | 149 | 18 | 14 | 227 | 163 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 13.5 | 13.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-25 | -664 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-27 | 2025-01-09 | IOU Designed & Installed | N/A | No | N/A | 107.87 | -1.5 | Unknown | Unknown | Unknown | 109.37 | 3981 | 2209.77 | 107.87 | 2101.9 | Yes | N/A | N/A | 2024-12-09 | 2024-12-27 | 19 | 15 | 2024-12-27 | 2024-12-27 | 1 | 1 | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-01-09 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-30 | 1900-01-21 | 16 | 2025-01-30 | 2025-01-30 | 1 | 1 | 33 | 25 | 24 | 18 | 57 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 130.05 | 130.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | -31 | -24 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-07-11 | 2023-10-16 | IOU Designed & Installed | N/A | No | N/A | 5041.54 | Unknown | Unknown | Unknown | Unknown | 5041.54 | Unknown | 196.01 | 5041.54 | -4845.53 | Yes | N/A | N/A | 2023-06-21 | 2023-07-26 | 36 | 26 | 2023-07-26 | 2023-09-15 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2023-10-30 | 1900-01-14 | 11 | 2023-10-30 | 2023-10-30 | 1 | 1 | 36 | 26 | 68 | 50 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-08 | -593 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-06-10 | 2024-07-24 | IOU Designed & Installed | N/A | No | N/A | 5.54 | Unknown | Unknown | Unknown | Unknown | 5.54 | Unknown | 984.98 | 5.54 | 979.44 | Yes | N/A | N/A | 2024-05-14 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-06-10 | 54 | 38 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-07-24 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-08-23 | 1900-01-30 | 23 | 2024-08-23 | 2024-08-23 | 1 | 1 | 45 | 33 | 86 | 62 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-10 | -168 | -121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.64 | -4.1 | Unknown | Unknown | Unknown | -1.54 | Unknown | 363.72 | -5.64 | 369.36 | Yes | N/A | N/A | 2023-03-15 | 2023-03-16 | 2 | 2 | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | Unknown | Unknown | 2023-07-26 | 2023-07-26 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | -36 | -27 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1703.13 | -32.42 | Unknown | Unknown | Unknown | -1670.71 | Unknown | 1066.55 | -1703.13 | 2769.68 | Yes | N/A | N/A | 2024-10-24 | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2025-01-10 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-12-13 | 31 | 23 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-02-19 | 1 | 1 | 0 | 0 | 140 | 102 | 140 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 20.75 | 20.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -249 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-26 | 2023-01-26 | 2024-04-03 | IOU Designed & Installed | N/A | No | N/A | 2216.3 | 464.94 | Unknown | 41.94 | 47.31 | 1662.11 | 3981 | 703.78 | 2216.3 | -1512.52 | Yes | N/A | N/A | 2023-01-26 | 2023-02-15 | 21 | 15 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | 2024-04-03 | 414 | 296 | Unknown | 2024-05-07 | Unknown | Unknown | 2024-04-03 | 2024-05-20 | 1900-02-16 | 34 | 2024-05-20 | 2024-05-20 | 1 | 1 | 435 | 311 | 49 | 35 | 484 | 346 | Steps 2,3,5,6,7 | 34 | 24 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | 30.05 | 30.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-26 | -261 | -188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | 2023-11-05 | IOU Designed & Installed | N/A | No | N/A | 3231.85 | 965.5 | Unknown | 460.32 | 1.2 | 1804.83 | 3981 | 2027 | 3231.85 | -1204.85 | Yes | N/A | N/A | 2023-09-07 | 2023-08-21 | Unknown | Unknown | 2023-08-21 | 2023-10-02 | 43 | 31 | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2023-11-05 | 35 | 25 | Unknown | 2023-10-27 | Unknown | Unknown | 2023-11-05 | 2023-11-08 | 1900-01-03 | 3 | 2023-11-08 | 2023-11-08 | 1 | 1 | 35 | 25 | 48 | 35 | 83 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-08 | -555 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-08 | 2023-08-22 | IOU Designed & Installed | N/A | No | N/A | -869.01 | -13.24 | Unknown | Unknown | -1076 | 220.23 | 3885 | 2309.19 | -869.01 | 3178.2 | Yes | N/A | N/A | 2023-06-06 | 2023-06-30 | 25 | 19 | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | 2023-07-27 | 28 | 20 | 2023-06-30 | 2023-07-25 | 26 | 18 | 2023-07-27 | 2023-08-22 | 27 | 19 | Unknown | 2023-08-04 | Unknown | Unknown | 2023-08-22 | 2023-08-31 | 1900-01-09 | 8 | 2023-08-31 | 2023-08-31 | 1 | 1 | 80 | 58 | 38 | 28 | 118 | 86 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-12 | -427 | -306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | 2024-11-26 | IOU Designed & Installed | N/A | No | N/A | 524.64 | Unknown | Unknown | Unknown | -1076.76 | 1601.4 | Unknown | 1118.16 | 524.64 | 593.52 | Yes | N/A | N/A | 2024-06-04 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-07-31 | 133 | 95 | 2024-07-31 | 2024-08-02 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-11-26 | 117 | 83 | Unknown | 2025-03-05 | Unknown | Unknown | 2024-11-26 | 2025-01-09 | 1900-02-13 | 33 | 2025-01-09 | 2025-01-09 | 1 | 1 | 120 | 86 | 179 | 129 | 299 | 215 | Steps 2,3,5,6,7 | 99 | 71 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-28 | -422 | -303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-10 | 2023-08-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1196.4 | -10.1 | Unknown | Unknown | 21.01 | 1185.49 | 3981 | 650.91 | 1196.4 | -545.49 | Yes | N/A | N/A | 2023-08-10 | 2023-06-02 | Unknown | Unknown | 2023-06-02 | 2023-09-06 | 97 | 69 | 2023-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | Unknown | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | 2024-01-31 | 2024-01-31 | 1 | 1 | 0 | 0 | 98 | 70 | 98 | 70 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 154 | 154 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-11 | -371 | -266 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2023-11-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -454.38 | Unknown | Unknown | Unknown | -1330.47 | 876.09 | 0 | 1082.65 | -454.38 | 1537.03 | Yes | N/A | N/A | 2023-11-02 | 2023-08-21 | Unknown | Unknown | 2023-08-21 | 2023-12-12 | 114 | 82 | 2023-12-12 | 2023-12-15 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | Unknown | Unknown | Unknown | 2024-08-05 | Unknown | Unknown | 2024-08-05 | 2024-08-05 | 1 | 1 | 4 | 4 | 115 | 83 | 119 | 87 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | La Mesa | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-11 | -104 | -75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-06 | 2023-07-07 | 2023-09-23 | IOU Designed & Installed | N/A | No | N/A | 12655.86 | 3019.65 | Unknown | 730.24 | 204.62 | 8701.35 | Unknown | 1834.39 | 12655.86 | -10821.47 | Yes | N/A | N/A | 2023-07-06 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | 2023-09-23 | 79 | 56 | Unknown | Unknown | Unknown | Unknown | 2023-09-23 | 2023-12-29 | 1900-04-07 | 70 | 2023-12-29 | 2023-12-29 | 1 | 1 | 79 | 56 | 99 | 71 | 178 | 127 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | -499 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-09-18 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 477.63 | -9.09 | Unknown | Unknown | Unknown | 486.72 | Unknown | 1739.3 | 477.63 | 1261.67 | Yes | N/A | N/A | 2024-06-11 | 2024-04-05 | Unknown | Unknown | 2024-04-05 | 2024-09-18 | 167 | 119 | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-10-24 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-18 | 1900-01-25 | 18 | 2024-11-18 | 2024-11-18 | 1 | 1 | 37 | 27 | 194 | 138 | 231 | 165 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-31 | -363 | -260 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3179.15 | 59.57 | Unknown | Unknown | Unknown | 3119.58 | Unknown | 403.93 | 3179.15 | -2775.22 | Yes | N/A | N/A | 2024-11-11 | 2024-11-18 | 8 | 6 | 2024-11-18 | 2025-03-13 | 116 | 84 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-02 | 2025-04-02 | 1 | 1 | 8 | 6 | 117 | 85 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-20 | -351 | -252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-06-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 62.82 | -10.92 | Unknown | Unknown | 68.4 | 5.34 | 3981 | 473.64 | 62.82 | 410.82 | Yes | N/A | N/A | 2023-05-23 | 2023-06-09 | 18 | 14 | 2023-06-09 | 2023-06-14 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | 2023-08-24 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2023-10-05 | Unknown | Unknown | 90 | 66 | 6 | 4 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-10 | -35 | -26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-10-23 | 2023-12-27 | IOU Designed & Installed | N/A | No | N/A | 24.13 | -25.75 | Unknown | Unknown | 4.44 | 45.44 | 3981 | 811.03 | 24.13 | 786.9 | Yes | N/A | N/A | 2023-09-26 | 2023-10-23 | 28 | 20 | 2023-10-23 | 2023-10-23 | 1 | 1 | 2023-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2023-12-27 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2024-04-08 | 1900-04-13 | 74 | 2024-04-08 | 2024-04-05 | Unknown | Unknown | 94 | 68 | 105 | 75 | 199 | 143 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | CAMPO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-03 | 143 | 103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3101.06 | 4256.55 | Unknown | Unknown | -2926 | 1770.51 | Unknown | 2210.67 | 3101.06 | -890.39 | Yes | N/A | N/A | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -208 | -149 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | 2024-08-15 | IOU Designed & Installed | N/A | No | N/A | 5376.82 | Unknown | Unknown | Unknown | Unknown | 5376.82 | Unknown | 1409.91 | 5376.82 | -3966.91 | Yes | N/A | N/A | 2024-04-24 | 2024-04-22 | Unknown | Unknown | 2024-04-22 | 2024-07-19 | 89 | 65 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-09-05 | 1900-01-21 | 16 | 2024-09-05 | 2024-09-05 | 1 | 1 | 0 | 0 | 112 | 82 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 102 | 102 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-22 | -83 | -60 | No | 2022-08-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-09 | 2022-09-01 | Unknown | IOU Designed & Installed | N/A | Yes | 185 | -2.32 | -6.89 | Unknown | Unknown | Unknown | 4.57 | 3981 | 741.86 | -2.32 | 744.18 | Yes | N/A | N/A | 2022-08-09 | 2023-02-10 | 186 | 134 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-09-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | Unknown | Unknown | 2023-07-26 | 2023-03-31 | Unknown | Unknown | 186 | 134 | 0 | 0 | 186 | 134 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | -624 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-04 | 2024-12-12 | IOU Designed & Installed | N/A | No | N/A | 628.26 | -11.72 | Unknown | Unknown | Unknown | 639.98 | Unknown | 1972.39 | 628.26 | 1344.13 | Yes | N/A | N/A | 2024-12-04 | 2024-12-03 | Unknown | Unknown | 2024-12-03 | 2024-12-09 | 7 | 5 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2024-12-12 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-01-15 | 1900-02-03 | 25 | 2025-01-15 | 2025-01-15 | 1 | 1 | 4 | 4 | 43 | 31 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 63 | 63 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-17 | -604 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-07-05 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 27.95 | Unknown | Unknown | Unknown | Unknown | 27.95 | Unknown | 1608.93 | 27.95 | 1580.98 | Yes | N/A | N/A | 2024-05-30 | 2024-04-26 | Unknown | Unknown | 2024-04-26 | 2024-07-05 | 71 | 51 | 2024-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | 2024-07-29 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-21 | 1900-01-23 | 18 | 2024-08-21 | 2024-08-21 | 1 | 1 | 25 | 17 | 96 | 70 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-08 | -883 | -632 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-03-13 | 2023-08-02 | IOU Designed & Installed | N/A | No | N/A | -22.64 | -16.4 | Unknown | Unknown | Unknown | -6.24 | 23991 | 324.29 | -22.64 | 346.93 | Yes | N/A | N/A | 2023-03-13 | 2023-03-13 | 1 | 1 | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-13 | 2023-08-02 | 143 | 103 | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | 2023-08-09 | 1900-01-07 | 6 | 2023-08-09 | 2023-08-09 | 1 | 1 | 144 | 104 | 9 | 7 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-21 | 419 | 300 | No | 2022-08-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-04 | 2022-08-05 | 2024-08-06 | IOU Designed & Installed | N/A | Yes | 571 | 14.03 | Unknown | Unknown | Unknown | Unknown | 14.03 | 7770 | 677.44 | 14.03 | 663.41 | Yes | N/A | N/A | 2022-08-04 | 2024-02-29 | 575 | 411 | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-08-08 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-13 | 1900-01-07 | 6 | 2024-08-13 | 2024-08-13 | 1 | 1 | 575 | 411 | 9 | 7 | 584 | 418 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-28 | -269 | -194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-26 | 2023-08-26 | 2023-09-29 | IOU Designed & Installed | N/A | No | N/A | 1491.3 | 368.64 | Unknown | 155.7 | Unknown | 966.96 | 3981 | 1051.35 | 1491.3 | -439.95 | Yes | N/A | N/A | 2023-08-26 | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-08-26 | 5 | 4 | 2023-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-26 | 2023-09-29 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-10-03 | 1900-01-04 | 3 | 2023-10-03 | 2023-10-03 | 1 | 1 | 35 | 25 | 11 | 8 | 46 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.35 | 9.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-12 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-03-04 | 2024-03-06 | IOU Designed & Installed | N/A | No | N/A | 366.5 | -13.9 | Unknown | Unknown | Unknown | 380.4 | 3981 | 875.46 | 366.5 | 508.96 | Yes | N/A | N/A | 2024-02-23 | 2024-01-22 | Unknown | Unknown | 2024-01-22 | 2024-03-04 | 43 | 31 | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-03-06 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-03-18 | 1900-01-12 | 9 | 2024-03-18 | 2024-03-18 | 1 | 1 | 3 | 3 | 57 | 41 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 133.05 | 133.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-15 | -558 | -399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-13 | 2025-06-02 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1208.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2025-01-10 | 4 | 4 | 2025-01-10 | 2025-01-13 | 4 | 2 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-06-02 | 141 | 101 | Unknown | 2025-05-28 | Unknown | Unknown | 2025-06-02 | 2025-06-09 | 1900-01-07 | 6 | 2025-06-09 | 2025-06-05 | Unknown | Unknown | 145 | 105 | 12 | 8 | 157 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-17 | -197 | -142 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | 2023-06-29 | 2024-03-11 | IOU Designed & Installed | N/A | No | N/A | 6271.69 | 433.83 | Unknown | Unknown | -6377.46 | 12215.32 | 3981 | 10213.81 | 6271.69 | 3942.12 | Yes | N/A | N/A | 2023-06-28 | 2023-06-29 | 2 | 2 | 2023-06-29 | 2023-07-31 | 33 | 23 | 2023-07-03 | 2023-07-11 | 9 | 7 | 2023-08-23 | 2023-08-25 | 3 | 3 | 2023-07-31 | 2024-03-05 | 219 | 157 | 2023-08-16 | 2024-03-05 | 203 | 145 | 2024-03-11 | 2024-04-04 | 1900-01-24 | 19 | 2024-04-04 | 2024-04-03 | Unknown | Unknown | 230 | 166 | 264 | 190 | 494 | 356 | Steps 2,3,5,6,7 | 255 | 183 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | -604 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-17 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | 1950.57 | -39.02 | Unknown | Unknown | 9.31 | 1980.28 | Unknown | 2151.77 | 1950.57 | 201.2 | Yes | N/A | N/A | 2025-03-12 | 2025-03-17 | 6 | 4 | 2025-03-17 | 2025-03-17 | 1 | 1 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-04-09 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-06-05 | 1900-02-26 | 42 | 2025-06-05 | 2025-06-05 | 1 | 1 | 30 | 22 | 60 | 44 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-29 | -57 | -41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | 2024-12-03 | IOU Designed & Installed | N/A | No | N/A | 3952.09 | 385.62 | Unknown | Unknown | 142.26 | 3424.21 | 3981 | 626.6 | 3952.09 | -3325.49 | Yes | N/A | N/A | 2023-06-20 | 2023-08-11 | 53 | 39 | 2023-08-11 | 2025-03-06 | 574 | 410 | 2025-03-06 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2024-12-03 | 476 | 340 | Unknown | 2024-11-07 | Unknown | Unknown | 2024-12-03 | 2025-01-31 | 1900-02-28 | 44 | 2025-01-31 | 2025-01-31 | 1 | 1 | 529 | 379 | 635 | 455 | 1164 | 834 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-11 | -642 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | 2024-12-09 | IOU Designed & Installed | N/A | No | N/A | 77.19 | -1.5 | Unknown | Unknown | Unknown | 78.69 | Unknown | 1066.55 | 77.19 | 989.36 | Yes | N/A | N/A | 2024-11-25 | 2024-11-25 | 1 | 1 | 2024-11-25 | 2024-11-25 | 1 | 1 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-09 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-01-07 | 1900-01-29 | 22 | 2025-01-07 | 2025-01-07 | 1 | 1 | 16 | 12 | 32 | 24 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 286 | 286 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | -72 | -53 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2024-05-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | -224.6 | -22.07 | Unknown | Unknown | -1403 | 1200.47 | Unknown | 1402.65 | -224.6 | 1627.25 | Yes | N/A | N/A | 2024-05-22 | 2024-08-08 | 79 | 57 | 2024-08-08 | 2024-08-29 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-09-25 | 34 | 24 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-01-08 | 1 | 1 | 79 | 57 | 57 | 41 | 136 | 98 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-12 | -360 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-05 | 2024-06-18 | 2025-01-02 | IOU Designed & Installed | N/A | No | N/A | 1565.52 | 420.74 | Unknown | Unknown | Unknown | 1144.78 | 3981 | 1813.79 | 1565.52 | 248.27 | Yes | N/A | N/A | 2024-04-05 | 2024-06-17 | 74 | 52 | 2024-06-17 | 2024-06-18 | 2 | 2 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2025-01-02 | 199 | 143 | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-01-17 | 1900-01-15 | 12 | 2025-01-17 | 2025-01-17 | 1 | 1 | 273 | 195 | 19 | 15 | 292 | 210 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-19 | -177 | -126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2025-03-24 | IOU Designed & Installed | N/A | No | N/A | 2806 | 330.46 | Unknown | 15.56 | 95.31 | 2364.67 | 3981 | 1384.24 | 2806 | -1421.76 | Yes | N/A | N/A | 2024-01-09 | 2024-06-21 | 165 | 119 | 2024-06-21 | 2024-06-24 | 4 | 2 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2025-03-24 | 274 | 196 | Unknown | 2025-03-20 | Unknown | Unknown | 2025-03-24 | 2025-04-25 | 1900-02-01 | 25 | 2025-04-25 | 2025-04-25 | 1 | 1 | 439 | 315 | 38 | 28 | 477 | 343 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 198 | 198 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-12 | 178 | 127 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-22 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 1049.48 | Unknown | Unknown | Unknown | 13.84 | 1035.64 | 3981 | 1586.5 | 1049.48 | 537.02 | Yes | N/A | N/A | 2024-05-14 | 2024-05-21 | 8 | 6 | 2024-05-21 | 2024-07-01 | 42 | 30 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-10-01 | 93 | 67 | Unknown | 2024-09-25 | Unknown | Unknown | 2024-10-01 | 2024-10-10 | 1900-01-09 | 8 | 2024-10-10 | 2024-10-07 | Unknown | Unknown | 101 | 73 | 52 | 38 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | San Marcos | SAN MARCOS | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-06 | 644 | 461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-07-06 | 2024-08-14 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -4653.95 | -67.35 | Unknown | Unknown | -17778 | 13191.4 | Unknown | 17777.88 | -4653.95 | 22431.83 | Yes | N/A | N/A | 2024-06-17 | 2024-06-17 | 1 | 1 | 2024-06-17 | 2024-08-01 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-07-25 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-09-10 | 1900-01-27 | 20 | 2024-09-10 | 2024-09-10 | 1 | 1 | 1 | 1 | 87 | 65 | 88 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 126 | 126 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | -544 | -389 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | -1238.98 | Unknown | Unknown | Unknown | -1312 | 73.02 | Unknown | 1576.22 | -1238.98 | 2815.2 | Yes | N/A | N/A | 2024-10-01 | 2024-09-20 | Unknown | Unknown | 2024-09-20 | 2024-10-07 | 18 | 12 | 2024-10-07 | 2024-11-15 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2025-02-11 | 72 | 52 | Unknown | 2025-02-05 | Unknown | Unknown | 2025-02-11 | 2025-02-14 | 1900-01-03 | 4 | 2025-02-14 | 2025-02-14 | 1 | 1 | 112 | 82 | 23 | 17 | 135 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | -640 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-07 | 2025-03-07 | 2025-04-14 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1906.34 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-07 | 2025-03-07 | 1 | 1 | 2025-03-07 | 2025-03-07 | 1 | 1 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-04-14 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | 2025-05-13 | 1900-01-29 | 22 | 2025-05-13 | 2025-05-13 | 1 | 1 | 40 | 28 | 32 | 24 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 92 | 92 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-20 | 371 | 266 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-04-27 | 2024-04-16 | IOU Designed & Installed | N/A | No | N/A | 11188.67 | -62.16 | Unknown | Unknown | 77.82 | 11173.01 | 30609 | 7958.46 | 11188.67 | -3230.21 | Yes | N/A | N/A | 2022-04-27 | 2023-03-14 | 322 | 230 | 2023-03-14 | 2023-10-04 | 205 | 147 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | 2024-04-02 | 182 | 130 | Unknown | 2024-04-11 | Unknown | Unknown | 2024-04-16 | 2024-04-29 | 1900-01-13 | 10 | 2024-04-29 | 2024-04-25 | Unknown | Unknown | 504 | 360 | 219 | 157 | 723 | 517 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | -695 | -497 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-10-24 | 2024-10-30 | IOU Designed & Installed | N/A | No | N/A | 36.04 | Unknown | Unknown | Unknown | Unknown | 36.04 | 3981 | 1446.93 | 36.04 | 1410.89 | Yes | N/A | N/A | 2024-10-24 | 2024-10-23 | Unknown | Unknown | 2024-10-23 | 2024-10-24 | 2 | 2 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-10-30 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2024-11-14 | 1900-01-15 | 12 | 2024-11-14 | 2024-11-14 | 1 | 1 | 7 | 5 | 19 | 15 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-15 | -634 | -453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 61.39 | Unknown | Unknown | Unknown | Unknown | 61.39 | 3981 | 1959.1 | 61.39 | 1897.71 | Yes | N/A | N/A | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | 2024-08-21 | 7 | 5 | 2024-08-14 | 2024-08-27 | 9 | 7 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | 2024-09-19 | 2024-09-19 | 1 | 1 | 8 | 6 | 11 | 9 | 19 | 15 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-30 | -385 | -276 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 26.88 | Unknown | Unknown | Unknown | Unknown | 26.88 | 3941 | 856.84 | 26.88 | 829.96 | Yes | N/A | N/A | 2024-02-15 | 2023-11-16 | Unknown | Unknown | 2023-11-16 | 2024-02-15 | 92 | 66 | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | 2024-10-14 | 2024-10-10 | Unknown | Unknown | 0 | 0 | 92 | 66 | 92 | 66 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Spring Valley | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | -198 | -142 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | 2023-06-13 | IOU Designed & Installed | N/A | No | N/A | 2540.82 | 579.43 | Unknown | 423.66 | 36.54 | 1501.19 | Unknown | 1785.68 | 2540.82 | -755.14 | Yes | N/A | N/A | 2023-05-23 | 2023-05-23 | 1 | 1 | 2023-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | 2023-06-13 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | 2023-08-31 | 1900-03-20 | 58 | 2023-08-31 | 2023-08-31 | 1 | 1 | 23 | 17 | 81 | 59 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | Rancho Mission Viejo | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | 252 | 181 | No | 2022-11-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-22 | 2023-05-16 | 2023-10-03 | IOU Designed & Installed | N/A | Yes | 189 | 39516.32 | 2669.11 | Unknown | Unknown | 5261.72 | 31585.49 | Unknown | 31191.9 | 39516.32 | -8324.42 | Yes | N/A | N/A | 2022-11-22 | 2023-05-16 | 176 | 126 | 2023-05-16 | 2023-09-28 | 136 | 98 | 2023-05-25 | 2023-09-23 | 42 | 31 | 2023-09-19 | 2023-09-25 | 7 | 5 | 2023-09-28 | Unknown | Unknown | Unknown | 2023-09-28 | 2024-08-20 | 328 | 234 | 2023-10-03 | 2023-10-11 | 1900-01-08 | 7 | 2023-10-11 | 2023-10-11 | 1 | 1 | 218 | 157 | 481 | 345 | 699 | 502 | Steps 2,3,5,6,7 | 452 | 323 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 196 | 196 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-31 | -30 | -23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | 2024-06-13 | IOU Designed & Installed | N/A | No | N/A | -10.16 | -14.3 | Unknown | Unknown | Unknown | 4.14 | 3981 | 1239.05 | -10.16 | 1249.21 | Yes | N/A | N/A | 2024-05-21 | 2024-05-17 | Unknown | Unknown | 2024-05-17 | 2024-05-21 | 5 | 3 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2024-06-13 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-07-02 | 1900-01-19 | 14 | 2024-07-02 | 2024-07-01 | Unknown | Unknown | 24 | 18 | 25 | 17 | 49 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 770 | 770 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-09 | 431 | 308 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-14 | 2023-04-25 | 2024-07-18 | IOU Designed & Installed | N/A | No | N/A | 585983.16 | -6438.19 | Unknown | Unknown | 8288.97 | 584132.38 | 0 | 80704.73 | 585983.16 | -505278.43 | Yes | N/A | N/A | 2021-06-14 | 2023-04-21 | 677 | 485 | 2023-04-21 | 2024-07-01 | 438 | 312 | 2023-06-09 | 2023-06-28 | 20 | 14 | 2023-09-15 | 2024-08-21 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | Unknown | Unknown | Unknown | 2024-07-18 | 2025-01-13 | 1900-06-28 | 128 | 2025-01-13 | 2025-01-13 | 1 | 1 | 697 | 499 | 680 | 484 | 1377 | 983 | Steps 2,3,5,6,7 | 388 | 276 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | -231 | -166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | -2.81 | -4.35 | Unknown | Unknown | Unknown | 1.54 | 3981 | 1813.95 | -2.81 | 1816.76 | Yes | N/A | N/A | 2024-05-23 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-05-23 | 99 | 71 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-05-30 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-14 | 1900-01-15 | 12 | 2024-06-14 | 2024-06-14 | 1 | 1 | 8 | 6 | 116 | 84 | 124 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-15 | -489 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-08-12 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 1284.22 | Unknown | Unknown | Unknown | 10.08 | 1274.14 | 3981 | 1336.34 | 1284.22 | 52.12 | Yes | N/A | N/A | 2024-08-12 | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-08-26 | 33 | 23 | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2025-01-22 | 150 | 108 | Unknown | 2025-01-10 | Unknown | Unknown | 2025-01-22 | 2025-02-10 | 1900-01-19 | 14 | 2025-02-10 | 2025-03-13 | 32 | 24 | 150 | 108 | 85 | 61 | 235 | 169 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-08 | -605 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-04-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 26.97 | -11.07 | Unknown | Unknown | Unknown | 38.04 | 3981 | 828.63 | 26.97 | 801.66 | Yes | N/A | N/A | 2023-03-22 | 2023-04-10 | 20 | 14 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | Unknown | Unknown | 2023-06-14 | 2023-06-14 | 1 | 1 | 20 | 14 | 1 | 1 | 21 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 17.45 | 17.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-17 | -459 | -328 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 300.38 | Unknown | Unknown | Unknown | -429.99 | 730.37 | 3891 | 1909.69 | 300.38 | 1609.31 | Yes | N/A | N/A | 2024-08-06 | 2024-08-22 | 17 | 13 | 2024-08-22 | 2024-08-22 | 1 | 1 | 2024-08-22 | 2024-10-22 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2025-01-28 | 99 | 71 | Unknown | 2025-01-23 | Unknown | Unknown | 2025-01-28 | 2025-02-12 | 1900-01-15 | 12 | 2025-02-12 | 2025-02-12 | 1 | 1 | 178 | 128 | 18 | 14 | 196 | 142 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-22 | -226 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-14 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | -546.36 | Unknown | Unknown | Unknown | -1530 | 983.64 | 3981 | 3120.72 | -546.36 | 3667.08 | Yes | N/A | N/A | 2025-01-14 | 2024-12-04 | Unknown | Unknown | 2024-12-04 | 2025-01-23 | 51 | 37 | 2025-01-23 | 2025-04-01 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-04-01 | 56 | 40 | Unknown | 2025-04-01 | Unknown | Unknown | 2025-04-01 | 2025-04-10 | 1900-01-09 | 8 | 2025-04-10 | 2025-04-10 | 1 | 1 | 125 | 89 | 62 | 46 | 187 | 135 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-16 | 407 | 292 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-20 | 2021-07-29 | 2023-03-15 | IOU Designed & Installed | N/A | No | N/A | -7.43 | -5.38 | Unknown | Unknown | Unknown | -2.05 | Unknown | 483.49 | -7.43 | 490.92 | Yes | N/A | N/A | 2021-07-20 | 2023-03-30 | 619 | 443 | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-07-29 | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-15 | 2023-07-28 | 1900-05-15 | 98 | 2023-07-28 | 2023-07-28 | 1 | 1 | 619 | 443 | 137 | 99 | 756 | 542 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 11.4 | 11.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-03 | -616 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-10-13 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | 1246.67 | 803.28 | Unknown | 65.07 | Unknown | 378.32 | 3241 | 1215.09 | 1246.67 | -31.58 | Yes | N/A | N/A | 2023-09-29 | 2023-10-13 | 15 | 11 | 2023-10-13 | 2023-10-13 | 1 | 1 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-10-13 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-10-26 | 1900-01-13 | 10 | 2023-10-26 | 2023-10-26 | 1 | 1 | 16 | 12 | 16 | 12 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | -612 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-19 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 2682.59 | 495.54 | Unknown | 83.59 | Unknown | 2103.46 | Unknown | 1476.56 | 2682.59 | -1206.03 | Yes | N/A | N/A | 2024-09-13 | 2024-09-19 | 7 | 5 | 2024-09-19 | 2024-09-19 | 1 | 1 | 2024-09-19 | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-07 | 18 | 12 | 2024-09-19 | 2024-10-31 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-14 | 1900-01-14 | 11 | 2024-11-14 | 2024-11-14 | 1 | 1 | 50 | 36 | 35 | 25 | 85 | 61 | Steps 2,3,5,6,7 | 18 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -641 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-03 | 2024-02-25 | IOU Designed & Installed | N/A | No | N/A | 874.04 | 489.8 | Unknown | 35.57 | Unknown | 348.67 | Unknown | 158.79 | 874.04 | -715.25 | Yes | N/A | N/A | 2024-01-02 | 2024-01-09 | 8 | 6 | 2024-01-09 | 2024-01-09 | 1 | 1 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-02-25 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-02-25 | 2024-02-28 | 1900-01-03 | 3 | 2024-02-28 | 2024-02-28 | 1 | 1 | 56 | 40 | 6 | 5 | 62 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-31 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2024-01-08 | 2024-01-10 | IOU Designed & Installed | N/A | No | N/A | 302.29 | -9.23 | Unknown | Unknown | Unknown | 311.52 | Unknown | 933.46 | 302.29 | 631.17 | Yes | N/A | N/A | 2023-12-13 | 2024-01-08 | 27 | 19 | 2024-01-08 | 2024-01-08 | 1 | 1 | 2024-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-01-10 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-01-24 | 1900-01-14 | 11 | 2024-01-24 | 2024-01-24 | 1 | 1 | 30 | 22 | 17 | 13 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | DANA POINT | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-26 | -650 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1073.53 | -20.56 | Unknown | Unknown | Unknown | 1094.09 | Unknown | 1663.09 | 1073.53 | 589.56 | Yes | N/A | N/A | 2024-09-10 | 2024-09-16 | 7 | 5 | 2024-09-16 | 2024-09-23 | 8 | 6 | 2024-09-23 | Unknown | Unknown | Unknown | 2024-09-23 | 2024-10-30 | 38 | 28 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | 2024-10-14 | 2024-10-14 | 1 | 1 | 7 | 5 | 47 | 35 | 54 | 40 | Steps 2,3,5,6,7 | 37 | 27 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | -491 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-17 | 2024-06-05 | IOU Designed & Installed | N/A | No | N/A | 4.16 | -3.69 | Unknown | Unknown | Unknown | 7.85 | 3241 | 802.08 | 4.16 | 797.92 | Yes | N/A | N/A | 2024-04-16 | 2024-04-12 | Unknown | Unknown | 2024-04-12 | 2024-04-17 | 6 | 4 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-06-05 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-06-19 | 1900-01-14 | 11 | 2024-06-19 | 2024-06-19 | 1 | 1 | 50 | 36 | 22 | 16 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -613 | -438 | No | 2024-01-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-10 | 2024-03-26 | IOU Designed & Installed | N/A | Yes | 1 | 532.94 | 174.71 | Unknown | 18.3 | Unknown | 339.93 | 7962 | 634.41 | 532.94 | 101.47 | Yes | N/A | N/A | 2024-01-10 | 2024-01-11 | 2 | 2 | 2024-01-11 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-03-26 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-03-28 | 1900-01-02 | 3 | 2024-03-28 | 2024-03-28 | 1 | 1 | 79 | 57 | 4 | 4 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 80.05 | 80.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-26 | -231 | -166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 631.27 | -12.13 | Unknown | Unknown | 3.38 | 640.02 | 3981 | 505.38 | 631.27 | -125.89 | Yes | N/A | N/A | 2023-03-22 | 2023-03-29 | 8 | 6 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | Unknown | Unknown | Unknown | 2023-06-09 | Unknown | Unknown | 2023-06-09 | 2023-06-09 | 1 | 1 | 8 | 6 | 1 | 1 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-22 | -495 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-06 | 2024-10-25 | IOU Designed & Installed | N/A | No | N/A | -454.01 | 1028.07 | Unknown | 30.27 | -2032 | 519.65 | 3941 | 2031.52 | -454.01 | 2485.53 | Yes | N/A | N/A | 2024-05-06 | 2024-04-08 | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2024-11-12 | 1900-01-18 | 13 | 2024-11-12 | 2024-11-12 | 1 | 1 | 0 | 0 | 20 | 14 | 20 | 14 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-13 | -643 | -460 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-07 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 41.14 | Unknown | Unknown | Unknown | Unknown | 41.14 | Unknown | 1720.59 | 41.14 | 1679.45 | Yes | N/A | N/A | 2025-01-06 | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2025-01-07 | 22 | 16 | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-02-25 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-10 | 1900-01-13 | 10 | 2025-03-10 | 2025-03-10 | 1 | 1 | 50 | 36 | 37 | 27 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | -553 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-30 | 2025-06-16 | IOU Designed & Installed | N/A | No | N/A | 3.58 | Unknown | Unknown | Unknown | Unknown | 3.58 | Unknown | 118.25 | 3.58 | 114.67 | Yes | N/A | N/A | 2025-01-29 | 2025-06-09 | 132 | 94 | 2025-06-09 | 2025-06-09 | 1 | 1 | 2025-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-16 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-06-26 | 1900-01-10 | 9 | 2025-06-26 | 2025-06-26 | 1 | 1 | 140 | 100 | 13 | 11 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-05 | 71 | 52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-07-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 482.18 | -32.76 | Unknown | Unknown | 1.65 | 513.29 | 11943 | 1197.36 | 482.18 | 715.18 | Yes | N/A | N/A | 2023-05-22 | 2023-05-15 | Unknown | Unknown | 2023-05-15 | 2023-09-06 | 115 | 83 | 2023-07-25 | 2023-07-26 | 2 | 2 | 2023-07-26 | 2023-08-02 | 8 | 6 | 2023-09-06 | 2023-12-11 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-02-14 | Unknown | Unknown | 99 | 71 | 123 | 89 | 222 | 160 | Steps 2,3,5,6,7 | 43 | 31 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-18 | -543 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | 2025-03-14 | IOU Designed & Installed | N/A | No | N/A | 9781.81 | 3090.16 | Unknown | 202 | -2318.17 | 8807.82 | Unknown | 2343.03 | 9781.81 | -7438.78 | Yes | N/A | N/A | 2024-11-19 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-19 | 7 | 5 | 2024-11-19 | 2025-01-21 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2025-03-14 | 116 | 84 | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-04-23 | 1900-02-09 | 29 | 2025-04-23 | 2025-04-23 | 1 | 1 | 180 | 130 | 49 | 35 | 229 | 165 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 300 | 300 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-19 | -16 | -11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | Unknown | 2023-10-20 | IOU Designed & Installed | N/A | No | N/A | 616.7 | -13.06 | Unknown | Unknown | 6.03 | 623.73 | 3981 | 1980.78 | 616.7 | 1364.08 | Yes | N/A | N/A | 2023-03-20 | 2023-04-11 | 23 | 17 | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | 2023-10-20 | 215 | 155 | Unknown | 2023-09-21 | Unknown | Unknown | 2023-10-20 | 2023-11-03 | 1900-01-14 | 11 | 2023-11-03 | 2023-11-03 | 1 | 1 | 238 | 172 | 16 | 12 | 254 | 184 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -424 | -305 | No | 2024-08-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | 2025-03-03 | IOU Designed & Installed | N/A | Yes | 201 | 282.79 | -5.35 | Unknown | Unknown | Unknown | 288.14 | 3981 | 2180.63 | 282.79 | 1897.84 | Yes | N/A | N/A | 2024-08-01 | 2025-02-18 | 202 | 144 | 2025-02-18 | 2024-05-31 | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-03-03 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-17 | 1900-01-14 | 11 | 2025-03-17 | 2025-03-17 | 1 | 1 | 228 | 162 | 16 | 12 | 244 | 174 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | -597 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-13 | 2025-01-24 | IOU Designed & Installed | N/A | No | N/A | 429.61 | Unknown | Unknown | Unknown | 7.25 | 422.36 | 3981 | 1146.59 | 429.61 | 716.98 | Yes | N/A | N/A | 2024-11-01 | 2024-10-16 | Unknown | Unknown | 2024-10-16 | 2024-11-25 | 41 | 29 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-01-24 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-02-11 | 1900-01-18 | 13 | 2025-02-11 | 2025-02-11 | 1 | 1 | 61 | 45 | 61 | 43 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-03 | -598 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-13 | 2024-02-01 | IOU Designed & Installed | N/A | No | N/A | 9.07 | -10.95 | Unknown | Unknown | Unknown | 20.02 | Unknown | 891.5 | 9.07 | 882.43 | Yes | N/A | N/A | 2023-12-12 | 2023-11-28 | Unknown | Unknown | 2023-11-28 | 2023-12-13 | 16 | 12 | 2023-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-02-01 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-03-15 | 1900-02-12 | 32 | 2024-03-15 | 2024-03-15 | 1 | 1 | 51 | 37 | 61 | 45 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-03 | 163 | 117 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 543.1 | -11.47 | Unknown | Unknown | Unknown | 554.57 | 3981 | 905.47 | 543.1 | 362.37 | Yes | N/A | N/A | 2023-05-10 | 2023-06-07 | 29 | 21 | 2023-06-07 | 2023-06-08 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | 2024-01-30 | 237 | 169 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-02-13 | Unknown | Unknown | 266 | 190 | 2 | 2 | 268 | 192 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-14 | -639 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | 2024-02-06 | IOU Designed & Installed | N/A | No | N/A | -25.48 | -12.75 | Unknown | Unknown | Unknown | -12.73 | 3981 | 990.2 | -25.48 | 1015.68 | Yes | N/A | N/A | 2024-01-23 | 2023-12-19 | Unknown | Unknown | 2023-12-19 | 2024-01-23 | 36 | 26 | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-02-06 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-03-15 | 1900-02-07 | 29 | 2024-03-15 | 2024-03-15 | 1 | 1 | 15 | 11 | 76 | 56 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | 84.05 | 84.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-20 | -531 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-23 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | -6.09 | -25.52 | Unknown | Unknown | Unknown | 19.43 | 3981 | 1591.13 | -6.09 | 1597.22 | Yes | N/A | N/A | 2025-01-23 | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-01-23 | 16 | 12 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-03-06 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-04-07 | 1900-02-01 | 23 | 2025-04-07 | 2025-04-07 | 1 | 1 | 43 | 31 | 50 | 36 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-11 | -489 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | 2024-07-01 | IOU Designed & Installed | N/A | No | N/A | 24.28 | -18.74 | Unknown | Unknown | Unknown | 43.02 | 7882 | 1419.07 | 24.28 | 1394.79 | Yes | N/A | N/A | 2023-12-04 | 2023-11-20 | Unknown | Unknown | 2023-11-20 | 2023-12-04 | 15 | 11 | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2024-07-01 | 211 | 151 | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-07-08 | 1900-01-07 | 6 | 2024-07-08 | 2024-07-10 | 3 | 3 | 211 | 151 | 26 | 20 | 237 | 171 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | CARLSBAD | 148.1 | 148.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-30 | 222 | 160 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-05-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 306.14 | -12.46 | Unknown | Unknown | Unknown | 318.6 | 3981 | 933.44 | 306.14 | 627.3 | Yes | N/A | N/A | 2023-04-11 | 2023-05-08 | 28 | 20 | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | 2023-08-29 | 114 | 82 | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | Unknown | Unknown | 2023-12-08 | 2023-12-08 | 1 | 1 | 28 | 20 | 115 | 83 | 143 | 103 | Steps 2,3,5,6,7 | 113 | 81 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-05-12 | -42 | -31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-23 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | 29293.12 | 3831.94 | Unknown | Unknown | 401.47 | 25059.71 | 63503 | 21237.1 | 29293.12 | -8056.02 | Yes | N/A | N/A | 2024-04-17 | 2024-04-12 | Unknown | Unknown | 2024-04-12 | 2024-06-19 | 69 | 49 | 2024-04-19 | 2024-05-08 | 6 | 4 | 2024-05-08 | 2024-06-26 | 36 | 26 | 2024-06-19 | Unknown | Unknown | Unknown | 2024-11-13 | 2025-02-10 | 90 | 64 | 2025-02-24 | 2025-03-31 | 1900-02-04 | 26 | 2025-03-31 | 2025-03-31 | 1 | 1 | 6 | 4 | 232 | 166 | 238 | 170 | Steps 2,3,5,6,7 | 68 | 48 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-02-08 | -254 | -182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-16 | 2024-05-08 | IOU Designed & Installed | N/A | No | N/A | -4796.69 | 698.15 | Unknown | Unknown | -9545 | 4050.16 | 3981 | 13175.54 | -4796.69 | 17972.23 | Yes | N/A | N/A | 2024-02-16 | 2023-12-20 | Unknown | Unknown | 2023-12-20 | 2024-03-08 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-04-30 | 56 | 40 | 2024-03-08 | 2024-04-18 | 42 | 30 | 2024-04-02 | 2024-05-01 | 30 | 22 | 2024-05-08 | 2024-06-04 | 1900-01-27 | 20 | 2024-06-04 | 2024-05-30 | Unknown | Unknown | 42 | 30 | 194 | 140 | 236 | 170 | Steps 2,3,5,6,7 | 69 | 49 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-21 | 410 | 293 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-07 | 2024-09-18 | IOU Designed & Installed | N/A | No | N/A | 49975.87 | 4987.54 | Unknown | Unknown | 167.65 | 44820.68 | Unknown | 22941.97 | 49975.87 | -27033.9 | Yes | N/A | N/A | 2024-02-07 | 2024-02-07 | 1 | 1 | 2024-02-07 | 2024-08-29 | 205 | 147 | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | 2024-08-13 | 34 | 24 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-11-04 | 1900-02-16 | 34 | 2024-11-04 | 2024-11-04 | 1 | 1 | 1 | 1 | 288 | 206 | 289 | 207 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | -472 | -339 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-04-12 | 2024-05-16 | IOU Designed & Installed | N/A | No | N/A | 1661.47 | -13.88 | Unknown | Unknown | Unknown | 1675.35 | 3981 | 1142.13 | 1661.47 | -519.34 | Yes | N/A | N/A | 2024-03-12 | 2024-04-12 | 32 | 24 | 2024-04-12 | 2024-04-12 | 1 | 1 | 2024-04-12 | Unknown | Unknown | Unknown | 2024-04-12 | 2024-05-09 | 28 | 20 | 2024-04-12 | 2024-05-16 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-06-24 | 1900-02-08 | 28 | 2024-06-24 | 2024-06-24 | 1 | 1 | 67 | 49 | 70 | 50 | 137 | 99 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-19 | -599 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-02 | 2024-01-16 | IOU Designed & Installed | N/A | No | N/A | -16.74 | -13.22 | Unknown | Unknown | Unknown | -3.52 | Unknown | 158.79 | -16.74 | 175.53 | Yes | N/A | N/A | 2024-01-02 | 2023-10-10 | Unknown | Unknown | 2023-10-10 | 2024-01-05 | 88 | 64 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-01-16 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-01-29 | 1900-01-13 | 10 | 2024-01-29 | 2024-01-29 | 1 | 1 | 12 | 8 | 103 | 75 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | 352 | 352 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-30 | 108 | 78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-06-09 | 2023-06-21 | IOU Designed & Installed | N/A | No | N/A | 2640.66 | Unknown | Unknown | Unknown | Unknown | 2640.66 | Unknown | 1573.01 | 2640.66 | -1067.65 | Yes | N/A | N/A | 2023-06-09 | 2023-06-09 | 1 | 1 | 2023-06-09 | 2023-06-13 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | 2023-08-16 | 1900-02-25 | 41 | 2023-08-16 | 2023-08-16 | 1 | 1 | 1 | 1 | 63 | 45 | 64 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 74.05 | 74.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | -583 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-07 | 2025-01-31 | IOU Designed & Installed | N/A | No | N/A | 2090.69 | Unknown | Unknown | Unknown | Unknown | 2090.69 | 3981 | 2229.43 | 2090.69 | 138.74 | Yes | N/A | N/A | 2024-10-07 | 2024-10-29 | 23 | 17 | 2024-10-29 | 2024-11-11 | 14 | 10 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2025-01-31 | 82 | 60 | Unknown | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-02-18 | 1900-01-18 | 13 | 2025-02-18 | 2025-02-12 | Unknown | Unknown | 105 | 77 | 33 | 23 | 138 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-08 | -293 | -210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-29 | 2023-09-29 | IOU Designed & Installed | N/A | No | N/A | 2934 | Unknown | Unknown | Unknown | -1976 | 4910 | Unknown | 1976.39 | 2934 | -957.61 | Yes | N/A | N/A | 2023-08-16 | 2023-08-29 | 14 | 10 | 2023-08-29 | 2023-09-05 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | Unknown | Unknown | 2023-09-29 | 2023-10-20 | 1900-01-21 | 16 | 2023-10-20 | 2023-10-20 | 1 | 1 | 14 | 10 | 31 | 23 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 74.05 | 74.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | -534 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-22 | 2024-03-28 | 2024-06-19 | IOU Designed & Installed | N/A | No | N/A | 12.75 | -11.35 | Unknown | Unknown | Unknown | 24.1 | 3981 | 644.75 | 12.75 | 632 | Yes | N/A | N/A | 2024-03-22 | 2023-12-21 | Unknown | Unknown | 2023-12-21 | 2024-03-28 | 99 | 71 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-06-19 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-06-24 | 1900-01-05 | 4 | 2024-06-24 | 2024-06-21 | Unknown | Unknown | 84 | 60 | 105 | 75 | 189 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 12.05 | 12.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-20 | -614 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-07-12 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 240.28 | -4.28 | Unknown | Unknown | Unknown | 244.56 | 3981 | 1574.85 | 240.28 | 1334.57 | Yes | N/A | N/A | 2024-06-12 | 2024-05-23 | Unknown | Unknown | 2024-05-23 | 2024-07-22 | 61 | 43 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-09-06 | 47 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-13 | 1900-01-07 | 6 | 2024-09-13 | 2024-09-13 | 1 | 1 | 47 | 35 | 70 | 50 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | -502 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-10-01 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 9075.79 | Unknown | Unknown | Unknown | Unknown | 9075.79 | 3981 | 1327.99 | 9075.79 | -7747.8 | Yes | N/A | N/A | 2024-08-12 | 2024-10-03 | 53 | 39 | 2024-10-03 | 2025-01-22 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-01-23 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-03-10 | 1900-02-02 | 24 | 2025-03-10 | 2025-03-04 | Unknown | Unknown | 55 | 41 | 146 | 104 | 201 | 145 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 79 | 79 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-21 | -209 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-18 | 2023-08-10 | IOU Designed & Installed | N/A | No | N/A | -12.98 | -9.43 | Unknown | Unknown | Unknown | -3.55 | Unknown | 153.87 | -12.98 | 166.85 | Yes | N/A | N/A | 2023-07-05 | 2023-07-05 | 1 | 1 | 2023-07-05 | 2023-07-18 | 14 | 10 | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-08-10 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-08-25 | 1900-01-15 | 12 | 2023-08-25 | 2023-08-25 | 1 | 1 | 25 | 19 | 31 | 23 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-24 | -71 | -52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-08-02 | 2024-02-27 | IOU Designed & Installed | N/A | No | N/A | -1350.53 | -19.51 | Unknown | Unknown | -1643 | 311.98 | Unknown | 1643.23 | -1350.53 | 2993.76 | Yes | N/A | N/A | 2023-07-26 | 2023-07-26 | 1 | 1 | 2023-07-26 | 2023-11-13 | 111 | 79 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2024-02-27 | 2024-03-14 | 1900-01-16 | 13 | 2024-03-14 | 2024-03-14 | 1 | 1 | 1 | 1 | 129 | 93 | 130 | 94 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-23 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-09-06 | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | 20.07 | Unknown | Unknown | Unknown | Unknown | 20.07 | Unknown | 1639.56 | 20.07 | 1619.49 | Yes | N/A | N/A | 2024-08-21 | 2024-08-05 | Unknown | Unknown | 2024-08-05 | 2024-09-06 | 33 | 25 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-17 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-09-26 | 1900-01-09 | 8 | 2024-09-26 | 2024-09-26 | 1 | 1 | 12 | 8 | 44 | 34 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -174 | -125 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-09-28 | 2025-06-10 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 17259.36 | 6377.91 | Unknown | Unknown | -81320.97 | 92202.42 | 0 | 69957.91 | 17259.36 | 52698.55 | Yes | N/A | N/A | 2023-09-28 | 2024-02-20 | 146 | 104 | 2024-02-20 | 2024-06-12 | 114 | 82 | 2024-03-06 | 2024-03-18 | 13 | 9 | 2024-06-13 | 2025-01-29 | 231 | 165 | 2024-11-14 | Unknown | Unknown | Unknown | 2024-11-14 | 2025-04-22 | 160 | 114 | 2025-06-10 | 2025-06-10 | 1899-12-31 | 1 | 2025-06-10 | 2025-06-10 | 1 | 1 | 159 | 113 | 507 | 363 | 666 | 476 | Steps 2,3,5,6,7 | 174 | 124 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 151.15 | 151.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-07 | -310 | -223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | 2024-01-02 | IOU Designed & Installed | N/A | No | N/A | 1074.36 | 363.64 | Unknown | Unknown | Unknown | 710.72 | Unknown | 288.14 | 1074.36 | -786.22 | Yes | N/A | N/A | 2023-12-20 | 2023-12-20 | 1 | 1 | 2023-12-20 | 2023-12-20 | 1 | 1 | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-01-02 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | 2024-01-02 | 1899-12-31 | 1 | 2024-01-02 | 2024-01-02 | 1 | 1 | 15 | 11 | 3 | 3 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | VALLEY CENTER | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-14 | -515 | -368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2024-01-23 | 2024-02-08 | IOU Designed & Installed | N/A | No | N/A | 176.13 | 41.93 | Unknown | Unknown | 0.32 | 133.88 | 3981 | 663.84 | 176.13 | 487.71 | Yes | N/A | N/A | 2023-08-16 | 2023-06-29 | Unknown | Unknown | 2023-06-29 | 2024-01-23 | 209 | 149 | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-02-08 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-03-15 | 1900-02-05 | 27 | 2024-03-15 | 2024-02-15 | Unknown | Unknown | 17 | 13 | 246 | 176 | 263 | 189 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CAMPO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | -658 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | 2030.97 | 509.4 | Unknown | 29.81 | Unknown | 1491.76 | Unknown | 1618.58 | 2030.97 | -412.39 | Yes | N/A | N/A | 2025-03-10 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-03-13 | 17 | 13 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-04-25 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-04-25 | 1899-12-31 | 1 | 2025-04-25 | 2025-04-25 | 1 | 1 | 44 | 32 | 19 | 15 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | Applicant Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | 439 | 315 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-12 | 2022-12-12 | 2024-02-16 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 21104.21 | 2280.57 | Unknown | Unknown | Unknown | 18823.64 | 328322.16 | 9620.39 | 21104.21 | -11483.82 | Yes | N/A | N/A | 2022-12-12 | 2023-04-26 | 136 | 98 | 2023-04-26 | 2023-06-28 | 64 | 46 | 2023-04-27 | 2023-06-03 | 38 | 27 | 2023-06-26 | 2023-06-29 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-03-15 | 1900-01-28 | 21 | 2024-03-15 | 2024-03-15 | 1 | 1 | 174 | 125 | 98 | 72 | 272 | 197 | Steps 2,3,5,6,7 | 62 | 44 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-16 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-18 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | 867.68 | -0.94 | Unknown | Unknown | Unknown | 868.62 | Unknown | 2146.61 | 867.68 | 1278.93 | Yes | N/A | N/A | 2025-04-18 | 2025-03-18 | Unknown | Unknown | 2025-03-18 | 2025-04-18 | 32 | 24 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-04-22 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-20 | 1900-01-28 | 21 | 2025-05-20 | 2025-05-20 | 1 | 1 | 5 | 3 | 62 | 46 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 79 | 79 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-16 | 406 | 291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-09-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2404.23 | -64.21 | Unknown | Unknown | -474 | 2942.44 | 7962 | 1311.38 | 2404.23 | -1092.85 | Yes | N/A | N/A | 2023-05-03 | 2023-06-30 | 59 | 43 | 2023-06-30 | 2024-05-31 | 337 | 241 | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | 2024-03-06 | 21 | 15 | 2024-05-31 | 2024-06-06 | 7 | 5 | Unknown | 2024-06-07 | Unknown | Unknown | Unknown | 2024-07-01 | Unknown | Unknown | 2024-07-01 | 2024-06-25 | Unknown | Unknown | 66 | 48 | 358 | 256 | 424 | 304 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | -214 | -154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-17 | 2023-11-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | -16958.27 | Unknown | Unknown | Unknown | -31025 | 14066.73 | Unknown | 16486.27 | -16958.27 | 33444.54 | Yes | N/A | N/A | 2023-11-17 | 2024-10-23 | 342 | 244 | 2024-10-23 | 2024-12-09 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-09-25 | 36 | 26 | 2024-12-09 | 2025-01-28 | 51 | 37 | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | 2025-04-09 | 2025-04-08 | Unknown | Unknown | 393 | 281 | 84 | 60 | 477 | 341 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | 160 | 160 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | 22 | 16 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-05 | 2023-07-13 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 178505 | 5929.81 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-05 | 2023-07-13 | 190 | 136 | 2023-07-13 | 2023-09-26 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | 2025-06-23 | 2025-06-23 | 1899-12-31 | 1 | 2025-06-23 | 2025-06-23 | 1 | 1 | 190 | 136 | 78 | 56 | 268 | 192 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | -337 | -242 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-02-28 | 2024-03-04 | IOU Designed & Installed | N/A | No | N/A | -7.39 | -6 | Unknown | Unknown | Unknown | -1.39 | Unknown | 163.83 | -7.39 | 171.22 | Yes | N/A | N/A | 2024-02-28 | 2024-02-28 | 1 | 1 | 2024-02-28 | 2024-02-28 | 1 | 1 | 2024-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-03-04 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-03-27 | 1900-01-23 | 18 | 2024-03-27 | 2024-03-27 | 1 | 1 | 7 | 5 | 26 | 20 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-18 | -487 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-09-14 | IOU Designed & Installed | N/A | No | N/A | -3.44 | -6.81 | Unknown | Unknown | Unknown | 3.37 | Unknown | 676.16 | -3.44 | 679.6 | Yes | N/A | N/A | 2023-03-29 | 2023-03-30 | 2 | 2 | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | 2023-09-14 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-09-19 | 1900-01-05 | 4 | 2023-09-19 | 2023-09-19 | 1 | 1 | 171 | 123 | 7 | 5 | 178 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | -234 | -168 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-21 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | 1.46 | Unknown | Unknown | Unknown | Unknown | 1.46 | 3961 | 192.83 | 1.46 | 191.37 | Yes | N/A | N/A | 2024-03-07 | 2024-05-29 | 84 | 60 | 2024-05-29 | 2024-06-10 | 13 | 9 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2025-06-11 | 367 | 263 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-11 | 1899-12-31 | 1 | 2025-06-11 | 2025-06-11 | 1 | 1 | 451 | 323 | 15 | 11 | 466 | 334 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 110.05 | 110.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-04 | 85 | 62 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 9875.76 | Unknown | Unknown | Unknown | Unknown | 9875.76 | 3981 | 853.41 | 9875.76 | -9022.35 | Yes | N/A | N/A | 2024-08-13 | 2024-08-12 | Unknown | Unknown | 2024-08-12 | 2024-12-06 | 117 | 85 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-01-24 | 50 | 36 | Unknown | 2025-02-04 | Unknown | Unknown | 2025-02-11 | 2025-03-03 | 1900-01-20 | 15 | 2025-03-03 | 2025-02-27 | Unknown | Unknown | 50 | 36 | 138 | 100 | 188 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 2203.05 | 2203.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-02-02 | -106 | -77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-10-16 | IOU Designed & Installed | N/A | No | N/A | 1444.86 | 456.09 | Unknown | 147.4 | Unknown | 841.37 | 3981 | 1561.26 | 1444.86 | 116.4 | Yes | N/A | N/A | 2023-03-07 | 2023-03-07 | 1 | 1 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | 2023-10-16 | 224 | 160 | Unknown | 2023-09-22 | Unknown | Unknown | 2023-10-16 | 2023-10-19 | 1900-01-03 | 4 | 2023-10-19 | 2023-10-19 | 1 | 1 | 225 | 161 | 5 | 5 | 230 | 166 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-04-05 | 43 | 31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | 2023-04-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3725.5 | -118.27 | Unknown | Unknown | -2472 | 6315.77 | 0 | 481.86 | 3725.5 | -3243.64 | Yes | N/A | N/A | 2023-04-05 | 2023-04-05 | 1 | 1 | 2023-04-05 | 2023-09-14 | 163 | 117 | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-04-20 | 15 | 11 | 2023-09-14 | 2023-12-26 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | Unknown | Unknown | 2024-05-20 | 2024-05-18 | Unknown | Unknown | 105 | 75 | 178 | 128 | 283 | 203 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-10 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-04-15 | 2025-05-14 | IOU Designed & Installed | N/A | No | N/A | -5449.45 | 1921.64 | Unknown | 101.61 | -8316 | 843.3 | Unknown | 8315.72 | -5449.45 | 13765.17 | Yes | N/A | N/A | 2025-03-05 | 2025-03-05 | 1 | 1 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-05-14 | 1899-12-31 | 1 | 2025-05-14 | 2025-05-14 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-08 | -275 | -198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-10-18 | 2024-03-20 | IOU Designed & Installed | N/A | No | N/A | 11.21 | -9.92 | Unknown | Unknown | Unknown | 21.13 | 3981 | 1098.01 | 11.21 | 1086.8 | Yes | N/A | N/A | 2023-09-08 | 2023-10-17 | 40 | 28 | 2023-10-17 | 2023-10-17 | 1 | 1 | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | 2024-03-20 | 155 | 111 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-04-09 | 1900-01-20 | 15 | 2024-04-09 | 2024-04-08 | Unknown | Unknown | 195 | 139 | 22 | 16 | 217 | 155 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 138.05 | 138.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | -218 | -157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-02-23 | 2024-05-24 | IOU Designed & Installed | N/A | No | N/A | 635.63 | 335.26 | Unknown | 36.56 | Unknown | 263.81 | 3981 | 867.88 | 635.63 | 232.25 | Yes | N/A | N/A | 2024-02-23 | 2023-11-20 | Unknown | Unknown | 2023-11-20 | 2024-02-23 | 96 | 70 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-05-24 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-06-27 | 1900-02-03 | 25 | 2024-06-27 | 2024-06-27 | 1 | 1 | 92 | 66 | 132 | 96 | 224 | 162 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-28 | -252 | -181 | No | 2022-07-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-08 | 2022-07-08 | 2023-06-15 | IOU Designed & Installed | N/A | Yes | 251 | -3.53 | -10.44 | Unknown | Unknown | Unknown | 6.91 | Unknown | 970.06 | -3.53 | 973.59 | Yes | N/A | N/A | 2022-07-08 | 2023-03-17 | 253 | 181 | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-07-08 | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | 2023-09-19 | 1900-04-06 | 69 | 2023-09-19 | 2023-09-19 | 1 | 1 | 253 | 181 | 98 | 70 | 351 | 251 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-03 | -591 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-08 | 2024-11-04 | IOU Designed & Installed | N/A | No | N/A | 1186.13 | Unknown | Unknown | Unknown | 4.91 | 1181.22 | 3981 | 1090.55 | 1186.13 | -95.58 | Yes | N/A | N/A | 2024-08-05 | 2024-09-16 | 43 | 31 | 2024-09-16 | 2024-09-16 | 1 | 1 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-11-04 | 50 | 36 | Unknown | 2024-10-30 | Unknown | Unknown | 2024-11-04 | 2024-11-19 | 1900-01-15 | 12 | 2024-11-19 | 2024-11-19 | 1 | 1 | 93 | 67 | 18 | 14 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | 325 | 232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 480.74 | -22.63 | Unknown | Unknown | 0.74 | 502.63 | 3981 | 881.17 | 480.74 | 400.43 | Yes | N/A | N/A | 2023-05-16 | 2024-03-05 | 295 | 211 | 2024-03-05 | 2024-03-20 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-04-10 | 9 | 7 | 2024-03-20 | 2024-05-20 | 62 | 44 | Unknown | 2024-05-14 | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-05-20 | Unknown | Unknown | 357 | 255 | 25 | 19 | 382 | 274 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-23 | 29 | 22 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | 2023-02-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 546.11 | -4.77 | Unknown | Unknown | 97.59 | 453.29 | 7962 | 283.56 | 546.11 | -262.55 | Yes | N/A | N/A | 2022-12-29 | 2023-02-10 | 44 | 32 | 2023-02-10 | 2023-07-12 | 153 | 109 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2023-09-21 | Unknown | Unknown | 44 | 32 | 153 | 109 | 197 | 141 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | -676 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | Unknown | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | 44.19 | Unknown | Unknown | Unknown | Unknown | 44.19 | 3981 | 1481.67 | 44.19 | 1437.48 | Yes | N/A | N/A | 2024-07-31 | 2024-07-31 | 1 | 1 | 2024-07-31 | 2024-07-31 | 1 | 1 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-09-03 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-09-16 | 1900-01-13 | 10 | 2024-09-16 | 2024-09-16 | 1 | 1 | 36 | 26 | 16 | 12 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-30 | -218 | -157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 2010.8 | 601.05 | Unknown | 147.27 | Unknown | 1262.48 | 3241 | 942.21 | 2010.8 | -1068.59 | Yes | N/A | N/A | 2024-03-11 | 2024-03-11 | 1 | 1 | 2024-03-11 | 2024-03-11 | 1 | 1 | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | 2024-03-25 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-03-26 | 1900-01-01 | 2 | 2024-03-26 | 2024-03-26 | 1 | 1 | 16 | 12 | 4 | 4 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CHULA VISTA | N/A | 630 | 630 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-23 | -539 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2024-01-25 | IOU Designed & Installed | N/A | No | N/A | 722.31 | -6.36 | Unknown | Unknown | 15.26 | 713.41 | 3981 | 776.76 | 722.31 | 54.45 | Yes | N/A | N/A | 2023-09-27 | 2023-08-01 | Unknown | Unknown | 2023-08-01 | 2023-11-10 | 102 | 74 | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2024-01-25 | 77 | 55 | Unknown | 2023-11-20 | Unknown | Unknown | 2024-01-25 | 2024-01-31 | 1900-01-06 | 5 | 2024-01-31 | 2024-01-31 | 1 | 1 | 77 | 55 | 110 | 80 | 187 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-22 | -383 | -274 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 813.91 | -5.65 | Unknown | Unknown | Unknown | 819.56 | Unknown | 499.14 | 813.91 | -314.77 | Yes | N/A | N/A | 2025-01-22 | 2025-01-22 | 1 | 1 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-02-25 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-04 | 1900-01-07 | 6 | 2025-03-04 | 2025-03-04 | 1 | 1 | 35 | 25 | 9 | 7 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-16 | 325 | 234 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1007.65 | Unknown | Unknown | Unknown | Unknown | 1007.65 | 1408 | 472.31 | 1007.65 | -535.34 | Yes | N/A | N/A | 2024-05-03 | 2024-05-16 | 14 | 10 | 2024-05-16 | 2024-06-20 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2025-02-03 | 18 | 14 | 2024-06-20 | 2025-02-10 | 236 | 168 | Unknown | 2025-03-04 | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-03-07 | Unknown | Unknown | 250 | 178 | 54 | 40 | 304 | 218 | Steps 2,3,5,6,7 | 228 | 162 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 307 | 307 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | -93 | -68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 740.03 | 183.4 | Unknown | 100.27 | 5.22 | 451.14 | 3981 | 2487.01 | 740.03 | 1746.98 | Yes | N/A | N/A | 2023-09-06 | 2024-01-12 | 129 | 93 | 2024-01-12 | 2024-01-12 | 1 | 1 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2024-04-16 | 1 | 1 | 129 | 93 | 2 | 2 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 570 | 570 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 455 | 326 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-27 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2814.32 | -13.95 | Unknown | Unknown | 13.06 | 2815.21 | 77426 | 11501.4 | 2814.32 | 8687.08 | Yes | N/A | N/A | 2022-06-27 | 2023-03-01 | 248 | 178 | 2023-03-01 | 2023-06-15 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | Unknown | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-02-28 | Unknown | Unknown | 248 | 178 | 107 | 77 | 355 | 255 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 82 | 82 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -540 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 1052.21 | Unknown | Unknown | Unknown | Unknown | 1052.21 | 3981 | 1206.27 | 1052.21 | 154.06 | Yes | N/A | N/A | 2024-09-27 | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-09-27 | 2 | 2 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2025-02-05 | 132 | 94 | Unknown | 2025-01-31 | Unknown | Unknown | 2025-02-05 | 2025-02-11 | 1900-01-06 | 5 | 2025-02-11 | 2025-02-11 | 1 | 1 | 132 | 94 | 10 | 8 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -225 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 940.5 | -16.36 | Unknown | Unknown | Unknown | 956.86 | Unknown | 468.05 | 940.5 | -472.45 | Yes | N/A | N/A | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | 2024-08-13 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-06-19 | 42 | 30 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | 2024-09-10 | 2024-09-10 | 1 | 1 | 2 | 2 | 148 | 106 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -291 | -208 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-28 | 2023-12-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1080.58 | 360.23 | Unknown | Unknown | 3.39 | 716.96 | 3981 | 2147.34 | 1080.58 | 1066.76 | Yes | N/A | N/A | 2023-12-28 | 2023-12-27 | Unknown | Unknown | 2023-12-27 | 2024-01-16 | 21 | 15 | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 0 | 0 | 22 | 16 | 22 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 42.05 | 42.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -415 | -298 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | 2025-06-16 | IOU Designed & Installed | N/A | No | N/A | 2844.57 | 727.49 | Unknown | Unknown | Unknown | 2117.08 | 3981 | 1465.36 | 2844.57 | -1379.21 | Yes | N/A | N/A | 2024-09-19 | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-09-19 | 42 | 30 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2025-06-16 | 271 | 193 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-06-16 | 1899-12-31 | 1 | 2025-06-16 | 2025-06-16 | 1 | 1 | 271 | 193 | 44 | 32 | 315 | 225 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-03 | -64 | -46 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2024-02-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 30.41 | Unknown | Unknown | Unknown | Unknown | 30.41 | 0 | 924.49 | 30.41 | 894.08 | Yes | N/A | N/A | 2023-09-21 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2024-02-02 | 220 | 158 | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | Unknown | Unknown | 2025-02-28 | 2025-02-28 | 1 | 1 | 0 | 0 | 221 | 159 | 221 | 159 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-06 | -469 | -336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-05 | 2024-06-04 | IOU Designed & Installed | N/A | No | N/A | 597.56 | -8.72 | Unknown | Unknown | 7 | 599.28 | Unknown | 1027.39 | 597.56 | 429.83 | Yes | N/A | N/A | 2024-01-04 | 2023-12-19 | Unknown | Unknown | 2023-12-19 | 2024-01-05 | 18 | 14 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-06-04 | 152 | 108 | Unknown | 2024-05-14 | Unknown | Unknown | 2024-06-04 | 2024-06-24 | 1900-01-20 | 15 | 2024-06-24 | 2024-06-24 | 1 | 1 | 152 | 108 | 40 | 30 | 192 | 138 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-30 | -605 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-03 | 2023-09-27 | IOU Designed & Installed | N/A | No | N/A | -3.25 | -5.97 | Unknown | Unknown | Unknown | 2.72 | Unknown | 148.7 | -3.25 | 151.95 | Yes | N/A | N/A | 2023-08-03 | 2023-08-30 | 28 | 20 | 2023-08-30 | 2023-08-30 | 1 | 1 | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-09-27 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-10-03 | 1900-01-06 | 5 | 2023-10-03 | 2023-10-03 | 1 | 1 | 57 | 41 | 9 | 7 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | -663 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-13 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 21.93 | Unknown | Unknown | Unknown | Unknown | 21.93 | Unknown | 1603.77 | 21.93 | 1581.84 | Yes | N/A | N/A | 2024-08-07 | 2024-08-13 | 7 | 5 | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-09-10 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-23 | 1900-01-13 | 10 | 2024-09-23 | 2024-09-23 | 1 | 1 | 36 | 26 | 16 | 12 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-19 | -8 | -7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-08 | 2023-06-01 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | -18.64 | -13.51 | Unknown | Unknown | Unknown | -5.13 | 3981 | 464.78 | -18.64 | 483.42 | Yes | N/A | N/A | 2022-12-08 | 2023-06-01 | 176 | 126 | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | 2023-07-27 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-09-11 | 1900-02-15 | 33 | 2023-09-11 | 2023-09-11 | 1 | 1 | 233 | 167 | 48 | 34 | 281 | 201 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | 135.05 | 135.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-25 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-06-19 | 2024-05-12 | IOU Designed & Installed | N/A | No | N/A | 2717.66 | 20.7 | Unknown | 36.71 | Unknown | 2660.25 | 3991 | 559.99 | 2717.66 | -2157.67 | Yes | N/A | N/A | 2023-05-30 | 2023-06-18 | 20 | 14 | 2023-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-06-26 | 4 | 2 | 2023-09-11 | 2024-05-12 | 245 | 175 | Unknown | Unknown | Unknown | Unknown | 2024-05-12 | 2024-05-17 | 1900-01-05 | 5 | 2024-05-17 | 2024-05-17 | 1 | 1 | 265 | 189 | 11 | 8 | 276 | 197 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-27 | -65 | -47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-06 | 2024-04-23 | IOU Designed & Installed | N/A | No | N/A | -6.95 | -5.64 | Unknown | Unknown | Unknown | -1.31 | Unknown | 534.57 | -6.95 | 541.52 | Yes | N/A | N/A | 2024-01-31 | 2024-01-31 | 1 | 1 | 2024-01-31 | 2024-01-31 | 1 | 1 | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-04-23 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-05-23 | 1900-01-30 | 23 | 2024-05-23 | 2024-05-23 | 1 | 1 | 2 | 2 | 33 | 25 | 35 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-09 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-23 | 2024-12-23 | 2025-02-04 | IOU Designed & Installed | N/A | No | N/A | 1692.3 | 448.13 | Unknown | Unknown | Unknown | 1244.17 | Unknown | 2090.03 | 1692.3 | 397.73 | Yes | N/A | N/A | 2024-12-23 | 2024-12-23 | 1 | 1 | 2024-12-23 | 2024-12-23 | 1 | 1 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-02-04 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-02-27 | 1900-01-23 | 18 | 2025-02-27 | 2025-02-27 | 1 | 1 | 45 | 33 | 26 | 20 | 71 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-14 | -669 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-07 | 2025-03-07 | 2025-03-11 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1610.06 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-07 | 2025-03-07 | 1 | 1 | 2025-03-07 | 2025-03-07 | 1 | 1 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-03-11 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-04-16 | 1900-02-05 | 27 | 2025-04-16 | 2025-04-16 | 1 | 1 | 6 | 4 | 39 | 29 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | DANA POINT | 111.05 | 111.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-28 | 170 | 121 | No | 2024-08-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | 2024-12-05 | IOU Designed & Installed | N/A | Yes | 100 | 32776.26 | Unknown | Unknown | Unknown | 164.69 | 32611.57 | 3981 | 2344.53 | 32776.26 | -30431.73 | Yes | N/A | N/A | 2024-08-05 | 2024-11-13 | 101 | 73 | 2024-11-13 | 2024-08-05 | Unknown | Unknown | 2024-08-05 | Unknown | Unknown | Unknown | 2024-11-13 | 2024-11-26 | 14 | 10 | 2024-08-05 | 2024-12-05 | 123 | 89 | Unknown | 2024-11-11 | Unknown | Unknown | 2024-12-05 | 2025-03-17 | 1900-04-12 | 73 | 2025-03-17 | 2025-03-17 | 1 | 1 | 224 | 162 | 118 | 84 | 342 | 246 | Steps 2,3,5,6,7 | 113 | 81 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56, ESCONDIDO | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-02 | -376 | -270 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-07-19 | 2025-04-21 | IOU Designed & Installed | N/A | No | N/A | 1224.93 | 365.95 | Unknown | 85.13 | -1169 | 1942.85 | 0 | 1051.26 | 1224.93 | -173.67 | Yes | N/A | N/A | 2024-06-11 | 2024-05-09 | Unknown | Unknown | 2024-05-09 | 2024-07-19 | 72 | 52 | 2024-07-19 | 2024-10-01 | 75 | 53 | 2025-01-22 | 2025-02-05 | 15 | 11 | 2024-10-01 | 2025-04-21 | 203 | 145 | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | 2025-04-21 | 1899-12-31 | 1 | 2025-04-21 | 2025-04-21 | 1 | 1 | 278 | 198 | 89 | 65 | 367 | 263 | Steps 2,3,5,6,7 | 127 | 91 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-06 | -317 | -227 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | 2024-10-16 | IOU Designed & Installed | N/A | No | N/A | 1711.21 | 379.98 | Unknown | Unknown | Unknown | 1331.23 | 3981 | 1763.17 | 1711.21 | 51.96 | Yes | N/A | N/A | 2024-10-14 | 2024-09-10 | Unknown | Unknown | 2024-09-10 | 2024-10-14 | 35 | 25 | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2024-10-16 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-24 | 1900-01-08 | 7 | 2024-10-24 | 2024-10-24 | 1 | 1 | 3 | 3 | 45 | 33 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 190 | 190 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-17 | -137 | -98 | No | 2022-07-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-09 | 2022-07-15 | 2023-09-28 | IOU Designed & Installed | N/A | Yes | 446 | 745.27 | -23.26 | Unknown | Unknown | Unknown | 768.53 | 3885 | 709.2 | 745.27 | -36.07 | Yes | N/A | N/A | 2022-06-09 | 2023-10-04 | 483 | 345 | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-09-28 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-11-01 | 1900-02-03 | 25 | 2023-11-01 | 2023-11-01 | 1 | 1 | 493 | 353 | 36 | 26 | 529 | 379 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-17 | -168 | -121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.07 | -13.6 | Unknown | Unknown | 0.58 | 8.95 | 3981 | 1615.59 | -4.07 | 1619.66 | Yes | N/A | N/A | 2023-02-28 | 2023-03-20 | 21 | 15 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | Unknown | 2023-08-02 | Unknown | Unknown | 2023-08-02 | 2023-08-02 | 1 | 1 | 21 | 15 | 1 | 1 | 22 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-28 | 604 | 433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | 2023-10-02 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2354.17 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-23 | 2023-05-23 | 1 | 1 | 2023-05-23 | 2023-06-22 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | 2023-06-26 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2023-10-25 | 1900-01-23 | 18 | 2023-10-25 | 2023-10-25 | 1 | 1 | 1 | 1 | 76 | 56 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN MARCOS | N/A | 95 | 95 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-10 | 207 | 148 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-08-31 | 2024-06-04 | IOU Designed & Installed | N/A | No | N/A | 14384.81 | 4724.38 | Unknown | Unknown | -476 | 10136.43 | 3981 | 1336.71 | 14384.81 | -13048.1 | Yes | N/A | N/A | 2023-08-21 | 2023-08-29 | 9 | 7 | 2023-08-29 | 2023-10-06 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2024-05-15 | 163 | 117 | 2023-10-06 | 2024-05-20 | 228 | 162 | Unknown | 2024-05-20 | Unknown | Unknown | 2024-06-04 | 2024-06-04 | 1899-12-31 | 1 | 2024-06-04 | 2024-06-04 | 1 | 1 | 237 | 169 | 204 | 148 | 441 | 317 | Steps 2,3,5,6,7 | 222 | 158 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-18 | -401 | -286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 545.57 | -11.37 | Unknown | Unknown | Unknown | 556.94 | 31848 | 1141.38 | 545.57 | 595.81 | Yes | N/A | N/A | 2024-08-26 | 2024-06-28 | Unknown | Unknown | 2024-06-28 | 2024-10-03 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-10-24 | 8 | 4 | 2024-10-03 | 2024-11-19 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | Unknown | Unknown | 2024-12-16 | 2024-12-13 | Unknown | Unknown | 48 | 34 | 106 | 74 | 154 | 108 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-16 | -658 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-09 | 2025-05-15 | IOU Designed & Installed | N/A | No | N/A | 1524.97 | 381.42 | Unknown | Unknown | Unknown | 1143.55 | 3981 | 1630.05 | 1524.97 | 105.08 | Yes | N/A | N/A | 2025-04-09 | 2025-04-09 | 1 | 1 | 2025-04-09 | 2025-04-09 | 1 | 1 | 2025-04-09 | Unknown | Unknown | Unknown | 2025-04-10 | 2025-04-30 | 21 | 15 | 2025-04-09 | 2025-05-15 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-05-27 | 1900-01-12 | 9 | 2025-05-27 | 2025-05-27 | 1 | 1 | 38 | 28 | 36 | 26 | 74 | 54 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | -403 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-20 | 2023-01-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | -101.17 | -13.99 | Unknown | Unknown | -527.32 | 440.14 | Unknown | 542.25 | -101.17 | 643.42 | Yes | N/A | N/A | 2023-01-20 | 2023-02-03 | 15 | 11 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | 2023-10-02 | 2023-10-02 | 1 | 1 | 15 | 11 | 1 | 1 | 16 | 12 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 5408.1 | 5408.1 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-11-27 | -490 | -351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-06 | 2024-04-11 | 2024-07-15 | IOU Designed & Installed | N/A | No | N/A | 9.82 | -7.54 | Unknown | Unknown | Unknown | 17.36 | 3981 | 1142.83 | 9.82 | 1133.01 | Yes | N/A | N/A | 2024-04-06 | 2024-04-11 | 6 | 4 | 2024-04-11 | 2024-04-11 | 1 | 1 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-07-15 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-07-25 | 1900-01-10 | 9 | 2024-07-25 | 2024-07-25 | 1 | 1 | 102 | 72 | 13 | 11 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-31 | 58 | 41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2023-10-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 9.58 | Unknown | Unknown | Unknown | Unknown | 9.58 | 3981 | 863.37 | 9.58 | 853.79 | Yes | N/A | N/A | 2023-10-26 | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2023-10-27 | 12 | 10 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | Unknown | Unknown | 2024-10-28 | 2024-10-28 | 1 | 1 | 0 | 0 | 13 | 11 | 13 | 11 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 179.05 | 179.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-21 | 359 | 258 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | 2024-03-04 | IOU Designed & Installed | N/A | No | N/A | 4.02 | -3.59 | Unknown | Unknown | Unknown | 7.61 | Unknown | 274.43 | 4.02 | 270.41 | Yes | N/A | N/A | 2023-09-07 | 2023-09-07 | 1 | 1 | 2023-09-07 | 2023-09-11 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-03-14 | 1900-01-10 | 9 | 2024-03-14 | 2024-03-14 | 1 | 1 | 1 | 1 | 17 | 13 | 18 | 14 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 99 | 99 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-14 | -20 | -15 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-06-12 | 2023-10-12 | IOU Designed & Installed | N/A | No | N/A | 0.43 | -12.61 | Unknown | Unknown | Unknown | 13.04 | 3981 | 848.18 | 0.43 | 847.75 | Yes | N/A | N/A | 2023-05-23 | 2023-06-12 | 21 | 15 | 2023-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-12 | 2023-10-12 | 123 | 89 | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-10-26 | 1900-01-14 | 11 | 2023-10-26 | 2023-10-25 | Unknown | Unknown | 144 | 104 | 15 | 11 | 159 | 115 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-06 | -282 | -203 | No | 2025-04-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | 2025-04-14 | IOU Designed & Installed | N/A | Yes | 35 | 1985.93 | -39.9 | Unknown | Unknown | Unknown | 2025.83 | Unknown | 2129.28 | 1985.93 | 143.35 | Yes | N/A | N/A | 2025-04-08 | 2025-05-13 | 36 | 26 | 2025-05-13 | 2025-05-13 | 1 | 1 | 2025-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-14 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | 2025-05-28 | 1900-02-13 | 33 | 2025-05-28 | 2025-05-28 | 1 | 1 | 43 | 31 | 47 | 35 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | BOULEVARD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | -400 | -287 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | 2023-06-26 | IOU Designed & Installed | N/A | No | N/A | 1654.48 | 592.72 | Unknown | 134.04 | Unknown | 927.72 | 3981 | 787.97 | 1654.48 | -866.51 | Yes | N/A | N/A | 2023-05-19 | 2023-05-19 | 1 | 1 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2023-06-26 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | 2023-06-28 | 1900-01-02 | 3 | 2023-06-28 | 2023-06-28 | 1 | 1 | 40 | 28 | 4 | 4 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | -204 | -147 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-20 | 2021-09-20 | 2024-05-24 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 2499272.51 | 634234.58 | Unknown | 25.03 | 256732.41 | 1608280.49 | 0 | Not available | 2499272.51 | Unknown | Yes | N/A | N/A | 2021-09-20 | 2023-03-09 | 536 | 384 | 2023-03-09 | 2023-05-15 | 68 | 48 | 2023-04-11 | 2024-05-22 | 37 | 27 | 2023-05-16 | 2023-08-08 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | 2024-09-18 | 490 | 350 | 2024-05-24 | 2024-07-23 | 1900-03-01 | 43 | 2024-07-23 | 2024-07-23 | 1 | 1 | 573 | 411 | 705 | 503 | 1278 | 914 | Steps 2,3,5,6,7 | 523 | 373 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-06 | -289 | -208 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2024-01-22 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | 587.4 | -20.48 | Unknown | Unknown | Unknown | 607.88 | Unknown | 889.73 | 587.4 | 302.33 | Yes | N/A | N/A | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-05-17 | 117 | 85 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-05-21 | 1900-01-04 | 3 | 2024-05-21 | 2024-05-21 | 1 | 1 | 118 | 86 | 7 | 5 | 125 | 91 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-16 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | 2023-12-12 | IOU Designed & Installed | N/A | No | N/A | 2254.49 | 183.68 | Unknown | 176.88 | 40.12 | 1853.81 | Unknown | 617.86 | 2254.49 | -1636.63 | Yes | N/A | N/A | 2023-07-17 | 2023-08-28 | 43 | 31 | 2023-08-28 | 2023-08-28 | 1 | 1 | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2023-12-12 | 107 | 77 | Unknown | 2023-11-13 | Unknown | Unknown | 2023-12-12 | 2024-01-08 | 1900-01-27 | 20 | 2024-01-08 | 2024-01-08 | 1 | 1 | 150 | 108 | 30 | 22 | 180 | 130 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-13 | 576 | 412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-07-19 | 2023-09-25 | IOU Designed & Installed | N/A | No | N/A | 449.36 | -12.64 | Unknown | Unknown | 4.24 | 457.76 | 3981 | 635.84 | 449.36 | 186.48 | Yes | N/A | N/A | 2023-07-13 | 2023-07-19 | 7 | 5 | 2023-07-19 | 2023-07-19 | 1 | 1 | 2023-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | 2023-09-25 | 69 | 49 | Unknown | 2023-09-21 | Unknown | Unknown | 2023-09-25 | 2023-10-10 | 1900-01-15 | 12 | 2023-10-10 | 2023-10-10 | 1 | 1 | 76 | 54 | 18 | 14 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-07 | -189 | -136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-10-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1217.64 | -11.25 | Unknown | Unknown | -1218 | 11.61 | Unknown | 1218.2 | -1217.64 | 2435.84 | Yes | N/A | N/A | 2023-10-02 | 2023-10-02 | 1 | 1 | 2023-10-02 | 2023-10-02 | 1 | 1 | 2023-10-02 | 2023-10-23 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | 2024-01-31 | 2024-01-31 | 1 | 1 | 23 | 17 | 2 | 2 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | SAN DIEGO | 56.05 | 56.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | -354 | -254 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | 3537.9 | 1111.65 | Unknown | Unknown | 83.71 | 2342.54 | Unknown | 6725.61 | 3537.9 | 3187.71 | Yes | N/A | N/A | 2024-04-18 | 2024-04-18 | 1 | 1 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-08-12 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-10-15 | 1900-02-11 | 31 | 2024-10-15 | 2024-10-15 | 1 | 1 | 1 | 1 | 106 | 76 | 107 | 77 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 11.4 | 11.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | -626 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-08-13 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 10.29 | Unknown | Unknown | Unknown | Unknown | 10.29 | Unknown | 192.95 | 10.29 | 182.66 | Yes | N/A | N/A | 2024-08-12 | 2024-08-12 | 1 | 1 | 2024-08-12 | 2024-08-20 | 9 | 7 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-09-23 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-11-05 | 1900-02-12 | 32 | 2024-11-05 | 2024-11-05 | 1 | 1 | 36 | 26 | 54 | 40 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 44.4 | 44.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | -142 | -103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 7337.18 | 1204.88 | Unknown | 287.49 | Unknown | 5844.81 | 3981 | 432.64 | 7337.18 | -6904.54 | Yes | N/A | N/A | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | Unknown | Unknown | Unknown | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-03-26 | Unknown | Unknown | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-24 | -166 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 232.57 | -7.42 | Unknown | Unknown | Unknown | 239.99 | 3981 | 1563.93 | 232.57 | 1331.36 | Yes | N/A | N/A | 2023-02-15 | 2023-03-14 | 28 | 20 | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | 2023-04-19 | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | 2023-08-11 | 2023-08-11 | 1 | 1 | 28 | 20 | 1 | 1 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-03 | 532 | 381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2024-05-22 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | 31475.18 | 24295.12 | Unknown | Unknown | -98687 | 105867.06 | Unknown | 121305.93 | 31475.18 | 89830.75 | Yes | N/A | N/A | 2024-05-22 | 2024-09-04 | 106 | 76 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-09-13 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-10-16 | 1900-01-30 | 23 | 2024-10-16 | 2024-10-16 | 1 | 1 | 106 | 76 | 52 | 38 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | N/A | DM 1187-F5 hILLSTONE (E) | DEL MAR | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-24 | 347 | 248 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2025-05-06 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 50670.95 | 17881.6 | Unknown | Unknown | -718.72 | 33508.07 | 94587 | 22406.95 | 50670.95 | -28264 | Yes | N/A | N/A | 2023-02-14 | 2023-09-22 | 221 | 159 | 2023-09-22 | 2024-03-20 | 181 | 129 | 2023-09-22 | 2024-01-31 | 28 | 20 | 2023-10-03 | 2024-11-21 | 71 | 53 | 2024-03-20 | Unknown | Unknown | Unknown | 2024-07-03 | 2025-03-28 | 269 | 193 | 2025-05-06 | 2025-05-06 | 1899-12-31 | 1 | 2025-05-06 | 2025-05-06 | 1 | 1 | 249 | 179 | 523 | 377 | 772 | 556 | Steps 2,3,5,6,7 | 546 | 390 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-07 | 484 | 346 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-15 | 2024-05-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1326.65 | 531.2 | Unknown | 41.55 | -2139 | 239.6 | Unknown | 2732.95 | -1326.65 | 4059.6 | Yes | N/A | N/A | 2022-04-15 | 2024-04-29 | 746 | 532 | 2024-04-29 | 2024-08-29 | 123 | 89 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2024-08-03 | 1 | 0 | 746 | 532 | 124 | 89 | 870 | 621 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | -675 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 24.32 | Unknown | Unknown | Unknown | Unknown | 24.32 | 3981 | 727.04 | 24.32 | 702.72 | Yes | N/A | N/A | 2024-12-05 | 2024-12-04 | Unknown | Unknown | 2024-12-04 | 2024-12-05 | 2 | 2 | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | Unknown | Unknown | 2025-01-15 | 2025-01-13 | Unknown | Unknown | 0 | 0 | 2 | 2 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 2615179 | 2615179 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-09-05 | 611 | 438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-15 | 2022-07-13 | 2025-02-04 | IOU Designed & Installed | N/A | No | N/A | 56642.64 | 8090.88 | Unknown | Unknown | 1408.37 | 47143.39 | 1347006.72 | 55747.14 | 56642.64 | -895.5 | Yes | N/A | N/A | 2022-06-15 | 2024-03-19 | 644 | 460 | 2024-03-19 | 2024-05-16 | 59 | 43 | 2023-12-29 | 2024-07-17 | 59 | 43 | 2024-01-26 | 2024-05-15 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2025-05-12 | 217 | 155 | 2025-02-04 | 2025-05-08 | 1900-04-03 | 68 | 2025-05-08 | 2025-05-08 | 1 | 1 | 703 | 503 | 413 | 297 | 1116 | 800 | Steps 2,3,5,6,7 | 409 | 291 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | -529 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-19 | 2024-06-18 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2296.91 | Unknown | Unknown | Yes | N/A | N/A | 2024-03-19 | 2023-12-20 | Unknown | Unknown | 2023-12-20 | 2024-03-21 | 93 | 67 | 2024-03-21 | 2024-03-25 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-06-18 | 86 | 62 | Unknown | 2024-05-21 | Unknown | Unknown | 2024-06-18 | 2024-06-26 | 1900-01-08 | 7 | 2024-06-26 | 2024-06-26 | 1 | 1 | 91 | 65 | 103 | 75 | 194 | 140 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 105.4 | 105.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-04 | -197 | -142 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1445.42 | 61.46 | Unknown | Unknown | 3.81 | 1380.15 | Unknown | 2371.57 | 1445.42 | 926.15 | Yes | N/A | N/A | 2025-02-18 | 2025-03-14 | 25 | 19 | 2025-03-14 | 2025-03-25 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-03-06 | 16 | 12 | 2025-03-25 | 2025-04-18 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | 2025-04-22 | 2025-04-21 | Unknown | Unknown | 50 | 38 | 28 | 20 | 78 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | 54 | 54 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-17 | -253 | -181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | 2023-11-06 | IOU Designed & Installed | N/A | No | N/A | -11.26 | Unknown | Unknown | Unknown | Unknown | -11.26 | 3981 | 650.84 | -11.26 | 662.1 | Yes | N/A | N/A | 2023-10-27 | 2023-10-27 | 1 | 1 | 2023-10-27 | 2023-10-27 | 1 | 1 | 2023-10-27 | Unknown | Unknown | Unknown | 2023-10-27 | 2023-11-13 | 18 | 12 | 2023-10-27 | 2023-11-06 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2023-12-08 | 1900-02-01 | 25 | 2023-12-08 | 2023-12-08 | 1 | 1 | 12 | 8 | 53 | 39 | 65 | 47 | Steps 2,3,5,6,7 | 17 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-29 | 228 | 163 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 27.07 | Unknown | Unknown | Unknown | Unknown | 27.07 | 3981 | 933.04 | 27.07 | 905.97 | Yes | N/A | N/A | 2024-01-24 | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2024-01-24 | 45 | 33 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | Unknown | Unknown | 2025-02-04 | 2025-02-12 | 9 | 7 | 0 | 0 | 54 | 40 | 54 | 40 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-26 | -218 | -156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-17 | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | 352.43 | Unknown | Unknown | Unknown | 4.8 | 347.63 | 3981 | 1165.94 | 352.43 | 813.51 | Yes | N/A | N/A | 2024-06-17 | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-07-11 | 65 | 47 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-09-17 | 69 | 49 | Unknown | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-09-20 | 1900-01-03 | 4 | 2024-09-20 | 2024-09-20 | 1 | 1 | 69 | 49 | 70 | 52 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | 172 | 124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-13 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 22985.37 | 5050.09 | Unknown | 36.91 | Unknown | 17898.37 | 213593 | 5050.15 | 22985.37 | -17935.22 | Yes | N/A | N/A | 2024-09-13 | 2024-09-13 | 1 | 1 | 2024-09-13 | 2024-11-11 | 60 | 42 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2025-02-27 | 109 | 79 | Unknown | 2025-02-28 | Unknown | Unknown | 2025-03-05 | 2025-03-24 | 1900-01-19 | 14 | 2025-03-24 | 2025-03-22 | Unknown | Unknown | 110 | 80 | 80 | 56 | 190 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-03 | -204 | -147 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | 2023-04-21 | IOU Designed & Installed | N/A | No | N/A | -5.45 | -3.94 | Unknown | Unknown | Unknown | -1.51 | 3981 | 341 | -5.45 | 346.45 | Yes | N/A | N/A | 2023-02-15 | 2023-02-15 | 1 | 1 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | 2023-04-21 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | 2023-06-13 | 1900-02-22 | 38 | 2023-06-13 | 2023-06-13 | 1 | 1 | 67 | 49 | 55 | 39 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 55.05 | 55.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-07 | -428 | -306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-05 | 2024-07-05 | 2024-12-05 | IOU Designed & Installed | N/A | No | N/A | 1894.07 | Unknown | Unknown | Unknown | 36.76 | 1857.31 | 3981 | 1311.67 | 1894.07 | -582.4 | Yes | N/A | N/A | 2024-07-05 | 2024-08-08 | 35 | 25 | 2024-08-08 | 2024-08-14 | 7 | 5 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-12-05 | 114 | 82 | Unknown | 2024-11-22 | Unknown | Unknown | 2024-12-05 | 2025-01-03 | 1900-01-29 | 22 | 2025-01-03 | 2025-01-03 | 1 | 1 | 149 | 107 | 38 | 28 | 187 | 135 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-06 | -276 | -198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-08 | 2023-10-03 | IOU Designed & Installed | N/A | No | N/A | 1792.65 | 1500.96 | Unknown | 904.48 | -1610 | 997.21 | Unknown | 1610.05 | 1792.65 | -182.6 | Yes | N/A | N/A | 2023-09-08 | 2023-09-08 | 1 | 1 | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-10-04 | 1900-01-01 | 2 | 2023-10-04 | 2023-10-04 | 1 | 1 | 1 | 1 | 3 | 3 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | -579 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 1382.14 | Unknown | Unknown | Unknown | 10.55 | 1371.59 | 3981 | 1369.12 | 1382.14 | -13.02 | Yes | N/A | N/A | 2024-05-14 | 2024-04-08 | Unknown | Unknown | 2024-04-08 | 2024-05-31 | 54 | 40 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-08-26 | 88 | 62 | Unknown | 2024-08-15 | Unknown | Unknown | 2024-08-26 | 2024-09-03 | 1900-01-08 | 7 | 2024-09-03 | 2024-09-03 | 1 | 1 | 88 | 62 | 64 | 48 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 201.15 | 201.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-18 | -175 | -126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-20 | 2025-06-19 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 875.99 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | 2025-04-02 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-06-19 | 101 | 73 | Unknown | 2025-05-12 | Unknown | Unknown | 2025-06-19 | 2025-06-26 | 1900-01-07 | 6 | 2025-06-26 | 2025-06-26 | 1 | 1 | 144 | 104 | 10 | 8 | 154 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-03-24 | 628 | 449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | 2024-01-26 | IOU Designed & Installed | N/A | No | N/A | 165.3 | -4.57 | Unknown | Unknown | -302.91 | 472.78 | Unknown | 270.46 | 165.3 | 105.16 | Yes | N/A | N/A | 2023-02-23 | 2023-02-23 | 1 | 1 | 2023-02-23 | 2023-04-20 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | 2023-11-20 | 215 | 153 | Unknown | 2023-12-07 | Unknown | Unknown | 2024-01-26 | 2024-02-12 | 1900-01-17 | 12 | 2024-02-12 | 2023-12-12 | Unknown | Unknown | 216 | 154 | 75 | 53 | 291 | 207 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 109.1 | 109.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-30 | -32 | -24 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 35965.53 | 11359.09 | Unknown | 3815.58 | 632.03 | 20158.83 | 3981 | 1417.64 | 35965.53 | -34547.89 | Yes | N/A | N/A | 2023-02-02 | 2023-04-19 | 77 | 55 | 2023-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | 2024-10-22 | 71 | 49 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | Unknown | 2024-10-30 | Unknown | Unknown | 2024-10-30 | 2024-10-29 | Unknown | Unknown | 77 | 55 | 71 | 49 | 148 | 104 | Steps 2,3,5,6,7 | 390 | 278 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 316 | 316 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-31 | 231 | 166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-12-05 | 2024-02-23 | IOU Designed & Installed | N/A | No | N/A | 904 | -20.67 | Unknown | Unknown | Unknown | 924.67 | 3241 | 882.77 | 904 | -21.23 | Yes | N/A | N/A | 2023-08-07 | 2023-12-05 | 121 | 87 | 2023-12-05 | 2023-12-05 | 1 | 1 | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2024-02-23 | 81 | 59 | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-03-18 | 1900-01-24 | 17 | 2024-03-18 | 2024-03-18 | 1 | 1 | 202 | 146 | 27 | 19 | 229 | 165 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-30 | 431 | 310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-04 | 2022-08-04 | 2024-12-19 | IOU Designed & Installed | N/A | No | N/A | 137508.31 | 3066.65 | Unknown | Unknown | 3883.4 | 130558.26 | Unknown | 30057.97 | 137508.31 | -107450.34 | Yes | N/A | N/A | 2022-08-04 | 2024-07-17 | 714 | 510 | 2024-07-17 | 2024-11-12 | 119 | 85 | 2024-10-07 | 2024-11-19 | 15 | 11 | 2024-08-29 | 2024-11-19 | 63 | 43 | 2024-11-22 | Unknown | Unknown | Unknown | 2024-11-22 | 2024-12-13 | 22 | 16 | 2024-12-19 | 2025-01-03 | 1900-01-15 | 12 | 2025-01-03 | 2025-01-03 | 1 | 1 | 729 | 521 | 221 | 157 | 950 | 678 | Steps 2,3,5,6,7 | 118 | 84 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-28 | -388 | -279 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-08-08 | 2025-04-29 | IOU Designed & Installed | N/A | No | N/A | 2709.17 | 400.32 | Unknown | 85.13 | 38.53 | 2185.19 | 3981 | 822.7 | 2709.17 | -1886.47 | Yes | N/A | N/A | 2024-07-18 | 2024-08-13 | 27 | 19 | 2024-08-13 | 2024-08-22 | 10 | 8 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2025-04-29 | 251 | 179 | Unknown | 2025-02-11 | Unknown | Unknown | 2025-04-29 | 2025-05-05 | 1900-01-06 | 5 | 2025-05-05 | 2025-05-05 | 1 | 1 | 278 | 198 | 18 | 14 | 296 | 212 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-05 | -141 | -102 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-03-01 | 2024-06-04 | IOU Designed & Installed | N/A | No | N/A | -12.63 | -14.55 | Unknown | Unknown | Unknown | 1.92 | 3981 | 888.02 | -12.63 | 900.65 | Yes | N/A | N/A | 2024-03-01 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-03-01 | 37 | 27 | 2024-03-01 | 2024-06-21 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-06-04 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-07-03 | 1900-01-29 | 22 | 2024-07-03 | 2024-07-17 | 15 | 11 | 209 | 149 | 82 | 60 | 291 | 209 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | 12 | 9 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-04-19 | 2023-09-06 | IOU Designed & Installed | N/A | No | N/A | 1543.53 | -9.55 | Unknown | Unknown | 319.27 | 1233.81 | 3981 | 669.19 | 1543.53 | -874.34 | Yes | N/A | N/A | 2023-04-19 | 2023-06-30 | 73 | 53 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-09-06 | 69 | 49 | Unknown | 2023-09-06 | Unknown | Unknown | 2023-09-06 | 2024-11-12 | 1901-03-09 | 310 | 2024-11-12 | 2024-11-12 | 1 | 1 | 142 | 102 | 435 | 311 | 577 | 413 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | BONSALL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-02 | 413 | 296 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | 2024-12-13 | IOU Designed & Installed | N/A | No | N/A | 11417.78 | 2992.37 | Unknown | 596.06 | Unknown | 7829.35 | 194415 | 23564.29 | 11417.78 | 12146.51 | Yes | N/A | N/A | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | 2024-08-26 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-12-19 | 116 | 84 | Unknown | 2024-12-05 | Unknown | Unknown | 2024-12-13 | 2024-12-19 | 1900-01-06 | 5 | 2024-12-19 | 2024-12-19 | 1 | 1 | 117 | 85 | 9 | 7 | 126 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | 5334.05 | 5334.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-04-18 | -648 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-17 | 2024-06-20 | IOU Designed & Installed | N/A | No | N/A | 19.84 | -15.28 | Unknown | Unknown | Unknown | 35.12 | 3981 | 1423.5 | 19.84 | 1403.66 | Yes | N/A | N/A | 2024-06-14 | 2024-04-25 | Unknown | Unknown | 2024-04-25 | 2024-06-17 | 54 | 38 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-06-20 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-09 | 1900-01-19 | 14 | 2024-07-09 | 2024-07-09 | 1 | 1 | 4 | 4 | 75 | 53 | 79 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | 1589 | 1136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 3428.09 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-28 | 2024-10-22 | 148 | 106 | 2024-10-22 | 2024-11-08 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | 2025-05-08 | 2025-05-08 | 1 | 1 | 148 | 106 | 19 | 15 | 167 | 121 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-21 | -683 | -488 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | 2061.95 | 414.6 | Unknown | Unknown | Unknown | 1647.35 | Unknown | 714.64 | 2061.95 | -1347.31 | Yes | N/A | N/A | 2025-04-08 | 2025-04-07 | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-18 | 10 | 8 | 2025-04-11 | 2025-04-25 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-07 | 1900-01-12 | 9 | 2025-05-07 | 2025-05-07 | 1 | 1 | 15 | 11 | 24 | 18 | 39 | 29 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 99.05 | 99.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-14 | -645 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-12 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 1904.99 | 403.79 | Unknown | Unknown | Unknown | 1501.2 | Unknown | 1635.08 | 1904.99 | -269.91 | Yes | N/A | N/A | 2024-12-12 | 2024-12-02 | Unknown | Unknown | 2024-12-02 | 2024-12-12 | 11 | 9 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-02-03 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-07 | 1900-01-04 | 5 | 2025-02-07 | 2025-02-07 | 1 | 1 | 54 | 38 | 17 | 15 | 71 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-06 | -59 | -44 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2023-12-26 | 2024-06-13 | IOU Designed & Installed | N/A | No | N/A | 943.79 | -18.33 | Unknown | Unknown | -692.59 | 1654.71 | Unknown | 708.72 | 943.79 | -235.07 | Yes | N/A | N/A | 2023-12-26 | 2023-11-06 | Unknown | Unknown | 2023-11-06 | 2024-01-11 | 67 | 49 | 2024-01-11 | 2024-04-16 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-06-13 | 140 | 100 | Unknown | 2024-06-12 | Unknown | Unknown | 2024-06-13 | 2024-07-09 | 1900-01-26 | 19 | 2024-07-09 | 2024-07-09 | 1 | 1 | 237 | 169 | 95 | 69 | 332 | 238 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | -550 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-12-15 | 2023-12-15 | IOU Designed & Installed | N/A | No | N/A | 920.56 | -26.34 | Unknown | Unknown | Unknown | 946.9 | 3981 | 777.95 | 920.56 | -142.61 | Yes | N/A | N/A | 2023-11-21 | 2023-10-25 | Unknown | Unknown | 2023-10-25 | 2023-12-15 | 52 | 38 | 2023-12-15 | Unknown | Unknown | Unknown | 2023-12-15 | 2023-12-27 | 13 | 9 | 2023-12-15 | 2023-12-15 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2024-01-08 | 1900-01-24 | 17 | 2024-01-08 | 2024-01-08 | 1 | 1 | 1 | 1 | 91 | 65 | 92 | 66 | Steps 2,3,5,6,7 | 12 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-06 | -579 | -414 | No | 2023-03-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-03-16 | 2023-05-10 | IOU Designed & Installed | N/A | Yes | 42 | 122.08 | -6.02 | Unknown | Unknown | Unknown | 128.1 | Unknown | 1125 | 122.08 | 1002.92 | Yes | N/A | N/A | 2023-03-16 | 2023-04-27 | 43 | 31 | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | 2023-05-10 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-05-10 | 2023-06-07 | 1900-01-28 | 21 | 2023-06-07 | 2023-06-07 | 1 | 1 | 57 | 41 | 30 | 22 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 21.05 | 21.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-12 | -209 | -150 | No | 2024-01-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-03-06 | 2024-04-11 | IOU Designed & Installed | N/A | Yes | 47 | 1695.95 | -38.37 | Unknown | Unknown | Unknown | 1734.32 | 3981 | 877.5 | 1695.95 | -818.45 | Yes | N/A | N/A | 2024-01-24 | 2024-03-11 | 48 | 34 | 2024-03-11 | 2024-03-05 | Unknown | Unknown | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-04-11 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-05-17 | 1900-02-05 | 27 | 2024-05-17 | 2024-05-17 | 1 | 1 | 85 | 61 | 38 | 28 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | -345 | -248 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-12-05 | 2025-04-08 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1655.9 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-31 | 2024-12-03 | 126 | 90 | 2024-12-03 | 2024-12-05 | 3 | 3 | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | 2025-04-08 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-21 | 1900-01-13 | 10 | 2025-04-21 | 2025-04-21 | 1 | 1 | 251 | 179 | 18 | 14 | 269 | 193 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community,Tribal Community | ALPINE | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 117 | 84 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | 2024-03-10 | IOU Designed & Installed | N/A | No | N/A | 29.89 | 556.72 | Unknown | Unknown | -1618 | 1091.17 | 3241 | 3194.61 | 29.89 | 3164.72 | Yes | N/A | N/A | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | 2024-01-10 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-03-10 | 61 | 43 | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-10 | 2024-03-14 | 1900-01-04 | 4 | 2024-03-14 | 2024-03-27 | 14 | 10 | 86 | 62 | 20 | 15 | 106 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | LAGUNA BEACH | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-12-31 | 507 | 363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-06-27 | 2025-02-06 | IOU Designed & Installed | N/A | No | N/A | -7724.77 | 459.1 | Unknown | Unknown | -8486 | 302.13 | 0 | 14089.81 | -7724.77 | 21814.58 | Yes | N/A | N/A | 2024-03-26 | 2024-04-23 | 29 | 21 | 2024-04-23 | Unknown | Unknown | Unknown | 2024-07-26 | 2024-07-29 | 4 | 2 | 2024-08-08 | 2025-04-25 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-05-21 | 1900-04-14 | 75 | 2025-05-21 | 2025-05-21 | 1 | 1 | 33 | 23 | 125 | 91 | 158 | 114 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-09 | -544 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | 2024-01-12 | IOU Designed & Installed | N/A | No | N/A | 248.02 | -14.24 | Unknown | Unknown | 3.86 | 258.4 | 3981 | 717.17 | 248.02 | 469.15 | Yes | N/A | N/A | 2023-11-09 | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2023-12-21 | 128 | 92 | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-01-12 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | 2024-02-12 | 1900-01-31 | 22 | 2024-02-12 | 2024-02-12 | 1 | 1 | 23 | 17 | 161 | 115 | 184 | 132 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 100.05 | 100.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-16 | 7 | 6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2025-01-15 | 2025-04-14 | IOU Designed & Installed | N/A | No | N/A | 273.47 | 273.47 | Unknown | Unknown | -337.19 | 337.19 | Unknown | 900.46 | 273.47 | 626.99 | Yes | N/A | N/A | 2023-10-12 | 2025-01-13 | 460 | 328 | 2025-01-13 | 2025-01-15 | 3 | 3 | 2025-01-15 | 2025-02-25 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-04-14 | 70 | 50 | Unknown | 2025-04-11 | Unknown | Unknown | 2025-04-14 | 2025-04-23 | 1900-01-09 | 8 | 2025-04-23 | 2025-04-23 | 1 | 1 | 572 | 408 | 14 | 12 | 586 | 420 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 17 | 17 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-30 | -573 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2024-11-08 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 3178.77 | 764.13 | Unknown | Unknown | Unknown | 2414.64 | 3981 | 1583.04 | 3178.77 | -1595.73 | Yes | N/A | N/A | 2024-11-08 | 2024-10-17 | Unknown | Unknown | 2024-10-17 | 2024-11-08 | 23 | 17 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | 2025-02-05 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-03-06 | 1900-01-29 | 22 | 2025-03-06 | 2025-03-06 | 1 | 1 | 90 | 64 | 54 | 40 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | VALLEY CENTER | COUNTY OF SAN DIEGO-NORTH of 56 | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-19 | -442 | -317 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-09-26 | 2024-11-27 | IOU Designed & Installed | N/A | No | N/A | 3769.63 | 2741.23 | Unknown | 251.18 | -4277.32 | 5054.54 | 2293 | 10851.99 | 3769.63 | 7082.36 | Yes | N/A | N/A | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | 2024-11-20 | 121 | 87 | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2024-10-30 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2024-12-04 | 1900-01-07 | 6 | 2024-12-04 | 2024-12-04 | 1 | 1 | 1 | 1 | 147 | 107 | 148 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | -694 | -497 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-06-25 | 2024-07-12 | IOU Designed & Installed | N/A | No | N/A | 4.18 | Unknown | Unknown | Unknown | Unknown | 4.18 | 3981 | 1497.1 | 4.18 | 1492.92 | Yes | N/A | N/A | 2024-06-24 | 2024-06-25 | 2 | 2 | 2024-06-25 | 2024-06-25 | 1 | 1 | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-12 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-07-25 | 1900-01-13 | 10 | 2024-07-25 | 2024-07-25 | 1 | 1 | 20 | 16 | 16 | 12 | 36 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | RA 1173-G4 (E) | COUNTY OF SAN DIEGO-NORTH of 56 | 166.2 | 166.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | -168 | -121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-06-07 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 44325.19 | 14702.68 | Unknown | Unknown | -14103.72 | 43726.23 | 2275.67 | 36850.52 | 44325.19 | -7474.67 | Yes | N/A | N/A | 2024-06-07 | 2024-06-13 | 7 | 5 | 2024-06-13 | 2024-12-06 | 177 | 127 | 2024-09-11 | 2025-01-28 | 8 | 6 | 2024-09-26 | 2025-01-29 | 80 | 58 | 2025-01-07 | Unknown | Unknown | Unknown | 2025-01-07 | 2025-01-24 | 18 | 14 | 2025-02-11 | 2025-03-17 | 1900-02-03 | 25 | 2025-03-17 | 2025-03-17 | 1 | 1 | 15 | 11 | 311 | 225 | 326 | 236 | Steps 2,3,5,6,7 | 232 | 166 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-09 | -87 | -64 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-08-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1305.48 | 397 | Unknown | 110.03 | 25.97 | 772.48 | 3981 | 1003.19 | 1305.48 | -302.29 | Yes | N/A | N/A | 2023-08-25 | 2023-09-20 | 27 | 19 | 2023-09-20 | 2023-11-22 | 64 | 46 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | Unknown | Unknown | 2024-02-12 | 2024-02-12 | 1 | 1 | 27 | 19 | 65 | 47 | 92 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | -71 | -52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 310.29 | -6.4 | Unknown | Unknown | Unknown | 316.69 | Unknown | 999.95 | 310.29 | 689.66 | Yes | N/A | N/A | 2025-01-08 | 2025-01-06 | Unknown | Unknown | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-02-05 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | 2025-05-14 | 2025-05-14 | 1 | 1 | 0 | 0 | 23 | 17 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-17 | -351 | -251 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | 2023-03-03 | IOU Designed & Installed | N/A | No | N/A | 212.85 | -2.58 | Unknown | Unknown | Unknown | 215.43 | 3981 | 102.14 | 212.85 | -110.71 | Yes | N/A | N/A | 2023-03-01 | 2023-03-01 | 1 | 1 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | 2023-03-03 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | 2023-03-08 | 1900-01-05 | 4 | 2023-03-08 | 2023-03-03 | Unknown | Unknown | 4 | 4 | 6 | 4 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | 226 | 226 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | 530 | 380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-25 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 95819.46 | 15921.36 | Unknown | Unknown | 2453.04 | 77445.06 | 89865.75 | 58237.33 | 95819.46 | -37582.13 | Yes | N/A | N/A | 2024-01-23 | 2023-11-03 | Unknown | Unknown | 2023-11-03 | 2024-03-04 | 123 | 87 | 2024-02-16 | 2024-04-03 | 5 | 3 | 2024-02-14 | 2024-04-11 | 16 | 12 | 2024-03-04 | 2024-06-26 | 115 | 83 | 2024-03-12 | 2024-07-01 | 112 | 80 | 2024-06-06 | 2024-06-14 | 1900-01-08 | 7 | 2024-06-14 | 2024-06-14 | 1 | 1 | 120 | 86 | 261 | 187 | 381 | 273 | Steps 2,3,5,6,7 | 235 | 167 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-10 | -591 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-09 | 2023-05-25 | IOU Designed & Installed | N/A | No | N/A | 599.5 | 421.38 | Unknown | 188.19 | -751 | 740.93 | 3991 | 1240.37 | 599.5 | 640.87 | Yes | N/A | N/A | 2023-03-09 | 2023-03-09 | 1 | 1 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | 2023-05-25 | 78 | 56 | Unknown | 2023-05-22 | Unknown | Unknown | 2023-05-25 | 2023-05-30 | 1900-01-05 | 4 | 2023-05-30 | 2023-05-30 | 1 | 1 | 79 | 57 | 7 | 5 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-28 | -653 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-03-25 | 2025-04-11 | IOU Designed & Installed | N/A | No | N/A | 1989.89 | 523.78 | Unknown | Unknown | Unknown | 1466.11 | Unknown | 1950.5 | 1989.89 | -39.39 | Yes | N/A | N/A | 2025-03-19 | 2025-03-25 | 7 | 5 | 2025-03-25 | 2025-03-25 | 1 | 1 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-04-11 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-05-16 | 1900-02-04 | 26 | 2025-05-16 | 2025-05-16 | 1 | 1 | 25 | 19 | 38 | 28 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | -599 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-12 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 357.08 | Unknown | Unknown | Unknown | 7.16 | 349.92 | 3981 | 1414.76 | 357.08 | 1057.68 | Yes | N/A | N/A | 2024-08-08 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2024-08-23 | 23 | 17 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-11-14 | 84 | 60 | Unknown | 2024-11-14 | Unknown | Unknown | 2024-11-14 | 2024-12-02 | 1900-01-18 | 13 | 2024-12-02 | 2024-12-02 | 1 | 1 | 84 | 60 | 43 | 31 | 127 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | -622 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-16 | 2025-04-29 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1488.86 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-04-16 | 1 | 1 | 2025-04-16 | 2025-04-16 | 1 | 1 | 2025-04-16 | 2025-04-21 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | 2025-04-29 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-05-23 | 1900-01-24 | 19 | 2025-05-23 | 2025-05-22 | Unknown | Unknown | 16 | 12 | 26 | 20 | 42 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | -199 | -142 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-08 | 2024-07-26 | IOU Designed & Installed | N/A | No | N/A | 35.86 | Unknown | Unknown | Unknown | Unknown | 35.86 | Unknown | 690.88 | 35.86 | 655.02 | Yes | N/A | N/A | 2024-03-08 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-03-08 | 2 | 2 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-07-26 | 141 | 101 | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-08-08 | 1900-01-13 | 10 | 2024-08-08 | 2024-08-08 | 1 | 1 | 141 | 101 | 17 | 13 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | COTO DE CAZA | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-07 | -642 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-03-19 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | 905.34 | Unknown | Unknown | Unknown | 18.15 | 887.19 | 3981 | 1429.33 | 905.34 | 523.99 | Yes | N/A | N/A | 2025-03-19 | 2025-03-12 | Unknown | Unknown | 2025-03-12 | 2025-03-28 | 17 | 13 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-06-03 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-03 | 1899-12-31 | 1 | 2025-06-03 | 2025-06-03 | 1 | 1 | 68 | 48 | 19 | 15 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-14 | -473 | -340 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-21 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 116.79 | -1.88 | Unknown | Unknown | Unknown | 118.67 | Unknown | 1499.84 | 116.79 | 1383.05 | Yes | N/A | N/A | 2024-06-04 | 2024-04-30 | Unknown | Unknown | 2024-04-30 | 2024-06-21 | 53 | 39 | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-07-09 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-07-29 | 1900-01-20 | 15 | 2024-07-29 | 2024-07-29 | 1 | 1 | 19 | 13 | 75 | 55 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | National City | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-07 | 699 | 500 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-06 | 2023-07-18 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | 102604.53 | 11539.15 | Unknown | Unknown | 1834.78 | 89230.6 | 26647.76 | 32256.08 | 102604.53 | -70348.45 | Yes | N/A | N/A | 2023-07-06 | 2023-03-23 | Unknown | Unknown | 2023-03-23 | 2023-12-01 | 254 | 182 | 2023-11-30 | 2023-12-19 | 3 | 3 | 2023-09-29 | 2024-01-30 | 110 | 76 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-11-05 | 1900-06-08 | 114 | 2024-11-05 | 2024-11-05 | 1 | 1 | 3 | 3 | 525 | 373 | 528 | 376 | Steps 2,3,5,6,7 | 82 | 58 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 109.05 | 109.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | -654 | -467 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-10-01 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 2766.84 | 653.33 | Unknown | 322.53 | Unknown | 1790.98 | Unknown | 1217.68 | 2766.84 | -1549.16 | Yes | N/A | N/A | 2024-09-27 | 2024-09-11 | Unknown | Unknown | 2024-09-11 | 2024-10-01 | 21 | 15 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-24 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-21 | 1900-01-28 | 21 | 2024-11-21 | 2024-11-21 | 1 | 1 | 24 | 18 | 51 | 37 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 89.4 | 89.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | -611 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-19 | 2024-08-23 | IOU Designed & Installed | N/A | No | N/A | 62.45 | Unknown | Unknown | Unknown | Unknown | 62.45 | Unknown | 1432.16 | 62.45 | 1369.71 | Yes | N/A | N/A | 2024-07-15 | 2024-07-19 | 5 | 5 | 2024-07-19 | 2024-07-19 | 1 | 1 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-08-23 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-10-16 | 1900-02-23 | 39 | 2024-10-16 | 2024-10-16 | 1 | 1 | 41 | 31 | 57 | 41 | 98 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 52.4 | 52.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-17 | -573 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2024-01-18 | 2024-02-12 | IOU Designed & Installed | N/A | No | N/A | 3.38 | -4.09 | Unknown | Unknown | Unknown | 7.47 | 3981 | 748.86 | 3.38 | 745.48 | Yes | N/A | N/A | 2023-12-27 | 2023-10-06 | Unknown | Unknown | 2023-10-06 | 2024-01-18 | 105 | 75 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-02-12 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-02-23 | 1900-01-11 | 10 | 2024-02-23 | 2024-02-22 | Unknown | Unknown | 26 | 18 | 117 | 85 | 143 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-05 | -605 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-17 | 2025-04-18 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1755.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-17 | 2025-03-06 | Unknown | Unknown | 2025-03-06 | 2025-04-18 | 44 | 32 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-06-03 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-10 | 1900-01-07 | 6 | 2025-06-10 | 2025-06-10 | 1 | 1 | 47 | 33 | 53 | 39 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | -659 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-03-03 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | -6.63 | -27.71 | Unknown | Unknown | Unknown | 21.08 | 3981 | 1923.9 | -6.63 | 1930.53 | Yes | N/A | N/A | 2025-02-24 | 2025-03-03 | 8 | 6 | 2025-03-03 | 2025-03-03 | 1 | 1 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-04-01 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-03 | 1900-01-02 | 3 | 2025-04-03 | 2025-04-03 | 1 | 1 | 38 | 28 | 5 | 5 | 43 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-05 | -655 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-16 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 1036.44 | Unknown | Unknown | Unknown | Unknown | 1036.44 | 3981 | 1418.83 | 1036.44 | 382.39 | Yes | N/A | N/A | 2024-12-16 | 2024-12-17 | 2 | 2 | 2024-12-17 | 2024-12-18 | 2 | 2 | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-02-05 | 50 | 36 | Unknown | 2025-02-04 | Unknown | Unknown | 2025-02-05 | 2025-02-18 | 1900-01-13 | 10 | 2025-02-18 | 2025-02-18 | 1 | 1 | 52 | 38 | 17 | 13 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-26 | -393 | -281 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2023-11-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.82 | -4.72 | Unknown | Unknown | Unknown | -1.1 | 3981 | 481.24 | -5.82 | 487.06 | Yes | N/A | N/A | 2023-10-26 | 2023-08-08 | Unknown | Unknown | 2023-08-08 | 2023-11-03 | 88 | 64 | 2023-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | Unknown | Unknown | 2024-06-28 | 2024-06-28 | 1 | 1 | 0 | 0 | 89 | 65 | 89 | 65 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-24 | 318 | 227 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-17 | 2025-01-17 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 2724.85 | 968.28 | Unknown | 107.55 | -1847 | 3496.02 | Unknown | 1567.33 | 2724.85 | -1157.52 | Yes | N/A | N/A | 2025-01-17 | 2024-12-26 | Unknown | Unknown | 2024-12-26 | 2025-01-17 | 23 | 17 | 2025-01-17 | 2025-02-21 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-04-02 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-07 | 1900-01-05 | 4 | 2025-04-07 | 2025-04-07 | 1 | 1 | 77 | 55 | 30 | 22 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-17 | -311 | -223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-06-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1471.64 | -15.08 | Unknown | Unknown | Unknown | 1486.72 | 0 | 1637.3 | 1471.64 | 165.66 | Yes | N/A | N/A | 2024-05-14 | 2024-04-17 | Unknown | Unknown | 2024-04-17 | 2024-09-03 | 140 | 100 | 2024-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | 2025-03-17 | 2025-03-12 | Unknown | Unknown | 0 | 0 | 140 | 100 | 140 | 100 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | BORREGO SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | -407 | -292 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | 2024-01-14 | IOU Designed & Installed | N/A | No | N/A | 5062.12 | 1643.4 | Unknown | 1059.75 | -751 | 3109.97 | 7962 | 1482.75 | 5062.12 | -3579.37 | Yes | N/A | N/A | 2023-03-22 | 2023-03-22 | 1 | 1 | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-25 | 2024-01-14 | 235 | 167 | Unknown | 2023-07-26 | Unknown | Unknown | 2024-01-14 | 2024-01-17 | 1900-01-03 | 3 | 2024-01-17 | 2024-01-17 | 1 | 1 | 236 | 168 | 5 | 4 | 241 | 172 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 72.05 | 72.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | -393 | -282 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-16 | 2025-03-07 | IOU Designed & Installed | N/A | No | N/A | 50661.37 | 1473.45 | Unknown | Unknown | 351.17 | 48836.75 | Unknown | 15956.92 | 50661.37 | -34704.45 | Yes | N/A | N/A | 2024-09-04 | 2024-08-21 | Unknown | Unknown | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2025-02-27 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-05-13 | 1900-03-08 | 48 | 2025-05-13 | 2025-05-13 | 1 | 1 | 0 | 0 | 147 | 105 | 147 | 105 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 141.4 | 141.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-03 | -258 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-21 | 2023-07-21 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 7764.16 | 1972.16 | Unknown | 329.94 | 7.22 | 5454.84 | 3981 | 974.79 | 7764.16 | -6789.37 | Yes | N/A | N/A | 2023-07-21 | 2023-07-21 | 1 | 1 | 2023-07-21 | 2024-07-03 | 349 | 249 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2024-08-22 | 399 | 285 | Unknown | 2024-08-29 | Unknown | Unknown | 2024-08-22 | 2024-09-10 | 1900-01-19 | 14 | 2024-09-10 | 2024-09-18 | 9 | 7 | 400 | 286 | 378 | 270 | 778 | 556 | Steps 2,3,5,6,7 | 7 | 5 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | COUNTY OF SAN DIEGO-NORTH of 56 | 12525 | 12525 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-07-10 | -317 | -228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-10-02 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 4273.87 | 966.72 | Unknown | 329.94 | Unknown | 2977.21 | 3981 | 473.67 | 4273.87 | -3800.2 | Yes | N/A | N/A | 2023-09-19 | 2023-10-10 | 22 | 16 | 2023-10-10 | 2023-10-10 | 1 | 1 | 2023-10-10 | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | Unknown | 2023-10-16 | 2024-08-22 | 312 | 224 | Unknown | 2024-07-03 | Unknown | Unknown | 2024-08-22 | 2024-08-27 | 1900-01-05 | 4 | 2024-08-27 | 2024-08-27 | 1 | 1 | 334 | 240 | 8 | 6 | 342 | 246 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-10 | 191 | 138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-09-26 | 2024-07-01 | IOU Designed & Installed | N/A | No | N/A | 4004.47 | Unknown | Unknown | Unknown | 17.57 | 3986.9 | 3981 | 1165.84 | 4004.47 | -2838.63 | Yes | N/A | N/A | 2023-03-16 | 2024-01-31 | 322 | 230 | 2024-01-31 | 2024-02-09 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-03-06 | 35 | 25 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | Unknown | Unknown | 2024-07-01 | 2024-07-19 | 1900-01-18 | 15 | 2024-07-19 | 2024-07-19 | 1 | 1 | 322 | 230 | 65 | 49 | 387 | 279 | Steps 2,3,5,6,7 | 26 | 18 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 85.4 | 85.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-11 | -63 | -46 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | 2024-08-05 | IOU Designed & Installed | N/A | No | N/A | -422.9 | Unknown | Unknown | Unknown | -480 | 57.1 | 7770 | 1096.37 | -422.9 | 1519.27 | Yes | N/A | N/A | 2023-12-20 | 2023-12-20 | 1 | 1 | 2023-12-20 | 2023-12-20 | 1 | 1 | 2023-12-20 | 2024-02-22 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-08-05 | 1 | 1 | Unknown | 2025-03-18 | Unknown | Unknown | 2024-08-05 | 2024-08-12 | 1900-01-07 | 6 | 2024-08-12 | 2024-08-09 | Unknown | Unknown | 67 | 49 | 9 | 7 | 76 | 56 | Steps 2,3,5,6,7 | 225 | 161 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 79 | 79 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-30 | 1160 | 829 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-01 | 2025-04-29 | IOU Designed & Installed | N/A | No | N/A | 40028.62 | 2114.68 | Unknown | Unknown | 63.04 | 37850.9 | 0 | 23435.84 | 40028.62 | -16592.78 | Yes | N/A | N/A | 2024-05-01 | 2024-03-23 | Unknown | Unknown | 2024-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-04-18 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-06-02 | 1900-02-03 | 25 | 2025-06-02 | 2025-06-02 | 1 | 1 | 0 | 0 | 77 | 55 | 77 | 55 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-20 | -181 | -130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 29.66 | -26.35 | Unknown | Unknown | Unknown | 56.01 | 3981 | 1186.9 | 29.66 | 1157.24 | Yes | N/A | N/A | 2023-12-19 | 2024-02-29 | 73 | 53 | 2024-02-29 | 2024-02-29 | 1 | 1 | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | 2024-05-23 | 2024-05-23 | 1 | 1 | 73 | 53 | 2 | 2 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-14 | -246 | -177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-14 | 2023-04-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.73 | -16.91 | Unknown | Unknown | Unknown | 11.18 | 3981 | 762.52 | -5.73 | 768.25 | Yes | N/A | N/A | 2023-04-14 | 2023-04-29 | 16 | 11 | 2023-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-12 | Unknown | Unknown | 2023-07-12 | 2023-07-12 | 1 | 1 | 16 | 11 | 1 | 1 | 17 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | -653 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | 2024-06-18 | IOU Designed & Installed | N/A | No | N/A | 1443.87 | -24.68 | Unknown | Unknown | 2.27 | 1466.28 | Unknown | 1155.13 | 1443.87 | -288.74 | Yes | N/A | N/A | 2024-05-20 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-05-23 | 43 | 31 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-06-18 | 27 | 19 | Unknown | 2024-06-19 | Unknown | Unknown | 2024-06-18 | 2024-07-01 | 1900-01-13 | 10 | 2024-07-01 | 2024-07-01 | 1 | 1 | 27 | 19 | 58 | 42 | 85 | 61 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-28 | 833 | 596 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | 2025-04-30 | IOU Designed & Installed | N/A | No | N/A | 2199.22 | 368.46 | Unknown | Unknown | 2.25 | 1828.51 | 3941 | 1896.35 | 2199.22 | -302.87 | Yes | N/A | N/A | 2024-04-23 | 2024-04-17 | Unknown | Unknown | 2024-04-17 | 2024-04-23 | 7 | 5 | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2025-04-30 | 373 | 267 | Unknown | 2025-04-23 | Unknown | Unknown | 2025-04-30 | 2025-06-10 | 1900-02-10 | 30 | 2025-06-10 | 2025-06-10 | 1 | 1 | 373 | 267 | 50 | 36 | 423 | 303 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-28 | -906 | -649 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-06-27 | 2024-09-27 | IOU Designed & Installed | N/A | No | N/A | 730.67 | -14.28 | Unknown | Unknown | Unknown | 744.95 | Unknown | 186.09 | 730.67 | -544.58 | Yes | N/A | N/A | 2024-06-27 | 2024-06-02 | Unknown | Unknown | 2024-06-02 | 2024-07-05 | 34 | 25 | 2024-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | 2024-09-27 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-12-03 | 1900-03-08 | 48 | 2024-12-03 | 2024-12-03 | 1 | 1 | 85 | 61 | 103 | 74 | 188 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | -598 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -9.51 | -7.74 | Unknown | Unknown | Unknown | -1.77 | 3981 | 100.59 | -9.51 | 110.1 | Yes | N/A | N/A | 2023-03-06 | 2023-03-15 | 10 | 8 | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 10 | 8 | 1 | 1 | 11 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 564.6 | 564.6 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | 179 | 128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-29 | 2024-11-25 | IOU Designed & Installed | N/A | No | N/A | 831.99 | -15.6 | Unknown | Unknown | Unknown | 847.59 | 11943 | 736.2 | 831.99 | -95.79 | Yes | N/A | N/A | 2024-08-14 | 2024-07-29 | Unknown | Unknown | 2024-07-29 | 2024-10-03 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-27 | 32 | 24 | 2024-10-03 | 2024-11-15 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-02 | 1900-01-07 | 6 | 2024-12-02 | 2024-11-27 | Unknown | Unknown | 44 | 32 | 107 | 79 | 151 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | La Mesa | COUNTY OF SAN DIEGO-SOUTH of 56 | 76.25 | 76.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-23 | 95 | 69 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-04-24 | 2024-08-29 | IOU Designed & Installed | N/A | No | N/A | 60363.9 | 14406.71 | Unknown | Unknown | 7.68 | 45949.51 | Unknown | 21032.02 | 60363.9 | -39331.88 | Yes | N/A | N/A | 2024-03-04 | 2024-03-19 | 16 | 12 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | 2024-08-19 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-09-26 | 1900-01-28 | 21 | 2024-09-26 | 2024-09-26 | 1 | 1 | 16 | 12 | 73 | 53 | 89 | 65 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 61.05 | 61.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -438 | -315 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 838.41 | 320.22 | Unknown | Unknown | Unknown | 518.19 | Unknown | 926.95 | 838.41 | 88.54 | Yes | N/A | N/A | 2023-09-14 | 2023-09-14 | 1 | 1 | 2023-09-14 | 2023-09-14 | 1 | 1 | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-12-04 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-18 | 1900-01-14 | 11 | 2023-12-18 | 2023-12-18 | 1 | 1 | 83 | 59 | 17 | 13 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 523 | 523 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -297 | -214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-10-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12.12 | -10.75 | Unknown | Unknown | Unknown | 22.87 | 11943 | 2249.34 | 12.12 | 2237.22 | Yes | N/A | N/A | 2023-06-09 | 2023-10-03 | 117 | 83 | 2023-10-03 | 2023-10-17 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2024-04-11 | 178 | 128 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-05-07 | Unknown | Unknown | 295 | 211 | 15 | 11 | 310 | 222 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 71 | 71 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | -380 | -272 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-23 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 2840.06 | 755.92 | Unknown | Unknown | Unknown | 2084.14 | Unknown | 1861.33 | 2840.06 | -978.73 | Yes | N/A | N/A | 2024-09-20 | 2024-10-16 | 27 | 19 | 2024-10-16 | 2024-10-16 | 1 | 1 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2025-01-22 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-27 | 1900-02-05 | 27 | 2025-02-27 | 2025-02-27 | 1 | 1 | 126 | 90 | 39 | 29 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-10 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-06 | 2025-04-15 | IOU Designed & Installed | N/A | No | N/A | 954.97 | -10.2 | Unknown | Unknown | 4.69 | 960.48 | 3981 | 1215.3 | 954.97 | 260.33 | Yes | N/A | N/A | 2025-03-06 | 2025-02-12 | Unknown | Unknown | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-04-15 | 37 | 27 | Unknown | 2025-04-14 | Unknown | Unknown | 2025-04-15 | 2025-05-07 | 1900-01-22 | 17 | 2025-05-07 | 2025-05-07 | 1 | 1 | 37 | 27 | 25 | 19 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-03 | -482 | -345 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2025-01-13 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | 1629.14 | -32.74 | Unknown | Unknown | Unknown | 1661.88 | 3981 | 2035.01 | 1629.14 | 405.87 | Yes | N/A | N/A | 2024-11-13 | 2024-11-20 | 8 | 6 | 2024-11-20 | 2025-01-13 | 55 | 39 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-04-07 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-05-09 | 1900-02-01 | 25 | 2025-05-09 | 2025-05-09 | 1 | 1 | 93 | 67 | 89 | 65 | 182 | 132 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | 269 | 192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-02 | 2022-05-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | -334.44 | 1749.14 | Unknown | 589.6 | -3442 | 768.82 | Unknown | 3441.93 | -334.44 | 3776.37 | Yes | N/A | N/A | 2022-05-02 | 2023-07-26 | 451 | 323 | 2023-07-26 | 2023-08-10 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 451 | 323 | 17 | 13 | 468 | 336 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 67077.2 | 67077.2 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-05-11 | -255 | -182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-04-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 56.8 | Unknown | Unknown | Unknown | Unknown | 56.8 | 3981 | 1497.67 | 56.8 | 1440.87 | Yes | N/A | N/A | 2024-03-15 | 2024-04-03 | 20 | 14 | 2024-04-03 | 2024-04-11 | 9 | 7 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2024-08-29 | 1 | 1 | 20 | 14 | 10 | 8 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-07 | -599 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-22 | 2024-10-07 | IOU Designed & Installed | N/A | No | N/A | 7.57 | Unknown | Unknown | Unknown | Unknown | 7.57 | 3241 | 1608.79 | 7.57 | 1601.22 | Yes | N/A | N/A | 2024-08-16 | 2024-08-22 | 7 | 5 | 2024-08-22 | 2024-08-22 | 1 | 1 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-10-07 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-17 | 1900-01-10 | 9 | 2024-10-17 | 2024-10-16 | Unknown | Unknown | 54 | 38 | 12 | 10 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-09 | -92 | -67 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-06 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 892.13 | 2942.08 | Unknown | 214.42 | -3943 | 1678.63 | Unknown | 3943.03 | 892.13 | 3050.9 | Yes | N/A | N/A | 2025-01-06 | 2025-01-06 | 1 | 1 | 2025-01-06 | 2025-01-31 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-06 | 1900-01-03 | 4 | 2025-02-06 | 2025-02-06 | 1 | 1 | 1 | 1 | 31 | 25 | 32 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-23 | 2023-04-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 112.04 | -13.25 | Unknown | Unknown | Unknown | 125.29 | 3981 | 785.25 | 112.04 | 673.21 | Yes | N/A | N/A | 2023-04-23 | 2023-04-23 | 1 | 0 | 2023-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 1 | 0 | 1 | 1 | 2 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-05 | 379 | 272 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-12-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 817.01 | -14.41 | Unknown | Unknown | Unknown | 831.42 | Unknown | 853.03 | 817.01 | 36.02 | Yes | N/A | N/A | 2023-11-28 | 2023-12-28 | 31 | 23 | 2023-12-28 | 2024-01-08 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | Unknown | 2024-06-18 | Unknown | Unknown | 2024-06-18 | 2024-06-18 | 1 | 1 | 31 | 23 | 13 | 9 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | SAN DIEGO | 260.05 | 260.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-04 | 2024-10-09 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 753.64 | Unknown | Unknown | Unknown | Unknown | 753.64 | Unknown | 541.93 | 753.64 | -211.71 | Yes | N/A | N/A | 2024-10-04 | 2024-10-07 | 4 | 2 | 2024-10-07 | 2024-10-15 | 9 | 7 | 2024-10-15 | Unknown | Unknown | Unknown | 2024-10-11 | 2024-11-07 | 28 | 20 | 2024-10-15 | 2024-11-05 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2024-11-21 | 1900-01-16 | 13 | 2024-11-21 | 2024-11-21 | 1 | 1 | 26 | 18 | 55 | 41 | 81 | 59 | Steps 2,3,5,6,7 | 23 | 17 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-30 | 769 | 550 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | 2022-11-11 | 2024-07-02 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 20650.23 | 6872.36 | Unknown | 539.99 | 378.65 | 12859.23 | 0 | 21598.95 | 20650.23 | 948.72 | Yes | N/A | N/A | 2022-11-11 | 2023-02-09 | 91 | 65 | 2023-02-09 | 2023-06-20 | 132 | 94 | 2023-02-24 | 2023-03-29 | 34 | 24 | 2023-06-20 | 2023-07-25 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-07 | 1900-01-05 | 4 | 2024-07-07 | 2024-07-07 | 1 | 0 | 125 | 89 | 175 | 124 | 300 | 213 | Steps 2,3,5,6,7 | 116 | 82 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 200 | 200 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-24 | -676 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-28 | 2025-06-02 | IOU Designed & Installed | N/A | No | N/A | 77.72 | Unknown | Unknown | Unknown | Unknown | 77.72 | 3981 | 996.06 | 77.72 | 918.34 | Yes | N/A | N/A | 2025-05-06 | 2025-05-06 | 1 | 1 | 2025-05-06 | 2025-05-28 | 23 | 17 | 2025-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-06-02 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-06-17 | 1900-01-15 | 12 | 2025-06-17 | 2025-06-17 | 1 | 1 | 7 | 5 | 40 | 30 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 2556.4 | 2556.4 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-09-03 | -525 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-16 | 2023-12-16 | 2024-03-19 | IOU Designed & Installed | N/A | No | N/A | -4.39 | -3.57 | Unknown | Unknown | Unknown | -0.82 | Unknown | 515.81 | -4.39 | 520.2 | Yes | N/A | N/A | 2023-12-16 | 2023-12-16 | 1 | 0 | 2023-12-16 | 2023-12-16 | 1 | 0 | 2023-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-16 | 2024-03-19 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-03-27 | 1900-01-08 | 7 | 2024-03-27 | 2024-03-27 | 1 | 1 | 96 | 67 | 11 | 8 | 107 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | 1163 | 832 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-12 | 2023-01-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 17753.39 | 10680.57 | Unknown | 178.65 | -9399.42 | 16293.59 | Unknown | 21866.37 | 17753.39 | 4112.98 | Yes | N/A | N/A | 2023-01-12 | 2024-06-07 | 513 | 367 | 2024-06-07 | 2024-08-13 | 68 | 48 | 2024-06-07 | 2024-07-31 | 45 | 31 | 2024-07-25 | 2024-08-21 | 22 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | 2025-04-09 | 2025-04-09 | 1 | 1 | 558 | 398 | 91 | 63 | 649 | 461 | Steps 2,3,5,6,7 | 73 | 51 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | -316 | -227 | No | 2022-10-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-19 | 2022-10-19 | Unknown | IOU Designed & Installed | N/A | Yes | 236 | 1484.24 | -10.59 | Unknown | Unknown | 106.46 | 1388.37 | 3981 | 753.54 | 1484.24 | -730.7 | Yes | N/A | N/A | 2022-10-19 | 2023-06-12 | 237 | 169 | 2023-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-12-21 | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | Unknown | Unknown | Unknown | 2023-09-20 | Unknown | Unknown | 2023-09-20 | 2023-09-20 | 1 | 1 | 237 | 169 | 1 | 1 | 238 | 170 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | -599 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-10 | 2025-02-27 | IOU Designed & Installed | N/A | No | N/A | 34.19 | Unknown | Unknown | Unknown | Unknown | 34.19 | Unknown | 1597.33 | 34.19 | 1563.14 | Yes | N/A | N/A | 2024-12-09 | 2024-11-22 | Unknown | Unknown | 2024-11-22 | 2024-12-10 | 19 | 13 | 2024-12-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2025-02-27 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-03-31 | 1900-02-01 | 23 | 2025-03-31 | 2025-03-31 | 1 | 1 | 80 | 58 | 53 | 37 | 133 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | -138 | -99 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 501.46 | -10.2 | Unknown | Unknown | Unknown | 511.66 | 3241 | 1036.97 | 501.46 | 535.51 | Yes | N/A | N/A | 2024-04-03 | 2024-04-03 | 1 | 1 | 2024-04-03 | 2024-04-03 | 1 | 1 | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-07-25 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-09-10 | 1900-02-16 | 34 | 2024-09-10 | 2024-09-10 | 1 | 1 | 115 | 83 | 50 | 36 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | -615 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-23 | 2024-07-03 | IOU Designed & Installed | N/A | No | N/A | 22.89 | Unknown | Unknown | Unknown | Unknown | 22.89 | Unknown | 1510.59 | 22.89 | 1487.7 | Yes | N/A | N/A | 2024-05-09 | 2024-04-10 | Unknown | Unknown | 2024-04-10 | 2024-04-10 | 1 | 1 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-07-03 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-07-25 | 1900-01-22 | 17 | 2024-07-25 | 2024-07-25 | 1 | 1 | 42 | 30 | 25 | 19 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | -295 | -212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-02-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 618.29 | -17.06 | Unknown | Unknown | Unknown | 635.35 | 0 | 217.6 | 618.29 | -400.69 | Yes | N/A | N/A | 2023-02-06 | 2023-02-06 | 1 | 1 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | Unknown | Unknown | 2024-01-18 | 2024-01-18 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-08 | -250 | -179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | 2024-09-11 | IOU Designed & Installed | N/A | No | N/A | 879.34 | 253.74 | Unknown | Unknown | Unknown | 625.6 | 3981 | 1115.79 | 879.34 | 236.45 | Yes | N/A | N/A | 2023-12-14 | 2023-09-22 | Unknown | Unknown | 2023-09-22 | 2023-12-14 | 84 | 60 | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2024-09-11 | 273 | 195 | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2024-10-01 | 1900-01-20 | 15 | 2024-10-01 | 2024-10-01 | 1 | 1 | 273 | 195 | 106 | 76 | 379 | 271 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 99 | 99 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | -60 | -44 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | 2024-12-12 | IOU Designed & Installed | N/A | No | N/A | 2386.76 | 651.3 | Unknown | 15.71 | Unknown | 1719.75 | 3885 | 865.18 | 2386.76 | -1521.58 | Yes | N/A | N/A | 2023-12-20 | 2023-12-20 | 1 | 1 | 2023-12-20 | 2023-12-20 | 1 | 1 | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-12-12 | 359 | 257 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2024-12-31 | 1900-01-19 | 14 | 2024-12-31 | 2024-12-31 | 1 | 1 | 360 | 258 | 22 | 16 | 382 | 274 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | SD 1189-H1 JUNIPERS PH2 REC | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-03-01 | 257 | 184 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-21 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 30272.86 | 803.15 | Unknown | Unknown | 1604.29 | 27865.42 | 138241.36 | 20098.87 | 30272.86 | -10173.99 | Yes | N/A | N/A | 2024-02-07 | 2024-02-15 | 9 | 7 | 2024-02-15 | 2024-06-12 | 119 | 85 | 2024-03-27 | 2024-10-29 | 162 | 114 | 2024-05-24 | 2024-06-03 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | 2024-11-05 | 2024-11-13 | 1900-01-08 | 7 | 2024-11-13 | 2024-11-13 | 1 | 1 | 171 | 121 | 140 | 100 | 311 | 221 | Steps 2,3,5,6,7 | 235 | 167 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-03 | -250 | -179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-03 | 2025-06-26 | IOU Designed & Installed | N/A | No | N/A | -4427.66 | 1766.47 | Unknown | 1285.35 | -8339 | 859.52 | Unknown | 8339.32 | -4427.66 | 12766.98 | Yes | N/A | N/A | 2025-04-02 | 2025-04-02 | 1 | 1 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | 2025-06-26 | 1899-12-31 | 1 | 2025-06-26 | 2025-06-26 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-04 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-06 | 2023-09-19 | IOU Designed & Installed | N/A | No | N/A | -8.03 | -5.81 | Unknown | Unknown | Unknown | -2.22 | Unknown | 480.37 | -8.03 | 488.4 | Yes | N/A | N/A | 2023-09-06 | 2023-05-25 | Unknown | Unknown | 2023-05-25 | 2023-09-06 | 105 | 75 | 2023-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | 2023-09-19 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-09-25 | 1900-01-06 | 5 | 2023-09-25 | 2023-09-25 | 1 | 1 | 14 | 10 | 113 | 81 | 127 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | -583 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | 2024-05-20 | IOU Designed & Installed | N/A | No | N/A | 1845.58 | 689.44 | Unknown | 47.81 | -1096.23 | 2204.56 | 3981 | 1098.97 | 1845.58 | -746.61 | Yes | N/A | N/A | 2024-04-17 | 2024-03-06 | Unknown | Unknown | 2024-03-06 | 2024-04-17 | 43 | 31 | 2024-04-17 | 2024-07-02 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2024-05-20 | 32 | 22 | Unknown | 2024-05-16 | Unknown | Unknown | 2024-05-20 | 2024-07-25 | 1900-03-07 | 49 | 2024-07-25 | 2024-07-25 | 1 | 1 | 109 | 77 | 111 | 81 | 220 | 158 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-19 | -442 | -317 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-10 | 2024-11-21 | IOU Designed & Installed | N/A | No | N/A | 3501.44 | 866.24 | Unknown | 251.18 | Unknown | 2384.02 | 3981 | 1564.87 | 3501.44 | -1936.57 | Yes | N/A | N/A | 2024-10-02 | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2024-11-20 | 121 | 87 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-12-04 | 1900-01-13 | 10 | 2024-12-04 | 2024-12-04 | 1 | 1 | 0 | 0 | 136 | 98 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-25 | 18 | 13 | No | 2023-03-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | Yes | 304 | 35.63 | -43.24 | Unknown | Unknown | Unknown | 78.87 | 3981 | 586.34 | 35.63 | 550.71 | Yes | N/A | N/A | 2023-03-21 | 2024-01-19 | 305 | 219 | 2024-01-19 | 2024-01-19 | 1 | 1 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-02-12 | Unknown | Unknown | 305 | 219 | 1 | 1 | 306 | 220 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-20 | -216 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-19 | 2025-06-02 | IOU Designed & Installed | N/A | No | N/A | 1853.93 | Unknown | Unknown | Unknown | Unknown | 1853.93 | Unknown | 7076.28 | 1853.93 | 5222.35 | Yes | N/A | N/A | 2024-11-14 | 2024-11-19 | 6 | 4 | 2024-11-19 | 2025-05-27 | 190 | 136 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-06-18 | 1900-01-16 | 13 | 2025-06-18 | 2025-06-18 | 1 | 1 | 6 | 4 | 208 | 150 | 214 | 154 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | -684 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-06 | 2025-01-16 | IOU Designed & Installed | N/A | No | N/A | 1633.38 | 3438.64 | Unknown | 193.47 | -4338 | 2339.27 | Unknown | 4337.83 | 1633.38 | 2704.45 | Yes | N/A | N/A | 2025-01-06 | 2025-01-06 | 1 | 1 | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-01-16 | 1899-12-31 | 1 | 2025-01-16 | 2025-01-16 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | COUNTY OF SAN DIEGO-SOUTH of 56 | 64524.2 | 64524.2 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-03-14 | -417 | -300 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | 2023-12-21 | IOU Designed & Installed | N/A | No | N/A | 30649.14 | 6688.68 | Unknown | Unknown | 7.03 | 23953.43 | Unknown | 15623.84 | 30649.14 | -15025.3 | Yes | N/A | N/A | 2023-08-08 | 2023-08-08 | 1 | 1 | 2023-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2023-12-27 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-01-22 | 1900-02-01 | 23 | 2024-01-22 | 2024-01-22 | 1 | 1 | 1 | 1 | 48 | 34 | 49 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-22 | -655 | -470 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 2034 | 217.53 | Unknown | 90.75 | Unknown | 1725.72 | 3981 | 1484.6 | 2034 | -549.4 | Yes | N/A | N/A | 2024-07-02 | 2024-05-29 | Unknown | Unknown | 2024-05-29 | 2024-07-02 | 35 | 25 | 2024-07-02 | Unknown | Unknown | Unknown | 2024-07-05 | 2024-07-18 | 14 | 10 | 2024-07-02 | 2024-07-09 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-08-05 | 1900-01-27 | 20 | 2024-08-05 | 2024-08-05 | 1 | 1 | 8 | 6 | 78 | 56 | 86 | 62 | Steps 2,3,5,6,7 | 16 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | El Cajon | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-01-24 | 1320 | 944 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-16 | 2024-08-09 | IOU Designed & Installed | N/A | No | N/A | 12736.33 | Unknown | Unknown | Unknown | 177.9 | 12558.43 | Unknown | 833.54 | 12736.33 | -11902.79 | Yes | N/A | N/A | 2024-04-15 | 2024-04-15 | 1 | 1 | 2024-04-15 | 2024-06-27 | 74 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-15 | 21 | 15 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-09-05 | 1900-01-27 | 20 | 2024-09-05 | 2024-09-05 | 1 | 1 | 1 | 1 | 124 | 90 | 125 | 91 | Steps 2,3,5,6,7 | 18 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-22 | -470 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-10-19 | 2024-04-01 | IOU Designed & Installed | N/A | No | N/A | -15.51 | -13.64 | Unknown | Unknown | Unknown | -1.87 | Unknown | 163.83 | -15.51 | 179.34 | Yes | N/A | N/A | 2023-10-19 | 2024-03-28 | 162 | 116 | 2024-03-28 | 2024-03-28 | 1 | 1 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-04-01 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-05-09 | 1900-02-07 | 29 | 2024-05-09 | 2024-05-09 | 1 | 1 | 167 | 119 | 41 | 31 | 208 | 150 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | -553 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-04 | 2025-02-07 | IOU Designed & Installed | N/A | No | N/A | 955.58 | -18.48 | Unknown | Unknown | Unknown | 974.06 | 3981 | 1700.3 | 955.58 | 744.72 | Yes | N/A | N/A | 2025-02-04 | 2025-02-04 | 1 | 1 | 2025-02-04 | 2025-02-04 | 1 | 1 | 2025-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-02-07 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-04-09 | 1900-03-02 | 44 | 2025-04-09 | 2025-04-09 | 1 | 1 | 5 | 5 | 64 | 46 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 884.1 | 884.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | -263 | -189 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-10 | 2024-02-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 98.93 | -1.57 | Unknown | Unknown | Unknown | 100.5 | 3981 | 953.55 | 98.93 | 854.62 | Yes | N/A | N/A | 2024-02-10 | 2024-02-10 | 1 | 0 | 2024-02-10 | 2024-02-10 | 1 | 0 | 2024-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | 2025-02-11 | 2025-02-11 | 1 | 1 | 1 | 0 | 2 | 1 | 3 | 1 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 930.25 | 930.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-20 | 144 | 103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-01-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2273.58 | -10.98 | Unknown | Unknown | 25.48 | 2259.08 | 3981 | 949.54 | 2273.58 | -1324.04 | Yes | N/A | N/A | 2023-01-25 | 2023-03-01 | 36 | 26 | 2023-03-01 | 2024-03-29 | 395 | 283 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-11-19 | 236 | 168 | Unknown | 2025-01-23 | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | 2025-02-11 | 2025-02-11 | 1 | 1 | 272 | 194 | 396 | 284 | 668 | 478 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-16 | 18 | 14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -433.55 | -14.83 | Unknown | Unknown | -430 | 11.28 | 0 | 814.25 | -433.55 | 1247.8 | Yes | N/A | N/A | 2023-07-05 | 2023-07-28 | 24 | 18 | 2023-07-28 | 2023-07-28 | 1 | 1 | 2023-07-28 | 2025-04-28 | 641 | 457 | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | 2025-04-03 | 2025-04-03 | 1 | 1 | 665 | 475 | 2 | 2 | 667 | 477 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-10-03 | -324 | -233 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-12 | 2023-01-27 | 2023-10-31 | IOU Designed & Installed | N/A | No | N/A | 41647.2 | 1291.47 | Unknown | Unknown | 1948.26 | 38407.47 | 73891 | 18587.31 | 41647.2 | -23059.89 | Yes | N/A | N/A | 2022-12-12 | 2023-04-10 | 120 | 86 | 2023-04-10 | 2023-04-11 | 2 | 2 | 2023-01-12 | 2023-05-01 | 87 | 61 | 2023-02-07 | 2023-04-13 | 19 | 15 | 2023-07-18 | Unknown | Unknown | Unknown | 2023-07-18 | 2023-10-25 | 100 | 72 | 2023-10-31 | 2023-11-14 | 1900-01-14 | 11 | 2023-11-14 | 2023-11-14 | 1 | 1 | 207 | 147 | 137 | 101 | 344 | 248 | Steps 2,3,5,6,7 | 83 | 59 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-22 | -592 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2024-09-18 | IOU Designed & Installed | N/A | No | N/A | -1094 | Unknown | Unknown | Unknown | -1123 | 29 | 3981 | 2266.62 | -1094 | 3360.62 | Yes | N/A | N/A | 2024-07-02 | 2024-06-25 | Unknown | Unknown | 2024-06-25 | 2024-08-14 | 51 | 37 | 2024-08-14 | 2024-08-14 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-09-18 | 36 | 26 | Unknown | 2024-09-17 | Unknown | Unknown | 2024-09-18 | 2024-10-07 | 1900-01-19 | 14 | 2024-10-07 | 2024-10-07 | 1 | 1 | 37 | 27 | 72 | 52 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 642.05 | 642.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-30 | -225 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | 2924.46 | 657.78 | Unknown | 964.86 | 0.24 | 1301.58 | 3981 | 730.92 | 2924.46 | -2193.54 | Yes | N/A | N/A | 2023-08-15 | 2023-08-31 | 17 | 13 | 2023-08-31 | 2023-08-31 | 1 | 1 | 2023-08-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | 2023-10-13 | 44 | 32 | Unknown | 2023-09-29 | Unknown | Unknown | 2023-10-13 | 2023-10-18 | 1900-01-05 | 4 | 2023-10-18 | 2023-10-18 | 1 | 1 | 61 | 45 | 8 | 6 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 70880 | 70880 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-01 | -27 | -20 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-05-30 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | 55925.34 | 8168.12 | Unknown | 25.21 | 179.04 | 47552.97 | 158104 | 37845.58 | 55925.34 | -18079.76 | Yes | N/A | N/A | 2023-03-22 | 2023-03-30 | 9 | 7 | 2023-03-30 | 2024-03-19 | 356 | 254 | 2023-08-29 | 2023-08-31 | 3 | 3 | 2024-02-14 | 2024-03-28 | 28 | 18 | 2024-03-19 | Unknown | Unknown | Unknown | 2024-04-12 | 2024-08-26 | 137 | 97 | 2024-04-22 | 2024-09-04 | 1900-05-15 | 98 | 2024-09-04 | 2024-09-04 | 1 | 1 | 12 | 10 | 658 | 468 | 670 | 478 | Steps 2,3,5,6,7 | 338 | 242 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-16 | -637 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-22 | 2025-01-13 | IOU Designed & Installed | N/A | No | N/A | 5.47 | Unknown | Unknown | Unknown | Unknown | 5.47 | 3981 | 1103.3 | 5.47 | 1097.83 | Yes | N/A | N/A | 2024-11-12 | 2024-11-13 | 2 | 2 | 2024-11-13 | 2024-11-22 | 10 | 8 | 2024-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-01-13 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-01-17 | 1900-01-04 | 5 | 2025-01-17 | 2025-01-17 | 1 | 1 | 55 | 39 | 16 | 14 | 71 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego PA10 PH2 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 584 | 419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-05-24 | 2024-10-09 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 244631.6 | 60644.11 | Unknown | Unknown | 32310.82 | 151676.67 | 0 | 89414.9 | 244631.6 | -155216.7 | Yes | N/A | N/A | 2022-04-27 | 2023-04-04 | 343 | 245 | 2023-04-04 | 2023-11-03 | 214 | 154 | 2023-05-10 | 2024-10-03 | 335 | 240 | 2023-07-27 | 2023-08-07 | 12 | 8 | 2023-11-09 | Unknown | Unknown | Unknown | 2023-11-09 | 2024-10-08 | 335 | 239 | 2024-10-09 | 2024-10-24 | 1900-01-15 | 12 | 2024-10-24 | 2024-10-24 | 1 | 1 | 678 | 485 | 578 | 414 | 1256 | 899 | Steps 2,3,5,6,7 | 611 | 437 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 305.05 | 305.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-22 | -360 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-02 | 2024-08-21 | IOU Designed & Installed | N/A | No | N/A | 6457.29 | 1389.75 | Unknown | Unknown | 106.53 | 4961.01 | 3981 | 743.44 | 6457.29 | -5713.85 | Yes | N/A | N/A | 2024-01-02 | 2023-10-20 | Unknown | Unknown | 2023-10-20 | 2024-02-22 | 126 | 90 | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-08-21 | 182 | 130 | Unknown | 2024-08-15 | Unknown | Unknown | 2024-08-21 | 2024-09-27 | 1900-02-06 | 28 | 2024-09-27 | 2024-09-27 | 1 | 1 | 182 | 130 | 165 | 119 | 347 | 249 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-23 | -684 | -490 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-11 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 89.49 | -0.94 | Unknown | Unknown | Unknown | 90.43 | 3981 | 2309.58 | 89.49 | 2220.09 | Yes | N/A | N/A | 2025-02-11 | 2025-02-11 | 1 | 1 | 2025-02-11 | 2025-02-12 | 2 | 2 | 2025-02-12 | Unknown | Unknown | Unknown | 2025-02-12 | 2025-03-04 | 21 | 15 | 2025-02-11 | 2025-02-20 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-03-10 | 1900-01-18 | 13 | 2025-03-10 | 2025-03-10 | 1 | 1 | 11 | 9 | 43 | 31 | 54 | 40 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-30 | -942 | -673 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2024-01-16 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | -6.62 | -5.36 | Unknown | Unknown | Unknown | -1.26 | 3981 | 1984.18 | -6.62 | 1990.8 | Yes | N/A | N/A | 2023-11-29 | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2024-01-16 | 126 | 90 | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-01-22 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-01-31 | 1900-01-09 | 8 | 2024-01-31 | 2024-01-31 | 1 | 1 | 7 | 5 | 137 | 99 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-04 | -225 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1298.91 | -23.91 | Unknown | Unknown | Unknown | 1322.82 | 7962 | 2223.77 | 1298.91 | 924.86 | Yes | N/A | N/A | 2024-09-27 | 2024-10-07 | 11 | 7 | 2024-10-07 | 2024-11-08 | 33 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-11-07 | 28 | 20 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2024-11-21 | 1 | 1 | 11 | 7 | 62 | 46 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-13 | -637 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-19 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 5.93 | Unknown | Unknown | Unknown | Unknown | 5.93 | Unknown | 1085.63 | 5.93 | 1079.7 | Yes | N/A | N/A | 2024-07-11 | 2024-06-10 | Unknown | Unknown | 2024-06-10 | 2024-07-19 | 40 | 30 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-07-30 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-14 | 1900-01-15 | 12 | 2024-08-14 | 2024-08-14 | 1 | 1 | 12 | 8 | 57 | 43 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | 504 | 504 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | -212 | -152 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-06-28 | 2024-10-26 | IOU Designed & Installed | N/A | No | N/A | 3122.45 | 785.37 | Unknown | 212.58 | Unknown | 2124.5 | Unknown | 526.49 | 3122.45 | -2595.96 | Yes | N/A | N/A | 2024-06-21 | 2024-06-25 | 5 | 3 | 2024-06-25 | 2024-07-18 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-26 | 2024-10-31 | 1900-01-05 | 4 | 2024-10-31 | 2024-10-31 | 1 | 1 | 5 | 3 | 31 | 23 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2030-12-31 | -2569 | -1836 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-03-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 680.8 | -27.58 | Unknown | Unknown | -863.29 | 1571.67 | Unknown | 573.5 | 680.8 | -107.3 | Yes | N/A | N/A | 2023-03-17 | 2023-03-17 | 1 | 1 | 2023-03-17 | 2023-03-31 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-03-17 | 2023-12-19 | 20 | 14 | 2023-03-31 | 2023-11-07 | 222 | 158 | Unknown | 2023-10-25 | Unknown | Unknown | Unknown | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2023-12-19 | Unknown | Unknown | 223 | 159 | 35 | 25 | 258 | 184 | Steps 2,3,5,6,7 | 263 | 187 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 55 | 55 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | -633 | -454 | No | 2025-02-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | 2025-04-29 | IOU Designed & Installed | N/A | Yes | 30 | 5634.19 | 1086.39 | Unknown | 22.11 | 20.36 | 4505.33 | 3981 | 2536.77 | 5634.19 | -3097.42 | Yes | N/A | N/A | 2025-02-03 | 2025-03-03 | 29 | 21 | 2025-03-03 | 2025-02-12 | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-04-29 | 77 | 55 | Unknown | 2025-04-21 | Unknown | Unknown | 2025-04-29 | 2025-04-29 | 1899-12-31 | 1 | 2025-04-29 | 2025-04-29 | 1 | 1 | 106 | 76 | 2 | 2 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-16 | -435 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-14 | 2023-09-27 | IOU Designed & Installed | N/A | No | N/A | 1286.57 | 122.45 | Unknown | 117.75 | 24.48 | 1021.89 | 3981 | 1142.29 | 1286.57 | -144.28 | Yes | N/A | N/A | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | 2023-07-17 | 4 | 2 | 2023-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-09-27 | 73 | 53 | Unknown | 2023-09-26 | Unknown | Unknown | 2023-09-27 | 2023-11-08 | 1900-02-11 | 31 | 2023-11-08 | 2023-11-08 | 1 | 1 | 74 | 54 | 48 | 34 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-25 | -574 | -411 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | 2024-02-14 | IOU Designed & Installed | N/A | No | N/A | -21.13 | -12.84 | Unknown | Unknown | Unknown | -8.29 | 3981 | 723.46 | -21.13 | 744.59 | Yes | N/A | N/A | 2024-01-04 | 2023-11-08 | Unknown | Unknown | 2023-11-08 | 2024-01-04 | 58 | 42 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-02-14 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-03-15 | 1900-01-30 | 23 | 2024-03-15 | 2024-02-29 | Unknown | Unknown | 42 | 30 | 89 | 65 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 125.1 | 125.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-25 | -209 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3147.42 | Unknown | Unknown | Unknown | 109.61 | 3037.81 | 3981 | 2853.1 | 3147.42 | -294.32 | Yes | N/A | N/A | 2024-01-29 | 2024-01-04 | Unknown | Unknown | 2024-01-04 | 2024-02-07 | 35 | 25 | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | 2025-03-10 | 2025-02-28 | Unknown | Unknown | 0 | 0 | 35 | 25 | 35 | 25 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-11 | -128 | -93 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-30 | 2024-12-02 | IOU Designed & Installed | N/A | No | N/A | 114.06 | 44.96 | Unknown | Unknown | Unknown | 69.1 | 3981 | 3298.97 | 114.06 | 3184.91 | Yes | N/A | N/A | 2024-05-30 | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-05-30 | 37 | 27 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-12-02 | 187 | 133 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2024-12-04 | 1900-01-02 | 3 | 2024-12-04 | 2024-12-04 | 1 | 1 | 187 | 133 | 41 | 31 | 228 | 164 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-28 | -674 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-14 | 2025-02-21 | 2025-03-25 | IOU Designed & Installed | N/A | No | N/A | 2059.12 | 502.72 | Unknown | 73.44 | Unknown | 1482.96 | 3981 | 1674.7 | 2059.12 | -384.42 | Yes | N/A | N/A | 2025-02-14 | 2025-02-05 | Unknown | Unknown | 2025-02-05 | 2025-02-21 | 17 | 13 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-03-25 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-03-25 | 1899-12-31 | 1 | 2025-03-25 | 2025-03-25 | 1 | 1 | 33 | 23 | 19 | 15 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-24 | -523 | -375 | No | 2024-12-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-12 | 2025-04-22 | IOU Designed & Installed | N/A | Yes | 79 | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1032.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-11 | 2025-02-28 | 80 | 58 | 2025-02-28 | 2024-12-12 | Unknown | Unknown | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-04-22 | 132 | 94 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-19 | 1900-01-27 | 20 | 2025-05-19 | 2025-05-19 | 1 | 1 | 212 | 152 | 29 | 21 | 241 | 173 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 516 | 516 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-23 | 327 | 234 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-09-14 | 2023-10-05 | IOU Designed & Installed | N/A | No | N/A | 1290.38 | -42.95 | Unknown | Unknown | Unknown | 1333.33 | 3981 | 1066.6 | 1290.38 | -223.78 | Yes | N/A | N/A | 2023-07-14 | 2023-05-03 | Unknown | Unknown | 2023-05-03 | 2023-09-14 | 135 | 97 | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-10-05 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-11-15 | 1900-02-10 | 30 | 2023-11-15 | 2023-11-15 | 1 | 1 | 22 | 16 | 178 | 128 | 200 | 144 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | COUNTY OF SAN DIEGO-NORTH of 56 | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-22 | -667 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-02 | 2024-05-21 | IOU Designed & Installed | N/A | No | N/A | 4809.59 | 1420.44 | Unknown | 329.67 | Unknown | 3059.48 | 3981 | 890.82 | 4809.59 | -3918.77 | Yes | N/A | N/A | 2024-05-02 | 2024-05-02 | 1 | 1 | 2024-05-02 | 2024-05-02 | 1 | 1 | 2024-05-02 | Unknown | Unknown | Unknown | 2024-05-02 | 2024-06-07 | 37 | 27 | 2024-05-02 | 2024-05-21 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2024-06-24 | 1900-02-03 | 25 | 2024-06-24 | 2024-06-24 | 1 | 1 | 21 | 15 | 74 | 54 | 95 | 69 | Steps 2,3,5,6,7 | 36 | 26 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-17 | -519 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-11-02 | 2024-02-09 | IOU Designed & Installed | N/A | No | N/A | -3.07 | -2.48 | Unknown | Unknown | Unknown | -0.59 | Unknown | 550.04 | -3.07 | 553.11 | Yes | N/A | N/A | 2023-10-05 | 2023-11-02 | 29 | 21 | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2024-02-09 | 96 | 70 | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-02-14 | 1900-01-05 | 4 | 2024-02-14 | 2024-02-14 | 1 | 1 | 125 | 91 | 7 | 5 | 132 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | -450 | -323 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-02-06 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | 1222.54 | -2.55 | Unknown | Unknown | 22.01 | 1203.08 | 3981 | 931.38 | 1222.54 | -291.16 | Yes | N/A | N/A | 2023-02-06 | 2023-04-20 | 74 | 54 | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | 2023-07-27 | 98 | 70 | Unknown | 2023-07-19 | Unknown | Unknown | 2023-07-27 | 2023-08-08 | 1900-01-12 | 9 | 2023-08-08 | 2023-08-08 | 1 | 1 | 172 | 124 | 14 | 10 | 186 | 134 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | -47 | -34 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3.03 | -4.62 | Unknown | Unknown | Unknown | 7.65 | Unknown | 248.98 | 3.03 | 245.95 | Yes | N/A | N/A | 2024-02-22 | 2024-02-23 | 2 | 2 | 2024-02-23 | 2024-02-23 | 1 | 1 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 2 | 2 | 2 | 2 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 247 | 247 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-30 | 0 | 1 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-16 | 2025-06-27 | IOU Designed & Installed | N/A | No | N/A | 463.43 | Unknown | Unknown | Unknown | 17.48 | 445.95 | 3981 | 1607.04 | 463.43 | 1143.61 | Yes | N/A | N/A | 2024-12-13 | 2024-12-30 | 18 | 12 | 2024-12-30 | 2024-12-31 | 2 | 2 | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-06-27 | 179 | 129 | Unknown | 2025-06-27 | Unknown | Unknown | 2025-06-27 | 2025-06-30 | 1900-01-03 | 2 | 2025-06-30 | 2025-06-30 | 1 | 1 | 197 | 141 | 7 | 5 | 204 | 146 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-02 | -143 | -103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 2288.32 | 614.1 | Unknown | Unknown | Unknown | 1674.22 | Unknown | 1556.54 | 2288.32 | -731.78 | Yes | N/A | N/A | 2024-09-17 | 2024-09-16 | Unknown | Unknown | 2024-09-16 | 2024-09-17 | 2 | 2 | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2025-02-10 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-03-12 | 1900-01-30 | 23 | 2025-03-12 | 2025-03-12 | 1 | 1 | 147 | 105 | 34 | 26 | 181 | 131 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-26 | -668 | -477 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-08-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 382.1 | Unknown | Unknown | Unknown | Unknown | 382.1 | 3981 | 894.32 | 382.1 | 512.22 | Yes | N/A | N/A | 2024-08-12 | 2024-07-31 | Unknown | Unknown | 2024-07-31 | 2024-08-28 | 29 | 21 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-09-26 | 1 | 1 | 0 | 0 | 30 | 22 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 84.1 | 84.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | -595 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | 2024-12-13 | IOU Designed & Installed | N/A | No | N/A | 4.68 | Unknown | Unknown | Unknown | Unknown | 4.68 | Unknown | 1050.75 | 4.68 | 1046.07 | Yes | N/A | N/A | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-12-13 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2024-12-20 | 1900-01-07 | 6 | 2024-12-20 | 2024-12-20 | 1 | 1 | 109 | 79 | 10 | 8 | 119 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -667 | -477 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-09-16 | 2024-10-25 | IOU Designed & Installed | N/A | No | N/A | 368.92 | Unknown | Unknown | Unknown | Unknown | 368.92 | 3981 | 1114.43 | 368.92 | 745.51 | Yes | N/A | N/A | 2024-09-16 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2024-09-26 | 23 | 17 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-10-25 | 30 | 22 | Unknown | 2024-10-22 | Unknown | Unknown | 2024-10-25 | 2024-10-31 | 1900-01-06 | 5 | 2024-10-31 | 2024-10-31 | 1 | 1 | 30 | 22 | 31 | 23 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-09 | -375 | -268 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | 2025-01-09 | IOU Designed & Installed | N/A | No | N/A | 2125.52 | Unknown | Unknown | Unknown | 21.12 | 2104.4 | 3981 | 1195.63 | 2125.52 | -929.89 | Yes | N/A | N/A | 2024-04-23 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2024-05-03 | 53 | 39 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2025-01-09 | 252 | 180 | Unknown | 2025-01-30 | Unknown | Unknown | 2025-01-09 | 2025-02-04 | 1900-01-26 | 19 | 2025-02-04 | 2025-02-27 | 24 | 18 | 252 | 180 | 104 | 76 | 356 | 256 | Steps 2,3,5,6,7 | 21 | 15 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-28 | -466 | -333 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | 2023-12-08 | IOU Designed & Installed | N/A | No | N/A | 4077.67 | -26.9 | Unknown | Unknown | Unknown | 4104.57 | 3981 | 1059.21 | 4077.67 | -3018.46 | Yes | N/A | N/A | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-11-16 | 2023-12-08 | 23 | 17 | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2023-12-08 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2024-01-18 | 1900-02-10 | 30 | 2024-01-18 | 2024-01-18 | 1 | 1 | 24 | 18 | 66 | 48 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | -318 | -229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-12-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 898.89 | -1.26 | Unknown | Unknown | Unknown | 900.15 | 3981 | 1063.81 | 898.89 | 164.92 | Yes | N/A | N/A | 2023-11-09 | 2023-11-15 | 7 | 5 | 2023-11-15 | 2023-12-06 | 22 | 16 | 2023-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | Unknown | Unknown | Unknown | 2024-08-27 | Unknown | Unknown | 2024-08-27 | 2024-08-27 | 1 | 1 | 7 | 5 | 23 | 17 | 30 | 22 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-26 | -42 | -31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3412.39 | Unknown | Unknown | Unknown | 40.43 | 3371.96 | 3981 | 2373.52 | 3412.39 | -1038.87 | Yes | N/A | N/A | 2024-06-11 | 2024-07-12 | 32 | 24 | 2024-07-12 | 2024-07-19 | 8 | 6 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | 2025-02-12 | 2025-02-12 | 1 | 1 | 32 | 24 | 9 | 7 | 41 | 31 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-21 | -584 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-04-14 | IOU Designed & Installed | N/A | No | N/A | 796.02 | 236.04 | Unknown | 155.78 | Unknown | 404.2 | 3885 | 786.5 | 796.02 | -9.52 | Yes | N/A | N/A | 2023-03-14 | 2023-03-14 | 1 | 1 | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-14 | 2023-04-14 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | 2023-04-17 | 1900-01-03 | 2 | 2023-04-17 | 2023-04-17 | 1 | 1 | 33 | 25 | 5 | 3 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 94 | 94 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-07 | -209 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-05-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | -459.63 | -17.92 | Unknown | Unknown | -461 | 19.29 | 3981 | 1315.99 | -459.63 | 1775.62 | Yes | N/A | N/A | 2023-04-11 | 2023-05-08 | 28 | 20 | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-12 | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | Unknown | Unknown | Unknown | 2023-12-12 | Unknown | Unknown | 2023-12-12 | 2023-12-11 | Unknown | Unknown | 28 | 20 | 0 | 0 | 28 | 20 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 600 | 600 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-22 | 318 | 229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-10-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1615.24 | -43.62 | Unknown | Unknown | Unknown | 1658.86 | 7962 | 1038.5 | 1615.24 | -576.74 | Yes | N/A | N/A | 2023-08-30 | 2023-09-22 | 24 | 18 | 2023-09-22 | 2023-11-20 | 60 | 42 | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-11-14 | 6 | 4 | 2023-11-20 | 2024-03-13 | 115 | 83 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | 2024-04-08 | 2024-04-04 | Unknown | Unknown | 139 | 101 | 66 | 46 | 205 | 147 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | -347 | -249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-02-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 0.32 | -4.33 | Unknown | Unknown | Unknown | 4.65 | 0 | 217.6 | 0.32 | 217.28 | Yes | N/A | N/A | 2023-01-24 | 2023-02-04 | 12 | 9 | 2023-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-04 | 2023-10-18 | 83 | 59 | 2023-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | Unknown | Unknown | 2023-12-26 | 2023-12-26 | 1 | 1 | 12 | 9 | 84 | 60 | 96 | 69 | Steps 2,3,5,6,7 | 256 | 182 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | CARDIFF | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-20 | 297 | 212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-04-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 201.11 | -12.92 | Unknown | Unknown | -511 | 725.03 | 3981 | 1491.98 | 201.11 | 1290.87 | Yes | N/A | N/A | 2024-01-26 | 2024-03-15 | 50 | 36 | 2024-03-15 | 2024-05-09 | 56 | 40 | 2024-05-09 | 2024-07-16 | 69 | 49 | 2025-01-14 | 2025-02-05 | 23 | 17 | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | 2025-02-11 | 2025-02-11 | 1 | 1 | 119 | 85 | 80 | 58 | 199 | 143 | Steps 2,3,5,6,7 | 204 | 146 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-06-23 | 2023-08-22 | IOU Designed & Installed | N/A | No | N/A | -4.88 | -9.52 | Unknown | Unknown | Unknown | 4.64 | 3981 | 584.47 | -4.88 | 589.35 | Yes | N/A | N/A | 2023-03-20 | 2023-06-23 | 96 | 70 | 2023-06-23 | 2023-06-23 | 1 | 1 | 2023-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-08-22 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | 2023-08-23 | 1900-01-01 | 2 | 2023-08-23 | 2023-08-23 | 1 | 1 | 157 | 113 | 4 | 4 | 161 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 823.4 | 823.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-26 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 591.43 | -2.81 | Unknown | Unknown | 9.16 | 585.08 | 3981 | 1213.24 | 591.43 | 621.81 | Yes | N/A | N/A | 2025-02-05 | 2025-02-06 | 2 | 2 | 2025-02-06 | 2025-02-12 | 7 | 5 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | 2025-05-15 | 2025-05-15 | 1 | 1 | 2 | 2 | 8 | 6 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-20 | 6 | 5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-31 | 2023-06-07 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | 24439.61 | 8446.87 | Unknown | 1285.38 | 16.21 | 14691.15 | 99121 | 14207.78 | 24439.61 | -10231.83 | Yes | N/A | N/A | 2022-10-31 | 2023-04-12 | 164 | 118 | 2023-04-12 | 2023-07-25 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | Unknown | Unknown | 2023-07-26 | 2023-08-02 | 1900-01-07 | 6 | 2023-08-02 | 2023-07-26 | Unknown | Unknown | 164 | 118 | 113 | 81 | 277 | 199 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | 1990 | 1423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 887.72 | -21.46 | Unknown | Unknown | Unknown | 909.18 | Unknown | 238.24 | 887.72 | -649.48 | Yes | N/A | N/A | 2023-12-06 | 2023-12-29 | 24 | 18 | 2023-12-29 | 2024-01-17 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | 2024-01-08 | 11 | 7 | 2024-01-17 | 2024-06-12 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | Unknown | Unknown | 2024-06-13 | 2024-06-12 | Unknown | Unknown | 172 | 124 | 31 | 21 | 203 | 145 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-17 | -617 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-02-07 | 2025-03-21 | IOU Designed & Installed | N/A | No | N/A | -16.85 | -12.2 | Unknown | Unknown | Unknown | -4.65 | 3981 | 1030.1 | -16.85 | 1046.95 | Yes | N/A | N/A | 2025-02-07 | 2025-02-07 | 1 | 1 | 2025-02-07 | 2025-02-07 | 1 | 1 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-03-21 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-04-10 | 1900-01-20 | 15 | 2025-04-10 | 2025-04-09 | Unknown | Unknown | 44 | 32 | 22 | 16 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-30 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-15 | 2024-04-02 | IOU Designed & Installed | N/A | No | N/A | -12.23 | -9.92 | Unknown | Unknown | Unknown | -2.31 | 3981 | 1062.73 | -12.23 | 1074.96 | Yes | N/A | N/A | 2024-03-07 | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-03-15 | 38 | 28 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-04-02 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-04-24 | 1900-01-22 | 17 | 2024-04-24 | 2024-04-24 | 1 | 1 | 19 | 13 | 62 | 46 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-18 | -278 | -199 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2.38 | -2.9 | Unknown | Unknown | Unknown | 5.28 | Unknown | 297.38 | 2.38 | 295 | Yes | N/A | N/A | 2024-01-24 | 2024-01-09 | Unknown | Unknown | 2024-01-09 | 2024-01-24 | 16 | 12 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 0 | 0 | 17 | 13 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 24011 | 24011 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-06-29 | -431 | -308 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 483.15 | 489.8 | Unknown | 60.89 | -1145 | 1077.46 | 3981 | 2167.42 | 483.15 | 1684.27 | Yes | N/A | N/A | 2023-11-10 | 2023-11-20 | 11 | 7 | 2023-11-20 | 2023-11-20 | 1 | 1 | 2023-11-20 | 2023-11-20 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2024-04-15 | 148 | 106 | Unknown | 2024-03-25 | Unknown | Unknown | 2024-04-15 | 2024-04-24 | 1900-01-09 | 8 | 2024-04-24 | 2024-04-24 | 1 | 1 | 160 | 114 | 12 | 10 | 172 | 124 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -439 | -314 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 771.71 | Unknown | Unknown | Unknown | Unknown | 771.71 | 8703 | 4726.8 | 771.71 | 3955.09 | Yes | N/A | N/A | 2024-03-18 | 2024-04-03 | 17 | 13 | 2024-04-03 | 2024-07-08 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-08-28 | 52 | 38 | Unknown | 2024-10-09 | Unknown | Unknown | Unknown | 2024-10-21 | Unknown | Unknown | 2024-10-21 | 2024-10-18 | Unknown | Unknown | 69 | 51 | 97 | 69 | 166 | 120 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 167 | 167 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-18 | -354 | -255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-10-16 | 2024-07-24 | IOU Designed & Installed | N/A | No | N/A | 591.16 | 181.27 | Unknown | Unknown | Unknown | 409.89 | 3981 | 1013.96 | 591.16 | 422.8 | Yes | N/A | N/A | 2023-10-16 | 2023-08-03 | Unknown | Unknown | 2023-08-03 | 2023-10-16 | 75 | 53 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2024-07-24 | 283 | 203 | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-07-29 | 1900-01-05 | 4 | 2024-07-29 | 2024-07-29 | 1 | 1 | 283 | 203 | 82 | 58 | 365 | 261 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-05 | -637 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-03-02 | 2024-03-26 | IOU Designed & Installed | N/A | No | N/A | -6.52 | -5.29 | Unknown | Unknown | Unknown | -1.23 | 3981 | 501.14 | -6.52 | 507.66 | Yes | N/A | N/A | 2024-02-21 | 2024-01-17 | Unknown | Unknown | 2024-01-17 | 2024-03-02 | 46 | 33 | 2024-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-02 | 2024-03-26 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-04-08 | 1900-01-13 | 10 | 2024-04-08 | 2024-04-08 | 1 | 1 | 25 | 17 | 61 | 44 | 86 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 107.05 | 107.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | 526 | 377 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-18 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | 1220.19 | 1142.47 | Unknown | Unknown | -1327 | 1404.72 | 3981 | 2083.79 | 1220.19 | 863.6 | Yes | N/A | N/A | 2024-04-17 | 2024-04-25 | 9 | 7 | 2024-04-25 | 2025-02-26 | 308 | 220 | 2024-07-17 | 2024-09-05 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-05-08 | 72 | 52 | Unknown | 2025-05-09 | Unknown | Unknown | 2025-06-18 | 2025-06-18 | 1899-12-31 | 1 | 2025-06-18 | 2025-06-10 | Unknown | Unknown | 132 | 96 | 309 | 221 | 441 | 317 | Steps 2,3,5,6,7 | 224 | 160 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 42.05 | 42.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | -394 | -282 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-09 | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | 64.51 | Unknown | Unknown | Unknown | Unknown | 64.51 | 3981 | 1520.49 | 64.51 | 1455.98 | Yes | N/A | N/A | 2024-08-05 | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-08-09 | 108 | 78 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-09-03 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-09-05 | 1900-01-02 | 3 | 2024-09-05 | 2024-09-05 | 1 | 1 | 26 | 18 | 112 | 82 | 138 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | -590 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-11-11 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | 28.21 | Unknown | Unknown | Unknown | Unknown | 28.21 | Unknown | 1591.75 | 28.21 | 1563.54 | Yes | N/A | N/A | 2024-10-14 | 2024-11-11 | 29 | 21 | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2025-01-29 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-03 | 1900-01-05 | 4 | 2025-02-03 | 2025-02-03 | 1 | 1 | 109 | 79 | 8 | 6 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | -387 | -278 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2025-02-14 | 2025-06-17 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1581.19 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-30 | 2025-02-13 | 107 | 77 | 2025-02-13 | 2025-02-13 | 1 | 1 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-06-17 | 124 | 88 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-06-18 | 1900-01-01 | 2 | 2025-06-18 | 2025-06-18 | 1 | 1 | 231 | 165 | 4 | 4 | 235 | 169 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-12 | -425 | -305 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-07-26 | 2024-01-29 | IOU Designed & Installed | N/A | No | N/A | 1197.52 | -6.02 | Unknown | Unknown | 59.33 | 1144.21 | 3981 | 945.58 | 1197.52 | -251.94 | Yes | N/A | N/A | 2023-07-26 | 2023-08-04 | 10 | 8 | 2023-08-04 | 2023-08-04 | 1 | 1 | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | 2024-01-29 | 179 | 127 | Unknown | 2024-01-09 | Unknown | Unknown | 2024-01-29 | 2024-02-13 | 1900-01-15 | 12 | 2024-02-13 | 2024-02-12 | Unknown | Unknown | 189 | 135 | 17 | 13 | 206 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | -679 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | 1421.85 | 388.41 | Unknown | Unknown | Unknown | 1033.44 | 3981 | 1915.88 | 1421.85 | 494.03 | Yes | N/A | N/A | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-03-31 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-25 | 1900-01-25 | 20 | 2025-04-25 | 2025-04-25 | 1 | 1 | 20 | 14 | 28 | 22 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | SOLANA BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-29 | -555 | -398 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 947.67 | Unknown | Unknown | Unknown | 8.23 | 939.44 | 3981 | 975.35 | 947.67 | 27.68 | Yes | N/A | N/A | 2024-06-25 | 2024-06-25 | 1 | 1 | 2024-06-25 | 2024-07-15 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-08-01 | 18 | 14 | 2024-07-15 | 2024-10-11 | 89 | 65 | Unknown | 2024-09-09 | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | 2024-10-17 | 2024-10-21 | 5 | 3 | 90 | 66 | 44 | 32 | 134 | 98 | Steps 2,3,5,6,7 | 17 | 13 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-08 | -485 | -348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-12-12 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | 2311.86 | -5.95 | Unknown | Unknown | -1532.65 | 3850.46 | Unknown | 1404.45 | 2311.86 | -907.41 | Yes | N/A | N/A | 2024-11-19 | 2025-01-17 | 60 | 44 | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-06-23 | 61 | 43 | Unknown | 2025-06-11 | Unknown | Unknown | 2025-06-23 | 2025-06-26 | 1900-01-03 | 4 | 2025-06-26 | 2025-06-10 | Unknown | Unknown | 121 | 87 | 4 | 4 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-02 | -264 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-03-16 | 2023-04-18 | IOU Designed & Installed | N/A | No | N/A | 28.53 | -9.51 | Unknown | Unknown | Unknown | 38.04 | 3981 | 639.68 | 28.53 | 611.15 | Yes | N/A | N/A | 2023-03-16 | 2023-03-16 | 1 | 1 | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-16 | 2023-04-18 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | 2023-05-14 | 1900-01-26 | 19 | 2023-05-14 | 2023-05-14 | 1 | 0 | 35 | 25 | 28 | 19 | 63 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-04 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-11-06 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 453.39 | Unknown | Unknown | Unknown | 6.41 | 446.98 | 3981 | 325.03 | 453.39 | -128.36 | Yes | N/A | N/A | 2024-11-06 | 2024-10-27 | Unknown | Unknown | 2024-10-27 | 2024-11-25 | 30 | 21 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-01-30 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-25 | 1900-01-26 | 19 | 2025-02-25 | 2025-02-24 | Unknown | Unknown | 67 | 49 | 57 | 40 | 124 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-08 | -267 | -192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1724.26 | 1186.04 | Unknown | Unknown | -3472 | 561.7 | Unknown | 3472.27 | -1724.26 | 5196.53 | Yes | N/A | N/A | 2024-04-15 | 2024-05-15 | 31 | 23 | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 31 | 23 | 1 | 1 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | -604 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-07-17 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 3.03 | Unknown | Unknown | Unknown | Unknown | 3.03 | 3981 | 983.86 | 3.03 | 980.83 | Yes | N/A | N/A | 2024-05-30 | 2024-06-04 | 6 | 4 | 2024-06-04 | 2024-07-17 | 44 | 32 | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-07-30 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-19 | 1900-01-20 | 15 | 2024-08-19 | 2024-08-19 | 1 | 1 | 20 | 14 | 66 | 48 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | -672 | -481 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 247.74 | -25.7 | Unknown | Unknown | Unknown | 273.44 | 3981 | 1894.27 | 247.74 | 1646.53 | Yes | N/A | N/A | 2025-02-19 | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-02-19 | 2 | 2 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-20 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-04-10 | 1900-02-18 | 36 | 2025-04-10 | 2025-04-10 | 1 | 1 | 2 | 2 | 53 | 39 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | 652.05 | 652.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | -393 | -281 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-24 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 31.66 | Unknown | Unknown | Unknown | Unknown | 31.66 | 3981 | 1903.89 | 31.66 | 1872.23 | Yes | N/A | N/A | 2024-11-22 | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2024-11-24 | 20 | 14 | 2024-11-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-24 | 2025-01-28 | 66 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-01-30 | 1900-01-02 | 3 | 2025-01-30 | 2025-01-31 | 2 | 2 | 66 | 47 | 25 | 19 | 91 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-24 | -678 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-10 | 2025-02-28 | IOU Designed & Installed | N/A | No | N/A | 50.71 | Unknown | Unknown | Unknown | Unknown | 50.71 | 3981 | 1678.84 | 50.71 | 1628.13 | Yes | N/A | N/A | 2025-02-10 | 2025-02-10 | 1 | 1 | 2025-02-10 | 2025-02-10 | 1 | 1 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-28 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-03-17 | 1900-01-17 | 12 | 2025-03-17 | 2025-03-17 | 1 | 1 | 20 | 16 | 20 | 14 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 168.05 | 168.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-23 | -519 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-11 | 2023-12-07 | IOU Designed & Installed | N/A | No | N/A | 535.55 | 181.27 | Unknown | Unknown | Unknown | 354.28 | 3981 | 1569.27 | 535.55 | 1033.72 | Yes | N/A | N/A | 2023-10-11 | 2023-10-11 | 1 | 1 | 2023-10-11 | 2023-10-11 | 1 | 1 | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2023-12-07 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | 2023-12-21 | 1900-01-14 | 11 | 2023-12-21 | 2023-12-21 | 1 | 1 | 59 | 43 | 17 | 13 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | LEMON GROVE | 123.2 | 123.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-10 | 71 | 52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1583.6 | 285.38 | Unknown | 36.3 | 25.78 | 1236.14 | 5245 | 3841.95 | 1583.6 | 2258.35 | Yes | N/A | N/A | 2024-03-20 | 2024-06-05 | 78 | 56 | 2024-06-05 | 2024-07-17 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2025-01-23 | 67 | 49 | 2024-07-17 | 2025-04-21 | 279 | 199 | Unknown | 2025-03-27 | Unknown | Unknown | Unknown | 2025-04-22 | Unknown | Unknown | 2025-04-22 | 2025-04-22 | 1 | 1 | 357 | 255 | 111 | 81 | 468 | 336 | Steps 2,3,5,6,7 | 190 | 136 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 110 | 110 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-30 | 32 | 23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2024-05-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 43.22 | Unknown | Unknown | Unknown | Unknown | 43.22 | 3981 | 1127.42 | 43.22 | 1084.2 | Yes | N/A | N/A | 2024-05-22 | 2024-05-23 | 2 | 2 | 2024-05-23 | 2024-08-29 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-08-05 | 35 | 25 | 2024-08-29 | 2024-09-16 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | 2024-10-02 | 2024-10-01 | Unknown | Unknown | 21 | 15 | 134 | 96 | 155 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 19.2 | 19.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-02 | -632 | -453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-03-19 | 2024-04-02 | IOU Designed & Installed | N/A | No | N/A | 16.11 | -14.29 | Unknown | Unknown | Unknown | 30.4 | 3981 | 855.69 | 16.11 | 839.58 | Yes | N/A | N/A | 2024-01-24 | 2024-01-12 | Unknown | Unknown | 2024-01-12 | 2024-03-19 | 68 | 48 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-04-02 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-04-10 | 1900-01-08 | 7 | 2024-04-10 | 2024-04-10 | 1 | 1 | 15 | 11 | 78 | 56 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | -206 | -148 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2023-12-11 | 2024-07-18 | IOU Designed & Installed | N/A | No | N/A | 39755.57 | Unknown | Unknown | Unknown | Unknown | 39755.57 | 3320197 | 33005.57 | 39755.57 | -6750 | Yes | N/A | N/A | 2023-12-08 | 2024-02-08 | 63 | 45 | 2024-02-08 | 2024-05-13 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-07-16 | 65 | 47 | Unknown | 2024-06-07 | Unknown | Unknown | 2024-07-18 | 2024-07-25 | 1900-01-07 | 6 | 2024-07-25 | 2024-07-21 | Unknown | Unknown | 128 | 92 | 104 | 74 | 232 | 166 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 147.05 | 147.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | -633 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-25 | 2024-11-15 | 2024-12-02 | IOU Designed & Installed | N/A | No | N/A | 4.81 | Unknown | Unknown | Unknown | Unknown | 4.81 | Unknown | 1625.64 | 4.81 | 1620.83 | Yes | N/A | N/A | 2024-10-25 | 2024-10-04 | Unknown | Unknown | 2024-10-04 | 2024-11-15 | 43 | 31 | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-02 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2024-12-16 | 1900-01-14 | 11 | 2024-12-16 | 2024-12-12 | Unknown | Unknown | 18 | 12 | 58 | 42 | 76 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-18 | 2025-02-13 | IOU Designed & Installed | N/A | No | N/A | 434.23 | -8.05 | Unknown | Unknown | Unknown | 442.28 | 3981 | 1590.78 | 434.23 | 1156.55 | Yes | N/A | N/A | 2024-10-08 | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2024-10-18 | 24 | 18 | 2024-10-18 | Unknown | Unknown | Unknown | 2024-10-18 | 2024-11-09 | 23 | 16 | 2024-10-18 | 2025-02-13 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-02-25 | 1900-01-12 | 9 | 2025-02-25 | 2025-02-25 | 1 | 1 | 119 | 85 | 61 | 44 | 180 | 129 | Steps 2,3,5,6,7 | 22 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-08 | -677 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-04 | 2025-06-04 | 2025-06-16 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1431.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-04 | 2025-05-19 | Unknown | Unknown | 2025-05-19 | 2025-06-09 | 22 | 16 | 2025-06-09 | 2025-06-24 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-16 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-06-30 | 1900-01-14 | 11 | 2025-06-30 | 2025-06-30 | 1 | 1 | 24 | 18 | 38 | 28 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 117 | 117 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | -556 | -399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-22 | 2024-03-05 | IOU Designed & Installed | N/A | No | N/A | 495.38 | -8.26 | Unknown | Unknown | 7.42 | 496.22 | 3981 | 799 | 495.38 | 303.62 | Yes | N/A | N/A | 2024-01-22 | 2023-12-20 | Unknown | Unknown | 2023-12-20 | 2024-02-06 | 49 | 35 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-03-05 | 29 | 21 | Unknown | 2024-04-03 | Unknown | Unknown | 2024-03-05 | 2024-04-01 | 1900-01-27 | 20 | 2024-04-01 | 2024-04-01 | 1 | 1 | 29 | 21 | 78 | 56 | 107 | 77 | Steps 2,3,5,6,7 | 29 | 21 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 52 | 52 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-03 | 320 | 229 | No | 2024-04-30 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | 2025-06-18 | IOU Designed & Installed | N/A | Yes | 57 | -24.1 | Unknown | Unknown | Unknown | -594 | 569.9 | 7962 | 1550.47 | -24.1 | 1574.57 | Yes | N/A | N/A | 2024-04-30 | 2024-07-12 | 74 | 54 | 2024-07-12 | 2024-08-15 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2025-06-18 | 308 | 220 | Unknown | 2025-05-16 | Unknown | Unknown | 2025-06-18 | 2025-06-19 | 1900-01-01 | 2 | 2025-06-19 | 2025-06-19 | 1 | 1 | 382 | 274 | 38 | 28 | 420 | 302 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-13 | 2023-12-27 | IOU Designed & Installed | N/A | No | N/A | 0.92 | -13.65 | Unknown | Unknown | Unknown | 14.57 | 7882 | 568.27 | 0.92 | 567.35 | Yes | N/A | N/A | 2023-12-13 | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-13 | 3 | 3 | 2023-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2023-12-27 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2024-03-01 | 1900-03-06 | 48 | 2024-03-01 | 2024-03-01 | 1 | 1 | 15 | 11 | 70 | 52 | 85 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SD 1190-A2 CMR PA17 WO2 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 584 | 419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | -2798.75 | 474.6 | Unknown | Unknown | -12221 | 8947.65 | Unknown | Not available | -2798.75 | Unknown | Yes | N/A | N/A | 2024-08-08 | 2024-08-08 | 1 | 1 | 2024-08-08 | 2024-10-16 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-31 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-12-30 | 1900-03-11 | 51 | 2024-12-30 | 2024-10-24 | Unknown | Unknown | 17 | 13 | 141 | 101 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | VALLEY CENTER | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-23 | 548 | 393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-05-31 | 2024-11-27 | IOU Designed & Installed | N/A | No | N/A | 22343.32 | 2839.83 | Unknown | 805.01 | 76.94 | 18621.54 | 3981 | 240.98 | 22343.32 | -22102.34 | Yes | N/A | N/A | 2024-04-09 | 2024-05-31 | 53 | 39 | 2024-05-31 | 2024-11-22 | 176 | 126 | 2024-08-01 | 2024-08-01 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2025-04-23 | 1900-05-27 | 106 | 2025-04-23 | 2025-04-23 | 1 | 1 | 54 | 40 | 325 | 233 | 379 | 273 | Steps 2,3,5,6,7 | 113 | 81 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | 2025-03-26 | IOU Designed & Installed | N/A | No | N/A | -5.02 | -21.06 | Unknown | Unknown | Unknown | 16.04 | 3981 | 1633.73 | -5.02 | 1638.75 | Yes | N/A | N/A | 2024-12-05 | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2024-12-05 | 72 | 52 | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | 2025-03-26 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-04-17 | 1900-01-22 | 17 | 2025-04-17 | 2025-04-17 | 1 | 1 | 112 | 80 | 96 | 70 | 208 | 150 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-03 | -114 | -83 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-07-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | -693.14 | 1408.44 | Unknown | Unknown | -2753 | 651.42 | Unknown | 2753.5 | -693.14 | 3446.64 | Yes | N/A | N/A | 2023-07-26 | 2023-07-26 | 1 | 1 | 2023-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-09 | -657 | -470 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-28 | 2024-12-28 | 2025-02-06 | IOU Designed & Installed | N/A | No | N/A | 33.26 | Unknown | Unknown | Unknown | Unknown | 33.26 | 3981 | 1993.02 | 33.26 | 1959.76 | Yes | N/A | N/A | 2024-12-28 | 2024-12-27 | Unknown | Unknown | 2024-12-27 | 2024-12-28 | 2 | 1 | 2024-12-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-28 | 2025-02-06 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-20 | 1900-01-14 | 11 | 2025-02-20 | 2025-02-20 | 1 | 1 | 41 | 29 | 18 | 13 | 59 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-17 | 54 | 39 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | Unknown | Unknown | IOU Designed & Installed | N/A | No | N/A | -63.11 | Unknown | Unknown | Unknown | 3.65 | -66.76 | 3981 | 1924.08 | -63.11 | 1987.19 | Yes | N/A | N/A | 2023-04-04 | 2023-04-14 | 11 | 9 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-04-11 | 1 | 1 | 11 | 9 | 1 | 1 | 12 | 10 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-17 | 29 | 22 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-06-09 | 2024-01-11 | IOU Designed & Installed | N/A | No | N/A | 180672.59 | 23595.9 | Unknown | 49.68 | 2269.15 | 154757.86 | 370014 | 109417.34 | 180672.59 | -71255.25 | Yes | N/A | N/A | 2023-02-28 | 2023-06-09 | 102 | 74 | 2023-06-09 | 2023-12-26 | 201 | 143 | 2023-07-28 | 2023-12-21 | 37 | 27 | 2023-09-07 | 2024-01-10 | 126 | 90 | 2023-12-26 | 2024-06-12 | 170 | 122 | 2024-05-21 | 2024-07-18 | 59 | 43 | 2024-01-11 | 2024-08-15 | 1900-08-05 | 156 | 2024-08-15 | 2024-08-15 | 1 | 1 | 309 | 223 | 605 | 433 | 914 | 656 | Steps 2,3,5,6,7 | 482 | 344 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 786 | 786 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | -485 | -347 | No | 2024-08-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | 2025-03-18 | IOU Designed & Installed | N/A | Yes | 81 | 1404.99 | Unknown | Unknown | Unknown | 32.89 | 1372.1 | 3941 | 1501.3 | 1404.99 | 96.31 | Yes | N/A | N/A | 2024-08-26 | 2024-11-15 | 82 | 60 | 2024-11-15 | 2024-09-05 | Unknown | Unknown | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2025-03-18 | 195 | 139 | Unknown | 2025-01-03 | Unknown | Unknown | 2025-03-18 | 2025-03-21 | 1900-01-03 | 4 | 2025-03-21 | 2025-03-20 | Unknown | Unknown | 277 | 199 | 4 | 4 | 281 | 203 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | -554 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | 2025-02-14 | IOU Designed & Installed | N/A | No | N/A | -524.8 | Unknown | Unknown | Unknown | -1185.7 | 660.9 | Unknown | 1175.27 | -524.8 | 1700.07 | Yes | N/A | N/A | 2024-10-29 | 2024-11-14 | 17 | 13 | 2024-11-14 | 2024-12-03 | 20 | 14 | 2024-12-03 | 2025-01-15 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-02-14 | 31 | 23 | Unknown | 2025-02-10 | Unknown | Unknown | 2025-02-14 | 2025-03-26 | 1900-02-09 | 29 | 2025-03-26 | 2025-03-26 | 1 | 1 | 92 | 68 | 62 | 44 | 154 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 150.05 | 150.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-13 | 120 | 87 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-06-02 | 2024-03-06 | IOU Designed & Installed | N/A | No | N/A | 502.52 | -5.81 | Unknown | Unknown | 13.12 | 495.21 | 3981 | 1010.38 | 502.52 | 507.86 | Yes | N/A | N/A | 2023-05-22 | 2023-06-05 | 15 | 11 | 2023-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2024-03-06 | 276 | 198 | Unknown | 2024-02-27 | Unknown | Unknown | 2024-03-06 | 2024-03-07 | 1900-01-01 | 2 | 2024-03-07 | 2024-03-12 | 6 | 4 | 291 | 209 | 8 | 6 | 299 | 215 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 223 | 223 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-20 | -578 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-05-04 | 2023-06-14 | IOU Designed & Installed | N/A | No | N/A | -18.41 | -13.34 | Unknown | Unknown | Unknown | -5.07 | 3981 | 512.85 | -18.41 | 531.26 | Yes | N/A | N/A | 2023-04-03 | 2023-05-04 | 32 | 24 | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | 2023-06-14 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | 2023-06-22 | 1900-01-08 | 7 | 2023-06-22 | 2023-06-22 | 1 | 1 | 74 | 54 | 10 | 8 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-13 | -381 | -273 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2024-01-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 533.16 | -9.92 | Unknown | Unknown | Unknown | 543.08 | 0 | 957.59 | 533.16 | 424.43 | Yes | N/A | N/A | 2023-11-28 | 2023-09-20 | Unknown | Unknown | 2023-09-20 | 2024-01-05 | 108 | 78 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | 2024-08-28 | 2024-08-28 | 1 | 1 | 0 | 0 | 109 | 79 | 109 | 79 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | -596 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-17 | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | 25.44 | Unknown | Unknown | Unknown | Unknown | 25.44 | 3981 | 1364.79 | 25.44 | 1339.35 | Yes | N/A | N/A | 2024-07-17 | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2025-03-06 | 235 | 169 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-09-17 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-11-19 | 1900-03-04 | 46 | 2024-11-19 | 2024-11-19 | 1 | 1 | 63 | 45 | 300 | 216 | 363 | 261 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 1092 | 1092 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-11-07 | -38 | -29 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2024-01-11 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | -531.62 | -32.23 | Unknown | Unknown | -1156 | 656.61 | 8192.38 | 2391.44 | -531.62 | 2923.06 | Yes | N/A | N/A | 2023-12-12 | 2024-01-11 | 31 | 23 | 2024-01-11 | 2024-01-11 | 1 | 1 | 2024-01-11 | 2024-07-01 | 80 | 54 | 2024-01-11 | 2024-07-05 | 78 | 58 | 2024-05-01 | 2024-07-09 | 70 | 50 | Unknown | 2024-06-11 | Unknown | Unknown | 2024-07-09 | 2024-07-24 | 1900-01-15 | 12 | 2024-07-24 | 2024-09-30 | 69 | 49 | 181 | 127 | 164 | 120 | 345 | 247 | Steps 2,3,5,6,7 | 237 | 169 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-15 | -479 | -343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-09-28 | IOU Designed & Installed | N/A | No | N/A | 1338.83 | -11.65 | Unknown | Unknown | 4.73 | 1345.75 | 3981 | 2025.27 | 1338.83 | 686.44 | Yes | N/A | N/A | 2023-04-18 | 2023-06-30 | 74 | 54 | 2023-06-30 | 2023-07-03 | 4 | 2 | 2023-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-09-28 | 91 | 65 | Unknown | 2023-09-27 | Unknown | Unknown | 2023-09-28 | 2023-10-26 | 1900-01-28 | 21 | 2023-10-26 | 2023-10-25 | Unknown | Unknown | 165 | 119 | 33 | 23 | 198 | 142 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 65.4 | 65.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-30 | -448 | -321 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-11-29 | 2024-04-18 | IOU Designed & Installed | N/A | No | N/A | 8674.66 | 273.47 | Unknown | Unknown | Unknown | 8401.19 | 3981 | 1965.87 | 8674.66 | -6708.79 | Yes | N/A | N/A | 2023-10-10 | 2023-11-29 | 51 | 37 | 2023-11-29 | 2024-03-08 | 101 | 73 | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-03-08 | 1 | 1 | 2024-03-08 | 2024-04-05 | 29 | 21 | Unknown | 2024-03-27 | Unknown | Unknown | 2024-04-18 | 2024-05-16 | 1900-01-28 | 21 | 2024-05-16 | 2024-05-08 | Unknown | Unknown | 80 | 58 | 131 | 95 | 211 | 153 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-09 | -639 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-08 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 129.49 | -1.88 | Unknown | Unknown | Unknown | 131.37 | 3981 | 1489.77 | 129.49 | 1360.28 | Yes | N/A | N/A | 2024-10-02 | 2024-09-16 | Unknown | Unknown | 2024-09-16 | 2024-10-08 | 23 | 17 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-10 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-12-09 | 1900-03-01 | 43 | 2024-12-09 | 2024-12-09 | 1 | 1 | 3 | 3 | 85 | 61 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | 51 | 51 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | -168 | -121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-06-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 11.52 | Unknown | Unknown | Unknown | Unknown | 11.52 | Unknown | 362.22 | 11.52 | 350.7 | Yes | N/A | N/A | 2024-05-07 | 2024-06-06 | 31 | 23 | 2024-06-06 | 2024-08-29 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-06-05 | 27 | 19 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2024-10-24 | 1 | 1 | 31 | 23 | 113 | 81 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | -499 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2024-12-31 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 1039.69 | 264.94 | Unknown | Unknown | Unknown | 774.75 | Unknown | 1797.26 | 1039.69 | 757.57 | Yes | N/A | N/A | 2024-12-31 | 2024-12-02 | Unknown | Unknown | 2024-12-02 | 2024-12-31 | 30 | 22 | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-02-20 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-04-09 | 1900-02-17 | 35 | 2025-04-09 | 2025-04-09 | 1 | 1 | 52 | 38 | 80 | 58 | 132 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-31 | 206 | 147 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-10-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 553.86 | -38.32 | Unknown | Unknown | 2.71 | 589.47 | 3981 | 2052.25 | 553.86 | 1498.39 | Yes | N/A | N/A | 2024-09-26 | 2024-07-29 | Unknown | Unknown | 2024-07-29 | 2024-10-17 | 81 | 59 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2025-01-09 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-03-25 | Unknown | Unknown | 85 | 61 | 81 | 59 | 166 | 120 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | Encinitas | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-16 | -81 | -58 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-11 | 2023-03-09 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | 20420.93 | 74.45 | Unknown | Unknown | -3574.03 | 23920.51 | 0 | 3881.79 | 20420.93 | -16539.14 | Yes | N/A | N/A | 2023-01-11 | 2023-03-21 | 70 | 50 | 2023-03-21 | 2023-12-28 | 283 | 203 | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-01-11 | 24 | 18 | 2024-01-24 | Unknown | Unknown | Unknown | 2024-01-24 | 2024-01-30 | 7 | 5 | 2024-05-17 | 2024-09-26 | 1900-05-12 | 95 | 2024-09-26 | 2024-09-26 | 1 | 1 | 70 | 50 | 448 | 322 | 518 | 372 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-13 | -503 | -360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-03 | 2025-03-26 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1640.84 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-03 | 2025-03-08 | 6 | 5 | 2025-03-08 | 2025-03-10 | 3 | 1 | 2025-03-03 | 2025-03-10 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-03-26 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-04-28 | 1900-02-02 | 24 | 2025-04-28 | 2025-04-28 | 1 | 1 | 31 | 24 | 38 | 26 | 69 | 50 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 77.05 | 77.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-23 | -428 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-10-14 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1683.03 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-23 | 2024-10-01 | 162 | 116 | 2024-10-01 | 2024-10-14 | 14 | 10 | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2024-10-24 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-21 | 1900-01-28 | 21 | 2024-11-21 | 2024-11-21 | 1 | 1 | 173 | 125 | 44 | 32 | 217 | 157 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-14 | -533 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | 2023-11-28 | IOU Designed & Installed | N/A | No | N/A | 914.3 | 579.62 | Unknown | Unknown | Unknown | 334.68 | Unknown | 496.75 | 914.3 | -417.55 | Yes | N/A | N/A | 2023-11-01 | 2023-11-01 | 1 | 1 | 2023-11-01 | 2023-11-01 | 1 | 1 | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2023-11-28 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2023-12-29 | 1900-01-31 | 24 | 2023-12-29 | 2023-12-29 | 1 | 1 | 29 | 21 | 34 | 26 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-04 | 226 | 163 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2025-01-07 | 2025-04-17 | IOU Designed & Installed | N/A | No | N/A | 36969.31 | 3244.26 | Unknown | 47.14 | 41.97 | 33635.94 | Unknown | 23560.05 | 36969.31 | -13409.26 | Yes | N/A | N/A | 2024-12-09 | 2024-12-12 | 4 | 4 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-04-07 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-06-18 | 1900-03-03 | 45 | 2025-06-18 | 2025-06-18 | 1 | 1 | 4 | 4 | 92 | 66 | 96 | 70 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-10 | 11 | 8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-10 | 2022-08-10 | 2023-09-15 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 55554.38 | 11220.06 | Unknown | Unknown | 180.62 | 44153.7 | 1538940 | 74945.56 | 55554.38 | 19391.18 | Yes | N/A | N/A | 2022-08-10 | 2023-02-28 | 203 | 145 | 2023-02-28 | 2023-06-02 | 95 | 69 | 2023-03-08 | 2023-05-26 | 10 | 7 | 2023-06-02 | 2023-06-05 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | 2023-09-12 | 79 | 57 | 2023-09-15 | 2023-11-21 | 1900-03-08 | 48 | 2023-11-21 | 2023-11-21 | 1 | 1 | 213 | 152 | 247 | 177 | 460 | 329 | Steps 2,3,5,6,7 | 86 | 62 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-11-12 | 1581 | 1130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-27 | 2023-01-27 | 2025-03-06 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 38432.43 | 10643.51 | Unknown | Unknown | 124.02 | 27664.9 | 110964 | 27990.78 | 38432.43 | -10441.65 | Yes | N/A | N/A | 2023-01-27 | 2023-08-28 | 214 | 152 | 2023-08-28 | 2024-03-01 | 187 | 135 | 2023-09-21 | 2024-01-29 | 12 | 8 | 2023-10-06 | 2024-10-16 | 238 | 170 | 2024-11-20 | Unknown | Unknown | Unknown | 2024-11-20 | 2025-02-03 | 76 | 54 | 2025-03-06 | 2025-03-12 | 1900-01-06 | 5 | 2025-03-12 | 2025-03-12 | 1 | 1 | 226 | 160 | 509 | 365 | 735 | 525 | Steps 2,3,5,6,7 | 277 | 197 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-24 | 2024-10-25 | IOU Designed & Installed | N/A | No | N/A | 5.69 | Unknown | Unknown | Unknown | Unknown | 5.69 | 3981 | 197.01 | 5.69 | 191.32 | Yes | N/A | N/A | 2024-09-19 | 2024-08-24 | Unknown | Unknown | 2024-08-24 | 2024-10-07 | 45 | 31 | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-25 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2024-11-13 | 1900-01-19 | 14 | 2024-11-13 | 2024-11-13 | 1 | 1 | 19 | 15 | 66 | 46 | 85 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-06 | -154 | -110 | No | 2023-06-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-06-08 | 2023-10-16 | IOU Designed & Installed | N/A | Yes | 8 | 1176.58 | 808.88 | Unknown | Unknown | Unknown | 367.7 | 3981 | 464.78 | 1176.58 | -711.8 | Yes | N/A | N/A | 2023-06-08 | 2023-06-16 | 9 | 7 | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-10-16 | 123 | 87 | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2024-02-03 | 1900-04-20 | 80 | 2024-02-03 | 2024-02-03 | 1 | 0 | 132 | 94 | 112 | 80 | 244 | 174 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 117.05 | 117.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | -126 | -91 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-08-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1021.81 | 321.51 | Unknown | 40.84 | 39.57 | 619.89 | 3981 | 810.31 | 1021.81 | -211.5 | Yes | N/A | N/A | 2023-08-29 | 2023-08-01 | Unknown | Unknown | 2023-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-29 | -126 | -91 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-10 | 2022-11-13 | 2023-04-21 | IOU Designed & Installed | N/A | No | N/A | 2937.25 | 517.17 | Unknown | 165.51 | 20.14 | 2234.43 | 3981 | 565.59 | 2937.25 | -2371.66 | Yes | N/A | N/A | 2022-11-10 | 2023-02-14 | 97 | 69 | 2023-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-13 | 2023-04-21 | 68 | 50 | Unknown | 2023-04-12 | Unknown | Unknown | 2023-04-21 | 2023-04-25 | 1900-01-04 | 3 | 2023-04-25 | 2023-04-25 | 1 | 1 | 165 | 119 | 6 | 4 | 171 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-02 | -257 | -184 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-10-26 | 2024-12-17 | IOU Designed & Installed | N/A | No | N/A | 21563.63 | 3610.23 | Unknown | Unknown | 353.51 | 17599.89 | 59739.32 | 16213.68 | 21563.63 | -5349.95 | Yes | N/A | N/A | 2023-10-23 | 2023-08-02 | Unknown | Unknown | 2023-08-02 | 2024-10-18 | 444 | 318 | 2024-02-12 | 2024-10-16 | 1 | 1 | 2024-02-09 | 2024-10-23 | 31 | 21 | 2024-10-18 | Unknown | Unknown | Unknown | 2024-12-06 | 2024-12-06 | 1 | 1 | 2024-12-17 | 2025-03-20 | 1900-04-03 | 68 | 2025-03-20 | 2025-03-20 | 1 | 1 | 1 | 1 | 571 | 409 | 572 | 410 | Steps 2,3,5,6,7 | 504 | 360 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | 297.1 | 297.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | 372 | 266 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-28 | 2022-04-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 412.09 | -12.07 | Unknown | Unknown | -2708.59 | 3132.75 | Unknown | 2240.72 | 412.09 | 1828.63 | Yes | N/A | N/A | 2022-04-28 | 2024-02-26 | 670 | 478 | 2024-02-26 | 2024-04-24 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-05-07 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | Unknown | 2025-01-06 | Unknown | Unknown | 2025-01-06 | 2025-01-06 | 1 | 1 | 670 | 478 | 87 | 63 | 757 | 541 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-09 | -466 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-08 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 1170.45 | 376.26 | Unknown | 58.16 | Unknown | 736.03 | Unknown | 928.27 | 1170.45 | -242.18 | Yes | N/A | N/A | 2023-11-08 | 2023-11-08 | 1 | 1 | 2023-11-08 | 2023-11-08 | 1 | 1 | 2023-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2023-12-04 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2024-01-29 | 1900-02-25 | 41 | 2024-01-29 | 2024-01-29 | 1 | 1 | 28 | 20 | 59 | 43 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-13 | -640 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-14 | 2024-05-07 | IOU Designed & Installed | N/A | No | N/A | -5.34 | -5.48 | Unknown | Unknown | Unknown | 0.14 | 3961 | 163.83 | -5.34 | 169.17 | Yes | N/A | N/A | 2024-03-07 | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-04-15 | 43 | 31 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-05-07 | 23 | 17 | Unknown | 2024-05-07 | Unknown | Unknown | 2024-05-07 | 2024-05-14 | 1900-01-07 | 6 | 2024-05-14 | 2024-05-14 | 1 | 1 | 23 | 17 | 52 | 38 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 94.2 | 94.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-11 | -580 | -415 | No | 2024-03-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-04-26 | 2024-06-20 | IOU Designed & Installed | N/A | Yes | 95 | 467.66 | 288.35 | Unknown | Unknown | -2295 | 2474.31 | Unknown | 2294.96 | 467.66 | 1827.3 | Yes | N/A | N/A | 2024-03-28 | 2024-07-01 | 96 | 68 | 2024-07-01 | 2024-07-01 | 1 | 1 | 2024-07-01 | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-06-20 | 1 | 1 | Unknown | 2024-07-03 | Unknown | Unknown | 2024-06-20 | 2024-07-11 | 1900-01-21 | 16 | 2024-07-11 | 2024-07-11 | 1 | 1 | 97 | 69 | 24 | 18 | 121 | 87 | Steps 2,3,5,6,7 | 13 | 9 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-16 | -83 | -60 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-27 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 7185.53 | Unknown | Unknown | Unknown | -1809 | 8994.53 | Unknown | 1808.56 | 7185.53 | -5376.97 | Yes | N/A | N/A | 2024-02-08 | 2024-04-27 | 80 | 57 | 2024-04-27 | 2024-05-29 | 33 | 23 | 2024-09-12 | 2024-09-12 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | Unknown | Unknown | 2024-08-22 | 2024-09-24 | 1900-02-02 | 24 | 2024-09-24 | 2024-09-24 | 1 | 1 | 81 | 58 | 68 | 48 | 149 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | 179.1 | 179.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-11 | -189 | -136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 28.16 | -25.08 | Unknown | Unknown | 2.6 | 50.64 | 3981 | 1248.04 | 28.16 | 1219.88 | Yes | N/A | N/A | 2023-11-14 | 2023-12-04 | 21 | 15 | 2023-12-04 | 2023-12-06 | 3 | 3 | 2023-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | Unknown | Unknown | Unknown | 2024-04-05 | Unknown | Unknown | 2024-04-05 | 2024-04-05 | 1 | 1 | 21 | 15 | 4 | 4 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-12 | -500 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-04-28 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | -5.65 | -4.43 | Unknown | Unknown | Unknown | -1.22 | 3241 | 479.76 | -5.65 | 485.41 | Yes | N/A | N/A | 2023-04-28 | 2023-04-28 | 1 | 1 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | 2023-07-17 | 81 | 57 | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-07-31 | 1900-01-14 | 11 | 2023-07-31 | 2023-07-31 | 1 | 1 | 82 | 58 | 16 | 12 | 98 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-20 | -37 | -27 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-25 | 2024-02-05 | IOU Designed & Installed | N/A | No | N/A | 633.43 | -14.65 | Unknown | Unknown | 0.71 | 647.37 | 3981 | 949.49 | 633.43 | 316.06 | Yes | N/A | N/A | 2023-09-19 | 2023-04-26 | Unknown | Unknown | 2023-04-26 | 2023-09-25 | 153 | 109 | 2023-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | 2024-02-05 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-03-14 | 1900-02-07 | 29 | 2024-03-14 | 2024-03-14 | 1 | 1 | 134 | 96 | 193 | 139 | 327 | 235 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-20 | 549 | 394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 973.57 | -21.88 | Unknown | Unknown | -326.17 | 1321.62 | 0 | 288.31 | 973.57 | -685.26 | Yes | N/A | N/A | 2023-02-03 | 2023-03-02 | 28 | 20 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | 2024-04-30 | 110 | 78 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | Unknown | Unknown | Unknown | 2024-06-21 | Unknown | Unknown | 2024-06-21 | 2024-06-21 | 1 | 1 | 28 | 20 | 111 | 79 | 139 | 99 | Steps 2,3,5,6,7 | 399 | 285 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -688 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-02-22 | 2023-03-10 | IOU Designed & Installed | N/A | No | N/A | 283.91 | 175.8 | Unknown | Unknown | Unknown | 108.11 | Unknown | 95.13 | 283.91 | -188.78 | Yes | N/A | N/A | 2023-02-22 | 2023-02-27 | 6 | 4 | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-27 | 2023-03-10 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | 2023-03-14 | 1900-01-04 | 3 | 2023-03-14 | 2023-03-14 | 1 | 1 | 18 | 14 | 6 | 4 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 125.05 | 125.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-05 | -511 | -366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-04-03 | 2024-07-26 | IOU Designed & Installed | N/A | No | N/A | 3081.47 | 676.96 | Unknown | 186.08 | Unknown | 2218.43 | 3981 | 994.1 | 3081.47 | -2087.37 | Yes | N/A | N/A | 2024-03-26 | 2024-04-03 | 9 | 7 | 2024-04-03 | 2024-04-12 | 10 | 8 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-07-26 | 106 | 76 | Unknown | 2024-07-12 | Unknown | Unknown | 2024-07-26 | 2024-08-12 | 1900-01-17 | 12 | 2024-08-12 | 2024-08-12 | 1 | 1 | 115 | 83 | 29 | 21 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SM 1128-H1 N. CITY PA6 MSO (E) | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | 352 | 253 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 10502.55 | 4704.65 | Unknown | Unknown | Unknown | 5797.9 | 110654 | Not available | 10502.55 | Unknown | Yes | N/A | N/A | 2024-07-16 | 2024-07-19 | 4 | 4 | 2024-07-19 | 2025-02-07 | 204 | 146 | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | 2025-06-20 | 1 | 1 | 2025-02-07 | 2025-09-03 | 209 | 149 | Unknown | Unknown | Unknown | Unknown | 2025-07-04 | 2025-06-18 | Unknown | Unknown | 2025-06-18 | 2025-06-18 | 1 | 1 | 213 | 153 | 206 | 148 | 419 | 301 | Steps 2,3,5,6,7 | 133 | 95 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-02 | -645 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | 2025-03-13 | IOU Designed & Installed | N/A | No | N/A | 1641.86 | 239.1 | Unknown | 40.57 | Unknown | 1362.19 | Unknown | 1660.91 | 1641.86 | 19.05 | Yes | N/A | N/A | 2025-01-29 | 2025-02-11 | 14 | 10 | 2025-02-11 | 2025-02-28 | 18 | 14 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-03-13 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-03-28 | 1900-01-15 | 12 | 2025-03-28 | 2025-03-28 | 1 | 1 | 28 | 20 | 35 | 27 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-06-17 | 768 | 549 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-29 | 2023-07-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 384.85 | Unknown | Unknown | Unknown | -469 | 853.85 | 0 | 406.27 | 384.85 | 21.42 | Yes | N/A | N/A | 2022-09-29 | 2023-07-25 | 300 | 214 | 2023-07-25 | 2024-02-09 | 200 | 144 | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-04-16 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-07-24 | Unknown | Unknown | 300 | 214 | 201 | 145 | 501 | 359 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 5336 | 5336 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-06-18 | 80 | 59 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2024-01-23 | 2024-08-15 | IOU Designed & Installed | N/A | No | N/A | 14839.49 | 1764.27 | Unknown | Unknown | -4763.71 | 17838.93 | 7962 | 12392.37 | 14839.49 | -2447.12 | Yes | N/A | N/A | 2023-12-18 | 2023-12-04 | Unknown | Unknown | 2023-12-04 | 2024-04-18 | 137 | 99 | 2024-03-04 | 2024-03-05 | 2 | 2 | 2024-04-19 | 2024-05-01 | 13 | 9 | 2024-04-18 | 2025-03-19 | 336 | 240 | 2024-05-03 | 2024-08-05 | 95 | 67 | 2024-08-15 | 2024-09-09 | 1900-01-25 | 18 | 2024-09-09 | 2024-09-06 | Unknown | Unknown | 338 | 242 | 271 | 193 | 609 | 435 | Steps 2,3,5,6,7 | 378 | 270 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-07 | -285 | -204 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-01-30 | 2025-03-24 | IOU Designed & Installed | N/A | No | N/A | -1071.69 | -13.1 | Unknown | Unknown | -1771 | 712.41 | Unknown | 1657.92 | -1071.69 | 2729.61 | Yes | N/A | N/A | 2025-01-30 | 2025-01-16 | Unknown | Unknown | 2025-01-16 | 2025-01-30 | 15 | 11 | 2025-01-30 | 2025-03-24 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-03-24 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-03-31 | 1900-01-07 | 6 | 2025-03-31 | 2025-03-28 | Unknown | Unknown | 108 | 76 | 23 | 17 | 131 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-07 | -568 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-05 | 2023-03-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.95 | -4.32 | Unknown | Unknown | Unknown | -1.63 | Unknown | 771.39 | -5.95 | 777.34 | Yes | N/A | N/A | 2023-03-05 | 2023-03-05 | 1 | 0 | 2023-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | Unknown | Unknown | 2023-06-19 | 2023-06-19 | 1 | 1 | 1 | 0 | 1 | 1 | 2 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-09 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 22.43 | Unknown | Unknown | Unknown | Unknown | 22.43 | Unknown | 2500.06 | 22.43 | 2477.63 | Yes | N/A | N/A | 2024-08-09 | 2024-06-25 | Unknown | Unknown | 2024-06-25 | 2024-08-09 | 46 | 34 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-11-07 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-11-18 | 1900-01-11 | 8 | 2024-11-18 | 2024-11-18 | 1 | 1 | 91 | 65 | 59 | 43 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-18 | -500 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-11 | 2023-12-26 | IOU Designed & Installed | N/A | No | N/A | -13.96 | -10.54 | Unknown | Unknown | Unknown | -3.42 | Unknown | 514.57 | -13.96 | 528.53 | Yes | N/A | N/A | 2023-10-11 | 2023-10-11 | 1 | 1 | 2023-10-11 | 2023-10-11 | 1 | 1 | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2023-12-26 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | 2024-01-04 | 1900-01-09 | 8 | 2024-01-04 | 2024-01-04 | 1 | 1 | 78 | 56 | 12 | 10 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | Carlsbad | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-18 | 169 | 122 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-07 | 2022-06-07 | 2024-05-22 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 136226.22 | 38513.81 | Unknown | Unknown | 8564.35 | 89148.06 | 0 | 44871.99 | 136226.22 | -91354.23 | Yes | N/A | N/A | 2022-06-07 | 2023-06-09 | 368 | 264 | 2023-06-09 | 2023-09-06 | 90 | 64 | 2023-06-26 | 2023-12-14 | 38 | 28 | 2023-09-01 | 2024-01-29 | 12 | 8 | 2023-09-11 | Unknown | Unknown | Unknown | 2023-09-11 | 2024-05-20 | 253 | 181 | 2024-05-22 | 2024-06-04 | 1900-01-13 | 10 | 2024-06-04 | 2024-06-04 | 1 | 1 | 406 | 292 | 370 | 264 | 776 | 556 | Steps 2,3,5,6,7 | 316 | 226 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | -604 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-04 | 2024-12-31 | IOU Designed & Installed | N/A | No | N/A | 2635.36 | 494.56 | Unknown | Unknown | 0.68 | 2140.12 | 3981 | 1510.64 | 2635.36 | -1124.72 | Yes | N/A | N/A | 2024-12-04 | 2024-12-03 | Unknown | Unknown | 2024-12-03 | 2024-12-04 | 2 | 2 | 2024-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | 2024-12-31 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-03-25 | 1900-03-25 | 61 | 2025-03-25 | 2025-03-25 | 1 | 1 | 28 | 20 | 88 | 64 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | LAKESIDE | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | -31 | -24 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-16 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | 9585.13 | 1687.75 | Unknown | 534.26 | 141.31 | 7221.81 | 3981 | 481.77 | 9585.13 | -9103.36 | Yes | N/A | N/A | 2023-11-13 | 2023-11-16 | 4 | 4 | 2023-11-16 | 2024-01-09 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2023-11-17 | 2 | 2 | 2024-01-09 | 2024-10-31 | 297 | 213 | Unknown | 2024-12-20 | Unknown | Unknown | 2025-03-31 | 2025-04-04 | 1900-01-04 | 5 | 2025-04-04 | 2025-01-27 | Unknown | Unknown | 301 | 217 | 62 | 46 | 363 | 263 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-19 | -625 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-23 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | 36.02 | Unknown | Unknown | Unknown | Unknown | 36.02 | Unknown | 1931.43 | 36.02 | 1895.41 | Yes | N/A | N/A | 2025-01-15 | 2025-01-14 | Unknown | Unknown | 2025-01-14 | 2025-01-23 | 10 | 8 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-02-24 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-04-03 | 1900-02-07 | 29 | 2025-04-03 | 2025-04-03 | 1 | 1 | 33 | 23 | 50 | 38 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 55 | 55 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-20 | -538 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | 2025-02-14 | IOU Designed & Installed | N/A | No | N/A | 557.37 | Unknown | Unknown | Unknown | Unknown | 557.37 | 3981 | 1284.47 | 557.37 | 727.1 | Yes | N/A | N/A | 2025-01-07 | 2024-12-20 | Unknown | Unknown | 2024-12-20 | 2025-01-14 | 26 | 18 | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-02-14 | 32 | 24 | Unknown | 2025-02-03 | Unknown | Unknown | 2025-02-14 | 2025-02-26 | 1900-01-12 | 9 | 2025-02-26 | 2025-02-28 | 3 | 3 | 32 | 24 | 42 | 30 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | 1086 | 777 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 596.34 | -2.75 | Unknown | Unknown | -635 | 1234.09 | 0 | 562.63 | 596.34 | -33.71 | Yes | N/A | N/A | 2023-11-27 | 2023-11-27 | 1 | 1 | 2023-11-27 | 2023-12-29 | 33 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | 2024-05-23 | 147 | 105 | Unknown | 2025-01-13 | Unknown | Unknown | Unknown | 2025-01-23 | Unknown | Unknown | 2025-01-23 | 2025-01-22 | Unknown | Unknown | 148 | 106 | 33 | 25 | 181 | 131 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | 1615 | 1154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-08-13 | 2025-06-02 | IOU Designed & Installed | N/A | No | N/A | 455.02 | -9.14 | Unknown | Unknown | Unknown | 464.16 | Unknown | 3216.74 | 455.02 | 2761.72 | Yes | N/A | N/A | 2024-07-31 | 2024-08-13 | 14 | 10 | 2024-08-13 | 2024-10-08 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-09-13 | 32 | 24 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-06-03 | 1900-01-01 | 2 | 2025-06-03 | 2025-06-03 | 1 | 1 | 14 | 10 | 92 | 68 | 106 | 78 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-22 | 70 | 51 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-06-26 | 2024-07-28 | IOU Designed & Installed | N/A | No | N/A | 12866.5 | 2849.22 | Unknown | 1056.27 | Unknown | 8961.01 | 7962 | 1780.24 | 12866.5 | -11086.26 | Yes | N/A | N/A | 2023-06-01 | 2023-11-14 | 167 | 119 | 2023-11-14 | 2023-12-06 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2024-09-30 | 300 | 214 | Unknown | 2025-04-15 | Unknown | Unknown | 2024-07-28 | 2024-07-31 | 1900-01-03 | 3 | 2024-07-31 | 2024-07-31 | 1 | 1 | 467 | 333 | 28 | 21 | 495 | 354 | Steps 2,3,5,6,7 | 261 | 186 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 9.45 | 9.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-13 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-29 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 2497.25 | 680.85 | Unknown | Unknown | Unknown | 1816.4 | Unknown | 1845.21 | 2497.25 | -652.04 | Yes | N/A | N/A | 2025-01-28 | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-01-29 | 8 | 6 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-25 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-19 | 1900-01-22 | 17 | 2025-03-19 | 2025-03-19 | 1 | 1 | 28 | 20 | 32 | 24 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-12 | -563 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-15 | 2023-02-03 | 2023-02-23 | IOU Designed & Installed | N/A | No | N/A | 2184.59 | 686.12 | Unknown | 239.8 | Unknown | 1258.67 | 3981 | 686.29 | 2184.59 | -1498.3 | Yes | N/A | N/A | 2022-12-15 | 2023-02-03 | 51 | 37 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | 2023-02-23 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | 2023-02-27 | 1900-01-04 | 3 | 2023-02-27 | 2023-02-27 | 1 | 1 | 72 | 52 | 6 | 4 | 78 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 27.05 | 27.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | 2023-08-31 | IOU Designed & Installed | N/A | No | N/A | 110.99 | -13.38 | Unknown | Unknown | 56.15 | 68.22 | 3981 | 834.12 | 110.99 | 723.13 | Yes | N/A | N/A | 2023-03-31 | 2023-03-31 | 1 | 1 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | 2023-08-31 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | 2024-10-08 | 1901-02-08 | 289 | 2024-10-08 | 2023-09-08 | Unknown | Unknown | 155 | 111 | 405 | 289 | 560 | 400 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-14 | -477 | -342 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | 2023-10-12 | IOU Designed & Installed | N/A | No | N/A | 137.56 | -16.56 | Unknown | Unknown | Unknown | 154.12 | 3981 | 883.5 | 137.56 | 745.94 | Yes | N/A | N/A | 2023-09-18 | 2023-09-22 | 5 | 5 | 2023-09-22 | 2023-09-27 | 6 | 4 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-26 | 2023-10-12 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-10-27 | 1900-01-15 | 12 | 2023-10-27 | 2023-10-26 | Unknown | Unknown | 22 | 18 | 22 | 16 | 44 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | La Mesa | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-09 | 384 | 275 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-22 | 2023-05-24 | IOU Designed & Installed | N/A | No | N/A | 632.26 | Unknown | Unknown | Unknown | Unknown | 632.26 | Unknown | 967.65 | 632.26 | 335.39 | Yes | N/A | N/A | 2023-03-01 | 2023-04-07 | 38 | 28 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-12 | 2023-04-19 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-24 | 2023-06-28 | 1900-02-04 | 26 | 2023-06-28 | 2023-06-28 | 1 | 1 | 38 | 28 | 45 | 33 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-31 | 428 | 307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | 2024-06-05 | IOU Designed & Installed | N/A | No | N/A | 36.97 | -5.07 | Unknown | Unknown | Unknown | 42.04 | 3981 | 839.77 | 36.97 | 802.8 | Yes | N/A | N/A | 2023-10-27 | 2023-10-09 | Unknown | Unknown | 2023-10-09 | 2023-10-27 | 19 | 15 | 2023-10-27 | 2024-07-16 | 264 | 188 | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2024-06-05 | 223 | 159 | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-08-02 | 1900-02-27 | 43 | 2024-08-02 | 2024-08-01 | Unknown | Unknown | 487 | 347 | 78 | 58 | 565 | 405 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-08 | 636 | 455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-04-24 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 22434.33 | 651.49 | Unknown | 45.4 | 28.1 | 21709.34 | 0 | 10738.03 | 22434.33 | -11696.3 | Yes | N/A | N/A | 2023-02-03 | 2023-04-10 | 67 | 47 | 2023-04-10 | 2023-08-29 | 142 | 102 | 2023-04-18 | 2024-11-04 | 457 | 327 | 2023-05-11 | 2024-11-01 | 144 | 104 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-11-05 | 1900-01-21 | 16 | 2024-11-05 | 2024-11-05 | 1 | 1 | 524 | 374 | 309 | 223 | 833 | 597 | Steps 2,3,5,6,7 | 676 | 482 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | -416 | -299 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-09-19 | 2025-02-28 | IOU Designed & Installed | N/A | No | N/A | 41.47 | -0.31 | Unknown | Unknown | Unknown | 41.78 | 3981 | 1602.85 | 41.47 | 1561.38 | Yes | N/A | N/A | 2024-08-08 | 2024-09-18 | 42 | 30 | 2024-09-18 | 2024-09-19 | 2 | 2 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2025-02-28 | 163 | 117 | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-03-19 | 1900-01-19 | 14 | 2025-03-19 | 2025-03-18 | Unknown | Unknown | 205 | 147 | 22 | 16 | 227 | 163 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-17 | -14 | -11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-07 | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | 18.74 | Unknown | Unknown | Unknown | Unknown | 18.74 | 0 | 499.96 | 18.74 | 481.22 | Yes | N/A | N/A | 2023-04-07 | 2023-04-07 | 1 | 1 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2024-09-03 | 516 | 368 | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-10-03 | 1900-01-30 | 23 | 2024-10-03 | 2024-10-03 | 1 | 1 | 517 | 369 | 32 | 24 | 549 | 393 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-08 | 129 | 92 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 536.62 | 1220.95 | Unknown | 300.22 | -1512 | 527.45 | 0 | 1511.5 | 536.62 | 974.88 | Yes | N/A | N/A | 2023-04-18 | 2023-04-18 | 1 | 1 | 2023-04-18 | 2023-05-08 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 22 | 16 | 23 | 17 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 32 | 32 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-30 | -571 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-03-08 | IOU Designed & Installed | N/A | No | N/A | 720.58 | 243.32 | Unknown | Unknown | Unknown | 477.26 | 3885 | 726.03 | 720.58 | 5.45 | Yes | N/A | N/A | 2023-02-07 | 2023-02-07 | 1 | 1 | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-07 | 2023-03-08 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | 2023-03-09 | 1900-01-01 | 2 | 2023-03-09 | 2023-03-09 | 1 | 1 | 31 | 23 | 3 | 3 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 13.1 | 13.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | 46 | 33 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 18452.53 | 273.47 | Unknown | Unknown | -1185 | 19364.06 | 3981 | 1729.2 | 18452.53 | -16723.33 | Yes | N/A | N/A | 2024-04-16 | 2024-04-16 | 1 | 1 | 2024-04-16 | 2024-04-16 | 1 | 1 | 2024-04-16 | 2024-07-30 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2025-03-06 | 220 | 158 | Unknown | 2025-02-21 | Unknown | Unknown | 2025-03-06 | 2025-03-24 | 1900-01-18 | 13 | 2025-03-24 | 2025-04-08 | 16 | 12 | 327 | 235 | 36 | 26 | 363 | 261 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 1346.05 | 1346.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-03-10 | -497 | -356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-28 | 2023-10-03 | IOU Designed & Installed | N/A | No | N/A | 696.68 | 244.9 | Unknown | Unknown | Unknown | 451.78 | 3981 | 898.86 | 696.68 | 202.18 | Yes | N/A | N/A | 2023-09-25 | 2023-09-28 | 4 | 4 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-10-03 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-10-30 | 1900-01-27 | 20 | 2023-10-30 | 2023-10-30 | 1 | 1 | 10 | 8 | 29 | 21 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 123 | 123 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-09 | 10 | 7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | 2023-11-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 571.42 | -11 | Unknown | Unknown | Unknown | 582.42 | 3981 | 739 | 571.42 | 167.58 | Yes | N/A | N/A | 2023-11-03 | 2023-08-24 | Unknown | Unknown | 2023-08-24 | 2023-11-13 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2024-10-24 | 347 | 249 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2024-11-19 | Unknown | Unknown | 347 | 249 | 82 | 58 | 429 | 307 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-20 | 138 | 99 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-03-11 | 2024-05-29 | IOU Designed & Installed | N/A | No | N/A | 3512.38 | 1110.23 | Unknown | Unknown | Unknown | 2402.15 | 3981 | 2029.37 | 3512.38 | -1483.01 | Yes | N/A | N/A | 2023-01-24 | 2023-03-10 | 46 | 34 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-11 | 2024-05-29 | 446 | 318 | Unknown | 2024-04-10 | Unknown | Unknown | 2024-05-29 | 2024-06-06 | 1900-01-08 | 7 | 2024-06-06 | 2024-06-06 | 1 | 1 | 492 | 352 | 10 | 8 | 502 | 360 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | -65 | -48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-14 | 2024-11-19 | IOU Designed & Installed | N/A | No | N/A | 1007.98 | Unknown | Unknown | Unknown | 26.29 | 981.69 | 3981 | 1134.23 | 1007.98 | 126.25 | Yes | N/A | N/A | 2024-03-14 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-03-25 | 42 | 30 | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-11-19 | 240 | 172 | Unknown | 2024-11-13 | Unknown | Unknown | 2024-11-19 | 2024-11-27 | 1900-01-08 | 7 | 2024-11-27 | 2024-11-27 | 1 | 1 | 240 | 172 | 52 | 38 | 292 | 210 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | -621 | -444 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2024-10-31 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 26.81 | Unknown | Unknown | Unknown | Unknown | 26.81 | 3981 | 1446.93 | 26.81 | 1420.12 | Yes | N/A | N/A | 2024-10-31 | 2024-10-31 | 1 | 1 | 2024-10-31 | 2024-10-31 | 1 | 1 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-15 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2025-02-07 | 1900-03-25 | 61 | 2025-02-07 | 2025-02-07 | 1 | 1 | 17 | 13 | 87 | 63 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | 409 | 294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-09-08 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | 32012.84 | 11555.04 | Unknown | Unknown | -19074 | 39531.8 | 0 | 18022.37 | 32012.84 | -13990.47 | Yes | N/A | N/A | 2023-08-31 | 2023-07-10 | Unknown | Unknown | 2023-07-10 | 2023-10-31 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2024-11-22 | 389 | 279 | Unknown | 2025-01-13 | Unknown | Unknown | 2025-01-29 | 2025-02-24 | 1900-01-26 | 19 | 2025-02-24 | 2025-02-13 | Unknown | Unknown | 389 | 279 | 141 | 101 | 530 | 380 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-08 | -208 | -149 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | 2024-02-01 | IOU Designed & Installed | N/A | No | N/A | -4.63 | -3.76 | Unknown | Unknown | Unknown | -0.87 | Unknown | 153.49 | -4.63 | 158.12 | Yes | N/A | N/A | 2023-12-04 | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2023-12-04 | 50 | 36 | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2024-02-01 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-02-13 | 1900-01-12 | 9 | 2024-02-13 | 2024-02-13 | 1 | 1 | 60 | 44 | 64 | 46 | 124 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-29 | 45 | 32 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2024-06-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1119.81 | -22.5 | Unknown | Unknown | 0.14 | 1142.17 | 11943 | 1062.31 | 1119.81 | -57.5 | Yes | N/A | N/A | 2024-05-22 | 2024-07-17 | 57 | 41 | 2024-07-17 | 2024-09-16 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-08-16 | 31 | 23 | 2024-09-16 | 2025-04-16 | 213 | 153 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | Unknown | Unknown | 2025-05-14 | 2025-05-13 | Unknown | Unknown | 270 | 194 | 93 | 67 | 363 | 261 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 80.05 | 80.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-14 | 71 | 52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-07 | 2024-02-15 | IOU Designed & Installed | N/A | No | N/A | 377.91 | -21.71 | Unknown | Unknown | 11.45 | 388.17 | 3981 | 852.19 | 377.91 | 474.28 | Yes | N/A | N/A | 2023-11-07 | 2023-10-12 | Unknown | Unknown | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2024-02-15 | 81 | 59 | Unknown | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-03-14 | 1900-01-28 | 21 | 2024-03-14 | 2024-02-23 | Unknown | Unknown | 81 | 59 | 29 | 21 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-10 | -686 | -491 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | -6.3 | -26.37 | Unknown | Unknown | Unknown | 20.07 | 3981 | 1532.32 | -6.3 | 1538.62 | Yes | N/A | N/A | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-02-19 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-03-26 | 1900-02-04 | 26 | 2025-03-26 | 2025-03-26 | 1 | 1 | 3 | 3 | 38 | 28 | 41 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OLIVENHAIN | N/A | 157.05 | 157.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-24 | -543 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-06-16 | 2023-08-16 | IOU Designed & Installed | N/A | No | N/A | 6028.51 | 52.14 | Unknown | Unknown | Unknown | 5976.37 | 3981 | 1318.22 | 6028.51 | -4710.29 | Yes | N/A | N/A | 2023-05-16 | 2023-03-17 | Unknown | Unknown | 2023-03-17 | 2023-07-14 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | Unknown | Unknown | 2023-08-16 | 2023-08-31 | 1900-01-15 | 12 | 2023-08-31 | 2023-08-31 | 1 | 1 | 0 | 0 | 137 | 99 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-26 | -590 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-02-01 | 2024-02-07 | IOU Designed & Installed | N/A | No | N/A | -10.64 | -8.64 | Unknown | Unknown | Unknown | -2 | 3981 | 1155.49 | -10.64 | 1166.13 | Yes | N/A | N/A | 2024-01-12 | 2023-11-03 | Unknown | Unknown | 2023-11-03 | 2024-02-01 | 91 | 65 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-02-07 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-03-15 | 1900-02-06 | 28 | 2024-03-15 | 2024-03-15 | 1 | 1 | 7 | 5 | 130 | 94 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-03 | -608 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | Unknown | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 1474.39 | -28.85 | Unknown | Unknown | Unknown | 1503.24 | 3981 | 1669.8 | 1474.39 | 195.41 | Yes | N/A | N/A | 2024-06-07 | 2024-06-07 | 1 | 1 | 2024-06-07 | 2024-06-07 | 1 | 1 | 2024-06-07 | Unknown | Unknown | Unknown | 2024-06-07 | 2024-07-12 | 36 | 26 | 2024-06-07 | 2024-08-22 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-10-03 | 1900-02-11 | 31 | 2024-10-03 | 2024-10-03 | 1 | 1 | 78 | 56 | 81 | 59 | 159 | 115 | Steps 2,3,5,6,7 | 35 | 25 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-29 | 99 | 71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | 2024-01-19 | IOU Designed & Installed | N/A | No | N/A | 11.29 | -14.21 | Unknown | Unknown | Unknown | 25.5 | 3941 | 791.07 | 11.29 | 779.78 | Yes | N/A | N/A | 2023-11-10 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2023-11-10 | 45 | 33 | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2024-01-19 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-02-05 | 1900-01-17 | 12 | 2024-02-05 | 2024-02-05 | 1 | 1 | 71 | 51 | 64 | 46 | 135 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-04 | -622 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-21 | 2025-02-21 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | 378.93 | -7.62 | Unknown | Unknown | Unknown | 386.55 | 3981 | 1633.57 | 378.93 | 1254.64 | Yes | N/A | N/A | 2025-02-21 | 2025-02-21 | 1 | 1 | 2025-02-21 | 2025-02-21 | 1 | 1 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-05-20 | 89 | 63 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-05-23 | 1900-01-03 | 4 | 2025-05-23 | 2025-05-23 | 1 | 1 | 90 | 64 | 6 | 6 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 175.1 | 175.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-16 | 91 | 66 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2024-04-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 386.62 | Unknown | Unknown | Unknown | Unknown | 386.62 | 3981 | 1303.94 | 386.62 | 917.32 | Yes | N/A | N/A | 2023-09-19 | 2024-03-20 | 184 | 132 | 2024-03-20 | 2024-04-04 | 16 | 12 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | Unknown | Unknown | 2024-11-15 | 2024-11-15 | 1 | 1 | 184 | 132 | 17 | 13 | 201 | 145 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-28 | -519 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-03 | 2023-07-20 | IOU Designed & Installed | N/A | No | N/A | 325.78 | -16.29 | Unknown | Unknown | -657.71 | 999.78 | Unknown | 661.33 | 325.78 | 335.55 | Yes | N/A | N/A | 2023-03-03 | 2023-05-16 | 75 | 53 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | 2023-07-20 | 49 | 35 | Unknown | 2023-07-12 | Unknown | Unknown | 2023-07-20 | 2023-07-28 | 1900-01-08 | 7 | 2023-07-28 | 2023-07-28 | 1 | 1 | 124 | 88 | 10 | 8 | 134 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | -681 | -488 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-08-13 | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 72.87 | Unknown | Unknown | Unknown | Unknown | 72.87 | 3981 | 1510.5 | 72.87 | 1437.63 | Yes | N/A | N/A | 2024-07-29 | 2024-07-11 | Unknown | Unknown | 2024-07-11 | 2024-08-13 | 34 | 24 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-08-14 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-08-27 | 1900-01-13 | 10 | 2024-08-27 | 2024-08-27 | 1 | 1 | 2 | 2 | 49 | 35 | 51 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 54.4 | 54.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-12 | -603 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 999.91 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2024-12-18 | Unknown | Unknown | 2024-12-18 | 2025-01-10 | 24 | 18 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-03-05 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-19 | 1900-01-14 | 11 | 2025-03-19 | 2025-03-19 | 1 | 1 | 55 | 39 | 40 | 30 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 134 | 134 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-08 | 230 | 165 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-12 | 2023-11-17 | IOU Designed & Installed | N/A | No | N/A | 75.66 | -1.26 | Unknown | Unknown | 1.08 | 75.84 | 3981 | 822.71 | 75.66 | 747.05 | Yes | N/A | N/A | 2023-10-09 | 2023-10-12 | 4 | 4 | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | 2024-04-01 | 173 | 123 | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-11-17 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2024-10-30 | 1900-12-14 | 249 | 2024-10-30 | 2024-10-24 | Unknown | Unknown | 214 | 154 | 350 | 250 | 564 | 404 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | -647 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 106.21 | -1.5 | Unknown | Unknown | Unknown | 107.71 | Unknown | 1548.82 | 106.21 | 1442.61 | Yes | N/A | N/A | 2024-09-03 | 2024-09-03 | 1 | 1 | 2024-09-03 | 2024-09-04 | 2 | 2 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-10-18 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-10-29 | 1900-01-11 | 8 | 2024-10-29 | 2024-10-29 | 1 | 1 | 46 | 34 | 15 | 11 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | 9066 | 9066 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-15 | -43 | -32 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2023-12-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 50.78 | -39.15 | Unknown | Unknown | Unknown | 89.93 | 11943 | 930.55 | 50.78 | 879.77 | Yes | N/A | N/A | 2023-12-15 | 2023-12-15 | 1 | 1 | 2023-12-15 | 2023-12-26 | 12 | 8 | 2023-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2024-07-03 | Unknown | Unknown | 1 | 1 | 12 | 8 | 13 | 9 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-22 | -366 | -263 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-04 | 2022-10-04 | 2023-04-26 | IOU Designed & Installed | N/A | No | N/A | -4.1 | -3.79 | Unknown | Unknown | Unknown | -0.31 | 3885 | 193.42 | -4.1 | 197.52 | Yes | N/A | N/A | 2022-10-04 | 2023-04-26 | 205 | 147 | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-26 | 2023-04-26 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-04-26 | 2023-08-22 | 1900-04-28 | 85 | 2023-08-22 | 2023-08-22 | 1 | 1 | 206 | 148 | 120 | 86 | 326 | 234 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-16 | -285 | -204 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-03-28 | IOU Designed & Installed | N/A | No | N/A | 1596.92 | 526.64 | Unknown | 186.52 | Unknown | 883.76 | Unknown | 389.6 | 1596.92 | -1207.32 | Yes | N/A | N/A | 2023-02-09 | 2023-03-22 | 42 | 30 | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | 2023-03-28 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | 2023-04-06 | 1900-01-09 | 8 | 2023-04-06 | 2023-04-06 | 1 | 1 | 49 | 35 | 11 | 9 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | -654 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-07 | 2025-03-07 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1586.4 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-07 | 2025-03-06 | Unknown | Unknown | 2025-03-06 | 2025-03-07 | 2 | 2 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-04-24 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-04-28 | 1900-01-04 | 3 | 2025-04-28 | 2025-04-28 | 1 | 1 | 49 | 35 | 8 | 6 | 57 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 9.45 | 9.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | -611 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | 2025-04-29 | IOU Designed & Installed | N/A | No | N/A | 4555.61 | 330.92 | Unknown | 1270.09 | 13.85 | 2940.75 | 3981 | 1245.46 | 4555.61 | -3310.15 | Yes | N/A | N/A | 2025-03-13 | 2025-03-31 | 19 | 13 | 2025-03-31 | 2025-03-27 | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-29 | 34 | 24 | Unknown | 2025-04-24 | Unknown | Unknown | 2025-04-29 | 2025-05-21 | 1900-01-22 | 17 | 2025-05-21 | 2025-05-21 | 1 | 1 | 53 | 37 | 24 | 18 | 77 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-05 | -548 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.18 | -5.31 | Unknown | Unknown | Unknown | -0.87 | Unknown | 154.79 | -6.18 | 160.97 | Yes | N/A | N/A | 2023-02-15 | 2023-04-10 | 55 | 39 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | Unknown | Unknown | 2023-06-06 | 2023-06-06 | 1 | 1 | 55 | 39 | 1 | 1 | 56 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-27 | -532 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 693.24 | -11.95 | Unknown | Unknown | 17.49 | 687.7 | 3885 | 657.09 | 693.24 | -36.15 | Yes | N/A | N/A | 2023-03-02 | 2023-04-11 | 41 | 29 | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | Unknown | Unknown | Unknown | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2023-07-14 | 1 | 1 | 41 | 29 | 1 | 1 | 42 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | San Diego | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2027-12-31 | -1205 | -862 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-29 | 2023-06-23 | 2024-05-24 | IOU Designed & Installed | N/A | No | N/A | 14538.76 | 799.13 | Unknown | Unknown | 20.51 | 13719.12 | 108710.34 | 21076.32 | 14538.76 | 6537.56 | Yes | N/A | N/A | 2022-09-29 | 2023-10-09 | 376 | 268 | 2023-10-09 | 2023-10-30 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2024-05-09 | 212 | 152 | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-05-22 | 56 | 40 | 2024-05-24 | 2024-09-12 | 1900-04-21 | 80 | 2024-09-12 | 2024-09-12 | 1 | 1 | 376 | 268 | 403 | 289 | 779 | 557 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-12 | -656 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-03-02 | 2024-03-19 | IOU Designed & Installed | N/A | No | N/A | -5.25 | -4.26 | Unknown | Unknown | Unknown | -0.99 | 3981 | 920.65 | -5.25 | 925.9 | Yes | N/A | N/A | 2024-02-21 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-03-02 | 38 | 27 | 2024-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-02 | 2024-03-19 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-03-27 | 1900-01-08 | 7 | 2024-03-27 | 2024-03-27 | 1 | 1 | 18 | 12 | 48 | 35 | 66 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-27 | -300 | -215 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-01-16 | 2024-09-27 | IOU Designed & Installed | N/A | No | N/A | 1790.5 | 532.86 | Unknown | Unknown | Unknown | 1257.64 | Unknown | 1053.79 | 1790.5 | -736.71 | Yes | N/A | N/A | 2024-01-16 | 2024-01-29 | 14 | 10 | 2024-01-29 | 2024-02-06 | 9 | 7 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-09-27 | 243 | 175 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-09-30 | 1900-01-03 | 2 | 2024-09-30 | 2024-09-30 | 1 | 1 | 257 | 185 | 14 | 10 | 271 | 195 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-16 | -590 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | 2024-12-27 | IOU Designed & Installed | N/A | No | N/A | 1730.22 | -6.84 | Unknown | Unknown | 18.67 | 1718.39 | 3981 | 1336.34 | 1730.22 | -393.88 | Yes | N/A | N/A | 2024-09-03 | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-09-11 | 22 | 16 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2024-12-27 | 108 | 78 | Unknown | 2024-11-26 | Unknown | Unknown | 2024-12-27 | 2025-01-03 | 1900-01-07 | 6 | 2025-01-03 | 2025-01-03 | 1 | 1 | 108 | 78 | 31 | 23 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-28 | -391 | -280 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-07-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1812.04 | -12.86 | Unknown | Unknown | Unknown | 1824.9 | 3981 | 1142.92 | 1812.04 | -669.12 | Yes | N/A | N/A | 2024-06-10 | 2024-07-26 | 47 | 35 | 2024-07-26 | 2024-07-26 | 1 | 1 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-02 | 2025-04-02 | 1 | 1 | 47 | 35 | 2 | 2 | 49 | 37 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | 270 | 193 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | 2609.23 | Unknown | Unknown | Unknown | 53.19 | 2556.04 | Unknown | 721.3 | 2609.23 | -1887.93 | Yes | N/A | N/A | 2023-10-09 | 2024-10-17 | 375 | 269 | 2024-10-17 | 2025-02-04 | 111 | 79 | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-09-19 | 36 | 26 | 2025-02-04 | 2025-05-22 | 108 | 78 | Unknown | 2025-03-27 | Unknown | Unknown | 2025-06-11 | 2025-06-25 | 1900-01-14 | 11 | 2025-06-25 | 2025-06-25 | 1 | 1 | 483 | 347 | 163 | 117 | 646 | 464 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-01 | 133 | 96 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-16 | 2023-06-16 | 2024-04-09 | IOU Designed & Installed | N/A | No | N/A | 230404.05 | -601.85 | Unknown | Unknown | 884.71 | 230121.19 | 0 | 65595.94 | 230404.05 | -164808.11 | Yes | N/A | N/A | 2023-06-16 | 2023-08-31 | 77 | 55 | 2023-08-31 | 2024-02-08 | 162 | 116 | 2023-10-24 | 2024-01-11 | 16 | 12 | 2024-01-12 | 2024-02-05 | 25 | 17 | 2024-02-08 | 2024-07-17 | 161 | 115 | 2024-05-28 | 2024-08-01 | 66 | 48 | 2024-04-09 | 2024-09-11 | 1900-06-04 | 112 | 2024-09-11 | 2024-09-11 | 1 | 1 | 254 | 182 | 410 | 294 | 664 | 476 | Steps 2,3,5,6,7 | 271 | 195 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-15 | 2024-11-15 | 2024-11-20 | IOU Designed & Installed | N/A | No | N/A | 59.21 | Unknown | Unknown | Unknown | Unknown | 59.21 | Unknown | 1572.94 | 59.21 | 1513.73 | Yes | N/A | N/A | 2024-11-15 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-15 | 3 | 3 | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-11-20 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2025-01-09 | 1900-02-19 | 37 | 2025-01-09 | 2025-01-09 | 1 | 1 | 6 | 4 | 55 | 41 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-05 | 11 | 8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | 2025-04-16 | IOU Designed & Installed | N/A | No | N/A | 11628.68 | 2552.39 | Unknown | Unknown | 32.06 | 9044.23 | 3981 | 3329.68 | 11628.68 | -8299 | Yes | N/A | N/A | 2024-05-21 | 2024-10-01 | 134 | 96 | 2024-10-01 | 2024-10-04 | 4 | 4 | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2025-04-16 | 195 | 139 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-04-16 | 1899-12-31 | 1 | 2025-04-16 | 2025-04-16 | 1 | 1 | 329 | 235 | 6 | 6 | 335 | 241 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-09 | 128 | 92 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-08 | 2024-10-02 | IOU Designed & Installed | N/A | No | N/A | 3493.16 | 794.18 | Unknown | 68.02 | 20.78 | 2610.18 | 3981 | 900.12 | 3493.16 | -2593.04 | Yes | N/A | N/A | 2023-11-08 | 2024-02-29 | 114 | 82 | 2024-02-29 | 2024-02-29 | 1 | 1 | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2024-10-02 | 217 | 155 | Unknown | 2024-09-30 | Unknown | Unknown | 2024-10-02 | 2024-10-15 | 1900-01-13 | 10 | 2024-10-15 | 2024-10-15 | 1 | 1 | 331 | 237 | 16 | 12 | 347 | 249 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | -697 | -500 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-03 | 2024-01-08 | IOU Designed & Installed | N/A | No | N/A | 10.76 | -17.73 | Unknown | Unknown | Unknown | 28.49 | 3981 | 724.04 | 10.76 | 713.28 | Yes | N/A | N/A | 2023-04-03 | 2023-04-03 | 1 | 1 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | 2024-01-08 | 281 | 201 | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-01-08 | 1899-12-31 | 1 | 2024-01-08 | 2024-01-08 | 1 | 1 | 282 | 202 | 2 | 2 | 284 | 204 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-03 | -425 | -305 | No | 2023-09-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2023-12-06 | IOU Designed & Installed | N/A | Yes | 121 | 2183.92 | 707.39 | Unknown | 116.98 | Unknown | 1359.55 | Unknown | 788.19 | 2183.92 | -1395.73 | Yes | N/A | N/A | 2023-09-27 | 2024-01-26 | 122 | 88 | 2024-01-26 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-12-06 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2024-03-04 | 1900-03-30 | 64 | 2024-03-04 | 2024-03-04 | 1 | 1 | 193 | 139 | 91 | 65 | 284 | 204 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 548.05 | 548.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | 73 | 54 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-10-09 | 2025-01-03 | IOU Designed & Installed | N/A | No | N/A | 8820.35 | Unknown | Unknown | Unknown | 4.27 | 8816.08 | 3981 | 853.74 | 8820.35 | -7966.61 | Yes | N/A | N/A | 2024-09-18 | 2024-08-23 | Unknown | Unknown | 2024-08-23 | 2024-11-15 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-27 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-03-17 | 1900-03-14 | 52 | 2025-03-17 | 2025-03-14 | Unknown | Unknown | 43 | 31 | 159 | 113 | 202 | 144 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 89.4 | 89.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-05 | -573 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-03-03 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 39.59 | Unknown | Unknown | Unknown | Unknown | 39.59 | Unknown | 1989.05 | 39.59 | 1949.46 | Yes | N/A | N/A | 2025-01-30 | 2025-02-04 | 6 | 4 | 2025-02-04 | 2025-03-03 | 28 | 20 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-05 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-04-11 | 1900-02-06 | 28 | 2025-04-11 | 2025-04-11 | 1 | 1 | 9 | 7 | 67 | 49 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-16 | -186 | -135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.08 | -9.03 | Unknown | Unknown | Unknown | 5.95 | 3981 | 1040.6 | -3.08 | 1043.68 | Yes | N/A | N/A | 2023-03-31 | 2023-04-07 | 8 | 6 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1 | 1 | 8 | 6 | 1 | 1 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | -574 | -411 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | 2025-03-04 | IOU Designed & Installed | N/A | No | N/A | 75.17 | Unknown | Unknown | Unknown | Unknown | 75.17 | Unknown | 1583.04 | 75.17 | 1507.87 | Yes | N/A | N/A | 2024-11-18 | 2024-10-14 | Unknown | Unknown | 2024-10-14 | 2024-11-18 | 36 | 26 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2025-03-04 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-03-06 | 1900-01-02 | 3 | 2025-03-06 | 2025-03-06 | 1 | 1 | 107 | 77 | 40 | 30 | 147 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-17 | -487 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-11-07 | 2023-12-27 | IOU Designed & Installed | N/A | No | N/A | 496.2 | -16.46 | Unknown | Unknown | Unknown | 512.66 | Unknown | 1190.33 | 496.2 | 694.13 | Yes | N/A | N/A | 2023-08-30 | 2023-05-24 | Unknown | Unknown | 2023-05-24 | 2023-11-07 | 168 | 120 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2023-12-27 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2024-01-16 | 1900-01-20 | 15 | 2024-01-16 | 2024-01-16 | 1 | 1 | 51 | 37 | 190 | 136 | 241 | 173 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | -605 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-27 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 11.18 | Unknown | Unknown | Unknown | Unknown | 11.18 | 3241 | 1087 | 11.18 | 1075.82 | Yes | N/A | N/A | 2024-08-14 | 2024-08-27 | 14 | 10 | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-23 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-10-02 | 1900-01-09 | 8 | 2024-10-02 | 2024-10-02 | 1 | 1 | 42 | 30 | 12 | 10 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 6.4 | 6.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-03 | -603 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-11-06 | 2024-12-06 | IOU Designed & Installed | N/A | No | N/A | 20.38 | Unknown | Unknown | Unknown | Unknown | 20.38 | 3981 | 1588.36 | 20.38 | 1567.98 | Yes | N/A | N/A | 2024-11-06 | 2024-11-13 | 8 | 6 | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-12-06 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-01-09 | 1900-02-03 | 25 | 2025-01-09 | 2025-01-08 | Unknown | Unknown | 32 | 24 | 36 | 26 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-14 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-20 | 2023-12-20 | IOU Designed & Installed | N/A | No | N/A | -11.28 | -8.9 | Unknown | Unknown | Unknown | -2.38 | Unknown | 41.38 | -11.28 | 52.66 | Yes | N/A | N/A | 2023-11-20 | 2023-08-23 | Unknown | Unknown | 2023-08-23 | 2023-11-22 | 92 | 66 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2023-12-20 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-01-23 | 1900-02-03 | 25 | 2024-01-23 | 2024-01-23 | 1 | 1 | 29 | 21 | 128 | 92 | 157 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | -704 | -504 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | 2024-12-05 | IOU Designed & Installed | N/A | No | N/A | 109.78 | -1.5 | Unknown | Unknown | Unknown | 111.28 | 3981 | 1496.59 | 109.78 | 1386.81 | Yes | N/A | N/A | 2024-11-25 | 2024-11-25 | 1 | 1 | 2024-11-25 | 2024-11-25 | 1 | 1 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-05 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | 2024-12-17 | 1900-01-12 | 9 | 2024-12-17 | 2024-12-17 | 1 | 1 | 12 | 10 | 15 | 11 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-04 | -466 | -333 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-08-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 38.64 | Unknown | Unknown | Unknown | Unknown | 38.64 | 7962 | 1534.47 | 38.64 | 1495.83 | Yes | N/A | N/A | 2024-02-29 | 2024-05-02 | 64 | 46 | 2024-05-02 | 2024-09-04 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-25 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-09-25 | Unknown | Unknown | 86 | 62 | 126 | 90 | 212 | 152 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 14.05 | 14.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-19 | -238 | -171 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-29 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | 2018.22 | Unknown | Unknown | Unknown | 140.49 | 1877.73 | 3981 | 1080.8 | 2018.22 | -937.42 | Yes | N/A | N/A | 2024-02-16 | 2024-05-07 | 82 | 58 | 2024-05-07 | 2024-05-15 | 9 | 7 | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | 2025-04-22 | 343 | 245 | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-22 | 2025-04-25 | 1900-01-03 | 4 | 2025-04-25 | 2025-04-25 | 1 | 1 | 425 | 303 | 14 | 12 | 439 | 315 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 56.05 | 56.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-21 | 217 | 156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | -36.16 | -23.43 | Unknown | Unknown | Unknown | -12.73 | Unknown | 1049.43 | -36.16 | 1085.59 | Yes | N/A | N/A | 2024-07-24 | 2024-07-24 | 1 | 1 | 2024-07-24 | 2024-07-24 | 1 | 1 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | 2025-03-28 | 2025-03-26 | Unknown | Unknown | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-03 | -620 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-10-07 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 7.1 | Unknown | Unknown | Unknown | Unknown | 7.1 | Unknown | 1665.03 | 7.1 | 1657.93 | Yes | N/A | N/A | 2024-09-11 | 2024-09-17 | 7 | 5 | 2024-09-17 | 2024-10-23 | 37 | 27 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-11-14 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-12-06 | 1900-01-22 | 17 | 2024-12-06 | 2024-11-21 | Unknown | Unknown | 30 | 22 | 60 | 44 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-13 | -202 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | 2023-05-26 | 2023-06-13 | IOU Designed & Installed | N/A | No | N/A | 8206.14 | Unknown | Unknown | Unknown | 73.64 | 8132.5 | 3981 | 775.01 | 8206.14 | -7431.13 | Yes | N/A | N/A | 2023-05-26 | 2023-05-30 | 5 | 3 | 2023-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | 2023-06-13 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | 2023-08-24 | 1900-03-13 | 53 | 2023-08-24 | 2023-08-24 | 1 | 1 | 24 | 16 | 74 | 54 | 98 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 18.1 | 18.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-13 | -121 | -86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2023-08-01 | 2024-08-29 | IOU Designed & Installed | N/A | No | N/A | 24763.59 | Unknown | Unknown | Unknown | 53.85 | 24709.74 | 3981 | 1686.6 | 24763.59 | -23076.99 | Yes | N/A | N/A | 2023-08-01 | 2023-08-16 | 16 | 12 | 2023-08-16 | 2024-06-26 | 316 | 226 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-12-13 | 1900-04-16 | 77 | 2024-12-13 | 2024-12-13 | 1 | 1 | 16 | 12 | 424 | 304 | 440 | 316 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 60.05 | 60.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-16 | -394 | -283 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | 2024-03-26 | IOU Designed & Installed | N/A | No | N/A | 510.76 | 187.85 | Unknown | Unknown | Unknown | 322.91 | 3981 | 1028.55 | 510.76 | 517.79 | Yes | N/A | N/A | 2024-02-06 | 2023-11-07 | Unknown | Unknown | 2023-11-07 | 2024-02-06 | 92 | 66 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-03-26 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-04-17 | 1900-01-22 | 17 | 2024-04-17 | 2024-04-17 | 1 | 1 | 50 | 36 | 116 | 84 | 166 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-14 | 31 | 22 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -992.19 | 458.04 | Unknown | 25.2 | -1774 | 298.57 | Unknown | 1773.84 | -992.19 | 2766.03 | Yes | N/A | N/A | 2023-10-04 | 2023-10-16 | 13 | 9 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 13 | 9 | 1 | 1 | 14 | 10 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 62 | 62 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-04 | -262 | -187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1092.91 | Unknown | Unknown | Unknown | 12.82 | 1080.09 | 3891 | 776.76 | 1092.91 | -316.15 | Yes | N/A | N/A | 2023-06-15 | 2023-06-15 | 1 | 1 | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | Unknown | 2024-08-15 | Unknown | Unknown | 2024-08-15 | 2024-08-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-25 | -135 | -98 | No | 2024-01-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-17 | 2024-07-19 | IOU Designed & Installed | N/A | Yes | 168 | 1560.41 | Unknown | Unknown | Unknown | 33.16 | 1527.25 | 3981 | 1278.9 | 1560.41 | -281.51 | Yes | N/A | N/A | 2024-01-17 | 2024-07-03 | 169 | 121 | 2024-07-03 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-07-19 | 177 | 127 | Unknown | 2024-07-09 | Unknown | Unknown | 2024-07-19 | 2024-08-06 | 1900-01-18 | 13 | 2024-08-06 | 2024-08-12 | 7 | 5 | 346 | 248 | 26 | 18 | 372 | 266 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | -89 | -65 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | 2023-11-07 | IOU Designed & Installed | N/A | No | N/A | 68.63 | -17.47 | Unknown | Unknown | 6.68 | 79.42 | 3981 | 722.55 | 68.63 | 653.92 | Yes | N/A | N/A | 2023-05-23 | 2023-05-23 | 1 | 1 | 2023-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2024-03-14 | 1900-05-08 | 93 | 2024-03-14 | 2023-12-18 | Unknown | Unknown | 1 | 1 | 129 | 93 | 130 | 94 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 173.05 | 173.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-06 | 171 | 124 | No | 2023-11-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2023-11-02 | 2024-04-11 | IOU Designed & Installed | N/A | Yes | 48 | 800.95 | -11.26 | Unknown | Unknown | 15.42 | 796.79 | 3981 | 743.13 | 800.95 | -57.82 | Yes | N/A | N/A | 2023-11-02 | 2023-12-20 | 49 | 35 | 2023-12-20 | 2023-11-09 | Unknown | Unknown | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2024-04-11 | 155 | 111 | Unknown | 2024-02-20 | Unknown | Unknown | 2024-04-11 | 2024-04-25 | 1900-01-14 | 11 | 2024-04-25 | 2024-04-25 | 1 | 1 | 204 | 146 | 16 | 12 | 220 | 158 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-11 | -416 | -299 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-02-24 | 2023-08-15 | IOU Designed & Installed | N/A | No | N/A | -4.95 | -9.75 | Unknown | Unknown | Unknown | 4.8 | 3885 | 691.94 | -4.95 | 696.89 | Yes | N/A | N/A | 2023-01-31 | 2023-02-24 | 25 | 19 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | 2023-08-15 | 173 | 123 | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2023-08-22 | 1900-01-07 | 6 | 2023-08-22 | 2023-08-22 | 1 | 1 | 198 | 142 | 9 | 7 | 207 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-02 | 896 | 641 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-17 | 2023-01-17 | 2025-02-06 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 594388.78 | 119562.53 | Unknown | 399.17 | 19712.41 | 454714.67 | 7939110 | 137433.25 | 594388.78 | -456955.53 | Yes | N/A | N/A | 2023-01-17 | 2023-08-16 | 212 | 152 | 2023-08-16 | 2024-05-16 | 275 | 197 | 2023-08-30 | 2024-06-18 | 43 | 31 | 2024-05-14 | 2024-06-21 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-10-23 | 149 | 107 | 2025-02-06 | 2025-06-11 | 1900-05-05 | 90 | 2025-06-11 | 2025-02-14 | Unknown | Unknown | 255 | 183 | 589 | 423 | 844 | 606 | Steps 2,3,5,6,7 | 295 | 211 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 24.05 | 24.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-26 | -328 | -235 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-03 | 2024-08-21 | IOU Designed & Installed | N/A | No | N/A | 27.59 | Unknown | Unknown | Unknown | Unknown | 27.59 | 3981 | 1690.2 | 27.59 | 1662.61 | Yes | N/A | N/A | 2024-07-02 | 2024-07-03 | 2 | 2 | 2024-07-03 | 2024-07-03 | 1 | 1 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-08-21 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-08-27 | 1900-01-06 | 5 | 2024-08-27 | 2025-03-04 | 190 | 136 | 52 | 38 | 198 | 142 | 250 | 180 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | El Cajon | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | 225 | 162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-07 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 9141.88 | 1922.2 | Unknown | 722.6 | Unknown | 6497.08 | 88962 | Not available | 9141.88 | Unknown | Yes | N/A | N/A | 2024-02-06 | 2023-12-15 | Unknown | Unknown | 2023-12-15 | 2024-03-29 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2025-05-20 | 418 | 298 | Unknown | 2025-02-21 | Unknown | Unknown | 2025-02-25 | 2025-02-28 | 1900-01-03 | 4 | 2025-02-28 | 2025-02-28 | 1 | 1 | 418 | 298 | 111 | 81 | 529 | 379 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 19.1 | 19.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | -528 | -377 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | 2025-03-10 | IOU Designed & Installed | N/A | No | N/A | 5715.32 | 876.32 | Unknown | 50.71 | 11.7 | 4776.59 | 3981 | 2660.26 | 5715.32 | -3055.06 | Yes | N/A | N/A | 2024-12-09 | 2024-12-30 | 22 | 16 | 2024-12-30 | 2025-01-06 | 8 | 6 | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-03-10 | 64 | 46 | Unknown | 2025-02-24 | Unknown | Unknown | 2025-03-10 | 2025-03-27 | 1900-01-17 | 14 | 2025-03-27 | 2025-03-27 | 1 | 1 | 86 | 62 | 27 | 21 | 113 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 540 | 387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-03-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 388.73 | Unknown | Unknown | Unknown | Unknown | 388.73 | 2252898 | 30553.97 | 388.73 | 30165.24 | Yes | N/A | N/A | 2023-03-17 | 2023-04-06 | 21 | 15 | 2023-04-06 | 2023-04-10 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | 2958465 | Unknown | Unknown | Unknown | 2023-11-03 | Unknown | Unknown | Unknown | 2024-11-25 | Unknown | Unknown | 2024-11-25 | 2024-11-22 | Unknown | Unknown | 21 | 15 | 5 | 3 | 26 | 18 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 13.1 | 13.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-03 | -586 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-27 | 2025-05-22 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1337.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-12 | 2025-03-13 | 2 | 2 | 2025-03-13 | 2025-03-27 | 15 | 11 | 2025-03-12 | 2025-03-13 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-05-22 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-05-27 | 1900-01-05 | 4 | 2025-05-27 | 2025-05-27 | 1 | 1 | 61 | 45 | 22 | 16 | 83 | 61 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | -135 | -96 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -448.18 | Unknown | Unknown | Unknown | -511 | 62.82 | 3981 | 1562.97 | -448.18 | 2011.15 | Yes | N/A | N/A | 2024-01-26 | 2024-03-15 | 50 | 36 | 2024-03-15 | 2024-03-27 | 13 | 9 | 2024-03-27 | 2024-07-16 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | 2025-01-17 | 2025-01-17 | 1 | 1 | 162 | 116 | 14 | 10 | 176 | 126 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-04 | 141 | 101 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 793.23 | -50.52 | Unknown | Unknown | 239.15 | 604.6 | 14058 | 7042.85 | 793.23 | 6249.62 | Yes | N/A | N/A | 2023-03-10 | 2023-03-21 | 12 | 8 | 2023-03-21 | 2023-03-29 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | 2023-10-23 | 209 | 149 | Unknown | 2023-10-05 | Unknown | Unknown | Unknown | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2023-10-23 | Unknown | Unknown | 221 | 157 | 9 | 7 | 230 | 164 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | 7.7 | 7.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-03 | -216 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-05 | 2024-04-05 | 2024-12-27 | IOU Designed & Installed | N/A | No | N/A | 21166.9 | 5023.1 | Unknown | 1981.69 | Unknown | 14162.11 | Unknown | 9047.25 | 21166.9 | -12119.65 | Yes | N/A | N/A | 2024-04-05 | 2024-04-19 | 15 | 11 | 2024-04-19 | 2024-11-08 | 204 | 146 | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-11-27 | 24 | 16 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2024-12-30 | 1900-01-03 | 2 | 2024-12-30 | 2024-12-30 | 1 | 1 | 15 | 11 | 233 | 165 | 248 | 176 | Steps 2,3,5,6,7 | 19 | 13 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2028-08-31 | -1365 | -976 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-11-21 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 2549.81 | Unknown | Unknown | Unknown | Unknown | 2549.81 | 3981 | 817.64 | 2549.81 | -1732.17 | Yes | N/A | N/A | 2023-08-22 | 2023-08-03 | Unknown | Unknown | 2023-08-03 | 2024-01-24 | 175 | 125 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-08-14 | 204 | 146 | Unknown | 2024-10-31 | Unknown | Unknown | 2024-11-05 | 2024-12-06 | 1900-01-31 | 24 | 2024-12-06 | 2024-12-05 | Unknown | Unknown | 204 | 146 | 207 | 149 | 411 | 295 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-29 | -777 | -556 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | 2023-09-08 | IOU Designed & Installed | N/A | No | N/A | 849.75 | 583.59 | Unknown | Unknown | Unknown | 266.16 | Unknown | 148.62 | 849.75 | -701.13 | Yes | N/A | N/A | 2023-02-15 | 2023-05-11 | 86 | 62 | 2023-05-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-11 | 2023-09-08 | 121 | 87 | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | 2023-09-13 | 1900-01-05 | 4 | 2023-09-13 | 2023-09-13 | 1 | 1 | 207 | 149 | 7 | 5 | 214 | 154 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 45 | 45 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-15 | 623 | 446 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | 2023-11-15 | IOU Designed & Installed | N/A | No | N/A | -14.92 | -11.28 | Unknown | Unknown | Unknown | -3.64 | 3981 | 905.96 | -14.92 | 920.88 | Yes | N/A | N/A | 2023-10-27 | 2023-07-25 | Unknown | Unknown | 2023-07-25 | 2023-10-27 | 95 | 69 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2023-11-15 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2024-02-01 | 1900-03-19 | 57 | 2024-02-01 | 2023-11-28 | Unknown | Unknown | 20 | 14 | 174 | 126 | 194 | 140 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 93.05 | 93.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-16 | 35 | 26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 962.39 | Unknown | Unknown | Unknown | Unknown | 962.39 | 3981 | 1885.19 | 962.39 | 922.8 | Yes | N/A | N/A | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-11-16 | 2023-11-20 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2024-11-18 | 365 | 261 | Unknown | 2024-09-27 | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2024-11-20 | Unknown | Unknown | 366 | 262 | 5 | 3 | 371 | 265 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-22 | -93 | -68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 668.4 | -13.44 | Unknown | Unknown | Unknown | 681.84 | 19905 | 3268.67 | 668.4 | 2600.27 | Yes | N/A | N/A | 2024-04-02 | 2024-04-02 | 1 | 1 | 2024-04-02 | 2024-04-25 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-04-24 | 23 | 17 | 2024-04-25 | 2025-05-12 | 383 | 273 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | 2025-05-22 | 2025-05-21 | Unknown | Unknown | 384 | 274 | 47 | 35 | 431 | 309 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 84.05 | 84.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | -446 | -320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-06-24 | 2024-12-04 | IOU Designed & Installed | N/A | No | N/A | 5.93 | Unknown | Unknown | Unknown | Unknown | 5.93 | 3981 | 1189.62 | 5.93 | 1183.69 | Yes | N/A | N/A | 2024-05-06 | 2024-04-10 | Unknown | Unknown | 2024-04-10 | 2024-06-24 | 76 | 54 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-12-04 | 164 | 118 | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | 2024-12-10 | 1900-01-06 | 5 | 2024-12-10 | 2024-12-09 | Unknown | Unknown | 164 | 118 | 83 | 59 | 247 | 177 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 158 | 158 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-21 | -508 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 417.94 | -24.23 | Unknown | Unknown | Unknown | 442.17 | 15924 | 1179.9 | 417.94 | 761.96 | Yes | N/A | N/A | 2024-01-08 | 2023-12-21 | Unknown | Unknown | 2023-12-21 | 2024-02-07 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-02-20 | 28 | 20 | 2024-02-07 | 2024-02-12 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-02-29 | Unknown | Unknown | 6 | 4 | 77 | 55 | 83 | 59 | Steps 2,3,5,6,7 | 13 | 9 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 287 | 287 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-03 | -86 | -63 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -166.76 | -10.4 | Unknown | Unknown | -659 | 502.64 | Unknown | 659.07 | -166.76 | 825.83 | Yes | N/A | N/A | 2023-09-06 | 2023-09-05 | Unknown | Unknown | 2023-09-05 | 2023-09-28 | 24 | 18 | 2023-09-28 | 2023-11-09 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | Unknown | Unknown | Unknown | 2024-01-08 | Unknown | Unknown | 2024-01-08 | 2024-01-08 | 1 | 1 | 43 | 31 | 25 | 19 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-23 | -520 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1123.45 | -30.1 | Unknown | Unknown | Unknown | 1153.55 | Unknown | 363.72 | 1123.45 | -759.73 | Yes | N/A | N/A | 2023-03-15 | 2023-03-15 | 1 | 1 | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-08-22 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | -537 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-15 | 2024-06-24 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 1883.71 | Unknown | Unknown | Unknown | Unknown | 1883.71 | Unknown | 4693.2 | 1883.71 | 2809.49 | Yes | N/A | N/A | 2024-05-15 | 2024-06-24 | 41 | 29 | 2024-06-24 | 2024-06-24 | 1 | 1 | 2024-06-24 | Unknown | Unknown | Unknown | 2024-06-24 | 2024-06-27 | 4 | 4 | 2024-06-27 | 2024-07-02 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-08-12 | 1900-02-10 | 30 | 2024-08-12 | 2024-08-12 | 1 | 1 | 47 | 33 | 48 | 36 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2028-02-12 | -1599 | -1143 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | 2023-09-13 | IOU Designed & Installed | N/A | No | N/A | -10.78 | -7.82 | Unknown | Unknown | Unknown | -2.96 | 3754 | 330.53 | -10.78 | 341.31 | Yes | N/A | N/A | 2023-06-20 | 2023-06-20 | 1 | 1 | 2023-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | 2023-09-13 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2023-09-27 | 1900-01-14 | 11 | 2023-09-27 | 2023-09-27 | 1 | 1 | 87 | 63 | 16 | 12 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-30 | -508 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-15 | 2024-02-09 | IOU Designed & Installed | N/A | No | N/A | 230.44 | -12.3 | Unknown | Unknown | Unknown | 242.74 | Unknown | 996.63 | 230.44 | 766.19 | Yes | N/A | N/A | 2023-11-15 | 2023-11-15 | 1 | 1 | 2023-11-15 | 2023-11-15 | 1 | 1 | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2024-02-09 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-04-09 | 1900-03-01 | 43 | 2024-04-09 | 2024-04-09 | 1 | 1 | 88 | 64 | 63 | 45 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | -548 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-06-07 | IOU Designed & Installed | N/A | No | N/A | 521.18 | 236.04 | Unknown | 101.22 | Unknown | 183.92 | 3981 | 153.75 | 521.18 | -367.43 | Yes | N/A | N/A | 2023-03-28 | 2023-04-27 | 31 | 23 | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | 2023-06-07 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | 2023-06-08 | 1900-01-01 | 2 | 2023-06-08 | 2023-06-08 | 1 | 1 | 73 | 53 | 3 | 3 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-30 | 538 | 385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-02 | 2025-04-19 | IOU Designed & Installed | N/A | No | N/A | 7784.51 | 11232.17 | Unknown | 637.52 | -9044 | 4958.82 | Unknown | 9043.68 | 7784.51 | 1259.17 | Yes | N/A | N/A | 2025-04-01 | 2025-04-01 | 1 | 1 | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-19 | 2025-04-20 | 1900-01-01 | 0 | 2025-04-20 | 2025-04-20 | 1 | 0 | 1 | 1 | 3 | 0 | 4 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-19 | -638 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-10-08 | 2024-11-06 | IOU Designed & Installed | N/A | No | N/A | 18.82 | Unknown | Unknown | Unknown | Unknown | 18.82 | 3981 | 234.01 | 18.82 | 215.19 | Yes | N/A | N/A | 2024-09-26 | 2024-09-10 | Unknown | Unknown | 2024-09-10 | 2024-10-08 | 29 | 21 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-11-06 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-11-19 | 1900-01-13 | 10 | 2024-11-19 | 2024-11-19 | 1 | 1 | 30 | 22 | 44 | 32 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-10 | -145 | -104 | No | 2022-12-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-09 | 2022-12-09 | 2023-03-24 | IOU Designed & Installed | N/A | Yes | 82 | -7 | -5.06 | Unknown | Unknown | Unknown | -1.94 | Unknown | 343.5 | -7 | 350.5 | Yes | N/A | N/A | 2022-12-09 | 2023-03-01 | 83 | 59 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-12-09 | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | 2023-05-18 | 1900-02-24 | 40 | 2023-05-18 | 2023-05-18 | 1 | 1 | 83 | 59 | 57 | 41 | 140 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-04 | -192 | -138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-07-19 | 2023-09-29 | IOU Designed & Installed | N/A | No | N/A | 227.79 | -3.93 | Unknown | Unknown | 3.95 | 227.77 | Unknown | 701.9 | 227.79 | 474.11 | Yes | N/A | N/A | 2023-07-19 | 2023-05-11 | Unknown | Unknown | 2023-05-11 | 2023-07-26 | 77 | 55 | 2023-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-09-29 | 66 | 48 | Unknown | 2023-09-28 | Unknown | Unknown | 2023-09-29 | 2023-10-25 | 1900-01-26 | 19 | 2023-10-25 | 2023-10-25 | 1 | 1 | 66 | 48 | 105 | 75 | 171 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-11 | 29 | 21 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-03 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 3753.7 | Unknown | Unknown | Unknown | Unknown | 3753.7 | 3981 | 1511.34 | 3753.7 | -2242.36 | Yes | N/A | N/A | 2023-04-03 | 2023-04-17 | 15 | 11 | 2023-04-17 | 2024-06-12 | 423 | 303 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-08-22 | 2024-09-09 | 1900-01-18 | 13 | 2024-09-09 | 2024-09-09 | 1 | 1 | 15 | 11 | 443 | 317 | 458 | 328 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 171 | 171 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-27 | 399 | 286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-10-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1461.7 | Unknown | Unknown | Unknown | Unknown | 1461.7 | 3981 | 372.34 | 1461.7 | -1089.36 | Yes | N/A | N/A | 2023-09-28 | 2023-08-21 | Unknown | Unknown | 2023-08-21 | 2024-04-09 | 233 | 167 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2024-08-23 | 137 | 99 | Unknown | 2024-08-22 | Unknown | Unknown | Unknown | 2024-08-30 | Unknown | Unknown | 2024-08-30 | 2024-08-29 | Unknown | Unknown | 137 | 99 | 233 | 167 | 370 | 266 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | -48 | -35 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 522.68 | -8.93 | Unknown | Unknown | 18.24 | 513.37 | 1616 | 647.9 | 522.68 | 125.22 | Yes | N/A | N/A | 2023-03-08 | 2023-03-08 | 1 | 1 | 2023-03-08 | 2023-04-10 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | 2023-04-10 | 34 | 24 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1 | 1 | 1 | 1 | 69 | 49 | 70 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-18 | -436 | -312 | No | 2024-06-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-07-03 | 2025-01-03 | IOU Designed & Installed | N/A | Yes | 134 | 12020.99 | Unknown | Unknown | Unknown | Unknown | 12020.99 | 3981 | 1809.65 | 12020.99 | -10211.34 | Yes | N/A | N/A | 2024-06-06 | 2024-09-10 | 97 | 69 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-02-10 | 1900-02-07 | 27 | 2025-02-10 | 2025-02-06 | Unknown | Unknown | 97 | 69 | 39 | 27 | 136 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-04 | -687 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | Unknown | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | 46.44 | -0.94 | Unknown | Unknown | Unknown | 47.38 | 3981 | 1489.16 | 46.44 | 1442.72 | Yes | N/A | N/A | 2024-06-14 | 2024-06-14 | 1 | 1 | 2024-06-14 | 2024-06-14 | 1 | 1 | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-07-16 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-07-17 | 1900-01-01 | 2 | 2024-07-17 | 2024-07-17 | 1 | 1 | 34 | 24 | 4 | 4 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 77.1 | 77.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | -601 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-27 | 2024-12-03 | IOU Designed & Installed | N/A | No | N/A | 1066.18 | -20.84 | Unknown | Unknown | Unknown | 1087.02 | 3981 | 1731.89 | 1066.18 | 665.71 | Yes | N/A | N/A | 2024-09-23 | 2024-09-27 | 5 | 5 | 2024-09-27 | 2024-09-27 | 1 | 1 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-12-03 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2024-12-06 | 1900-01-03 | 4 | 2024-12-06 | 2024-12-06 | 1 | 1 | 73 | 53 | 6 | 6 | 79 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-09 | -637 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-03-04 | 2025-04-10 | IOU Designed & Installed | N/A | No | N/A | 448.29 | Unknown | Unknown | Unknown | 5.59 | 442.7 | 3981 | 1395.74 | 448.29 | 947.45 | Yes | N/A | N/A | 2025-02-27 | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-03-21 | 26 | 20 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-04-10 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-05-13 | 1900-02-02 | 24 | 2025-05-13 | 2025-05-13 | 1 | 1 | 21 | 15 | 61 | 45 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 138.05 | 138.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-12 | -273 | -196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | -747.22 | -22.89 | Unknown | Unknown | -984 | 259.67 | 3981 | 1660.75 | -747.22 | 2407.97 | Yes | N/A | N/A | 2023-02-14 | 2023-04-17 | 63 | 45 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 63 | 45 | 1 | 1 | 64 | 46 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | N/A | El Cajon | El Cajon | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-04-01 | 1289 | 922 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-08 | 2021-04-08 | 2024-09-04 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -14441.66 | 3697.83 | Unknown | Unknown | -50684 | 32544.51 | 0 | 50598.55 | -14441.66 | 65040.21 | Yes | N/A | N/A | 2021-04-08 | 2023-08-29 | 874 | 624 | 2023-08-29 | 2024-05-22 | 268 | 192 | 2023-09-28 | 2024-04-08 | 20 | 14 | 2024-02-29 | 2024-08-22 | 44 | 34 | 2024-05-28 | Unknown | Unknown | Unknown | 2024-05-28 | 2024-08-14 | 79 | 57 | 2024-09-04 | 2024-10-11 | 1900-02-06 | 28 | 2024-10-11 | 2024-10-11 | 1 | 1 | 894 | 638 | 430 | 312 | 1324 | 950 | Steps 2,3,5,6,7 | 362 | 258 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | Applicant Design | Residential | Underserved Community | Valley Center | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 283 | 202 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-27 | 2022-07-27 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 8574.78 | 623.36 | Unknown | Unknown | -23522.4 | 31473.82 | Unknown | 23528.02 | 8574.78 | 14953.24 | Yes | N/A | N/A | 2022-07-27 | 2023-02-08 | 197 | 141 | 2023-02-08 | 2023-06-13 | 126 | 90 | 2023-02-28 | 2023-04-27 | 19 | 13 | 2023-04-28 | 2023-06-07 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | Unknown | Unknown | 2024-01-09 | 2024-01-09 | 1 | 1 | 216 | 154 | 168 | 120 | 384 | 274 | Steps 2,3,5,6,7 | 105 | 75 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-20 | -150 | -107 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1302.81 | Unknown | Unknown | Unknown | 7.63 | 1295.18 | 3981 | 717.32 | 1302.81 | -585.49 | Yes | N/A | N/A | 2023-04-03 | 2023-04-05 | 3 | 3 | 2023-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | Unknown | Unknown | Unknown | 2024-08-23 | Unknown | Unknown | 2024-08-23 | 2024-08-23 | 1 | 1 | 3 | 3 | 1 | 1 | 4 | 4 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-15 | -240 | -171 | No | 2023-09-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | Unknown | IOU Designed & Installed | N/A | Yes | 331 | 459.75 | Unknown | Unknown | Unknown | 5.08 | 454.67 | 3981 | 766.01 | 459.75 | 306.26 | Yes | N/A | N/A | 2023-09-11 | 2024-08-06 | 331 | 237 | 2024-08-06 | 2024-08-07 | 2 | 2 | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-10-18 | 1 | 1 | 331 | 237 | 3 | 3 | 334 | 240 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -282 | -202 | No | 2024-04-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-07-09 | Unknown | IOU Designed & Installed | N/A | Yes | 103 | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 4840.53 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-17 | 2024-07-09 | 84 | 60 | 2024-07-09 | 2024-07-29 | 21 | 15 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-07-03 | Unknown | Unknown | 2025-07-03 | 2025-05-15 | Unknown | Unknown | 84 | 60 | 21 | 15 | 105 | 75 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | 409 | 292 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-09-26 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | 5826.14 | 124.03 | Unknown | Unknown | Unknown | 5702.11 | Unknown | 566.8 | 5826.14 | -5259.34 | Yes | N/A | N/A | 2024-09-26 | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2024-10-07 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-10-23 | 24 | 18 | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-11-12 | 1900-02-04 | 26 | 2024-11-12 | 2024-11-12 | 1 | 1 | 0 | 0 | 74 | 54 | 74 | 54 | Steps 2,3,5,6,7 | 16 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-11 | 289 | 208 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-12 | 2024-05-28 | IOU Designed & Installed | N/A | No | N/A | 26.8 | -8.7 | Unknown | Unknown | Unknown | 35.5 | Unknown | 1049.39 | 26.8 | 1022.59 | Yes | N/A | N/A | 2024-01-03 | 2023-10-26 | Unknown | Unknown | 2023-10-26 | 2024-01-12 | 79 | 57 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | 2024-05-28 | 138 | 98 | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-07-10 | 1900-02-12 | 32 | 2024-07-10 | 2024-07-26 | 17 | 13 | 138 | 98 | 140 | 102 | 278 | 200 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 1667 | 1667 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-02-07 | -239 | -172 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-02-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -162.91 | -26.08 | Unknown | Unknown | -505 | 368.17 | 3981 | 1137.08 | -162.91 | 1299.99 | Yes | N/A | N/A | 2024-01-19 | 2024-02-14 | 27 | 19 | 2024-02-14 | 2024-02-16 | 3 | 3 | 2024-02-16 | 2024-05-28 | 103 | 73 | 2024-02-20 | 2024-03-01 | 11 | 9 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | Unknown | 2024-06-13 | Unknown | Unknown | 2024-06-13 | 2024-06-13 | 1 | 1 | 130 | 92 | 15 | 13 | 145 | 105 | Steps 2,3,5,6,7 | 98 | 70 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-02 | -261 | -188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 45.2 | Unknown | Unknown | Unknown | Unknown | 45.2 | Unknown | 1627.17 | 45.2 | 1581.97 | Yes | N/A | N/A | 2024-07-03 | 2024-05-20 | Unknown | Unknown | 2024-05-20 | 2024-07-03 | 45 | 33 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | Unknown | Unknown | 2024-08-14 | 2024-08-14 | 1 | 1 | 0 | 0 | 46 | 34 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-14 | -244 | -175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | 2024-02-05 | IOU Designed & Installed | N/A | No | N/A | 5.86 | -7.09 | Unknown | Unknown | Unknown | 12.95 | Unknown | 872.64 | 5.86 | 866.78 | Yes | N/A | N/A | 2024-01-04 | 2023-11-30 | Unknown | Unknown | 2023-11-30 | 2024-01-04 | 36 | 26 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-02-05 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-03-15 | 1900-02-08 | 30 | 2024-03-15 | 2024-03-15 | 1 | 1 | 33 | 23 | 77 | 57 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-13 | -186 | -134 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-10-03 | IOU Designed & Installed | N/A | No | N/A | 3563.05 | Unknown | Unknown | Unknown | Unknown | 3563.05 | Unknown | 539.93 | 3563.05 | -3023.12 | Yes | N/A | N/A | 2023-04-18 | 2023-08-28 | 133 | 95 | 2023-08-28 | 2023-09-18 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-10-10 | 1900-01-07 | 6 | 2023-10-10 | 2023-10-10 | 1 | 1 | 133 | 95 | 31 | 23 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 46.05 | 46.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-06 | -396 | -283 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-04-24 | 2024-05-06 | IOU Designed & Installed | N/A | No | N/A | 33.8 | -30.04 | Unknown | Unknown | Unknown | 63.84 | 3981 | 885.32 | 33.8 | 851.52 | Yes | N/A | N/A | 2024-03-01 | 2024-03-05 | 5 | 3 | 2024-03-05 | 2024-04-24 | 51 | 37 | 2024-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-06 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-06-05 | 1900-01-30 | 23 | 2024-06-05 | 2024-06-05 | 1 | 1 | 18 | 12 | 83 | 61 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 1064.1 | 1064.1 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2022-11-01 | 497 | 356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4.6 | -4.09 | Unknown | Unknown | Unknown | 8.69 | 3241 | 535.47 | 4.6 | 530.87 | Yes | N/A | N/A | 2023-02-01 | 2023-02-01 | 1 | 1 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | Unknown | Unknown | 2024-03-13 | 2024-03-12 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 44.1 | 44.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-08 | -584 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-26 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 109.78 | -1.26 | Unknown | Unknown | Unknown | 111.04 | 3981 | 1583.05 | 109.78 | 1473.27 | Yes | N/A | N/A | 2024-11-01 | 2024-10-10 | Unknown | Unknown | 2024-10-10 | 2024-11-26 | 48 | 34 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-02-11 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-03-03 | 1900-01-20 | 15 | 2025-03-03 | 2025-03-03 | 1 | 1 | 78 | 56 | 70 | 50 | 148 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | N/A | El Cajon | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-04-01 | 1349 | 964 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-07-26 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 30900.55 | 5642.6 | Unknown | 477.55 | 913.94 | 23866.46 | 2969480 | 21574.02 | 30900.55 | -9326.53 | Yes | N/A | N/A | 2023-07-19 | 2024-03-12 | 238 | 170 | 2024-03-12 | 2024-08-01 | 143 | 103 | 2023-09-28 | 2024-07-22 | 16 | 10 | 2024-07-23 | 2024-07-31 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | Unknown | Unknown | 2024-12-10 | 2024-12-10 | 1 | 1 | 254 | 180 | 153 | 111 | 407 | 291 | Steps 2,3,5,6,7 | 308 | 220 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-10 | 232 | 167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-06-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1073.75 | Unknown | Unknown | Unknown | 65.03 | 1008.72 | 11943 | Not available | 1073.75 | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-01-22 | Unknown | Unknown | 2024-01-22 | 2024-07-01 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2025-02-26 | 241 | 173 | Unknown | 2025-02-04 | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | 2025-02-27 | 2025-02-27 | 1 | 1 | 241 | 173 | 163 | 117 | 404 | 290 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-20 | -340 | -243 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-02 | 2025-05-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 693.09 | Unknown | Unknown | Unknown | Unknown | 693.09 | Unknown | 1059.29 | 693.09 | 366.2 | Yes | N/A | N/A | 2025-05-02 | 2025-05-12 | 11 | 7 | 2025-05-12 | 2025-05-12 | 1 | 1 | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | 2025-05-15 | 2025-05-15 | 1 | 1 | 11 | 7 | 2 | 2 | 13 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-10 | -322 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-02-23 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 734.24 | -14.87 | Unknown | Unknown | Unknown | 749.11 | 0 | 1198.92 | 734.24 | 464.68 | Yes | N/A | N/A | 2024-02-23 | 2023-11-08 | Unknown | Unknown | 2023-11-08 | 2024-02-23 | 108 | 78 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-11-05 | 257 | 183 | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2024-11-22 | 1900-01-17 | 14 | 2024-11-22 | 2024-11-22 | 1 | 1 | 257 | 183 | 127 | 93 | 384 | 276 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 115 | 115 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | -442 | -317 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-10 | 2024-06-24 | IOU Designed & Installed | N/A | No | N/A | 1681.77 | -41.7 | Unknown | Unknown | 3.27 | 1720.2 | Unknown | 722.91 | 1681.77 | -958.86 | Yes | N/A | N/A | 2024-05-08 | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-06-04 | 100 | 72 | 2024-06-04 | Unknown | Unknown | Unknown | 2024-05-08 | 2024-06-14 | 38 | 28 | 2024-05-10 | 2024-06-24 | 46 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-09-20 | 1900-03-29 | 65 | 2024-09-20 | 2024-09-19 | Unknown | Unknown | 46 | 32 | 227 | 165 | 273 | 197 | Steps 2,3,5,6,7 | 35 | 25 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-11 | -536 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | 2023-04-21 | IOU Designed & Installed | N/A | No | N/A | 1165.44 | 401.14 | Unknown | 155.78 | Unknown | 608.52 | Unknown | 722.18 | 1165.44 | -443.26 | Yes | N/A | N/A | 2023-03-02 | 2023-03-02 | 1 | 1 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | 2023-04-21 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | 2023-04-24 | 1900-01-03 | 2 | 2023-04-24 | 2023-04-24 | 1 | 1 | 52 | 38 | 5 | 3 | 57 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | -374 | -268 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-17 | 2025-05-14 | IOU Designed & Installed | N/A | No | N/A | 531.74 | 266.88 | Unknown | 72.04 | Unknown | 192.82 | 3981 | 1141.39 | 531.74 | 609.65 | Yes | N/A | N/A | 2024-06-12 | 2024-05-28 | Unknown | Unknown | 2024-05-28 | 2024-06-17 | 21 | 15 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2025-05-14 | 332 | 238 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-05-14 | 1899-12-31 | 1 | 2025-05-14 | 2025-05-14 | 1 | 1 | 332 | 238 | 23 | 17 | 355 | 255 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-12 | -335 | -240 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | 2024-12-10 | IOU Designed & Installed | N/A | No | N/A | 100.79 | Unknown | Unknown | Unknown | Unknown | 100.79 | 3981 | 197.01 | 100.79 | 96.22 | Yes | N/A | N/A | 2024-11-19 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-27 | 15 | 11 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2024-12-10 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2024-12-13 | 1900-01-03 | 4 | 2024-12-13 | 2024-12-12 | Unknown | Unknown | 9 | 7 | 19 | 15 | 28 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | 441 | 316 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 12683.59 | Unknown | Unknown | Unknown | 42.32 | 12641.27 | 49559 | 2236.14 | 12683.59 | -10447.45 | Yes | N/A | N/A | 2024-06-12 | 2024-07-26 | 45 | 33 | 2024-07-26 | 2024-08-06 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-10-21 | 77 | 55 | Unknown | 2024-11-21 | Unknown | Unknown | 2025-02-05 | 2025-02-05 | 1899-12-31 | 1 | 2025-02-05 | 2025-01-15 | Unknown | Unknown | 122 | 88 | 13 | 9 | 135 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 3500 | 3500 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-10-27 | -511 | -366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-10 | 2025-05-30 | IOU Designed & Installed | N/A | No | N/A | 7704.63 | 1277.08 | Unknown | 488.75 | 123.06 | 5815.74 | 3981 | 1186.27 | 7704.63 | -6518.36 | Yes | N/A | N/A | 2024-12-09 | 2025-01-16 | 39 | 29 | 2025-01-16 | 2025-01-17 | 2 | 2 | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-05-30 | 135 | 97 | Unknown | 2025-05-16 | Unknown | Unknown | 2025-05-30 | 2025-06-03 | 1900-01-04 | 3 | 2025-06-03 | 2025-06-03 | 1 | 1 | 174 | 126 | 8 | 6 | 182 | 132 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community,Tribal Community | ALPINE | N/A | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-01 | 469 | 335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-08-08 | 2023-11-17 | IOU Designed & Installed | N/A | No | N/A | 2070.74 | 631.15 | Unknown | 201.48 | 121.79 | 1116.32 | 3981 | 431.54 | 2070.74 | -1639.2 | Yes | N/A | N/A | 2023-05-10 | 2023-08-20 | 103 | 73 | 2023-08-20 | 2023-08-20 | 1 | 0 | 2023-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2023-11-17 | 89 | 65 | Unknown | 2023-10-26 | Unknown | Unknown | 2023-11-17 | 2024-10-12 | 1900-11-26 | 236 | 2024-10-12 | 2024-10-12 | 1 | 0 | 192 | 138 | 333 | 236 | 525 | 374 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-28 | -700 | -501 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-23 | 2025-06-23 | 2025-06-27 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2185.98 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-23 | 2025-06-02 | Unknown | Unknown | 2025-06-02 | 2025-06-23 | 22 | 16 | 2025-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-27 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-06-27 | 2025-06-27 | 1899-12-31 | 1 | 2025-06-27 | 2025-06-27 | 1 | 1 | 5 | 5 | 24 | 18 | 29 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Vista | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | -93 | -68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-08-30 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 5513.17 | Unknown | Unknown | Unknown | -1934 | 7447.17 | 0 | 4633.24 | 5513.17 | -879.93 | Yes | N/A | N/A | 2023-06-27 | 2023-06-27 | 1 | 1 | 2023-06-27 | 2023-10-16 | 112 | 80 | 2024-06-18 | 2024-06-19 | 2 | 2 | 2024-06-05 | 2024-06-25 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-07-30 | 1900-02-19 | 37 | 2024-07-30 | 2024-07-30 | 1 | 1 | 3 | 3 | 180 | 130 | 183 | 133 | Steps 2,3,5,6,7 | 14 | 10 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-11 | -237 | -170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-18 | 2025-06-19 | IOU Designed & Installed | N/A | No | N/A | -373.72 | 308.62 | Unknown | Unknown | -886 | 203.66 | Unknown | 885.84 | -373.72 | 1259.56 | Yes | N/A | N/A | 2025-04-18 | 2025-04-23 | 6 | 4 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-06-19 | 1899-12-31 | 1 | 2025-06-19 | 2025-06-19 | 1 | 1 | 6 | 4 | 2 | 2 | 8 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | JAMUL | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-29 | 165 | 119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | 76127.16 | 9373.88 | Unknown | Unknown | -8495.04 | 75248.32 | 0 | 32111.37 | 76127.16 | -44015.79 | Yes | N/A | N/A | 2023-09-26 | 2024-03-26 | 183 | 131 | 2024-03-26 | 2024-07-03 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2024-05-21 | 22 | 16 | 2024-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2025-03-13 | 1900-09-03 | 177 | 2025-03-13 | 2025-03-13 | 1 | 1 | 183 | 131 | 370 | 266 | 553 | 397 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56, LA MESA | 117 | 117 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-20 | 1051 | 752 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2024-04-25 | 2025-03-04 | IOU Designed & Installed | N/A | No | N/A | 5773.9 | 4408.48 | Unknown | 771.86 | -10694 | 11287.56 | 0 | 10582.78 | 5773.9 | 4808.88 | Yes | N/A | N/A | 2023-02-23 | 2023-11-23 | 274 | 196 | 2023-11-23 | 2024-08-29 | 281 | 201 | 2024-04-24 | 2024-04-25 | 2 | 2 | 2024-04-25 | 2024-09-05 | 49 | 35 | 2024-08-29 | 2025-02-13 | 169 | 121 | 2024-09-09 | 2024-11-21 | 74 | 54 | 2025-03-04 | 2025-03-10 | 1900-01-06 | 5 | 2025-03-10 | 2025-03-06 | Unknown | Unknown | 445 | 319 | 411 | 295 | 856 | 614 | Steps 2,3,5,6,7 | 291 | 209 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-18 | -338 | -242 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-06-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1316.43 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-27 | 2024-07-01 | 5 | 3 | 2024-07-01 | 2024-07-18 | 18 | 14 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | 2025-05-15 | 2025-05-15 | 1 | 1 | 5 | 3 | 19 | 15 | 24 | 18 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 54 | 54 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-06 | -510 | -365 | No | 2023-07-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2023-07-24 | 2023-09-12 | IOU Designed & Installed | N/A | Yes | 8 | -8.51 | -16.61 | Unknown | Unknown | Unknown | 8.1 | 6481 | 906.06 | -8.51 | 914.57 | Yes | N/A | N/A | 2023-07-24 | 2023-08-01 | 9 | 7 | 2023-08-01 | 2025-03-06 | 584 | 418 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2023-09-12 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2023-09-12 | 2023-10-13 | 1900-01-31 | 24 | 2023-10-13 | 2023-10-13 | 1 | 1 | 60 | 44 | 617 | 443 | 677 | 487 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | 772 | 772 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-21 | 67 | 48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-04-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 423.08 | Unknown | Unknown | Unknown | 4.21 | 418.87 | 2766157 | 88970.33 | 423.08 | 88547.25 | Yes | N/A | N/A | 2024-02-22 | 2024-03-20 | 28 | 20 | 2024-03-20 | 2025-01-27 | 314 | 224 | 2024-07-11 | 2025-01-13 | 3 | 3 | 2024-08-09 | 2025-04-09 | 115 | 83 | 2025-01-27 | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | 2025-02-26 | 2025-02-26 | 1 | 1 | 31 | 23 | 430 | 308 | 461 | 331 | Steps 2,3,5,6,7 | 429 | 305 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | -518 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | 2025-04-23 | IOU Designed & Installed | N/A | No | N/A | 729.63 | 517.88 | Unknown | Unknown | Unknown | 211.75 | 9601 | 525.39 | 729.63 | -204.24 | Yes | N/A | N/A | 2024-10-14 | 2024-07-02 | Unknown | Unknown | 2024-07-02 | 2024-10-14 | 105 | 75 | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2025-04-23 | 192 | 138 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-04-25 | 1900-01-02 | 3 | 2025-04-25 | 2025-04-25 | 1 | 1 | 192 | 138 | 109 | 79 | 301 | 217 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 1987.05 | 1987.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-03-14 | -397 | -285 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-10 | 2024-05-10 | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 27.22 | Unknown | Unknown | Unknown | Unknown | 27.22 | 0 | 1212.75 | 27.22 | 1185.53 | Yes | N/A | N/A | 2024-05-10 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-05-10 | 51 | 37 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2025-01-21 | 257 | 183 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | 2025-02-10 | 1900-01-20 | 15 | 2025-02-10 | 2025-02-10 | 1 | 1 | 257 | 183 | 73 | 53 | 330 | 236 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | -492 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-18 | 2024-07-03 | IOU Designed & Installed | N/A | No | N/A | 2011.65 | 370.22 | Unknown | Unknown | Unknown | 1641.43 | Unknown | 1889.83 | 2011.65 | -121.82 | Yes | N/A | N/A | 2024-06-18 | 2024-06-10 | Unknown | Unknown | 2024-06-10 | 2024-06-18 | 9 | 7 | 2024-06-18 | Unknown | Unknown | Unknown | 2024-06-28 | 2024-08-01 | 35 | 25 | 2024-06-18 | 2024-07-03 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-11-07 | 1900-05-07 | 92 | 2024-11-07 | 2024-11-07 | 1 | 1 | 16 | 12 | 173 | 125 | 189 | 137 | Steps 2,3,5,6,7 | 44 | 32 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-28 | -706 | -505 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-09 | 2025-05-13 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 344.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | 2025-05-12 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | 2025-05-22 | 1900-01-09 | 8 | 2025-05-22 | 2025-05-22 | 1 | 1 | 1 | 1 | 15 | 11 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-21 | -308 | -221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-13 | 2025-02-13 | IOU Designed & Installed | N/A | No | N/A | 265.88 | -4.38 | Unknown | Unknown | Unknown | 270.26 | 3981 | 1863.39 | 265.88 | 1597.51 | Yes | N/A | N/A | 2025-02-06 | 2025-01-30 | Unknown | Unknown | 2025-01-30 | 2025-02-13 | 15 | 11 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-02-13 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-03-19 | 1900-02-03 | 25 | 2025-03-19 | 2025-03-19 | 1 | 1 | 1 | 1 | 51 | 37 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 222 | 159 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-14 | 2023-08-24 | IOU Designed & Installed | N/A | No | N/A | 4821.45 | 1701.44 | Unknown | Unknown | 67.46 | 3052.55 | 3885 | 472.55 | 4821.45 | -4348.9 | Yes | N/A | N/A | 2023-04-11 | 2023-04-14 | 4 | 4 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | 2023-08-24 | 133 | 95 | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | 2023-11-09 | 1900-03-18 | 56 | 2023-11-09 | 2023-11-09 | 1 | 1 | 137 | 99 | 79 | 57 | 216 | 156 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-11 | -293 | -210 | No | 2024-04-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-12 | 2024-04-12 | 2025-02-19 | IOU Designed & Installed | N/A | Yes | 290 | 1633.8 | 244.51 | Unknown | Unknown | Unknown | 1389.29 | 3981 | 1806.59 | 1633.8 | 172.79 | Yes | N/A | N/A | 2024-04-12 | 2025-01-27 | 291 | 207 | 2025-01-27 | 2024-04-12 | Unknown | Unknown | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2025-02-19 | 314 | 224 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-21 | 1900-01-02 | 3 | 2025-02-21 | 2025-02-21 | 1 | 1 | 605 | 431 | 4 | 4 | 609 | 435 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 74.4 | 74.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | -435 | -311 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-03-21 | 2023-09-22 | IOU Designed & Installed | N/A | No | N/A | 683.82 | -8.35 | Unknown | Unknown | 21.8 | 670.37 | 3885 | 1187.58 | 683.82 | 503.76 | Yes | N/A | N/A | 2023-02-22 | 2023-05-19 | 87 | 63 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | 2023-09-22 | 128 | 92 | Unknown | 2023-09-14 | Unknown | Unknown | 2023-09-22 | 2023-10-02 | 1900-01-10 | 7 | 2023-10-02 | 2023-09-29 | Unknown | Unknown | 215 | 155 | 11 | 7 | 226 | 162 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 23 | 23 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | -428 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-17 | 2023-08-17 | 2023-11-06 | IOU Designed & Installed | N/A | No | N/A | 350.89 | 123.34 | Unknown | Unknown | Unknown | 227.55 | 3981 | 953.97 | 350.89 | 603.08 | Yes | N/A | N/A | 2023-08-17 | 2023-08-17 | 1 | 1 | 2023-08-17 | 2023-08-17 | 1 | 1 | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2023-11-06 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2023-11-16 | 1900-01-10 | 9 | 2023-11-16 | 2023-11-16 | 1 | 1 | 83 | 59 | 13 | 11 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-12 | -536 | -383 | No | 2024-02-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-02 | 2024-03-26 | IOU Designed & Installed | N/A | Yes | 3 | 226.92 | -22.03 | Unknown | Unknown | 5.35 | 243.6 | 3981 | 1221.25 | 226.92 | 994.33 | Yes | N/A | N/A | 2024-01-02 | 2024-02-23 | 53 | 39 | 2024-02-23 | 2024-02-26 | 4 | 2 | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-03-26 | 33 | 23 | Unknown | 2024-03-21 | Unknown | Unknown | 2024-03-26 | 2024-04-24 | 1900-01-29 | 22 | 2024-04-24 | 2024-04-24 | 1 | 1 | 86 | 62 | 35 | 25 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-20 | -282 | -203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | 2025-04-18 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1860.6 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-26 | 2025-03-06 | 315 | 225 | 2025-03-06 | 2025-04-18 | 44 | 32 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-04-24 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-06-30 | 1900-03-08 | 48 | 2025-06-30 | 2025-05-14 | Unknown | Unknown | 322 | 230 | 112 | 80 | 434 | 310 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-29 | -77 | -56 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-02-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 3559.13 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-06 | 2023-02-01 | Unknown | Unknown | 2023-02-01 | 2023-06-07 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | 2023-06-12 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-06-13 | Unknown | Unknown | 6 | 4 | 127 | 91 | 133 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-22 | -480 | -343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-03-08 | 2024-08-27 | IOU Designed & Installed | N/A | No | N/A | 3063.08 | 482.1 | Unknown | 89.74 | 15.08 | 2476.16 | 3981 | 1237.63 | 3063.08 | -1825.45 | Yes | N/A | N/A | 2024-02-29 | 2024-03-19 | 20 | 14 | 2024-03-19 | 2024-03-19 | 1 | 1 | 2024-03-19 | 2024-07-26 | 130 | 94 | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-08-27 | 159 | 113 | Unknown | 2024-08-20 | Unknown | Unknown | 2024-08-27 | 2024-08-29 | 1900-01-02 | 3 | 2024-08-29 | 2024-08-29 | 1 | 1 | 309 | 221 | 5 | 5 | 314 | 226 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-09 | -613 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-29 | 2024-04-01 | IOU Designed & Installed | N/A | No | N/A | 517.97 | -17.1 | Unknown | Unknown | Unknown | 535.07 | Unknown | 917.4 | 517.97 | 399.43 | Yes | N/A | N/A | 2024-03-21 | 2024-02-16 | Unknown | Unknown | 2024-02-16 | 2024-03-29 | 43 | 31 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-04-01 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-06-06 | 1900-03-07 | 49 | 2024-06-06 | 2024-06-06 | 1 | 1 | 4 | 2 | 111 | 81 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-11 | -599 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-04-01 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | 18.48 | -16.42 | Unknown | Unknown | Unknown | 34.9 | Unknown | 931.18 | 18.48 | 912.7 | Yes | N/A | N/A | 2024-03-01 | 2024-01-30 | Unknown | Unknown | 2024-01-30 | 2024-04-01 | 63 | 45 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-05-17 | 47 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-05-23 | 1900-01-06 | 5 | 2024-05-23 | 2024-05-22 | Unknown | Unknown | 47 | 35 | 70 | 50 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | MOUNT LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-29 | -36 | -26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-12 | 2024-12-12 | IOU Designed & Installed | N/A | No | N/A | 8113.02 | 2088.72 | Unknown | 129.81 | Unknown | 5894.49 | Unknown | 1416.44 | 8113.02 | -6696.58 | Yes | N/A | N/A | 2024-07-12 | 2024-06-21 | Unknown | Unknown | 2024-06-21 | 2024-07-12 | 22 | 16 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-12-12 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-02-21 | 1900-03-12 | 52 | 2025-02-21 | 2025-02-21 | 1 | 1 | 154 | 110 | 95 | 69 | 249 | 179 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-23 | -190 | -137 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 609.2 | -11.6 | Unknown | Unknown | 6.34 | 614.46 | Unknown | 1504.99 | 609.2 | 895.79 | Yes | N/A | N/A | 2024-06-06 | 2024-04-25 | Unknown | Unknown | 2024-04-25 | 2024-06-06 | 43 | 31 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-07-09 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-10-15 | 1900-04-08 | 71 | 2024-10-15 | 2024-10-15 | 1 | 1 | 34 | 24 | 143 | 103 | 177 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-05 | 189 | 136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-06-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5717.92 | 4126.86 | Unknown | 984.67 | -1143 | 1749.39 | Unknown | 1143.32 | 5717.92 | -4574.6 | Yes | N/A | N/A | 2023-05-18 | 2023-05-18 | 1 | 1 | 2023-05-18 | 2023-06-27 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 1 | 1 | 42 | 30 | 43 | 31 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | -613 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | 2024-10-14 | IOU Designed & Installed | N/A | No | N/A | 357.34 | Unknown | Unknown | Unknown | 5.34 | 352 | 3981 | 1082.67 | 357.34 | 725.33 | Yes | N/A | N/A | 2024-08-26 | 2024-08-13 | Unknown | Unknown | 2024-08-13 | 2024-09-04 | 23 | 17 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-10-14 | 41 | 29 | Unknown | 2024-10-11 | Unknown | Unknown | 2024-10-14 | 2024-12-03 | 1900-02-19 | 37 | 2024-12-03 | 2024-12-03 | 1 | 1 | 41 | 29 | 75 | 55 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-13 | -198 | -142 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | 2023-06-28 | 2023-08-21 | IOU Designed & Installed | N/A | No | N/A | -7.56 | -5.47 | Unknown | Unknown | Unknown | -2.09 | Unknown | 480.44 | -7.56 | 488 | Yes | N/A | N/A | 2023-06-28 | 2023-05-03 | Unknown | Unknown | 2023-05-03 | 2023-06-28 | 57 | 41 | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-08-21 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2023-09-28 | 1900-02-07 | 29 | 2023-09-28 | 2023-09-28 | 1 | 1 | 55 | 39 | 97 | 71 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ALPINE | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-24 | -383 | -274 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 27.59 | Unknown | Unknown | Unknown | Unknown | 27.59 | 2841 | 973.93 | 27.59 | 946.34 | Yes | N/A | N/A | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2025-01-30 | 156 | 112 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-06 | 1900-01-07 | 6 | 2025-02-06 | 2025-02-06 | 1 | 1 | 157 | 113 | 10 | 8 | 167 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-02 | -621 | -444 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | 2025-04-10 | IOU Designed & Installed | N/A | No | N/A | 2323.75 | -1.26 | Unknown | Unknown | 25.85 | 2299.16 | Unknown | 3987.2 | 2323.75 | 1663.45 | Yes | N/A | N/A | 2025-02-18 | 2025-03-17 | 28 | 20 | 2025-03-17 | 2025-03-24 | 8 | 6 | 2025-02-19 | 2025-03-24 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-04-10 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-05-22 | 1900-02-11 | 31 | 2025-05-22 | 2025-05-22 | 1 | 1 | 80 | 58 | 52 | 38 | 132 | 96 | Steps 2,3,5,6,7 | 33 | 23 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-11 | -7 | -6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-08-01 | IOU Designed & Installed | N/A | No | N/A | 4.2 | -5.58 | Unknown | Unknown | 7.06 | 2.72 | 3981 | 831.26 | 4.2 | 827.06 | Yes | N/A | N/A | 2023-06-13 | 2023-03-30 | Unknown | Unknown | 2023-03-30 | 2023-06-19 | 82 | 58 | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | 2023-08-01 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2024-03-04 | 1900-08-04 | 155 | 2024-03-04 | 2024-03-04 | 1 | 1 | 44 | 32 | 300 | 214 | 344 | 246 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-05 | -598 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | -1060.53 | Unknown | Unknown | Unknown | -1135 | 74.47 | 6669.61 | 2916.37 | -1060.53 | 3976.9 | Yes | N/A | N/A | 2024-08-14 | 2024-08-15 | 2 | 2 | 2024-08-15 | 2024-08-15 | 1 | 1 | 2024-08-15 | 2024-09-04 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-10-10 | 37 | 27 | Unknown | 2024-10-09 | Unknown | Unknown | 2024-10-10 | 2024-10-15 | 1900-01-05 | 4 | 2024-10-15 | 2024-10-15 | 1 | 1 | 60 | 44 | 8 | 6 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-25 | -141 | -101 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | 2023-09-15 | 2023-12-27 | IOU Designed & Installed | N/A | No | N/A | 1014.39 | -33.69 | Unknown | Unknown | Unknown | 1048.08 | 3981 | 603.63 | 1014.39 | -410.76 | Yes | N/A | N/A | 2023-08-24 | 2023-08-15 | Unknown | Unknown | 2023-08-15 | 2023-09-15 | 32 | 24 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2023-12-27 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2024-01-05 | 1900-01-09 | 8 | 2024-01-05 | 2024-01-05 | 1 | 1 | 104 | 74 | 43 | 33 | 147 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-28 | -258 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-07 | 2025-03-05 | 2025-03-12 | IOU Designed & Installed | N/A | No | N/A | 419.47 | -8.43 | Unknown | Unknown | Unknown | 427.9 | Unknown | 3046.23 | 419.47 | 2626.76 | Yes | N/A | N/A | 2025-02-07 | 2025-02-04 | Unknown | Unknown | 2025-02-04 | 2025-03-05 | 30 | 22 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-12 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-05-15 | 1900-03-05 | 47 | 2025-05-15 | 2025-05-15 | 1 | 1 | 8 | 6 | 96 | 70 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DULZURA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-10 | -320 | -230 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-15 | 2023-03-21 | IOU Designed & Installed | N/A | No | N/A | 888.59 | 580.66 | Unknown | 176.2 | -753 | 884.73 | 2841 | 1203.02 | 888.59 | 314.43 | Yes | N/A | N/A | 2023-02-13 | 2023-02-15 | 3 | 3 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-22 | 2023-03-21 | 28 | 20 | Unknown | 2023-03-15 | Unknown | Unknown | 2023-03-21 | 2023-03-27 | 1900-01-06 | 5 | 2023-03-27 | 2023-03-27 | 1 | 1 | 31 | 23 | 8 | 6 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-06 | -550 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-03 | 2023-09-28 | IOU Designed & Installed | N/A | No | N/A | -19.89 | -6.71 | Unknown | Unknown | -691.15 | 677.97 | Unknown | 696.77 | -19.89 | 716.66 | Yes | N/A | N/A | 2023-08-02 | 2023-08-16 | 15 | 11 | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | 2023-08-21 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2023-09-28 | 39 | 29 | Unknown | 2023-09-26 | Unknown | Unknown | 2023-09-28 | 2023-10-04 | 1900-01-06 | 5 | 2023-10-04 | 2023-10-04 | 1 | 1 | 60 | 44 | 9 | 7 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-15 | 516 | 369 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | 2025-04-10 | IOU Designed & Installed | N/A | No | N/A | 2570.11 | -30.02 | Unknown | Unknown | 115.89 | 2484.24 | 36350 | 449.05 | 2570.11 | -2121.06 | Yes | N/A | N/A | 2024-03-18 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2024-04-04 | 24 | 18 | 2024-12-30 | 2025-01-08 | 10 | 8 | 2024-12-05 | 2025-02-07 | 57 | 41 | 2024-04-04 | 2025-04-04 | 366 | 262 | Unknown | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-04-15 | 1900-01-05 | 4 | 2025-04-15 | 2025-04-14 | Unknown | Unknown | 376 | 270 | 87 | 63 | 463 | 333 | Steps 2,3,5,6,7 | 343 | 245 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-08 | 21 | 16 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 542.17 | -10.89 | Unknown | Unknown | Unknown | 553.06 | 15924 | 3717.62 | 542.17 | 3175.45 | Yes | N/A | N/A | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | 2025-02-21 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-01-01 | 41 | 29 | 2025-02-21 | 2025-04-04 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | 2025-04-30 | 2025-04-29 | Unknown | Unknown | 44 | 32 | 154 | 110 | 198 | 142 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-15 | -596 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-27 | 2024-11-27 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | 94.01 | -1.5 | Unknown | Unknown | Unknown | 95.51 | 3981 | 2015.12 | 94.01 | 1921.11 | Yes | N/A | N/A | 2024-11-27 | 2024-11-27 | 1 | 1 | 2024-11-27 | 2024-11-27 | 1 | 1 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2025-02-19 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-26 | 1900-01-07 | 6 | 2025-02-26 | 2025-02-26 | 1 | 1 | 86 | 62 | 10 | 8 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-08 | -641 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 738.89 | Unknown | Unknown | Unknown | 5.03 | 733.86 | 3981 | 2564.38 | 738.89 | 1825.49 | Yes | N/A | N/A | 2024-09-18 | 2024-10-04 | 17 | 13 | 2024-10-04 | 2024-10-09 | 6 | 4 | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | 2024-12-06 | 2024-12-06 | 1 | 1 | 17 | 13 | 7 | 5 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-23 | -193 | -140 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | Unknown | 2023-07-31 | IOU Designed & Installed | N/A | No | N/A | -6.64 | -12.82 | Unknown | Unknown | Unknown | 6.18 | 3981 | 1069.71 | -6.64 | 1076.35 | Yes | N/A | N/A | 2023-05-03 | 2023-05-03 | 1 | 1 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2023-08-14 | 1900-01-14 | 11 | 2023-08-14 | 2023-08-14 | 1 | 1 | 1 | 1 | 16 | 12 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-19 | -497 | -356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | 8688.65 | Unknown | Unknown | Unknown | 1.24 | 8687.41 | 3981 | 2118.81 | 8688.65 | -6569.84 | Yes | N/A | N/A | 2023-12-01 | 2023-12-15 | 15 | 11 | 2023-12-15 | 2023-12-15 | 1 | 1 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2024-01-22 | 39 | 27 | Unknown | 2024-01-17 | Unknown | Unknown | 2024-01-22 | 2024-02-13 | 1900-01-22 | 17 | 2024-02-13 | 2024-02-08 | Unknown | Unknown | 54 | 38 | 24 | 18 | 78 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 21 | 21 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-04 | -399 | -286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-05-02 | 2024-11-19 | IOU Designed & Installed | N/A | No | N/A | 1130.76 | Unknown | Unknown | Unknown | 21.03 | 1109.73 | 3981 | 814.17 | 1130.76 | -316.59 | Yes | N/A | N/A | 2024-04-24 | 2024-05-15 | 22 | 16 | 2024-05-15 | 2024-05-17 | 3 | 3 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-11-19 | 187 | 133 | Unknown | 2024-10-28 | Unknown | Unknown | 2024-11-19 | 2025-01-29 | 1900-03-12 | 52 | 2025-01-29 | 2025-01-29 | 1 | 1 | 209 | 149 | 76 | 56 | 285 | 205 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-19 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2382.07 | 743.21 | Unknown | Unknown | 7.99 | 1630.87 | 3981 | 753.18 | 2382.07 | -1628.89 | Yes | N/A | N/A | 2023-03-01 | 2023-03-17 | 17 | 13 | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 17 | 13 | 1 | 1 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-22 | -617 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | 2024-03-04 | IOU Designed & Installed | N/A | No | N/A | 11.3 | -10.07 | Unknown | Unknown | Unknown | 21.37 | Unknown | 794.16 | 11.3 | 782.86 | Yes | N/A | N/A | 2024-01-04 | 2023-12-14 | Unknown | Unknown | 2023-12-14 | 2024-01-04 | 22 | 16 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-03-04 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-03-15 | 1900-01-11 | 10 | 2024-03-15 | 2024-03-15 | 1 | 1 | 61 | 43 | 35 | 27 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-17 | 454 | 325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-06 | 2023-07-19 | 2024-03-22 | IOU Designed & Installed | N/A | No | N/A | -2118.89 | -68.27 | Unknown | Unknown | -4507 | 2456.38 | Unknown | 4506.65 | -2118.89 | 6625.54 | Yes | N/A | N/A | 2023-07-06 | 2023-07-06 | 1 | 1 | 2023-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2024-02-27 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-04-15 | 1900-01-24 | 17 | 2024-04-15 | 2024-04-15 | 1 | 1 | 1 | 1 | 35 | 25 | 36 | 26 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JULIAN | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -914 | -653 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-04-28 | 2023-05-28 | IOU Designed & Installed | N/A | No | N/A | 2155.36 | 702.3 | Unknown | 223.4 | Unknown | 1229.66 | 3981 | 792.82 | 2155.36 | -1362.54 | Yes | N/A | N/A | 2023-04-28 | 2023-04-28 | 1 | 1 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | 2023-05-28 | 31 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-05-28 | 2023-05-31 | 1900-01-03 | 3 | 2023-05-31 | 2023-05-31 | 1 | 1 | 32 | 22 | 5 | 4 | 37 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 80.1 | 80.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-09 | -67 | -48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-08-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 771.74 | -20.23 | Unknown | Unknown | Unknown | 791.97 | 7962 | 814.48 | 771.74 | 42.74 | Yes | N/A | N/A | 2023-07-05 | 2023-08-16 | 43 | 31 | 2023-08-16 | 2023-08-28 | 13 | 9 | 2023-08-28 | Unknown | Unknown | Unknown | 2023-08-16 | 2024-02-29 | 20 | 16 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-04-03 | 1 | 1 | 43 | 31 | 34 | 26 | 77 | 57 | Steps 2,3,5,6,7 | 197 | 141 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | -536 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | 2024-06-12 | IOU Designed & Installed | N/A | No | N/A | 638.24 | Unknown | Unknown | Unknown | 10.76 | 627.48 | 3941 | 1009.25 | 638.24 | 371.01 | Yes | N/A | N/A | 2024-04-16 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-05-06 | 75 | 53 | 2024-05-06 | 2025-03-06 | 305 | 219 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-06-12 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-07-23 | 1900-02-10 | 30 | 2024-07-23 | 2024-07-22 | Unknown | Unknown | 343 | 247 | 117 | 83 | 460 | 330 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | DANA POINT | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | -645 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-08-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1017.61 | -17.8 | Unknown | Unknown | Unknown | 1035.41 | 3981 | 1472.92 | 1017.61 | 455.31 | Yes | N/A | N/A | 2024-08-15 | 2024-08-15 | 1 | 1 | 2024-08-15 | 2024-08-15 | 1 | 1 | 2024-08-15 | Unknown | Unknown | Unknown | 2024-08-15 | 2024-09-24 | 41 | 29 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | Unknown | Unknown | 2024-10-31 | 2024-10-31 | 1 | 1 | 1 | 1 | 43 | 31 | 44 | 32 | Steps 2,3,5,6,7 | 40 | 28 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-30 | 299 | 214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | Unknown | 2023-10-24 | IOU Designed & Installed | N/A | No | N/A | 0.2 | -6.4 | Unknown | Unknown | Unknown | 6.6 | 3885 | 492.16 | 0.2 | 491.96 | Yes | N/A | N/A | 2023-01-10 | 2023-02-10 | 32 | 24 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-11 | 2023-10-24 | 256 | 182 | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2023-10-25 | 1900-01-01 | 2 | 2023-10-25 | 2023-10-25 | 1 | 1 | 288 | 206 | 3 | 3 | 291 | 209 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-12 | -708 | -506 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-20 | 2024-09-20 | IOU Designed & Installed | N/A | No | N/A | 34.67 | Unknown | Unknown | Unknown | Unknown | 34.67 | 3981 | 1699.98 | 34.67 | 1665.31 | Yes | N/A | N/A | 2024-09-19 | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-09-20 | 4 | 4 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-09-20 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-04 | 1900-01-14 | 11 | 2024-10-04 | 2024-10-04 | 1 | 1 | 1 | 1 | 20 | 16 | 21 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | -307 | -220 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-01 | 2023-02-09 | IOU Designed & Installed | N/A | No | N/A | 392.1 | -15.26 | Unknown | Unknown | Unknown | 407.36 | 3981 | 652.68 | 392.1 | 260.58 | Yes | N/A | N/A | 2023-02-01 | 2023-02-01 | 1 | 1 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-01 | 2023-02-09 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-02-09 | 2023-03-31 | 1900-02-19 | 37 | 2023-03-31 | 2023-03-31 | 1 | 1 | 10 | 8 | 52 | 38 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-31 | -767 | -550 | No | 2023-05-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-16 | 2023-09-19 | IOU Designed & Installed | N/A | Yes | 121 | -7.3 | -5.29 | Unknown | Unknown | Unknown | -2.01 | Unknown | 480.37 | -7.3 | 487.67 | Yes | N/A | N/A | 2023-05-02 | 2023-08-31 | 122 | 88 | 2023-08-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | 2023-09-19 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-09-25 | 1900-01-06 | 5 | 2023-09-25 | 2023-09-25 | 1 | 1 | 249 | 179 | 8 | 6 | 257 | 185 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-15 | -36 | -27 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | 2023-09-29 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 106435 | 62.92 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-08 | 2023-05-08 | 1 | 1 | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-10-11 | 1900-01-12 | 9 | 2023-10-11 | 2023-10-10 | Unknown | Unknown | 1 | 1 | 13 | 9 | 14 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-02 | -518 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2025-01-23 | IOU Designed & Installed | N/A | No | N/A | 37.99 | Unknown | Unknown | Unknown | Unknown | 37.99 | Unknown | Not available | 37.99 | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-09-23 | 28 | 20 | 2024-09-23 | 2024-12-06 | 75 | 55 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-01-23 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-01-30 | 1900-01-07 | 6 | 2025-01-30 | 2025-01-30 | 1 | 1 | 77 | 55 | 84 | 62 | 161 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-20 | -598 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-06 | 2022-06-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 817.2 | -16.81 | Unknown | Unknown | Unknown | 834.01 | Unknown | 435.18 | 817.2 | -382.02 | Yes | N/A | N/A | 2022-06-06 | 2024-03-25 | 659 | 471 | 2024-03-25 | 2024-03-26 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-05-01 | 1 | 1 | 659 | 471 | 3 | 3 | 662 | 474 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | LA MESA | N/A | 10.05 | 10.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-27 | -678 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-30 | 2024-08-30 | 2024-09-04 | IOU Designed & Installed | N/A | No | N/A | 29.57 | Unknown | Unknown | Unknown | Unknown | 29.57 | 3241 | 1550.62 | 29.57 | 1521.05 | Yes | N/A | N/A | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-09-04 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-17 | 1900-01-13 | 10 | 2024-09-17 | 2024-09-17 | 1 | 1 | 7 | 5 | 16 | 12 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-11 | -585 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-21 | 2023-10-21 | 2023-10-23 | IOU Designed & Installed | N/A | No | N/A | 307.14 | -15.35 | Unknown | Unknown | Unknown | 322.49 | 3885 | 849.93 | 307.14 | 542.79 | Yes | N/A | N/A | 2023-10-21 | 2023-10-21 | 1 | 0 | 2023-10-21 | 2023-10-21 | 1 | 0 | 2023-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-21 | 2023-10-23 | 3 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2024-01-04 | 1900-03-14 | 54 | 2024-01-04 | 2024-01-04 | 1 | 1 | 4 | 1 | 76 | 55 | 80 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-21 | -251 | -180 | No | 2024-06-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | 2024-10-31 | IOU Designed & Installed | N/A | Yes | 127 | 67.91 | Unknown | Unknown | Unknown | Unknown | 67.91 | 3241 | 1682.31 | 67.91 | 1614.4 | Yes | N/A | N/A | 2024-06-26 | 2024-10-31 | 128 | 92 | 2024-10-31 | 2024-06-26 | Unknown | Unknown | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-10-31 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-12 | 1900-01-12 | 9 | 2024-11-12 | 2024-11-12 | 1 | 1 | 256 | 184 | 14 | 10 | 270 | 194 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | -577 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 5316.44 | 480.97 | Unknown | 81.15 | 5.16 | 4749.16 | 3981 | 2389.38 | 5316.44 | -2927.06 | Yes | N/A | N/A | 2024-07-03 | 2024-08-06 | 35 | 25 | 2024-08-06 | 2024-08-08 | 3 | 3 | 2024-08-08 | Unknown | Unknown | Unknown | 2024-08-08 | 2024-09-12 | 36 | 26 | 2024-08-15 | 2024-11-07 | 85 | 61 | Unknown | 2024-11-06 | Unknown | Unknown | 2024-11-07 | 2024-11-19 | 1900-01-12 | 9 | 2024-11-19 | 2024-11-19 | 1 | 1 | 120 | 86 | 53 | 39 | 173 | 125 | Steps 2,3,5,6,7 | 28 | 20 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | 7.35 | 7.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -233 | -168 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-06-25 | IOU Designed & Installed | N/A | No | N/A | 17.17 | -13.25 | Unknown | Unknown | Unknown | 30.42 | 3981 | 895.79 | 17.17 | 878.62 | Yes | N/A | N/A | 2024-04-25 | 2024-03-11 | Unknown | Unknown | 2024-03-11 | 2024-05-03 | 54 | 40 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-06-25 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-10 | 1900-01-15 | 12 | 2024-07-10 | 2024-07-10 | 1 | 1 | 54 | 38 | 71 | 53 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-07 | -172 | -125 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | 2023-12-12 | IOU Designed & Installed | N/A | No | N/A | -12 | -9.96 | Unknown | Unknown | Unknown | -2.04 | Unknown | 158.14 | -12 | 170.14 | Yes | N/A | N/A | 2023-11-01 | 2023-11-15 | 15 | 11 | 2023-11-15 | 2023-11-16 | 2 | 2 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2023-12-12 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2023-12-18 | 1900-01-06 | 5 | 2023-12-18 | 2023-12-18 | 1 | 1 | 42 | 30 | 10 | 8 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-17 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-14 | 2024-06-19 | IOU Designed & Installed | N/A | No | N/A | -0.73 | Unknown | Unknown | Unknown | Unknown | -0.73 | Unknown | 1558.01 | -0.73 | 1558.74 | Yes | N/A | N/A | 2024-06-14 | 2024-04-23 | Unknown | Unknown | 2024-04-23 | 2024-06-14 | 53 | 39 | 2024-06-14 | Unknown | Unknown | Unknown | 2024-06-20 | 2024-06-29 | 10 | 7 | 2024-06-14 | 2024-06-19 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-09-05 | 1900-03-19 | 57 | 2024-09-05 | 2024-09-05 | 1 | 1 | 6 | 4 | 143 | 104 | 149 | 108 | Steps 2,3,5,6,7 | 15 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-24 | -604 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-13 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 673.51 | -13.34 | Unknown | Unknown | 1.49 | 685.36 | 3981 | 1962.61 | 673.51 | 1289.1 | Yes | N/A | N/A | 2025-01-13 | 2025-01-13 | 1 | 1 | 2025-01-13 | 2025-01-13 | 1 | 1 | 2025-01-13 | 2025-03-14 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-02-10 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-04-29 | 1900-03-19 | 57 | 2025-04-29 | 2025-04-29 | 1 | 1 | 91 | 67 | 81 | 59 | 172 | 126 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 84.05 | 84.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | -541 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-07-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 253.18 | -9.75 | Unknown | Unknown | Unknown | 262.93 | 3981 | 789.31 | 253.18 | 536.13 | Yes | N/A | N/A | 2023-06-30 | 2023-07-12 | 13 | 9 | 2023-07-12 | 2023-07-13 | 2 | 2 | 2023-07-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2023-09-27 | 1 | 1 | 13 | 9 | 3 | 3 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego | San Diego | 236.25 | 236.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | 291 | 210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-31 | 2022-10-31 | 2023-10-24 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 429801.5 | 117987.06 | Unknown | Unknown | -8167.82 | 319982.26 | 48222 | 223053.53 | 429801.5 | -206747.97 | Yes | N/A | N/A | 2022-10-31 | 2023-02-09 | 102 | 74 | 2023-02-09 | Unknown | Unknown | Unknown | 2023-02-24 | 2023-05-15 | 34 | 23 | 2023-03-09 | 2023-08-10 | 60 | 44 | 2023-06-23 | 2023-10-24 | 124 | 88 | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2024-02-16 | 1900-04-25 | 84 | 2024-02-16 | 2024-02-16 | 1 | 1 | 260 | 185 | 177 | 129 | 437 | 314 | Steps 2,3,5,6,7 | 115 | 81 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 88 | 88 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -409 | -294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-07-12 | 2023-12-14 | IOU Designed & Installed | N/A | No | N/A | 1346.71 | -21.65 | Unknown | Unknown | Unknown | 1368.36 | 3981 | 1102.47 | 1346.71 | -244.24 | Yes | N/A | N/A | 2023-07-12 | 2023-07-12 | 1 | 1 | 2023-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-12 | 2023-12-14 | 156 | 112 | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2023-12-18 | 1900-01-04 | 3 | 2023-12-18 | 2023-12-18 | 1 | 1 | 157 | 113 | 6 | 4 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | DEL MAR | DEL MAR, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-10 | 330 | 236 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-27 | 2023-08-16 | IOU Designed & Installed | N/A | No | N/A | 790.15 | -22.54 | Unknown | Unknown | 73.98 | 738.71 | 0 | 385.69 | 790.15 | -404.46 | Yes | N/A | N/A | 2023-06-27 | 2023-04-12 | Unknown | Unknown | 2023-04-12 | 2023-08-08 | 119 | 85 | 2023-08-08 | Unknown | Unknown | Unknown | 2024-02-20 | 2024-06-17 | 58 | 42 | 2023-08-08 | 2023-08-16 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2025-02-03 | 1901-06-21 | 384 | 2025-02-03 | 2025-02-03 | 1 | 1 | 9 | 7 | 716 | 512 | 725 | 519 | Steps 2,3,5,6,7 | 314 | 224 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-30 | 192 | 137 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-09 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | 35.02 | Unknown | Unknown | Unknown | Unknown | 35.02 | 0 | 1479.8 | 35.02 | 1444.78 | Yes | N/A | N/A | 2024-07-08 | 2023-04-19 | Unknown | Unknown | 2023-04-19 | 2024-07-09 | 448 | 320 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-09-16 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-10-08 | 1900-01-22 | 17 | 2024-10-08 | 2024-10-08 | 1 | 1 | 70 | 50 | 472 | 338 | 542 | 388 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 20.05 | 20.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-28 | -466 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-06-27 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 59.86 | Unknown | Unknown | Unknown | Unknown | 59.86 | 7962 | 1803.41 | 59.86 | 1743.55 | Yes | N/A | N/A | 2024-03-20 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2024-06-27 | 212 | 152 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-07-23 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-08-20 | 1900-01-28 | 21 | 2024-08-20 | 2024-08-19 | Unknown | Unknown | 27 | 19 | 241 | 173 | 268 | 192 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 79.05 | 79.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-28 | -594 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-24 | 2025-05-08 | IOU Designed & Installed | N/A | No | N/A | 2653.18 | 428.76 | Unknown | Unknown | 11.69 | 2212.73 | 3981 | 1898.01 | 2653.18 | -755.17 | Yes | N/A | N/A | 2025-02-18 | 2025-02-21 | 4 | 4 | 2025-02-21 | 2025-02-21 | 1 | 1 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-05-08 | 74 | 54 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-06-13 | 1900-02-05 | 27 | 2025-06-13 | 2025-06-13 | 1 | 1 | 78 | 58 | 39 | 29 | 117 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 115.05 | 115.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | -534 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | 2024-12-06 | IOU Designed & Installed | N/A | No | N/A | 1412.31 | Unknown | Unknown | Unknown | 8.71 | 1403.6 | 3981 | 2366.05 | 1412.31 | 953.74 | Yes | N/A | N/A | 2024-07-03 | 2024-07-18 | 16 | 12 | 2024-07-18 | 2024-07-18 | 1 | 1 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-12-06 | 142 | 102 | Unknown | 2024-11-27 | Unknown | Unknown | 2024-12-06 | 2024-12-13 | 1900-01-07 | 6 | 2024-12-13 | 2024-12-13 | 1 | 1 | 158 | 114 | 10 | 8 | 168 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | DANA POINT | COUNTY OF ORANGE, DANA POINT | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-02 | 681 | 488 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 6191.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-17 | 2024-12-16 | Unknown | Unknown | 2024-12-16 | 2025-01-29 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-06-10 | 59 | 41 | 2025-01-29 | 2025-06-02 | 125 | 89 | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | 2025-06-18 | Unknown | Unknown | 2025-06-18 | 2025-06-13 | Unknown | Unknown | 125 | 89 | 104 | 74 | 229 | 163 | Steps 2,3,5,6,7 | 132 | 94 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-31 | 797 | 570 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2024-01-11 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 1903.84 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-19 | 2023-05-17 | Unknown | Unknown | 2023-05-17 | 2024-01-11 | 240 | 172 | 2024-01-11 | 2024-04-09 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2025-06-03 | 421 | 301 | Unknown | 2025-03-19 | Unknown | Unknown | 2025-06-03 | 2025-06-05 | 1900-01-02 | 3 | 2025-06-05 | 2025-06-05 | 1 | 1 | 511 | 365 | 244 | 176 | 755 | 541 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | 1169 | 836 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-06 | 2023-07-11 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | 4352.71 | 1307.69 | Unknown | Unknown | -13064.85 | 16109.87 | 0 | 13657.31 | 4352.71 | 9304.6 | Yes | N/A | N/A | 2023-07-06 | 2023-08-22 | 48 | 34 | 2023-08-22 | 2024-08-01 | 346 | 248 | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-10-11 | 72 | 52 | 2024-08-01 | Unknown | Unknown | Unknown | 2024-08-07 | 2024-10-17 | 72 | 52 | 2024-10-21 | 2025-04-15 | 1900-06-25 | 127 | 2025-04-15 | 2025-04-15 | 1 | 1 | 48 | 34 | 668 | 480 | 716 | 514 | Steps 2,3,5,6,7 | 71 | 51 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 99.05 | 99.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-12 | -578 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-09-06 | 2024-10-03 | IOU Designed & Installed | N/A | No | N/A | 5.4 | Unknown | Unknown | Unknown | Unknown | 5.4 | Unknown | 1437.91 | 5.4 | 1432.51 | Yes | N/A | N/A | 2024-08-15 | 2024-07-24 | Unknown | Unknown | 2024-07-24 | 2024-09-06 | 45 | 33 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-10-03 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-15 | 1900-01-12 | 9 | 2024-10-15 | 2024-10-11 | Unknown | Unknown | 28 | 20 | 58 | 42 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-09 | 198 | 143 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-17 | 2023-01-17 | 2023-07-20 | IOU Designed & Installed | N/A | No | N/A | 884.37 | -3.41 | Unknown | Unknown | 45.13 | 842.65 | 1193 | 376.35 | 884.37 | -508.02 | Yes | N/A | N/A | 2023-01-17 | 2023-03-11 | 54 | 39 | 2023-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-11 | 2023-07-20 | 132 | 94 | Unknown | 2023-07-13 | Unknown | Unknown | 2023-07-20 | 2023-10-16 | 1900-03-29 | 63 | 2023-10-16 | 2023-07-26 | Unknown | Unknown | 186 | 133 | 89 | 63 | 275 | 196 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-03 | -204 | -147 | No | 2021-07-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-07-14 | 2022-10-04 | 2022-10-05 | IOU Designed & Installed | N/A | Yes | 812 | 678.85 | -10.57 | Unknown | Unknown | 4.05 | 685.37 | 3885 | 807.87 | 678.85 | 129.02 | Yes | N/A | N/A | 2021-07-14 | 2023-10-04 | 813 | 581 | 2023-10-04 | 2023-10-04 | 1 | 1 | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-09-07 | 2022-10-05 | Unknown | Unknown | Unknown | 2023-11-27 | Unknown | Unknown | 2022-10-05 | 2021-11-11 | Unknown | Unknown | 2021-11-11 | 2021-11-11 | Unknown | Unknown | 813 | 581 | 1 | 1 | 814 | 582 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-17 | 292 | 209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-11-30 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | 22.27 | -8.87 | Unknown | Unknown | 0.16 | 30.98 | 3981 | 943.97 | 22.27 | 921.7 | Yes | N/A | N/A | 2023-10-30 | 2023-11-30 | 32 | 24 | 2023-11-30 | 2023-11-30 | 1 | 1 | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2024-01-22 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-03-04 | 1900-02-11 | 31 | 2024-03-04 | 2024-03-04 | 1 | 1 | 86 | 62 | 45 | 33 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-06 | -583 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-15 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | 5508.62 | 1829.4 | Unknown | 237.49 | -1530 | 4971.73 | 3981 | 3032.55 | 5508.62 | -2476.07 | Yes | N/A | N/A | 2025-01-06 | 2025-01-15 | 10 | 8 | 2025-01-15 | 2025-01-15 | 1 | 1 | 2025-01-15 | 2025-01-23 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-04-24 | 100 | 72 | Unknown | 2025-04-22 | Unknown | Unknown | 2025-04-24 | 2025-05-02 | 1900-01-08 | 7 | 2025-05-02 | 2025-05-02 | 1 | 1 | 119 | 87 | 11 | 9 | 130 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-25 | -314 | -225 | No | 2024-03-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-22 | 2024-04-01 | 2024-10-21 | IOU Designed & Installed | N/A | Yes | 208 | 2026.46 | 516.88 | Unknown | Unknown | Unknown | 1509.58 | 3981 | 959.61 | 2026.46 | -1066.85 | Yes | N/A | N/A | 2024-03-22 | 2024-10-16 | 209 | 149 | 2024-10-16 | 2024-04-01 | Unknown | Unknown | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-10-21 | 204 | 146 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-11-15 | 1900-01-25 | 20 | 2024-11-15 | 2024-11-15 | 1 | 1 | 413 | 295 | 27 | 21 | 440 | 316 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-29 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-09 | 2023-09-09 | 2023-09-26 | IOU Designed & Installed | N/A | No | N/A | 1687.68 | 232.06 | Unknown | Unknown | Unknown | 1455.62 | Unknown | 928.52 | 1687.68 | -759.16 | Yes | N/A | N/A | 2023-09-09 | 2023-09-09 | 1 | 0 | 2023-09-09 | 2023-09-09 | 1 | 0 | 2023-09-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-09 | 2023-09-26 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-09-26 | 2023-10-02 | 1900-01-06 | 5 | 2023-10-02 | 2023-10-02 | 1 | 1 | 19 | 12 | 9 | 6 | 28 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-23 | -613 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-03 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 19.43 | -17.27 | Unknown | Unknown | Unknown | 36.7 | 3981 | 602.53 | 19.43 | 583.1 | Yes | N/A | N/A | 2024-05-03 | 2024-03-01 | Unknown | Unknown | 2024-03-01 | 2024-05-03 | 64 | 46 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-06-06 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-06-20 | 1900-01-14 | 11 | 2024-06-20 | 2024-06-20 | 1 | 1 | 32 | 24 | 80 | 58 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-23 | -497 | -356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-06-04 | 2024-12-06 | IOU Designed & Installed | N/A | No | N/A | 631.21 | Unknown | Unknown | Unknown | 4.22 | 626.99 | 3981 | 1229.54 | 631.21 | 598.33 | Yes | N/A | N/A | 2024-05-29 | 2024-11-04 | 160 | 114 | 2024-11-04 | 2024-11-11 | 8 | 6 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2024-12-06 | 26 | 20 | Unknown | 2024-11-27 | Unknown | Unknown | 2024-12-06 | 2024-12-13 | 1900-01-07 | 6 | 2024-12-13 | 2024-12-12 | Unknown | Unknown | 186 | 134 | 16 | 12 | 202 | 146 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-13 | -688 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-03-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.91 | -20.44 | Unknown | Unknown | Unknown | 15.53 | Unknown | 1679 | -4.91 | 1683.91 | Yes | N/A | N/A | 2025-02-28 | 2025-03-07 | 8 | 6 | 2025-03-07 | 2025-03-07 | 1 | 1 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | 2025-03-27 | 2025-03-27 | 1 | 1 | 8 | 6 | 2 | 2 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | 488 | 349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-30 | 2025-01-10 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 17190.14 | 301.8 | Unknown | Unknown | 400.58 | 16487.76 | 45752 | 14634.86 | 17190.14 | -2555.28 | Yes | N/A | N/A | 2023-05-30 | 2024-05-16 | 353 | 253 | 2024-05-16 | 2024-08-06 | 83 | 59 | 2024-05-23 | 2024-05-29 | 7 | 5 | 2024-07-04 | 2025-01-08 | 61 | 45 | 2024-08-06 | Unknown | Unknown | Unknown | 2024-10-24 | 2024-12-04 | 42 | 30 | 2025-01-10 | 2025-03-03 | 1900-02-21 | 37 | 2025-03-03 | 2025-03-03 | 1 | 1 | 360 | 258 | 240 | 172 | 600 | 430 | Steps 2,3,5,6,7 | 230 | 164 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-24 | -658 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-03 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | 663.01 | -13.33 | Unknown | Unknown | Unknown | 676.34 | 3981 | 1996.53 | 663.01 | 1333.52 | Yes | N/A | N/A | 2025-04-03 | 2025-04-03 | 1 | 1 | 2025-04-03 | 2025-04-03 | 1 | 1 | 2025-04-03 | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-28 | 25 | 17 | 2025-04-03 | 2025-05-16 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-06-04 | 1900-01-19 | 14 | 2025-06-04 | 2025-06-04 | 1 | 1 | 45 | 33 | 47 | 33 | 92 | 66 | Steps 2,3,5,6,7 | 25 | 17 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 40367 | 40367 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-03-07 | 358 | 257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 68.46 | Unknown | Unknown | Unknown | Unknown | 68.46 | 3981 | 1435.75 | 68.46 | 1367.29 | Yes | N/A | N/A | 2024-05-20 | 2024-04-05 | Unknown | Unknown | 2024-04-05 | 2024-05-21 | 47 | 33 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | 2025-02-27 | 2025-02-28 | 2 | 2 | 0 | 0 | 49 | 35 | 49 | 35 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | 148 | 148 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | 219 | 158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-09-13 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 59601.25 | 14609.13 | Unknown | Unknown | -18168.65 | 63160.77 | 81582.93 | 54315.96 | 59601.25 | -5285.29 | Yes | N/A | N/A | 2023-07-12 | 2023-06-20 | Unknown | Unknown | 2023-06-20 | 2023-12-06 | 170 | 122 | 2023-07-12 | 2023-11-21 | 2 | 0 | 2023-12-06 | 2024-05-15 | 21 | 7 | 2023-12-06 | Unknown | Unknown | Unknown | 2024-01-18 | 2024-08-01 | 197 | 141 | 2024-08-28 | 2024-10-11 | 1900-02-13 | 33 | 2024-10-11 | 2024-10-11 | 1 | 1 | 2 | 0 | 434 | 304 | 436 | 304 | Steps 2,3,5,6,7 | 308 | 220 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-10 | 417 | 300 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | 2024-06-14 | IOU Designed & Installed | N/A | No | N/A | 2563.66 | 248.74 | Unknown | 63.72 | 134.22 | 2116.98 | 3981 | 1043.56 | 2563.66 | -1520.1 | Yes | N/A | N/A | 2023-09-19 | 2023-10-10 | 22 | 16 | 2023-10-10 | 2023-10-10 | 1 | 1 | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2024-06-14 | 249 | 179 | Unknown | 2024-08-20 | Unknown | Unknown | 2024-06-14 | 2024-09-28 | 1900-04-16 | 76 | 2024-09-28 | 2024-08-30 | Unknown | Unknown | 271 | 195 | 108 | 77 | 379 | 272 | Steps 2,3,5,6,7 | 67 | 47 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-07 | -24 | -17 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-08-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1508.42 | -75.47 | Unknown | Unknown | Unknown | 1583.89 | Unknown | 1266.37 | 1508.42 | -242.05 | Yes | N/A | N/A | 2023-07-10 | 2023-08-10 | 32 | 24 | 2023-08-10 | 2023-08-16 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-08-18 | 9 | 7 | 2023-08-16 | 2024-07-22 | 342 | 244 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 374 | 268 | 17 | 13 | 391 | 281 | Steps 2,3,5,6,7 | 2 | 2 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Marcos | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | -323 | -232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-03-03 | 2025-03-26 | IOU Designed & Installed | N/A | No | N/A | -2912.95 | 930.28 | Unknown | 166.61 | -4405 | 395.16 | Unknown | 4405.45 | -2912.95 | 7318.4 | Yes | N/A | N/A | 2025-02-26 | 2025-02-26 | 1 | 1 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-03-26 | 1899-12-31 | 1 | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-30 | -554 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | 2025-03-19 | IOU Designed & Installed | N/A | No | N/A | -589.09 | -22.4 | Unknown | Unknown | -1173.28 | 606.59 | Unknown | 1056.03 | -589.09 | 1645.12 | Yes | N/A | N/A | 2024-11-05 | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2024-11-05 | 28 | 20 | 2024-11-05 | 2025-01-14 | 71 | 51 | 2025-01-14 | 2025-01-17 | 4 | 4 | 2024-11-05 | 2025-03-19 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-03-26 | 1900-01-07 | 6 | 2025-03-26 | 2025-03-25 | Unknown | Unknown | 206 | 148 | 40 | 30 | 246 | 178 | Steps 2,3,5,6,7 | 73 | 53 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-16 | -527 | -377 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-12-27 | 2024-01-10 | IOU Designed & Installed | N/A | No | N/A | -8.09 | -6.38 | Unknown | Unknown | Unknown | -1.71 | 3981 | 916.32 | -8.09 | 924.41 | Yes | N/A | N/A | 2023-11-29 | 2023-12-27 | 29 | 21 | 2023-12-27 | 2023-12-27 | 1 | 1 | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2024-01-10 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-03-07 | 1900-02-26 | 42 | 2024-03-07 | 2024-03-07 | 1 | 1 | 44 | 32 | 60 | 44 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-09 | -541 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-22 | 2024-03-29 | IOU Designed & Installed | N/A | No | N/A | 1645.21 | 513.24 | Unknown | 10.9 | Unknown | 1121.07 | Unknown | 1021.96 | 1645.21 | -623.25 | Yes | N/A | N/A | 2024-03-04 | 2024-03-22 | 19 | 15 | 2024-03-22 | 2024-03-22 | 1 | 1 | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-03-29 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-05-17 | 1900-02-18 | 36 | 2024-05-17 | 2024-05-17 | 1 | 1 | 27 | 21 | 52 | 38 | 79 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | -207 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | 2024-02-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1107.73 | 2555.55 | Unknown | 339.72 | -2969 | 1181.46 | Unknown | 2969.22 | 1107.73 | 1861.49 | Yes | N/A | N/A | 2024-02-27 | 2024-02-27 | 1 | 1 | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-15 | -103 | -74 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 11757.09 | 272.1 | Unknown | Unknown | -491.92 | 11976.91 | Unknown | 2363.27 | 11757.09 | -9393.82 | Yes | N/A | N/A | 2023-12-05 | 2023-12-05 | 1 | 1 | 2023-12-05 | 2023-12-29 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | Unknown | 2024-09-03 | Unknown | Unknown | 2024-09-03 | 2024-09-03 | 1 | 1 | 1 | 1 | 26 | 20 | 27 | 21 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-08 | 386 | 277 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | 2024-05-02 | 2025-05-28 | IOU Designed & Installed | N/A | No | N/A | 6.66 | Unknown | Unknown | Unknown | Unknown | 6.66 | 0 | 513.9 | 6.66 | 507.24 | Yes | N/A | N/A | 2024-04-26 | 2024-05-02 | 7 | 5 | 2024-05-02 | 2024-05-02 | 1 | 1 | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2025-05-28 | 392 | 280 | Unknown | 2025-05-12 | Unknown | Unknown | 2025-05-28 | 2025-05-29 | 1900-01-01 | 2 | 2025-05-29 | 2025-05-29 | 1 | 1 | 399 | 285 | 4 | 4 | 403 | 289 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 88.05 | 88.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-08 | -567 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | 2023-10-03 | IOU Designed & Installed | N/A | No | N/A | 741.46 | -12.35 | Unknown | Unknown | Unknown | 753.81 | 3981 | 692.53 | 741.46 | -48.93 | Yes | N/A | N/A | 2023-09-11 | 2023-07-28 | Unknown | Unknown | 2023-07-28 | 2023-09-12 | 47 | 33 | 2023-09-12 | Unknown | Unknown | Unknown | 2023-09-22 | 2023-10-04 | 13 | 9 | 2023-09-12 | 2023-10-03 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-10-19 | 1900-01-16 | 13 | 2023-10-19 | 2023-10-19 | 1 | 1 | 22 | 16 | 78 | 56 | 100 | 72 | Steps 2,3,5,6,7 | 22 | 16 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-16 | -276 | -198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | 2024-02-01 | IOU Designed & Installed | N/A | No | N/A | 4961.7 | 1513.48 | Unknown | 408.04 | Unknown | 3040.18 | 11943 | 1274.35 | 4961.7 | -3687.35 | Yes | N/A | N/A | 2023-11-28 | 2023-11-28 | 1 | 1 | 2023-11-28 | 2023-11-28 | 1 | 1 | 2023-11-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2024-02-01 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-02-14 | 1900-01-13 | 10 | 2024-02-14 | 2024-02-14 | 1 | 1 | 67 | 49 | 16 | 12 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-04 | -13 | -10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-08-13 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | 3423.79 | 697.71 | Unknown | 68.04 | Unknown | 2658.04 | Unknown | 1133.08 | 3423.79 | -2290.71 | Yes | N/A | N/A | 2024-05-16 | 2024-05-16 | 1 | 1 | 2024-05-16 | 2025-01-28 | 258 | 184 | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2025-01-28 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-19 | 1899-12-31 | 1 | 2025-02-19 | 2025-02-19 | 1 | 1 | 1 | 1 | 291 | 209 | 292 | 210 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 91 | 91 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-22 | -47 | -35 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-19 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | -1715.28 | -10.58 | Unknown | Unknown | -2362 | 657.3 | Unknown | 2361.56 | -1715.28 | 4076.84 | Yes | N/A | N/A | 2024-09-18 | 2024-09-20 | 3 | 3 | 2024-09-20 | 2024-09-20 | 1 | 1 | 2024-09-20 | 2024-10-24 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2025-01-15 | 84 | 60 | Unknown | 2024-12-05 | Unknown | Unknown | 2025-01-15 | 2025-02-03 | 1900-01-19 | 14 | 2025-02-03 | 2025-02-03 | 1 | 1 | 122 | 88 | 22 | 16 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-14 | -129 | -94 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 563.32 | -10.51 | Unknown | Unknown | Unknown | 573.83 | 7962 | 3246.07 | 563.32 | 2682.75 | Yes | N/A | N/A | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-04-25 | 2024-06-11 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-05-31 | 31 | 23 | 2024-06-11 | 2024-09-19 | 101 | 73 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | 2024-11-06 | 2024-11-05 | Unknown | Unknown | 102 | 74 | 79 | 57 | 181 | 131 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-04 | 97 | 70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-05 | 2023-05-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 453.13 | -3.93 | Unknown | Unknown | Unknown | 457.06 | 3241 | 790.64 | 453.13 | 337.51 | Yes | N/A | N/A | 2023-05-05 | 2023-05-05 | 1 | 1 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | Unknown | Unknown | 2023-06-09 | 2023-06-09 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-09 | -676 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-29 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | 45.41 | -0.94 | Unknown | Unknown | Unknown | 46.35 | 3981 | 1600.18 | 45.41 | 1554.77 | Yes | N/A | N/A | 2025-04-29 | 2025-04-29 | 1 | 1 | 2025-04-29 | 2025-04-30 | 2 | 2 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-05-20 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-06-02 | 1900-01-13 | 10 | 2025-06-02 | 2025-06-02 | 1 | 1 | 23 | 17 | 17 | 13 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-01 | 639 | 458 | No | 2023-08-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-11-09 | Unknown | IOU Designed & Installed | N/A | Yes | 562 | Unknown |  | Unknown | Unknown | Unknown | Unknown | 7866 | 1754.85 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-23 | 2025-03-07 | 563 | 403 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | Unknown | 2025-05-02 | Unknown | Unknown | 2025-05-02 | 2025-05-01 | Unknown | Unknown | 563 | 403 | 0 | 0 | 563 | 403 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -320 | -229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-02-27 | 2024-01-30 | IOU Designed & Installed | N/A | No | N/A | 9182.35 | 1398.38 | Unknown | Unknown | 94.8 | 7689.17 | 310964 | 8402.2 | 9182.35 | -780.15 | Yes | N/A | N/A | 2023-01-31 | 2023-02-27 | 28 | 20 | 2023-02-27 | 2023-03-27 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | 2023-04-06 | 16 | 12 | 2023-03-27 | 2958465 | Unknown | Unknown | Unknown | 2024-01-30 | Unknown | Unknown | 2024-01-30 | 2024-02-15 | 1900-01-16 | 13 | 2024-02-15 | 2024-02-15 | 1 | 1 | 28 | 20 | 63 | 47 | 91 | 67 | Steps 2,3,5,6,7 | 10 | 8 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | -623 | -446 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-12-01 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 488.08 | -13.77 | Unknown | Unknown | Unknown | 501.85 | 3885 | 515.81 | 488.08 | 27.73 | Yes | N/A | N/A | 2023-11-27 | 2023-12-01 | 5 | 5 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2023-12-04 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2024-03-14 | 1900-04-11 | 74 | 2024-03-14 | 2024-03-14 | 1 | 1 | 9 | 7 | 103 | 75 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-28 | -693 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-09 | 2025-05-09 | 2025-05-27 | IOU Designed & Installed | N/A | No | N/A | 442.8 | -8.91 | Unknown | Unknown | Unknown | 451.71 | 3981 | 1088.61 | 442.8 | 645.81 | Yes | N/A | N/A | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | 2025-05-09 | 1 | 1 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-27 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | 2025-06-04 | 1900-01-08 | 7 | 2025-06-04 | 2025-06-04 | 1 | 1 | 20 | 14 | 11 | 9 | 31 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 69615 | 69615 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-11-17 | -52 | -37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-08-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1858.92 | -78.73 | Unknown | Unknown | 417.24 | 1520.41 | 4862 | 1384.68 | 1858.92 | -474.24 | Yes | N/A | N/A | 2023-07-19 | 2023-02-22 | Unknown | Unknown | 2023-02-22 | 2023-08-16 | 176 | 126 | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-08-17 | 17 | 13 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-09-26 | 1 | 1 | 0 | 0 | 194 | 140 | 194 | 140 | Steps 2,3,5,6,7 | 1 | 1 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-25 | 172 | 125 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | 2024-02-27 | IOU Designed & Installed | N/A | No | N/A | 7.18 | -6.4 | Unknown | Unknown | Unknown | 13.58 | 3941 | 990.84 | 7.18 | 983.66 | Yes | N/A | N/A | 2023-10-09 | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-10-09 | 49 | 35 | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2024-02-27 | 142 | 102 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-15 | 1900-01-17 | 14 | 2024-03-15 | 2024-03-15 | 1 | 1 | 142 | 102 | 68 | 50 | 210 | 152 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 179.35 | 179.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | -282 | -203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2023-10-24 | 2024-10-04 | IOU Designed & Installed | N/A | No | N/A | 552.51 | -9.64 | Unknown | Unknown | Unknown | 562.15 | 0 | 1000.14 | 552.51 | 447.63 | Yes | N/A | N/A | 2023-10-24 | 2023-07-24 | Unknown | Unknown | 2023-07-24 | 2024-04-22 | 274 | 196 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-10-04 | 166 | 120 | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2024-10-23 | 1900-01-19 | 14 | 2024-10-23 | 2024-10-23 | 1 | 1 | 166 | 120 | 295 | 211 | 461 | 331 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO MISSION VIEJO | N/A | 553.5 | 553.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | 168 | 121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-05-10 | IOU Designed & Installed | N/A | No | N/A | 1202.42 | 306.13 | Unknown | 212.21 | Unknown | 684.08 | 4798 | 598.04 | 1202.42 | -604.38 | Yes | N/A | N/A | 2024-04-25 | 2024-04-17 | Unknown | Unknown | 2024-04-17 | 2024-05-10 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-04-10 | Unknown | Unknown | Unknown | 2024-05-09 | Unknown | Unknown | 2024-05-10 | 2024-05-17 | 1900-01-07 | 6 | 2024-05-17 | 2024-05-16 | Unknown | Unknown | 0 | 0 | 32 | 24 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-26 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | 2024-12-26 | IOU Designed & Installed | N/A | No | N/A | 1780.76 | 374.1 | Unknown | Unknown | Unknown | 1406.66 | Unknown | 1713.69 | 1780.76 | -67.07 | Yes | N/A | N/A | 2024-10-14 | 2024-11-18 | 36 | 26 | 2024-11-18 | 2024-11-22 | 5 | 5 | 2024-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2024-12-26 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-02-03 | 1900-02-08 | 28 | 2025-02-03 | 2025-02-03 | 1 | 1 | 71 | 51 | 46 | 34 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | Escondido | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-27 | -328 | -235 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | -1009.87 | 2158.5 | Unknown | Unknown | -4472 | 1303.63 | Unknown | 4471.94 | -1009.87 | 5481.81 | Yes | N/A | N/A | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-04 | 1899-12-31 | 1 | 2023-12-04 | 2023-12-04 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | -675 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | 2024-06-26 | IOU Designed & Installed | N/A | No | N/A | 3655.8 | 690.49 | Unknown | 29.93 | Unknown | 2935.38 | 3981 | 1538.16 | 3655.8 | -2117.64 | Yes | N/A | N/A | 2024-06-06 | 2024-06-06 | 1 | 1 | 2024-06-06 | 2024-06-06 | 1 | 1 | 2024-06-06 | Unknown | Unknown | Unknown | 2024-06-06 | 2024-06-26 | 21 | 15 | 2024-06-06 | 2024-06-26 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-07-23 | 1900-01-27 | 20 | 2024-07-23 | 2024-07-23 | 1 | 1 | 22 | 16 | 51 | 37 | 73 | 53 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-29 | 33 | 24 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1485.99 | -37 | Unknown | Unknown | Unknown | 1522.99 | 11943 | 2497.85 | 1485.99 | 1011.86 | Yes | N/A | N/A | 2024-02-08 | 2024-02-12 | 5 | 3 | 2024-02-12 | 2024-03-08 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-12 | 27 | 19 | 2024-03-08 | 2024-04-16 | 40 | 28 | Unknown | 2024-05-15 | Unknown | Unknown | Unknown | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-07-01 | Unknown | Unknown | 45 | 31 | 53 | 39 | 98 | 70 | Steps 2,3,5,6,7 | 96 | 68 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | -71 | -52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 829.41 | -15.79 | Unknown | Unknown | 1.16 | 844.04 | 7962 | 1633.95 | 829.41 | 804.54 | Yes | N/A | N/A | 2024-09-24 | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-10-29 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-10-24 | 31 | 23 | 2024-10-29 | 2024-10-31 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | 2025-01-10 | 2025-01-09 | Unknown | Unknown | 3 | 3 | 86 | 62 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | -164 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 10101.52 | -16.72 | Unknown | Unknown | 385.66 | 9732.58 | 3941 | 1025.75 | 10101.52 | -9075.77 | Yes | N/A | N/A | 2024-03-12 | 2024-05-29 | 79 | 57 | 2024-05-29 | 2025-02-26 | 274 | 196 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-07-11 | 44 | 32 | 2025-02-26 | 2024-10-30 | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | 2024-10-31 | 2025-03-19 | 1900-05-19 | 100 | 2025-03-19 | 2025-03-18 | Unknown | Unknown | 79 | 57 | 458 | 328 | 537 | 385 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-03 | -172 | -125 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5.87 | -5.19 | Unknown | Unknown | Unknown | 11.06 | 3981 | 1622.99 | 5.87 | 1617.12 | Yes | N/A | N/A | 2024-03-15 | 2024-03-17 | 3 | 1 | 2024-03-17 | 2024-03-21 | 5 | 4 | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 3 | 1 | 6 | 5 | 9 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-23 | -359 | -258 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2023-10-24 | 2023-10-26 | IOU Designed & Installed | N/A | No | N/A | 683.65 | 113.75 | Unknown | 58.96 | Unknown | 510.94 | 3981 | 771.82 | 683.65 | 88.17 | Yes | N/A | N/A | 2023-10-24 | 2023-10-24 | 1 | 1 | 2023-10-24 | 2023-10-24 | 1 | 1 | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2023-10-26 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2023-10-30 | 1900-01-04 | 3 | 2023-10-30 | 2023-10-30 | 1 | 1 | 4 | 4 | 7 | 5 | 11 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-07-10 | 1466 | 1047 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | -872.37 | 1376.79 | Unknown | 62.93 | -2946 | 633.91 | Unknown | 2620.75 | -872.37 | 3493.12 | Yes | N/A | N/A | 2024-03-12 | 2024-03-29 | 18 | 14 | 2024-03-29 | 2024-04-01 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 18 | 14 | 5 | 3 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | Lemon Grove | LEMON GROVE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-13 | -320 | -230 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-28 | 2023-08-02 | 2023-08-20 | IOU Designed & Installed | N/A | No | N/A | -142.29 | 536.99 | Unknown | 608.63 | -2300 | 1012.09 | Unknown | 2300.12 | -142.29 | 2442.41 | Yes | N/A | N/A | 2023-07-28 | 2023-07-31 | 4 | 2 | 2023-07-31 | 2023-08-16 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | 2023-09-28 | 58 | 42 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-20 | 2023-08-28 | 1900-01-08 | 6 | 2023-08-28 | 2023-08-28 | 1 | 1 | 4 | 2 | 85 | 62 | 89 | 64 | Steps 2,3,5,6,7 | 43 | 31 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-17 | -251 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2024-01-22 | 2024-05-10 | IOU Designed & Installed | N/A | No | N/A | 16.4 | -14.58 | Unknown | Unknown | Unknown | 30.98 | 3981 | 961.25 | 16.4 | 944.85 | Yes | N/A | N/A | 2023-11-16 | 2023-08-19 | Unknown | Unknown | 2023-08-19 | 2024-01-22 | 157 | 111 | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-05-10 | 110 | 80 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-07-09 | 1900-03-01 | 43 | 2024-07-09 | 2024-07-09 | 1 | 1 | 110 | 80 | 219 | 155 | 329 | 235 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-08 | -303 | -218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-15 | 2024-11-26 | IOU Designed & Installed | N/A | No | N/A | 6975.8 | 3914.19 | Unknown | 1037.85 | Unknown | 2023.76 | 3241 | 1066.51 | 6975.8 | -5909.29 | Yes | N/A | N/A | 2024-10-15 | 2024-11-07 | 24 | 18 | 2024-11-07 | 2024-11-07 | 1 | 1 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-11-26 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2024-12-09 | 1900-01-13 | 10 | 2024-12-09 | 2024-12-09 | 1 | 1 | 44 | 32 | 16 | 12 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-08 | -76 | -55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-09 | 2023-01-09 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 1785.14 | Unknown | Unknown | Unknown | -426.3 | 2211.44 | 0 | 520 | 1785.14 | -1265.14 | Yes | N/A | N/A | 2023-01-09 | 2023-02-02 | 25 | 19 | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | 2024-07-09 | 421 | 301 | Unknown | 2024-06-12 | Unknown | Unknown | 2024-07-09 | 2024-07-24 | 1900-01-15 | 12 | 2024-07-24 | 2024-07-24 | 1 | 1 | 446 | 320 | 17 | 13 | 463 | 333 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-03 | 20 | 15 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | 2024-11-20 | IOU Designed & Installed | N/A | No | N/A | 4101.87 | Unknown | Unknown | Unknown | Unknown | 4101.87 | Unknown | 4981.59 | 4101.87 | 879.72 | Yes | N/A | N/A | 2024-10-01 | 2024-10-08 | 8 | 6 | 2024-10-08 | 2024-10-11 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | 2024-11-20 | 2025-01-23 | 1900-03-05 | 47 | 2025-01-23 | 2025-01-23 | 1 | 1 | 8 | 6 | 70 | 52 | 78 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | 114 | 114 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-14 | 312 | 224 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 460.21 | -9.25 | Unknown | Unknown | Unknown | 469.46 | 3981 | 1970.66 | 460.21 | 1510.45 | Yes | N/A | N/A | 2023-12-11 | 2023-12-12 | 2 | 2 | 2023-12-12 | 2023-12-28 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2023-12-21 | 10 | 8 | 2023-12-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | 2025-05-22 | 2025-05-22 | 1 | 1 | 2 | 2 | 28 | 22 | 30 | 24 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-18 | -368 | -263 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-31 | 2022-10-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 920 | -12.85 | Unknown | Unknown | -656.64 | 1589.49 | Unknown | 703.93 | 920 | -216.07 | Yes | N/A | N/A | 2022-10-31 | 2023-03-08 | 129 | 93 | 2023-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | Unknown | Unknown | Unknown | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2023-08-16 | 1 | 1 | 129 | 93 | 1 | 1 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | -598 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-26 | 2025-03-20 | IOU Designed & Installed | N/A | No | N/A | 1538.59 | Unknown | Unknown | Unknown | 5.66 | 1532.93 | 3981 | 1226.81 | 1538.59 | -311.78 | Yes | N/A | N/A | 2025-02-20 | 2025-03-17 | 26 | 18 | 2025-03-17 | 2025-03-17 | 1 | 1 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-03-20 | 4 | 4 | Unknown | 2025-06-06 | Unknown | Unknown | 2025-03-20 | 2025-06-18 | 1900-03-31 | 65 | 2025-06-18 | 2025-06-18 | 1 | 1 | 30 | 22 | 93 | 67 | 123 | 89 | Steps 2,3,5,6,7 | 78 | 56 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 1067 | 1067 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-04-12 | 460 | 329 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-09 | 2022-05-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 732.47 | 5096.26 | Unknown | 1025.69 | -8267 | 2877.52 | 0 | 8266.81 | 732.47 | 7534.34 | Yes | N/A | N/A | 2022-05-09 | 2023-03-08 | 304 | 218 | 2023-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 304 | 218 | 1 | 1 | 305 | 219 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -611 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.53 | -10.44 | Unknown | Unknown | Unknown | 6.91 | Unknown | 364.52 | -3.53 | 368.05 | Yes | N/A | N/A | 2023-03-30 | 2023-03-30 | 1 | 1 | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | Unknown | Unknown | 2023-06-01 | 2023-06-01 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-12 | -253 | -182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 24.14 | Unknown | Unknown | Unknown | Unknown | 24.14 | 3981 | 1109.39 | 24.14 | 1085.25 | Yes | N/A | N/A | 2023-09-21 | 2024-06-05 | 259 | 185 | 2024-06-05 | 2024-06-13 | 9 | 7 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | 2024-10-02 | 2024-10-02 | 1 | 1 | 259 | 185 | 10 | 8 | 269 | 193 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-16 | -363 | -260 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-16 | 2025-06-16 | 2025-06-17 | IOU Designed & Installed | N/A | No | N/A | 961.35 | Unknown | Unknown | Unknown | Unknown | 961.35 | Unknown | 1422.11 | 961.35 | 460.76 | Yes | N/A | N/A | 2025-06-16 | 2025-06-16 | 1 | 1 | 2025-06-16 | 2025-06-16 | 1 | 1 | 2025-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-06-17 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-06-18 | 1900-01-01 | 2 | 2025-06-18 | 2025-06-18 | 1 | 1 | 3 | 3 | 4 | 4 | 7 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-18 | -481 | -344 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-01-31 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | 43.16 | -5.04 | Unknown | Unknown | 9.13 | 39.07 | 3981 | 533.2 | 43.16 | 490.04 | Yes | N/A | N/A | 2023-01-31 | 2023-02-15 | 16 | 12 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | 2023-07-17 | 153 | 109 | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-07-26 | 1900-01-09 | 8 | 2023-07-26 | 2023-07-26 | 1 | 1 | 169 | 121 | 11 | 9 | 180 | 130 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-21 | -232 | -167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-08 | 2024-03-21 | IOU Designed & Installed | N/A | No | N/A | -6.76 | -5.47 | Unknown | Unknown | Unknown | -1.29 | 3981 | 663.73 | -6.76 | 670.49 | Yes | N/A | N/A | 2024-01-08 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2024-01-08 | 41 | 29 | 2024-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-03-21 | 74 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-04-03 | 1900-01-13 | 10 | 2024-04-03 | 2024-04-03 | 1 | 1 | 74 | 54 | 56 | 40 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-12 | -232 | -166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2024-01-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 519.02 | -24.09 | Unknown | Unknown | 0.37 | 542.74 | 7962 | 1134.23 | 519.02 | 615.21 | Yes | N/A | N/A | 2023-12-19 | 2023-12-19 | 1 | 1 | 2023-12-19 | 2024-02-01 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | 2024-01-29 | 13 | 9 | 2024-02-01 | 2024-02-12 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-02-23 | Unknown | Unknown | 13 | 9 | 58 | 42 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-02 | -92 | -67 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | 2024-01-29 | IOU Designed & Installed | N/A | No | N/A | 10.63 | -12.83 | Unknown | Unknown | Unknown | 23.46 | 3981 | 697.12 | 10.63 | 686.49 | Yes | N/A | N/A | 2024-01-29 | 2024-01-29 | 1 | 1 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-01-29 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-01-31 | 1900-01-02 | 3 | 2024-01-31 | 2024-01-31 | 1 | 1 | 2 | 2 | 4 | 4 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-22 | 125 | 90 | No | 2022-10-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-27 | 2022-10-27 | Unknown | IOU Designed & Installed | N/A | Yes | 357 | 734.04 | -14.51 | Unknown | Unknown | 10.87 | 737.68 | 3885 | 597.16 | 734.04 | -136.88 | Yes | N/A | N/A | 2022-10-27 | 2023-10-18 | 357 | 255 | 2023-10-18 | 2023-10-19 | 2 | 2 | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-11-04 | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | Unknown | Unknown | Unknown | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-01-25 | 1 | 1 | 357 | 255 | 3 | 3 | 360 | 258 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 603.05 | 603.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | -109 | -78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-03-30 | 2024-09-15 | IOU Designed & Installed | N/A | No | N/A | 2423.13 | 643.74 | Unknown | 285.36 | Unknown | 1494.03 | 3981 | 711.75 | 2423.13 | -1711.38 | Yes | N/A | N/A | 2023-03-07 | 2023-03-30 | 24 | 18 | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | 2024-09-15 | 536 | 382 | Unknown | Unknown | Unknown | Unknown | 2024-09-15 | 2024-09-18 | 1900-01-03 | 3 | 2024-09-18 | 2024-09-18 | 1 | 1 | 560 | 400 | 5 | 4 | 565 | 404 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-25 | 352 | 253 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-10 | 2024-12-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1795.24 | 621.4 | Unknown | 127.85 | -731 | 1776.99 | Unknown | 586.01 | 1795.24 | -1209.23 | Yes | N/A | N/A | 2024-12-10 | 2024-12-10 | 1 | 1 | 2024-12-10 | 2025-01-22 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-01-02 | 8 | 6 | 2025-01-22 | 2025-02-28 | 38 | 28 | Unknown | 2025-01-29 | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | 2025-03-12 | 2025-03-12 | 1 | 1 | 39 | 29 | 53 | 39 | 92 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 70 | 70 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | -535 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-08 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 1105.21 | Unknown | Unknown | Unknown | 9.8 | 1095.41 | 3981 | 790.36 | 1105.21 | -314.85 | Yes | N/A | N/A | 2024-03-08 | 2024-01-19 | Unknown | Unknown | 2024-01-19 | 2024-03-18 | 60 | 42 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | 2024-07-25 | 130 | 94 | Unknown | 2024-07-19 | Unknown | Unknown | 2024-07-25 | 2024-07-30 | 1900-01-05 | 4 | 2024-07-30 | 2024-07-30 | 1 | 1 | 130 | 94 | 67 | 47 | 197 | 141 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-08 | 519 | 372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-03 | 2024-07-19 | IOU Designed & Installed | N/A | No | N/A | 23.41 | Unknown | Unknown | Unknown | Unknown | 23.41 | 7962 | 742.24 | 23.41 | 718.83 | Yes | N/A | N/A | 2024-04-02 | 2024-04-02 | 1 | 1 | 2024-04-02 | 2024-04-02 | 1 | 1 | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-07-19 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-08-09 | 1900-01-21 | 16 | 2024-08-09 | 2024-08-08 | Unknown | Unknown | 109 | 79 | 23 | 17 | 132 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-24 | -660 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-29 | 2023-08-03 | IOU Designed & Installed | N/A | No | N/A | -9.78 | -7.09 | Unknown | Unknown | Unknown | -2.69 | 3981 | 465.44 | -9.78 | 475.22 | Yes | N/A | N/A | 2023-06-19 | 2023-06-29 | 11 | 9 | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | 2023-08-03 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-08-03 | 2023-08-03 | 1899-12-31 | 1 | 2023-08-03 | 2023-08-03 | 1 | 1 | 47 | 35 | 3 | 3 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-11 | -609 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-28 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 614.19 | -12.33 | Unknown | Unknown | Unknown | 626.52 | Unknown | 2035.16 | 614.19 | 1420.97 | Yes | N/A | N/A | 2025-01-02 | 2025-01-21 | 20 | 14 | 2025-01-21 | 2025-01-28 | 8 | 6 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-03-18 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-04-11 | 1900-01-24 | 19 | 2025-04-11 | 2025-04-11 | 1 | 1 | 70 | 50 | 34 | 26 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 228.05 | 228.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-10 | -400 | -286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-02 | 2023-11-28 | IOU Designed & Installed | N/A | No | N/A | 1106.17 | -21.99 | Unknown | Unknown | 16.79 | 1111.37 | 3981 | 629.85 | 1106.17 | -476.32 | Yes | N/A | N/A | 2023-08-02 | 2023-08-07 | 6 | 4 | 2023-08-07 | 2023-08-26 | 20 | 15 | 2023-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-26 | 2023-11-28 | 95 | 67 | Unknown | 2023-11-15 | Unknown | Unknown | 2023-11-28 | 2023-12-20 | 1900-01-22 | 17 | 2023-12-20 | 2024-04-05 | 108 | 78 | 101 | 71 | 151 | 110 | 252 | 181 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-14 | -374 | -268 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2024-01-08 | 2024-02-01 | IOU Designed & Installed | N/A | No | N/A | 385.64 | -18.33 | Unknown | Unknown | Unknown | 403.97 | 3981 | 840.76 | 385.64 | 455.12 | Yes | N/A | N/A | 2023-10-16 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2024-01-09 | 180 | 128 | 2024-01-09 | Unknown | Unknown | Unknown | 2024-05-10 | 2024-05-28 | 19 | 13 | 2024-01-08 | 2024-02-01 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-06-05 | 1900-05-05 | 90 | 2024-06-05 | 2024-06-05 | 1 | 1 | 25 | 19 | 326 | 232 | 351 | 251 | Steps 2,3,5,6,7 | 141 | 101 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 1092 | 1092 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-01-24 | -106 | -77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 28.08 | -2.55 | Unknown | Unknown | 1.05 | 29.58 | 3981 | 2299.18 | 28.08 | 2271.1 | Yes | N/A | N/A | 2024-04-11 | 2024-05-10 | 30 | 22 | 2024-05-10 | 2024-05-10 | 1 | 1 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | 2024-10-10 | 2024-10-10 | 1 | 1 | 30 | 22 | 2 | 2 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 91.05 | 91.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-04 | -369 | -264 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 458.64 | Unknown | Unknown | Unknown | 16.34 | 442.3 | 3961 | 1096.01 | 458.64 | 637.37 | Yes | N/A | N/A | 2024-06-12 | 2024-07-09 | 28 | 20 | 2024-07-09 | 2024-07-12 | 4 | 4 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | 2025-05-01 | 2025-04-30 | Unknown | Unknown | 28 | 20 | 4 | 4 | 32 | 24 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | 308 | 221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1394.39 | -12.02 | Unknown | Unknown | -2042 | 659.63 | Unknown | 1781.03 | -1394.39 | 3175.42 | Yes | N/A | N/A | 2024-08-16 | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-10-29 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-26 | 34 | 24 | 2024-10-29 | 2024-11-04 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | Unknown | Unknown | 2024-12-04 | 2024-12-05 | 2 | 2 | 7 | 5 | 118 | 84 | 125 | 89 | Steps 2,3,5,6,7 | 28 | 20 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-14 | -366 | -263 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3074.49 | 1006.87 | Unknown | 112.25 | 142.79 | 1812.58 | Unknown | 683.72 | 3074.49 | -2390.77 | Yes | N/A | N/A | 2023-03-14 | 2023-03-14 | 1 | 1 | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | 2025-01-21 | 2023-03-14 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-04 | -611 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-17 | 2025-05-13 | IOU Designed & Installed | N/A | No | N/A | 1185.22 | 303.12 | Unknown | Unknown | Unknown | 882.1 | 3981 | 1329.87 | 1185.22 | 144.65 | Yes | N/A | N/A | 2025-03-05 | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-03-17 | 28 | 20 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-05-13 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | 2025-06-03 | 1900-01-21 | 16 | 2025-06-03 | 2025-06-03 | 1 | 1 | 58 | 42 | 51 | 37 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-17 | -125 | -90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-22 | 2023-11-22 | 2024-01-23 | IOU Designed & Installed | N/A | No | N/A | -11.13 | -9.02 | Unknown | Unknown | Unknown | -2.11 | Unknown | 513.31 | -11.13 | 524.44 | Yes | N/A | N/A | 2023-11-22 | 2023-11-22 | 1 | 1 | 2023-11-22 | 2023-11-22 | 1 | 1 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2024-01-23 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-03-14 | 1900-02-20 | 38 | 2024-03-14 | 2024-03-14 | 1 | 1 | 64 | 46 | 54 | 40 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-27 | 670 | 479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-08 | 2022-07-08 | 2025-03-13 | IOU Designed & Installed | N/A | No | N/A | 14799.69 | 3049.58 | Unknown | 757 | -564.46 | 11557.57 | 3981 | 1144.95 | 14799.69 | -13654.74 | Yes | N/A | N/A | 2022-07-08 | 2023-01-31 | 208 | 148 | 2023-01-31 | 2023-09-19 | 232 | 166 | 2023-08-21 | 2023-08-21 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | 2025-03-13 | 2025-03-27 | 1900-01-14 | 11 | 2025-03-27 | 2025-03-27 | 1 | 1 | 209 | 149 | 248 | 178 | 457 | 327 | Steps 2,3,5,6,7 | 29 | 21 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -673 | -482 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | Unknown | 2024-05-22 | IOU Designed & Installed | N/A | No | N/A | 410.16 | -8.63 | Unknown | Unknown | Unknown | 418.79 | 3981 | 1607.63 | 410.16 | 1197.47 | Yes | N/A | N/A | 2024-05-21 | 2024-05-21 | 1 | 1 | 2024-05-21 | 2024-05-21 | 1 | 1 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2024-05-22 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-07-11 | 1900-02-19 | 37 | 2024-07-11 | 2024-07-11 | 1 | 1 | 3 | 3 | 53 | 39 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-03 | -692 | -495 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | Unknown | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | 5.27 | Unknown | Unknown | Unknown | Unknown | 5.27 | 3981 | 1503.32 | 5.27 | 1498.05 | Yes | N/A | N/A | 2024-08-07 | 2024-08-07 | 1 | 1 | 2024-08-07 | 2024-08-07 | 1 | 1 | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-09-03 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-09-10 | 1900-01-07 | 6 | 2024-09-10 | 2024-09-10 | 1 | 1 | 29 | 21 | 10 | 8 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | Rancho Santa Fe | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-19 | -330 | -237 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-29 | 2023-10-21 | IOU Designed & Installed | N/A | No | N/A | -845.24 | 940.21 | Unknown | 80.15 | -2386 | 520.4 | Unknown | 2385.8 | -845.24 | 3231.04 | Yes | N/A | N/A | 2023-09-25 | 2023-09-25 | 1 | 1 | 2023-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-21 | 2023-10-25 | 1900-01-04 | 3 | 2023-10-25 | 2023-10-25 | 1 | 1 | 1 | 1 | 6 | 4 | 7 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-02 | -366 | -262 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | 2024-12-19 | IOU Designed & Installed | N/A | No | N/A | 12.66 | Unknown | Unknown | Unknown | 1.32 | 11.34 | Unknown | 1680.74 | 12.66 | 1668.08 | Yes | N/A | N/A | 2024-12-03 | 2024-11-22 | Unknown | Unknown | 2024-11-22 | 2024-12-03 | 12 | 8 | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2024-12-19 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-05-01 | 1900-05-13 | 96 | 2025-05-01 | 2025-05-01 | 1 | 1 | 17 | 13 | 147 | 105 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-08 | -689 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-16 | 2024-11-16 | 2024-11-20 | IOU Designed & Installed | N/A | No | N/A | 1614.69 | -31.79 | Unknown | Unknown | Unknown | 1646.48 | 3981 | 1748.75 | 1614.69 | 134.06 | Yes | N/A | N/A | 2024-11-16 | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-11-16 | 5 | 4 | 2024-11-16 | Unknown | Unknown | Unknown | 2024-11-16 | 2024-12-19 | 34 | 24 | 2024-11-16 | 2024-11-20 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2024-12-19 | 1900-01-29 | 22 | 2024-12-19 | 2024-12-19 | 1 | 1 | 5 | 3 | 70 | 51 | 75 | 54 | Steps 2,3,5,6,7 | 33 | 23 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-21 | -170 | -123 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | 2023-12-17 | IOU Designed & Installed | N/A | No | N/A | 884.35 | 302.11 | Unknown | 294.8 | Unknown | 287.44 | Unknown | 807.54 | 884.35 | -76.81 | Yes | N/A | N/A | 2023-12-04 | 2023-12-12 | 9 | 7 | 2023-12-12 | 2023-12-12 | 1 | 1 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2023-12-17 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-12-17 | 2024-01-03 | 1900-01-17 | 13 | 2024-01-03 | 2024-01-03 | 1 | 1 | 15 | 11 | 20 | 15 | 35 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | -522 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-31 | 2024-12-06 | IOU Designed & Installed | N/A | No | N/A | 5.51 | Unknown | Unknown | Unknown | Unknown | 5.51 | 3981 | 1050.75 | 5.51 | 1045.24 | Yes | N/A | N/A | 2024-07-29 | 2024-06-25 | Unknown | Unknown | 2024-06-25 | 2024-07-31 | 37 | 27 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-12-06 | 129 | 93 | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-01-07 | 1900-02-01 | 23 | 2025-01-07 | 2025-01-06 | Unknown | Unknown | 129 | 93 | 70 | 50 | 199 | 143 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | -697 | -500 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 624.39 | -11.7 | Unknown | Unknown | Unknown | 636.09 | 3981 | 1411.72 | 624.39 | 787.33 | Yes | N/A | N/A | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-03 | 8 | 6 | 2024-08-27 | 2024-09-09 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2024-09-16 | 1900-01-07 | 6 | 2024-09-16 | 2024-09-16 | 1 | 1 | 15 | 11 | 18 | 14 | 33 | 25 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | -527 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-16 | 2025-03-19 | IOU Designed & Installed | N/A | No | N/A | 3493.72 | 503.06 | Unknown | 80.67 | Unknown | 2909.99 | Unknown | 2053.67 | 3493.72 | -1440.05 | Yes | N/A | N/A | 2025-01-07 | 2025-01-16 | 10 | 8 | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-03-19 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-04-07 | 1900-01-19 | 14 | 2025-04-07 | 2025-04-07 | 1 | 1 | 73 | 53 | 22 | 16 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | -486 | -348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 845.15 | -5.49 | Unknown | Unknown | 19.5 | 831.14 | 3941 | 1239.77 | 845.15 | 394.62 | Yes | N/A | N/A | 2024-09-19 | 2024-08-22 | Unknown | Unknown | 2024-08-22 | 2024-10-15 | 55 | 39 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2025-04-02 | 170 | 122 | Unknown | 2025-03-19 | Unknown | Unknown | 2025-04-02 | 2025-04-16 | 1900-01-14 | 11 | 2025-04-16 | 2025-04-16 | 1 | 1 | 170 | 122 | 71 | 51 | 241 | 173 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 599 | 430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 7372.28 | 1136.52 | Unknown | 121.28 | -3895 | 10009.48 | Unknown | 2292.06 | 7372.28 | -5080.22 | Yes | N/A | N/A | 2024-10-22 | 2024-10-24 | 3 | 3 | 2024-10-24 | 2024-10-29 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-11-04 | 7 | 5 | Unknown | 2024-11-07 | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-08 | Unknown | Unknown | 10 | 8 | 6 | 4 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-19 | 71 | 52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | 2024-02-15 | IOU Designed & Installed | N/A | No | N/A | 502.76 | -5.82 | Unknown | Unknown | 15.97 | 492.61 | 3662 | 375.85 | 502.76 | -126.91 | Yes | N/A | N/A | 2023-12-19 | 2023-12-18 | Unknown | Unknown | 2023-12-18 | 2023-12-21 | 4 | 4 | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-02-15 | 57 | 41 | Unknown | 2024-02-05 | Unknown | Unknown | 2024-02-15 | 2024-03-15 | 1900-01-29 | 22 | 2024-03-15 | 2024-02-28 | Unknown | Unknown | 57 | 41 | 34 | 26 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | 83 | 60 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-05-03 | 2025-04-17 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 1592.12 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-24 | 2024-05-01 | 8 | 6 | 2024-05-01 | 2024-12-31 | 245 | 175 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-04-02 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-05-19 | 1900-02-01 | 23 | 2025-05-19 | 2025-05-15 | Unknown | Unknown | 101 | 73 | 278 | 198 | 379 | 271 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | 806.05 | 806.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-31 | 110 | 79 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-06-03 | IOU Designed & Installed | N/A | No | N/A | -1155.25 | 292.04 | Unknown | 528.36 | -2533 | 557.35 | 3981 | 8958.19 | -1155.25 | 10113.44 | Yes | N/A | N/A | 2023-03-21 | 2023-03-21 | 1 | 1 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | 2023-06-03 | 2 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-06-03 | 2023-07-19 | 1900-02-15 | 33 | 2023-07-19 | 2023-07-19 | 1 | 1 | 3 | 2 | 48 | 34 | 51 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-23 | -416 | -299 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2716.13 | 555.99 | Unknown | 149.34 | 21.22 | 1989.58 | Unknown | 139.89 | 2716.13 | -2576.24 | Yes | N/A | N/A | 2024-05-02 | 2024-07-31 | 91 | 65 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | Unknown | Unknown | 2024-12-03 | 2024-12-03 | 1 | 1 | 91 | 65 | 1 | 1 | 92 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | -534 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1624.07 | 287.21 | Unknown | 140.05 | 25.44 | 1171.37 | Unknown | 1136.89 | 1624.07 | -487.18 | Yes | N/A | N/A | 2024-09-23 | 2024-07-12 | Unknown | Unknown | 2024-07-12 | 2024-09-26 | 77 | 55 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | 2025-01-21 | 2025-01-21 | 1 | 1 | 0 | 0 | 78 | 56 | 78 | 56 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 649 | 464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 523.97 | -56.38 | Unknown | Unknown | Unknown | 580.35 | Unknown | 142.42 | 523.97 | -381.55 | Yes | N/A | N/A | 2025-03-12 | 2025-03-12 | 1 | 1 | 2025-03-12 | 2025-03-18 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-02 | 2025-04-02 | 1 | 1 | 1 | 1 | 8 | 6 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 168 | 168 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-04 | -249 | -178 | No | 2023-07-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-11 | 2024-05-09 | IOU Designed & Installed | N/A | Yes | 195 | 1336 | 428.58 | Unknown | Unknown | 4.41 | 903.01 | Unknown | 1206.38 | 1336 | -129.62 | Yes | N/A | N/A | 2023-07-11 | 2024-01-22 | 196 | 140 | 2024-01-22 | 2023-07-11 | Unknown | Unknown | 2023-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | 2024-05-09 | 304 | 218 | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-06-28 | 1900-02-19 | 37 | 2024-06-28 | 2024-06-28 | 1 | 1 | 500 | 358 | 52 | 38 | 552 | 396 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 105.05 | 105.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-03 | -240 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-15 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 18.62 | Unknown | Unknown | Unknown | Unknown | 18.62 | 3981 | 1292.29 | 18.62 | 1273.67 | Yes | N/A | N/A | 2023-09-15 | 2023-09-15 | 1 | 1 | 2023-09-15 | 2023-09-15 | 1 | 1 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2024-10-31 | 413 | 295 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-06 | 1900-01-06 | 5 | 2024-11-06 | 2024-11-05 | Unknown | Unknown | 414 | 296 | 8 | 6 | 422 | 302 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | -596 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-10-13 | 2023-12-05 | IOU Designed & Installed | N/A | No | N/A | -14.5 | -10.96 | Unknown | Unknown | Unknown | -3.54 | Unknown | 514.57 | -14.5 | 529.07 | Yes | N/A | N/A | 2023-09-29 | 2023-10-13 | 15 | 11 | 2023-10-13 | 2023-10-13 | 1 | 1 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-12-05 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2023-12-13 | 1900-01-08 | 7 | 2023-12-13 | 2023-12-13 | 1 | 1 | 69 | 49 | 11 | 9 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-03 | 52 | 39 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1362.75 | 109.78 | Unknown | Unknown | Unknown | 1252.97 | Unknown | 873.55 | 1362.75 | -489.2 | Yes | N/A | N/A | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | 2025-01-10 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-03-26 | 71 | 51 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | 2025-04-24 | 2025-04-24 | 1 | 1 | 1 | 1 | 95 | 69 | 96 | 70 | Steps 2,3,5,6,7 | 75 | 53 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | -473 | -338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-21 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | 2292.1 | 609.18 | Unknown | Unknown | Unknown | 1682.92 | Unknown | 1684.12 | 2292.1 | -607.98 | Yes | N/A | N/A | 2024-11-21 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-11-21 | 14 | 10 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2025-05-16 | 177 | 127 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-05-21 | 1900-01-05 | 4 | 2025-05-21 | 2025-05-21 | 1 | 1 | 177 | 127 | 21 | 15 | 198 | 142 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | -219 | -158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-03 | 2024-06-11 | IOU Designed & Installed | N/A | No | N/A | 1149.52 | -42.09 | Unknown | Unknown | Unknown | 1191.61 | 3241 | 537.74 | 1149.52 | -611.78 | Yes | N/A | N/A | 2024-05-03 | 2024-05-03 | 1 | 1 | 2024-05-03 | 2024-05-03 | 1 | 1 | 2024-05-03 | Unknown | Unknown | Unknown | 2024-06-11 | 2024-06-24 | 14 | 10 | 2024-05-03 | 2024-06-11 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-07-03 | 1900-01-22 | 17 | 2024-07-03 | 2024-07-03 | 1 | 1 | 41 | 29 | 39 | 29 | 80 | 58 | Steps 2,3,5,6,7 | 52 | 36 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 63 | 63 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-06 | -682 | -489 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-10 | 2025-06-10 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1058.29 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-10 | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-06-11 | 16 | 12 | 2025-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-11 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-23 | 1900-01-12 | 9 | 2025-06-23 | 2025-06-23 | 1 | 1 | 1 | 1 | 30 | 22 | 31 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 185.1 | 185.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | -432 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-11 | 2024-03-07 | IOU Designed & Installed | N/A | No | N/A | 525.22 | -9.8 | Unknown | Unknown | 8.39 | 526.63 | 3981 | 937.82 | 525.22 | 412.6 | Yes | N/A | N/A | 2024-01-10 | 2023-11-01 | Unknown | Unknown | 2023-11-01 | 2024-02-02 | 94 | 68 | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-03-07 | 35 | 25 | Unknown | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-03-25 | 1900-01-18 | 13 | 2024-03-25 | 2024-03-25 | 1 | 1 | 35 | 25 | 114 | 82 | 149 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-23 | 426 | 305 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | Unknown | Customer elected Applicant Install | Step 2 Engineering & Design | No | N/A | 1774.45 | -16.48 | Unknown | Unknown | 15.17 | 1775.76 | 24082 | 3218.18 | 1774.45 | 1443.73 | Yes | N/A | N/A | 2023-09-12 | 2023-09-05 | Unknown | Unknown | 2023-09-05 | 2023-09-20 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | 2025-03-19 | 547 | 391 | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-03-24 | Unknown | Unknown | 547 | 391 | 16 | 12 | 563 | 403 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | -563 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-02 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | 260.39 | -12.82 | Unknown | Unknown | 7.12 | 266.09 | 3961 | 1193.44 | 260.39 | 933.05 | Yes | N/A | N/A | 2024-01-02 | 2023-10-24 | Unknown | Unknown | 2023-10-24 | 2024-01-29 | 98 | 70 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-03-14 | 46 | 34 | Unknown | 2024-03-11 | Unknown | Unknown | 2024-03-14 | 2024-04-01 | 1900-01-18 | 13 | 2024-04-01 | 2024-04-01 | 1 | 1 | 46 | 34 | 118 | 84 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-31 | 30 | 23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | 2023-11-22 | IOU Designed & Installed | N/A | No | N/A | -1884.82 | 1844.88 | Unknown | Unknown | -4454 | 724.3 | Unknown | 4454.15 | -1884.82 | 6338.97 | Yes | N/A | N/A | 2023-11-01 | 2023-11-01 | 1 | 1 | 2023-11-01 | 2023-11-30 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | Unknown | Unknown | Unknown | 2023-11-30 | 2023-11-30 | 1 | 1 | 2023-11-22 | 2023-11-30 | 1900-01-08 | 7 | 2023-11-30 | 2023-11-30 | 1 | 1 | 1 | 1 | 41 | 31 | 42 | 32 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | -660 | -473 | No | 2024-09-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-10-07 | 2024-10-07 | IOU Designed & Installed | N/A | Yes | 35 | 1064.92 | -21.16 | Unknown | Unknown | Unknown | 1086.08 | Unknown | 1730.99 | 1064.92 | 666.07 | Yes | N/A | N/A | 2024-09-11 | 2024-10-15 | 35 | 25 | 2024-10-15 | 2024-10-07 | Unknown | Unknown | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-07 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-16 | 1900-01-09 | 8 | 2024-10-16 | 2024-10-16 | 1 | 1 | 36 | 26 | 11 | 9 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 17 | 17 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-15 | -486 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-03-11 | 2024-04-03 | IOU Designed & Installed | N/A | No | N/A | -4.2 | -3.4 | Unknown | Unknown | Unknown | -0.8 | 3981 | 961.6 | -4.2 | 965.8 | Yes | N/A | N/A | 2024-02-29 | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2024-03-11 | 39 | 27 | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | 2024-04-03 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-04-16 | 1900-01-13 | 10 | 2024-04-16 | 2024-04-16 | 1 | 1 | 24 | 18 | 54 | 38 | 78 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-17 | -679 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-03-21 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | 507.56 | -10.2 | Unknown | Unknown | Unknown | 517.76 | 3981 | 1573.66 | 507.56 | 1066.1 | Yes | N/A | N/A | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-05-02 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-07 | 1900-01-05 | 4 | 2025-05-07 | 2025-05-07 | 1 | 1 | 44 | 32 | 8 | 6 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | 1015 | 726 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-10-09 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -3677.86 | 299.55 | Unknown | 96.2 | -12025 | 7951.39 | Unknown | 12024.57 | -3677.86 | 15702.43 | Yes | N/A | N/A | 2024-04-25 | 2024-05-23 | 29 | 21 | 2024-05-23 | 2024-08-14 | 84 | 60 | 2024-05-30 | 2024-06-05 | 7 | 5 | 2024-06-05 | 2024-08-19 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-11-12 | 1900-02-03 | 25 | 2024-11-12 | 2024-11-12 | 1 | 1 | 36 | 26 | 196 | 140 | 232 | 166 | Steps 2,3,5,6,7 | 76 | 54 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | -668 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-11-07 | 2024-11-08 | IOU Designed & Installed | N/A | No | N/A | 85.92 | Unknown | Unknown | Unknown | Unknown | 85.92 | 3981 | 1191.24 | 85.92 | 1105.32 | Yes | N/A | N/A | 2024-11-06 | 2024-10-21 | Unknown | Unknown | 2024-10-21 | 2024-11-07 | 18 | 14 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-11-08 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | 2024-12-18 | 1900-02-09 | 29 | 2024-12-18 | 2024-12-18 | 1 | 1 | 2 | 2 | 60 | 44 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-29 | -626 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-02-24 | 2025-04-30 | IOU Designed & Installed | N/A | No | N/A | 1824.02 | 303.12 | Unknown | 172.23 | 3.03 | 1345.64 | 3981 | 1315.73 | 1824.02 | -508.29 | Yes | N/A | N/A | 2025-02-24 | 2025-04-07 | 43 | 31 | 2025-04-07 | 2025-04-07 | 1 | 1 | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-04-30 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-05-13 | 1900-01-13 | 10 | 2025-05-13 | 2025-05-13 | 1 | 1 | 67 | 49 | 16 | 12 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | -959 | -686 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-16 | 2024-07-18 | IOU Designed & Installed | N/A | No | N/A | 28.32 | Unknown | Unknown | Unknown | Unknown | 28.32 | Unknown | 1177.81 | 28.32 | 1149.49 | Yes | N/A | N/A | 2024-05-16 | 2024-05-16 | 1 | 1 | 2024-05-16 | 2024-05-17 | 2 | 2 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-07-18 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-08-09 | 1900-01-22 | 17 | 2024-08-09 | 2024-08-09 | 1 | 1 | 64 | 46 | 26 | 20 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-17 | -469 | -336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2023-12-08 | 2024-03-27 | IOU Designed & Installed | N/A | No | N/A | 283.2 | -10.85 | Unknown | Unknown | 4.87 | 289.18 | 3961 | 925.79 | 283.2 | 642.59 | Yes | N/A | N/A | 2023-12-08 | 2024-02-13 | 68 | 48 | 2024-02-13 | 2024-02-14 | 2 | 2 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-03-27 | 43 | 31 | Unknown | 2024-03-21 | Unknown | Unknown | 2024-03-27 | 2024-04-05 | 1900-01-09 | 8 | 2024-04-05 | 2024-04-04 | Unknown | Unknown | 111 | 79 | 12 | 10 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | 125 | 125 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | -499 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2024-12-10 | IOU Designed & Installed | N/A | No | N/A | 1574.05 | Unknown | Unknown | Unknown | 30.58 | 1543.47 | 3981 | 1280.29 | 1574.05 | -293.76 | Yes | N/A | N/A | 2024-08-22 | 2024-10-03 | 43 | 31 | 2024-10-03 | 2024-10-15 | 13 | 9 | 2024-10-15 | 2024-10-28 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-12-10 | 44 | 32 | Unknown | 2024-12-04 | Unknown | Unknown | 2024-12-10 | 2025-01-13 | 1900-02-03 | 25 | 2025-01-13 | 2025-02-05 | 24 | 18 | 101 | 73 | 72 | 52 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 1788.15 | 1788.15 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-08-01 | 322 | 231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-11-06 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | 3887.33 | 1187.01 | Unknown | Unknown | -754 | 3454.32 | 3981 | 1989.9 | 3887.33 | -1897.43 | Yes | N/A | N/A | 2024-11-06 | 2024-11-07 | 2 | 2 | 2024-11-07 | 2024-11-14 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2025-06-03 | 202 | 144 | Unknown | 2025-06-06 | Unknown | Unknown | 2025-06-18 | 2025-06-23 | 1900-01-05 | 4 | 2025-06-23 | 2025-06-19 | Unknown | Unknown | 204 | 146 | 14 | 10 | 218 | 156 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | CARLSBAD | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-27 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-31 | 2024-12-06 | IOU Designed & Installed | N/A | No | N/A | 43.46 | Unknown | Unknown | Unknown | Unknown | 43.46 | 3981 | 1872.65 | 43.46 | 1829.19 | Yes | N/A | N/A | 2024-10-07 | 2024-11-06 | 31 | 23 | 2024-11-06 | 2024-11-26 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-12-06 | 30 | 22 | 2024-11-26 | 2025-02-07 | 74 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2024-12-20 | 1900-01-14 | 11 | 2024-12-20 | 2025-02-12 | 55 | 39 | 105 | 77 | 121 | 87 | 226 | 164 | Steps 2,3,5,6,7 | 10 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 27 | 27 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-08 | -147 | -106 | No | 2023-10-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-11-07 | 2023-11-30 | IOU Designed & Installed | N/A | Yes | 45 | -8.14 | -6.14 | Unknown | Unknown | Unknown | -2 | 3981 | 958.38 | -8.14 | 966.52 | Yes | N/A | N/A | 2023-10-13 | 2023-11-27 | 46 | 32 | 2023-11-27 | 2023-11-07 | Unknown | Unknown | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2023-11-30 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2023-12-14 | 1900-01-14 | 11 | 2023-12-14 | 2023-12-13 | Unknown | Unknown | 70 | 50 | 15 | 11 | 85 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | San Diego | CALTRANS-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-27 | 504 | 361 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | 2024-04-25 | IOU Designed & Installed | N/A | No | N/A | 8939.51 | 1476.14 | Unknown | Unknown | -13467.88 | 20931.25 | 0 | 16271.29 | 8939.51 | 7331.78 | Yes | N/A | N/A | 2023-03-15 | 2023-03-01 | Unknown | Unknown | 2023-03-01 | 2023-10-30 | 244 | 174 | 2023-07-25 | 2024-04-23 | 222 | 160 | 2023-08-23 | 2024-05-13 | 198 | 138 | 2023-11-03 | Unknown | Unknown | Unknown | 2023-11-03 | 2024-04-15 | 165 | 117 | 2024-04-25 | 2024-06-14 | 1900-02-19 | 37 | 2024-06-14 | 2024-06-14 | 1 | 1 | 222 | 160 | 659 | 467 | 881 | 627 | Steps 2,3,5,6,7 | 533 | 379 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | NCTD-Trolly South of 56, SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | -259 | -186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-27 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | 291.21 | Unknown | Unknown | Unknown | Unknown | 291.21 | 54899 | 81.53 | 291.21 | -209.68 | Yes | N/A | N/A | 2024-03-21 | 2024-08-08 | 141 | 101 | 2024-08-08 | 2024-08-14 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-08-26 | 37 | 25 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | 2025-06-18 | 2025-06-19 | 1900-01-01 | 2 | 2025-06-19 | 2025-06-19 | 1 | 1 | 141 | 101 | 47 | 33 | 188 | 134 | Steps 2,3,5,6,7 | 12 | 8 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -371 | -266 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-26 | 2025-05-07 | IOU Designed & Installed | N/A | No | N/A | 1008.28 | Unknown | Unknown | Unknown | Unknown | 1008.28 | 3981 | 1497.85 | 1008.28 | 489.57 | Yes | N/A | N/A | 2025-02-25 | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-02-26 | 9 | 7 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-05-07 | 71 | 51 | Unknown | 2025-05-07 | Unknown | Unknown | 2025-05-07 | 2025-05-16 | 1900-01-09 | 8 | 2025-05-16 | 2025-05-15 | Unknown | Unknown | 71 | 51 | 19 | 15 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-02 | -441 | -316 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-19 | 2024-08-20 | IOU Designed & Installed | N/A | No | N/A | 1160.87 | Unknown | Unknown | Unknown | 25.5 | 1135.37 | 3981 | 872.6 | 1160.87 | -288.27 | Yes | N/A | N/A | 2024-03-11 | 2024-04-17 | 38 | 28 | 2024-04-17 | 2024-04-17 | 1 | 1 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-08-20 | 126 | 90 | Unknown | 2024-07-16 | Unknown | Unknown | 2024-08-20 | 2024-10-18 | 1900-02-28 | 44 | 2024-10-18 | 2024-10-18 | 1 | 1 | 164 | 118 | 62 | 46 | 226 | 164 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-21 | -594 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-16 | 2023-11-17 | IOU Designed & Installed | N/A | No | N/A | 0.47 | -6.36 | Unknown | Unknown | Unknown | 6.83 | Unknown | 284.51 | 0.47 | 284.04 | Yes | N/A | N/A | 2023-11-13 | 2023-11-16 | 4 | 4 | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2023-11-17 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2023-12-05 | 1900-01-18 | 13 | 2023-12-05 | 2023-12-05 | 1 | 1 | 6 | 6 | 21 | 15 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | -681 | -488 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | 2024-10-07 | IOU Designed & Installed | N/A | No | N/A | 1424.15 | -26.75 | Unknown | Unknown | Unknown | 1450.9 | 3981 | 1509.88 | 1424.15 | 85.73 | Yes | N/A | N/A | 2024-09-25 | 2024-09-11 | Unknown | Unknown | 2024-09-11 | 2024-09-25 | 15 | 11 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-07 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-23 | 1900-01-16 | 13 | 2024-10-23 | 2024-10-23 | 1 | 1 | 13 | 9 | 33 | 25 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | -506 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-17 | 2023-01-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.23 | -5.39 | Unknown | Unknown | Unknown | -0.84 | Unknown | 98.41 | -6.23 | 104.64 | Yes | N/A | N/A | 2023-01-17 | 2023-02-03 | 18 | 14 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | Unknown | Unknown | Unknown | 2023-05-16 | Unknown | Unknown | 2023-05-16 | 2023-05-16 | 1 | 1 | 18 | 14 | 1 | 1 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-11 | -331 | -236 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-19 | 2024-06-11 | IOU Designed & Installed | N/A | No | N/A | 1432.53 | 489.8 | Unknown | Unknown | Unknown | 942.73 | 3885 | 1204.98 | 1432.53 | -227.55 | Yes | N/A | N/A | 2023-09-14 | 2023-09-19 | 6 | 4 | 2023-09-19 | 2023-09-19 | 1 | 1 | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2024-06-11 | 267 | 191 | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-06-14 | 1900-01-03 | 4 | 2024-06-14 | 2024-06-14 | 1 | 1 | 273 | 195 | 6 | 6 | 279 | 201 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-30 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-10-31 | 2024-11-11 | IOU Designed & Installed | N/A | No | N/A | 60.7 | Unknown | Unknown | Unknown | 5.56 | 55.14 | 3981 | 1609.1 | 60.7 | 1548.4 | Yes | N/A | N/A | 2024-10-24 | 2024-10-01 | Unknown | Unknown | 2024-10-01 | 2024-10-31 | 31 | 23 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-11 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2025-02-20 | 1900-04-11 | 74 | 2025-02-20 | 2025-02-20 | 1 | 1 | 12 | 8 | 134 | 98 | 146 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | Carlsbad | CARLSBAD | 306 | 306 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-11-22 | 938 | 671 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-18 | 2023-11-06 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 9803.5 | 432.5 | Unknown | 47.23 | 298.81 | 9024.96 | 10018.94 | 5058.61 | 9803.5 | -4744.89 | Yes | N/A | N/A | 2022-09-18 | 2023-09-15 | 363 | 260 | 2023-09-15 | 2023-12-18 | 95 | 67 | 2023-11-17 | 2024-05-07 | 111 | 77 | 2023-11-27 | 2024-06-03 | 85 | 60 | 2023-12-19 | Unknown | Unknown | Unknown | 2023-12-19 | 2024-05-06 | 140 | 100 | 2024-06-06 | 2024-06-17 | 1900-01-11 | 8 | 2024-06-17 | 2024-06-17 | 1 | 1 | 474 | 337 | 333 | 236 | 807 | 573 | Steps 2,3,5,6,7 | 360 | 256 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 96 | 96 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | -618 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-04-01 | 2024-05-06 | IOU Designed & Installed | N/A | No | N/A | 12.97 | -11.47 | Unknown | Unknown | Unknown | 24.44 | Unknown | 1139.67 | 12.97 | 1126.7 | Yes | N/A | N/A | 2024-03-04 | 2024-04-01 | 29 | 21 | 2024-04-01 | 2024-04-01 | 1 | 1 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-05-06 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-05-08 | 1900-01-02 | 3 | 2024-05-08 | 2024-05-08 | 1 | 1 | 64 | 46 | 5 | 5 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-03 | -209 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-06-27 | 2024-12-23 | IOU Designed & Installed | N/A | No | N/A | 24.94 | Unknown | Unknown | Unknown | Unknown | 24.94 | 3981 | 2076.27 | 24.94 | 2051.33 | Yes | N/A | N/A | 2024-05-28 | 2024-05-06 | Unknown | Unknown | 2024-05-06 | 2024-06-27 | 53 | 39 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-12-23 | 180 | 128 | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-01-06 | 1900-01-14 | 11 | 2025-01-06 | 2025-01-06 | 1 | 1 | 180 | 128 | 69 | 51 | 249 | 179 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-01 | 812 | 581 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6649.5 | 2838.2 | Unknown | 118.1 | -10931 | 1325.2 | Unknown | 10930.89 | -6649.5 | 17580.39 | Yes | N/A | N/A | 2024-03-11 | 2024-03-11 | 1 | 1 | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-05-21 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 168 | 121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-11 | 2022-11-11 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 21126.52 | 9762.84 | Unknown | Unknown | -36267.55 | 47631.23 | 0 | 37937.26 | 21126.52 | 16810.74 | Yes | N/A | N/A | 2022-11-11 | 2023-07-19 | 251 | 179 | 2023-07-19 | 2024-06-18 | 336 | 240 | 2023-08-04 | 2023-10-12 | 70 | 50 | 2023-12-29 | 2024-04-30 | 117 | 81 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | 2024-08-16 | 2024-08-16 | 1 | 1 | 321 | 229 | 454 | 322 | 775 | 551 | Steps 2,3,5,6,7 | 319 | 227 | Unknown | Unknown | Not Available | Unknown
| R15 | Both | Applicant Design | Residential | Underserved Community | SAN DIEGO | N/A | 3026.3 | 3026.3 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-06-28 | 203 | 146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-02 | 2022-08-02 | 2023-09-28 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 54024.96 | 3881.21 | Unknown | Unknown | -8645.15 | 58788.9 | 43037 | 26988.88 | 54024.96 | -27036.08 | Yes | N/A | N/A | 2022-08-02 | 2023-03-29 | 240 | 172 | 2023-03-29 | 2023-08-31 | 156 | 112 | 2023-04-06 | 2023-08-30 | 120 | 86 | 2023-08-31 | 2023-09-27 | 28 | 20 | 2023-09-06 | Unknown | Unknown | Unknown | 2023-09-06 | 2023-12-13 | 99 | 71 | 2023-09-28 | 2024-01-17 | 1900-04-21 | 80 | 2024-01-17 | 2024-01-17 | 1 | 1 | 360 | 258 | 396 | 284 | 756 | 542 | Steps 2,3,5,6,7 | 244 | 174 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-29 | 265 | 190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-01-23 | 2023-09-11 | IOU Designed & Installed | N/A | No | N/A | 1008.35 | -9.16 | Unknown | Unknown | 228.21 | 789.3 | 3981 | 960.66 | 1008.35 | -47.69 | Yes | N/A | N/A | 2023-01-23 | 2023-02-12 | 21 | 15 | 2023-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | 2023-09-11 | 209 | 149 | Unknown | 2023-08-11 | Unknown | Unknown | 2023-09-11 | 2024-10-03 | 1901-01-23 | 279 | 2024-10-03 | 2023-09-20 | Unknown | Unknown | 230 | 164 | 389 | 279 | 619 | 443 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-29 | -32 | -23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-06-28 | 2025-03-28 | IOU Designed & Installed | N/A | No | N/A | 37689.2 | 16588.88 | Unknown | 185.87 | -10568.55 | 31483 | Unknown | 10211.86 | 37689.2 | -27477.34 | Yes | N/A | N/A | 2024-06-28 | 2024-06-20 | Unknown | Unknown | 2024-06-20 | 2024-08-06 | 48 | 34 | 2024-07-24 | 2024-07-25 | 2 | 2 | 2024-07-25 | 2024-08-28 | 35 | 25 | 2024-08-06 | 2025-01-13 | 161 | 115 | Unknown | 2025-03-10 | Unknown | Unknown | 2025-03-28 | 2025-03-28 | 1899-12-31 | 1 | 2025-03-28 | 2025-03-28 | 1 | 1 | 163 | 117 | 85 | 61 | 248 | 178 | Steps 2,3,5,6,7 | 35 | 25 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-21 | -268 | -193 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-10-18 | 2023-11-13 | IOU Designed & Installed | N/A | No | N/A | -429.4 | 2127.58 | Unknown | 958.2 | -4454 | 938.82 | Unknown | 3922.45 | -429.4 | 4351.85 | Yes | N/A | N/A | 2023-10-18 | 2023-10-30 | 13 | 9 | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2023-11-27 | 1900-01-14 | 11 | 2023-11-27 | 2023-11-27 | 1 | 1 | 13 | 9 | 16 | 12 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Residential | Underserved Community | San Diego | San Diego | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-19 | 150 | 108 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-15 | 2024-11-18 | 2025-05-13 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 11139.55 | 1479.31 | Unknown | Unknown | 0.22 | 9660.02 | Unknown | 9168.32 | 11139.55 | -1971.23 | Yes | N/A | N/A | 2024-11-15 | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2025-05-01 | 218 | 156 | 2024-10-22 | 2025-04-29 | 163 | 117 | 2025-03-10 | 2025-05-06 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | 2025-06-18 | 1900-02-05 | 27 | 2025-06-18 | 2025-06-18 | 1 | 1 | 163 | 117 | 274 | 198 | 437 | 315 | Steps 2,3,5,6,7 | 241 | 173 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-09 | 90 | 65 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-22 | 2024-03-18 | IOU Designed & Installed | N/A | No | N/A | 13313 | 4152.15 | Unknown | Unknown | Unknown | 9160.85 | 14713 | 3491.94 | 13313 | -9821.06 | Yes | N/A | N/A | 2023-05-10 | 2023-05-16 | 7 | 5 | 2023-05-16 | 2023-10-24 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2024-02-15 | 115 | 83 | Unknown | 2024-03-13 | Unknown | Unknown | 2024-03-18 | 2024-04-09 | 1900-01-22 | 17 | 2024-04-09 | 2024-04-08 | Unknown | Unknown | 122 | 88 | 185 | 133 | 307 | 221 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-19 | 2024-02-12 | IOU Designed & Installed | N/A | No | N/A | 225.72 | -7.86 | Unknown | Unknown | 0.31 | 233.27 | Unknown | 782.9 | 225.72 | 557.18 | Yes | N/A | N/A | 2024-01-18 | 2023-10-27 | Unknown | Unknown | 2023-10-27 | 2024-01-19 | 85 | 61 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-02-12 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-03-15 | 1900-02-01 | 25 | 2024-03-15 | 2024-03-15 | 1 | 1 | 25 | 17 | 119 | 87 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | -505 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-11-02 | 2023-11-22 | IOU Designed & Installed | N/A | No | N/A | 409.46 | -15.81 | Unknown | Unknown | Unknown | 425.27 | 3981 | 481.24 | 409.46 | 71.78 | Yes | N/A | N/A | 2023-10-30 | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-11-02 | 81 | 59 | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2023-11-22 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2024-03-14 | 1900-04-23 | 82 | 2024-03-14 | 2024-03-14 | 1 | 1 | 21 | 15 | 196 | 142 | 217 | 157 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 72 | 72 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-03 | -289 | -208 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | 2024-03-05 | IOU Designed & Installed | N/A | No | N/A | 1611.59 | -34.67 | Unknown | Unknown | Unknown | 1646.26 | Unknown | 1183.66 | 1611.59 | -427.93 | Yes | N/A | N/A | 2024-02-06 | 2024-01-17 | Unknown | Unknown | 2024-01-17 | 2024-02-06 | 21 | 15 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-03-05 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | 2024-03-20 | 1900-01-15 | 12 | 2024-03-20 | 2024-03-20 | 1 | 1 | 29 | 21 | 38 | 28 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | -409 | -294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1.51 | Unknown | Unknown | Unknown | Unknown | 1.51 | 3981 | 192.95 | 1.51 | 191.44 | Yes | N/A | N/A | 2024-08-01 | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2024-08-23 | 45 | 33 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | 2025-05-12 | 2025-05-12 | 1 | 1 | 0 | 0 | 46 | 34 | 46 | 34 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 132 | 132 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -235 | -168 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-09-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1046.47 | -10.81 | Unknown | Unknown | Unknown | 1057.28 | 3981 | 992.83 | 1046.47 | -53.64 | Yes | N/A | N/A | 2023-08-22 | 2023-09-20 | 30 | 22 | 2023-09-20 | 2023-10-19 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2024-04-11 | 176 | 126 | Unknown | 2024-04-29 | Unknown | Unknown | Unknown | 2024-05-20 | Unknown | Unknown | 2024-05-20 | 2024-05-10 | Unknown | Unknown | 206 | 148 | 30 | 22 | 236 | 170 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -225 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-10 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 200414.25 | 34907.59 | Unknown | Unknown | -61675 | 227181.66 | 0 | 60318.97 | 200414.25 | -140095.28 | Yes | N/A | N/A | 2024-04-10 | 2024-04-17 | 8 | 6 | 2024-04-17 | 2024-06-28 | 73 | 53 | 2024-04-12 | 2024-04-23 | 12 | 8 | 2024-07-12 | 2024-11-07 | 119 | 85 | 2025-02-11 | Unknown | Unknown | Unknown | 2025-02-11 | 2025-03-26 | 44 | 32 | 2025-04-02 | 2025-05-20 | 1900-02-17 | 35 | 2025-05-20 | 2025-05-20 | 1 | 1 | 20 | 14 | 286 | 206 | 306 | 220 | Steps 2,3,5,6,7 | 77 | 55 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-04 | -177 | -128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-14 | 2023-09-25 | IOU Designed & Installed | N/A | No | N/A | -9.47 | -7.72 | Unknown | Unknown | Unknown | -1.75 | Unknown | 153.83 | -9.47 | 163.3 | Yes | N/A | N/A | 2023-08-14 | 2023-04-13 | Unknown | Unknown | 2023-04-13 | 2023-09-01 | 142 | 102 | 2023-09-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2023-09-25 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | 2023-10-10 | 1900-01-15 | 12 | 2023-10-10 | 2023-10-10 | 1 | 1 | 25 | 17 | 159 | 115 | 184 | 132 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-16 | -427 | -306 | No | 2024-05-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | 2025-01-06 | IOU Designed & Installed | N/A | Yes | 139 | 2337.01 | Unknown | Unknown | Unknown | 63.86 | 2273.15 | 3961 | 1352.76 | 2337.01 | -984.25 | Yes | N/A | N/A | 2024-05-09 | 2024-09-16 | 131 | 93 | 2024-09-16 | 2024-09-25 | 10 | 8 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2025-01-06 | 181 | 129 | Unknown | 2024-11-26 | Unknown | Unknown | 2025-01-06 | 2025-01-14 | 1900-01-08 | 7 | 2025-01-14 | 2025-01-13 | Unknown | Unknown | 312 | 222 | 19 | 15 | 331 | 237 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-22 | -335 | -240 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | 2024-02-20 | IOU Designed & Installed | N/A | No | N/A | -4297.27 | 1041.49 | Unknown | 111.88 | -5975 | 524.36 | Unknown | 5975.08 | -4297.27 | 10272.35 | Yes | N/A | N/A | 2024-02-02 | 2024-01-31 | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-02-22 | 1900-01-02 | 3 | 2024-02-22 | 2024-02-22 | 1 | 1 | 0 | 0 | 4 | 4 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-30 | -543 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-08 | 2024-01-01 | IOU Designed & Installed | N/A | No | N/A | 2943.85 | 993.3 | Unknown | 32.06 | 7.88 | 1910.61 | 3981 | 734.46 | 2943.85 | -2209.39 | Yes | N/A | N/A | 2023-11-08 | 2023-11-20 | 13 | 9 | 2023-11-20 | 2023-11-20 | 1 | 1 | 2023-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2024-01-01 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-01-01 | 2024-01-04 | 1900-01-03 | 4 | 2024-01-04 | 2024-01-04 | 1 | 1 | 56 | 40 | 6 | 6 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-25 | 16 | 13 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2024-05-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1440.94 | -0.63 | Unknown | Unknown | -1511 | 70.69 | Unknown | 1511.11 | -1440.94 | 2952.05 | Yes | N/A | N/A | 2024-05-22 | 2024-08-30 | 101 | 73 | 2024-08-30 | 2025-01-08 | 132 | 94 | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-08-09 | 31 | 23 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | Unknown | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-04-10 | 1 | 1 | 101 | 73 | 164 | 118 | 265 | 191 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-20 | 574 | 411 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-18 | 2022-10-10 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 153749.16 | 38086.59 | Unknown | 385.96 | 839.17 | 114437.44 | 55074 | 86232.87 | 153749.16 | -67516.29 | Yes | N/A | N/A | 2022-04-18 | 2023-03-21 | 338 | 242 | 2023-03-21 | 2024-04-17 | 394 | 282 | 2024-01-19 | Unknown | Unknown | Unknown | 2024-03-07 | 2024-04-10 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2025-04-08 | 351 | 251 | 2025-03-17 | 2025-05-16 | 1900-03-01 | 45 | 2025-05-16 | 2025-05-16 | 1 | 1 | 338 | 242 | 825 | 593 | 1163 | 835 | Steps 2,3,5,6,7 | 111 | 79 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-20 | -523 | -374 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-10-16 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | -9.45 | -7.68 | Unknown | Unknown | Unknown | -1.77 | Unknown | 514.57 | -9.45 | 524.02 | Yes | N/A | N/A | 2023-09-29 | 2023-10-16 | 18 | 12 | 2023-10-16 | 2023-10-16 | 1 | 1 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2024-01-22 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-02-13 | 1900-01-22 | 17 | 2024-02-13 | 2024-02-13 | 1 | 1 | 117 | 83 | 25 | 19 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-14 | -605 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-20 | 2023-11-14 | IOU Designed & Installed | N/A | No | N/A | 987.6 | 493.36 | Unknown | 173.52 | Unknown | 320.72 | Unknown | 465.44 | 987.6 | -522.16 | Yes | N/A | N/A | 2023-07-17 | 2023-07-20 | 4 | 4 | 2023-07-20 | 2023-07-20 | 1 | 1 | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-11-14 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2023-11-17 | 1900-01-03 | 4 | 2023-11-17 | 2023-11-17 | 1 | 1 | 122 | 88 | 6 | 6 | 128 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-26 | -674 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-04-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 74.68 | -1.5 | Unknown | Unknown | Unknown | 76.18 | 3981 | 2303.37 | 74.68 | 2228.69 | Yes | N/A | N/A | 2025-03-19 | 2025-03-18 | Unknown | Unknown | 2025-03-18 | 2025-04-08 | 22 | 16 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-04-23 | 1 | 1 | 0 | 0 | 23 | 17 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-19 | 2024-04-19 | 2024-04-19 | IOU Designed & Installed | N/A | No | N/A | -10.08 | -8.19 | Unknown | Unknown | Unknown | -1.89 | 3981 | 1030.98 | -10.08 | 1041.06 | Yes | N/A | N/A | 2024-04-19 | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2024-04-19 | 4 | 4 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2024-04-19 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2024-04-25 | 1900-01-06 | 5 | 2024-04-25 | 2024-04-25 | 1 | 1 | 1 | 1 | 12 | 10 | 13 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | -571 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-01-19 | 2024-03-06 | IOU Designed & Installed | N/A | No | N/A | -5.48 | -4.45 | Unknown | Unknown | Unknown | -1.03 | Unknown | 163.83 | -5.48 | 169.31 | Yes | N/A | N/A | 2024-01-19 | 2023-11-15 | Unknown | Unknown | 2023-11-15 | 2024-02-12 | 90 | 64 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-03-06 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-04-16 | 1900-02-10 | 30 | 2024-04-16 | 2024-04-16 | 1 | 1 | 24 | 18 | 133 | 95 | 157 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | -562 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | -1447.58 | -7.98 | Unknown | Unknown | -1862 | 422.4 | Unknown | 1862.24 | -1447.58 | 3309.82 | Yes | N/A | N/A | 2024-11-18 | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-11-18 | 7 | 5 | 2024-11-18 | 2024-11-22 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-02-25 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-04 | 1900-01-07 | 6 | 2025-03-04 | 2025-03-04 | 1 | 1 | 101 | 73 | 16 | 12 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-03 | -167 | -120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | 2025-05-13 | IOU Designed & Installed | N/A | No | N/A | 757.85 | -15.64 | Unknown | Unknown | Unknown | 773.49 | 0 | 679.38 | 757.85 | -78.47 | Yes | N/A | N/A | 2024-03-21 | 2024-02-05 | Unknown | Unknown | 2024-02-05 | 2024-03-21 | 46 | 34 | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2025-05-13 | 419 | 299 | Unknown | Unknown | Unknown | Unknown | 2025-05-13 | 2025-05-20 | 1900-01-07 | 6 | 2025-05-20 | 2025-05-20 | 1 | 1 | 419 | 299 | 55 | 41 | 474 | 340 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | Vista | Vista | 130.05 | 130.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | -184 | -133 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | 2024-04-04 | IOU Designed & Installed | N/A | No | N/A | 3243.65 | 656.59 | Unknown | 35.79 | Unknown | 2551.27 | Unknown | 1493.6 | 3243.65 | -1750.05 | Yes | N/A | N/A | 2024-03-20 | 2024-03-20 | 1 | 1 | 2024-03-20 | 2024-03-29 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-04-22 | 15 | 11 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-05-01 | 1900-01-27 | 20 | 2024-05-01 | 2024-05-01 | 1 | 1 | 1 | 1 | 54 | 40 | 55 | 41 | Steps 2,3,5,6,7 | 24 | 16 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | 26 | 20 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | 2023-11-07 | 2024-11-13 | IOU Designed & Installed | N/A | No | N/A | 2833.78 | Unknown | Unknown | Unknown | Unknown | 2833.78 | 34387 | 1136.36 | 2833.78 | -1697.42 | Yes | N/A | N/A | 2023-10-06 | 2023-10-19 | 14 | 10 | 2023-10-19 | 2023-11-17 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-12-27 | 1900-02-13 | 33 | 2024-12-27 | 2024-12-27 | 1 | 1 | 14 | 10 | 76 | 56 | 90 | 66 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-07 | 282 | 201 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4484.58 | 4426.04 | Unknown | 545.96 | -2778 | 2290.58 | Unknown | 2777.68 | 4484.58 | -1706.9 | Yes | N/A | N/A | 2024-03-08 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-13 | 35 | 26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-06-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 629.56 | -39.6 | Unknown | Unknown | Unknown | 669.16 | 23481 | 330.93 | 629.56 | -298.63 | Yes | N/A | N/A | 2023-03-16 | 2023-07-18 | 125 | 89 | 2023-07-18 | 2024-02-01 | 199 | 143 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | 2024-04-17 | 2024-04-17 | 1 | 1 | 125 | 89 | 200 | 144 | 325 | 233 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 321.05 | 321.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-31 | 44 | 33 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-06 | 2023-09-07 | IOU Designed & Installed | N/A | No | N/A | 1176.58 | -12.63 | Unknown | Unknown | 11.72 | 1177.49 | Unknown | 604.01 | 1176.58 | -572.57 | Yes | N/A | N/A | 2023-06-06 | 2023-06-22 | 17 | 13 | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-09-07 | 78 | 56 | Unknown | 2023-09-07 | Unknown | Unknown | 2023-09-07 | 2023-09-13 | 1900-01-06 | 5 | 2023-09-13 | 2023-09-13 | 1 | 1 | 95 | 69 | 8 | 6 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 6.35 | 6.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-04 | -471 | -338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-12 | 2024-04-12 | 2024-08-02 | IOU Designed & Installed | N/A | No | N/A | 1362.49 | 740.04 | Unknown | 123.95 | Unknown | 498.5 | 3981 | 900.34 | 1362.49 | -462.15 | Yes | N/A | N/A | 2024-04-12 | 2024-01-29 | Unknown | Unknown | 2024-01-29 | 2024-04-12 | 75 | 55 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-08-02 | 113 | 81 | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-08-20 | 1900-01-18 | 13 | 2024-08-20 | 2024-08-20 | 1 | 1 | 113 | 81 | 95 | 69 | 208 | 150 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-17 | -690 | -495 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-08-15 | 2024-08-15 | IOU Designed & Installed | N/A | No | N/A | 86.93 | Unknown | Unknown | Unknown | Unknown | 86.93 | Unknown | 1461.67 | 86.93 | 1374.74 | Yes | N/A | N/A | 2024-08-15 | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2024-08-15 | 24 | 18 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-08-15 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-08-26 | 1900-01-11 | 8 | 2024-08-26 | 2024-08-26 | 1 | 1 | 1 | 1 | 37 | 27 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 3656 | 3656 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-06-07 | 236 | 169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2024-03-21 | 2024-12-18 | IOU Designed & Installed | N/A | No | N/A | 73938.61 | 11471.32 | Unknown | Unknown | 2257.95 | 60209.34 | 61676 | 53897.22 | 73938.61 | -20041.39 | Yes | N/A | N/A | 2023-10-24 | 2024-01-19 | 88 | 64 | 2024-01-19 | 2024-09-27 | 253 | 181 | 2024-09-04 | 2024-09-19 | 3 | 3 | 2024-07-31 | 2024-10-03 | 53 | 37 | 2024-09-27 | Unknown | Unknown | Unknown | 2024-10-22 | 2024-12-09 | 49 | 35 | 2024-12-18 | 2025-01-29 | 1900-02-11 | 31 | 2025-01-29 | 2025-01-29 | 1 | 1 | 91 | 67 | 399 | 285 | 490 | 352 | Steps 2,3,5,6,7 | 79 | 57 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | -110 | -80 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-26 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 1002.75 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-24 | 2023-10-27 | Unknown | Unknown | 2023-10-27 | 2024-01-26 | 92 | 66 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2025-06-09 | 501 | 357 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-16 | 1900-01-07 | 6 | 2025-06-16 | 2025-06-16 | 1 | 1 | 501 | 357 | 101 | 73 | 602 | 430 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-09 | -658 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-14 | 2025-02-06 | IOU Designed & Installed | N/A | No | N/A | 2101.68 | 513.12 | Unknown | 74.38 | Unknown | 1514.18 | 3981 | 2121.68 | 2101.68 | 20 | Yes | N/A | N/A | 2025-01-07 | 2025-01-08 | 2 | 2 | 2025-01-08 | 2025-01-14 | 7 | 5 | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-02-06 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-19 | 1900-01-13 | 10 | 2025-02-19 | 2025-02-19 | 1 | 1 | 26 | 20 | 22 | 16 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | N/A | 171 | 171 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-11 | 642 | 459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-04 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 7129.79 | Unknown | Unknown | Unknown | -6906 | 14035.79 | 0 | 7457.2 | 7129.79 | 327.41 | Yes | N/A | N/A | 2024-12-04 | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2025-02-06 | 371 | 265 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-05-14 | 1900-03-10 | 50 | 2025-05-14 | 2025-05-14 | 1 | 1 | 0 | 0 | 442 | 316 | 442 | 316 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-28 | -492 | -351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2024-12-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 761.05 | -14.62 | Unknown | Unknown | Unknown | 775.67 | Unknown | 1932.99 | 761.05 | 1171.94 | Yes | N/A | N/A | 2024-11-08 | 2024-12-06 | 29 | 21 | 2024-12-06 | 2025-01-29 | 55 | 39 | 2025-01-28 | 2025-01-28 | 1 | 1 | 2024-12-18 | 2025-01-21 | 35 | 25 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | 2025-02-21 | 2025-02-21 | 1 | 1 | 30 | 22 | 91 | 65 | 121 | 87 | Steps 2,3,5,6,7 | 42 | 30 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-08 | -376 | -269 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 2082.73 | 241.68 | Unknown | 164.97 | 17.45 | 1658.63 | 3981 | 1404.67 | 2082.73 | -678.06 | Yes | N/A | N/A | 2023-12-19 | 2024-01-26 | 39 | 29 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-08-26 | 210 | 150 | Unknown | 2024-08-01 | Unknown | Unknown | 2024-08-26 | 2024-08-28 | 1900-01-02 | 3 | 2024-08-28 | 2024-08-28 | 1 | 1 | 249 | 179 | 4 | 4 | 253 | 183 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | -493 | -354 | No | 2024-12-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-13 | 2025-05-28 | IOU Designed & Installed | N/A | Yes | 51 | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 5170.74 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-04 | 2025-01-10 | 38 | 28 | 2025-01-10 | 2025-01-24 | 15 | 11 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-05-28 | 167 | 119 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-06-24 | 1900-01-27 | 20 | 2025-06-24 | 2025-06-24 | 1 | 1 | 205 | 147 | 44 | 32 | 249 | 179 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-10 | -633 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | 2025-03-11 | IOU Designed & Installed | N/A | No | N/A | 1515.49 | 243.28 | Unknown | Unknown | Unknown | 1272.21 | 3981 | 2015.99 | 1515.49 | 500.5 | Yes | N/A | N/A | 2025-01-07 | 2025-01-07 | 1 | 1 | 2025-01-07 | 2025-01-07 | 1 | 1 | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-03-11 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-03-17 | 1900-01-06 | 5 | 2025-03-17 | 2025-03-17 | 1 | 1 | 65 | 47 | 9 | 7 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-13 | -676 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-23 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 8.88 | Unknown | Unknown | Unknown | Unknown | 8.88 | 3981 | 1641.32 | 8.88 | 1632.44 | Yes | N/A | N/A | 2024-07-23 | 2024-06-19 | Unknown | Unknown | 2024-06-19 | 2024-07-23 | 35 | 25 | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-07-29 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-06 | 1900-01-08 | 7 | 2024-08-06 | 2024-08-06 | 1 | 1 | 7 | 5 | 45 | 33 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-20 | -484 | -347 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-06 | 2025-04-23 | IOU Designed & Installed | N/A | No | N/A | -926.73 | 1699.68 | Unknown | 251.56 | -4064 | 1186.03 | Unknown | 4063.91 | -926.73 | 4990.64 | Yes | N/A | N/A | 2025-03-06 | 2025-03-26 | 21 | 15 | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-04-23 | 1899-12-31 | 1 | 2025-04-23 | 2025-04-23 | 1 | 1 | 21 | 15 | 2 | 2 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-04 | -254 | -183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-30 | 2024-03-15 | IOU Designed & Installed | N/A | No | N/A | 5582.98 | Unknown | Unknown | Unknown | -2813 | 8395.98 | Unknown | 2391.22 | 5582.98 | -3191.76 | Yes | N/A | N/A | 2024-01-18 | 2024-01-19 | 2 | 2 | 2024-01-19 | 2024-03-08 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-03-22 | 15 | 11 | Unknown | 2024-03-13 | Unknown | Unknown | 2024-03-15 | 2024-03-25 | 1900-01-10 | 7 | 2024-03-25 | 2024-03-25 | 1 | 1 | 17 | 13 | 62 | 44 | 79 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-27 | -603 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-17 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 1152.27 | 362.52 | Unknown | Unknown | Unknown | 789.75 | Unknown | 1517.72 | 1152.27 | 365.45 | Yes | N/A | N/A | 2024-06-17 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-06-18 | 84 | 60 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-07-30 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-01 | 1900-01-02 | 3 | 2024-08-01 | 2024-08-01 | 1 | 1 | 43 | 31 | 88 | 64 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-25 | -430 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-09-19 | 2025-02-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1424.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-30 | 2024-08-08 | 10 | 8 | 2024-08-08 | 2024-09-19 | 43 | 31 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2025-02-12 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-03-24 | 1900-02-09 | 29 | 2025-03-24 | 2025-03-21 | Unknown | Unknown | 157 | 113 | 84 | 60 | 241 | 173 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-24 | -505 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-01 | 2024-09-19 | IOU Designed & Installed | N/A | No | N/A | -1108.09 | -11.59 | Unknown | Unknown | -1747 | 650.5 | Unknown | 1746.64 | -1108.09 | 2854.73 | Yes | N/A | N/A | 2024-05-01 | 2024-02-27 | Unknown | Unknown | 2024-02-27 | 2024-08-23 | 179 | 129 | 2024-08-23 | 2024-09-05 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2024-09-19 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-10-08 | 1900-01-19 | 14 | 2024-10-08 | 2024-10-07 | Unknown | Unknown | 29 | 21 | 199 | 143 | 228 | 164 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 55.2 | 55.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-06 | -535 | -384 | No | 2024-03-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | 2024-08-07 | IOU Designed & Installed | N/A | Yes | 117 | 917.78 | Unknown | Unknown | Unknown | 33.13 | 884.65 | 3961 | 1111.46 | 917.78 | 193.68 | Yes | N/A | N/A | 2024-03-20 | 2024-07-12 | 115 | 83 | 2024-07-12 | 2024-07-15 | 4 | 2 | 2024-07-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-08-07 | 115 | 83 | Unknown | 2024-08-01 | Unknown | Unknown | 2024-08-07 | 2024-08-21 | 1900-01-14 | 11 | 2024-08-21 | 2024-08-20 | Unknown | Unknown | 230 | 166 | 19 | 13 | 249 | 179 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-11-19 | -513 | -368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-12 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | 2540.59 | Unknown | Unknown | Unknown | 38.12 | 2502.47 | 3981 | 1244.98 | 2540.59 | -1295.61 | Yes | N/A | N/A | 2024-12-12 | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2024-12-19 | 29 | 21 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-06-23 | 187 | 133 | Unknown | 2025-06-06 | Unknown | Unknown | 2025-06-23 | 2025-06-24 | 1900-01-01 | 2 | 2025-06-24 | 2025-06-24 | 1 | 1 | 187 | 133 | 32 | 24 | 219 | 157 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | -320 | -229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 419.71 | -8.54 | Unknown | Unknown | Unknown | 428.25 | 54899 | 81.53 | 419.71 | -338.18 | Yes | N/A | N/A | 2024-03-21 | 2024-07-03 | 105 | 75 | 2024-07-03 | 2024-08-29 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-06-19 | 44 | 32 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | Unknown | 2025-04-19 | Unknown | Unknown | 2025-04-19 | 2025-04-19 | 1 | 0 | 105 | 75 | 103 | 74 | 208 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | Encinitas | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-16 | 141 | 102 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | 2024-11-04 | IOU Designed & Installed | N/A | No | N/A | 48816.87 | 26111.11 | Unknown | Unknown | -38922 | 61627.76 | 0 | 38925.2 | 48816.87 | -9891.67 | Yes | N/A | N/A | 2023-05-19 | 2023-09-18 | 123 | 87 | 2023-09-18 | 2024-08-05 | 323 | 231 | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | 2025-05-02 | -72 | -58 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2025-05-06 | 1900-07-02 | 132 | 2025-05-06 | 2025-05-06 | 1 | 1 | 123 | 87 | 436 | 306 | 559 | 393 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | -93 | -68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2.05 | -6.08 | Unknown | Unknown | Unknown | 4.03 | 3981 | 551.5 | -2.05 | 553.55 | Yes | N/A | N/A | 2023-02-01 | 2023-02-06 | 6 | 4 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | 6 | 4 | 1 | 1 | 7 | 5 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-10 | -497 | -356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | 2023-06-26 | 2023-10-27 | IOU Designed & Installed | N/A | No | N/A | 1153.21 | -8.31 | Unknown | Unknown | 19.94 | 1141.58 | 3981 | 481.95 | 1153.21 | -671.26 | Yes | N/A | N/A | 2023-06-26 | 2023-08-12 | 48 | 35 | 2023-08-12 | 2023-08-12 | 1 | 0 | 2023-08-12 | 2023-08-14 | 3 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2023-10-27 | 75 | 55 | Unknown | 2023-10-06 | Unknown | Unknown | 2023-10-27 | 2023-10-30 | 1900-01-03 | 2 | 2023-10-30 | 2023-10-30 | 1 | 1 | 126 | 91 | 6 | 3 | 132 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-31 | -648 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-26 | 2025-03-07 | 2025-03-27 | IOU Designed & Installed | N/A | No | N/A | 507.59 | -10.2 | Unknown | Unknown | Unknown | 517.79 | Unknown | 2301.77 | 507.59 | 1794.18 | Yes | N/A | N/A | 2025-02-26 | 2025-02-10 | Unknown | Unknown | 2025-02-10 | 2025-03-07 | 26 | 20 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-03-27 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-23 | 1900-01-27 | 20 | 2025-04-23 | 2025-04-23 | 1 | 1 | 21 | 15 | 55 | 41 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 342.7 | 342.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-14 | -213 | -154 | No | 2024-10-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-25 | 2024-10-25 | 2024-10-28 | IOU Designed & Installed | N/A | Yes | 7 | 1438.8 | -27.55 | Unknown | Unknown | Unknown | 1466.35 | 3981 | 1776.54 | 1438.8 | 337.74 | Yes | N/A | N/A | 2024-10-25 | 2024-10-21 | Unknown | Unknown | 2024-10-21 | 2024-10-25 | 5 | 5 | 2024-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2024-10-28 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2025-01-14 | 1900-03-19 | 57 | 2025-01-14 | 2025-01-13 | Unknown | Unknown | 4 | 2 | 84 | 62 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-26 | -102 | -75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-04-24 | 2023-07-21 | IOU Designed & Installed | N/A | No | N/A | -33.01 | -23.89 | Unknown | Unknown | Unknown | -9.12 | 3981 | 1890.48 | -33.01 | 1923.49 | Yes | N/A | N/A | 2023-03-30 | 2023-04-13 | 15 | 11 | 2023-04-13 | 2023-07-21 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2023-10-16 | 1900-03-28 | 62 | 2023-10-16 | 2023-10-16 | 1 | 1 | 15 | 11 | 189 | 135 | 204 | 146 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-09 | -326 | -234 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | 2025-06-17 | IOU Designed & Installed | N/A | No | N/A | 2407.58 | 615.74 | Unknown | Unknown | Unknown | 1791.84 | 3981 | 1611.88 | 2407.58 | -795.7 | Yes | N/A | N/A | 2024-10-01 | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-10-01 | 140 | 100 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2025-06-17 | 260 | 186 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-06-17 | 1899-12-31 | 1 | 2025-06-17 | 2025-06-17 | 1 | 1 | 260 | 186 | 142 | 102 | 402 | 288 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-16 | -634 | -453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-08 | 2024-11-20 | IOU Designed & Installed | N/A | No | N/A | 1965.71 | 428.3 | Unknown | Unknown | Unknown | 1537.41 | Unknown | 1563.64 | 1965.71 | -402.07 | Yes | N/A | N/A | 2024-10-07 | 2024-10-08 | 2 | 2 | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-11-20 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2024-11-20 | 1899-12-31 | 1 | 2024-11-20 | 2024-11-20 | 1 | 1 | 46 | 34 | 3 | 3 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 107 | 107 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-19 | -335 | -240 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-12 | 2024-06-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2264.45 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-12 | 2024-05-13 | 32 | 22 | 2024-05-13 | 2024-07-24 | 73 | 53 | 2024-07-24 | 2024-07-24 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | 2025-03-21 | 2025-03-21 | 1 | 1 | 33 | 23 | 74 | 54 | 107 | 77 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-08 | 120 | 87 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-11-10 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | 20739.69 | 6008.76 | Unknown | Unknown | -5187.18 | 19918.11 | 9749 | 14871.3 | 20739.69 | -5868.39 | Yes | N/A | N/A | 2023-09-27 | 2023-09-25 | Unknown | Unknown | 2023-09-25 | 2023-12-18 | 85 | 61 | 2023-10-04 | 2023-10-27 | 24 | 18 | 2023-11-27 | 2024-05-02 | 31 | 25 | 2023-12-18 | 2024-06-05 | 171 | 123 | 2023-12-29 | 2024-05-09 | 133 | 95 | 2024-05-14 | 2024-05-29 | 1900-01-15 | 12 | 2024-05-29 | 2024-06-07 | 10 | 8 | 195 | 141 | 275 | 201 | 470 | 342 | Steps 2,3,5,6,7 | 370 | 264 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-14 | -355 | -255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-15 | 2023-09-21 | IOU Designed & Installed | N/A | No | N/A | 2118.58 | 1093.12 | Unknown | 324.64 | Unknown | 700.82 | Unknown | 153.83 | 2118.58 | -1964.75 | Yes | N/A | N/A | 2023-09-15 | 2023-09-14 | Unknown | Unknown | 2023-09-14 | 2023-09-15 | 2 | 2 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2023-09-21 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2023-09-25 | 1900-01-04 | 3 | 2023-09-25 | 2023-09-25 | 1 | 1 | 7 | 5 | 8 | 6 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-06 | -261 | -188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-04 | 2024-11-13 | IOU Designed & Installed | N/A | No | N/A | 14.78 | Unknown | Unknown | Unknown | Unknown | 14.78 | 3941 | 1411.09 | 14.78 | 1396.31 | Yes | N/A | N/A | 2024-09-04 | 2024-08-14 | Unknown | Unknown | 2024-08-14 | 2024-09-04 | 22 | 16 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-11-13 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-11-18 | 1900-01-05 | 4 | 2024-11-18 | 2024-11-18 | 1 | 1 | 71 | 51 | 29 | 21 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-07 | -441 | -316 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-08-29 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 48.33 | Unknown | Unknown | Unknown | Unknown | 48.33 | 3981 | 1867.13 | 48.33 | 1818.8 | Yes | N/A | N/A | 2024-06-03 | 2024-08-06 | 65 | 47 | 2024-08-06 | 2024-09-19 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-20 | 1900-01-10 | 9 | 2025-02-20 | 2025-02-20 | 1 | 1 | 65 | 47 | 57 | 43 | 122 | 90 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | -351 | -252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2023-12-21 | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 1130.54 | 393.66 | Unknown | Unknown | Unknown | 736.88 | 3981 | 890.72 | 1130.54 | -239.82 | Yes | N/A | N/A | 2023-12-21 | 2024-01-05 | 16 | 12 | 2024-01-05 | 2024-01-09 | 5 | 3 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-08-14 | 219 | 157 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-08-16 | 1900-01-02 | 3 | 2024-08-16 | 2024-08-15 | Unknown | Unknown | 235 | 169 | 8 | 6 | 243 | 175 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-02-13 | 990 | 708 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 710.05 | -7.57 | Unknown | Unknown | Unknown | 717.62 | Unknown | 1001.8 | 710.05 | 291.75 | Yes | N/A | N/A | 2024-01-05 | 2024-02-29 | 56 | 40 | 2024-02-29 | 2024-03-01 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-02-20 | 27 | 19 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | Unknown | Unknown | 2024-10-30 | 2024-10-30 | 1 | 1 | 56 | 40 | 30 | 22 | 86 | 62 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | -604 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | 2024-06-11 | IOU Designed & Installed | N/A | No | N/A | 776.96 | 244.9 | Unknown | Unknown | Unknown | 532.06 | Unknown | Not available | 776.96 | Unknown | Yes | N/A | N/A | 2024-04-15 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-04-17 | 56 | 40 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-06-11 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-06-18 | 1900-01-07 | 6 | 2024-06-18 | 2024-06-18 | 1 | 1 | 56 | 40 | 65 | 47 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | -554 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2025-01-28 | 2025-04-03 | IOU Designed & Installed | N/A | No | N/A | 2771.29 | 770.24 | Unknown | Unknown | -801 | 2802.05 | 3981 | 2318.24 | 2771.29 | -453.05 | Yes | N/A | N/A | 2024-11-21 | 2025-01-22 | 63 | 45 | 2025-01-22 | 2025-01-28 | 7 | 5 | 2025-01-28 | 2025-02-03 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-04-03 | 60 | 44 | Unknown | 2025-03-18 | Unknown | Unknown | 2025-04-03 | 2025-04-11 | 1900-01-08 | 7 | 2025-04-11 | 2025-04-11 | 1 | 1 | 130 | 94 | 17 | 13 | 147 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-03 | -195 | -140 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 676.62 | Unknown | Unknown | Unknown | 13.21 | 663.41 | 3981 | 997.23 | 676.62 | 320.61 | Yes | N/A | N/A | 2025-01-07 | 2024-12-17 | Unknown | Unknown | 2024-12-17 | 2025-01-10 | 25 | 19 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | 2025-05-22 | 2025-05-22 | 1 | 1 | 0 | 0 | 26 | 20 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -232 | -167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 163.73 | -3.1 | Unknown | Unknown | Unknown | 166.83 | Unknown | 466.88 | 163.73 | 303.15 | Yes | N/A | N/A | 2024-04-30 | 2024-04-30 | 1 | 1 | 2024-04-30 | 2024-08-19 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-12 | 27 | 19 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | Unknown | Unknown | 2024-09-03 | 2024-09-03 | 1 | 1 | 1 | 1 | 140 | 100 | 141 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | 183 | 132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 931.88 | -5.5 | Unknown | Unknown | 9.25 | 928.13 | 7962 | 893.95 | 931.88 | -37.93 | Yes | N/A | N/A | 2024-03-15 | 2024-03-15 | 1 | 1 | 2024-03-15 | 2024-05-14 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-06-07 | 26 | 20 | 2024-05-14 | 2024-06-11 | 29 | 21 | Unknown | 2024-07-15 | Unknown | Unknown | Unknown | 2024-08-02 | Unknown | Unknown | 2024-08-02 | 2024-08-01 | Unknown | Unknown | 30 | 22 | 87 | 63 | 117 | 85 | Steps 2,3,5,6,7 | 24 | 18 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-30 | 492 | 351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6488.44 | Unknown | Unknown | Unknown | Unknown | 6488.44 | 0 | 617.1 | 6488.44 | -5871.34 | Yes | N/A | N/A | 2023-07-10 | 2023-06-02 | Unknown | Unknown | 2023-06-02 | 2023-08-22 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | Unknown | Unknown | 2025-05-05 | 2025-05-05 | 1 | 1 | 0 | 0 | 83 | 59 | 83 | 59 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 15.05 | 15.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-26 | -621 | -444 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | 2024-11-26 | IOU Designed & Installed | N/A | No | N/A | 581.94 | 196.92 | Unknown | Unknown | 1.14 | 383.88 | 3981 | 197.01 | 581.94 | -384.93 | Yes | N/A | N/A | 2024-10-16 | 2024-11-08 | 24 | 18 | 2024-11-08 | 2024-11-18 | 11 | 7 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-11-26 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2024-12-20 | 1900-01-24 | 19 | 2024-12-20 | 2024-12-13 | Unknown | Unknown | 33 | 25 | 36 | 26 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-09 | 36 | 26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 410.09 | 1926.34 | Unknown | 678.04 | -2995 | 800.71 | 0 | 2995.14 | 410.09 | 2585.05 | Yes | N/A | N/A | 2023-06-15 | 2023-07-21 | 37 | 27 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 37 | 27 | 1 | 1 | 38 | 28 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 142 | 142 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-15 | -114 | -82 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-15 | 2023-03-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1188.53 | -9.67 | Unknown | Unknown | Unknown | 1198.2 | 3885 | 480.42 | 1188.53 | -708.11 | Yes | N/A | N/A | 2021-10-15 | 2023-03-03 | 505 | 361 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | 2023-03-06 | 4 | 2 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | Unknown | Unknown | 2023-07-07 | 2023-03-23 | Unknown | Unknown | 505 | 361 | 4 | 2 | 509 | 363 | Steps 2,3,5,6,7 | 3 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-26 | -449 | -322 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-13 | 2025-03-28 | IOU Designed & Installed | N/A | No | N/A | 3534.74 | -13.37 | Unknown | Unknown | -775.21 | 4323.32 | Unknown | 1117.24 | 3534.74 | -2417.5 | Yes | N/A | N/A | 2024-09-13 | 2024-11-01 | 50 | 36 | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | 2024-12-13 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-03-28 | 1 | 1 | Unknown | 2025-02-13 | Unknown | Unknown | 2025-03-28 | 2025-04-03 | 1900-01-06 | 5 | 2025-04-03 | 2025-04-03 | 1 | 1 | 94 | 68 | 9 | 7 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-19 | -188 | -135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1.37 | -3.59 | Unknown | Unknown | Unknown | 4.96 | Unknown | 332.58 | 1.37 | 331.21 | Yes | N/A | N/A | 2023-12-19 | 2023-11-30 | Unknown | Unknown | 2023-11-30 | 2023-12-27 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 0 | 0 | 29 | 21 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-08 | -620 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-01-30 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1563.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-04-24 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-04-28 | 1900-01-04 | 3 | 2025-04-28 | 2025-04-28 | 1 | 1 | 86 | 62 | 7 | 5 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -323 | -232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1267.34 | -6.4 | Unknown | Unknown | 0.83 | 1272.91 | 8703 | 4033.43 | 1267.34 | 2766.09 | Yes | N/A | N/A | 2024-03-18 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-09-16 | 194 | 138 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2025-01-21 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | 2025-02-12 | 2025-02-11 | Unknown | Unknown | 128 | 92 | 194 | 138 | 322 | 230 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-10 | -166 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | 2023-03-14 | IOU Designed & Installed | N/A | No | N/A | -7.3 | -21.42 | Unknown | Unknown | Unknown | 14.12 | Unknown | 688.02 | -7.3 | 695.32 | Yes | N/A | N/A | 2023-03-10 | 2023-03-10 | 1 | 1 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | 2023-03-14 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-03-14 | 2023-07-28 | 1900-05-16 | 99 | 2023-07-28 | 2023-07-28 | 1 | 1 | 6 | 4 | 138 | 100 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4000 | 4000 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-07-08 | -496 | -355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 390.13 | Unknown | Unknown | Unknown | 10.29 | 379.84 | 3981 | 1090.55 | 390.13 | 700.42 | Yes | N/A | N/A | 2024-09-04 | 2024-08-20 | Unknown | Unknown | 2024-08-20 | 2024-09-10 | 22 | 16 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-02-27 | 28 | 20 | 0 | 0 | 50 | 36 | 50 | 36 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 566.05 | 566.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-23 | -159 | -114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-02-02 | 2024-03-28 | IOU Designed & Installed | N/A | No | N/A | 3012.22 | Unknown | Unknown | Unknown | Unknown | 3012.22 | Unknown | 910.29 | 3012.22 | -2101.93 | Yes | N/A | N/A | 2024-01-03 | 2024-01-03 | 1 | 1 | 2024-01-03 | 2024-03-12 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-03-04 | 21 | 14 | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-04-17 | 1900-01-20 | 15 | 2024-04-17 | 2024-04-17 | 1 | 1 | 1 | 1 | 113 | 80 | 114 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-30 | 26 | 20 | No | 2022-10-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-11 | 2022-10-17 | 2023-05-26 | IOU Designed & Installed | N/A | Yes | 171 | 379.18 | 236.04 | Unknown | Unknown | Unknown | 143.14 | 3241 | 360.12 | 379.18 | -19.06 | Yes | N/A | N/A | 2022-10-11 | 2023-04-06 | 178 | 128 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-10-17 | 2023-05-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | 2023-05-26 | 1899-12-31 | 1 | 2023-05-26 | 2023-05-26 | 1 | 1 | 178 | 128 | 2 | 2 | 180 | 130 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | 437 | 313 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-12 | 2022-12-12 | 2024-02-15 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -30946.86 | 1566.34 | Unknown | Unknown | Unknown | -32513.2 | 370014 | 41026.69 | -30946.86 | 71973.55 | Yes | N/A | N/A | 2022-12-12 | 2023-04-26 | 136 | 98 | 2023-04-26 | 2023-06-28 | 64 | 46 | 2023-04-27 | 2023-06-16 | 28 | 20 | 2023-06-28 | 2023-06-29 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | 2024-01-30 | 105 | 75 | 2024-02-15 | 2024-03-25 | 1900-02-08 | 28 | 2024-03-25 | 2024-03-13 | Unknown | Unknown | 164 | 118 | 211 | 151 | 375 | 269 | Steps 2,3,5,6,7 | 62 | 44 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | -667 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-04 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | 754.27 | Unknown | Unknown | Unknown | 5.03 | 749.24 | Unknown | 1130.51 | 754.27 | 376.24 | Yes | N/A | N/A | 2024-09-04 | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-09-11 | 22 | 16 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-10-08 | 29 | 21 | Unknown | 2024-10-04 | Unknown | Unknown | 2024-10-08 | 2024-10-15 | 1900-01-07 | 6 | 2024-10-15 | 2024-10-15 | 1 | 1 | 29 | 21 | 31 | 23 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-21 | -231 | -166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-07 | 2023-05-03 | IOU Designed & Installed | N/A | No | N/A | 836.15 | 344.6 | Unknown | Unknown | Unknown | 491.55 | Unknown | 483.84 | 836.15 | -352.31 | Yes | N/A | N/A | 2023-04-07 | 2023-04-07 | 1 | 1 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-05-03 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | 2023-05-04 | 1900-01-01 | 2 | 2023-05-04 | 2023-05-04 | 1 | 1 | 28 | 20 | 3 | 3 | 31 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-13 | -648 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-18 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 3895.38 | 1177.84 | Unknown | Unknown | Unknown | 2717.54 | 3981 | 1472.88 | 3895.38 | -2422.5 | Yes | N/A | N/A | 2024-06-18 | 2024-06-18 | 1 | 1 | 2024-06-18 | 2024-06-18 | 1 | 1 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-08-26 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-09-03 | 1900-01-08 | 7 | 2024-09-03 | 2024-09-03 | 1 | 1 | 71 | 51 | 11 | 9 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-13 | -687 | -491 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.46 | -18.67 | Unknown | Unknown | Unknown | 14.21 | 3981 | 1742.92 | -4.46 | 1747.38 | Yes | N/A | N/A | 2025-03-03 | 2025-03-03 | 1 | 1 | 2025-03-03 | 2025-03-03 | 1 | 1 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | 2025-03-28 | 2025-03-28 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 50.25 | 50.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | -189 | -136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-10-04 | 2023-12-19 | IOU Designed & Installed | N/A | No | N/A | 1055.82 | -29.63 | Unknown | Unknown | Unknown | 1085.45 | 3981 | 825.12 | 1055.82 | -230.7 | Yes | N/A | N/A | 2023-10-03 | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2023-10-04 | 50 | 36 | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | 2023-12-19 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-01-25 | 1900-02-06 | 28 | 2024-01-25 | 2024-01-25 | 1 | 1 | 77 | 55 | 89 | 65 | 166 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Santee | SANTEE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-04 | 133 | 96 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1456.73 | 2872.87 | Unknown | 510.07 | -6213 | 1373.33 | Unknown | 6213.27 | -1456.73 | 7670 | Yes | N/A | N/A | 2024-05-14 | 2024-05-14 | 1 | 1 | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-06-07 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 9 | 7 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-09 | -628 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-11-06 | 2024-11-19 | IOU Designed & Installed | N/A | No | N/A | 67.95 | Unknown | Unknown | Unknown | Unknown | 67.95 | Unknown | 1666.21 | 67.95 | 1598.26 | Yes | N/A | N/A | 2024-11-06 | 2024-09-18 | Unknown | Unknown | 2024-09-18 | 2024-11-06 | 50 | 36 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-11-19 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2024-12-20 | 1900-01-31 | 24 | 2024-12-20 | 2024-12-20 | 1 | 1 | 14 | 10 | 83 | 61 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-08 | 657 | 470 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-05 | 2025-02-21 | IOU Designed & Installed | N/A | No | N/A | 17910.34 | 722.47 | Unknown | Unknown | 6.51 | 17181.36 | Unknown | 9662.05 | 17910.34 | -8248.29 | Yes | N/A | N/A | 2024-12-04 | 2024-12-03 | Unknown | Unknown | 2024-12-03 | 2025-02-05 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-02-04 | 47 | 33 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-03-26 | 1900-02-02 | 24 | 2025-03-26 | 2025-03-26 | 1 | 1 | 0 | 0 | 147 | 105 | 147 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-15 | -461 | -330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-15 | 2024-11-15 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | 39.65 | Unknown | Unknown | Unknown | Unknown | 39.65 | 3981 | 1657.68 | 39.65 | 1618.03 | Yes | N/A | N/A | 2024-11-15 | 2024-11-07 | Unknown | Unknown | 2024-11-07 | 2024-11-16 | 10 | 7 | 2024-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-16 | 2025-03-03 | 108 | 76 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-04-11 | 1900-02-08 | 30 | 2025-04-11 | 2025-04-10 | Unknown | Unknown | 108 | 76 | 50 | 37 | 158 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | 115 | 115 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-03 | -187 | -135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 236.98 | -23.04 | Unknown | Unknown | 5.47 | 254.55 | 3981 | 900.04 | 236.98 | 663.06 | Yes | N/A | N/A | 2023-03-06 | 2023-03-07 | 2 | 2 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 172.2 | 172.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-01 | 612 | 439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2.11 | -1.86 | Unknown | Unknown | Unknown | 3.97 | 15964 | 929.3 | 2.11 | 927.19 | Yes | N/A | N/A | 2023-03-01 | 2023-03-01 | 1 | 1 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | 2024-04-08 | 2024-04-04 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | -802 | -573 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-07-21 | 2023-08-10 | IOU Designed & Installed | N/A | No | N/A | 1351.65 | -52.32 | Unknown | Unknown | 3.36 | 1400.61 | Unknown | 1204.32 | 1351.65 | -147.33 | Yes | N/A | N/A | 2023-07-07 | 2023-05-04 | Unknown | Unknown | 2023-05-04 | 2023-07-21 | 79 | 57 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2023-08-10 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-10-03 | 1900-02-23 | 39 | 2023-10-03 | 2023-09-27 | Unknown | Unknown | 21 | 15 | 134 | 96 | 155 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -85 | -62 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-05-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1037.47 | -18.97 | Unknown | Unknown | Unknown | 1056.44 | Unknown | 984.98 | 1037.47 | -52.49 | Yes | N/A | N/A | 2024-04-08 | 2024-04-08 | 1 | 1 | 2024-04-08 | 2024-06-13 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-06-20 | 24 | 18 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | Unknown | Unknown | 2024-10-16 | 2024-10-16 | 1 | 1 | 1 | 1 | 92 | 68 | 93 | 69 | Steps 2,3,5,6,7 | 7 | 5 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-02 | -592 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | 2024-08-27 | IOU Designed & Installed | N/A | No | N/A | 7.82 | Unknown | Unknown | Unknown | Unknown | 7.82 | 3961 | 192.51 | 7.82 | 184.69 | Yes | N/A | N/A | 2024-06-12 | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-07-16 | 70 | 50 | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-08-27 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-17 | 1900-01-21 | 16 | 2024-09-17 | 2024-09-17 | 1 | 1 | 43 | 31 | 93 | 67 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-10 | 623 | 446 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-15 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | 13243.15 | 3078.48 | Unknown | Unknown | -14405 | 24569.67 | Unknown | 20812.21 | 13243.15 | 7569.06 | Yes | N/A | N/A | 2023-05-03 | 2023-05-03 | 1 | 1 | 2023-05-03 | 2023-08-08 | 98 | 70 | 2023-05-24 | 2023-07-21 | 2 | 1 | 2023-05-25 | 2023-06-08 | 15 | 11 | 2023-08-09 | Unknown | Unknown | Unknown | 2023-08-09 | 2023-10-09 | 62 | 44 | 2023-10-10 | 2023-10-26 | 1900-01-16 | 13 | 2023-10-26 | 2023-10-26 | 1 | 1 | 3 | 2 | 193 | 139 | 196 | 141 | Steps 2,3,5,6,7 | 133 | 95 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | POWAY | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-11 | -260 | -187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 9740.67 | Unknown | Unknown | Unknown | 15.17 | 9725.5 | 3981 | 1675.01 | 9740.67 | -8065.66 | Yes | N/A | N/A | 2024-02-22 | 2024-04-10 | 49 | 35 | 2024-04-10 | 2024-04-10 | 1 | 1 | 2024-04-10 | 2024-12-31 | 2 | 2 | 2024-04-18 | 2025-01-07 | 54 | 38 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | Unknown | Unknown | Unknown | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-02-24 | Unknown | Unknown | 51 | 37 | 55 | 39 | 106 | 76 | Steps 2,3,5,6,7 | 529 | 377 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | -647 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | 752 | -8.96 | Unknown | Unknown | Unknown | 760.96 | 3961 | 1154.85 | 752 | 402.85 | Yes | N/A | N/A | 2024-05-09 | 2024-04-09 | Unknown | Unknown | 2024-04-09 | 2024-06-14 | 67 | 49 | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-06-17 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-06-27 | 1900-01-10 | 9 | 2024-06-27 | 2024-06-27 | 1 | 1 | 4 | 2 | 79 | 59 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-02 | -645 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-05-01 | 2025-06-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 15924 | 1224.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-04-09 | Unknown | Unknown | 2025-04-09 | 2025-05-01 | 23 | 17 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-06-25 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-06-26 | 1900-01-01 | 2 | 2025-06-26 | 2025-06-26 | 1 | 1 | 56 | 40 | 26 | 20 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-01 | 790 | 565 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2024-04-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1003.47 | -22.83 | Unknown | Unknown | Unknown | 1026.3 | 0 | 605.53 | 1003.47 | -397.94 | Yes | N/A | N/A | 2023-04-10 | 2023-03-06 | Unknown | Unknown | 2023-03-06 | 2024-05-08 | 430 | 308 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | 2024-05-30 | 2024-05-30 | 1 | 1 | 0 | 0 | 431 | 309 | 431 | 309 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-16 | -109 | -79 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-17 | 2025-04-15 | IOU Designed & Installed | N/A | No | N/A | 1605.15 | 124.03 | Unknown | Unknown | -1163.19 | 2644.31 | Unknown | 1221.52 | 1605.15 | -383.63 | Yes | N/A | N/A | 2024-09-17 | 2024-10-08 | 22 | 16 | 2024-10-08 | 2024-10-24 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-22 | 15 | 11 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | 2025-04-15 | 2025-04-29 | 1900-01-14 | 11 | 2025-04-29 | 2025-04-29 | 1 | 1 | 22 | 16 | 48 | 36 | 70 | 52 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | -555 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.05 | -5.23 | Unknown | Unknown | Unknown | -0.82 | 3981 | 153.75 | -6.05 | 159.8 | Yes | N/A | N/A | 2023-04-10 | 2023-04-27 | 18 | 14 | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 18 | 14 | 1 | 1 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | -74 | -55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2180.51 | 1709.14 | Unknown | Unknown | -4697 | 807.35 | Unknown | 4696.94 | -2180.51 | 6877.45 | Yes | N/A | N/A | 2023-09-27 | 2023-11-22 | 57 | 41 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 57 | 41 | 1 | 1 | 58 | 42 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 341.35 | 341.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-13 | 209 | 150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-07-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 690.55 | -23.93 | Unknown | Unknown | 75.78 | 638.7 | 27867 | 712.36 | 690.55 | 21.81 | Yes | N/A | N/A | 2023-07-07 | 2023-06-27 | Unknown | Unknown | 2023-06-27 | 2023-07-26 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-08-11 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | Unknown | Unknown | 2024-02-01 | 2023-08-10 | Unknown | Unknown | 17 | 13 | 30 | 22 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | -80 | -59 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | 2024-02-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 986.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-27 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 375.5 | 375.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-29 | 180 | 129 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-13 | 2023-04-13 | IOU Designed & Installed | N/A | No | N/A | 5294.08 | -23.1 | Unknown | Unknown | Unknown | 5317.18 | 3981 | 5314.89 | 5294.08 | 20.81 | Yes | N/A | N/A | 2023-02-08 | 2023-02-13 | 6 | 4 | 2023-02-13 | 2023-03-07 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | 2023-12-26 | 1900-09-14 | 184 | 2023-12-26 | 2023-12-26 | 1 | 1 | 6 | 4 | 282 | 202 | 288 | 206 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | 296 | 213 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-02 | 2025-01-13 | IOU Designed & Installed | N/A | No | N/A | 11538.01 | 552.5 | Unknown | 36.65 | Unknown | 10948.86 | 334394 | 6063.05 | 11538.01 | -5474.96 | Yes | N/A | N/A | 2024-05-02 | 2024-04-23 | Unknown | Unknown | 2024-04-23 | 2024-05-07 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2025-01-06 | 245 | 175 | Unknown | 2025-01-03 | Unknown | Unknown | 2025-01-13 | 2025-01-28 | 1900-01-15 | 12 | 2025-01-28 | 2025-01-22 | Unknown | Unknown | 245 | 175 | 31 | 23 | 276 | 198 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-14 | -653 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2024-05-24 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 26.49 | Unknown | Unknown | Unknown | Unknown | 26.49 | Unknown | 1465.28 | 26.49 | 1438.79 | Yes | N/A | N/A | 2024-05-24 | 2024-05-24 | 1 | 1 | 2024-05-24 | 2024-05-24 | 1 | 1 | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-07-11 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-07-30 | 1900-01-19 | 14 | 2024-07-30 | 2024-07-30 | 1 | 1 | 50 | 36 | 22 | 16 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 577.1 | 577.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-15 | 24 | 17 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-07-13 | 2023-07-28 | IOU Designed & Installed | N/A | No | N/A | -2.2 | -4.3 | Unknown | Unknown | Unknown | 2.1 | 3981 | 573.59 | -2.2 | 575.79 | Yes | N/A | N/A | 2023-07-13 | 2023-07-07 | Unknown | Unknown | 2023-07-07 | 2023-07-13 | 7 | 5 | 2023-07-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | 2023-07-28 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2023-08-14 | 1900-01-17 | 12 | 2023-08-14 | 2023-08-08 | Unknown | Unknown | 16 | 12 | 25 | 17 | 41 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-09 | -465 | -332 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-10 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | 62.22 | -1.25 | Unknown | Unknown | Unknown | 63.47 | Unknown | 1971.08 | 62.22 | 1908.86 | Yes | N/A | N/A | 2025-04-04 | 2025-03-31 | Unknown | Unknown | 2025-03-31 | 2025-04-10 | 11 | 9 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-04-22 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-01 | 1900-01-09 | 8 | 2025-05-01 | 2025-05-01 | 1 | 1 | 13 | 9 | 22 | 18 | 35 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-28 | -562 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | 2024-02-12 | IOU Designed & Installed | N/A | No | N/A | 20.2 | -18.05 | Unknown | Unknown | Unknown | 38.25 | Unknown | 297.38 | 20.2 | 277.18 | Yes | N/A | N/A | 2023-12-19 | 2023-10-10 | Unknown | Unknown | 2023-10-10 | 2024-02-01 | 115 | 83 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-02-12 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-03-15 | 1900-02-01 | 25 | 2024-03-15 | 2024-03-15 | 1 | 1 | 12 | 8 | 149 | 109 | 161 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 219.75 | 219.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 181 | 130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-09-22 | IOU Designed & Installed | N/A | No | N/A | 425.98 | -13.24 | Unknown | Unknown | 17.47 | 421.75 | 3241 | 387.3 | 425.98 | -38.68 | Yes | N/A | N/A | 2023-04-11 | 2023-05-05 | 25 | 19 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | 2023-09-22 | 148 | 106 | Unknown | 2023-09-21 | Unknown | Unknown | 2023-09-22 | 2023-09-29 | 1900-01-07 | 6 | 2023-09-29 | 2023-09-29 | 1 | 1 | 173 | 125 | 9 | 7 | 182 | 132 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-14 | -351 | -252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | -37.9 | -30.77 | Unknown | Unknown | Unknown | -7.13 | Unknown | 600.48 | -37.9 | 638.38 | Yes | N/A | N/A | 2023-08-07 | 2023-08-07 | 1 | 1 | 2023-08-07 | 2023-08-07 | 1 | 1 | 2023-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | Unknown | Unknown | 2024-03-28 | 2024-03-28 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-16 | -429 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-04-05 | 2024-06-12 | IOU Designed & Installed | N/A | No | N/A | 1329.63 | 428.58 | Unknown | Unknown | Unknown | 901.05 | 3981 | 947.82 | 1329.63 | -381.81 | Yes | N/A | N/A | 2024-03-07 | 2024-04-05 | 30 | 22 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-06-12 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-06-13 | 1900-01-01 | 2 | 2024-06-13 | 2024-06-13 | 1 | 1 | 99 | 71 | 3 | 3 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-15 | -697 | -498 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-02 | 2024-12-04 | IOU Designed & Installed | N/A | No | N/A | 5.11 | Unknown | Unknown | Unknown | Unknown | 5.11 | 3981 | 1616.75 | 5.11 | 1611.64 | Yes | N/A | N/A | 2024-12-02 | 2024-12-02 | 1 | 1 | 2024-12-02 | 2024-12-02 | 1 | 1 | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2024-12-04 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | 2024-12-18 | 1900-01-14 | 11 | 2024-12-18 | 2024-12-18 | 1 | 1 | 4 | 4 | 17 | 13 | 21 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-26 | -479 | -344 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 1654.13 | -5.35 | Unknown | Unknown | 85.77 | 1573.71 | 3981 | 278.35 | 1654.13 | -1375.78 | Yes | N/A | N/A | 2024-08-20 | 2024-09-04 | 16 | 12 | 2024-09-04 | 2024-09-04 | 1 | 1 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2025-01-21 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | 2025-03-05 | 1900-02-12 | 32 | 2025-03-05 | 2025-03-04 | Unknown | Unknown | 156 | 112 | 45 | 33 | 201 | 145 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 72.05 | 72.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | -629 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-04 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 1475.59 | Unknown | Unknown | Unknown | Unknown | 1475.59 | 3981 | 989.29 | 1475.59 | -486.3 | Yes | N/A | N/A | 2024-12-03 | 2025-01-03 | 32 | 24 | 2025-01-03 | 2025-02-28 | 57 | 41 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-02-20 | 49 | 35 | Unknown | 2025-02-19 | Unknown | Unknown | 2025-02-20 | 2025-02-28 | 1900-01-08 | 7 | 2025-02-28 | 2025-02-28 | 1 | 1 | 81 | 59 | 67 | 49 | 148 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-07-22 | 1751 | 1252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-07-11 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | 4989.52 | 70.93 | Unknown | Unknown | -2023 | 6941.59 | 3661.75 | 4059.9 | 4989.52 | -929.62 | Yes | N/A | N/A | 2023-07-07 | 2023-08-17 | 42 | 30 | 2023-08-17 | 2024-04-24 | 252 | 180 | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-03-07 | 1 | 1 | 2024-04-24 | 2025-02-26 | 309 | 221 | Unknown | 2025-04-02 | Unknown | Unknown | 2025-05-16 | 2025-05-16 | 1899-12-31 | 1 | 2025-05-16 | 2025-05-08 | Unknown | Unknown | 351 | 251 | 254 | 182 | 605 | 433 | Steps 2,3,5,6,7 | 317 | 227 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-16 | -201 | -144 | No | 2024-03-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | Unknown | IOU Designed & Installed | N/A | Yes | 318 | 1240.35 | Unknown | Unknown | Unknown | 24.34 | 1216.01 | 3981 | 1586.33 | 1240.35 | 345.98 | Yes | N/A | N/A | 2024-03-11 | 2025-01-23 | 319 | 229 | 2025-01-23 | 2024-06-03 | Unknown | Unknown | 2024-06-03 | Unknown | Unknown | Unknown | 2024-06-03 | 2024-07-11 | 39 | 29 | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | 2025-04-29 | 2025-04-29 | 1 | 1 | 319 | 229 | 40 | 30 | 359 | 259 | Steps 2,3,5,6,7 | 38 | 28 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 595.1 | 595.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-12 | -365 | -262 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-13 | 2023-05-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1840.51 | -57.99 | Unknown | Unknown | 29.43 | 1869.07 | 7962 | 770.57 | 1840.51 | -1069.94 | Yes | N/A | N/A | 2023-04-13 | 2023-04-11 | Unknown | Unknown | 2023-04-11 | 2023-05-17 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | 2023-05-08 | 7 | 5 | 2023-05-17 | 2023-06-21 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2023-09-13 | 1 | 1 | 36 | 26 | 45 | 33 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 88.05 | 88.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-19 | 113 | 81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-16 | 2025-05-05 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1472.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2024-11-06 | Unknown | Unknown | 2024-11-06 | 2024-12-16 | 41 | 29 | 2024-12-16 | 2025-04-30 | 136 | 98 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-05 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | 2025-05-13 | 1900-01-08 | 7 | 2025-05-13 | 2025-05-12 | Unknown | Unknown | 140 | 100 | 50 | 36 | 190 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego PA1 PH3 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 445 | 320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-07-05 | 2024-05-28 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 111727.18 | 23057.25 | Unknown | Unknown | 12962.17 | 75707.76 | 0 | 34130.6 | 111727.18 | -77596.58 | Yes | N/A | N/A | 2022-04-27 | 2023-04-05 | 344 | 246 | 2023-04-05 | 2023-10-11 | 190 | 136 | 2023-05-23 | 2024-04-08 | 250 | 179 | 2023-08-23 | 2023-09-11 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | 2024-05-28 | 2024-06-07 | 1900-01-10 | 9 | 2024-06-07 | 2024-06-07 | 1 | 1 | 594 | 425 | 222 | 160 | 816 | 585 | Steps 2,3,5,6,7 | 370 | 264 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-12-28 | -113 | -81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 13472.21 | Unknown | Unknown | Unknown | Unknown | 13472.21 | 2875.23 | 696.22 | 13472.21 | -12775.99 | Yes | N/A | N/A | 2024-07-18 | 2024-07-18 | 1 | 1 | 2024-07-18 | 2024-08-26 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | Unknown | Unknown | 2024-08-26 | 2024-09-06 | 1900-01-11 | 10 | 2024-09-06 | 2024-09-06 | 1 | 1 | 1 | 1 | 53 | 39 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-15 | -41 | -30 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2023-07-24 | 2023-09-11 | IOU Designed & Installed | N/A | No | N/A | 1210.41 | 399.1 | Unknown | 16.04 | 79.16 | 716.11 | 3981 | 462.42 | 1210.41 | -747.99 | Yes | N/A | N/A | 2023-07-24 | 2023-08-14 | 22 | 16 | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2023-09-11 | 27 | 19 | Unknown | 2023-09-07 | Unknown | Unknown | 2023-09-11 | 2024-04-04 | 1900-07-25 | 149 | 2024-04-04 | 2024-04-04 | 1 | 1 | 49 | 35 | 208 | 150 | 257 | 185 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-03 | -697 | -500 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-07-22 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 45.9 | Unknown | Unknown | Unknown | Unknown | 45.9 | 3981 | 1461.73 | 45.9 | 1415.83 | Yes | N/A | N/A | 2024-07-22 | 2024-07-22 | 1 | 1 | 2024-07-22 | 2024-07-23 | 2 | 2 | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-07-25 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-08-05 | 1900-01-11 | 8 | 2024-08-05 | 2024-08-05 | 1 | 1 | 4 | 4 | 15 | 11 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-12 | -549 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-27 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | 2084.51 | 614.1 | Unknown | Unknown | -203 | 1673.41 | Unknown | 1616.08 | 2084.51 | -468.43 | Yes | N/A | N/A | 2024-12-16 | 2024-12-27 | 12 | 10 | 2024-12-27 | 2024-12-27 | 1 | 1 | 2024-12-27 | 2025-01-29 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-19 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-03-12 | 1900-01-21 | 16 | 2025-03-12 | 2025-03-12 | 1 | 1 | 68 | 50 | 24 | 18 | 92 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 105.05 | 105.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-26 | -530 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-11-18 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 26.86 | Unknown | Unknown | Unknown | Unknown | 26.86 | 3981 | 1513.5 | 26.86 | 1486.64 | Yes | N/A | N/A | 2024-10-24 | 2024-10-31 | 8 | 6 | 2024-10-31 | 2024-11-18 | 19 | 13 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2025-02-20 | 95 | 69 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-03-26 | 1900-02-03 | 25 | 2025-03-26 | 2025-03-14 | Unknown | Unknown | 103 | 75 | 54 | 38 | 157 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | POWAY | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-13 | -289 | -208 | No | 2024-02-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-03-04 | 2025-01-27 | IOU Designed & Installed | N/A | Yes | 316 | 996.29 | -19.38 | Unknown | Unknown | Unknown | 1015.67 | 3981 | 735.69 | 996.29 | -260.6 | Yes | N/A | N/A | 2024-02-22 | 2024-12-17 | 300 | 214 | 2024-12-17 | 2025-01-03 | 18 | 14 | 2025-01-03 | Unknown | Unknown | Unknown | 2024-02-29 | 2024-03-06 | 7 | 5 | 2024-03-04 | 2025-01-27 | 330 | 236 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-01-29 | 1900-01-02 | 3 | 2025-01-29 | 2025-01-28 | Unknown | Unknown | 630 | 450 | 28 | 22 | 658 | 472 | Steps 2,3,5,6,7 | 2 | 2 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-24 | -645 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-18 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | 3147.09 | 854.01 | Unknown | Unknown | Unknown | 2293.08 | 3981 | 1277.67 | 3147.09 | -1869.42 | Yes | N/A | N/A | 2025-04-07 | 2025-04-18 | 12 | 10 | 2025-04-18 | 2025-04-18 | 1 | 1 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-06-10 | 54 | 38 | Unknown | 2025-06-10 | Unknown | Unknown | 2025-06-10 | 2025-06-17 | 1900-01-07 | 6 | 2025-06-17 | 2025-06-17 | 1 | 1 | 66 | 48 | 10 | 8 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 90 | 90 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -325 | -234 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | 2725.38 | Unknown | Unknown | Unknown | -1091 | 3816.38 | 0 | 1065.63 | 2725.38 | -1659.75 | Yes | N/A | N/A | 2024-07-29 | 2024-06-27 | Unknown | Unknown | 2024-06-27 | 2024-07-29 | 33 | 23 | 2024-07-29 | 2024-08-13 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2025-06-05 | 296 | 212 | Unknown | 2025-05-30 | Unknown | Unknown | 2025-06-05 | 2025-06-13 | 1900-01-08 | 7 | 2025-06-13 | 2025-06-10 | Unknown | Unknown | 312 | 224 | 42 | 30 | 354 | 254 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | -590 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-06 | 2024-06-11 | IOU Designed & Installed | N/A | No | N/A | 612.16 | -8.88 | Unknown | Unknown | Unknown | 621.04 | Unknown | 974.14 | 612.16 | 361.98 | Yes | N/A | N/A | 2024-05-06 | 2024-05-06 | 1 | 1 | 2024-05-06 | 2024-05-06 | 1 | 1 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-06-11 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-07-16 | 1900-02-04 | 26 | 2024-07-16 | 2024-07-16 | 1 | 1 | 38 | 28 | 38 | 28 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-14 | -519 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-10 | 2024-03-06 | IOU Designed & Installed | N/A | No | N/A | 2730.43 | 920.88 | Unknown | 82.72 | Unknown | 1726.83 | 3941 | 1053.26 | 2730.43 | -1677.17 | Yes | N/A | N/A | 2024-01-10 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2024-01-10 | 43 | 31 | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-03-06 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-03-13 | 1900-01-07 | 6 | 2024-03-13 | 2024-03-13 | 1 | 1 | 57 | 41 | 52 | 38 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-30 | 138 | 99 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2023-10-11 | 2023-11-10 | IOU Designed & Installed | N/A | No | N/A | 1260.64 | Unknown | Unknown | Unknown | Unknown | 1260.64 | 14132 | 514.57 | 1260.64 | -746.07 | Yes | N/A | N/A | 2023-07-25 | 2023-10-06 | 74 | 54 | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | Unknown | Unknown | 2023-11-10 | 2023-11-15 | 1900-01-05 | 4 | 2023-11-15 | 2023-11-15 | 1 | 1 | 74 | 54 | 7 | 5 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-19 | -565 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | 444.7 | -11.94 | Unknown | Unknown | Unknown | 456.64 | 3981 | 651.64 | 444.7 | 206.94 | Yes | N/A | N/A | 2023-04-11 | 2023-06-12 | 63 | 45 | 2023-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-12 | 2023-07-17 | 36 | 26 | Unknown | 2023-07-17 | Unknown | Unknown | 2023-07-17 | 2023-08-04 | 1900-01-18 | 15 | 2023-08-04 | 2023-08-04 | 1 | 1 | 99 | 71 | 20 | 16 | 119 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-31 | -901 | -644 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 696.08 | 280.25 | Unknown | Unknown | -403 | 818.83 | Unknown | 403.09 | 696.08 | -292.99 | Yes | N/A | N/A | 2023-04-19 | 2023-04-19 | 1 | 1 | 2023-04-19 | 2023-05-08 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | 2023-07-06 | 60 | 44 | Unknown | 2023-05-31 | Unknown | Unknown | Unknown | 2023-09-11 | Unknown | Unknown | 2023-09-11 | 2023-07-14 | Unknown | Unknown | 61 | 45 | 20 | 14 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 300 | 300 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | -159 | -114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | 2025-03-21 | IOU Designed & Installed | N/A | No | N/A | 50.71 | Unknown | Unknown | Unknown | Unknown | 50.71 | 7962 | 2515.53 | 50.71 | 2464.82 | Yes | N/A | N/A | 2024-09-24 | 2024-09-24 | 1 | 1 | 2024-09-24 | 2024-09-24 | 1 | 1 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2025-03-21 | 179 | 129 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-03-26 | 1900-01-05 | 4 | 2025-03-26 | 2025-03-26 | 1 | 1 | 180 | 130 | 8 | 6 | 188 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-15 | -493 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-03-14 | 2024-06-28 | IOU Designed & Installed | N/A | No | N/A | 17.93 | -13.82 | Unknown | Unknown | Unknown | 31.75 | 3981 | 1102.07 | 17.93 | 1084.14 | Yes | N/A | N/A | 2024-02-29 | 2024-03-06 | 7 | 5 | 2024-03-06 | 2024-03-13 | 8 | 6 | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-06-28 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-15 | 1900-01-17 | 12 | 2024-07-15 | 2024-08-09 | 26 | 20 | 114 | 82 | 52 | 38 | 166 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | -465 | -332 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 651.98 | -10.45 | Unknown | Unknown | 25.19 | 637.24 | 3981 | 995.25 | 651.98 | 343.27 | Yes | N/A | N/A | 2023-03-02 | 2023-04-04 | 34 | 24 | 2023-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-05 | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2023-09-28 | 1 | 1 | 34 | 24 | 1 | 1 | 35 | 25 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-01 | 356 | 255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-28 | 2024-06-07 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 5670.68 | Unknown | Unknown | Unknown | Unknown | 5670.68 | Unknown | 443.54 | 5670.68 | -5227.14 | Yes | N/A | N/A | 2022-09-28 | 2024-06-07 | 619 | 443 | 2024-06-07 | 2024-07-09 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-07-22 | 1900-01-13 | 10 | 2024-07-22 | 2024-07-22 | 1 | 1 | 619 | 443 | 48 | 34 | 667 | 477 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JULIAN | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 124 | 89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-26 | 2024-04-26 | 2024-06-27 | IOU Designed & Installed | N/A | No | N/A | 1758.26 | 740.04 | Unknown | 37.38 | -511 | 1491.84 | 3981 | 2343.85 | 1758.26 | 585.59 | Yes | N/A | N/A | 2024-04-26 | 2024-01-30 | Unknown | Unknown | 2024-01-30 | 2024-04-26 | 88 | 64 | 2024-04-26 | 2024-05-03 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-06-27 | 60 | 44 | Unknown | 2024-06-05 | Unknown | Unknown | 2024-06-27 | 2024-07-03 | 1900-01-06 | 5 | 2024-07-03 | 2024-07-03 | 1 | 1 | 68 | 50 | 96 | 70 | 164 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community,Tribal Community | SANTA YSABEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-11 | 62 | 45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-29 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 25599.84 | 19.17 | Unknown | Unknown | 39.57 | 25541.1 | 16690 | 665.25 | 25599.84 | -24934.59 | Yes | N/A | N/A | 2024-01-22 | 2024-01-29 | 8 | 6 | 2024-01-29 | 2024-06-07 | 131 | 95 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-06-17 | 1900-01-07 | 6 | 2024-06-17 | 2024-06-12 | Unknown | Unknown | 8 | 6 | 139 | 101 | 147 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | -693 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-02 | 2024-08-06 | IOU Designed & Installed | N/A | No | N/A | 7.89 | Unknown | Unknown | Unknown | Unknown | 7.89 | 3981 | 1404.73 | 7.89 | 1396.84 | Yes | N/A | N/A | 2024-08-02 | 2024-07-30 | Unknown | Unknown | 2024-07-30 | 2024-08-06 | 8 | 6 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-08-06 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-28 | 1900-01-22 | 17 | 2024-08-28 | 2024-08-28 | 1 | 1 | 5 | 3 | 32 | 24 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-24 | -485 | -347 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-05 | 2024-04-05 | 2024-08-20 | IOU Designed & Installed | N/A | No | N/A | 25.76 | Unknown | Unknown | Unknown | Unknown | 25.76 | 3981 | 861.19 | 25.76 | 835.43 | Yes | N/A | N/A | 2024-04-05 | 2024-01-29 | Unknown | Unknown | 2024-01-29 | 2024-04-05 | 68 | 50 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-08-20 | 138 | 98 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-09-26 | 1900-02-06 | 28 | 2024-09-26 | 2024-09-26 | 1 | 1 | 138 | 98 | 107 | 79 | 245 | 177 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-12 | 543 | 388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-15 | 2024-02-03 | IOU Designed & Installed | N/A | No | N/A | 168.71 | 2935.93 | Unknown | 310.42 | -4615 | 1537.36 | Unknown | 4615.08 | 168.71 | 4446.37 | Yes | N/A | N/A | 2023-11-15 | 2024-01-24 | 71 | 51 | 2024-01-24 | Unknown | Unknown | Unknown | 2024-01-31 | 2024-01-31 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-03 | 2024-02-06 | 1900-01-03 | 2 | 2024-02-06 | 2024-02-06 | 1 | 1 | 72 | 52 | 5 | 3 | 77 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | MISSION VIEJO | N/A | 90000 | 90000 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-02-14 | -188 | -135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-07-27 | 2023-08-09 | IOU Designed & Installed | N/A | No | N/A | -820.94 | 617.93 | Unknown | 459.21 | -2304 | 405.92 | Unknown | 2304.07 | -820.94 | 3125.01 | Yes | N/A | N/A | 2023-03-02 | 2023-07-21 | 142 | 102 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | 2023-08-10 | 1900-01-01 | 2 | 2023-08-10 | 2023-08-10 | 1 | 1 | 142 | 102 | 3 | 3 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 14.05 | 14.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | -519 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-08-21 | 2025-02-14 | IOU Designed & Installed | N/A | No | N/A | 96.05 | -1.5 | Unknown | Unknown | Unknown | 97.55 | 3981 | 1584.31 | 96.05 | 1488.26 | Yes | N/A | N/A | 2024-08-21 | 2024-08-22 | 2 | 2 | 2024-08-22 | 2024-08-22 | 1 | 1 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2025-02-14 | 177 | 127 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-10 | 1900-01-24 | 17 | 2025-03-10 | 2025-02-25 | Unknown | Unknown | 179 | 129 | 26 | 18 | 205 | 147 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-12 | -234 | -167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-17 | 2024-05-15 | IOU Designed & Installed | N/A | No | N/A | 12480.06 | 285.19 | Unknown | Unknown | -1229 | 13423.87 | 68774 | 3243.99 | 12480.06 | -9236.07 | Yes | N/A | N/A | 2024-04-17 | 2024-04-17 | 1 | 1 | 2024-04-17 | 2024-04-24 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-09 | 16 | 12 | Unknown | 2024-05-06 | Unknown | Unknown | 2024-05-15 | 2024-05-30 | 1900-01-15 | 12 | 2024-05-30 | 2024-05-23 | Unknown | Unknown | 17 | 13 | 24 | 18 | 41 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-28 | -616 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-18 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | 5591.69 | 901.67 | Unknown | 122.99 | 29.79 | 4537.24 | 3981 | 794.3 | 5591.69 | -4797.39 | Yes | N/A | N/A | 2025-03-10 | 2025-04-15 | 37 | 27 | 2025-04-15 | 2025-04-15 | 1 | 1 | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-05-16 | 32 | 24 | Unknown | 2025-05-14 | Unknown | Unknown | 2025-05-16 | 2025-06-03 | 1900-01-18 | 13 | 2025-06-03 | 2025-05-22 | Unknown | Unknown | 69 | 51 | 20 | 14 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Oceanside | OCEANSIDE | 20.1 | 20.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-17 | 452 | 325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-04-27 | 2024-08-30 | IOU Designed & Installed | N/A | No | N/A | 17751.74 | 1656.19 | Unknown | Unknown | -4391 | 20486.55 | 0 | 8781.54 | 17751.74 | -8970.2 | Yes | N/A | N/A | 2023-04-26 | 2023-04-27 | 2 | 2 | 2023-04-27 | 2024-01-10 | 259 | 185 | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-01-23 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-10-11 | 1900-02-11 | 31 | 2024-10-11 | 2024-10-11 | 1 | 1 | 2 | 2 | 319 | 229 | 321 | 231 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-11 | -606 | -433 | No | 2023-09-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-06 | 2023-12-05 | IOU Designed & Installed | N/A | Yes | 89 | -7.67 | -6.68 | Unknown | Unknown | Unknown | -0.99 | Unknown | 154.99 | -7.67 | 162.66 | Yes | N/A | N/A | 2023-09-06 | 2023-12-04 | 90 | 64 | 2023-12-04 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-12-05 | 70 | 50 | Unknown | 2023-11-29 | Unknown | Unknown | 2023-12-05 | 2023-12-14 | 1900-01-09 | 8 | 2023-12-14 | 2023-12-14 | 1 | 1 | 160 | 114 | 11 | 9 | 171 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-21 | -296 | -212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 2025-05-28 | IOU Designed & Installed | N/A | No | N/A | 3471.57 | 73.08 | Unknown | Unknown | Unknown | 3398.49 | Unknown | 1656 | 3471.57 | -1815.57 | Yes | N/A | N/A | 2025-04-07 | 2025-04-28 | 22 | 16 | 2025-04-28 | 2025-05-12 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-05-29 | 1900-01-01 | 2 | 2025-05-29 | 2025-05-29 | 1 | 1 | 22 | 16 | 18 | 14 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-19 | -597 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-13 | 2024-06-24 | IOU Designed & Installed | N/A | No | N/A | 74.67 | -0.94 | Unknown | Unknown | Unknown | 75.61 | Unknown | 1493.37 | 74.67 | 1418.7 | Yes | N/A | N/A | 2024-06-13 | 2024-06-13 | 1 | 1 | 2024-06-13 | 2024-06-13 | 1 | 1 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-06-24 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-07-30 | 1900-02-05 | 27 | 2024-07-30 | 2024-07-30 | 1 | 1 | 13 | 9 | 39 | 29 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-05 | 92 | 67 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-12 | 2024-06-05 | IOU Designed & Installed | N/A | No | N/A | 29224.04 | 8757.17 | Unknown | 1965.33 | 70.92 | 18430.62 | Unknown | 1511.14 | 29224.04 | -27712.9 | Yes | N/A | N/A | 2024-03-06 | 2024-03-12 | 7 | 5 | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-06-05 | 1899-12-31 | 1 | 2024-06-05 | 2024-06-05 | 1 | 1 | 7 | 5 | 2 | 2 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-05 | -610 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-04-04 | 2024-05-21 | IOU Designed & Installed | N/A | No | N/A | 1322.78 | 283.6 | Unknown | Unknown | Unknown | 1039.18 | Unknown | 2566.59 | 1322.78 | 1243.81 | Yes | N/A | N/A | 2024-03-28 | 2024-03-28 | 1 | 1 | 2024-03-28 | 2024-05-16 | 50 | 36 | 2024-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-05-21 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2024-06-05 | 1900-01-15 | 12 | 2024-06-05 | 2024-06-05 | 1 | 1 | 42 | 30 | 67 | 49 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-30 | -676 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-06-30 | 2023-07-25 | IOU Designed & Installed | N/A | No | N/A | 552.17 | -2.78 | Unknown | Unknown | 4.44 | 550.51 | Unknown | 356.73 | 552.17 | -195.44 | Yes | N/A | N/A | 2023-06-30 | 2023-07-10 | 11 | 7 | 2023-07-10 | 2023-07-10 | 1 | 1 | 2023-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | 2023-07-25 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2023-08-24 | 1900-01-30 | 23 | 2023-08-24 | 2023-08-24 | 1 | 1 | 27 | 19 | 33 | 25 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 98 | 98 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | -590 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-06-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 243.16 | -14.9 | Unknown | Unknown | Unknown | 258.06 | 3981 | 1225.06 | 243.16 | 981.9 | Yes | N/A | N/A | 2023-05-17 | 2023-06-06 | 21 | 15 | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | 2023-06-26 | 21 | 15 | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | Unknown | Unknown | 2023-07-13 | 2023-07-13 | 1 | 1 | 21 | 15 | 22 | 16 | 43 | 31 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-03 | -528 | -377 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | 2023-11-30 | 2024-02-20 | IOU Designed & Installed | N/A | No | N/A | 932.13 | 516.42 | Unknown | 93.81 | Unknown | 321.9 | Unknown | 936.68 | 932.13 | 4.55 | Yes | N/A | N/A | 2023-11-30 | 2023-11-30 | 1 | 1 | 2023-11-30 | 2023-11-30 | 1 | 1 | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2024-02-20 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-02-22 | 1900-01-02 | 3 | 2024-02-22 | 2024-02-22 | 1 | 1 | 84 | 60 | 5 | 5 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BORREGO SPRINGS | N/A | 357.05 | 357.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-18 | -663 | -474 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-08 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1186.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-08 | 2025-04-18 | Unknown | Unknown | 2025-04-18 | 2025-05-09 | 22 | 16 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-06-18 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-06-24 | 1900-01-06 | 5 | 2025-06-24 | 2025-06-24 | 1 | 1 | 42 | 30 | 30 | 22 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | 19.45 | 19.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | -380 | -273 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-04-23 | 2024-09-21 | IOU Designed & Installed | N/A | No | N/A | 9962.21 | 5972.21 | Unknown | 517.99 | -4925 | 8397.01 | 3981 | 9044.7 | 9962.21 | -917.51 | Yes | N/A | N/A | 2024-03-11 | 2024-02-06 | Unknown | Unknown | 2024-02-06 | 2024-08-23 | 200 | 144 | 2024-04-05 | 2024-05-02 | 28 | 20 | 2024-06-27 | 2024-08-09 | 24 | 18 | 2024-08-23 | Unknown | Unknown | Unknown | 2024-08-28 | 2024-09-17 | 21 | 15 | 2024-09-21 | 2024-09-24 | 1900-01-03 | 2 | 2024-09-24 | 2024-09-24 | 1 | 1 | 28 | 20 | 250 | 180 | 278 | 200 | Steps 2,3,5,6,7 | 140 | 100 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-28 | 131 | 94 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-09-06 | 2023-09-20 | IOU Designed & Installed | N/A | No | N/A | 264.59 | -8.89 | Unknown | Unknown | Unknown | 273.48 | 3981 | 1010.22 | 264.59 | 745.63 | Yes | N/A | N/A | 2023-08-23 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2023-09-06 | 71 | 51 | 2023-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | 2023-09-20 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | 2023-11-06 | 1900-02-16 | 34 | 2023-11-06 | 2023-11-06 | 1 | 1 | 15 | 11 | 120 | 86 | 135 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-03 | -684 | -490 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | Unknown | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 567.86 | -11.7 | Unknown | Unknown | Unknown | 579.56 | 3981 | 1562.13 | 567.86 | 994.27 | Yes | N/A | N/A | 2024-10-10 | 2024-10-10 | 1 | 1 | 2024-10-10 | 2024-10-10 | 1 | 1 | 2024-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-10-31 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-18 | 1900-01-18 | 13 | 2024-11-18 | 2024-11-18 | 1 | 1 | 23 | 17 | 21 | 15 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 40.05 | 40.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | -570 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-06 | 2023-08-01 | IOU Designed & Installed | N/A | No | N/A | 246.74 | -8.02 | Unknown | Unknown | Unknown | 254.76 | Unknown | 776.88 | 246.74 | 530.14 | Yes | N/A | N/A | 2023-06-06 | 2023-06-06 | 1 | 1 | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | 2023-08-01 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-08-07 | 1900-01-06 | 5 | 2023-08-07 | 2023-08-07 | 1 | 1 | 58 | 42 | 8 | 6 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | 206.1 | 206.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-17 | 363 | 260 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-06-11 | 2024-11-01 | IOU Designed & Installed | N/A | No | N/A | 27925.62 | 4662.32 | Unknown | Unknown | -447.7 | 23711 | 7962 | 3823.41 | 27925.62 | -24102.21 | Yes | N/A | N/A | 2024-02-21 | 2024-05-16 | 86 | 62 | 2024-05-16 | 2024-09-18 | 126 | 90 | 2024-07-18 | 2024-07-18 | 1 | 1 | 2024-09-10 | 2024-10-02 | 23 | 17 | 2024-09-18 | 2024-10-29 | 42 | 30 | Unknown | 2024-10-24 | Unknown | Unknown | 2024-11-01 | 2024-12-01 | 1900-01-30 | 21 | 2024-12-01 | 2024-11-14 | Unknown | Unknown | 129 | 93 | 180 | 128 | 309 | 221 | Steps 2,3,5,6,7 | 76 | 54 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 135.05 | 135.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | 60 | 43 | No | 2023-02-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-16 | 2023-03-13 | Unknown | IOU Designed & Installed | N/A | Yes | 89 | -685.7 | Unknown | Unknown | Unknown | -735 | 49.3 | 3981 | 1523.84 | -685.7 | 2209.54 | Yes | N/A | N/A | 2023-02-16 | 2023-05-16 | 90 | 64 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | 2024-07-30 | 2024-07-31 | 2 | 2 | 90 | 64 | 2 | 2 | 92 | 66 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 63 | 63 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | -97 | -70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-05 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 22795.96 | 2029.44 | Unknown | Unknown | Unknown | 20766.52 | 3981 | 2145.87 | 22795.96 | -20650.09 | Yes | N/A | N/A | 2024-04-04 | 2024-04-05 | 2 | 2 | 2024-04-05 | 2024-08-13 | 131 | 93 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-10-15 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-24 | 1900-01-29 | 22 | 2024-10-24 | 2024-11-01 | 9 | 7 | 66 | 48 | 170 | 122 | 236 | 170 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | LA JOLLA | LA JOLLA | 127 | 127 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-10 | 109 | 78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-03 | 2023-07-19 | 2023-09-11 | IOU Designed & Installed | N/A | No | N/A | 40737.73 | 4864.81 | Unknown | Unknown | -9223.88 | 45096.8 | Unknown | 18454.04 | 40737.73 | -22283.69 | Yes | N/A | N/A | 2023-07-03 | 2023-08-04 | 33 | 25 | 2023-08-04 | 2023-08-23 | 20 | 14 | 2023-08-09 | 2024-06-19 | 316 | 226 | 2023-08-07 | 2023-08-30 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-09-27 | 1900-01-16 | 13 | 2023-09-27 | 2023-09-27 | 1 | 1 | 349 | 251 | 49 | 37 | 398 | 288 | Steps 2,3,5,6,7 | 331 | 237 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 150.05 | 150.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-25 | 262 | 187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2043.71 | Unknown | Unknown | Unknown | Unknown | 2043.71 | 3981 | 1192.29 | 2043.71 | -851.42 | Yes | N/A | N/A | 2024-01-03 | 2023-06-03 | Unknown | Unknown | 2023-06-03 | 2024-01-17 | 229 | 163 | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | 2025-02-11 | 2025-02-11 | 1 | 1 | 0 | 0 | 230 | 164 | 230 | 164 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-08 | -344 | -247 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | 2023-05-30 | IOU Designed & Installed | N/A | No | N/A | 942.75 | 356.64 | Unknown | Unknown | Unknown | 586.11 | Unknown | 888.98 | 942.75 | -53.77 | Yes | N/A | N/A | 2023-05-16 | 2023-05-16 | 1 | 1 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | 2023-05-30 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | 2023-05-30 | 1899-12-31 | 1 | 2023-05-30 | 2023-05-30 | 1 | 1 | 16 | 12 | 2 | 2 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 24989 | 24989 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-09-08 | 613 | 438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-04-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2417.81 | -49.06 | Unknown | Unknown | 27.24 | 2439.63 | 15226 | 462.86 | 2417.81 | -1954.95 | Yes | N/A | N/A | 2023-04-26 | 2023-03-21 | Unknown | Unknown | 2023-03-21 | 2023-09-28 | 192 | 138 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2024-04-02 | 188 | 134 | Unknown | 2024-05-07 | Unknown | Unknown | Unknown | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-05-13 | Unknown | Unknown | 188 | 134 | 192 | 138 | 380 | 272 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-01 | 634 | 453 | No | 2021-02-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-25 | 2021-02-25 | 2024-05-15 | Customer elected Applicant Design | Step 2 Engineering & Design | Yes | 1104 | 256869.53 | 33871.69 | Unknown | 161.87 | 2262.44 | 220573.53 | 264274.9 | 93718.38 | 256869.53 | -163151.15 | Yes | N/A | N/A | 2021-02-25 | 2024-02-28 | 1099 | 785 | 2024-02-28 | 2022-07-07 | Unknown | Unknown | 2021-12-08 | 2024-03-21 | 73 | 53 | 2022-07-07 | 2022-07-12 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2022-07-21 | 2024-06-25 | Unknown | Unknown | 2024-05-15 | 2024-07-01 | 1900-02-16 | 34 | 2024-07-01 | 2024-06-26 | Unknown | Unknown | 1172 | 838 | 54 | 38 | 1226 | 876 | Steps 2,3,5,6,7 | 41 | 29 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-18 | -91 | -66 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-16 | 2024-12-04 | IOU Designed & Installed | N/A | No | N/A | -2505.47 | 1279.04 | Unknown | 153.3 | -4512 | 574.19 | Unknown | 4511.8 | -2505.47 | 7017.27 | Yes | N/A | N/A | 2024-10-16 | 2024-10-16 | 1 | 1 | 2024-10-16 | 2025-01-17 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | Unknown | 2025-01-17 | 2025-01-17 | 1 | 1 | 2024-12-04 | 2025-01-17 | 1900-02-13 | 33 | 2025-01-17 | 2025-01-17 | 1 | 1 | 1 | 1 | 141 | 103 | 142 | 104 | Steps 2,3,5,6,7 | 44 | 32 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | Coronado | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-08 | 874 | 625 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-20 | 2024-11-21 | IOU Designed & Installed | N/A | No | N/A | 66370.33 | 3529.81 | Unknown | 182.95 | 73.15 | 62584.42 | 0 | 16079.1 | 66370.33 | -50291.23 | Yes | N/A | N/A | 2023-04-06 | 2023-04-05 | Unknown | Unknown | 2023-04-05 | Unknown | Unknown | Unknown | 2023-06-23 | 2023-06-23 | 1 | 1 | 2023-07-26 | 2024-11-06 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2025-01-29 | 1900-03-10 | 50 | 2025-01-29 | 2025-01-29 | 1 | 1 | 1 | 1 | 101 | 73 | 102 | 74 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-27 | -450 | -321 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-03 | 2022-11-03 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | 248.8 | -8.26 | Unknown | Unknown | -522.22 | 779.28 | Unknown | 530.42 | 248.8 | 281.62 | Yes | N/A | N/A | 2022-11-03 | 2023-02-23 | 113 | 81 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | 2023-07-17 | 138 | 98 | Unknown | 2023-07-13 | Unknown | Unknown | 2023-07-17 | 2023-08-04 | 1900-01-18 | 15 | 2023-08-04 | 2023-08-04 | 1 | 1 | 251 | 179 | 20 | 16 | 271 | 195 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-21 | -221 | -159 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-10-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1420.64 | 404.46 | Unknown | 43.63 | 17.61 | 954.94 | 3981 | 760.57 | 1420.64 | -660.07 | Yes | N/A | N/A | 2023-10-23 | 2023-10-17 | Unknown | Unknown | 2023-10-17 | 2023-11-16 | 31 | 23 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-02-13 | 1 | 1 | 0 | 0 | 32 | 24 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-05 | -303 | -216 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-28 | 2024-04-10 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 86124.54 | 12505.26 | Unknown | Unknown | -21101.53 | 94720.81 | 14914 | 27624.39 | 86124.54 | -58500.15 | Yes | N/A | N/A | 2024-02-28 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-06-21 | 134 | 96 | 2024-05-28 | 2024-09-25 | 113 | 81 | 2024-06-13 | 2024-09-19 | 10 | 8 | 2024-06-21 | 2024-10-09 | 111 | 79 | 2024-07-03 | 2024-10-15 | 105 | 75 | 2024-10-18 | 2025-03-14 | 1900-05-27 | 106 | 2025-03-14 | 2024-12-06 | Unknown | Unknown | 224 | 160 | 397 | 285 | 621 | 445 | Steps 2,3,5,6,7 | 316 | 226 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-04 | -655 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-21 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 15.2 | Unknown | Unknown | Unknown | Unknown | 15.2 | Unknown | 196.44 | 15.2 | 181.24 | Yes | N/A | N/A | 2025-01-21 | 2025-03-03 | 42 | 30 | 2025-03-03 | 2025-03-05 | 3 | 3 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-06 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-03-20 | 1900-01-14 | 11 | 2025-03-20 | 2025-03-20 | 1 | 1 | 44 | 32 | 19 | 15 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | -394 | -283 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-21 | 2024-02-09 | IOU Designed & Installed | N/A | No | N/A | 1708.2 | -49.56 | Unknown | Unknown | 20.11 | 1737.65 | 2781 | 1467.37 | 1708.2 | -240.83 | Yes | N/A | N/A | 2023-08-03 | 2023-11-01 | 91 | 65 | 2023-11-01 | 2023-11-09 | 9 | 7 | 2023-11-09 | 2024-01-29 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2024-02-09 | 93 | 67 | Unknown | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-03-14 | 1900-02-03 | 25 | 2024-03-14 | 2024-03-12 | Unknown | Unknown | 185 | 133 | 44 | 32 | 229 | 165 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-20 | -385 | -276 | No | 2024-03-29 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-04-11 | 2024-05-28 | IOU Designed & Installed | N/A | Yes | 164 | 569.95 | -9.61 | Unknown | Unknown | 4.62 | 574.94 | 3981 | 932.11 | 569.95 | 362.16 | Yes | N/A | N/A | 2024-03-29 | 2024-09-09 | 165 | 117 | 2024-09-09 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-05-28 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-10-31 | 1900-06-05 | 113 | 2024-10-31 | 2024-10-31 | 1 | 1 | 213 | 151 | 158 | 114 | 371 | 265 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-18 | -245 | -176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-07-31 | 2023-07-31 | IOU Designed & Installed | N/A | No | N/A | -14.13 | -10.23 | Unknown | Unknown | Unknown | -3.9 | Unknown | 480.37 | -14.13 | 494.5 | Yes | N/A | N/A | 2023-07-07 | 2023-07-31 | 25 | 17 | 2023-07-31 | 2023-07-31 | 1 | 1 | 2023-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2023-08-17 | 1900-01-17 | 14 | 2023-08-17 | 2023-08-17 | 1 | 1 | 26 | 18 | 20 | 16 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | -624 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-12 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | 154.14 | -2.51 | Unknown | Unknown | Unknown | 156.65 | 3981 | 1545.31 | 154.14 | 1391.17 | Yes | N/A | N/A | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2025-01-15 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-02-06 | 1900-01-22 | 17 | 2025-02-06 | 2025-02-06 | 1 | 1 | 66 | 48 | 25 | 19 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | Oceanside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-07 | -254 | -183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | 50398.57 | 7046.92 | Unknown | 873.82 | -14272 | 56749.83 | Unknown | 14271.71 | 50398.57 | -36126.86 | Yes | N/A | N/A | 2024-11-18 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2025-02-12 | 92 | 66 | 2025-01-02 | 2025-01-10 | 9 | 7 | 2025-02-13 | 2025-02-24 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-02-26 | 1899-12-31 | 1 | 2025-02-26 | 2025-02-26 | 1 | 1 | 9 | 7 | 106 | 76 | 115 | 83 | Steps 2,3,5,6,7 | 41 | 29 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 90.05 | 90.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | -407 | -291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-29 | 2025-06-26 | IOU Designed & Installed | N/A | No | N/A | -407.49 | Unknown | Unknown | Unknown | -1817.75 | 1410.26 | 0 | 1542.08 | -407.49 | 1949.57 | Yes | N/A | N/A | 2024-02-16 | 2024-06-05 | 111 | 79 | 2024-06-05 | 2025-03-18 | 287 | 205 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-04-30 | 44 | 32 | Unknown | 2025-06-12 | Unknown | Unknown | 2025-06-26 | 2025-06-27 | 1900-01-01 | 2 | 2025-06-27 | 2025-06-27 | 1 | 1 | 155 | 111 | 290 | 208 | 445 | 319 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | -631 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-19 | 2024-10-09 | IOU Designed & Installed | N/A | No | N/A | 214.41 | -3.48 | Unknown | Unknown | Unknown | 217.89 | 3981 | 1473.81 | 214.41 | 1259.4 | Yes | N/A | N/A | 2024-07-19 | 2024-07-16 | Unknown | Unknown | 2024-07-16 | 2024-07-23 | 8 | 6 | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-10-09 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-10-16 | 1900-01-07 | 6 | 2024-10-16 | 2024-10-16 | 1 | 1 | 83 | 59 | 17 | 13 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-03 | -402 | -287 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-01-31 | 2023-09-19 | IOU Designed & Installed | N/A | No | N/A | 0.78 | -3.93 | Unknown | Unknown | Unknown | 4.71 | Unknown | 98.41 | 0.78 | 97.63 | Yes | N/A | N/A | 2023-01-31 | 2023-03-03 | 32 | 24 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | 2023-09-19 | 201 | 143 | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-09-28 | 1900-01-09 | 8 | 2023-09-28 | 2023-09-28 | 1 | 1 | 233 | 167 | 11 | 9 | 244 | 176 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Escondido | COUNTY OF SAN DIEGO-NORTH of 56 | 198 | 198 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | -519 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-08-14 | 2024-06-18 | IOU Designed & Installed | N/A | No | N/A | 141926.82 | 21702.39 | Unknown | Unknown | -46229 | 166453.43 | 0 | 92457.2 | 141926.82 | -49469.62 | Yes | N/A | N/A | 2023-05-03 | 2023-06-27 | 56 | 40 | 2023-06-27 | 2024-05-20 | 329 | 235 | 2024-01-19 | 2024-05-06 | 109 | 77 | 2023-11-27 | 2024-06-28 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-07-19 | 1900-01-31 | 24 | 2024-07-19 | 2024-07-19 | 1 | 1 | 165 | 117 | 414 | 298 | 579 | 415 | Steps 2,3,5,6,7 | 283 | 201 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-16 | -248 | -179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-10 | 2023-04-28 | IOU Designed & Installed | N/A | No | N/A | -13.22 | -9.59 | Unknown | Unknown | Unknown | -3.63 | Unknown | 149.62 | -13.22 | 162.84 | Yes | N/A | N/A | 2023-04-10 | 2023-04-10 | 1 | 1 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | 2023-04-28 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | 2023-06-13 | 1900-02-15 | 33 | 2023-06-13 | 2023-06-13 | 1 | 1 | 20 | 16 | 48 | 34 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-24 | -40 | -30 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | 2023-09-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2776.35 | 515.57 | Unknown | Unknown | -3565 | 273.08 | Unknown | 3564.96 | -2776.35 | 6341.31 | Yes | N/A | N/A | 2023-09-05 | 2023-09-12 | 8 | 6 | 2023-09-12 | 2023-09-27 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 8 | 6 | 17 | 13 | 25 | 19 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-04 | -338 | -243 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | 2023-10-31 | IOU Designed & Installed | N/A | No | N/A | 2091.75 | 372.58 | Unknown | 921.3 | Unknown | 797.87 | 3981 | 876.3 | 2091.75 | -1215.45 | Yes | N/A | N/A | 2023-10-17 | 2023-10-17 | 1 | 1 | 2023-10-17 | 2023-10-17 | 1 | 1 | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2023-10-31 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2023-11-01 | 1900-01-01 | 2 | 2023-11-01 | 2023-11-01 | 1 | 1 | 16 | 12 | 4 | 4 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-23 | -255 | -182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2025-04-14 | 2025-06-06 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 798.8 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-21 | 2025-03-13 | 266 | 190 | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | 2025-06-06 | 54 | 40 | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-06-13 | 1900-01-07 | 6 | 2025-06-13 | 2025-06-13 | 1 | 1 | 320 | 230 | 10 | 8 | 330 | 238 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 250 | 179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 819.7 | 2800.5 | Unknown | 875.45 | -4314 | 1457.75 | Unknown | 4314.12 | 819.7 | 3494.42 | Yes | N/A | N/A | 2023-04-20 | 2023-05-04 | 15 | 11 | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-02-21 | 1 | 1 | 15 | 11 | 1 | 1 | 16 | 12 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | -673 | -482 | No | 2023-08-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | Unknown | 2024-11-12 | IOU Designed & Installed | N/A | Yes | 388 | 109.49 | -1.5 | Unknown | Unknown | Unknown | 110.99 | 3981 | 1081.39 | 109.49 | 971.9 | Yes | N/A | N/A | 2023-08-08 | 2024-08-30 | 389 | 279 | 2024-08-30 | 2024-08-07 | Unknown | Unknown | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | 2024-11-12 | 463 | 331 | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2024-11-15 | 1900-01-03 | 4 | 2024-11-15 | 2024-11-14 | Unknown | Unknown | 852 | 610 | 4 | 4 | 856 | 614 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | -279 | -200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-25 | 2024-03-28 | IOU Designed & Installed | N/A | No | N/A | 7.7 | -6.83 | Unknown | Unknown | Unknown | 14.53 | 3981 | 450.91 | 7.7 | 443.21 | Yes | N/A | N/A | 2024-03-25 | 2024-03-25 | 1 | 1 | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-03-29 | 5 | 5 | Unknown | 2024-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-04-01 | 1900-01-04 | 3 | 2024-04-01 | 2024-03-28 | Unknown | Unknown | 1 | 1 | 10 | 8 | 11 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-20 | -549 | -394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2024-04-29 | IOU Designed & Installed | N/A | No | N/A | 4.4 | -3.91 | Unknown | Unknown | Unknown | 8.31 | Unknown | 747.91 | 4.4 | 743.51 | Yes | N/A | N/A | 2024-04-11 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-04-11 | 78 | 56 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-04-29 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-05-20 | 1900-01-21 | 16 | 2024-05-20 | 2024-05-20 | 1 | 1 | 19 | 13 | 101 | 73 | 120 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | -596 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-17 | 2024-01-31 | IOU Designed & Installed | N/A | No | N/A | 8.03 | -9.75 | Unknown | Unknown | Unknown | 17.78 | Unknown | 974.88 | 8.03 | 966.85 | Yes | N/A | N/A | 2024-01-17 | 2023-12-01 | Unknown | Unknown | 2023-12-01 | 2024-01-19 | 50 | 36 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-01-31 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-03-15 | 1900-02-13 | 33 | 2024-03-15 | 2024-03-15 | 1 | 1 | 13 | 9 | 96 | 70 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-30 | -691 | -495 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 610.85 | -11.7 | Unknown | Unknown | Unknown | 622.55 | 3981 | 1582.63 | 610.85 | 971.78 | Yes | N/A | N/A | 2025-02-05 | 2025-02-05 | 1 | 1 | 2025-02-05 | 2025-02-05 | 1 | 1 | 2025-02-05 | Unknown | Unknown | Unknown | 2025-02-11 | 2025-02-20 | 10 | 8 | 2025-02-05 | 2025-02-25 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-10 | 1900-01-13 | 10 | 2025-03-10 | 2025-03-10 | 1 | 1 | 22 | 16 | 26 | 20 | 48 | 36 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | -631 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-04-01 | 2024-04-18 | IOU Designed & Installed | N/A | No | N/A | -16.98 | -16.15 | Unknown | Unknown | Unknown | -0.83 | 3981 | 1056.41 | -16.98 | 1073.39 | Yes | N/A | N/A | 2024-03-20 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-04-01 | 49 | 35 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-04-18 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-04-25 | 1900-01-07 | 6 | 2024-04-25 | 2024-04-25 | 1 | 1 | 18 | 14 | 58 | 42 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | -563 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-04-06 | IOU Designed & Installed | N/A | No | N/A | -5.23 | -3.78 | Unknown | Unknown | Unknown | -1.45 | Unknown | 363.72 | -5.23 | 368.95 | Yes | N/A | N/A | 2023-03-20 | 2023-03-20 | 1 | 1 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | 2023-04-06 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-05-18 | 1900-02-11 | 31 | 2023-05-18 | 2023-05-18 | 1 | 1 | 19 | 15 | 44 | 32 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -358 | -257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-10-14 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | 205087.51 | 27910.25 | Unknown | Unknown | 109.53 | 177067.73 | Unknown | 103605.46 | 205087.51 | -101482.05 | Yes | N/A | N/A | 2024-09-04 | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2025-04-03 | 238 | 170 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-02-25 | 76 | 54 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-08 | 1900-01-16 | 13 | 2025-05-08 | 2025-05-08 | 1 | 1 | 0 | 0 | 332 | 238 | 332 | 238 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 510 | 510 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-27 | -467 | -334 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | 2023-03-14 | 2023-05-23 | IOU Designed & Installed | N/A | No | N/A | 5120.38 | 2891.91 | Unknown | 908.66 | Unknown | 1319.81 | Unknown | 363.72 | 5120.38 | -4756.66 | Yes | N/A | N/A | 2023-01-30 | 2023-03-14 | 44 | 32 | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-14 | 2023-05-23 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | 2023-07-18 | 1900-02-25 | 41 | 2023-07-18 | 2023-07-18 | 1 | 1 | 115 | 83 | 58 | 42 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-17 | -656 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-08 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | 1626.96 | 622.68 | Unknown | Unknown | Unknown | 1004.28 | 3941 | 114.3 | 1626.96 | -1512.66 | Yes | N/A | N/A | 2025-04-08 | 2025-04-25 | 18 | 14 | 2025-04-25 | 2025-04-25 | 1 | 1 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-04-25 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-30 | 1900-02-04 | 26 | 2025-05-30 | 2025-05-30 | 1 | 1 | 19 | 15 | 38 | 28 | 57 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | -399 | -286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-03-29 | 2024-05-23 | IOU Designed & Installed | N/A | No | N/A | 1097.83 | 335.26 | Unknown | 36.56 | Unknown | 726.01 | 3941 | 906.88 | 1097.83 | -190.95 | Yes | N/A | N/A | 2024-03-29 | 2023-12-07 | Unknown | Unknown | 2023-12-07 | 2024-03-29 | 114 | 82 | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-05-23 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-06-27 | 1900-02-04 | 26 | 2024-06-27 | 2024-06-28 | 2 | 2 | 56 | 40 | 152 | 110 | 208 | 150 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 13.05 | 13.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -179 | -128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-12-12 | 2025-05-14 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2152.81 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-28 | 2024-12-13 | 200 | 144 | 2024-12-13 | 2025-01-10 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-01-21 | 33 | 22 | 2025-01-10 | 2025-01-24 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-06-10 | 1900-01-27 | 20 | 2025-06-10 | 2025-06-04 | Unknown | Unknown | 215 | 155 | 90 | 63 | 305 | 218 | Steps 2,3,5,6,7 | 11 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-12 | -279 | -200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 101.86 | Unknown | Unknown | Unknown | Unknown | 101.86 | Unknown | 1755.39 | 101.86 | 1653.53 | Yes | N/A | N/A | 2025-01-07 | 2025-01-09 | 3 | 3 | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | Unknown | Unknown | 2025-02-06 | 2025-02-06 | 1 | 1 | 3 | 3 | 2 | 2 | 5 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-20 | -598 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-03-02 | 2024-03-12 | IOU Designed & Installed | N/A | No | N/A | -15.55 | -12.64 | Unknown | Unknown | Unknown | -2.91 | 3981 | 501.14 | -15.55 | 516.69 | Yes | N/A | N/A | 2024-02-07 | 2023-12-20 | Unknown | Unknown | 2023-12-20 | 2024-03-02 | 74 | 53 | 2024-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-02 | 2024-03-12 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-04-01 | 1900-01-20 | 15 | 2024-04-01 | 2024-04-01 | 1 | 1 | 11 | 7 | 96 | 69 | 107 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-19 | -274 | -197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-18 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 344.44 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-04-24 | 7 | 5 | 2025-04-24 | 2025-06-10 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-16 | 16 | 12 | 2025-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-18 | 1900-01-08 | 7 | 2025-06-18 | 2025-06-18 | 1 | 1 | 7 | 5 | 74 | 54 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-08 | -670 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | 2024-06-24 | IOU Designed & Installed | N/A | No | N/A | 738.87 | 241.68 | Unknown | Unknown | Unknown | 497.19 | 3981 | 1505.47 | 738.87 | 766.6 | Yes | N/A | N/A | 2024-06-12 | 2024-06-12 | 1 | 1 | 2024-06-12 | 2024-06-12 | 1 | 1 | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-06-24 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-08-07 | 1900-02-13 | 33 | 2024-08-07 | 2024-08-07 | 1 | 1 | 14 | 10 | 47 | 35 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-11 | 485 | 346 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 11.62 | -8.96 | Unknown | Unknown | Unknown | 20.58 | 14595 | 681.38 | 11.62 | 669.76 | Yes | N/A | N/A | 2023-08-23 | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2023-09-07 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | 2024-07-02 | 38 | 28 | 2023-09-07 | 2024-06-14 | 282 | 202 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | 2024-07-16 | 2024-07-08 | Unknown | Unknown | 282 | 202 | 61 | 45 | 343 | 247 | Steps 2,3,5,6,7 | 299 | 213 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | -652 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | 2024-06-21 | IOU Designed & Installed | N/A | No | N/A | 47.81 | Unknown | Unknown | Unknown | Unknown | 47.81 | Unknown | 1452.27 | 47.81 | 1404.46 | Yes | N/A | N/A | 2024-06-04 | 2024-06-04 | 1 | 1 | 2024-06-04 | 2024-06-04 | 1 | 1 | 2024-06-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-06-21 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-08-09 | 1900-02-18 | 36 | 2024-08-09 | 2024-08-09 | 1 | 1 | 19 | 15 | 52 | 38 | 71 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | -709 | -508 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | 2024-12-02 | IOU Designed & Installed | N/A | No | N/A | 112.32 | -1.5 | Unknown | Unknown | Unknown | 113.82 | 3981 | 1491.91 | 112.32 | 1379.59 | Yes | N/A | N/A | 2024-11-25 | 2024-11-25 | 1 | 1 | 2024-11-25 | 2024-11-25 | 1 | 1 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-02 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2024-12-11 | 1900-01-09 | 8 | 2024-12-11 | 2024-12-11 | 1 | 1 | 9 | 7 | 12 | 10 | 21 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 31.2 | 31.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | -499 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1069.56 | -64.23 | Unknown | Unknown | -1640 | 2773.79 | Unknown | 1640.16 | 1069.56 | 570.6 | Yes | N/A | N/A | 2023-12-05 | 2023-09-08 | Unknown | Unknown | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-04-09 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | 2024-04-17 | 2024-04-17 | 1 | 1 | 0 | 0 | 20 | 14 | 20 | 14 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-19 | 355 | 254 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-08 | 2022-06-16 | 2024-04-08 | IOU Designed & Installed | N/A | No | N/A | 29.29 | -18.16 | Unknown | Unknown | 28.63 | 18.82 | 3885 | 3429.11 | 29.29 | 3399.82 | Yes | N/A | N/A | 2022-06-08 | 2023-06-07 | 365 | 261 | 2023-06-07 | 2023-08-29 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | Unknown | Unknown | 2024-04-08 | 2024-04-08 | 1899-12-31 | 1 | 2024-04-08 | 2024-04-08 | 1 | 1 | 365 | 261 | 86 | 62 | 451 | 323 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 45 | 45 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -710 | -508 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1070.92 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-29 | 2024-08-29 | 1 | 1 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-10 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-18 | 1900-01-08 | 7 | 2024-09-18 | 2024-09-18 | 1 | 1 | 6 | 4 | 10 | 8 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 206.05 | 206.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-01 | 240 | 173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-28 | 2023-07-28 | 2024-03-26 | IOU Designed & Installed | N/A | No | N/A | 267.2 | -23.57 | Unknown | Unknown | 16.94 | 273.83 | 3981 | 1921.17 | 267.2 | 1653.97 | Yes | N/A | N/A | 2023-07-28 | 2023-05-11 | Unknown | Unknown | 2023-05-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-12 | 2024-03-26 | 197 | 141 | Unknown | 2024-01-18 | Unknown | Unknown | 2024-03-26 | 2024-03-28 | 1900-01-02 | 3 | 2024-03-28 | 2024-03-28 | 1 | 1 | 197 | 141 | 4 | 4 | 201 | 145 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-25 | -408 | -291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-10 | 2024-05-16 | 2024-12-06 | IOU Designed & Installed | N/A | No | N/A | 2426.74 | Unknown | Unknown | Unknown | 30.07 | 2396.67 | 3981 | 1244.99 | 2426.74 | -1181.75 | Yes | N/A | N/A | 2024-05-10 | 2024-06-11 | 33 | 23 | 2024-06-11 | 2024-06-21 | 11 | 9 | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-12-06 | 170 | 122 | Unknown | 2024-12-04 | Unknown | Unknown | 2024-12-06 | 2024-12-13 | 1900-01-07 | 6 | 2024-12-13 | 2024-12-13 | 1 | 1 | 203 | 145 | 20 | 16 | 223 | 161 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-09 | -702 | -503 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | Unknown | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 101.21 | -1.5 | Unknown | Unknown | Unknown | 102.71 | 3981 | 1560.16 | 101.21 | 1458.95 | Yes | N/A | N/A | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-10-23 | 2024-10-23 | 1 | 1 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-10-29 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-11-06 | 1900-01-08 | 7 | 2024-11-06 | 2024-11-06 | 1 | 1 | 8 | 6 | 11 | 9 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-26 | -557 | -399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | 2025-05-01 | IOU Designed & Installed | N/A | No | N/A | 77.72 | Unknown | Unknown | Unknown | Unknown | 77.72 | 3981 | 1560.56 | 77.72 | 1482.84 | Yes | N/A | N/A | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | 2025-01-08 | 1 | 1 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-05-01 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-06-17 | 1900-02-16 | 34 | 2025-06-17 | 2025-06-17 | 1 | 1 | 115 | 83 | 50 | 36 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | Santee | Santee | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-04 | 338 | 243 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | 2024-12-13 | IOU Designed & Installed | N/A | No | N/A | 31588.54 | 533.35 | Unknown | Unknown | 201.12 | 30854.07 | Unknown | 5141.82 | 31588.54 | -26446.72 | Yes | N/A | N/A | 2024-05-09 | 2024-05-09 | 1 | 1 | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-12-30 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-02-05 | 1900-02-23 | 39 | 2025-02-05 | 2025-02-05 | 1 | 1 | 1 | 1 | 117 | 83 | 118 | 84 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-17 | -329 | -236 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-06-16 | 2024-04-10 | IOU Designed & Installed | N/A | No | N/A | 14.69 | -13.06 | Unknown | Unknown | Unknown | 27.75 | 3981 | 848.3 | 14.69 | 833.61 | Yes | N/A | N/A | 2023-06-02 | 2023-06-16 | 15 | 11 | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2024-04-10 | 300 | 214 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-04-23 | 1900-01-13 | 10 | 2024-04-23 | 2024-04-22 | Unknown | Unknown | 315 | 225 | 14 | 10 | 329 | 235 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 5760 | 5760 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-09-24 | -593 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2024-01-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 491.69 | -19.31 | Unknown | Unknown | Unknown | 511 | 3981 | 933.16 | 491.69 | 441.47 | Yes | N/A | N/A | 2023-12-21 | 2024-01-04 | 15 | 11 | 2024-01-04 | 2024-01-04 | 1 | 1 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-02-09 | 1 | 1 | 15 | 11 | 2 | 2 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | BORREGO SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-31 | -716 | -513 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | 2023-11-13 | IOU Designed & Installed | N/A | No | N/A | 475.51 | 122.45 | Unknown | 117.92 | Unknown | 235.14 | 3241 | 626.42 | 475.51 | 150.91 | Yes | N/A | N/A | 2023-11-01 | 2023-11-13 | 13 | 9 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2023-11-13 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2023-11-15 | 1900-01-02 | 3 | 2023-11-15 | 2023-11-15 | 1 | 1 | 14 | 10 | 4 | 4 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-02 | -216 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | 2024-02-13 | 2024-03-06 | IOU Designed & Installed | N/A | No | N/A | 351.91 | -17.3 | Unknown | Unknown | Unknown | 369.21 | 3941 | 926.83 | 351.91 | 574.92 | Yes | N/A | N/A | 2024-02-13 | 2024-01-17 | Unknown | Unknown | 2024-01-17 | 2024-02-13 | 28 | 20 | 2024-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-03-06 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-03-26 | 1900-01-20 | 15 | 2024-03-26 | 2024-05-31 | 67 | 49 | 23 | 17 | 116 | 84 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-26 | -271 | -194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-10 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | 3055.55 | -142.6 | Unknown | Unknown | Unknown | 3198.15 | 3981 | 1211.69 | 3055.55 | -1843.86 | Yes | N/A | N/A | 2024-04-10 | 2024-04-05 | Unknown | Unknown | 2024-04-05 | 2024-04-10 | 6 | 4 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-06-17 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-06-28 | 1900-01-11 | 10 | 2024-06-28 | 2024-06-28 | 1 | 1 | 69 | 49 | 19 | 15 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | 41805 | 41805 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-12-27 | 63 | 46 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-20 | 2024-02-22 | IOU Designed & Installed | N/A | No | N/A | 6619.06 | Unknown | Unknown | Unknown | Unknown | 6619.06 | Unknown | 4222.25 | 6619.06 | -2396.81 | Yes | N/A | N/A | 2023-11-09 | 2023-10-24 | Unknown | Unknown | 2023-10-24 | 2024-01-23 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-02-28 | 1900-01-06 | 5 | 2024-02-28 | 2024-02-28 | 1 | 1 | 0 | 0 | 100 | 72 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 79 | 79 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-24 | -474 | -340 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-05 | 2023-01-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2632.38 | -12.21 | Unknown | Unknown | 52.82 | 2591.77 | 3981 | 567.45 | 2632.38 | -2064.93 | Yes | N/A | N/A | 2023-01-05 | 2023-02-16 | 43 | 31 | 2023-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-16 | Unknown | Unknown | Unknown | Unknown | 2023-04-26 | Unknown | Unknown | Unknown | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2023-05-08 | Unknown | Unknown | 43 | 31 | 0 | 0 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 32 | 32 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-16 | -22 | -17 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2155.63 | -42.23 | Unknown | Unknown | 2.2 | 2195.66 | 19905 | 827.16 | 2155.63 | -1328.47 | Yes | N/A | N/A | 2024-09-05 | 2024-08-20 | Unknown | Unknown | 2024-08-20 | 2024-11-19 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-01-24 | 19 | 15 | 2024-11-19 | 2025-03-21 | 123 | 89 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-03-25 | Unknown | Unknown | 123 | 89 | 111 | 81 | 234 | 170 | Steps 2,3,5,6,7 | 66 | 48 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | -476 | -341 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-08 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 1740.11 | 1069.08 | Unknown | 36.04 | Unknown | 634.99 | 54899 | 81.53 | 1740.11 | -1658.58 | Yes | N/A | N/A | 2024-03-06 | 2024-08-16 | 164 | 118 | 2024-08-16 | 2024-08-29 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-07-16 | 53 | 39 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | Unknown | Unknown | 2024-11-14 | 2024-11-14 | 1899-12-31 | 1 | 2024-11-14 | 2024-11-14 | 1 | 1 | 164 | 118 | 69 | 51 | 233 | 169 | Steps 2,3,5,6,7 | 11 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-15 | -694 | -497 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-01-24 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 33.83 | Unknown | Unknown | Unknown | Unknown | 33.83 | 3981 | 1519.94 | 33.83 | 1486.11 | Yes | N/A | N/A | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-02-11 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-02-20 | 1900-01-09 | 8 | 2025-02-20 | 2025-02-20 | 1 | 1 | 20 | 14 | 12 | 10 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | 8610 | 8610 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-01-17 | 76 | 55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-03-18 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | 6432.4 | 7214.84 | Unknown | 1514.11 | -23694 | 21397.45 | 0 | 22566.47 | 6432.4 | 16134.07 | Yes | N/A | N/A | 2024-01-24 | 2024-03-06 | 43 | 31 | 2024-03-06 | 2024-10-17 | 226 | 162 | 2024-05-14 | 2025-02-26 | 236 | 170 | 2024-07-02 | 2025-03-06 | 120 | 86 | 2024-10-23 | Unknown | Unknown | Unknown | 2024-10-23 | 2025-02-04 | 105 | 75 | 2025-03-31 | 2025-04-03 | 1900-01-03 | 4 | 2025-04-03 | 2025-04-03 | 1 | 1 | 279 | 201 | 456 | 328 | 735 | 529 | Steps 2,3,5,6,7 | 529 | 379 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-27 | -612 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-23 | 2025-01-14 | IOU Designed & Installed | N/A | No | N/A | 73.13 | Unknown | Unknown | Unknown | Unknown | 73.13 | Unknown | 1498.12 | 73.13 | 1424.99 | Yes | N/A | N/A | 2024-10-23 | 2024-11-05 | 14 | 10 | 2024-11-05 | 2024-11-11 | 7 | 5 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-01-14 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-01-23 | 1900-01-09 | 8 | 2025-01-23 | 2025-01-23 | 1 | 1 | 15 | 11 | 18 | 14 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 200 | 200 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-11 | -48 | -35 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-02-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4.85 | Unknown | Unknown | Unknown | Unknown | 4.85 | 3981 | 363.72 | 4.85 | 358.87 | Yes | N/A | N/A | 2023-01-23 | 2023-02-21 | 30 | 22 | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | Unknown | Unknown | 2024-09-24 | 2024-09-24 | 1 | 1 | 30 | 22 | 1 | 1 | 31 | 23 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-23 | 277 | 198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2023-11-07 | 2024-01-09 | IOU Designed & Installed | N/A | No | N/A | 25450.11 | 453.89 | Unknown | 149.61 | 0.43 | 24846.18 | 0 | 9048.4 | 25450.11 | -16401.71 | Yes | N/A | N/A | 2023-11-02 | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-11-20 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2023-11-30 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2025-02-24 | 1901-02-16 | 295 | 2025-02-24 | 2025-02-24 | 1 | 1 | 0 | 0 | 509 | 365 | 509 | 365 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 65 | 65 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-19 | -324 | -232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2024-02-01 | 2024-08-12 | IOU Designed & Installed | N/A | No | N/A | 30.69 | Unknown | Unknown | Unknown | Unknown | 30.69 | 3981 | 952.55 | 30.69 | 921.86 | Yes | N/A | N/A | 2023-10-05 | 2024-02-02 | 121 | 87 | 2024-02-02 | 2024-02-02 | 1 | 1 | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-08-12 | 194 | 138 | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-08-29 | 1900-01-17 | 14 | 2024-08-29 | 2024-08-29 | 1 | 1 | 315 | 225 | 20 | 16 | 335 | 241 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 6.05 | 6.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-05 | -534 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-21 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | 116.47 | -9.64 | Unknown | Unknown | Unknown | 126.11 | 3981 | 959.71 | 116.47 | 843.24 | Yes | N/A | N/A | 2024-02-15 | 2023-12-15 | Unknown | Unknown | 2023-12-15 | 2024-02-21 | 69 | 49 | 2024-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-04-17 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-04-19 | 1900-01-02 | 3 | 2024-04-19 | 2024-04-19 | 1 | 1 | 57 | 41 | 73 | 53 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA NIGUEL | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-08 | 182 | 131 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2506.74 | 462.75 | Unknown | 532.16 | -446.15 | 1957.98 | 0 | 534.34 | 2506.74 | -1972.4 | Yes | N/A | N/A | 2023-04-19 | 2023-05-01 | 13 | 9 | 2023-05-01 | 2024-06-27 | 424 | 304 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-06-10 | Unknown | Unknown | Unknown | 2024-06-27 | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-08 | Unknown | Unknown | 13 | 9 | 424 | 304 | 437 | 313 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-08 | -128 | -93 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-11-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5493.11 | 2145.69 | Unknown | Unknown | -1130 | 4477.42 | 3981 | 1722.46 | 5493.11 | -3770.65 | Yes | N/A | N/A | 2023-05-15 | 2023-10-13 | 152 | 110 | 2023-10-13 | 2024-02-26 | 137 | 97 | 2024-02-20 | 2024-02-20 | 1 | 1 | 2024-02-08 | 2024-02-16 | 9 | 7 | 2024-02-26 | 2024-03-07 | 11 | 9 | Unknown | 2024-02-29 | Unknown | Unknown | Unknown | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-04-02 | Unknown | Unknown | 164 | 120 | 146 | 104 | 310 | 224 | Steps 2,3,5,6,7 | 18 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-25 | -66 | -47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | 604.69 | -16.39 | Unknown | Unknown | 5.49 | 615.59 | 3941 | 785.7 | 604.69 | 181.01 | Yes | N/A | N/A | 2023-11-01 | 2023-09-08 | Unknown | Unknown | 2023-09-08 | 2023-11-01 | 55 | 39 | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2024-05-30 | 212 | 152 | Unknown | 2024-05-09 | Unknown | Unknown | 2024-05-30 | 2024-06-20 | 1900-01-21 | 16 | 2024-06-20 | 2024-06-20 | 1 | 1 | 212 | 152 | 78 | 56 | 290 | 208 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 52.3 | 52.3 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-05 | -118 | -85 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-14 | 2024-06-14 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 1126.65 | Unknown | Unknown | Unknown | 19.15 | 1107.5 | 3981 | 2650.28 | 1126.65 | 1523.63 | Yes | N/A | N/A | 2024-06-14 | 2024-04-30 | Unknown | Unknown | 2024-04-30 | 2024-06-20 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | 2024-10-01 | 2024-11-07 | 1900-02-06 | 28 | 2024-11-07 | 2024-11-07 | 1 | 1 | 0 | 0 | 91 | 67 | 91 | 67 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | -618 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 5.28 | Unknown | Unknown | Unknown | Unknown | 5.28 | Unknown | 997.93 | 5.28 | 992.65 | Yes | N/A | N/A | 2025-01-29 | 2025-01-16 | Unknown | Unknown | 2025-01-16 | 2025-01-29 | 14 | 10 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-03-05 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-24 | 1900-01-19 | 14 | 2025-03-24 | 2025-03-24 | 1 | 1 | 36 | 26 | 35 | 25 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | -295 | -212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-02-26 | 2024-03-12 | IOU Designed & Installed | N/A | No | N/A | -25.02 | -21.37 | Unknown | Unknown | Unknown | -3.65 | Unknown | 158.37 | -25.02 | 183.39 | Yes | N/A | N/A | 2024-02-26 | 2024-01-30 | Unknown | Unknown | 2024-01-30 | 2024-03-12 | 43 | 31 | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-03-12 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-03-28 | 1900-01-16 | 13 | 2024-03-28 | 2024-03-28 | 1 | 1 | 1 | 1 | 61 | 45 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 164.1 | 164.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-03 | -326 | -234 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-10-18 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 1432.72 | -14.79 | Unknown | Unknown | 28.93 | 1418.58 | 3981 | 737.9 | 1432.72 | -694.82 | Yes | N/A | N/A | 2023-10-18 | 2023-07-18 | Unknown | Unknown | 2023-07-18 | 2024-01-26 | 193 | 139 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-06-10 | 137 | 97 | Unknown | 2024-06-10 | Unknown | Unknown | 2024-06-10 | 2024-06-13 | 1900-01-03 | 4 | 2024-06-13 | 2024-06-11 | Unknown | Unknown | 137 | 97 | 197 | 143 | 334 | 240 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-06 | 305 | 218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2024-03-11 | 2024-12-23 | IOU Designed & Installed | N/A | No | N/A | 4.43 | Unknown | Unknown | Unknown | Unknown | 4.43 | 27449 | 584.27 | 4.43 | 579.84 | Yes | N/A | N/A | 2023-09-08 | 2024-02-15 | 161 | 115 | 2024-02-15 | 2024-05-20 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | Unknown | Unknown | 2024-12-23 | 2025-02-05 | 1900-02-13 | 33 | 2025-02-05 | 2025-02-05 | 1 | 1 | 161 | 115 | 142 | 102 | 303 | 217 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-24 | -51 | -36 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 391.46 | -20.94 | Unknown | Unknown | 58.67 | 353.73 | Unknown | 446.56 | 391.46 | 55.1 | Yes | N/A | N/A | 2023-05-16 | 2023-05-25 | 10 | 8 | 2023-05-25 | 2023-07-12 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2023-05-25 | 2023-06-14 | 21 | 15 | 2023-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2024-02-02 | 1 | 1 | 10 | 8 | 71 | 51 | 81 | 59 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | -428 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-10-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1167.62 | -46.67 | Unknown | Unknown | 2.36 | 1211.93 | 19905 | 853.19 | 1167.62 | -314.43 | Yes | N/A | N/A | 2023-10-23 | 2023-10-25 | 3 | 3 | 2023-10-25 | 2023-11-15 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2023-11-09 | 4 | 4 | 2023-11-15 | 2024-03-13 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-13 | Unknown | Unknown | 123 | 89 | 26 | 20 | 149 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-28 | -537 | -384 | No | 2024-02-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-29 | 2024-06-20 | IOU Designed & Installed | N/A | Yes | 143 | 1346.61 | -10.66 | Unknown | Unknown | 10.42 | 1346.85 | 3981 | 808.64 | 1346.61 | -537.97 | Yes | N/A | N/A | 2024-02-16 | 2024-07-08 | 144 | 102 | 2024-07-08 | 2024-07-08 | 1 | 1 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-06-20 | 78 | 56 | Unknown | 2024-06-18 | Unknown | Unknown | 2024-06-20 | 2024-07-10 | 1900-01-20 | 15 | 2024-07-10 | 2024-07-09 | Unknown | Unknown | 222 | 158 | 22 | 16 | 244 | 174 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | San Clemente | SAN CLEMENTE | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-22 | 285 | 204 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-09-20 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | 34478.11 | 1929.73 | Unknown | Unknown | 198.94 | 32349.44 | Unknown | 18828.06 | 34478.11 | -15650.05 | Yes | N/A | N/A | 2024-06-12 | 2024-07-22 | 41 | 29 | 2024-07-22 | 2025-01-02 | 165 | 119 | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-12-19 | 36 | 26 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-03-03 | 1900-02-16 | 34 | 2025-03-03 | 2025-03-03 | 1 | 1 | 41 | 29 | 250 | 180 | 291 | 209 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 19 | 19 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-11 | -610 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | 2025-01-17 | IOU Designed & Installed | N/A | No | N/A | 3920.6 | 703.16 | Unknown | Unknown | Unknown | 3217.44 | Unknown | 1949.41 | 3920.6 | -1971.19 | Yes | N/A | N/A | 2024-12-11 | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2024-12-26 | 36 | 26 | 2024-12-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-01-17 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | 2025-03-11 | 1900-02-22 | 38 | 2025-03-11 | 2025-03-11 | 1 | 1 | 23 | 17 | 91 | 65 | 114 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-22 | -606 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-04-08 | 2024-04-08 | IOU Designed & Installed | N/A | No | N/A | 562.37 | -30.29 | Unknown | Unknown | Unknown | 592.66 | 3981 | 677.09 | 562.37 | 114.72 | Yes | N/A | N/A | 2024-03-07 | 2024-01-11 | Unknown | Unknown | 2024-01-11 | 2024-04-08 | 89 | 63 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | 2024-04-08 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | 2024-04-25 | 1900-01-17 | 14 | 2024-04-25 | 2024-04-25 | 1 | 1 | 1 | 1 | 108 | 78 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | Encinitas | ENCINITAS | 83 | 83 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-09 | 283 | 203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | 2024-10-30 | IOU Designed & Installed | N/A | No | N/A | 531.68 | 302.64 | Unknown | 34.68 | Unknown | 194.36 | Unknown | 6454 | 531.68 | 5922.32 | Yes | N/A | N/A | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-08-27 | 27 | 19 | 2024-10-29 | 2024-10-30 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2025-03-19 | 1900-05-20 | 101 | 2025-03-19 | 2025-03-19 | 1 | 1 | 3 | 3 | 169 | 121 | 172 | 124 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-16 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-05 | 2023-10-20 | IOU Designed & Installed | N/A | No | N/A | 0.38 | -10.95 | Unknown | Unknown | Unknown | 11.33 | 3981 | 889.46 | 0.38 | 889.08 | Yes | N/A | N/A | 2023-10-05 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2023-10-05 | 98 | 70 | 2023-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-10-20 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2023-10-25 | 1900-01-05 | 4 | 2023-10-25 | 2023-10-25 | 1 | 1 | 16 | 12 | 105 | 75 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-30 | -508 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-04-11 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 2.88 | Unknown | Unknown | Unknown | -834 | 836.88 | Unknown | 833.7 | 2.88 | 830.82 | Yes | N/A | N/A | 2024-03-18 | 2023-12-29 | Unknown | Unknown | 2023-12-29 | 2024-04-11 | 105 | 75 | 2024-04-11 | 2024-04-26 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2024-07-23 | 89 | 63 | Unknown | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2024-08-09 | 1900-01-17 | 14 | 2024-08-09 | 2024-08-09 | 1 | 1 | 105 | 75 | 124 | 90 | 229 | 165 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-17 | -541 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-14 | 2024-01-03 | IOU Designed & Installed | N/A | No | N/A | 252.8 | -14.74 | Unknown | Unknown | Unknown | 267.54 | 3981 | 981.88 | 252.8 | 729.08 | Yes | N/A | N/A | 2023-12-05 | 2023-07-27 | Unknown | Unknown | 2023-07-27 | 2023-12-14 | 141 | 101 | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2024-01-03 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2024-01-23 | 1900-01-20 | 15 | 2024-01-23 | 2024-01-23 | 1 | 1 | 21 | 15 | 163 | 117 | 184 | 132 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-24 | -181 | -130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-06-01 | 2023-09-16 | IOU Designed & Installed | N/A | No | N/A | 4011.82 | 2254.08 | Unknown | 5681.85 | -5524 | 1599.89 | Unknown | 5523.59 | 4011.82 | 1511.77 | Yes | N/A | N/A | 2023-06-01 | 2023-06-01 | 1 | 1 | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-16 | 2023-09-25 | 1900-01-09 | 6 | 2023-09-25 | 2023-09-25 | 1 | 1 | 1 | 1 | 11 | 7 | 12 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 2615179 | 2615179 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-09-05 | -111 | -80 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-04-05 | 2023-05-09 | IOU Designed & Installed | N/A | No | N/A | 16227.42 | -161.04 | Unknown | Unknown | Unknown | 16388.46 | Unknown | 8492.25 | 16227.42 | -7735.17 | Yes | N/A | N/A | 2023-03-22 | 2023-04-26 | 36 | 26 | 2023-04-26 | 2023-05-02 | 7 | 5 | 2023-04-21 | 2023-04-29 | 9 | 6 | 2023-04-20 | 2023-05-09 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-09 | 2023-05-17 | 1900-01-08 | 7 | 2023-05-17 | 2023-05-17 | 1 | 1 | 45 | 32 | 30 | 22 | 75 | 54 | Steps 2,3,5,6,7 | 20 | 13 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-15 | 84 | 61 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-03-17 | 2023-11-28 | IOU Designed & Installed | N/A | No | N/A | 104499.99 | 19944.78 | Unknown | Unknown | 2441.28 | 82113.93 | 370014 | 82234.72 | 104499.99 | -22265.27 | Yes | N/A | N/A | 2023-02-09 | 2023-03-03 | 23 | 17 | 2023-03-03 | 2023-10-30 | 242 | 172 | 2023-06-28 | 2023-10-18 | 68 | 50 | 2023-05-09 | 2024-02-21 | 181 | 129 | 2023-10-30 | 2024-01-04 | 67 | 49 | Unknown | 2024-02-23 | Unknown | Unknown | 2023-11-28 | 2024-03-08 | 1900-04-11 | 74 | 2024-03-08 | 2024-03-08 | 1 | 1 | 158 | 116 | 526 | 376 | 684 | 492 | Steps 2,3,5,6,7 | 487 | 349 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-04 | -577 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | -0.68 | -2.04 | Unknown | Unknown | Unknown | 1.36 | Unknown | 216 | -0.68 | 216.68 | Yes | N/A | N/A | 2023-03-09 | 2023-03-24 | 16 | 12 | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | Unknown | 2023-06-07 | Unknown | Unknown | 2023-06-07 | 2023-06-07 | 1 | 1 | 16 | 12 | 1 | 1 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-12 | -476 | -341 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-06-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2829.42 | Unknown | Unknown | Unknown | 10.64 | 2818.78 | 3981 | 942.35 | 2829.42 | -1887.07 | Yes | N/A | N/A | 2024-06-28 | 2024-05-30 | Unknown | Unknown | 2024-05-30 | 2024-07-26 | 58 | 42 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2024-11-21 | 1 | 1 | 0 | 0 | 59 | 43 | 59 | 43 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 106.05 | 106.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | -534 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 542.95 | Unknown | Unknown | Unknown | 17.51 | 525.44 | 3981 | 1210 | 542.95 | 667.05 | Yes | N/A | N/A | 2024-09-25 | 2024-10-15 | 21 | 15 | 2024-10-15 | 2024-10-15 | 1 | 1 | 2024-10-15 | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-03 | 1 | 1 | 2024-10-15 | 2025-03-05 | 142 | 102 | Unknown | 2025-03-03 | Unknown | Unknown | 2025-03-05 | 2025-03-19 | 1900-01-14 | 11 | 2025-03-19 | 2025-03-19 | 1 | 1 | 163 | 117 | 18 | 14 | 181 | 131 | Steps 2,3,5,6,7 | 139 | 99 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | -520 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-17 | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 532.99 | -10.2 | Unknown | Unknown | Unknown | 543.19 | 3981 | 1394.09 | 532.99 | 861.1 | Yes | N/A | N/A | 2024-07-17 | 2024-07-17 | 1 | 1 | 2024-07-17 | 2024-07-17 | 1 | 1 | 2024-07-17 | Unknown | Unknown | Unknown | 2024-07-22 | 2024-08-19 | 29 | 21 | 2024-07-17 | 2025-01-21 | 189 | 135 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | 2025-02-04 | 1900-01-14 | 11 | 2025-02-04 | 2025-02-04 | 1 | 1 | 190 | 136 | 46 | 34 | 236 | 170 | Steps 2,3,5,6,7 | 33 | 23 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 114.05 | 114.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-08 | 509 | 364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-03 | 2024-02-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4889.47 | Unknown | Unknown | Unknown | Unknown | 4889.47 | 3981 | 844.81 | 4889.47 | -4044.66 | Yes | N/A | N/A | 2022-10-03 | 2023-07-31 | 302 | 216 | 2023-07-31 | 2024-04-11 | 256 | 184 | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-04-24 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-10-29 | Unknown | Unknown | 302 | 216 | 279 | 201 | 581 | 417 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-11 | -559 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-29 | 2023-08-02 | IOU Designed & Installed | N/A | No | N/A | -14.64 | -10.61 | Unknown | Unknown | Unknown | -4.03 | Unknown | 480.44 | -14.64 | 495.08 | Yes | N/A | N/A | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | 2023-08-02 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | 2023-08-30 | 1900-01-28 | 21 | 2023-08-30 | 2023-08-30 | 1 | 1 | 36 | 26 | 31 | 23 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 169.75 | 169.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-08 | -605 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-30 | 2024-06-04 | IOU Designed & Installed | N/A | No | N/A | 593.33 | 370.02 | Unknown | Unknown | Unknown | 223.31 | Unknown | 1050.61 | 593.33 | 457.28 | Yes | N/A | N/A | 2024-05-30 | 2024-05-30 | 1 | 1 | 2024-05-30 | 2024-05-30 | 1 | 1 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-04 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-07-11 | 1900-02-06 | 28 | 2024-07-11 | 2024-07-11 | 1 | 1 | 7 | 5 | 40 | 30 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-26 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-12 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | 110.69 | Unknown | Unknown | Unknown | 2.2 | 108.49 | Unknown | 1585.76 | 110.69 | 1475.07 | Yes | N/A | N/A | 2024-08-05 | 2024-08-12 | 8 | 6 | 2024-08-12 | 2024-08-12 | 1 | 1 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-09-16 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-09-20 | 1900-01-04 | 5 | 2024-09-20 | 2024-09-20 | 1 | 1 | 44 | 32 | 7 | 7 | 51 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 295 | 295 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-23 | -155 | -112 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-07-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 288.87 | Unknown | Unknown | Unknown | Unknown | 288.87 | 3981 | 1326.24 | 288.87 | 1037.37 | Yes | N/A | N/A | 2024-07-31 | 2024-08-01 | 2 | 2 | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | Unknown | Unknown | 2024-11-19 | 2024-11-19 | 1 | 1 | 2 | 2 | 2 | 2 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-24 | -367 | -262 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2024-01-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1006.24 | Unknown | Unknown | Yes | N/A | N/A | 2023-12-19 | 2023-12-29 | 11 | 9 | 2023-12-29 | 2024-08-01 | 217 | 155 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | Unknown | Unknown | 2024-08-22 | 2024-08-22 | 1 | 1 | 11 | 9 | 218 | 156 | 229 | 165 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 72 | 72 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-07 | -653 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | 2025-03-27 | IOU Designed & Installed | N/A | No | N/A | 1871.91 | 388.41 | Unknown | Unknown | 3.52 | 1479.98 | 3981 | 1362.98 | 1871.91 | -508.93 | Yes | N/A | N/A | 2025-02-18 | 2025-02-24 | 7 | 5 | 2025-02-24 | 2025-02-25 | 2 | 2 | 2025-02-24 | 2025-02-25 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | 2025-03-27 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-25 | 1900-01-29 | 22 | 2025-04-25 | 2025-04-25 | 1 | 1 | 40 | 30 | 33 | 25 | 73 | 55 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | EL CAJON | 36550.2 | 36550.2 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-02-01 | 136 | 97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-16 | 2025-06-17 | IOU Designed & Installed | N/A | No | N/A | 4199.75 | 1115.62 | Unknown | Unknown | Unknown | 3084.13 | 7962 | 2391.07 | 4199.75 | -1808.68 | Yes | N/A | N/A | 2024-08-16 | 2024-10-01 | 47 | 33 | 2024-10-01 | 2025-03-03 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-24 | 27 | 19 | 2025-03-03 | 2025-05-23 | 82 | 60 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-06-17 | 1899-12-31 | 1 | 2025-06-17 | 2025-06-17 | 1 | 1 | 129 | 93 | 183 | 131 | 312 | 224 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-27 | 101 | 74 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | 2022-08-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1089.69 | -8.4 | Unknown | Unknown | 10.98 | 1087.11 | 3981 | 728.63 | 1089.69 | -361.06 | Yes | N/A | N/A | 2022-08-12 | 2023-05-17 | 279 | 199 | 2023-05-17 | 2023-06-30 | 45 | 33 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | Unknown | Unknown | Unknown | 2023-10-06 | Unknown | Unknown | 2023-10-06 | 2023-10-06 | 1 | 1 | 279 | 199 | 46 | 34 | 325 | 233 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-26 | -673 | -482 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | 4.28 | -3.76 | Unknown | Unknown | Unknown | 8.04 | Unknown | 307.58 | 4.28 | 303.3 | Yes | N/A | N/A | 2024-05-14 | 2024-03-28 | Unknown | Unknown | 2024-03-28 | 2024-05-14 | 48 | 34 | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-05-14 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-05-22 | 1900-01-08 | 7 | 2024-05-22 | 2024-05-22 | 1 | 1 | 1 | 1 | 58 | 42 | 59 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-27 | -558 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | 2024-06-11 | IOU Designed & Installed | N/A | No | N/A | 2787.55 | 362.24 | Unknown | Unknown | Unknown | 2425.31 | 3941 | 1119.18 | 2787.55 | -1668.37 | Yes | N/A | N/A | 2024-04-16 | 2024-02-06 | Unknown | Unknown | 2024-02-06 | 2024-04-18 | 73 | 53 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-06-11 | 55 | 39 | Unknown | 2024-06-11 | Unknown | Unknown | 2024-06-11 | 2024-06-17 | 1900-01-06 | 5 | 2024-06-17 | 2024-06-17 | 1 | 1 | 55 | 39 | 81 | 59 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 27 | 27 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-10 | -20 | -15 | No | 2023-01-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-05 | 2023-01-06 | 2023-08-29 | IOU Designed & Installed | N/A | Yes | 1 | 947 | 545.22 | Unknown | 56.67 | Unknown | 345.11 | Unknown | 153.75 | 947 | -793.25 | Yes | N/A | N/A | 2023-01-05 | 2023-05-19 | 135 | 97 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2023-08-29 | 103 | 73 | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2023-09-20 | 1900-01-22 | 17 | 2023-09-20 | 2023-09-20 | 1 | 1 | 238 | 170 | 24 | 18 | 262 | 188 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-04 | -387 | -278 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-09-16 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 40.59 | Unknown | Unknown | Unknown | 5.68 | 34.91 | 3981 | 1554.45 | 40.59 | 1513.86 | Yes | N/A | N/A | 2024-04-25 | 2024-09-06 | 135 | 97 | 2024-09-06 | 2024-09-16 | 11 | 7 | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-10-01 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2025-02-10 | 1900-05-12 | 95 | 2025-02-10 | 2025-02-10 | 1 | 1 | 151 | 109 | 145 | 103 | 296 | 212 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | JAMUL | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-29 | 211 | 151 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-26 | 2023-09-26 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | 164490.46 | 61623.71 | Unknown | 5591.05 | -20580.06 | 117855.76 | 5680 | 58829.64 | 164490.46 | -105660.82 | Yes | N/A | N/A | 2023-09-26 | 2024-03-26 | 183 | 131 | 2024-03-26 | 2024-05-07 | 43 | 31 | 2023-11-03 | 2024-04-29 | 34 | 24 | 2024-01-11 | 2024-05-21 | 26 | 18 | 2024-05-10 | Unknown | Unknown | Unknown | 2024-05-10 | 2024-10-14 | 158 | 112 | 2024-10-21 | 2025-04-28 | 1900-07-08 | 136 | 2025-04-28 | 2025-04-28 | 1 | 1 | 217 | 155 | 418 | 298 | 635 | 453 | Steps 2,3,5,6,7 | 306 | 216 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-28 | -562 | -403 | No | 2023-11-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-12-04 | 2024-01-26 | IOU Designed & Installed | N/A | Yes | 66 | -8.73 | -7.07 | Unknown | Unknown | Unknown | -1.66 | 3961 | 1124.96 | -8.73 | 1133.69 | Yes | N/A | N/A | 2023-11-14 | 2024-01-12 | 60 | 44 | 2024-01-12 | 2024-01-19 | 8 | 6 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2024-01-26 | 54 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-02-13 | 1900-01-18 | 13 | 2024-02-13 | 2024-02-13 | 1 | 1 | 114 | 84 | 28 | 20 | 142 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-18 | -698 | -499 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2024-08-23 | 2024-09-04 | IOU Designed & Installed | N/A | No | N/A | 42.01 | Unknown | Unknown | Unknown | Unknown | 42.01 | 3981 | 1426.5 | 42.01 | 1384.49 | Yes | N/A | N/A | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-09-04 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-19 | 1900-01-15 | 12 | 2024-09-19 | 2024-09-19 | 1 | 1 | 14 | 10 | 18 | 14 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -370 | -265 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-02 | 2021-12-02 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 258046.71 | 47050.49 | Unknown | Unknown | 16331.01 | 194665.21 | 796328 | 157358.04 | 258046.71 | -100688.67 | Yes | N/A | N/A | 2021-12-02 | 2023-03-30 | 484 | 346 | 2023-03-30 | 2023-09-15 | 170 | 122 | 2023-04-14 | 2023-08-30 | 55 | 39 | 2023-06-06 | 2025-01-17 | 112 | 82 | 2023-11-13 | Unknown | Unknown | Unknown | 2023-11-13 | 2024-10-29 | 352 | 252 | Unknown | 2024-12-26 | Unknown | Unknown | 2024-12-26 | 2024-12-26 | 1 | 1 | 539 | 385 | 635 | 457 | 1174 | 842 | Steps 2,3,5,6,7 | 670 | 480 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-05 | -482 | -345 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | 2025-02-14 | IOU Designed & Installed | N/A | No | N/A | 1453.8 | -28.55 | Unknown | Unknown | Unknown | 1482.35 | 3981 | 1895.69 | 1453.8 | 441.89 | Yes | N/A | N/A | 2024-10-18 | 2024-10-02 | Unknown | Unknown | 2024-10-02 | 2024-10-18 | 17 | 13 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2025-02-14 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-10 | 1900-01-24 | 17 | 2025-03-10 | 2025-03-10 | 1 | 1 | 120 | 86 | 43 | 31 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | 24 | 17 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1143.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-06 | 2025-04-29 | Unknown | Unknown | 2025-04-29 | 2025-05-06 | 8 | 6 | 2025-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-06-23 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-06-23 | 2025-06-24 | 1900-01-01 | 2 | 2025-06-24 | 2025-06-24 | 1 | 1 | 49 | 35 | 11 | 9 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-13 | -594 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 452.3 | -9.28 | Unknown | Unknown | 38.39 | 423.19 | 3981 | 442.5 | 452.3 | -9.8 | Yes | N/A | N/A | 2023-03-01 | 2023-04-19 | 50 | 36 | 2023-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-19 | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | 2023-10-02 | 2023-06-30 | Unknown | Unknown | 50 | 36 | 0 | 0 | 50 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 2026.05 | 2026.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-09-19 | -119 | -86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 26578.61 | 9341.76 | Unknown | 745.48 | 65.07 | 16426.3 | 3981 | 2200.26 | 26578.61 | -24378.35 | Yes | N/A | N/A | 2023-10-13 | 2024-01-12 | 92 | 66 | 2024-01-12 | 2024-01-12 | 1 | 1 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | 2024-05-23 | 2024-05-23 | 1 | 1 | 92 | 66 | 2 | 2 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-15 | -344 | -247 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -216.54 | -10.25 | Unknown | Unknown | -901 | 694.71 | Unknown | 900.71 | -216.54 | 1117.25 | Yes | N/A | N/A | 2024-01-09 | 2023-11-30 | Unknown | Unknown | 2023-11-30 | 2024-03-07 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-08-21 | 18 | 14 | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-09-05 | 1 | 1 | 0 | 0 | 118 | 86 | 118 | 86 | Steps 2,3,5,6,7 | 167 | 119 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-25 | -59 | -42 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-10 | 2025-06-06 | IOU Designed & Installed | N/A | No | N/A | 402.04 | Unknown | Unknown | Unknown | 4.33 | 397.71 | Unknown | 13710.57 | 402.04 | 13308.53 | Yes | N/A | N/A | 2025-01-10 | 2025-01-15 | 6 | 4 | 2025-01-15 | 2025-05-21 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-05-20 | 28 | 20 | 2025-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-06 | 2025-06-27 | 1900-01-21 | 16 | 2025-06-27 | 2025-06-27 | 1 | 1 | 6 | 4 | 178 | 128 | 184 | 132 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | LAGUNA HILLS | 69.05 | 69.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | 336 | 241 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-30 | 2025-05-14 | IOU Designed & Installed | N/A | No | N/A | 5170.82 | Unknown | Unknown | Unknown | 2845.62 | 2325.2 | Unknown | 14332.14 | 5170.82 | 9161.32 | Yes | N/A | N/A | 2024-05-30 | 2024-07-24 | 56 | 40 | 2024-07-24 | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-14 | 8 | 6 | 2024-10-24 | 2025-01-13 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | 2025-05-14 | 2025-06-11 | 1900-01-28 | 21 | 2025-06-11 | 2025-06-02 | Unknown | Unknown | 64 | 46 | 111 | 79 | 175 | 125 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-08 | -237 | -170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2023-11-02 | 2023-12-13 | IOU Designed & Installed | N/A | No | N/A | 0.47 | -6.05 | Unknown | Unknown | Unknown | 6.52 | 3981 | 844.42 | 0.47 | 843.95 | Yes | N/A | N/A | 2023-11-02 | 2023-10-26 | Unknown | Unknown | 2023-10-26 | 2023-11-07 | 13 | 9 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2023-12-13 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2023-12-15 | 1900-01-02 | 3 | 2023-12-15 | 2023-12-15 | 1 | 1 | 37 | 27 | 17 | 13 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-05 | -661 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-01-31 | 2024-02-05 | IOU Designed & Installed | N/A | No | N/A | 337.79 | -14.99 | Unknown | Unknown | Unknown | 352.78 | 3981 | 675.82 | 337.79 | 338.03 | Yes | N/A | N/A | 2024-01-31 | 2024-01-16 | Unknown | Unknown | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-02-05 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-03-15 | 1900-02-08 | 30 | 2024-03-15 | 2024-03-15 | 1 | 1 | 6 | 4 | 41 | 31 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-17 | -121 | -87 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-11 | 2024-10-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1455.84 | -26.55 | Unknown | Unknown | 4.41 | 1477.98 | 27867 | Not available | 1455.84 | Unknown | Yes | N/A | N/A | 2024-10-11 | 2024-10-14 | 4 | 2 | 2024-10-14 | 2024-11-06 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2024-11-15 | 30 | 22 | 2024-11-06 | 2024-12-10 | 35 | 25 | Unknown | 2024-11-18 | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | 2025-01-17 | 2025-01-16 | Unknown | Unknown | 39 | 27 | 54 | 40 | 93 | 67 | Steps 2,3,5,6,7 | 9 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-02 | -566 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | 2024-02-14 | IOU Designed & Installed | N/A | No | N/A | 1727.45 | -6.46 | Unknown | Unknown | Unknown | 1733.91 | Unknown | 287.46 | 1727.45 | -1439.99 | Yes | N/A | N/A | 2024-01-30 | 2024-02-13 | 15 | 11 | 2024-02-13 | 2024-02-13 | 1 | 1 | 2024-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-02-14 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-03-15 | 1900-01-30 | 23 | 2024-03-15 | 2024-03-15 | 1 | 1 | 17 | 13 | 33 | 25 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 21.1 | 21.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-20 | -51 | -38 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-06-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | -942.82 | -7.05 | Unknown | Unknown | -1328 | 392.23 | Unknown | 1108.62 | -942.82 | 2051.44 | Yes | N/A | N/A | 2024-01-18 | 2024-06-06 | 141 | 101 | 2024-06-06 | 2024-08-23 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-07-18 | 32 | 24 | 2024-08-23 | 2024-09-19 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | 2024-10-01 | 2024-09-30 | Unknown | Unknown | 169 | 121 | 111 | 81 | 280 | 202 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-28 | 577 | 414 | No | 2022-03-29 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-29 | 2022-03-29 | Unknown | IOU Designed & Installed | N/A | Yes | 793 | -12.86 | -7.8 | Unknown | -3.26 | Unknown | -1.8 | 3885 | 497.4 | -12.86 | 510.26 | Yes | N/A | N/A | 2022-03-29 | 2024-05-30 | 794 | 568 | 2024-05-30 | 2024-05-30 | 1 | 1 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | Unknown | Unknown | 2024-09-27 | 2024-09-27 | 1 | 1 | 794 | 568 | 2 | 2 | 796 | 570 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -536 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-06-03 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | -388.3 | Unknown | Unknown | Unknown | -479 | 90.7 | 4148.48 | 1660.26 | -388.3 | 2048.56 | Yes | N/A | N/A | 2024-05-29 | 2024-05-29 | 1 | 1 | 2024-05-29 | 2024-06-03 | 6 | 4 | 2024-06-03 | 2024-07-10 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-07-10 | 37 | 27 | Unknown | 2024-10-29 | Unknown | Unknown | 2024-07-10 | 2024-11-11 | 1900-05-04 | 89 | 2024-11-11 | 2024-11-11 | 1 | 1 | 76 | 56 | 132 | 94 | 208 | 150 | Steps 2,3,5,6,7 | 111 | 79 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-18 | 129 | 92 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | 2024-03-22 | IOU Designed & Installed | N/A | No | N/A | -7.34 | -5.98 | Unknown | Unknown | Unknown | -1.36 | 3981 | 903.6 | -7.34 | 910.94 | Yes | N/A | N/A | 2024-01-29 | 2024-02-05 | 8 | 6 | 2024-02-05 | 2024-03-18 | 43 | 31 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | 2024-03-22 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-03-26 | 1900-01-04 | 3 | 2024-03-26 | 2024-03-26 | 1 | 1 | 13 | 11 | 49 | 35 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 802.05 | 802.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | -67 | -48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | -483.56 | -12.76 | Unknown | Unknown | -1196 | 725.2 | 3981 | 3097.15 | -483.56 | 3580.71 | Yes | N/A | N/A | 2024-03-20 | 2024-03-20 | 1 | 1 | 2024-03-20 | 2024-03-29 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-04-26 | 29 | 21 | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | 2024-07-29 | 2024-07-26 | Unknown | Unknown | 30 | 22 | 10 | 8 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 208 | 208 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-17 | -459 | -329 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-11-29 | 2024-02-01 | IOU Designed & Installed | N/A | No | N/A | 8.18 | -9.92 | Unknown | Unknown | Unknown | 18.1 | 3981 | 934.29 | 8.18 | 926.11 | Yes | N/A | N/A | 2023-08-25 | 2023-11-29 | 97 | 69 | 2023-11-29 | 2023-11-29 | 1 | 1 | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2024-02-01 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-02-13 | 1900-01-12 | 9 | 2024-02-13 | 2024-02-13 | 1 | 1 | 162 | 116 | 15 | 11 | 177 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-05 | 14 | 11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-07 | 2024-03-29 | IOU Designed & Installed | N/A | No | N/A | 513.05 | -18.29 | Unknown | Unknown | Unknown | 531.34 | 3981 | 856.14 | 513.05 | 343.09 | Yes | N/A | N/A | 2023-09-06 | 2023-07-11 | Unknown | Unknown | 2023-07-11 | 2023-09-07 | 59 | 43 | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | 2024-03-29 | 205 | 147 | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-05-30 | 1900-03-03 | 45 | 2024-05-30 | 2024-07-19 | 51 | 37 | 205 | 147 | 173 | 125 | 378 | 272 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-09 | -138 | -99 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-03-09 | 2023-08-09 | IOU Designed & Installed | N/A | No | N/A | 3984.13 | 352.45 | Unknown | Unknown | -751 | 4382.68 | 4001 | 1558.95 | 3984.13 | -2425.18 | Yes | N/A | N/A | 2023-02-27 | 2023-03-09 | 11 | 9 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | 2023-08-09 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | 2023-08-24 | 1900-01-15 | 12 | 2023-08-24 | 2023-08-24 | 1 | 1 | 165 | 119 | 17 | 13 | 182 | 132 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-12 | -312 | -223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-02-01 | 2024-11-26 | IOU Designed & Installed | N/A | No | N/A | 1263.63 | -24.78 | Unknown | Unknown | Unknown | 1288.41 | 0 | 890.13 | 1263.63 | -373.5 | Yes | N/A | N/A | 2024-01-19 | 2023-10-24 | Unknown | Unknown | 2023-10-24 | 2024-02-01 | 101 | 73 | 2024-02-01 | Unknown | Unknown | Unknown | 2024-02-01 | 2024-10-15 | 45 | 31 | 2024-02-01 | 2024-11-26 | 300 | 214 | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2024-12-04 | 1900-01-08 | 7 | 2024-12-04 | 2024-12-04 | 1 | 1 | 300 | 214 | 156 | 112 | 456 | 326 | Steps 2,3,5,6,7 | 257 | 183 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-25 | -309 | -222 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-05-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1285.27 | Unknown | Unknown | Unknown | 18.16 | 1267.11 | 3981 | 1521.96 | 1285.27 | 236.69 | Yes | N/A | N/A | 2024-04-23 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-06-24 | 83 | 59 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-05-20 | 1 | 1 | 0 | 0 | 84 | 60 | 84 | 60 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 21 | 21 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-08 | -584 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-25 | 2023-10-23 | IOU Designed & Installed | N/A | No | N/A | 1193.82 | 234.7 | Unknown | Unknown | Unknown | 959.12 | 3981 | 758.9 | 1193.82 | -434.92 | Yes | N/A | N/A | 2023-09-22 | 2023-09-25 | 4 | 2 | 2023-09-25 | 2023-09-25 | 1 | 1 | 2023-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | 2023-10-23 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2023-11-02 | 1900-01-10 | 9 | 2023-11-02 | 2023-11-02 | 1 | 1 | 33 | 23 | 13 | 11 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 228 | 228 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | -525 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-20 | 2023-08-21 | 2024-02-21 | IOU Designed & Installed | N/A | No | N/A | 290.05 | 244.9 | Unknown | Unknown | -471 | 516.15 | 7962 | 1410.33 | 290.05 | 1120.28 | Yes | N/A | N/A | 2023-08-20 | 2023-08-21 | 2 | 1 | 2023-08-21 | 2025-03-06 | 564 | 404 | 2025-03-06 | 2024-02-07 | Unknown | Unknown | 2023-08-24 | 2023-09-21 | 29 | 21 | 2024-02-08 | 2024-02-21 | 14 | 10 | Unknown | 2024-02-14 | Unknown | Unknown | 2024-02-21 | 2024-02-23 | 1900-01-02 | 3 | 2024-02-23 | 2024-02-23 | 1 | 1 | 16 | 11 | 597 | 429 | 613 | 440 | Steps 2,3,5,6,7 | 167 | 119 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-08 | -632 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-04-10 | 2024-05-03 | IOU Designed & Installed | N/A | No | N/A | -5.9 | -4.79 | Unknown | Unknown | Unknown | -1.11 | Unknown | 1059.43 | -5.9 | 1065.33 | Yes | N/A | N/A | 2024-04-08 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2024-04-15 | 35 | 25 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-05-03 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-05-17 | 1900-01-14 | 11 | 2024-05-17 | 2024-05-17 | 1 | 1 | 19 | 15 | 51 | 37 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | EL CAJON | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-23 | 30 | 23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2025-01-28 | 2025-04-23 | IOU Designed & Installed | N/A | No | N/A | 6558.81 | 340.26 | Unknown | Unknown | 17.15 | 6201.4 | 7962 | 1609.48 | 6558.81 | -4949.33 | Yes | N/A | N/A | 2024-11-13 | 2024-12-30 | 48 | 34 | 2024-12-30 | 2025-04-16 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-04-04 | 22 | 16 | 2025-04-16 | 2025-05-23 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-06-02 | 1900-02-09 | 29 | 2025-06-02 | 2025-05-23 | Unknown | Unknown | 86 | 62 | 171 | 123 | 257 | 185 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 194 | 194 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-24 | -370 | -265 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-19 | 2024-04-18 | IOU Designed & Installed | N/A | No | N/A | 1742.15 | 581.43 | Unknown | Unknown | Unknown | 1160.72 | Unknown | 517.29 | 1742.15 | -1224.86 | Yes | N/A | N/A | 2024-03-18 | 2024-03-19 | 2 | 2 | 2024-03-19 | 2024-03-19 | 1 | 1 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-04-18 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-04-19 | 1900-01-01 | 2 | 2024-04-19 | 2024-04-19 | 1 | 1 | 33 | 25 | 4 | 4 | 37 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 186.05 | 186.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-18 | -145 | -105 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2023-05-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 968.47 | Unknown | Unknown | Unknown | Unknown | 968.47 | 3981 | 2222.36 | 968.47 | 1253.89 | Yes | N/A | N/A | 2023-05-24 | 2023-05-26 | 3 | 3 | 2023-05-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | 2024-08-27 | Unknown | Unknown | 2024-08-27 | 2024-08-26 | Unknown | Unknown | 3 | 3 | 0 | 0 | 3 | 3 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | Escondido | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-27 | -65 | -48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-01-18 | 2023-10-19 | IOU Designed & Installed | N/A | No | N/A | -2083.69 | 1341.78 | Unknown | 270.5 | -4541 | 845.03 | Unknown | 4541.12 | -2083.69 | 6624.81 | Yes | N/A | N/A | 2023-01-10 | 2023-09-19 | 253 | 181 | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2023-10-23 | 1900-01-04 | 3 | 2023-10-23 | 2023-10-23 | 1 | 1 | 253 | 181 | 6 | 4 | 259 | 185 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | Chula Vista | Chula Vista | 13 | 13 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-16 | 248 | 179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-15 | 2022-12-07 | 2023-08-18 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 30549.86 | 4775.41 | Unknown | 235.84 | 41.12 | 25497.49 | 106001 | 23428.31 | 30549.86 | -7121.55 | Yes | N/A | N/A | 2022-11-15 | 2023-04-25 | 162 | 116 | 2023-04-25 | 2023-06-12 | 49 | 35 | 2023-05-03 | 2023-06-09 | 20 | 15 | 2023-05-24 | 2023-08-09 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-08-17 | 23 | 17 | 2023-08-18 | 2023-09-21 | 1900-02-03 | 25 | 2023-09-21 | 2023-09-21 | 1 | 1 | 182 | 131 | 185 | 133 | 367 | 264 | Steps 2,3,5,6,7 | 56 | 40 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN YSIDRO | N/A | 2034 | 2034 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-09-01 | -1029 | -736 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-01-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1584.51 | -14.09 | Unknown | Unknown | 267.63 | 1330.97 | 11943 | 824.77 | 1584.51 | -759.74 | Yes | N/A | N/A | 2023-01-31 | 2023-05-09 | 99 | 71 | 2023-05-09 | 2023-05-19 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2023-09-01 | 106 | 76 | Unknown | 2023-11-03 | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2022-11-07 | Unknown | Unknown | 205 | 147 | 11 | 9 | 216 | 156 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | 248.05 | 248.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | -35 | -26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-05-30 | 2023-12-26 | IOU Designed & Installed | N/A | No | N/A | 17370.15 | 3350.71 | Unknown | Unknown | -5924.85 | 19944.29 | 3487 | 14762.64 | 17370.15 | -2607.51 | Yes | N/A | N/A | 2023-03-15 | 2023-04-24 | 41 | 29 | 2023-04-24 | 2023-10-27 | 187 | 135 | 2023-08-09 | 2023-10-27 | 30 | 21 | 2023-09-07 | 2023-11-10 | 25 | 19 | 2023-11-01 | Unknown | Unknown | Unknown | 2023-11-01 | 2023-12-14 | 44 | 32 | 2023-12-26 | 2024-01-31 | 1900-02-05 | 27 | 2024-01-31 | 2024-01-31 | 1 | 1 | 71 | 50 | 294 | 214 | 365 | 264 | Steps 2,3,5,6,7 | 138 | 100 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-27 | -586 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | 2023-09-14 | IOU Designed & Installed | N/A | No | N/A | -9.54 | -6.92 | Unknown | Unknown | Unknown | -2.62 | Unknown | 480.37 | -9.54 | 489.91 | Yes | N/A | N/A | 2023-08-15 | 2023-05-10 | Unknown | Unknown | 2023-05-10 | 2023-08-15 | 98 | 70 | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2023-09-14 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-09-19 | 1900-01-05 | 4 | 2023-09-19 | 2023-09-19 | 1 | 1 | 31 | 23 | 105 | 75 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 174.05 | 174.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-14 | -567 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | 2025-02-06 | IOU Designed & Installed | N/A | No | N/A | 59.79 | Unknown | Unknown | Unknown | Unknown | 59.79 | 3981 | 1595.46 | 59.79 | 1535.67 | Yes | N/A | N/A | 2024-10-09 | 2024-09-27 | Unknown | Unknown | 2024-09-27 | 2024-10-31 | 35 | 25 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2025-02-06 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-24 | 1900-01-18 | 13 | 2025-02-24 | 2025-02-24 | 1 | 1 | 100 | 72 | 55 | 39 | 155 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-26 | 105 | 76 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-11-19 | 2025-03-13 | IOU Designed & Installed | N/A | No | N/A | 21097.49 | 7380.88 | Unknown | Unknown | -2025.81 | 15742.42 | Unknown | 2087.69 | 21097.49 | -19009.8 | Yes | N/A | N/A | 2024-08-07 | 2024-08-07 | 1 | 1 | 2024-08-07 | 2025-02-24 | 202 | 144 | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2024-12-28 | 40 | 29 | 2025-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-06-11 | 1900-03-31 | 65 | 2025-06-11 | 2025-06-11 | 1 | 1 | 1 | 1 | 334 | 239 | 335 | 240 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 57 | 57 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-11 | -364 | -261 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | 800.68 | Unknown | Unknown | Unknown | 18.93 | 781.75 | 3981 | 2722.56 | 800.68 | 1921.88 | Yes | N/A | N/A | 2024-08-22 | 2024-11-08 | 79 | 57 | 2024-11-08 | 2024-11-12 | 5 | 3 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2025-06-09 | 210 | 150 | Unknown | 2025-05-05 | Unknown | Unknown | 2025-06-09 | 2025-06-12 | 1900-01-03 | 4 | 2025-06-12 | 2025-06-12 | 1 | 1 | 289 | 207 | 10 | 8 | 299 | 215 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-02 | 628 | 449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-02 | 2021-09-02 | 2024-01-26 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 819741.34 | 228005.41 | Unknown | 49.65 | 20342.77 | 571343.51 | 1908652 | 331983.18 | 819741.34 | -487758.16 | Yes | N/A | N/A | 2021-09-02 | 2023-03-28 | 573 | 409 | 2023-03-28 | 2023-10-12 | 199 | 143 | 2023-04-12 | 2024-06-04 | 23 | 17 | 2023-10-12 | 2024-05-20 | 222 | 158 | 2023-10-20 | Unknown | Unknown | Unknown | 2023-10-20 | 2024-05-21 | 215 | 153 | 2024-01-26 | 2024-05-22 | 1900-04-27 | 84 | 2024-05-22 | 2024-05-22 | 1 | 1 | 596 | 426 | 755 | 539 | 1351 | 965 | Steps 2,3,5,6,7 | 748 | 532 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-13 | -257 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-06 | 2023-07-06 | 2023-07-11 | IOU Designed & Installed | N/A | No | N/A | -10.07 | -7.3 | Unknown | Unknown | Unknown | -2.77 | Unknown | 765.17 | -10.07 | 775.24 | Yes | N/A | N/A | 2023-07-06 | 2023-05-03 | Unknown | Unknown | 2023-05-03 | 2023-07-06 | 65 | 47 | 2023-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-07-11 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | 2023-07-31 | 1900-01-20 | 15 | 2023-07-31 | 2023-07-31 | 1 | 1 | 6 | 4 | 87 | 63 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-01 | -485 | -348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-16 | 2023-12-16 | 2024-01-04 | IOU Designed & Installed | N/A | No | N/A | -4.84 | -3.92 | Unknown | Unknown | Unknown | -0.92 | Unknown | 515.81 | -4.84 | 520.65 | Yes | N/A | N/A | 2023-12-16 | 2023-12-16 | 1 | 0 | 2023-12-16 | 2023-12-16 | 1 | 0 | 2023-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-16 | 2024-01-04 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-04-03 | 1900-03-31 | 65 | 2024-04-03 | 2024-04-03 | 1 | 1 | 21 | 14 | 93 | 66 | 114 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-19 | 42 | 31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-10 | 2023-03-15 | IOU Designed & Installed | N/A | No | N/A | 12753.05 | Unknown | Unknown | Unknown | 695.98 | 12057.07 | 3981 | 690.42 | 12753.05 | -12062.63 | Yes | N/A | N/A | 2023-03-01 | 2023-03-10 | 10 | 8 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | 2023-03-15 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-03-15 | 2024-03-01 | 1900-12-18 | 253 | 2024-03-01 | 2024-03-01 | 1 | 1 | 16 | 12 | 354 | 254 | 370 | 266 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 39539 | 39539 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-12-01 | 677 | 484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-11-30 | 2023-04-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 103.71 | Unknown | Unknown | Unknown | Unknown | 103.71 | 3981 | 3521.88 | 103.71 | 3418.17 | Yes | N/A | N/A | 2021-11-30 | 2023-04-04 | 491 | 351 | 2023-04-04 | 2023-07-31 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | 2023-02-22 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | Unknown | 2025-02-07 | Unknown | Unknown | 2025-02-07 | 2024-10-08 | Unknown | Unknown | 491 | 351 | 134 | 96 | 625 | 447 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 89 | 89 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | -453 | -325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | -1113.37 | Unknown | Unknown | Unknown | -1145 | 31.63 | Unknown | 875.96 | -1113.37 | 1989.33 | Yes | N/A | N/A | 2024-10-02 | 2024-10-31 | 30 | 22 | 2024-10-31 | 2024-11-11 | 12 | 8 | 2024-11-11 | 2025-01-29 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-24 | 27 | 19 | Unknown | 2025-02-03 | Unknown | Unknown | 2025-02-24 | 2025-03-03 | 1900-01-07 | 6 | 2025-03-03 | 2025-03-03 | 1 | 1 | 137 | 99 | 21 | 15 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-08 | -555 | -398 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-04-11 | 2024-06-28 | IOU Designed & Installed | N/A | No | N/A | 593.33 | 370.02 | Unknown | Unknown | Unknown | 223.31 | Unknown | 534.57 | 593.33 | -58.76 | Yes | N/A | N/A | 2024-03-29 | 2024-04-11 | 14 | 10 | 2024-04-11 | 2024-04-11 | 1 | 1 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-06-28 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-02 | 1900-01-04 | 3 | 2024-07-02 | 2024-07-02 | 1 | 1 | 93 | 67 | 7 | 5 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-20 | -572 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-11-21 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 404.15 | -7.5 | Unknown | Unknown | Unknown | 411.65 | Unknown | 1563.39 | 404.15 | 1159.24 | Yes | N/A | N/A | 2024-11-20 | 2024-11-21 | 2 | 2 | 2024-11-21 | 2024-11-21 | 1 | 1 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2025-01-30 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-25 | 1900-01-26 | 19 | 2025-02-25 | 2025-02-25 | 1 | 1 | 73 | 53 | 29 | 21 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-05 | -510 | -365 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -12.34 | -9.78 | Unknown | Unknown | Unknown | -2.56 | Unknown | 154.79 | -12.34 | 167.13 | Yes | N/A | N/A | 2023-04-04 | 2023-04-24 | 21 | 15 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | Unknown | Unknown | 2023-09-14 | 2023-09-14 | 1 | 1 | 21 | 15 | 1 | 1 | 22 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | SAN DIEGO | N/A | 151.1 | 151.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-22 | -483 | -346 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2024-01-26 | 2024-04-16 | IOU Designed & Installed | N/A | No | N/A | 14.57 | -12.93 | Unknown | Unknown | Unknown | 27.5 | 3981 | 911.88 | 14.57 | 897.31 | Yes | N/A | N/A | 2023-12-15 | 2023-10-12 | Unknown | Unknown | 2023-10-12 | 2024-01-26 | 107 | 77 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-04-16 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-04-29 | 1900-01-13 | 10 | 2024-04-29 | 2024-04-26 | Unknown | Unknown | 82 | 58 | 121 | 87 | 203 | 145 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-31 | 769 | 550 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-07-23 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 7.78 | Unknown | Unknown | Unknown | -522 | 529.78 | Unknown | 478.32 | 7.78 | 470.54 | Yes | N/A | N/A | 2024-06-11 | 2024-07-23 | 43 | 31 | 2024-07-23 | 2024-11-26 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2024-12-05 | 10 | 8 | Unknown | 2025-02-03 | Unknown | Unknown | 2025-02-03 | 2025-02-10 | 1900-01-07 | 6 | 2025-02-10 | 2025-02-07 | Unknown | Unknown | 53 | 39 | 135 | 97 | 188 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-03 | 7 | 6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-16 | 2023-06-16 | 2023-08-02 | IOU Designed & Installed | N/A | No | N/A | 444.47 | -12.47 | Unknown | Unknown | Unknown | 456.94 | 3981 | 1072.83 | 444.47 | 628.36 | Yes | N/A | N/A | 2023-06-16 | 2023-06-16 | 1 | 1 | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-08-02 | 48 | 34 | Unknown | 2023-08-02 | Unknown | Unknown | 2023-08-02 | 2023-08-10 | 1900-01-08 | 7 | 2023-08-10 | 2023-08-10 | 1 | 1 | 49 | 35 | 10 | 8 | 59 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 633 | 633 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-30 | -353 | -252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2024-04-01 | IOU Designed & Installed | N/A | No | N/A | 11.39 | -10.09 | Unknown | Unknown | Unknown | 21.48 | Unknown | 796.96 | 11.39 | 785.57 | Yes | N/A | N/A | 2023-09-14 | 2023-09-14 | 1 | 1 | 2023-09-14 | 2023-09-14 | 1 | 1 | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2024-04-01 | 201 | 143 | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-04-11 | 1900-01-10 | 9 | 2024-04-11 | 2024-04-11 | 1 | 1 | 202 | 144 | 13 | 11 | 215 | 155 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | Poway | Poway | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-02 | 419 | 300 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-01 | 2024-07-19 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -847.69 | 475.92 | Unknown | Unknown | -3348 | 2024.39 | Unknown | 9024.74 | -847.69 | 9872.43 | Yes | N/A | N/A | 2024-05-01 | 2024-05-02 | 2 | 2 | 2024-05-02 | 2024-07-02 | 62 | 44 | 2024-05-03 | 2024-06-25 | 6 | 2 | 2024-05-23 | 2024-07-16 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-07-25 | 1900-01-06 | 5 | 2024-07-25 | 2024-07-25 | 1 | 1 | 8 | 4 | 85 | 61 | 93 | 65 | Steps 2,3,5,6,7 | 93 | 65 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 389.05 | 389.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-31 | -80 | -58 | No | 2023-09-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-10-06 | Unknown | IOU Designed & Installed | N/A | Yes | 117 | 16.1 | -14.33 | Unknown | Unknown | Unknown | 30.43 | 3981 | 993.82 | 16.1 | 977.72 | Yes | N/A | N/A | 2023-09-14 | 2023-12-21 | 99 | 71 | 2023-12-21 | 2024-01-09 | 20 | 14 | 2024-01-09 | Unknown | Unknown | Unknown | 2023-10-06 | 2023-10-12 | 7 | 5 | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-06-12 | 1 | 1 | 99 | 71 | 28 | 20 | 127 | 91 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-02 | 92 | 67 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4003.97 | -34.69 | Unknown | Unknown | Unknown | 4038.66 | Unknown | 931.63 | 4003.97 | -3072.34 | Yes | N/A | N/A | 2023-04-11 | 2023-04-11 | 1 | 1 | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-05-05 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-29 | -680 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-19 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | 29.82 | Unknown | Unknown | Unknown | Unknown | 29.82 | Unknown | 1676.05 | 29.82 | 1646.23 | Yes | N/A | N/A | 2025-02-18 | 2025-02-04 | Unknown | Unknown | 2025-02-04 | 2025-02-19 | 16 | 12 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-26 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-03-20 | 1900-01-22 | 17 | 2025-03-20 | 2025-03-20 | 1 | 1 | 8 | 6 | 40 | 30 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-06 | -231 | -166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | -345.42 | -24.92 | Unknown | Unknown | -1119 | 798.5 | 4662.67 | 2163.64 | -345.42 | 2509.06 | Yes | N/A | N/A | 2023-09-18 | 2023-08-25 | Unknown | Unknown | 2023-08-25 | 2023-10-17 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2024-01-02 | 24 | 18 | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | Unknown | Unknown | Unknown | 2024-05-20 | Unknown | Unknown | 2024-05-20 | 2024-05-20 | 1 | 1 | 0 | 0 | 79 | 57 | 79 | 57 | Steps 2,3,5,6,7 | 77 | 55 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 577.4 | 577.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-09 | -604 | -431 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-01-16 | 2024-02-20 | IOU Designed & Installed | N/A | No | N/A | 398.64 | -19.96 | Unknown | Unknown | Unknown | 418.6 | 3981 | 883.81 | 398.64 | 485.17 | Yes | N/A | N/A | 2024-01-16 | 2023-11-22 | Unknown | Unknown | 2023-11-22 | 2024-01-16 | 56 | 40 | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-02-20 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-03-15 | 1900-01-24 | 19 | 2024-03-15 | 2024-03-15 | 1 | 1 | 36 | 26 | 82 | 60 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-21 | 145 | 104 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-07-28 | IOU Designed & Installed | N/A | No | N/A | 2615.36 | 764 | Unknown | 79.38 | 170.35 | 1601.63 | 3981 | 823.59 | 2615.36 | -1791.77 | Yes | N/A | N/A | 2023-06-13 | 2023-07-13 | 31 | 23 | 2023-07-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | 2023-07-28 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2024-08-13 | 1901-01-17 | 273 | 2024-08-13 | 2024-08-13 | 1 | 1 | 47 | 35 | 384 | 274 | 431 | 309 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | -578 | -413 | No | 2024-10-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-12-11 | 2024-12-13 | IOU Designed & Installed | N/A | Yes | 63 | 706.77 | -13.2 | Unknown | Unknown | Unknown | 719.97 | Unknown | 1650.15 | 706.77 | 943.38 | Yes | N/A | N/A | 2024-10-09 | 2024-12-09 | 62 | 44 | 2024-12-09 | 2024-12-11 | 3 | 3 | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2024-12-13 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2024-12-18 | 1900-01-05 | 4 | 2024-12-18 | 2024-12-18 | 1 | 1 | 65 | 47 | 10 | 8 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -618 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-11 | 2024-10-07 | IOU Designed & Installed | N/A | No | N/A | -129.12 | Unknown | Unknown | Unknown | -156 | 26.88 | Unknown | 1450.63 | -129.12 | 1579.75 | Yes | N/A | N/A | 2024-09-03 | 2024-09-11 | 9 | 7 | 2024-09-11 | 2024-09-11 | 1 | 1 | 2024-09-11 | 2024-09-26 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-10-07 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-22 | 1900-01-15 | 12 | 2024-10-22 | 2024-10-21 | Unknown | Unknown | 37 | 27 | 17 | 13 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-28 | -289 | -207 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | 2025-05-13 | IOU Designed & Installed | N/A | No | N/A | 2900.64 | 615.74 | Unknown | Unknown | 5.11 | 2279.79 | Unknown | 619.75 | 2900.64 | -2280.89 | Yes | N/A | N/A | 2025-04-10 | 2025-04-11 | 2 | 2 | 2025-04-11 | 2025-04-11 | 1 | 1 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-05-13 | 33 | 23 | Unknown | 2025-06-12 | Unknown | Unknown | 2025-05-13 | 2025-06-12 | 1900-01-30 | 23 | 2025-06-12 | 2025-06-12 | 1 | 1 | 35 | 25 | 33 | 25 | 68 | 50 | Steps 2,3,5,6,7 | 30 | 22 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-22 | 446 | 319 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2024-02-16 | 2024-04-16 | IOU Designed & Installed | N/A | No | N/A | 18427.65 | 1162.36 | Unknown | Unknown | 38.7 | 17226.59 | Unknown | 12174.32 | 18427.65 | -6253.33 | Yes | N/A | N/A | 2023-12-27 | 2024-03-07 | 72 | 52 | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-04-10 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-06-10 | 1900-02-24 | 40 | 2024-06-10 | 2024-06-10 | 1 | 1 | 72 | 52 | 86 | 62 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 84 | 84 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -502 | -360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-18 | 2024-12-16 | IOU Designed & Installed | N/A | No | N/A | 16.66 | Unknown | Unknown | Unknown | 4.04 | 12.62 | 3241 | 1586.22 | 16.66 | 1569.56 | Yes | N/A | N/A | 2024-10-17 | 2024-10-18 | 2 | 2 | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | 2025-03-24 | 158 | 112 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-12-16 | 60 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2025-04-14 | 1900-04-29 | 86 | 2025-04-14 | 2025-04-14 | 1 | 1 | 220 | 156 | 122 | 88 | 342 | 244 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-28 | -311 | -224 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-21 | 2024-09-30 | IOU Designed & Installed | N/A | No | N/A | 5.56 | Unknown | Unknown | Unknown | Unknown | 5.56 | 3981 | 1013.08 | 5.56 | 1007.52 | Yes | N/A | N/A | 2024-02-20 | 2024-02-20 | 1 | 1 | 2024-02-20 | 2024-02-21 | 2 | 2 | 2024-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-09-30 | 223 | 159 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-10-21 | 1900-01-21 | 16 | 2024-10-21 | 2024-10-21 | 1 | 1 | 224 | 160 | 25 | 19 | 249 | 179 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 53 | 53 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-05 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-12 | 2024-01-24 | IOU Designed & Installed | N/A | No | N/A | 1121.79 | 342.42 | Unknown | 100.6 | Unknown | 678.77 | Unknown | 1985.06 | 1121.79 | 863.27 | Yes | N/A | N/A | 2024-01-11 | 2023-09-21 | Unknown | Unknown | 2023-09-21 | 2024-01-12 | 114 | 82 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | 2024-01-24 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-02-22 | 1900-01-29 | 22 | 2024-02-22 | 2024-02-22 | 1 | 1 | 13 | 9 | 145 | 105 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-04 | -525 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-22 | 2024-06-21 | IOU Designed & Installed | N/A | No | N/A | 903.03 | -6.22 | Unknown | Unknown | 6.58 | 902.67 | 3981 | 790.36 | 903.03 | -112.67 | Yes | N/A | N/A | 2024-02-21 | 2023-12-29 | Unknown | Unknown | 2023-12-29 | 2024-03-08 | 71 | 51 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-06-21 | 106 | 76 | Unknown | 2024-05-31 | Unknown | Unknown | 2024-06-21 | 2024-06-27 | 1900-01-06 | 5 | 2024-06-27 | 2024-06-27 | 1 | 1 | 106 | 76 | 79 | 57 | 185 | 133 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 170 | 170 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | -205 | -148 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 614.9 | -32.85 | Unknown | Unknown | Unknown | 647.75 | 3981 | 483.59 | 614.9 | -131.31 | Yes | N/A | N/A | 2023-12-01 | 2023-11-20 | Unknown | Unknown | 2023-11-20 | 2023-12-13 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2023-12-19 | 12 | 8 | 2023-12-13 | 2024-02-21 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-12 | Unknown | Unknown | 71 | 51 | 36 | 26 | 107 | 77 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | -275 | -197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-03-07 | 2024-04-10 | IOU Designed & Installed | N/A | No | N/A | 1464.18 | -32.36 | Unknown | Unknown | 51.48 | 1445.06 | 0 | 903.6 | 1464.18 | -560.58 | Yes | N/A | N/A | 2024-02-26 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | 2024-03-07 | 58 | 42 | 2024-03-07 | Unknown | Unknown | Unknown | 2024-03-08 | 2024-07-24 | 33 | 23 | 2024-03-07 | 2024-04-10 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2025-02-06 | 1900-10-29 | 217 | 2025-02-06 | 2025-02-06 | 1 | 1 | 35 | 25 | 395 | 283 | 430 | 308 | Steps 2,3,5,6,7 | 139 | 99 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-14 | 2025-02-14 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | 115.19 | -1.5 | Unknown | Unknown | Unknown | 116.69 | 3981 | 1531.44 | 115.19 | 1416.25 | Yes | N/A | N/A | 2025-02-14 | 2025-02-14 | 1 | 1 | 2025-02-14 | 2025-02-14 | 1 | 1 | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-02-26 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-03-05 | 1900-01-07 | 6 | 2025-03-05 | 2025-03-05 | 1 | 1 | 14 | 10 | 10 | 8 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-07 | -845 | -604 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-02-21 | 2023-06-14 | IOU Designed & Installed | N/A | No | N/A | 377.3 | 232.94 | Unknown | Unknown | Unknown | 144.36 | Unknown | 148.62 | 377.3 | -228.68 | Yes | N/A | N/A | 2023-02-21 | 2023-04-28 | 67 | 49 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | 2023-06-14 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | 2023-06-15 | 1900-01-01 | 2 | 2023-06-15 | 2023-06-15 | 1 | 1 | 115 | 83 | 3 | 3 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -265 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-02 | 2025-04-09 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 115099.11 | 30626.98 | Unknown | 5734.81 | 2131.88 | 76605.44 | 223048 | 33463.2 | 115099.11 | -81635.91 | Yes | N/A | N/A | 2023-02-02 | 2023-06-14 | 133 | 95 | 2023-06-14 | 2023-10-11 | 120 | 86 | 2023-06-27 | 2023-11-02 | 82 | 60 | 2023-09-03 | 2023-10-17 | 16 | 11 | 2024-07-16 | Unknown | Unknown | Unknown | 2024-07-16 | 2025-03-14 | 242 | 174 | 2025-04-09 | 2025-04-10 | 1900-01-01 | 2 | 2025-04-10 | 2025-04-10 | 1 | 1 | 215 | 155 | 381 | 274 | 596 | 429 | Steps 2,3,5,6,7 | 166 | 119 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 114.05 | 114.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-20 | -531 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-07-05 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | 3.44 | Unknown | Unknown | Unknown | Unknown | 3.44 | Unknown | 1512.92 | 3.44 | 1509.48 | Yes | N/A | N/A | 2024-05-30 | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-07-05 | 73 | 53 | 2024-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | 2024-10-21 | 109 | 77 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-11-05 | 1900-01-15 | 12 | 2024-11-05 | 2024-11-05 | 1 | 1 | 109 | 77 | 90 | 66 | 199 | 143 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-19 | -687 | -491 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-06 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | 4335.99 | 697.03 | Unknown | 247.83 | Unknown | 3391.13 | 3981 | 1124.06 | 4335.99 | -3211.93 | Yes | N/A | N/A | 2025-01-06 | 2025-01-06 | 1 | 1 | 2025-01-06 | 2025-01-06 | 1 | 1 | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-01-15 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-01-31 | 1900-01-16 | 13 | 2025-01-31 | 2025-01-31 | 1 | 1 | 11 | 9 | 19 | 15 | 30 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-08 | -301 | -216 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-02 | 2022-11-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.9 | -3.55 | Unknown | Unknown | Unknown | -1.35 | 15994 | 326.65 | -4.9 | 331.55 | Yes | N/A | N/A | 2022-11-02 | 2023-12-12 | 406 | 290 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | Unknown | Unknown | 2023-12-12 | 2023-12-12 | 1 | 1 | 406 | 290 | 1 | 1 | 407 | 291 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-13 | -354 | -255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2023-09-21 | IOU Designed & Installed | N/A | No | N/A | 22.62 | -3.58 | Unknown | Unknown | 24.46 | 1.74 | 3754 | 375.8 | 22.62 | 353.18 | Yes | N/A | N/A | 2023-09-14 | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2023-09-14 | 2 | 2 | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-09-21 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2025-05-22 | 1901-09-01 | 436 | 2025-05-22 | 2023-09-25 | Unknown | Unknown | 8 | 6 | 612 | 438 | 620 | 444 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-30 | -408 | -293 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-07-11 | 2024-09-12 | IOU Designed & Installed | N/A | No | N/A | 60.23 | Unknown | Unknown | Unknown | Unknown | 60.23 | 3981 | 2268.59 | 60.23 | 2208.36 | Yes | N/A | N/A | 2024-07-11 | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-07-11 | 51 | 37 | 2024-07-11 | 2024-07-19 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-09-12 | 64 | 46 | Unknown | 2024-08-16 | Unknown | Unknown | 2024-09-12 | 2024-09-17 | 1900-01-05 | 4 | 2024-09-17 | 2024-09-17 | 1 | 1 | 73 | 53 | 58 | 42 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 68.4 | 68.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-18 | -413 | -296 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-07-26 | 2023-08-22 | IOU Designed & Installed | N/A | No | N/A | 0.21 | -12.77 | Unknown | Unknown | 6.79 | 6.19 | 3981 | 1156.36 | 0.21 | 1156.15 | Yes | N/A | N/A | 2023-03-13 | 2023-06-28 | 108 | 78 | 2023-06-28 | 2023-07-31 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2023-09-21 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | 2024-01-24 | 1900-06-04 | 112 | 2024-01-24 | 2023-10-02 | Unknown | Unknown | 161 | 117 | 190 | 136 | 351 | 253 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Marcos | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-01 | -265 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 3248.48 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-11 | 2023-10-05 | Unknown | Unknown | 2023-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-26 | 89 | 65 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-16 | 2024-08-19 | IOU Designed & Installed | N/A | No | N/A | 21.37 | Unknown | Unknown | Unknown | Unknown | 21.37 | 3981 | 552.7 | 21.37 | 531.33 | Yes | N/A | N/A | 2023-08-16 | 2023-06-15 | Unknown | Unknown | 2023-06-15 | 2023-08-16 | 63 | 45 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2024-08-19 | 370 | 264 | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-08-23 | 1900-01-04 | 5 | 2024-08-23 | 2024-08-23 | 1 | 1 | 370 | 264 | 69 | 51 | 439 | 315 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 900 | 900 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-21 | 195 | 140 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1458.05 | -73.29 | Unknown | Unknown | 4.69 | 1526.65 | Unknown | 9753.24 | 1458.05 | 8295.19 | Yes | N/A | N/A | 2023-05-02 | 2023-05-16 | 15 | 11 | 2023-05-16 | 2023-05-16 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | Unknown | Unknown | Unknown | 2024-02-01 | Unknown | Unknown | 2024-02-01 | 2024-02-01 | 1 | 1 | 15 | 11 | 2 | 2 | 17 | 13 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 540 | 387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-04-19 | 2024-11-22 | IOU Designed & Installed | N/A | No | N/A | -243.98 | 954.02 | Unknown | Unknown | -1198 | Unkonwn | 3981 | 2167.96 | -243.98 | 2411.94 | Yes | N/A | N/A | 2024-04-09 | 2024-04-09 | 1 | 1 | 2024-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-11-22 | 169 | 121 | Unknown | 2024-11-01 | Unknown | Unknown | 2024-11-22 | 2024-11-22 | 1899-12-31 | 1 | 2024-11-22 | 2024-11-22 | 1 | 1 | 170 | 122 | 2 | 2 | 172 | 124 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-04 | -212 | -153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | 2023-05-15 | 2024-02-16 | IOU Designed & Installed | N/A | No | N/A | -202.75 | -32.7 | Unknown | Unknown | -4508 | 4337.95 | Unknown | 12785.89 | -202.75 | 12988.64 | Yes | N/A | N/A | 2023-05-04 | 2023-11-06 | 187 | 133 | 2023-11-06 | 2024-02-09 | 96 | 70 | 2023-08-16 | 2024-02-09 | 178 | 128 | 2023-12-04 | 2024-02-14 | 10 | 8 | 2024-02-09 | Unknown | Unknown | Unknown | 2024-02-15 | Unknown | Unknown | Unknown | 2024-02-16 | 2024-03-06 | 1900-01-19 | 14 | 2024-03-06 | 2024-03-06 | 1 | 1 | 365 | 261 | 127 | 93 | 492 | 354 | Steps 2,3,5,6,7 | 249 | 179 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-25 | 282 | 203 | No | 2022-07-29 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-28 | 2022-07-29 | 2023-11-14 | IOU Designed & Installed | N/A | Yes | 452 | 6986.19 | -11.59 | Unknown | Unknown | 723.51 | 6274.27 | Unknown | 838.13 | 6986.19 | -6148.06 | Yes | N/A | N/A | 2022-07-28 | 2023-10-23 | 453 | 323 | 2023-10-23 | 2023-10-24 | 2 | 2 | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-07-29 | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2024-02-01 | 1900-03-20 | 58 | 2024-02-01 | 2024-02-01 | 1 | 1 | 453 | 323 | 83 | 61 | 536 | 384 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-21 | -182 | -131 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1072.1 | 1927.38 | Unknown | 536.06 | -4454 | 918.46 | Unknown | 3922.45 | -1072.1 | 4994.55 | Yes | N/A | N/A | 2023-11-20 | 2023-11-27 | 8 | 6 | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-02-21 | 1 | 1 | 8 | 6 | 1 | 1 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Residential | N/A | LADERA RANCH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-31 | 297 | 212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-08-07 | 2025-06-24 | IOU Designed & Installed | N/A | No | N/A | -23420.29 | -17.08 | Unknown | Unknown | -30704 | 7300.79 | 0 | 28519.4 | -23420.29 | 51939.69 | Yes | N/A | N/A | 2024-07-24 | 2024-07-26 | 3 | 3 | 2024-07-26 | Unknown | Unknown | Unknown | 2024-08-21 | 2025-02-18 | 2 | 2 | 2024-10-29 | 2024-11-07 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | 2025-06-24 | 2025-06-24 | 1899-12-31 | 1 | 2025-06-24 | 2025-06-24 | 1 | 1 | 5 | 5 | 12 | 10 | 17 | 15 | Steps 2,3,5,6,7 | 112 | 80 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 1649.05 | 1649.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-04-23 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-08-12 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | -1375.94 | 298.53 | Unknown | Unknown | -2111 | 436.53 | Unknown | 1854.16 | -1375.94 | 3230.1 | Yes | N/A | N/A | 2024-07-02 | 2024-07-10 | 9 | 7 | 2024-07-10 | 2024-08-12 | 34 | 24 | 2024-08-12 | 2024-08-27 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2024-10-11 | 33 | 25 | Unknown | 2024-09-20 | Unknown | Unknown | 2024-10-11 | 2024-10-21 | 1900-01-10 | 7 | 2024-10-21 | 2024-10-18 | Unknown | Unknown | 58 | 44 | 45 | 31 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-19 | -244 | -175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 115.18 | 66.94 | Unknown | Unknown | Unknown | 48.24 | 3981 | 192.83 | 115.18 | 77.65 | Yes | N/A | N/A | 2024-05-16 | 2024-06-07 | 23 | 17 | 2024-06-07 | 2024-06-10 | 4 | 2 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | Unknown | Unknown | 2024-07-18 | 2024-07-18 | 1 | 1 | 23 | 17 | 5 | 3 | 28 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | VISTA | N/A | 350 | 350 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-24 | -593 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-05-28 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | -12.72 | -10.99 | Unknown | Unknown | Unknown | -1.73 | Unknown | 192.83 | -12.72 | 205.55 | Yes | N/A | N/A | 2024-04-08 | 2024-05-28 | 51 | 37 | 2024-05-28 | 2024-05-28 | 1 | 1 | 2024-05-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-06-17 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-07-11 | 1900-01-24 | 19 | 2024-07-11 | 2024-07-11 | 1 | 1 | 72 | 52 | 27 | 21 | 99 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 568.05 | 568.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-23 | -62 | -45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-04-25 | 2024-10-17 | IOU Designed & Installed | N/A | No | N/A | 458.23 | 502.72 | Unknown | 367.38 | -1681 | 1269.13 | 0 | 1680.16 | 458.23 | 1221.93 | Yes | N/A | N/A | 2023-02-23 | 2023-02-23 | 1 | 1 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-24 | 2024-10-17 | 513 | 367 | Unknown | 2024-09-20 | Unknown | Unknown | 2024-10-17 | 2024-10-22 | 1900-01-05 | 4 | 2024-10-22 | 2024-10-22 | 1 | 1 | 514 | 368 | 7 | 5 | 521 | 373 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | 12.35 | 12.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | 140 | 101 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 387.93 | -7.79 | Unknown | Unknown | Unknown | 395.72 | 3981 | 1561.76 | 387.93 | 1173.83 | Yes | N/A | N/A | 2024-11-07 | 2024-11-06 | Unknown | Unknown | 2024-11-06 | 2025-01-08 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2024-12-10 | 22 | 16 | 2025-01-08 | 2025-03-03 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | 2025-03-21 | 2025-03-21 | 1 | 1 | 55 | 39 | 87 | 63 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | N/A | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | 1548 | 1548 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-10-25 | 74 | 53 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-11-27 | 2024-09-26 | IOU Designed & Installed | N/A | No | N/A | 181142.92 | 18728.53 | Unknown | Unknown | 1536.91 | 160877.48 | 646477 | 87120.76 | 181142.92 | -94022.16 | Yes | N/A | N/A | 2023-10-16 | 2024-02-21 | 129 | 93 | 2024-02-21 | 2024-07-22 | 153 | 109 | 2024-04-26 | 2024-07-22 | 16 | 10 | 2024-03-19 | 2024-08-08 | 85 | 62 | 2024-07-22 | 2024-12-16 | 148 | 106 | 2024-10-02 | 2024-11-20 | 50 | 36 | 2024-09-26 | 2025-01-07 | 1900-04-13 | 74 | 2025-01-07 | 2025-01-07 | 1 | 1 | 293 | 209 | 393 | 282 | 686 | 491 | Steps 2,3,5,6,7 | 359 | 255 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-04 | -692 | -495 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1155.43 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-04-29 | 1 | 1 | 2025-04-29 | 2025-04-29 | 1 | 1 | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | 2025-05-12 | 2025-05-12 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 74.05 | 74.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-24 | -273 | -196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | 2024-01-19 | IOU Designed & Installed | N/A | No | N/A | 3018.86 | 565.68 | Unknown | 320.5 | Unknown | 2132.68 | 3981 | 1789.01 | 3018.86 | -1229.85 | Yes | N/A | N/A | 2023-12-19 | 2023-12-13 | Unknown | Unknown | 2023-12-13 | 2023-12-19 | 7 | 5 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-01-19 | 32 | 24 | Unknown | 2024-01-11 | Unknown | Unknown | 2024-01-19 | 2024-01-25 | 1900-01-06 | 5 | 2024-01-25 | 2024-01-25 | 1 | 1 | 32 | 24 | 15 | 11 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-03-24 | 742 | 531 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-03-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -486.39 | -13.82 | Unknown | Unknown | -502 | 29.43 | 0 | 456.41 | -486.39 | 942.8 | Yes | N/A | N/A | 2023-03-27 | 2023-03-27 | 1 | 1 | 2023-03-27 | 2023-05-08 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | 2024-01-17 | 255 | 183 | Unknown | 2024-03-28 | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | 2024-04-08 | 2024-04-04 | Unknown | Unknown | 256 | 184 | 43 | 31 | 299 | 215 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-19 | -275 | -197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-31 | 2024-05-31 | IOU Designed & Installed | N/A | No | N/A | 686.33 | -13.44 | Unknown | Unknown | Unknown | 699.77 | Unknown | 1466.13 | 686.33 | 779.8 | Yes | N/A | N/A | 2024-05-29 | 2024-05-31 | 3 | 3 | 2024-05-31 | 2024-05-31 | 1 | 1 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-05-31 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-07-18 | 1900-02-17 | 35 | 2024-07-18 | 2024-07-18 | 1 | 1 | 4 | 4 | 51 | 37 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | -427 | -306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-03-01 | 2024-03-20 | IOU Designed & Installed | N/A | No | N/A | 1722.85 | -44.73 | Unknown | Unknown | 65.06 | 1702.52 | 3981 | 1028.89 | 1722.85 | -693.96 | Yes | N/A | N/A | 2024-02-21 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-03-01 | 37 | 27 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-03-20 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-11-08 | 1900-08-21 | 168 | 2024-11-08 | 2024-11-08 | 1 | 1 | 20 | 14 | 272 | 196 | 292 | 210 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 2.94 | Unknown | Unknown | Unknown | Unknown | 2.94 | 3981 | 180.38 | 2.94 | 177.44 | Yes | N/A | N/A | 2024-04-15 | 2024-02-12 | Unknown | Unknown | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-07-22 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-07-23 | 1900-01-01 | 2 | 2024-07-23 | 2024-07-23 | 1 | 1 | 36 | 26 | 3 | 3 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-02 | -488 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | 2024-02-23 | 2024-06-14 | IOU Designed & Installed | N/A | No | N/A | 3514.62 | 850.78 | Unknown | 20.15 | -505 | 3148.69 | 7946.17 | 1910.79 | 3514.62 | -1603.83 | Yes | N/A | N/A | 2024-02-13 | 2024-02-13 | 1 | 1 | 2024-02-13 | 2024-02-23 | 11 | 9 | 2024-02-23 | 2024-02-29 | 7 | 5 | 2024-02-26 | 2024-06-10 | 106 | 76 | 2024-02-29 | 2024-06-14 | 107 | 77 | Unknown | 2024-06-11 | Unknown | Unknown | 2024-06-14 | 2024-07-02 | 1900-01-18 | 13 | 2024-07-02 | 2024-07-02 | 1 | 1 | 115 | 83 | 137 | 99 | 252 | 182 | Steps 2,3,5,6,7 | 105 | 75 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-28 | -558 | -399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-09-24 | 2025-01-10 | IOU Designed & Installed | N/A | No | N/A | 113.86 | -1.57 | Unknown | Unknown | Unknown | 115.43 | Unknown | 1546.09 | 113.86 | 1432.23 | Yes | N/A | N/A | 2024-08-27 | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-09-24 | 47 | 33 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2025-01-10 | 109 | 79 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-01-16 | 1900-01-06 | 5 | 2025-01-16 | 2025-01-16 | 1 | 1 | 109 | 79 | 55 | 39 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-16 | -679 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-05 | 2024-08-16 | IOU Designed & Installed | N/A | No | N/A | 141.02 | -1.88 | Unknown | Unknown | Unknown | 142.9 | 3981 | 1482.36 | 141.02 | 1341.34 | Yes | N/A | N/A | 2024-08-05 | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2024-08-16 | 25 | 19 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-08-16 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-09-05 | 1900-01-20 | 15 | 2024-09-05 | 2024-09-05 | 1 | 1 | 1 | 1 | 47 | 35 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-27 | -55 | -40 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-07-07 | IOU Designed & Installed | N/A | No | N/A | 1768.79 | -37.61 | Unknown | Unknown | 2.64 | 1803.76 | 3981 | 767.6 | 1768.79 | -1001.19 | Yes | N/A | N/A | 2023-06-13 | 2023-06-13 | 1 | 1 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-02-01 | 14 | 10 | 2023-06-13 | 2023-07-07 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | 2024-02-01 | 1900-07-28 | 150 | 2024-02-01 | 2024-02-01 | 1 | 1 | 26 | 20 | 225 | 161 | 251 | 181 | Steps 2,3,5,6,7 | 233 | 167 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-16 | -1222 | -875 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | 2023-06-26 | 2023-12-06 | IOU Designed & Installed | N/A | No | N/A | 416.49 | 257.62 | Unknown | Unknown | Unknown | 158.87 | 23991 | 519.36 | 416.49 | 102.87 | Yes | N/A | N/A | 2023-06-26 | 2023-09-21 | 88 | 64 | 2023-09-21 | 2023-09-21 | 1 | 1 | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2023-12-06 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2023-12-11 | 1900-01-05 | 4 | 2023-12-11 | 2023-12-11 | 1 | 1 | 165 | 119 | 8 | 6 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-08 | -626 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-04-12 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | -466.9 | -21.66 | Unknown | Unknown | -1076 | 630.76 | Unknown | 1076.46 | -466.9 | 1543.36 | Yes | N/A | N/A | 2024-04-08 | 2024-02-27 | Unknown | Unknown | 2024-02-27 | 2024-04-12 | 46 | 34 | 2024-04-12 | 2024-04-22 | 11 | 7 | 2024-04-16 | 2024-05-03 | 18 | 14 | 2024-04-22 | 2024-04-22 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-05-23 | 1900-01-31 | 24 | 2024-05-23 | 2024-05-23 | 1 | 1 | 12 | 8 | 97 | 73 | 109 | 81 | Steps 2,3,5,6,7 | 17 | 13 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | Rancho Viejo | N/A | 372.6 | 372.6 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-07 | 16 | 11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-04-27 | 2024-01-09 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 81235.33 | 7401.98 | Unknown | 3455.04 | 26501.88 | 43876.43 | 0 | 26418.65 | 81235.33 | -54816.68 | Yes | N/A | N/A | 2022-04-27 | 2023-05-02 | 371 | 265 | 2023-05-02 | 2023-10-12 | 164 | 118 | 2023-08-08 | 2023-10-02 | 56 | 40 | 2023-09-18 | 2023-09-25 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | Unknown | Unknown | 2024-01-09 | 2024-09-23 | 1900-09-15 | 185 | 2024-09-23 | 2024-09-23 | 1 | 1 | 427 | 305 | 432 | 310 | 859 | 615 | Steps 2,3,5,6,7 | 263 | 189 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | 642 | 459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-10-23 | 2024-11-01 | IOU Designed & Installed | N/A | No | N/A | 32092.24 | 8230.88 | Unknown | Unknown | Unknown | 23861.36 | 13166 | Not available | 32092.24 | Unknown | Yes | N/A | N/A | 2023-10-23 | 2023-05-16 | Unknown | Unknown | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | 2024-11-01 | 2024-11-04 | 1900-01-03 | 2 | 2024-11-04 | 2024-11-04 | 1 | 1 | 0 | 0 | 5 | 3 | 5 | 3 | Steps 2,3,5,6,7 | 192 | 136 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-07 | -158 | -115 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | 2024-09-26 | IOU Designed & Installed | N/A | No | N/A | 6728.33 | -27.85 | Unknown | Unknown | 58.59 | 6697.59 | 3981 | 1104.02 | 6728.33 | -5624.31 | Yes | N/A | N/A | 2024-05-28 | 2024-07-08 | 42 | 30 | 2024-07-08 | 2024-07-09 | 2 | 2 | 2024-07-09 | Unknown | Unknown | Unknown | 2024-07-09 | 2024-09-20 | 74 | 54 | 2024-07-09 | 2024-09-26 | 80 | 58 | Unknown | 2024-09-09 | Unknown | Unknown | 2024-09-26 | 2024-10-04 | 1900-01-08 | 7 | 2024-10-04 | 2024-09-30 | Unknown | Unknown | 122 | 88 | 85 | 63 | 207 | 151 | Steps 2,3,5,6,7 | 73 | 53 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | DEL MAR | DEL MAR | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-30 | 37 | 28 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-22 | 2024-11-22 | IOU Designed & Installed | N/A | No | N/A | 854.09 | -17.2 | Unknown | Unknown | Unknown | 871.29 | 3981 | 1944.2 | 854.09 | 1090.11 | Yes | N/A | N/A | 2024-10-10 | 2024-10-16 | 7 | 5 | 2024-10-16 | 2024-10-28 | 13 | 9 | 2024-10-28 | Unknown | Unknown | Unknown | 2024-10-29 | 2024-11-22 | 25 | 19 | 2024-10-28 | 2024-11-22 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2024-12-06 | 1900-01-14 | 11 | 2024-12-06 | 2024-12-06 | 1 | 1 | 33 | 25 | 54 | 40 | 87 | 65 | Steps 2,3,5,6,7 | 25 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Escondido | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-18 | 68 | 49 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-01-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 2515.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-31 | 2023-03-27 | 56 | 40 | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | Unknown | Unknown | 2024-03-26 | 2024-03-26 | 1 | 1 | 56 | 40 | 1 | 1 | 57 | 41 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-09 | -579 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | 2024-01-04 | IOU Designed & Installed | N/A | No | N/A | 229.24 | 120.84 | Unknown | 21.69 | Unknown | 86.71 | 3885 | 158.79 | 229.24 | -70.45 | Yes | N/A | N/A | 2023-12-04 | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-12-08 | 109 | 79 | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2024-01-04 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-08 | 1900-01-04 | 3 | 2024-01-08 | 2024-01-08 | 1 | 1 | 28 | 20 | 115 | 83 | 143 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 448.05 | 448.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | -37 | -28 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-12-01 | 2023-12-12 | IOU Designed & Installed | N/A | No | N/A | -23.02 | -18.36 | Unknown | Unknown | Unknown | -4.66 | 3981 | 1507 | -23.02 | 1530.02 | Yes | N/A | N/A | 2023-11-20 | 2023-10-10 | Unknown | Unknown | 2023-10-10 | 2023-12-01 | 53 | 39 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2023-12-12 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2024-02-20 | 1900-03-11 | 51 | 2024-02-20 | 2023-12-26 | Unknown | Unknown | 12 | 8 | 124 | 90 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | 93.4 | 93.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-19 | 147 | 106 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2137.46 | -11.92 | Unknown | Unknown | 24.59 | 2124.79 | 8248 | 1680.37 | 2137.46 | -457.09 | Yes | N/A | N/A | 2023-11-15 | 2023-10-09 | Unknown | Unknown | 2023-10-09 | 2024-04-22 | 197 | 141 | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-04-15 | 98 | 70 | 2024-04-22 | 2024-12-04 | 227 | 163 | Unknown | 2025-01-03 | Unknown | Unknown | Unknown | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-02-13 | Unknown | Unknown | 227 | 163 | 295 | 211 | 522 | 374 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-28 | -242 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-20 | 2023-07-31 | IOU Designed & Installed | N/A | No | N/A | -13.57 | -9.85 | Unknown | Unknown | Unknown | -3.72 | Unknown | 480.44 | -13.57 | 494.01 | Yes | N/A | N/A | 2023-07-10 | 2023-05-03 | Unknown | Unknown | 2023-05-03 | 2023-07-13 | 72 | 52 | 2023-07-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-07-31 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2023-08-30 | 1900-01-30 | 23 | 2023-08-30 | 2023-08-30 | 1 | 1 | 12 | 8 | 104 | 76 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-22 | 334 | 239 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-06-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 9057.29 | 272.1 | Unknown | Unknown | -1120 | 9905.19 | 11955 | 2160.14 | 9057.29 | -6897.15 | Yes | N/A | N/A | 2024-06-07 | 2024-05-02 | Unknown | Unknown | 2024-05-02 | 2024-07-03 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2025-03-10 | 251 | 179 | Unknown | 2025-02-11 | Unknown | Unknown | Unknown | 2025-03-06 | Unknown | Unknown | 2025-03-06 | 2025-02-19 | Unknown | Unknown | 251 | 179 | 63 | 45 | 314 | 224 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-22 | -227 | -164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | -8.45 | -6.12 | Unknown | Unknown | Unknown | -2.33 | 3981 | 464.78 | -8.45 | 473.23 | Yes | N/A | N/A | 2023-06-15 | 2023-06-15 | 1 | 1 | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | Unknown | Unknown | 2023-07-10 | 2023-07-10 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-23 | -169 | -122 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-18 | 2024-12-05 | IOU Designed & Installed | N/A | No | N/A | 733.24 | 132.47 | Unknown | Unknown | -526.99 | 1127.76 | Unknown | 575.58 | 733.24 | -157.66 | Yes | N/A | N/A | 2024-06-18 | 2024-06-13 | Unknown | Unknown | 2024-06-13 | 2024-06-24 | 12 | 8 | 2024-06-24 | 2024-11-21 | 151 | 109 | 2024-06-25 | 2024-11-16 | 145 | 104 | 2024-08-14 | 2024-12-05 | 114 | 82 | Unknown | 2024-11-22 | Unknown | Unknown | 2024-12-05 | 2024-12-05 | 1899-12-31 | 1 | 2024-12-05 | 2024-12-05 | 1 | 1 | 265 | 191 | 159 | 114 | 424 | 305 | Steps 2,3,5,6,7 | 243 | 174 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-13 | -199 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-08 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | Not available | Unknown | Unknown | Yes | N/A | N/A | 2024-10-08 | 2024-10-02 | Unknown | Unknown | 2024-10-02 | 2024-10-08 | 7 | 5 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2025-03-18 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-04-28 | 1900-02-10 | 30 | 2025-04-28 | 2025-04-28 | 1 | 1 | 162 | 116 | 50 | 36 | 212 | 152 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | 107.05 | 107.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-20 | -632 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-11 | 2025-03-11 | 2025-05-27 | IOU Designed & Installed | N/A | No | N/A | 1875.54 | Unknown | Unknown | Unknown | 5.93 | 1869.61 | 3981 | 1237.59 | 1875.54 | -637.95 | Yes | N/A | N/A | 2025-03-11 | 2025-04-07 | 28 | 20 | 2025-04-07 | 2025-04-08 | 2 | 2 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-05-27 | 51 | 37 | Unknown | 2025-05-07 | Unknown | Unknown | 2025-05-27 | 2025-05-29 | 1900-01-02 | 3 | 2025-05-29 | 2025-05-29 | 1 | 1 | 79 | 57 | 6 | 6 | 85 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 142.05 | 142.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-30 | -428 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | 2023-06-26 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 1796.53 | Unknown | Unknown | Unknown | 29.24 | 1767.29 | 3981 | 793.51 | 1796.53 | -1003.02 | Yes | N/A | N/A | 2023-06-26 | 2023-06-26 | 1 | 1 | 2023-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-27 | 2024-10-24 | 486 | 348 | Unknown | 2024-10-23 | Unknown | Unknown | 2024-10-24 | 2024-10-29 | 1900-01-05 | 4 | 2024-10-29 | 2024-10-28 | Unknown | Unknown | 487 | 349 | 6 | 4 | 493 | 353 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JULIAN | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-03 | -654 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | 2025-05-21 | IOU Designed & Installed | N/A | No | N/A | 6751.34 | 1728.57 | Unknown | Unknown | Unknown | 5022.77 | 3981 | 1049.33 | 6751.34 | -5702.01 | Yes | N/A | N/A | 2025-05-06 | 2025-04-09 | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-21 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-06-18 | 1900-01-28 | 21 | 2025-06-18 | 2025-06-18 | 1 | 1 | 16 | 12 | 30 | 22 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 105.05 | 105.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | -651 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-06 | 2024-12-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 492.96 | Unknown | Unknown | Unknown | Unknown | 492.96 | 3981 | 2790.37 | 492.96 | 2297.41 | Yes | N/A | N/A | 2024-12-06 | 2025-01-09 | 35 | 25 | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | 2025-01-24 | 2025-01-24 | 1 | 1 | 35 | 25 | 2 | 2 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-12 | -633 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2023-03-25 | IOU Designed & Installed | N/A | No | N/A | 1477.78 | 486.64 | Unknown | 176.2 | Unknown | 814.94 | 3981 | 681.3 | 1477.78 | -796.48 | Yes | N/A | N/A | 2023-02-17 | 2023-02-17 | 1 | 1 | 2023-02-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-17 | 2023-03-25 | 37 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-03-25 | 2023-04-20 | 1900-01-26 | 19 | 2023-04-20 | 2023-04-20 | 1 | 1 | 38 | 27 | 28 | 20 | 66 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 98 | 98 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-09 | -635 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-10-17 | IOU Designed & Installed | N/A | No | N/A | 380.23 | Unknown | Unknown | Unknown | 2.53 | 377.7 | 3981 | 1198.27 | 380.23 | 818.04 | Yes | N/A | N/A | 2024-08-27 | 2024-08-15 | Unknown | Unknown | 2024-08-15 | 2024-10-07 | 54 | 38 | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-17 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | 2024-11-12 | 1900-01-26 | 19 | 2024-11-12 | 2024-11-12 | 1 | 1 | 11 | 9 | 82 | 58 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 13.1 | 13.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-25 | -606 | -435 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-15 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1721.23 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-13 | 2025-01-06 | Unknown | Unknown | 2025-01-06 | 2025-01-15 | 10 | 8 | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-04-24 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-04-28 | 1900-01-04 | 3 | 2025-04-28 | 2025-04-28 | 1 | 1 | 100 | 72 | 16 | 12 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-11 | -353 | -254 | No | 2024-02-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-12 | Unknown | IOU Designed & Installed | N/A | Yes | 200 | -903.47 | -12.08 | Unknown | Unknown | -2045.57 | 1154.18 | Unknown | 1789.97 | -903.47 | 2693.44 | Yes | N/A | N/A | 2024-02-08 | 2024-08-30 | 205 | 147 | 2024-08-30 | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-09-04 | 170 | 122 | 2024-09-18 | 2024-10-30 | 43 | 31 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | Unknown | 2024-12-23 | Unknown | Unknown | 2024-12-23 | 2024-12-23 | 1 | 1 | 375 | 269 | 44 | 32 | 419 | 301 | Steps 2,3,5,6,7 | 225 | 161 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-12 | -457 | -328 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | 2023-08-24 | 2024-03-08 | IOU Designed & Installed | N/A | No | N/A | 1465.89 | -13.51 | Unknown | Unknown | 17.86 | 1461.54 | 3241 | 2014.29 | 1465.89 | 548.4 | Yes | N/A | N/A | 2023-08-24 | 2023-10-20 | 58 | 42 | 2023-10-20 | 2023-10-20 | 1 | 1 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2024-03-08 | 141 | 101 | Unknown | 2024-03-08 | Unknown | Unknown | 2024-03-08 | 2024-03-12 | 1900-01-04 | 3 | 2024-03-12 | 2024-03-12 | 1 | 1 | 199 | 143 | 7 | 5 | 206 | 148 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.1 | 4.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-17 | -663 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-06 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | 4.39 | Unknown | Unknown | Unknown | Unknown | 4.39 | 3981 | 118.25 | 4.39 | 113.86 | Yes | N/A | N/A | 2025-05-06 | 2025-04-17 | Unknown | Unknown | 2025-04-17 | 2025-05-09 | 23 | 17 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-06-11 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-23 | 1900-01-12 | 9 | 2025-06-23 | 2025-06-23 | 1 | 1 | 34 | 24 | 37 | 27 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-18 | -540 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-12 | 2024-04-03 | IOU Designed & Installed | N/A | No | N/A | 2427.7 | 784.56 | Unknown | 69.56 | Unknown | 1573.58 | Unknown | 1022.67 | 2427.7 | -1405.03 | Yes | N/A | N/A | 2024-02-07 | 2023-10-30 | Unknown | Unknown | 2023-10-30 | 2024-02-12 | 106 | 76 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-04-03 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-04-26 | 1900-01-23 | 18 | 2024-04-26 | 2024-04-26 | 1 | 1 | 52 | 38 | 131 | 95 | 183 | 133 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 178 | 127 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 8238.23 | 272.1 | Unknown | Unknown | -511.68 | 8477.81 | 3981 | 2252.55 | 8238.23 | -5985.68 | Yes | N/A | N/A | 2023-11-29 | 2024-04-10 | 134 | 96 | 2024-04-10 | 2024-04-10 | 1 | 1 | 2024-04-10 | Unknown | Unknown | Unknown | 2024-04-10 | 2024-05-31 | 52 | 38 | 2024-04-26 | 2024-08-14 | 111 | 79 | Unknown | 2024-08-05 | Unknown | Unknown | 2024-08-14 | 2024-09-16 | 1900-02-02 | 24 | 2024-09-16 | 2024-08-26 | Unknown | Unknown | 245 | 175 | 87 | 63 | 332 | 238 | Steps 2,3,5,6,7 | 35 | 25 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | -250 | -179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1176.73 | -36.03 | Unknown | Unknown | 10.18 | 1202.58 | 3981 | 1009.28 | 1176.73 | -167.45 | Yes | N/A | N/A | 2024-03-15 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-03-19 | 27 | 19 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | Unknown | Unknown | 2024-06-04 | 2024-06-04 | 1 | 1 | 0 | 0 | 28 | 20 | 28 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-05-15 | 49 | 36 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2019-03-08 | 2019-03-08 | 2023-06-02 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 945535.4 | 296380.59 | Unknown | 979.59 | 3939.84 | 644235.38 | 750329 | 223587.76 | 945535.4 | -721947.64 | Yes | N/A | N/A | 2019-03-08 | 2023-02-01 | 1427 | 1019 | 2023-02-01 | 2023-05-23 | 112 | 80 | 2023-02-08 | 2023-08-31 | 124 | 90 | 2023-04-20 | 2023-07-13 | 85 | 60 | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-10-03 | 104 | 74 | 2023-06-02 | 2023-07-03 | 1900-01-31 | 22 | 2023-07-03 | 2023-07-03 | 1 | 1 | 1551 | 1109 | 334 | 237 | 1885 | 1346 | Steps 2,3,5,6,7 | 360 | 256 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-28 | -77 | -56 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1178.82 | -34.95 | Unknown | Unknown | Unknown | 1213.77 | 26990 | 341.06 | 1178.82 | -837.76 | Yes | N/A | N/A | 2023-02-02 | 2023-02-02 | 1 | 1 | 2023-02-02 | 2023-05-30 | 118 | 84 | 2023-03-17 | 2023-03-20 | 4 | 2 | 2023-02-24 | 2023-05-03 | 67 | 49 | 2023-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | Unknown | Unknown | 2023-10-12 | 2023-10-12 | 1 | 1 | 5 | 3 | 186 | 134 | 191 | 137 | Steps 2,3,5,6,7 | 98 | 68 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-11 | -273 | -196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-17 | 2024-12-12 | IOU Designed & Installed | N/A | No | N/A | 5053.76 | 4996.74 | Unknown | 149.01 | -2627 | 2535.01 | Unknown | 2627.03 | 5053.76 | -2426.73 | Yes | N/A | N/A | 2024-10-08 | 2024-11-07 | 31 | 23 | 2024-11-07 | 2024-12-09 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | Unknown | Unknown | Unknown | 2024-12-09 | 2024-12-09 | 1 | 1 | 2024-12-12 | 2024-12-12 | 1899-12-31 | 1 | 2024-12-12 | 2024-12-12 | 1 | 1 | 31 | 23 | 36 | 26 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Residential | Underserved Community | Escondido | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | -63 | -46 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2024-06-20 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 29744.43 | 8343.04 | Unknown | Unknown | -20234.34 | 41635.73 | Unknown | 25647.1 | 29744.43 | -4097.33 | Yes | N/A | N/A | 2023-09-27 | 2024-02-01 | 128 | 92 | 2024-02-01 | 2024-06-18 | 139 | 99 | 2024-03-20 | 2024-05-20 | 54 | 36 | 2024-05-21 | 2024-05-22 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-30 | 1900-02-09 | 29 | 2024-07-30 | 2024-07-30 | 1 | 1 | 182 | 128 | 183 | 131 | 365 | 259 | Steps 2,3,5,6,7 | 90 | 64 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 61.05 | 61.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-31 | -249 | -178 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-01-31 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 2668.82 | 869.44 | Unknown | Unknown | Unknown | 1799.38 | 7962 | 1167.37 | 2668.82 | -1501.45 | Yes | N/A | N/A | 2024-01-31 | 2023-10-20 | Unknown | Unknown | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | 2024-07-22 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-07-25 | 1900-01-03 | 4 | 2024-07-25 | 2024-07-25 | 1 | 1 | 134 | 96 | 5 | 5 | 139 | 101 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | 137.05 | 137.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-15 | -355 | -254 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12.12 | Unknown | Unknown | Unknown | Unknown | 12.12 | 3885 | 691.28 | 12.12 | 679.16 | Yes | N/A | N/A | 2024-02-07 | 2024-03-19 | 42 | 30 | 2024-03-19 | 2024-03-19 | 1 | 1 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2024-09-25 | 1 | 1 | 42 | 30 | 2 | 2 | 44 | 32 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2020-02-05 | 1288 | 921 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-12 | 2023-06-12 | 2023-07-20 | IOU Designed & Installed | N/A | No | N/A | 2724.25 | Unknown | Unknown | Unknown | -4719 | 7443.25 | Unknown | 4433.56 | 2724.25 | 1709.31 | Yes | N/A | N/A | 2023-06-12 | 2023-06-13 | 2 | 2 | 2023-06-13 | 2023-06-28 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | 2023-07-12 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | Unknown | Unknown | 2023-07-20 | 2023-08-16 | 1900-01-27 | 20 | 2023-08-16 | 2023-08-16 | 1 | 1 | 2 | 2 | 48 | 36 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 126.7 | 126.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 335 | 240 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 298.22 | -39.69 | Unknown | Unknown | -370 | 707.91 | Unknown | 902.47 | 298.22 | 604.25 | Yes | N/A | N/A | 2023-10-05 | 2023-10-09 | 5 | 3 | 2023-10-09 | 2023-10-26 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2024-03-29 | 156 | 112 | Unknown | 2024-03-19 | Unknown | Unknown | Unknown | 2024-05-02 | Unknown | Unknown | 2024-05-02 | 2024-05-01 | Unknown | Unknown | 161 | 115 | 18 | 14 | 179 | 129 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -63 | -46 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | -33.02 | -0.62 | Unknown | Unknown | Unknown | -32.4 | Unknown | 52.54 | -33.02 | 85.56 | Yes | N/A | N/A | 2024-09-19 | 2024-12-31 | 104 | 74 | 2024-12-31 | 2025-02-05 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-10-19 | 2024-11-21 | 34 | 24 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-02-19 | 1 | 1 | 104 | 74 | 72 | 52 | 176 | 126 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 118 | 118 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-10 | 62 | 45 | No | 2022-09-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | 2022-10-11 | 2024-08-17 | IOU Designed & Installed | N/A | Yes | 430 | 12074.65 | 3410.82 | Unknown | 34.01 | -9279.26 | 17909.08 | 0 | 13987.51 | 12074.65 | 1912.86 | Yes | N/A | N/A | 2022-09-19 | 2023-11-27 | 435 | 311 | 2023-11-27 | 2024-03-27 | 122 | 88 | 2023-01-26 | 2024-09-10 | 411 | 291 | 2024-02-22 | 2024-07-30 | 160 | 114 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-17 | 2024-10-11 | 1900-02-24 | 40 | 2024-10-11 | 2024-10-11 | 1 | 1 | 846 | 602 | 339 | 243 | 1185 | 845 | Steps 2,3,5,6,7 | 201 | 143 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 6.75 | 6.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | -660 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-14 | 2025-02-21 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 35.99 | Unknown | Unknown | Unknown | Unknown | 35.99 | 3981 | 1676.05 | 35.99 | 1640.06 | Yes | N/A | N/A | 2025-02-14 | 2025-02-21 | 8 | 6 | 2025-02-21 | 2025-02-21 | 1 | 1 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-04-02 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-07 | 1900-01-05 | 4 | 2025-04-07 | 2025-04-07 | 1 | 1 | 49 | 35 | 8 | 6 | 57 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-24 | -578 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-02-21 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | -12.63 | -10.26 | Unknown | Unknown | Unknown | -2.37 | 3981 | 910.75 | -12.63 | 923.38 | Yes | N/A | N/A | 2024-01-12 | 2024-02-16 | 36 | 26 | 2024-02-16 | 2024-02-21 | 6 | 4 | 2024-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-03-14 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-03-25 | 1900-01-11 | 8 | 2024-03-25 | 2024-03-25 | 1 | 1 | 59 | 43 | 19 | 13 | 78 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-05 | -613 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-04-22 | 2025-05-22 | IOU Designed & Installed | N/A | No | N/A | 528.2 | Unknown | Unknown | Unknown | Unknown | 528.2 | Unknown | 1680.93 | 528.2 | 1152.73 | Yes | N/A | N/A | 2025-04-22 | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-04-22 | 13 | 9 | 2025-04-22 | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-02 | 9 | 7 | 2025-04-22 | 2025-05-22 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-06-02 | 1900-01-11 | 8 | 2025-06-02 | 2025-06-02 | 1 | 1 | 31 | 23 | 35 | 25 | 66 | 48 | Steps 2,3,5,6,7 | 10 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-25 | -438 | -313 | No | 2024-03-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-29 | Unknown | IOU Designed & Installed | N/A | Yes | 32 | 3.44 | Unknown | Unknown | Unknown | Unknown | 3.44 | 3981 | 632.97 | 3.44 | 629.53 | Yes | N/A | N/A | 2024-03-07 | 2024-04-02 | 27 | 19 | 2024-04-02 | 2024-04-08 | 7 | 5 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-13 | 1 | 1 | 27 | 19 | 8 | 6 | 35 | 25 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Residential | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | 49 | 36 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 1914.78 | 15353.57 | Unknown | Unknown | -32224 | 18785.21 | 23651.67 | 139460.51 | 1914.78 | 137545.73 | Yes | N/A | N/A | 2024-04-24 | 2024-07-29 | 97 | 69 | 2024-07-29 | 2025-04-24 | 270 | 194 | 2024-08-06 | 2025-03-07 | 136 | 97 | 2024-08-14 | 2025-03-26 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-05-20 | 1 | 1 | 233 | 166 | 337 | 243 | 570 | 409 | Steps 2,3,5,6,7 | 466 | 334 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 54 | 54 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-12 | -473 | -338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-13 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.77 | -14.84 | Unknown | Unknown | 1.27 | 9.8 | 3981 | 625.47 | -3.77 | 629.24 | Yes | N/A | N/A | 2022-11-13 | 2023-03-15 | 123 | 88 | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | Unknown | Unknown | 2023-07-24 | 2023-04-27 | Unknown | Unknown | 123 | 88 | 0 | 0 | 123 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-17 | -710 | -508 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-29 | 2025-04-30 | IOU Designed & Installed | N/A | No | N/A | 582.23 | -11.7 | Unknown | Unknown | Unknown | 593.93 | 3981 | 2001.04 | 582.23 | 1418.81 | Yes | N/A | N/A | 2025-04-29 | 2025-04-29 | 1 | 1 | 2025-04-29 | 2025-04-29 | 1 | 1 | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-04-30 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-05-07 | 1900-01-07 | 6 | 2025-05-07 | 2025-05-07 | 1 | 1 | 3 | 3 | 10 | 8 | 13 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-03 | -687 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-11 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | 472.25 | -8.7 | Unknown | Unknown | Unknown | 480.95 | 3981 | 1647.26 | 472.25 | 1175.01 | Yes | N/A | N/A | 2025-02-11 | 2025-02-11 | 1 | 1 | 2025-02-11 | 2025-02-11 | 1 | 1 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-03-03 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-18 | 1900-01-15 | 12 | 2025-03-18 | 2025-03-18 | 1 | 1 | 22 | 16 | 18 | 14 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Residential | N/A | cb 1107-a6 marja acres ph2b | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-18 | 242 | 175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-03 | 2024-07-29 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 63595.21 | 4947.53 | Unknown | Unknown | -10940 | 69587.68 | 108460 | Not available | 63595.21 | Unknown | Yes | N/A | N/A | 2024-01-03 | 2024-01-04 | 2 | 2 | 2024-01-04 | 2024-07-17 | 196 | 140 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2025-01-31 | 199 | 143 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-16 | 1900-01-18 | 15 | 2024-08-16 | 2024-08-16 | 1 | 1 | 201 | 145 | 216 | 156 | 417 | 301 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | El Cajon | El Cajon | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 278 | 199 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-07-24 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 755.05 | 1578.81 | Unknown | Unknown | -20646 | 19822.24 | 15826.37 | 23210.81 | 755.05 | 22455.76 | Yes | N/A | N/A | 2023-04-11 | 2023-07-19 | 100 | 72 | 2023-07-19 | 2023-12-06 | 141 | 101 | 2023-08-31 | 2024-04-30 | 179 | 127 | 2023-10-25 | 2024-05-10 | 28 | 22 | 2023-12-06 | Unknown | Unknown | Unknown | 2024-05-08 | 2024-06-14 | 38 | 28 | 2024-09-25 | 2024-12-04 | 1900-03-11 | 51 | 2024-12-04 | 2024-12-04 | 1 | 1 | 279 | 199 | 279 | 203 | 558 | 402 | Steps 2,3,5,6,7 | 441 | 315 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-20 | 735 | 526 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-07-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1255.89 | -24.23 | Unknown | Unknown | Unknown | 1280.12 | 45578 | 2836.2 | 1255.89 | 1580.31 | Yes | N/A | N/A | 2024-02-20 | 2024-03-13 | 23 | 17 | 2024-03-13 | 2024-10-10 | 212 | 152 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2025-02-24 | 138 | 98 | Unknown | 2025-02-19 | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 161 | 115 | 213 | 153 | 374 | 268 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-04 | 159 | 114 | No | 2021-11-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-11-28 | 2022-01-31 | Unknown | IOU Designed & Installed | N/A | Yes | 435 | 2510.2 | -22.42 | Unknown | Unknown | Unknown | 2532.62 | 3885 | 977.41 | 2510.2 | -1532.79 | Yes | N/A | N/A | 2021-11-28 | 2023-02-06 | 436 | 311 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-04-12 | Unknown | Unknown | 436 | 311 | 0 | 0 | 436 | 311 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 83.05 | 83.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-21 | -417 | -299 | No | 2023-11-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2024-01-17 | 2024-04-23 | IOU Designed & Installed | N/A | Yes | 63 | -1398.11 | -14.11 | Unknown | Unknown | -1414 | 30 | 3981 | 2489.97 | -1398.11 | 3888.08 | Yes | N/A | N/A | 2023-11-15 | 2024-01-09 | 56 | 40 | 2024-01-09 | 2024-01-09 | 1 | 1 | 2024-01-09 | 2024-01-25 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-04-23 | 90 | 64 | Unknown | 2024-04-13 | Unknown | Unknown | 2024-04-23 | 2024-05-01 | 1900-01-08 | 7 | 2024-05-01 | 2024-04-30 | Unknown | Unknown | 163 | 117 | 10 | 8 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | -350 | -251 | No | 2024-04-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-07-17 | 2024-12-10 | IOU Designed & Installed | N/A | Yes | 165 | 504.02 | -6.35 | Unknown | Unknown | 4 | 506.37 | 3981 | 2453.32 | 504.02 | 1949.3 | Yes | N/A | N/A | 2024-04-15 | 2024-07-17 | 94 | 68 | 2024-07-17 | 2024-12-06 | 143 | 103 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2024-12-20 | 1900-01-10 | 9 | 2024-12-20 | 2024-12-20 | 1 | 1 | 94 | 68 | 155 | 113 | 249 | 181 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 9.6 | 9.6 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | -455 | -326 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-11 | 2024-06-19 | IOU Designed & Installed | N/A | No | N/A | 1598.79 | -38.36 | Unknown | Unknown | Unknown | 1637.15 | Unknown | 1214.72 | 1598.79 | -384.07 | Yes | N/A | N/A | 2024-01-10 | 2023-11-03 | Unknown | Unknown | 2023-11-03 | 2024-02-09 | 99 | 71 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-06-19 | 132 | 94 | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-07-25 | 1900-02-05 | 27 | 2024-07-25 | 2024-07-25 | 1 | 1 | 132 | 94 | 137 | 99 | 269 | 193 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 355 | 355 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-15 | -28 | -21 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | 2025-06-16 | IOU Designed & Installed | N/A | No | N/A | -1050.1 | Unknown | Unknown | Unknown | -1988 | 937.9 | Unknown | 1695.22 | -1050.1 | 2745.32 | Yes | N/A | N/A | 2024-09-27 | 2025-02-03 | 130 | 92 | 2025-02-03 | 2025-04-15 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-02-26 | 22 | 16 | 2025-04-15 | 2025-06-16 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-06-17 | 1900-01-01 | 2 | 2025-06-17 | 2025-06-17 | 1 | 1 | 193 | 137 | 97 | 71 | 290 | 208 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-24 | -466 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-04-06 | 2024-05-20 | IOU Designed & Installed | N/A | No | N/A | 21.96 | -17.26 | Unknown | Unknown | Unknown | 39.22 | 3981 | 1037.19 | 21.96 | 1015.23 | Yes | N/A | N/A | 2024-02-26 | 2024-04-06 | 41 | 30 | 2024-04-06 | 2024-04-06 | 1 | 0 | 2024-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-06 | 2024-05-20 | 45 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-07-15 | 1900-02-25 | 41 | 2024-07-15 | 2024-07-15 | 1 | 1 | 86 | 61 | 59 | 42 | 145 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | -710 | -507 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1141.19 | -33.93 | Unknown | Unknown | Unknown | 1175.12 | Unknown | 920.9 | 1141.19 | -220.29 | Yes | N/A | N/A | 2023-05-10 | 2023-04-21 | Unknown | Unknown | 2023-04-21 | 2023-05-20 | 30 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-05-25 | 2023-06-14 | 21 | 15 | 2023-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | Unknown | Unknown | 2023-09-22 | 2023-09-22 | 1 | 1 | 0 | 0 | 52 | 37 | 52 | 37 | Steps 2,3,5,6,7 | 25 | 17 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 185 | 185 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-08 | -45 | -34 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | 2025-06-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2070.76 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-27 | 2025-01-03 | Unknown | Unknown | 2025-01-03 | 2025-05-02 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-06-24 | 54 | 38 | Unknown | 2025-06-10 | Unknown | Unknown | 2025-06-12 | 2025-06-27 | 1900-01-15 | 12 | 2025-06-27 | 2025-06-24 | Unknown | Unknown | 54 | 38 | 136 | 98 | 190 | 136 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-30 | -418 | -299 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-01-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 952.82 | 398.37 | Unknown | Unknown | Unknown | 554.45 | Unknown | 95.13 | 952.82 | -857.69 | Yes | N/A | N/A | 2023-01-23 | 2023-03-10 | 47 | 35 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-08-09 | 1 | 1 | 47 | 35 | 1 | 1 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-12 | -369 | -264 | No | 2024-10-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-11 | 2024-10-11 | 2025-03-31 | IOU Designed & Installed | N/A | Yes | 108 | 2211.19 | 416.72 | Unknown | 135.71 | 9.11 | 1649.65 | 3981 | 1560.69 | 2211.19 | -650.5 | Yes | N/A | N/A | 2024-10-11 | 2025-01-27 | 109 | 77 | 2025-01-27 | 2025-01-27 | 1 | 1 | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-03-31 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-08 | 1900-01-08 | 7 | 2025-04-08 | 2025-04-08 | 1 | 1 | 173 | 123 | 11 | 9 | 184 | 132 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | -639 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | 2025-01-08 | IOU Designed & Installed | N/A | No | N/A | 69.7 | Unknown | Unknown | Unknown | Unknown | 69.7 | 3241 | 1646.83 | 69.7 | 1577.13 | Yes | N/A | N/A | 2024-11-25 | 2024-11-25 | 1 | 1 | 2024-11-25 | 2024-11-25 | 1 | 1 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-01-08 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-27 | 1900-01-19 | 14 | 2025-01-27 | 2025-01-27 | 1 | 1 | 46 | 34 | 22 | 16 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | BONSALL | COUNTY OF SAN DIEGO-NORTH of 56 | 142 | 142 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-08 | -86 | -63 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-03-22 | 2025-04-17 | IOU Designed & Installed | N/A | No | N/A | 48280.15 | 12593.14 | Unknown | Unknown | -32981 | 68668.01 | 0 | 56918.52 | 48280.15 | 8638.37 | Yes | N/A | N/A | 2024-02-20 | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2025-01-13 | 335 | 239 | 2024-06-04 | 2024-06-04 | 1 | 1 | 2025-01-02 | 2025-01-09 | 5 | 1 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-05-14 | 1900-01-27 | 20 | 2025-05-14 | 2025-05-14 | 1 | 1 | 1 | 1 | 369 | 261 | 370 | 262 | Steps 2,3,5,6,7 | 223 | 159 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 6.75 | 6.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-26 | -356 | -255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-01-08 | 2024-01-16 | IOU Designed & Installed | N/A | No | N/A | 5.25 | -9.18 | Unknown | Unknown | Unknown | 14.43 | Unknown | 577.54 | 5.25 | 572.29 | Yes | N/A | N/A | 2024-01-05 | 2024-01-08 | 4 | 2 | 2024-01-08 | 2024-01-16 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-03-07 | 1900-02-20 | 38 | 2024-03-07 | 2024-03-07 | 1 | 1 | 4 | 2 | 62 | 46 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 1598.1 | 1598.1 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-02-17 | -5 | -5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 9987.8 | 2911.38 | Unknown | 1649.19 | 236.41 | 5190.82 | 3981 | 1093.42 | 9987.8 | -8894.38 | Yes | N/A | N/A | 2023-04-25 | 2023-04-25 | 1 | 1 | 2023-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | Unknown | Unknown | 2024-02-12 | 2024-02-12 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-09 | -312 | -225 | No | 2022-11-16 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-08 | 2022-11-16 | Unknown | IOU Designed & Installed | N/A | Yes | 159 | -0.95 | -16.15 | Unknown | Unknown | 4.51 | 10.69 | 3885 | 717.07 | -0.95 | 718.02 | Yes | N/A | N/A | 2022-11-08 | 2023-04-24 | 168 | 120 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | 2023-10-02 | 2023-10-02 | 1 | 1 | 168 | 120 | 1 | 1 | 169 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-10 | -119 | -86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2023-11-02 | 2024-01-25 | IOU Designed & Installed | N/A | No | N/A | -1132.77 | -14.78 | Unknown | Unknown | -1145 | 27.01 | 3981 | 2044.72 | -1132.77 | 3177.49 | Yes | N/A | N/A | 2023-11-02 | 2023-06-19 | Unknown | Unknown | 2023-06-19 | 2023-11-02 | 137 | 99 | 2023-11-02 | 2023-12-05 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2024-01-25 | 51 | 37 | Unknown | 2024-01-12 | Unknown | Unknown | 2024-01-25 | 2024-02-12 | 1900-01-18 | 13 | 2024-02-12 | 2024-02-12 | 1 | 1 | 85 | 61 | 157 | 113 | 242 | 174 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-17 | -697 | -499 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-08 | 2025-05-09 | IOU Designed & Installed | N/A | No | N/A | 46.67 | -0.94 | Unknown | Unknown | Unknown | 47.61 | 3981 | 1185.74 | 46.67 | 1139.07 | Yes | N/A | N/A | 2025-05-08 | 2025-05-08 | 1 | 1 | 2025-05-08 | 2025-05-08 | 1 | 1 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-05-09 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-05-09 | 2025-05-20 | 1900-01-11 | 8 | 2025-05-20 | 2025-05-20 | 1 | 1 | 3 | 3 | 14 | 10 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 52 | 52 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | -575 | -411 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-06-19 | 2023-07-28 | IOU Designed & Installed | N/A | No | N/A | 13.39 | -4.05 | Unknown | Unknown | Unknown | 17.44 | 3981 | 853.94 | 13.39 | 840.55 | Yes | N/A | N/A | 2023-06-19 | 2023-06-19 | 1 | 1 | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | 2023-07-28 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2023-07-28 | 1899-12-31 | 1 | 2023-07-28 | 2023-07-28 | 1 | 1 | 41 | 31 | 2 | 2 | 43 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 75 | 75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | -95 | -68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-21 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 2385.42 | Unknown | Unknown | Unknown | 25.49 | 2359.93 | 3981 | 743.13 | 2385.42 | -1642.29 | Yes | N/A | N/A | 2023-09-11 | 2023-11-20 | 71 | 51 | 2023-11-20 | 2023-11-21 | 2 | 2 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2024-11-05 | 351 | 251 | Unknown | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2024-11-26 | 1900-01-21 | 16 | 2024-11-26 | 2024-11-20 | Unknown | Unknown | 422 | 302 | 24 | 18 | 446 | 320 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-02 | -605 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-01 | 2024-04-04 | 2024-05-29 | IOU Designed & Installed | N/A | No | N/A | 2618.17 | -42.09 | Unknown | Unknown | Unknown | 2660.26 | Unknown | 1030.98 | 2618.17 | -1587.19 | Yes | N/A | N/A | 2024-04-01 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-04-04 | 56 | 40 | 2024-04-04 | Unknown | Unknown | Unknown | 2024-04-04 | 2024-04-18 | 15 | 11 | 2024-04-04 | 2024-05-29 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-06-07 | 1900-01-09 | 8 | 2024-06-07 | 2024-06-07 | 1 | 1 | 56 | 40 | 82 | 60 | 138 | 100 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 79.05 | 79.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-05 | -689 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-03 | 2024-10-07 | IOU Designed & Installed | N/A | No | N/A | 67.72 | Unknown | Unknown | Unknown | Unknown | 67.72 | 3981 | 1604.34 | 67.72 | 1536.62 | Yes | N/A | N/A | 2024-10-01 | 2024-09-12 | Unknown | Unknown | 2024-09-12 | 2024-10-03 | 22 | 16 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-07 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-16 | 1900-01-09 | 8 | 2024-10-16 | 2024-10-16 | 1 | 1 | 5 | 3 | 33 | 25 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 320 | 320 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-01 | 624 | 447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-28 | 2022-04-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1083.42 | -27.14 | Unknown | Unknown | Unknown | 1110.56 | Unknown | 1492.73 | 1083.42 | 409.31 | Yes | N/A | N/A | 2022-02-28 | 2024-06-07 | 831 | 595 | 2024-06-07 | 2024-06-27 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-07-17 | Unknown | Unknown | 831 | 595 | 21 | 15 | 852 | 610 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-14 | 143 | 104 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-02-16 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 12.37 | -10.95 | Unknown | Unknown | Unknown | 23.32 | 3981 | 976.88 | 12.37 | 964.51 | Yes | N/A | N/A | 2024-01-24 | 2024-02-14 | 22 | 16 | 2024-02-14 | 2024-02-16 | 3 | 3 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-03-25 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-04-05 | 1900-01-11 | 10 | 2024-04-05 | 2024-04-05 | 1 | 1 | 61 | 43 | 16 | 14 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 178 | 127 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-22 | 2022-06-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1826.36 | Unknown | Unknown | Yes | N/A | N/A | 2022-06-22 | 2023-03-29 | 281 | 201 | 2023-03-29 | 2023-09-21 | 177 | 127 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 281 | 201 | 178 | 128 | 459 | 329 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-01 | -99 | -72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | 2025-05-28 | IOU Designed & Installed | N/A | No | N/A | -366.88 | 117.92 | Unknown | Unknown | -1967 | 1482.2 | Unknown | 1967.08 | -366.88 | 2333.96 | Yes | N/A | N/A | 2024-12-09 | 2024-12-06 | Unknown | Unknown | 2024-12-06 | 2025-04-21 | 137 | 97 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-02-13 | 32 | 24 | 2025-04-21 | 2025-05-07 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-05-29 | 1900-01-01 | 2 | 2025-05-29 | 2025-06-24 | 27 | 19 | 17 | 13 | 198 | 142 | 215 | 155 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-15 | -631 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | 2025-01-13 | IOU Designed & Installed | N/A | No | N/A | 29.47 | Unknown | Unknown | Unknown | Unknown | 29.47 | 3981 | 2008.04 | 29.47 | 1978.57 | Yes | N/A | N/A | 2024-11-14 | 2024-11-14 | 1 | 1 | 2024-11-14 | 2024-11-26 | 13 | 9 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-01-13 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-01-22 | 1900-01-09 | 8 | 2025-01-22 | 2025-01-22 | 1 | 1 | 50 | 36 | 24 | 18 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 94.25 | 94.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-18 | -409 | -294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-15 | 2025-04-03 | IOU Designed & Installed | N/A | No | N/A | 915.48 | Unknown | Unknown | Unknown | 20.16 | 895.32 | 3981 | 1629.53 | 915.48 | 714.05 | Yes | N/A | N/A | 2024-07-15 | 2024-08-01 | 18 | 14 | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2025-04-03 | 246 | 176 | Unknown | 2025-03-04 | Unknown | Unknown | 2025-04-03 | 2025-05-05 | 1900-02-01 | 23 | 2025-05-05 | 2025-05-05 | 1 | 1 | 264 | 190 | 35 | 25 | 299 | 215 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 89.05 | 89.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-14 | -524 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-03-30 | IOU Designed & Installed | N/A | No | N/A | -7.69 | -5.59 | Unknown | Unknown | Unknown | -2.1 | Unknown | 98.41 | -7.69 | 106.1 | Yes | N/A | N/A | 2023-03-14 | 2023-03-20 | 7 | 5 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | 2023-03-30 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | 2023-08-09 | 1900-05-12 | 95 | 2023-08-09 | 2023-08-09 | 1 | 1 | 18 | 14 | 134 | 96 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-10 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-04-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.37 | -4.02 | Unknown | Unknown | Unknown | 2.65 | Unknown | 370.33 | -1.37 | 371.7 | Yes | N/A | N/A | 2023-03-17 | 2023-04-06 | 21 | 15 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | 21 | 15 | 1 | 1 | 22 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | 24506 | 24506 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-03-18 | 1155 | 826 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-08 | 2022-09-07 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | 9280.15 | 305.37 | Unknown | Unknown | 18.37 | 8956.41 | 582592 | 5897.9 | 9280.15 | -3382.25 | Yes | N/A | N/A | 2021-06-08 | 2024-07-19 | 1138 | 814 | 2024-07-19 | 2024-07-22 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-07-31 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | 2025-05-16 | 2025-05-16 | 1899-12-31 | 1 | 2025-05-16 | 2025-05-16 | 1 | 1 | 1138 | 814 | 7 | 5 | 1145 | 819 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 156 | 156 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-30 | -70 | -51 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-05-26 | 2023-08-01 | IOU Designed & Installed | N/A | No | N/A | 8486.78 | 341.66 | Unknown | Unknown | 3.17 | 8141.95 | 1329.19 | 5734.17 | 8486.78 | -2752.61 | Yes | N/A | N/A | 2023-03-27 | 2023-03-24 | Unknown | Unknown | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | 2023-07-31 | 24 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-08-21 | 1900-01-20 | 15 | 2023-08-21 | 2023-08-21 | 1 | 1 | 0 | 0 | 46 | 32 | 46 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN JUAN CAPISTRANO | SAN JUAN CAPISTRANO | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | -652 | -467 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 42.89 | Unknown | Unknown | Unknown | Unknown | 42.89 | 3981 | 691.69 | 42.89 | 648.8 | Yes | N/A | N/A | 2024-12-09 | 2024-12-10 | 2 | 2 | 2024-12-10 | 2024-12-12 | 3 | 3 | 2024-12-12 | Unknown | Unknown | Unknown | 2024-12-12 | 2024-12-18 | 7 | 5 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | Unknown | 2025-02-06 | Unknown | Unknown | 2025-02-06 | 2025-02-06 | 1 | 1 | 2 | 2 | 11 | 9 | 13 | 11 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | -573 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2024-12-20 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | 46.67 | -0.94 | Unknown | Unknown | Unknown | 47.61 | 3981 | 1826.14 | 46.67 | 1779.47 | Yes | N/A | N/A | 2024-12-20 | 2024-12-20 | 1 | 1 | 2024-12-20 | 2024-12-20 | 1 | 1 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-04-24 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-22 | 1900-01-28 | 21 | 2025-05-22 | 2025-05-22 | 1 | 1 | 127 | 91 | 31 | 23 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | 80 | 80 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-28 | -565 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2023-07-24 | 2023-08-17 | IOU Designed & Installed | N/A | No | N/A | 0 | 1861.93 | Unknown | 253.86 | -2924.13 | 808.34 | Unknown | 2914.25 | Unknown | 2914.25 | Yes | N/A | N/A | 2023-07-24 | 2023-07-24 | 1 | 1 | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2023-12-11 | 1900-04-26 | 83 | 2023-12-11 | 2023-12-11 | 1 | 1 | 1 | 1 | 118 | 84 | 119 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | 2009 | 1436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 526.97 | -7.88 | Unknown | Unknown | 50.25 | 484.6 | Unknown | 661.68 | 526.97 | 134.71 | Yes | N/A | N/A | 2023-09-22 | 2023-09-22 | 1 | 1 | 2023-09-22 | 2023-09-29 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | Unknown | Unknown | Unknown | 2024-07-01 | Unknown | Unknown | 2024-07-01 | 2024-07-01 | 1 | 1 | 1 | 1 | 9 | 7 | 10 | 8 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | -508 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-26 | 2025-02-18 | 2025-05-05 | IOU Designed & Installed | N/A | No | N/A | 1008.26 | Unknown | Unknown | Unknown | Unknown | 1008.26 | 3981 | 1196.64 | 1008.26 | 188.38 | Yes | N/A | N/A | 2024-11-26 | 2024-12-13 | 18 | 14 | 2024-12-13 | 2025-02-18 | 68 | 48 | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-05-05 | 77 | 55 | Unknown | 2025-05-05 | Unknown | Unknown | 2025-05-05 | 2025-05-20 | 1900-01-15 | 12 | 2025-05-20 | 2025-05-20 | 1 | 1 | 95 | 69 | 85 | 61 | 180 | 130 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-31 | 568 | 407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-08-10 | IOU Designed & Installed | N/A | No | N/A | 3451.29 | Unknown | Unknown | Unknown | Unknown | 3451.29 | 3981 | 531.94 | 3451.29 | -2919.35 | Yes | N/A | N/A | 2023-03-20 | 2023-03-20 | 1 | 1 | 2023-03-20 | 2023-05-23 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | 2023-08-25 | 95 | 69 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-08-28 | 1900-01-18 | 13 | 2023-08-28 | 2023-08-22 | Unknown | Unknown | 96 | 70 | 84 | 60 | 180 | 130 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 46.05 | 46.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-05 | -648 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | 2025-01-31 | IOU Designed & Installed | N/A | No | N/A | 335.69 | -6.08 | Unknown | Unknown | Unknown | 341.77 | 7962 | 1628.19 | 335.69 | 1292.5 | Yes | N/A | N/A | 2025-01-09 | 2024-12-26 | Unknown | Unknown | 2024-12-26 | 2025-01-09 | 15 | 11 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-31 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-02-25 | 1900-01-25 | 18 | 2025-02-25 | 2025-02-25 | 1 | 1 | 23 | 17 | 42 | 30 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-03 | -127 | -91 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-09-27 | 2024-12-16 | IOU Designed & Installed | N/A | No | N/A | 26.5 | 1217.6 | Unknown | 177.81 | -1921 | 552.09 | Unknown | 1920.98 | 26.5 | 1894.48 | Yes | N/A | N/A | 2024-09-26 | 2024-09-26 | 1 | 1 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2024-12-27 | 1900-01-11 | 10 | 2024-12-27 | 2024-12-27 | 1 | 1 | 1 | 1 | 13 | 11 | 14 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | POWAY | COUNTY OF SAN DIEGO-SOUTH of 56, POWAY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-12 | 303 | 218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-01-31 | 2024-06-14 | IOU Designed & Installed | N/A | No | N/A | 5.74 | -5.1 | Unknown | Unknown | Unknown | 10.84 | 3981 | 392.34 | 5.74 | 386.6 | Yes | N/A | N/A | 2023-01-18 | 2024-05-30 | 499 | 357 | 2024-05-30 | 2024-06-14 | 16 | 12 | 2023-02-03 | 2023-02-07 | 5 | 3 | 2023-02-07 | 2024-06-14 | 12 | 10 | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-07-11 | 1900-01-27 | 20 | 2024-07-11 | 2024-07-11 | 1 | 1 | 504 | 360 | 57 | 43 | 561 | 403 | Steps 2,3,5,6,7 | 497 | 355 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-06 | 313 | 224 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 888.26 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-03 | 2024-04-03 | 1 | 1 | 2024-04-03 | 2024-04-03 | 1 | 1 | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | 2025-04-16 | 2025-04-15 | Unknown | Unknown | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 29 | 29 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -462 | -331 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-05-22 | 2023-09-27 | IOU Designed & Installed | N/A | No | N/A | 453.83 | -11.44 | Unknown | Unknown | 8.8 | 456.47 | 3981 | 713.92 | 453.83 | 260.09 | Yes | N/A | N/A | 2023-03-09 | 2023-05-22 | 75 | 53 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | 2023-09-27 | 129 | 93 | Unknown | 2023-08-16 | Unknown | Unknown | 2023-09-27 | 2023-10-06 | 1900-01-09 | 8 | 2023-10-06 | 2023-10-05 | Unknown | Unknown | 204 | 146 | 10 | 8 | 214 | 154 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | -254 | -181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-14 | 2023-10-14 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 244.27 | -4.28 | Unknown | Unknown | Unknown | 248.55 | 3885 | 978.48 | 244.27 | 734.21 | Yes | N/A | N/A | 2023-10-14 | 2023-10-14 | 1 | 0 | 2023-10-14 | 2023-10-14 | 1 | 0 | 2023-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-14 | 2024-07-30 | 291 | 207 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-09-20 | 1900-02-21 | 39 | 2024-09-20 | 2024-09-20 | 1 | 1 | 292 | 207 | 55 | 40 | 347 | 247 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-07 | -548 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-22 | 2025-04-18 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1885.05 | Unknown | Unknown | Yes | N/A | N/A | 2024-11-22 | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2024-11-23 | 3 | 2 | 2024-11-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-04-18 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-05-08 | 1900-01-20 | 15 | 2025-05-08 | 2025-05-08 | 1 | 1 | 148 | 106 | 25 | 18 | 173 | 124 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | -435 | -311 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-12 | 2023-06-12 | 2023-11-27 | IOU Designed & Installed | N/A | No | N/A | 838.37 | -17.09 | Unknown | Unknown | -581.55 | 1437.01 | Unknown | 625.93 | 838.37 | -212.44 | Yes | N/A | N/A | 2023-06-12 | 2023-07-28 | 47 | 35 | 2023-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2023-11-27 | 35 | 25 | Unknown | 2023-11-21 | Unknown | Unknown | 2023-11-27 | 2024-01-05 | 1900-02-08 | 30 | 2024-01-05 | 2024-01-05 | 1 | 1 | 82 | 60 | 41 | 31 | 123 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 861.05 | 861.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-15 | -59 | -44 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | 2023-08-18 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | -437.34 | -20.18 | Unknown | Unknown | -438 | 20.84 | 3981 | 1145.91 | -437.34 | 1583.25 | Yes | N/A | N/A | 2023-08-18 | 2023-03-01 | Unknown | Unknown | 2023-03-01 | 2023-08-18 | 171 | 123 | 2023-08-18 | 2023-08-30 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-08-26 | 2023-10-10 | 46 | 32 | Unknown | 2023-09-12 | Unknown | Unknown | 2023-10-10 | 2023-10-17 | 1900-01-07 | 6 | 2023-10-17 | 2023-10-17 | 1 | 1 | 59 | 41 | 180 | 130 | 239 | 171 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | -599 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-29 | 2024-06-20 | IOU Designed & Installed | N/A | No | N/A | 615.11 | -12.27 | Unknown | Unknown | -743.06 | 1370.44 | Unknown | 747.62 | 615.11 | 132.51 | Yes | N/A | N/A | 2024-04-03 | 2024-05-13 | 41 | 29 | 2024-05-13 | 2024-05-15 | 3 | 3 | 2024-05-15 | 2024-05-20 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-06-20 | 32 | 24 | Unknown | 2024-06-19 | Unknown | Unknown | 2024-06-20 | 2024-07-08 | 1900-01-18 | 13 | 2024-07-08 | 2024-07-08 | 1 | 1 | 79 | 57 | 23 | 17 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-03 | -513 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | 2023-11-08 | IOU Designed & Installed | N/A | No | N/A | 0.37 | -4.45 | Unknown | Unknown | Unknown | 4.82 | 3981 | 556.6 | 0.37 | 556.23 | Yes | N/A | N/A | 2023-10-09 | 2023-10-09 | 1 | 1 | 2023-10-09 | 2023-10-09 | 1 | 1 | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2023-11-08 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2023-12-07 | 1900-01-29 | 22 | 2023-12-07 | 2023-12-07 | 1 | 1 | 32 | 24 | 32 | 24 | 64 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-03 | -462 | -331 | No | 2023-08-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-04 | 2023-10-05 | IOU Designed & Installed | N/A | Yes | 28 | -3.79 | -4.27 | Unknown | Unknown | Unknown | 0.48 | 3961 | 153.83 | -3.79 | 157.62 | Yes | N/A | N/A | 2023-08-04 | 2023-09-01 | 29 | 21 | 2023-09-01 | 2023-09-01 | 1 | 1 | 2023-09-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2023-10-05 | 35 | 25 | Unknown | 2023-10-04 | Unknown | Unknown | 2023-10-05 | 2023-11-27 | 1900-02-22 | 38 | 2023-11-27 | 2023-11-27 | 1 | 1 | 64 | 46 | 56 | 40 | 120 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-07-19 | 798 | 571 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-11-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 493.02 | Unknown | Unknown | Unknown | -447 | 940.02 | Unknown | 392.22 | 493.02 | -100.8 | Yes | N/A | N/A | 2023-10-03 | 2023-11-20 | 49 | 35 | 2023-11-20 | 2024-01-16 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2025-02-06 | 297 | 213 | 2024-01-16 | 2024-09-09 | 238 | 170 | Unknown | 2024-09-13 | Unknown | Unknown | Unknown | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2024-09-24 | Unknown | Unknown | 287 | 205 | 355 | 255 | 642 | 460 | Steps 2,3,5,6,7 | 387 | 277 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 184.15 | 184.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | -603 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 3134.97 | 318.38 | Unknown | 42.73 | 5.52 | 2768.34 | 3981 | 1399.47 | 3134.97 | -1735.5 | Yes | N/A | N/A | 2024-10-22 | 2024-11-01 | 11 | 9 | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2025-01-28 | 89 | 63 | Unknown | 2025-01-23 | Unknown | Unknown | 2025-01-28 | 2025-01-28 | 1899-12-31 | 1 | 2025-01-28 | 2025-01-28 | 1 | 1 | 100 | 72 | 3 | 3 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | BORREGO SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-03 | 70 | 51 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-04-12 | 2024-01-02 | IOU Designed & Installed | N/A | No | N/A | 13884.56 | 2156.88 | Unknown | Unknown | 41.86 | 11685.82 | 13056 | 10247.34 | 13884.56 | -3637.22 | Yes | N/A | N/A | 2023-02-17 | 2023-02-13 | Unknown | Unknown | 2023-02-13 | 2023-06-14 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | 2023-06-15 | 3 | 3 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-02 | 2024-01-12 | 1900-01-10 | 9 | 2024-01-12 | 2024-01-12 | 1 | 1 | 0 | 0 | 137 | 101 | 137 | 101 | Steps 2,3,5,6,7 | 1 | 1 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | 240 | 240 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-19 | -247 | -178 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1245.82 | 2770.94 | Unknown | Unknown | -5347 | 1330.24 | Unknown | 5347.08 | -1245.82 | 6592.9 | Yes | N/A | N/A | 2024-04-30 | 2024-04-17 | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-11 | -121 | -87 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-05 | 2023-08-30 | 2023-11-07 | IOU Designed & Installed | N/A | No | N/A | -18.78 | -15.93 | Unknown | Unknown | Unknown | -2.85 | 3981 | 1061.96 | -18.78 | 1080.74 | Yes | N/A | N/A | 2023-08-05 | 2023-08-30 | 26 | 18 | 2023-08-30 | 2023-08-30 | 1 | 1 | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-11-07 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2024-01-11 | 1900-03-06 | 48 | 2024-01-11 | 2024-01-11 | 1 | 1 | 96 | 68 | 68 | 50 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | LA JOLLA | LA JOLLA | 234 | 234 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-15 | -305 | -218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-16 | 2022-12-16 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 53596.96 | 17547.08 | Unknown | Unknown | -42392.35 | 78442.23 | 3981 | 47562.94 | 53596.96 | -6034.02 | Yes | N/A | N/A | 2022-12-16 | 2023-03-06 | 81 | 57 | 2023-03-06 | 2023-08-01 | 149 | 107 | 2023-04-12 | 2023-07-31 | 9 | 7 | 2023-04-18 | 2024-02-22 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2024-10-24 | 322 | 230 | 2024-10-28 | 2025-02-13 | 1900-04-18 | 79 | 2025-02-13 | 2025-02-13 | 1 | 1 | 90 | 64 | 606 | 436 | 696 | 500 | Steps 2,3,5,6,7 | 215 | 153 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-20 | -612 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | 446.39 | Unknown | Unknown | Unknown | 3.48 | 442.91 | 3981 | 2890.97 | 446.39 | 2444.58 | Yes | N/A | N/A | 2025-03-12 | 2025-04-03 | 23 | 17 | 2025-04-03 | 2025-04-09 | 7 | 5 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-06-18 | 71 | 51 | Unknown | 2025-05-29 | Unknown | Unknown | 2025-06-18 | 2025-06-18 | 1899-12-31 | 1 | 2025-06-18 | 2025-06-18 | 1 | 1 | 94 | 68 | 9 | 7 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | -406 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-09-01 | 2023-10-16 | IOU Designed & Installed | N/A | No | N/A | 662.98 | 309 | Unknown | 147.4 | Unknown | 206.58 | 3981 | 465.36 | 662.98 | -197.62 | Yes | N/A | N/A | 2023-05-15 | 2023-09-01 | 110 | 80 | 2023-09-01 | 2023-09-01 | 1 | 1 | 2023-09-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2023-10-16 | 46 | 32 | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | 2024-02-03 | 1900-04-20 | 80 | 2024-02-03 | 2024-02-03 | 1 | 0 | 156 | 112 | 113 | 81 | 269 | 193 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 57.05 | 57.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | -351 | -252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-08 | 2023-10-09 | 2024-08-13 | IOU Designed & Installed | N/A | No | N/A | 2228.88 | 483.36 | Unknown | Unknown | Unknown | 1745.52 | 3941 | 741.27 | 2228.88 | -1487.61 | Yes | N/A | N/A | 2023-10-08 | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-11-06 | 99 | 71 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2024-08-13 | 282 | 202 | Unknown | 2024-07-24 | Unknown | Unknown | 2024-08-13 | 2024-08-14 | 1900-01-01 | 2 | 2024-08-14 | 2024-08-14 | 1 | 1 | 282 | 202 | 102 | 74 | 384 | 276 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | -439 | -315 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-04-04 | 2023-09-08 | IOU Designed & Installed | N/A | No | N/A | 124.81 | -8.46 | Unknown | Unknown | Unknown | 133.27 | 3981 | 923.07 | 124.81 | 798.26 | Yes | N/A | N/A | 2023-03-23 | 2023-04-04 | 13 | 9 | 2023-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-04 | 2023-08-30 | 43 | 31 | 2023-04-04 | 2023-09-08 | 158 | 114 | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | 2023-09-25 | 1900-01-17 | 12 | 2023-09-25 | 2023-09-25 | 1 | 1 | 171 | 123 | 62 | 44 | 233 | 167 | Steps 2,3,5,6,7 | 148 | 106 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-17 | -201 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -947.23 | -11.89 | Unknown | Unknown | -1539 | 603.66 | 0 | 996.08 | -947.23 | 1943.31 | Yes | N/A | N/A | 2023-11-13 | 2023-12-07 | 25 | 19 | 2023-12-07 | 2024-08-09 | 247 | 177 | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-03-25 | 1 | 1 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | 2025-04-30 | 2025-04-30 | 1 | 1 | 25 | 19 | 249 | 179 | 274 | 198 | Steps 2,3,5,6,7 | 228 | 162 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-31 | -363 | -260 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 508.48 | -9.82 | Unknown | Unknown | Unknown | 518.3 | Unknown | 403.93 | 508.48 | -104.55 | Yes | N/A | N/A | 2024-11-11 | 2024-11-12 | 2 | 2 | 2024-11-12 | 2025-01-10 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-12-13 | 31 | 23 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-02 | 2025-04-02 | 1 | 1 | 2 | 2 | 92 | 68 | 94 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-13 | -133 | -96 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-08-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1192.39 | -52.61 | Unknown | Unknown | 5.27 | 1239.73 | Unknown | 1266.37 | 1192.39 | 73.98 | Yes | N/A | N/A | 2023-07-11 | 2023-07-11 | 1 | 1 | 2023-07-11 | 2023-08-16 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-08-18 | 9 | 7 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | Unknown | Unknown | Unknown | 2024-02-01 | Unknown | Unknown | 2024-02-01 | 2024-02-01 | 1 | 1 | 1 | 1 | 47 | 35 | 48 | 36 | Steps 2,3,5,6,7 | 2 | 2 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-25 | -558 | -399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 1613.76 | 506.17 | Unknown | Unknown | Unknown | 1107.59 | Unknown | 1094.11 | 1613.76 | -519.65 | Yes | N/A | N/A | 2024-04-18 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | 2024-04-18 | 71 | 51 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-07-11 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-07-16 | 1900-01-05 | 4 | 2024-07-16 | 2024-07-16 | 1 | 1 | 85 | 61 | 78 | 56 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | -219 | -158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2023-10-17 | IOU Designed & Installed | N/A | No | N/A | 2866.59 | 857.15 | Unknown | 243.48 | Unknown | 1765.96 | 3981 | 1120.5 | 2866.59 | -1746.09 | Yes | N/A | N/A | 2023-09-14 | 2023-10-06 | 23 | 17 | 2023-10-06 | 2023-10-06 | 1 | 1 | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | 2023-10-17 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2023-10-26 | 1900-01-09 | 8 | 2023-10-26 | 2023-10-25 | Unknown | Unknown | 35 | 25 | 11 | 9 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 198.05 | 198.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-19 | -220 | -159 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | 2024-02-09 | IOU Designed & Installed | N/A | No | N/A | 3653.31 | 1072.22 | Unknown | 483.46 | Unknown | 2097.63 | 3981 | 1400.65 | 3653.31 | -2252.66 | Yes | N/A | N/A | 2023-10-17 | 2023-10-27 | 11 | 9 | 2023-10-27 | 2023-10-27 | 1 | 1 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2024-02-09 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-02-12 | 1900-01-03 | 2 | 2024-02-12 | 2024-02-12 | 1 | 1 | 117 | 85 | 6 | 4 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-20 | -5 | -5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 2795.29 | Unknown | Unknown | Yes | N/A | N/A | 2023-09-07 | 2023-08-28 | Unknown | Unknown | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -163 | -118 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-30 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 619.24 | -11.7 | Unknown | Unknown | Unknown | 630.94 | 3981 | 1495.36 | 619.24 | 876.12 | Yes | N/A | N/A | 2024-05-28 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-05-30 | 85 | 61 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-07-25 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-08-14 | 1900-01-20 | 15 | 2024-08-14 | 2024-08-14 | 1 | 1 | 57 | 41 | 107 | 77 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-23 | -494 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | 2024-09-05 | IOU Designed & Installed | N/A | No | N/A | 12.61 | Unknown | Unknown | Unknown | Unknown | 12.61 | 3981 | 974.14 | 12.61 | 961.53 | Yes | N/A | N/A | 2024-04-30 | 2024-04-30 | 1 | 1 | 2024-04-30 | 2024-04-30 | 1 | 1 | 2024-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2024-09-05 | 129 | 93 | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2024-10-18 | 1900-02-12 | 32 | 2024-10-18 | 2024-10-17 | Unknown | Unknown | 130 | 94 | 45 | 33 | 175 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 1374.05 | 1374.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-02-03 | -262 | -187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-06-30 | 2023-10-03 | IOU Designed & Installed | N/A | No | N/A | 617.97 | -29.3 | Unknown | Unknown | 159.58 | 487.69 | 3961 | 871.91 | 617.97 | 253.94 | Yes | N/A | N/A | 2023-04-19 | 2023-06-30 | 73 | 53 | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-03 | 2023-10-03 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2024-10-10 | 1901-01-08 | 268 | 2024-10-10 | 2024-05-17 | Unknown | Unknown | 166 | 120 | 375 | 269 | 541 | 389 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-13 | -60 | -45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-11-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 959.3 | 3651.22 | Unknown | 1634.7 | -5939 | 1612.38 | Unknown | 5938.8 | 959.3 | 4979.5 | Yes | N/A | N/A | 2023-10-23 | 2023-10-23 | 1 | 1 | 2023-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-25 | -419 | -300 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | 2024-07-30 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 832.81 | -11.21 | Unknown | Unknown | 25.03 | 818.99 | 3981 | 1146.68 | 832.81 | 313.87 | Yes | N/A | N/A | 2024-07-01 | 2024-05-31 | Unknown | Unknown | 2024-05-31 | 2024-07-30 | 61 | 43 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2025-03-17 | 231 | 165 | Unknown | 2025-03-05 | Unknown | Unknown | 2025-03-17 | 2025-04-03 | 1900-01-17 | 14 | 2025-04-03 | 2025-04-01 | Unknown | Unknown | 231 | 165 | 79 | 57 | 310 | 222 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-24 | -584 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | 2025-03-19 | IOU Designed & Installed | N/A | No | N/A | 9195.23 | 1560.96 | Unknown | Unknown | 5.82 | 7628.45 | 3981 | 1219.94 | 9195.23 | -7975.29 | Yes | N/A | N/A | 2024-12-03 | 2024-11-11 | Unknown | Unknown | 2024-11-11 | 2025-01-22 | 73 | 53 | 2025-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-03-19 | 57 | 41 | Unknown | 2025-02-03 | Unknown | Unknown | 2025-03-19 | 2025-03-19 | 1899-12-31 | 1 | 2025-03-19 | 2025-03-19 | 1 | 1 | 57 | 41 | 75 | 55 | 132 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | SAN MARCOS | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-01 | 713 | 510 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-09 | 2023-03-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 49887.93 | 13469.73 | Unknown | Unknown | 128.94 | 36289.26 | 27030 | 20640.61 | 49887.93 | -29247.32 | Yes | N/A | N/A | 2022-02-09 | 2023-03-02 | 387 | 277 | 2023-03-02 | 2023-09-22 | 205 | 147 | 2023-06-19 | 2024-01-08 | 24 | 18 | 2023-07-10 | 2024-08-08 | 21 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-08-08 | 113 | 81 | Unknown | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-09-13 | Unknown | Unknown | 411 | 295 | 339 | 235 | 750 | 530 | Steps 2,3,5,6,7 | 277 | 199 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 309 | 309 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-17 | -412 | -295 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-11-02 | 2024-05-08 | IOU Designed & Installed | N/A | No | N/A | -6.32 | -5.12 | Unknown | Unknown | Unknown | -1.2 | Unknown | 513.31 | -6.32 | 519.63 | Yes | N/A | N/A | 2023-10-09 | 2023-10-31 | 23 | 17 | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2024-05-08 | 189 | 135 | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2024-05-31 | 1900-01-23 | 18 | 2024-05-31 | 2024-05-31 | 1 | 1 | 212 | 152 | 25 | 19 | 237 | 171 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | 146 | 146 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -451 | -322 | No | 2024-01-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-10 | 2024-08-30 | IOU Designed & Installed | N/A | Yes | 50 | 4484.49 | 1115.38 | Unknown | Unknown | 9.22 | 3359.89 | 3981 | 2625.49 | 4484.49 | -1859 | Yes | N/A | N/A | 2024-01-10 | 2024-02-29 | 51 | 37 | 2024-02-29 | 2024-01-10 | Unknown | Unknown | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-08-30 | 234 | 168 | Unknown | 2024-07-26 | Unknown | Unknown | 2024-08-30 | 2024-08-30 | 1899-12-31 | 1 | 2024-08-30 | 2024-09-05 | 7 | 5 | 285 | 205 | 8 | 6 | 293 | 211 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | 600 | 429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-29 | 2023-05-16 | 2024-01-29 | IOU Designed & Installed | N/A | No | N/A | 131956.76 | 15998.46 | Unknown | 4146.03 | 32114.59 | 79697.68 | 0 | 76939.65 | 131956.76 | -55017.11 | Yes | N/A | N/A | 2022-11-29 | 2023-05-16 | 169 | 121 | 2023-05-16 | 2024-01-29 | 259 | 185 | 2023-05-26 | 2023-10-19 | 52 | 37 | 2023-11-10 | 2023-11-14 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | 2024-01-29 | 2024-09-23 | 1900-08-26 | 171 | 2024-09-23 | 2024-09-23 | 1 | 1 | 221 | 158 | 504 | 360 | 725 | 518 | Steps 2,3,5,6,7 | 417 | 297 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 9 | 7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-17 | 2023-05-05 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | 1998.32 | Unknown | Unknown | Unknown | Unknown | 1998.32 | Unknown | 2081.9 | 1998.32 | 83.58 | Yes | N/A | N/A | 2022-11-17 | 2023-05-05 | 170 | 122 | 2023-05-05 | 2023-10-04 | 153 | 109 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2023-10-24 | 1900-01-13 | 10 | 2023-10-24 | 2023-10-24 | 1 | 1 | 170 | 122 | 168 | 120 | 338 | 242 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-12 | -699 | -500 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-15 | 2024-11-15 | 2024-11-18 | IOU Designed & Installed | N/A | No | N/A | 40.22 | Unknown | Unknown | Unknown | Unknown | 40.22 | 3981 | 1446.93 | 40.22 | 1406.71 | Yes | N/A | N/A | 2024-11-15 | 2024-11-15 | 1 | 1 | 2024-11-15 | 2024-11-15 | 1 | 1 | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-11-18 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-12-13 | 1900-01-25 | 20 | 2024-12-13 | 2024-12-13 | 1 | 1 | 5 | 3 | 28 | 22 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | San Juan Capistrano | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-02 | 414 | 297 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-06-07 | 2023-06-18 | IOU Designed & Installed | N/A | No | N/A | -6394.52 | 1724.4 | Unknown | 1163.76 | -10451 | 1168.32 | Unknown | 10450.71 | -6394.52 | 16845.23 | Yes | N/A | N/A | 2023-05-19 | 2023-06-06 | 19 | 13 | 2023-06-06 | 2023-06-20 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-18 | 2023-06-20 | 1900-01-02 | 2 | 2023-06-20 | 2023-06-20 | 1 | 1 | 19 | 13 | 19 | 14 | 38 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DESCANSO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-23 | -259 | -186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2023-11-14 | IOU Designed & Installed | N/A | No | N/A | 3481.5 | 1208.4 | Unknown | Unknown | 23.3 | 2249.8 | 3981 | 842.03 | 3481.5 | -2639.47 | Yes | N/A | N/A | 2023-09-29 | 2023-09-12 | Unknown | Unknown | 2023-09-12 | 2023-09-29 | 18 | 14 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-11-14 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2023-12-08 | 1900-01-24 | 19 | 2023-12-08 | 2023-12-08 | 1 | 1 | 47 | 33 | 44 | 34 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | 235 | 168 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 762.5 | 62.64 | Unknown | Unknown | 16.92 | 682.94 | 0 | 3591.83 | 762.5 | 2829.33 | Yes | N/A | N/A | 2023-10-11 | 2024-06-19 | 253 | 181 | 2024-06-19 | 2024-07-08 | 20 | 14 | 2025-03-31 | 2025-04-14 | 15 | 11 | 2024-02-15 | 2025-04-28 | 112 | 80 | 2024-07-08 | 2025-01-28 | 205 | 147 | Unknown | 2025-02-12 | Unknown | Unknown | Unknown | 2025-05-23 | Unknown | Unknown | 2025-05-23 | 2025-05-21 | Unknown | Unknown | 473 | 339 | 132 | 94 | 605 | 433 | Steps 2,3,5,6,7 | 718 | 512 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 100.05 | 100.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | -487 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | 2023-07-24 | IOU Designed & Installed | N/A | No | N/A | 428.17 | -6.79 | Unknown | Unknown | Unknown | 434.96 | 3981 | 705.99 | 428.17 | 277.82 | Yes | N/A | N/A | 2023-02-23 | 2023-05-01 | 68 | 48 | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | 2023-07-24 | 85 | 61 | Unknown | 2023-07-19 | Unknown | Unknown | 2023-07-24 | 2023-07-31 | 1900-01-07 | 6 | 2023-07-31 | 2023-07-31 | 1 | 1 | 153 | 109 | 9 | 7 | 162 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-19 | 214 | 154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8562.75 | Unknown | Unknown | Unknown | Unknown | 8562.75 | 49057 | 2982.91 | 8562.75 | -5579.84 | Yes | N/A | N/A | 2023-06-27 | 2023-06-21 | Unknown | Unknown | 2023-06-21 | 2023-11-20 | 153 | 109 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2024-05-09 | 172 | 124 | Unknown | 2024-06-06 | Unknown | Unknown | Unknown | 2024-07-08 | Unknown | Unknown | 2024-07-08 | 2024-06-20 | Unknown | Unknown | 172 | 124 | 153 | 109 | 325 | 233 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-06 | -275 | -197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-08 | 2023-10-03 | IOU Designed & Installed | N/A | No | N/A | 388.42 | 894.52 | Unknown | 426.46 | -1610 | 677.44 | Unknown | 1610.05 | 388.42 | 1221.63 | Yes | N/A | N/A | 2023-09-08 | 2023-09-08 | 1 | 1 | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-10-05 | 1900-01-02 | 3 | 2023-10-05 | 2023-10-05 | 1 | 1 | 1 | 1 | 4 | 4 | 5 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-05 | -254 | -183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-10 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | 1751.49 | 27.23 | Unknown | Unknown | 5.52 | 1718.74 | 3981 | 1751.29 | 1751.49 | -0.2 | Yes | N/A | N/A | 2024-07-10 | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2025-05-06 | 315 | 225 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-06-20 | 46 | 34 | Unknown | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-06-24 | 1900-02-04 | 26 | 2025-06-24 | 2025-06-24 | 1 | 1 | 46 | 34 | 352 | 252 | 398 | 286 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-09 | -563 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-28 | 2023-07-18 | IOU Designed & Installed | N/A | No | N/A | 475.19 | 292.22 | Unknown | Unknown | Unknown | 182.97 | Unknown | 480.44 | 475.19 | 5.25 | Yes | N/A | N/A | 2023-06-07 | 2023-06-28 | 22 | 16 | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-07-18 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-08-24 | 1900-02-06 | 28 | 2023-08-24 | 2023-08-24 | 1 | 1 | 43 | 31 | 39 | 29 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | -501 | -360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2025-01-19 | 2025-05-21 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1694.84 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-03 | 2025-01-16 | 45 | 33 | 2025-01-16 | 2025-04-24 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-04-22 | 27 | 19 | 2025-04-24 | 2025-05-19 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-06-27 | 1900-02-06 | 28 | 2025-06-27 | 2025-06-23 | Unknown | Unknown | 71 | 51 | 164 | 118 | 235 | 169 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | El Cajon | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -432 | -309 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2024-10-22 | IOU Designed & Installed | N/A | No | N/A | 2068.22 | 15405.52 | Unknown | 2089.17 | -24836 | 9409.53 | Unknown | 23415.55 | 2068.22 | 21347.33 | Yes | N/A | N/A | 2024-08-22 | 2024-08-27 | 6 | 4 | 2024-08-27 | 2024-09-19 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-10-16 | 51 | 37 | 2024-09-25 | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-16 | 22 | 16 | 2024-10-22 | 2024-10-25 | 1900-01-03 | 4 | 2024-10-25 | 2024-10-25 | 1 | 1 | 6 | 4 | 102 | 76 | 108 | 80 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | POWAY | 137 | 137 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-08-30 | 833 | 596 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-02-14 | 2023-11-14 | IOU Designed & Installed | N/A | No | N/A | 1275.73 | 1248.54 | Unknown | Unknown | -9426 | 9453.19 | 3981 | 13172.4 | 1275.73 | 11896.67 | Yes | N/A | N/A | 2023-01-31 | 2023-01-31 | 1 | 1 | 2023-01-31 | 2023-06-08 | 129 | 93 | 2023-02-14 | 2023-09-27 | 51 | 37 | 2023-06-01 | 2023-10-18 | 114 | 82 | 2023-06-08 | 2023-11-29 | 175 | 125 | 2023-10-11 | 2023-11-09 | 30 | 22 | 2023-11-14 | 2023-12-12 | 1900-01-28 | 21 | 2023-12-12 | 2023-12-11 | Unknown | Unknown | 227 | 163 | 302 | 218 | 529 | 381 | Steps 2,3,5,6,7 | 413 | 295 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-02 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-10-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 611.99 | Unknown | Unknown | Unknown | Unknown | 611.99 | Unknown | 1577.5 | 611.99 | 965.51 | Yes | N/A | N/A | 2024-09-16 | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-10-01 | 27 | 19 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | 2024-11-06 | 2024-11-06 | 1 | 1 | 0 | 0 | 28 | 20 | 28 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-25 | -626 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | 1201.65 | -24.15 | Unknown | Unknown | Unknown | 1225.8 | Unknown | 1901.08 | 1201.65 | 699.43 | Yes | N/A | N/A | 2025-04-07 | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-04-18 | 25 | 19 | 2025-04-18 | Unknown | Unknown | Unknown | 2025-04-11 | 2025-05-14 | 34 | 24 | 2025-04-18 | 2025-05-20 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-06-09 | 1900-01-20 | 15 | 2025-06-09 | 2025-06-09 | 1 | 1 | 33 | 23 | 81 | 59 | 114 | 82 | Steps 2,3,5,6,7 | 26 | 18 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-28 | -583 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-18 | 2025-05-21 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1727.87 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-18 | 2025-02-18 | 1 | 1 | 2025-02-18 | 2025-03-06 | 17 | 13 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-05-21 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-06-24 | 1900-02-03 | 25 | 2025-06-24 | 2025-06-24 | 1 | 1 | 78 | 56 | 53 | 39 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-12 | -686 | -491 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4.39 | Unknown | Unknown | Unknown | Unknown | 4.39 | Unknown | 1653.95 | 4.39 | 1649.56 | Yes | N/A | N/A | 2024-12-11 | 2024-11-14 | Unknown | Unknown | 2024-11-14 | 2024-12-13 | 30 | 22 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | 2024-12-26 | 2024-12-26 | 1 | 1 | 0 | 0 | 31 | 23 | 31 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 36.05 | 36.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-23 | -432 | -309 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 59.35 | Unknown | Unknown | Unknown | Unknown | 59.35 | Unknown | 1714.96 | 59.35 | 1655.61 | Yes | N/A | N/A | 2024-10-03 | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-10-03 | 29 | 21 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | 2024-12-18 | 2024-12-18 | 1 | 1 | 0 | 0 | 30 | 22 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-05 | -410 | -293 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-06-27 | IOU Designed & Installed | N/A | No | N/A | 26.86 | Unknown | Unknown | Unknown | Unknown | 26.86 | 3241 | 949.52 | 26.86 | 922.66 | Yes | N/A | N/A | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-04-25 | 2024-10-17 | 176 | 126 | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-06-27 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-11-21 | 1900-05-27 | 106 | 2024-11-21 | 2024-11-21 | 1 | 1 | 241 | 173 | 150 | 108 | 391 | 281 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 405098.75 | 405098.75 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-11-01 | 370 | 265 | No | 2023-02-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-03-10 | 2024-09-16 | IOU Designed & Installed | N/A | Yes | 593 | 117.16 | Unknown | Unknown | Unknown | Unknown | 117.16 | 3981 | 515.35 | 117.16 | 398.19 | Yes | N/A | N/A | 2023-02-23 | 2024-10-08 | 594 | 424 | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | 2024-09-16 | 557 | 397 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-10-25 | 1900-02-08 | 30 | 2024-10-25 | 2024-11-05 | 12 | 8 | 1151 | 821 | 53 | 39 | 1204 | 860 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-07 | -554 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2025-02-27 | 2025-04-18 | IOU Designed & Installed | N/A | No | N/A | 62.22 | -1.25 | Unknown | Unknown | Unknown | 63.47 | 3981 | 2341.45 | 62.22 | 2279.23 | Yes | N/A | N/A | 2024-11-25 | 2025-02-26 | 94 | 68 | 2025-02-26 | 2025-02-26 | 1 | 1 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-04-18 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-05-02 | 1900-01-14 | 11 | 2025-05-02 | 2025-05-02 | 1 | 1 | 145 | 105 | 17 | 13 | 162 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-22 | -155 | -112 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 872.77 | 189.35 | Unknown | Unknown | 3.19 | 680.23 | 3981 | 452.47 | 872.77 | -420.3 | Yes | N/A | N/A | 2024-02-02 | 2023-11-01 | Unknown | Unknown | 2023-11-01 | 2024-02-08 | 100 | 72 | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-04-15 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-04-17 | 1900-01-02 | 3 | 2024-04-17 | 2024-08-20 | 126 | 90 | 68 | 48 | 229 | 165 | 297 | 213 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-12-31 | 943 | 674 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-03-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 411.96 | -7.43 | Unknown | Unknown | Unknown | 419.39 | 7962 | 2012.52 | 411.96 | 1600.56 | Yes | N/A | N/A | 2024-02-29 | 2024-03-05 | 6 | 4 | 2024-03-05 | 2024-04-11 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-03-29 | 24 | 18 | 2024-04-11 | 2024-07-12 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2024-07-31 | Unknown | Unknown | 99 | 71 | 62 | 46 | 161 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-03 | -577 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-06-24 | 2024-09-13 | IOU Designed & Installed | N/A | No | N/A | 31.78 | Unknown | Unknown | Unknown | Unknown | 31.78 | Unknown | 1431.05 | 31.78 | 1399.27 | Yes | N/A | N/A | 2024-06-24 | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-06-24 | 48 | 34 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-09-13 | 82 | 60 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-10-03 | 1900-01-20 | 15 | 2024-10-03 | 2024-10-03 | 1 | 1 | 82 | 60 | 70 | 50 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-25 | -253 | -182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1303.86 | 2545.77 | Unknown | 485.57 | -2950 | 1222.52 | Unknown | 2950.03 | 1303.86 | 1646.17 | Yes | N/A | N/A | 2024-05-09 | 2024-05-03 | Unknown | Unknown | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-07 | -630 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1582.63 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-04-01 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-17 | 1900-01-16 | 13 | 2025-04-17 | 2025-04-17 | 1 | 1 | 65 | 47 | 19 | 15 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-07 | -419 | -300 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-11 | 2023-11-11 | 2024-05-10 | IOU Designed & Installed | N/A | No | N/A | 14.29 | -12.72 | Unknown | Unknown | Unknown | 27.01 | Unknown | 892.89 | 14.29 | 878.6 | Yes | N/A | N/A | 2023-11-11 | 2023-11-11 | 1 | 0 | 2023-11-11 | 2023-11-11 | 1 | 0 | 2023-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-11 | 2024-05-10 | 182 | 130 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-05-14 | 1900-01-04 | 3 | 2024-05-14 | 2024-05-14 | 1 | 1 | 183 | 130 | 7 | 4 | 190 | 134 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | 632 | 451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-03 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 573264 | 25185.61 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-03 | 2024-06-03 | 1 | 1 | 2024-06-03 | 2024-07-17 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2025-09-05 | 416 | 298 | Unknown | 2025-05-20 | Unknown | Unknown | 2025-09-03 | 2025-06-23 | Unknown | Unknown | 2025-06-23 | 2025-06-23 | 1 | 1 | 417 | 299 | 46 | 34 | 463 | 333 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-26 | -567 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-13 | 2025-05-01 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1464.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2025-01-08 | 2 | 2 | 2025-01-08 | 2025-01-13 | 6 | 4 | 2025-01-13 | 2025-05-01 | 109 | 79 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-01 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-08 | 1900-01-07 | 6 | 2025-05-08 | 2025-05-08 | 1 | 1 | 112 | 82 | 15 | 11 | 127 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-NORTH of 56, COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -277 | -198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-02-01 | 2024-03-08 | IOU Designed & Installed | N/A | No | N/A | 18426.11 | Unknown | Unknown | Unknown | Unknown | 18426.11 | 335039 | 8451.97 | 18426.11 | -9974.14 | Yes | N/A | N/A | 2023-01-31 | 2023-02-27 | 28 | 20 | 2023-02-27 | 2023-05-11 | 74 | 54 | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | 2023-04-04 | 14 | 10 | 2023-05-11 | 2958465 | Unknown | Unknown | Unknown | 2024-02-23 | Unknown | Unknown | 2024-03-08 | 2024-03-29 | 1900-01-21 | 16 | 2024-03-29 | 2024-03-29 | 1 | 1 | 28 | 20 | 111 | 81 | 139 | 101 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | Carlsbad | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-21 | -177 | -126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-09 | 2023-06-19 | IOU Designed & Installed | N/A | No | N/A | 1440.02 | 1685.52 | Unknown | 998.64 | -2362 | 1117.86 | Unknown | 2361.73 | 1440.02 | 921.71 | Yes | N/A | N/A | 2023-05-09 | 2023-06-12 | 35 | 25 | 2023-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | 2023-10-27 | 1900-05-10 | 95 | 2023-10-27 | 2023-10-27 | 1 | 1 | 35 | 25 | 132 | 96 | 167 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | Encinitas | N/A | 30000 | 30000 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-11-01 | 504 | 361 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-23 | 2023-04-20 | 2024-01-31 | IOU Designed & Installed | N/A | No | N/A | 36740.38 | 1670.5 | Unknown | Unknown | 8017.43 | 27052.45 | Unknown | 35013.86 | 36740.38 | -1726.52 | Yes | N/A | N/A | 2022-02-23 | 2023-08-02 | 526 | 376 | 2023-08-02 | 2023-09-19 | 49 | 35 | 2023-07-26 | 2023-09-15 | 51 | 36 | 2023-09-20 | 2023-09-29 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | Unknown | Unknown | 2024-01-31 | 2024-03-19 | 1900-02-17 | 35 | 2024-03-19 | 2024-03-19 | 1 | 1 | 577 | 412 | 109 | 79 | 686 | 491 | Steps 2,3,5,6,7 | 55 | 39 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 72 | 72 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-22 | -559 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | 2023-05-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 928.87 | -30.14 | Unknown | Unknown | Unknown | 959.01 | 3885 | 756.7 | 928.87 | -172.17 | Yes | N/A | N/A | 2023-05-26 | 2023-05-26 | 1 | 1 | 2023-05-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | Unknown | Unknown | 2023-07-13 | 2023-07-13 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-13 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | -18.66 | -14.38 | Unknown | Unknown | Unknown | -4.28 | Unknown | 154.79 | -18.66 | 173.45 | Yes | N/A | N/A | 2023-04-11 | 2023-04-24 | 14 | 10 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | Unknown | Unknown | 2023-07-13 | 2023-07-13 | 1 | 1 | 14 | 10 | 1 | 1 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-14 | 187 | 134 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1757.5 | Unknown | Unknown | Unknown | 96.19 | 1661.31 | 3981 | 604.8 | 1757.5 | -1152.7 | Yes | N/A | N/A | 2024-02-16 | 2024-02-20 | 5 | 3 | 2024-02-20 | 2024-02-20 | 1 | 1 | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-05-20 | 1 | 1 | 5 | 3 | 2 | 2 | 7 | 5 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-02 | 569 | 408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-03-18 | 2025-04-28 | IOU Designed & Installed | N/A | No | N/A | 30349.15 | 2091.41 | Unknown | 28.71 | Unknown | 28229.03 | 0 | 44933.27 | 30349.15 | 14584.12 | Yes | N/A | N/A | 2024-01-08 | 2024-01-08 | 1 | 1 | 2024-01-08 | 2024-12-12 | 340 | 244 | 2024-03-22 | 2024-10-18 | 38 | 28 | 2024-11-22 | 2024-12-11 | 20 | 14 | 2024-12-12 | 2025-01-24 | 44 | 32 | Unknown | 2025-01-17 | Unknown | Unknown | 2025-04-28 | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-02-21 | Unknown | Unknown | 83 | 61 | 360 | 258 | 443 | 319 | Steps 2,3,5,6,7 | 265 | 189 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-19 | -111 | -80 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 550.41 | -14.95 | Unknown | Unknown | 2.94 | 562.42 | 3981 | 751.7 | 550.41 | 201.29 | Yes | N/A | N/A | 2023-12-20 | 2023-12-19 | Unknown | Unknown | 2023-12-19 | 2024-01-04 | 17 | 13 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | Unknown | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | 2024-05-31 | 2024-05-31 | 1 | 1 | 0 | 0 | 18 | 14 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-23 | 297 | 212 | No | 2021-12-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-13 | 2021-12-13 | Unknown | IOU Designed & Installed | N/A | Yes | 912 | 10.56 | -8.7 | Unknown | Unknown | Unknown | 19.26 | 3981 | 1408.24 | 10.56 | 1397.68 | Yes | N/A | N/A | 2021-12-13 | 2024-06-12 | 913 | 653 | 2024-06-12 | 2024-06-12 | 1 | 1 | 2024-06-12 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-07-16 | Unknown | Unknown | 913 | 653 | 1 | 1 | 914 | 654 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-10 | 328 | 235 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-04 | 2023-05-04 | 2023-09-27 | IOU Designed & Installed | N/A | No | N/A | 12423.74 | 350.69 | Unknown | Unknown | -461 | 12534.05 | 3981 | 1159.53 | 12423.74 | -11264.21 | Yes | N/A | N/A | 2023-05-04 | 2023-05-08 | 5 | 3 | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-09-27 | 97 | 69 | Unknown | 2023-09-25 | Unknown | Unknown | 2023-09-27 | 2023-10-04 | 1900-01-07 | 6 | 2023-10-04 | 2023-10-04 | 1 | 1 | 102 | 72 | 9 | 7 | 111 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | -486 | -348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | 2023-03-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1274.6 | -11.51 | Unknown | Unknown | 6.97 | 1279.14 | Unknown | 857.53 | 1274.6 | -417.07 | Yes | N/A | N/A | 2023-03-08 | 2023-03-20 | 13 | 9 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-08-09 | 1 | 1 | 13 | 9 | 1 | 1 | 14 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-03 | 742 | 531 | No | 2023-01-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-26 | 2023-01-26 | 2024-08-02 | IOU Designed & Installed | N/A | Yes | 84 | 1643.99 | 243.98 | Unknown | 21.68 | 50.82 | 1327.51 | 3981 | 1113.62 | 1643.99 | -530.37 | Yes | N/A | N/A | 2023-01-26 | 2023-04-20 | 85 | 61 | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | 2024-08-02 | 471 | 337 | Unknown | 2024-07-17 | Unknown | Unknown | 2024-08-02 | 2024-11-14 | 1900-04-14 | 75 | 2024-11-14 | 2024-11-14 | 1 | 1 | 556 | 398 | 106 | 76 | 662 | 474 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | N/A | San Diego | CALTRANS-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-09 | 670 | 479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-04 | 2022-02-04 | 2024-08-12 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 130988.95 | 64114.62 | Unknown | 260.71 | -78595.37 | 145208.99 | Unknown | 75237.04 | 130988.95 | -55751.91 | Yes | N/A | N/A | 2022-02-04 | 2023-10-16 | 620 | 442 | 2023-10-16 | 2024-02-22 | 130 | 94 | 2023-11-07 | 2024-03-25 | 13 | 9 | 2024-02-23 | 2024-07-24 | -776 | -574 | 2024-04-03 | Unknown | Unknown | Unknown | 2024-04-03 | 2024-05-16 | 44 | 32 | 2024-08-12 | 2024-09-09 | 1900-01-28 | 21 | 2024-09-09 | 2024-09-09 | 1 | 1 | 633 | 451 | -572 | -426 | 61 | 25 | Steps 2,3,5,6,7 | 250 | 178 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -208 | -149 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-09 | 2024-02-09 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | 3446.25 | 11034.82 | Unknown | Unknown | -22843 | 15254.43 | Unknown | 22843.41 | 3446.25 | 19397.16 | Yes | N/A | N/A | 2024-02-09 | 2024-02-09 | 1 | 1 | 2024-02-09 | 2024-04-11 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-03-29 | 10 | 8 | 2024-05-24 | Unknown | Unknown | Unknown | 2024-05-24 | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-06 | 1900-01-07 | 6 | 2024-06-06 | 2024-06-06 | 1 | 1 | 1 | 1 | 82 | 60 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 6606 | 6606 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-04-24 | -210 | -151 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-27 | 2023-08-23 | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 33587.94 | 8604.14 | Unknown | Unknown | 70.12 | 24913.68 | 49733 | 20065.34 | 33587.94 | -13522.6 | Yes | N/A | N/A | 2021-04-27 | 2023-07-05 | 800 | 572 | 2023-07-05 | 2024-07-16 | 378 | 270 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-06-19 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-07-16 | 2 | 2 | 2024-09-09 | 2024-09-26 | 1900-01-17 | 14 | 2024-09-26 | 2024-09-26 | 1 | 1 | 800 | 572 | 436 | 314 | 1236 | 886 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-11 | -572 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-06-01 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | 5.82 | -5.16 | Unknown | Unknown | Unknown | 10.98 | 3981 | 1570.72 | 5.82 | 1564.9 | Yes | N/A | N/A | 2024-05-07 | 2024-06-01 | 26 | 19 | 2024-06-01 | 2024-06-01 | 1 | 0 | 2024-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-01 | 2024-06-17 | 17 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-06-19 | 1900-01-02 | 3 | 2024-06-19 | 2024-06-18 | Unknown | Unknown | 43 | 30 | 4 | 3 | 47 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-26 | -420 | -301 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-03-09 | 2023-07-31 | IOU Designed & Installed | N/A | No | N/A | 775.7 | 250.54 | Unknown | Unknown | Unknown | 525.16 | 3981 | 1333.86 | 775.7 | 558.16 | Yes | N/A | N/A | 2023-02-03 | 2023-03-09 | 35 | 25 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | 2023-07-31 | 145 | 103 | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2023-08-03 | 1900-01-03 | 4 | 2023-08-03 | 2023-08-03 | 1 | 1 | 180 | 128 | 5 | 5 | 185 | 133 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | -693 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-28 | 2025-02-28 | 2025-02-28 | IOU Designed & Installed | N/A | No | N/A | 139.81 | -2.82 | Unknown | Unknown | Unknown | 142.63 | 3981 | 1742.92 | 139.81 | 1603.11 | Yes | N/A | N/A | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-02-28 | 2025-02-28 | 1 | 1 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-02-28 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-03-21 | 1900-01-21 | 16 | 2025-03-21 | 2025-03-21 | 1 | 1 | 2 | 2 | 24 | 18 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-31 | 766 | 547 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 748.83 | -14.98 | Unknown | Unknown | Unknown | 763.81 | Unknown | 104.74 | 748.83 | -644.09 | Yes | N/A | N/A | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | 2024-11-08 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | Unknown | Unknown | 2025-02-04 | 2025-02-04 | 1 | 1 | 1 | 1 | 12 | 10 | 13 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-05 | -363 | -260 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-06 | 2025-02-06 | IOU Designed & Installed | N/A | No | N/A | 1196.4 | 305.5 | Unknown | Unknown | Unknown | 890.9 | 3981 | 1422.53 | 1196.4 | 226.13 | Yes | N/A | N/A | 2025-02-06 | 2025-02-06 | 1 | 1 | 2025-02-06 | 2025-02-06 | 1 | 1 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-07 | 1900-01-01 | 2 | 2025-02-07 | 2025-02-07 | 1 | 1 | 2 | 2 | 4 | 4 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 111.05 | 111.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -413 | -296 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | 2024-10-03 | IOU Designed & Installed | N/A | No | N/A | 1244.34 | Unknown | Unknown | Unknown | 18.34 | 1226 | 3981 | 828.89 | 1244.34 | -415.45 | Yes | N/A | N/A | 2024-07-03 | 2024-05-30 | Unknown | Unknown | 2024-05-30 | 2024-07-18 | 50 | 36 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-10-03 | 78 | 56 | Unknown | 2024-09-23 | Unknown | Unknown | 2024-10-03 | 2024-10-15 | 1900-01-12 | 9 | 2024-10-15 | 2024-10-14 | Unknown | Unknown | 78 | 56 | 63 | 45 | 141 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-29 | 744 | 533 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-04-17 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 12380.7 | Unknown | Unknown | Unknown | Unknown | 12380.7 | 18948 | 3704.94 | 12380.7 | -8675.76 | Yes | N/A | N/A | 2023-03-24 | 2023-03-23 | Unknown | Unknown | 2023-03-23 | 2023-12-11 | 264 | 188 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2024-12-31 | 387 | 277 | Unknown | 2024-12-26 | Unknown | Unknown | 2025-01-30 | 2025-03-28 | 1900-02-26 | 42 | 2025-03-28 | 2025-04-11 | 15 | 11 | 387 | 277 | 337 | 241 | 724 | 518 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 88.05 | 88.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-20 | 63 | 46 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-06 | 2025-01-07 | IOU Designed & Installed | N/A | No | N/A | 31.2 | Unknown | Unknown | Unknown | Unknown | 31.2 | 2841 | 936.41 | 31.2 | 905.21 | Yes | N/A | N/A | 2024-11-05 | 2024-11-05 | 1 | 1 | 2024-11-05 | 2024-11-05 | 1 | 1 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2025-01-07 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-01-21 | 1900-01-14 | 11 | 2025-01-21 | 2025-01-22 | 2 | 2 | 64 | 46 | 18 | 14 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-27 | 308 | 221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-04-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | -876.79 | 1081.8 | Unknown | Unknown | -3207 | 1248.41 | 0 | 2596.76 | -876.79 | 3473.55 | Yes | N/A | N/A | 2023-04-26 | 2023-05-02 | 7 | 5 | 2023-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-07-29 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | 2024-09-30 | 2024-09-30 | 1 | 1 | 7 | 5 | 12 | 8 | 19 | 13 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-22 | -550 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-25 | 2025-01-25 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | 1905 | 338.38 | Unknown | Unknown | Unknown | 1566.62 | 3981 | 1547.8 | 1905 | -357.2 | Yes | N/A | N/A | 2025-01-25 | 2025-01-24 | Unknown | Unknown | 2025-01-24 | 2025-01-25 | 2 | 1 | 2025-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-25 | 2025-05-16 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-05-21 | 1900-01-05 | 4 | 2025-05-21 | 2025-05-21 | 1 | 1 | 112 | 80 | 9 | 6 | 121 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-08 | -126 | -91 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | 2023-12-13 | IOU Designed & Installed | N/A | No | N/A | 10.33 | -13.02 | Unknown | Unknown | Unknown | 23.35 | 3981 | 983.07 | 10.33 | 972.74 | Yes | N/A | N/A | 2023-11-21 | 2023-05-15 | Unknown | Unknown | 2023-05-15 | 2023-11-21 | 191 | 137 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2023-12-13 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-01-03 | 1900-01-21 | 16 | 2024-01-03 | 2024-01-03 | 1 | 1 | 23 | 17 | 214 | 154 | 237 | 171 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 2059 | 2059 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-06-01 | 748 | 535 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 8825.6 | 3953.45 | Unknown | Unknown | Unknown | 4872.15 | 3981 | 683.65 | 8825.6 | -8141.95 | Yes | N/A | N/A | 2023-04-03 | 2023-03-15 | Unknown | Unknown | 2023-03-15 | 2023-08-08 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | 2025-04-04 | 606 | 434 | Unknown | 2025-05-22 | Unknown | Unknown | Unknown | 2025-06-19 | Unknown | Unknown | 2025-06-19 | 2025-06-18 | Unknown | Unknown | 606 | 434 | 147 | 105 | 753 | 539 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | 326 | 233 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-03 | 2023-04-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6929.74 | -314.76 | Unknown | Unknown | 34.85 | 7209.65 | 350714 | 16389.82 | 6929.74 | 9460.08 | Yes | N/A | N/A | 2022-08-03 | 2023-07-07 | 339 | 243 | 2023-07-07 | 2023-10-05 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | Unknown | Unknown | Unknown | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2024-07-23 | 1 | 1 | 339 | 243 | 92 | 66 | 431 | 309 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-18 | -488 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-06 | 2025-01-06 | 2025-05-28 | IOU Designed & Installed | N/A | No | N/A | 0 | Unknown | Unknown | Unknown | -344.19 | 344.19 | Unknown | 1101.99 | Unknown | 1101.99 | Yes | N/A | N/A | 2025-01-06 | 2025-01-16 | 11 | 9 | 2025-01-16 | 2025-01-31 | 16 | 12 | 2025-01-31 | 2025-05-28 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | 2025-05-28 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-06-17 | 1900-01-20 | 15 | 2025-06-17 | 2025-06-17 | 1 | 1 | 131 | 95 | 38 | 28 | 169 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-23 | -545 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-04-15 | 2024-04-16 | IOU Designed & Installed | N/A | No | N/A | 29.16 | -2.73 | Unknown | Unknown | Unknown | 31.89 | Unknown | 1095.35 | 29.16 | 1066.19 | Yes | N/A | N/A | 2024-03-19 | 2024-03-01 | Unknown | Unknown | 2024-03-01 | 2024-04-15 | 46 | 32 | 2024-04-15 | 2024-08-08 | 116 | 84 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-04-16 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-08-27 | 1900-05-13 | 96 | 2024-08-27 | 2024-08-27 | 1 | 1 | 118 | 86 | 181 | 129 | 299 | 215 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Residential | N/A | Poway | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | 321 | 230 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-13 | 2024-08-20 | IOU Designed & Installed | N/A | No | N/A | 12145.2 | 1516.5 | Unknown | Unknown | -13386.46 | 24015.16 | Unknown | 19574.88 | 12145.2 | 7429.68 | Yes | N/A | N/A | 2023-12-13 | 2023-12-12 | Unknown | Unknown | 2023-12-12 | 2024-01-31 | 51 | 37 | 2024-01-30 | 2024-07-02 | 155 | 111 | 2024-08-02 | 2024-08-06 | 5 | 3 | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | 2024-08-20 | 2024-09-17 | 1900-01-28 | 21 | 2024-09-17 | 2024-09-17 | 1 | 1 | 155 | 111 | 86 | 62 | 241 | 173 | Steps 2,3,5,6,7 | 189 | 135 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-07 | -542 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-08-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1136.55 | -35.43 | Unknown | Unknown | Unknown | 1171.98 | Unknown | 982.97 | 1136.55 | -153.58 | Yes | N/A | N/A | 2023-08-21 | 2023-04-14 | Unknown | Unknown | 2023-04-14 | 2023-08-25 | 134 | 96 | 2023-08-25 | Unknown | Unknown | Unknown | 2023-08-25 | 2023-09-11 | 18 | 12 | 2023-08-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | Unknown | Unknown | 2023-10-13 | 2023-10-13 | 1 | 1 | 0 | 0 | 153 | 109 | 153 | 109 | Steps 2,3,5,6,7 | 17 | 11 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-03 | 666 | 477 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-04 | 2022-10-05 | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 18576.51 | 502.05 | Unknown | 32.21 | -8847.55 | 26889.8 | Unknown | 8042.34 | 18576.51 | -10534.17 | Yes | N/A | N/A | 2022-10-04 | 2023-12-15 | 438 | 314 | 2023-12-15 | 2024-02-21 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | Unknown | Unknown | 2024-08-14 | 2024-09-04 | 1900-01-21 | 16 | 2024-09-04 | 2024-08-30 | Unknown | Unknown | 438 | 314 | 91 | 65 | 529 | 379 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-15 | 107 | 76 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2025-02-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1035.26 | -20.79 | Unknown | Unknown | Unknown | 1056.05 | 3981 | 1663.86 | 1035.26 | 628.6 | Yes | N/A | N/A | 2024-07-23 | 2025-01-22 | 184 | 132 | 2025-01-22 | 2025-03-27 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-05-29 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | 2025-05-01 | 2025-06-02 | 33 | 23 | 248 | 178 | 98 | 70 | 346 | 248 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | -633 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-02-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -8.22 | -5.95 | Unknown | Unknown | Unknown | -2.27 | Unknown | 341 | -8.22 | 349.22 | Yes | N/A | N/A | 2023-01-31 | 2023-02-03 | 4 | 4 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | Unknown | Unknown | 2023-05-04 | 2023-05-04 | 1 | 1 | 4 | 4 | 1 | 1 | 5 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN YSIDRO | SAN DIEGO | 2034 | 2034 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-09-01 | -642 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-06-05 | 2023-11-03 | IOU Designed & Installed | N/A | No | N/A | 3342.96 | 247.28 | Unknown | Unknown | 2.4 | 3093.28 | Unknown | 6499.72 | 3342.96 | 3156.76 | Yes | N/A | N/A | 2023-02-21 | 2023-05-18 | 87 | 63 | 2023-05-18 | 2023-09-28 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2023-10-02 | 16 | 12 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | 2023-11-29 | 1900-01-26 | 19 | 2023-11-29 | 2023-11-29 | 1 | 1 | 87 | 63 | 178 | 128 | 265 | 191 | Steps 2,3,5,6,7 | 4 | 2 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | -477 | -342 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-12 | 2023-09-12 | 2024-01-05 | IOU Designed & Installed | N/A | No | N/A | 1487.62 | -10.03 | Unknown | Unknown | Unknown | 1497.65 | 7962 | 1091.88 | 1487.62 | -395.74 | Yes | N/A | N/A | 2023-09-12 | 2023-09-12 | 1 | 1 | 2023-09-12 | 2023-11-07 | 57 | 41 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2024-01-05 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-01-10 | 1900-01-05 | 4 | 2024-01-10 | 2024-01-10 | 1 | 1 | 61 | 45 | 64 | 46 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-01 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-17 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 3.86 | Unknown | Unknown | Unknown | Unknown | 3.86 | 3981 | 1553.37 | 3.86 | 1549.51 | Yes | N/A | N/A | 2024-06-13 | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-06-14 | 3 | 3 | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-07-30 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-20 | 1900-01-21 | 16 | 2024-08-20 | 2024-08-20 | 1 | 1 | 44 | 32 | 26 | 20 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-20 | -637 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 42.72 | Unknown | Unknown | Unknown | Unknown | 42.72 | 3981 | 1577.12 | 42.72 | 1534.4 | Yes | N/A | N/A | 2024-07-18 | 2024-05-28 | Unknown | Unknown | 2024-05-28 | 2024-07-18 | 52 | 38 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-07-29 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-26 | 1900-01-28 | 21 | 2024-08-26 | 2024-08-21 | Unknown | Unknown | 12 | 8 | 81 | 59 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 75.1 | 75.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | -628 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-07-24 | 2023-08-16 | IOU Designed & Installed | N/A | No | N/A | 1139.88 | -32.74 | Unknown | Unknown | Unknown | 1172.62 | 3981 | 1081.1 | 1139.88 | -58.78 | Yes | N/A | N/A | 2023-07-13 | 2023-07-24 | 12 | 8 | 2023-07-24 | 2023-07-24 | 1 | 1 | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2023-08-16 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2023-09-11 | 1900-01-26 | 19 | 2023-09-11 | 2023-09-11 | 1 | 1 | 36 | 26 | 29 | 21 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-03 | -455 | -326 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | -1.45 | Unknown | Unknown | Unknown | Unknown | -1.45 | Unknown | 497.98 | -1.45 | 499.43 | Yes | N/A | N/A | 2023-10-09 | 2023-10-09 | 1 | 1 | 2023-10-09 | 2023-10-09 | 1 | 1 | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2023-10-11 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2024-01-04 | 1900-03-26 | 62 | 2024-01-04 | 2024-01-04 | 1 | 1 | 4 | 4 | 88 | 64 | 92 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | -633 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-27 | 2023-03-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.81 | -11.12 | Unknown | Unknown | Unknown | 7.31 | Unknown | 997.7 | -3.81 | 1001.51 | Yes | N/A | N/A | 2023-03-27 | 2023-03-31 | 5 | 5 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 5 | 5 | 1 | 1 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-03 | -484 | -346 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-01 | 2025-05-27 | IOU Designed & Installed | N/A | No | N/A | 1438.94 | Unknown | Unknown | Unknown | 20.87 | 1418.07 | 3981 | 3324.26 | 1438.94 | 1885.32 | Yes | N/A | N/A | 2024-11-01 | 2024-12-19 | 49 | 35 | 2024-12-19 | 2025-01-02 | 15 | 11 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-05-27 | 146 | 104 | Unknown | 2025-05-22 | Unknown | Unknown | 2025-05-27 | 2025-06-06 | 1900-01-10 | 9 | 2025-06-06 | 2025-06-06 | 1 | 1 | 195 | 139 | 27 | 21 | 222 | 160 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-14 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-23 | 2023-06-23 | 2023-08-03 | IOU Designed & Installed | N/A | No | N/A | 699.36 | 252.1 | Unknown | Unknown | Unknown | 447.26 | 3981 | 1013.81 | 699.36 | 314.45 | Yes | N/A | N/A | 2023-06-23 | 2023-06-23 | 1 | 1 | 2023-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-08-03 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-08-03 | 2023-08-04 | 1900-01-01 | 2 | 2023-08-04 | 2023-08-04 | 1 | 1 | 43 | 31 | 3 | 3 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | -553 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-05-07 | 2024-08-08 | IOU Designed & Installed | N/A | No | N/A | 2823.68 | 322.56 | Unknown | Unknown | 13.17 | 2487.95 | Unknown | 1028.66 | 2823.68 | -1795.02 | Yes | N/A | N/A | 2024-05-07 | 2024-06-05 | 30 | 22 | 2024-06-05 | 2024-06-05 | 1 | 1 | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-08-08 | 65 | 47 | Unknown | 2024-08-07 | Unknown | Unknown | 2024-08-08 | 2024-08-22 | 1900-01-14 | 11 | 2024-08-22 | 2024-08-22 | 1 | 1 | 95 | 69 | 17 | 13 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Residential | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-26 | -267 | -192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-10 | 2025-02-03 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 174244.78 | 34071.79 | Unknown | Unknown | 672.23 | 139500.76 | 1612132 | 141735.05 | 174244.78 | -32509.73 | Yes | N/A | N/A | 2023-04-10 | 2024-03-19 | 345 | 247 | 2024-03-19 | 2024-06-27 | 101 | 73 | 2024-04-02 | 2024-06-25 | 38 | 28 | 2024-06-29 | 2024-07-19 | 21 | 15 | 2024-06-27 | Unknown | Unknown | Unknown | 2024-07-09 | 2025-01-23 | 199 | 143 | 2025-02-03 | 2025-03-04 | 1900-01-29 | 22 | 2025-03-04 | 2025-03-04 | 1 | 1 | 383 | 275 | 352 | 254 | 735 | 529 | Steps 2,3,5,6,7 | 108 | 78 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-16 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | 3.92 | Unknown | Unknown | Unknown | Unknown | 3.92 | 3981 | 1624.01 | 3.92 | 1620.09 | Yes | N/A | N/A | 2024-12-16 | 2024-10-27 | Unknown | Unknown | 2024-10-27 | 2024-12-17 | 52 | 37 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2025-01-15 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-02-06 | 1900-01-22 | 17 | 2025-02-06 | 2025-02-06 | 1 | 1 | 31 | 23 | 76 | 55 | 107 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 42732 | 42732 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-12-20 | -564 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-24 | 2025-04-17 | IOU Designed & Installed | N/A | No | N/A | -2257.35 | -1.5 | Unknown | Unknown | -2332 | 76.15 | Unknown | 2189.37 | -2257.35 | 4446.72 | Yes | N/A | N/A | 2025-02-11 | 2025-01-29 | Unknown | Unknown | 2025-01-29 | 2025-02-24 | 27 | 19 | 2025-02-24 | 2025-03-14 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-04-17 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-04-23 | 1900-01-06 | 5 | 2025-04-23 | 2025-06-04 | 43 | 31 | 26 | 20 | 77 | 55 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Residential | Underserved Community | Vista | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | 4 | 4 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-12 | 2023-01-12 | 2025-05-28 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 93152.98 | 21445.84 | Unknown | 1379.75 | 1051.68 | 69275.71 | 992636 | 60046.13 | 93152.98 | -33106.85 | Yes | N/A | N/A | 2023-01-12 | 2024-04-17 | 462 | 330 | 2024-04-17 | 2024-08-09 | 115 | 83 | 2024-03-20 | 2024-08-07 | 41 | 31 | 2024-03-21 | 2025-07-21 | 292 | 210 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-28 | 2025-06-05 | 1900-01-08 | 7 | 2025-06-05 | 2025-06-05 | 1 | 1 | 503 | 361 | 417 | 301 | 920 | 662 | Steps 2,3,5,6,7 | 281 | 201 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 87 | 87 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-03 | 441 | 316 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1180.44 | -8.88 | Unknown | Unknown | 5.36 | 1183.96 | 73670 | 2760.57 | 1180.44 | 1580.13 | Yes | N/A | N/A | 2023-02-02 | 2023-03-15 | 42 | 30 | 2023-03-15 | 2023-03-16 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-16 | 2024-08-26 | 530 | 378 | Unknown | 2024-08-28 | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-09-16 | Unknown | Unknown | 572 | 408 | 2 | 2 | 574 | 410 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 629.05 | 629.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-27 | -168 | -121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | 2024-08-05 | IOU Designed & Installed | N/A | No | N/A | 974.36 | 391.99 | Unknown | Unknown | 30.6 | 551.77 | 3885 | 1164.7 | 974.36 | 190.34 | Yes | N/A | N/A | 2023-05-19 | 2023-05-19 | 1 | 1 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2024-08-05 | 445 | 317 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-08-12 | 1900-01-07 | 6 | 2024-08-12 | 2024-08-12 | 1 | 1 | 446 | 318 | 9 | 7 | 455 | 325 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 629 | 450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2024-10-30 | IOU Designed & Installed | N/A | No | N/A | 246436.24 | 31372.59 | Unknown | 174.13 | 708.42 | 214181.1 | 1755108.4 | 75289.11 | 246436.24 | -171147.13 | Yes | N/A | N/A | 2023-03-28 | 2024-01-04 | 283 | 203 | 2024-01-04 | 2024-09-04 | 245 | 175 | 2024-01-04 | 2023-11-09 | Unknown | Unknown | 2023-11-29 | 2024-09-10 | 18 | 14 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2025-02-19 | 1900-04-22 | 81 | 2025-02-19 | 2025-02-19 | 1 | 1 | 283 | 203 | 377 | 271 | 660 | 474 | Steps 2,3,5,6,7 | 250 | 178 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-28 | 295 | 212 | No | 2021-09-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-17 | 2021-10-04 | 2023-04-18 | IOU Designed & Installed | N/A | Yes | 558 | 2438.21 | 667.62 | Unknown | 88.1 | Unknown | 1682.49 | 3885 | 1537.83 | 2438.21 | -900.38 | Yes | N/A | N/A | 2021-09-17 | 2023-03-29 | 559 | 399 | 2023-03-29 | Unknown | Unknown | Unknown | 2021-10-04 | 2022-02-07 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2021-10-05 | 2023-04-18 | Unknown | Unknown | Unknown | 2023-04-04 | Unknown | Unknown | 2023-04-18 | 2023-04-19 | 1900-01-01 | 2 | 2023-04-19 | 2023-04-19 | 1 | 1 | 686 | 490 | 3 | 3 | 689 | 493 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-08 | -514 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-15 | 2023-10-15 | 2023-11-10 | IOU Designed & Installed | N/A | No | N/A | 3.95 | -4.95 | Unknown | Unknown | Unknown | 8.9 | Unknown | 909.98 | 3.95 | 906.03 | Yes | N/A | N/A | 2023-10-15 | 2023-10-15 | 1 | 0 | 2023-10-15 | 2023-10-15 | 1 | 0 | 2023-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-15 | 2023-11-10 | 27 | 20 | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2024-01-11 | 1900-03-03 | 45 | 2024-01-11 | 2024-01-11 | 1 | 1 | 28 | 20 | 65 | 46 | 93 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | -310 | -223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-07-05 | 2025-01-31 | IOU Designed & Installed | N/A | No | N/A | 20859.11 | -51.47 | Unknown | Unknown | Unknown | 20910.58 | 3981 | 3686.93 | 20859.11 | -17172.18 | Yes | N/A | N/A | 2024-03-12 | 2024-07-05 | 116 | 84 | 2024-07-05 | 2024-07-05 | 1 | 1 | 2024-07-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | 2025-01-31 | 211 | 151 | Unknown | 2025-01-30 | Unknown | Unknown | 2025-01-31 | 2025-03-13 | 1900-02-10 | 30 | 2025-03-13 | 2025-03-05 | Unknown | Unknown | 327 | 235 | 43 | 31 | 370 | 266 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-06 | -269 | -192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-09-03 | 2024-12-13 | IOU Designed & Installed | N/A | No | N/A | 28.09 | Unknown | Unknown | Unknown | Unknown | 28.09 | 3981 | 1638.41 | 28.09 | 1610.32 | Yes | N/A | N/A | 2024-01-24 | 2024-05-10 | 108 | 78 | 2024-05-10 | 2024-09-03 | 117 | 83 | 2024-09-03 | Unknown | Unknown | Unknown | 2024-09-03 | 2024-10-02 | 30 | 22 | 2024-11-15 | 2024-12-13 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-01-10 | 1900-01-28 | 21 | 2025-01-10 | 2025-01-10 | 1 | 1 | 137 | 99 | 177 | 127 | 314 | 226 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 3261.05 | 3261.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-01-31 | 308 | 221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-20 | 2023-07-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1071.95 | Unknown | Unknown | Unknown | -1101 | 29.05 | 3981 | 1955.7 | -1071.95 | 3027.65 | Yes | N/A | N/A | 2023-07-20 | 2023-07-20 | 1 | 1 | 2023-07-20 | 2023-07-20 | 1 | 1 | 2023-07-20 | 2023-07-27 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | Unknown | 2024-12-05 | Unknown | Unknown | 2024-12-05 | 2024-12-04 | Unknown | Unknown | 9 | 7 | 1 | 1 | 10 | 8 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | -145 | -105 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-03-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1578.6 | 2184.84 | Unknown | 365.83 | -5038 | 908.73 | Unknown | 5038.44 | -1578.6 | 6617.04 | Yes | N/A | N/A | 2023-03-17 | 2023-03-21 | 5 | 3 | 2023-03-21 | 2023-04-10 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2023-10-02 | Unknown | Unknown | 5 | 3 | 21 | 15 | 26 | 18 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | -450 | -323 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | 2024-02-27 | 2024-07-03 | IOU Designed & Installed | N/A | No | N/A | 259.5 | -4.39 | Unknown | Unknown | Unknown | 263.89 | Unknown | 879.8 | 259.5 | 620.3 | Yes | N/A | N/A | 2024-02-27 | 2023-11-21 | Unknown | Unknown | 2023-11-21 | 2024-02-27 | 99 | 71 | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-07-03 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-08-13 | 1900-02-10 | 30 | 2024-08-13 | 2024-08-13 | 1 | 1 | 128 | 92 | 142 | 102 | 270 | 194 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 84 | 84 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | -686 | -491 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-02 | 2024-08-09 | IOU Designed & Installed | N/A | No | N/A | 1733.36 | 483.36 | Unknown | 52.69 | Unknown | 1197.31 | 3981 | 1090.55 | 1733.36 | -642.81 | Yes | N/A | N/A | 2024-08-01 | 2024-08-02 | 2 | 2 | 2024-08-02 | 2024-08-02 | 1 | 1 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-08-09 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-08-21 | 1900-01-12 | 9 | 2024-08-21 | 2024-08-21 | 1 | 1 | 10 | 8 | 15 | 11 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-11-01 | 1066 | 763 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 740.39 | Unknown | Unknown | Unknown | -516 | 1256.39 | Unknown | 471.38 | 740.39 | -269.01 | Yes | N/A | N/A | 2024-09-05 | 2024-09-05 | 1 | 1 | 2024-09-05 | 2024-09-09 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2024-10-01 | 23 | 17 | Unknown | 2024-09-23 | Unknown | Unknown | 2024-10-01 | 2024-10-03 | 1900-01-02 | 3 | 2024-10-03 | 2024-10-02 | Unknown | Unknown | 24 | 18 | 8 | 6 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 35.05 | 35.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-06 | -506 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | 2023-07-20 | IOU Designed & Installed | N/A | No | N/A | 8082.39 | 3160.12 | Unknown | Unknown | 7.3 | 4914.97 | 3981 | 719.26 | 8082.39 | -7363.13 | Yes | N/A | N/A | 2023-02-23 | 2023-03-03 | 9 | 7 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | 2023-07-20 | 140 | 100 | Unknown | 2023-07-20 | Unknown | Unknown | 2023-07-20 | 2023-07-20 | 1899-12-31 | 1 | 2023-07-20 | 2023-07-19 | Unknown | Unknown | 149 | 107 | 1 | 1 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | -135 | -97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-05-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.21 | -6.19 | Unknown | Unknown | Unknown | 2.98 | 3981 | 1519.64 | -3.21 | 1522.85 | Yes | N/A | N/A | 2023-04-26 | 2023-05-04 | 9 | 7 | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | Unknown | Unknown | 2023-10-12 | 2023-10-12 | 1 | 1 | 9 | 7 | 1 | 1 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-05 | -304 | -219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-07-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4.4 | Unknown | Unknown | Unknown | Unknown | 4.4 | Unknown | 444.8 | 4.4 | 440.4 | Yes | N/A | N/A | 2024-07-09 | 2024-06-24 | Unknown | Unknown | 2024-06-24 | 2024-07-25 | 32 | 24 | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | Unknown | Unknown | 2024-08-05 | 2024-08-05 | 1 | 1 | 0 | 0 | 33 | 25 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | -414 | -297 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-05 | 2023-07-06 | 2023-08-01 | IOU Designed & Installed | N/A | No | N/A | 8639.79 | Unknown | Unknown | Unknown | Unknown | 8639.79 | Unknown | 270.38 | 8639.79 | -8369.41 | Yes | N/A | N/A | 2023-07-05 | 2023-07-06 | 2 | 2 | 2023-07-06 | 2023-07-28 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-07-17 | 12 | 8 | 2023-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-08-23 | 1900-01-22 | 17 | 2023-08-23 | 2023-08-23 | 1 | 1 | 2 | 2 | 59 | 43 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-20 | 331 | 238 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-07-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2.02 | -8.57 | Unknown | Unknown | Unknown | 6.55 | 3981 | 1316.43 | -2.02 | 1318.45 | Yes | N/A | N/A | 2024-07-09 | 2024-06-04 | Unknown | Unknown | 2024-06-04 | 2024-07-22 | 49 | 35 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | Unknown | Unknown | 2025-04-18 | 2025-04-16 | Unknown | Unknown | 0 | 0 | 49 | 35 | 49 | 35 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | -563 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-06 | 2024-05-22 | IOU Designed & Installed | N/A | No | N/A | 699.33 | 246.68 | Unknown | Unknown | 2.05 | 450.6 | 3981 | 156.93 | 699.33 | -542.4 | Yes | N/A | N/A | 2024-05-06 | 2024-05-20 | 15 | 11 | 2024-05-20 | 2024-05-20 | 1 | 1 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-05-22 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-07-02 | 1900-02-10 | 30 | 2024-07-02 | 2024-07-02 | 1 | 1 | 18 | 14 | 44 | 32 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-21 | -322 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | 2023-12-27 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -1083.21 | 753.75 | Unknown | Unknown | -2370 | 533.04 | Unknown | 2369.96 | -1083.21 | 3453.17 | Yes | N/A | N/A | 2023-12-12 | 2023-12-12 | 1 | 1 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2024-01-04 | 1900-01-08 | 7 | 2024-01-04 | 2024-01-04 | 1 | 1 | 1 | 1 | 10 | 8 | 11 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-29 | 132 | 95 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 909.99 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-23 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-04-23 | 71 | 51 | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2025-06-09 | 413 | 295 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-09 | 1899-12-31 | 1 | 2025-06-09 | 2025-06-10 | 2 | 2 | 413 | 295 | 74 | 54 | 487 | 349 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-13 | -545 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-26 | 2023-09-12 | IOU Designed & Installed | N/A | No | N/A | -1.21 | -2.38 | Unknown | Unknown | Unknown | 1.17 | Unknown | 264.34 | -1.21 | 265.55 | Yes | N/A | N/A | 2023-06-21 | 2023-06-21 | 1 | 1 | 2023-06-21 | 2023-06-26 | 6 | 4 | 2023-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | 2023-09-12 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2023-09-12 | 2023-09-15 | 1900-01-03 | 4 | 2023-09-15 | 2023-09-15 | 1 | 1 | 80 | 58 | 11 | 9 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | -625 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | Unknown | 2025-01-06 | IOU Designed & Installed | N/A | No | N/A | 578.83 | -11.7 | Unknown | Unknown | Unknown | 590.53 | 3981 | 1550.49 | 578.83 | 971.66 | Yes | N/A | N/A | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | 2024-10-29 | 1 | 1 | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2025-01-06 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-01-27 | 1900-01-21 | 16 | 2025-01-27 | 2025-01-27 | 1 | 1 | 71 | 51 | 24 | 18 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 561.05 | 561.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-12 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-02-29 | 2024-05-09 | IOU Designed & Installed | N/A | No | N/A | 1589.39 | -32 | Unknown | Unknown | Unknown | 1621.39 | 3981 | 772.69 | 1589.39 | -816.7 | Yes | N/A | N/A | 2024-02-29 | 2024-01-26 | Unknown | Unknown | 2024-01-26 | 2024-03-01 | 36 | 26 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-05-09 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-05-17 | 1900-01-08 | 7 | 2024-05-17 | 2024-05-31 | 15 | 11 | 70 | 50 | 60 | 44 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-06 | -184 | -132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-28 | 2023-12-27 | IOU Designed & Installed | N/A | No | N/A | -5.42 | -4.09 | Unknown | Unknown | Unknown | -1.33 | Unknown | 500.87 | -5.42 | 506.29 | Yes | N/A | N/A | 2023-09-25 | 2023-09-28 | 4 | 4 | 2023-09-28 | 2023-09-28 | 1 | 1 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-12-27 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2024-01-04 | 1900-01-08 | 7 | 2024-01-04 | 2024-01-04 | 1 | 1 | 95 | 69 | 11 | 9 | 106 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | DEL MAR | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-26 | -373 | -268 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-09-16 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1680.36 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-24 | 2024-09-16 | 55 | 39 | 2024-09-16 | 2024-09-18 | 3 | 3 | 2024-09-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2025-06-18 | 276 | 198 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-06-18 | 1899-12-31 | 1 | 2025-06-18 | 2025-06-18 | 1 | 1 | 331 | 237 | 5 | 5 | 336 | 242 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | 323 | 232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-12-19 | 2024-03-19 | IOU Designed & Installed | N/A | No | N/A | 376.93 | 547.65 | Unknown | Unknown | -1156 | 985.28 | 3981 | 1689.49 | 376.93 | 1312.56 | Yes | N/A | N/A | 2023-03-31 | 2023-12-19 | 264 | 188 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-03-19 | 62 | 44 | Unknown | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-03-19 | 1899-12-31 | 1 | 2024-03-19 | 2024-03-19 | 1 | 1 | 326 | 232 | 2 | 2 | 328 | 234 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -232 | -167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 184.21 | -3.41 | Unknown | Unknown | Unknown | 187.62 | Unknown | 488.99 | 184.21 | 304.78 | Yes | N/A | N/A | 2024-04-30 | 2024-05-02 | 3 | 3 | 2024-05-02 | 2024-07-10 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-06-18 | 28 | 20 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | Unknown | Unknown | 2024-09-03 | 2024-09-03 | 1 | 1 | 3 | 3 | 99 | 71 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-25 | -183 | -132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | 2024-12-05 | IOU Designed & Installed | N/A | No | N/A | 1719.36 | Unknown | Unknown | Unknown | 97.3 | 1622.06 | 3981 | 1122.43 | 1719.36 | -596.93 | Yes | N/A | N/A | 2024-08-13 | 2024-07-26 | Unknown | Unknown | 2024-07-26 | 2024-08-23 | 29 | 21 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-12-05 | 105 | 75 | Unknown | 2024-10-04 | Unknown | Unknown | 2024-12-05 | 2025-05-08 | 1900-06-03 | 111 | 2025-05-08 | 2025-01-23 | Unknown | Unknown | 105 | 75 | 184 | 132 | 289 | 207 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-11 | -205 | -147 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-07 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | -95.37 | -10.93 | Unknown | Unknown | -729 | 644.56 | Unknown | 729.47 | -95.37 | 824.84 | Yes | N/A | N/A | 2024-02-02 | 2024-02-02 | 1 | 1 | 2024-02-02 | 2024-03-25 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-03-21 | 30 | 22 | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | Unknown | Unknown | 2024-05-30 | 2024-06-20 | 1900-01-21 | 16 | 2024-06-20 | 2024-06-20 | 1 | 1 | 1 | 1 | 106 | 76 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-19 | -501 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | 2023-08-18 | 2023-12-27 | IOU Designed & Installed | N/A | No | N/A | 1301.48 | 163.28 | Unknown | Unknown | -241 | 1379.2 | Unknown | 1130.35 | 1301.48 | -171.13 | Yes | N/A | N/A | 2023-08-18 | 2023-08-18 | 1 | 1 | 2023-08-18 | 2023-08-18 | 1 | 1 | 2023-08-18 | 2023-12-27 | 132 | 94 | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2023-12-27 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2024-01-04 | 1900-01-08 | 7 | 2024-01-04 | 2024-01-04 | 1 | 1 | 191 | 137 | 11 | 9 | 202 | 146 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | SAN DIEGO | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 490 | 351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-09 | 2022-09-09 | 2024-05-29 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 122973.84 | 32177 | Unknown | Unknown | 11603.44 | 79193.4 | 0 | 55381.77 | 122973.84 | -67592.07 | Yes | N/A | N/A | 2022-09-09 | 2023-03-14 | 187 | 133 | 2023-03-14 | 2023-09-06 | 177 | 127 | 2023-04-04 | 2024-04-08 | 234 | 166 | 2023-08-31 | 2023-09-05 | 6 | 4 | 2023-11-09 | Unknown | Unknown | Unknown | 2023-11-09 | 2024-05-23 | 197 | 141 | 2024-05-29 | 2024-07-22 | 1900-02-23 | 39 | 2024-07-22 | 2024-07-22 | 1 | 1 | 421 | 299 | 436 | 312 | 857 | 611 | Steps 2,3,5,6,7 | 376 | 268 | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Commercial | Underserved Community | ALPINE | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | -200 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | 2024-08-02 | IOU Designed & Installed | N/A | No | N/A | -2921.79 | 4099.76 | Unknown | 817.22 | -10381 | 2542.23 | Unknown | 10380.72 | -2921.79 | 13302.51 | Yes | N/A | N/A | 2024-06-06 | 2024-06-06 | 1 | 1 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-08-06 | 1900-01-04 | 3 | 2024-08-06 | 2024-08-06 | 1 | 1 | 1 | 1 | 6 | 4 | 7 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | LA JOLLA | 100 | 100 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-01 | 359 | 258 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-08 | 2021-12-08 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | 4381.62 | Unknown | Unknown | Unknown | 12.03 | 4369.59 | 7962 | 601.02 | 4381.62 | -3780.6 | Yes | N/A | N/A | 2021-12-08 | 2023-02-09 | 429 | 307 | 2023-02-09 | 2023-10-09 | 243 | 173 | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | 2023-03-30 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | Unknown | Unknown | 2023-10-10 | 2023-10-30 | 1900-01-20 | 15 | 2023-10-30 | 2023-10-26 | Unknown | Unknown | 429 | 307 | 273 | 195 | 702 | 502 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-03 | -528 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-14 | 2025-04-14 | IOU Designed & Installed | N/A | No | N/A | 221.99 | Unknown | Unknown | Unknown | -1228.8 | 1450.79 | Unknown | 1230.06 | 221.99 | 1008.07 | Yes | N/A | N/A | 2025-01-08 | 2025-01-21 | 14 | 10 | 2025-01-21 | 2025-01-24 | 4 | 4 | 2025-01-24 | 2025-02-21 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-04-14 | 47 | 33 | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-14 | 2025-04-23 | 1900-01-09 | 8 | 2025-04-23 | 2025-04-23 | 1 | 1 | 90 | 64 | 15 | 13 | 105 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-08 | 95 | 68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | 2024-04-24 | IOU Designed & Installed | N/A | No | N/A | 9723.38 | 262.67 | Unknown | Unknown | -422.03 | 9882.74 | 3981 | 1184.82 | 9723.38 | -8538.56 | Yes | N/A | N/A | 2023-05-08 | 2023-05-08 | 1 | 1 | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2024-04-24 | 280 | 200 | Unknown | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-05-13 | 1900-01-19 | 14 | 2024-05-13 | 2024-05-13 | 1 | 1 | 281 | 201 | 21 | 15 | 302 | 216 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | -693 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-20 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | 29.91 | Unknown | Unknown | Unknown | Unknown | 29.91 | 3981 | 1372.72 | 29.91 | 1342.81 | Yes | N/A | N/A | 2024-09-20 | 2024-09-18 | Unknown | Unknown | 2024-09-18 | 2024-09-20 | 3 | 3 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-11 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-10-18 | 1900-01-07 | 6 | 2024-10-18 | 2024-10-18 | 1 | 1 | 22 | 16 | 12 | 10 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-09 | -476 | -341 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2025-03-20 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | -1523.12 | -12.92 | Unknown | Unknown | -2166 | 655.8 | Unknown | 2028.31 | -1523.12 | 3551.43 | Yes | N/A | N/A | 2024-10-07 | 2025-03-20 | 165 | 119 | 2025-03-20 | 2025-03-20 | 1 | 1 | 2025-03-20 | 2025-05-01 | 43 | 31 | 2025-03-27 | 2025-04-09 | 14 | 10 | 2025-05-06 | 2025-05-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-21 | 1900-01-15 | 12 | 2025-05-21 | 2025-05-21 | 1 | 1 | 209 | 151 | 32 | 24 | 241 | 175 | Steps 2,3,5,6,7 | 35 | 25 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-15 | -295 | -212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | 2023-07-18 | 2023-07-24 | IOU Designed & Installed | N/A | No | N/A | -483.33 | 438.33 | Unknown | 216.75 | -1419 | 280.59 | Unknown | 1419 | -483.33 | 1902.33 | Yes | N/A | N/A | 2023-06-28 | 2023-07-18 | 21 | 15 | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2023-07-25 | 1900-01-01 | 2 | 2023-07-25 | 2023-07-25 | 1 | 1 | 21 | 15 | 3 | 3 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 630.05 | 630.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-01 | -621 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-10-08 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 1912.52 | -38.1 | Unknown | Unknown | Unknown | 1950.62 | 3981 | 1571.48 | 1912.52 | -341.04 | Yes | N/A | N/A | 2024-09-10 | 2024-09-30 | 21 | 15 | 2024-09-30 | 2024-10-08 | 9 | 7 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-31 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-18 | 1900-01-18 | 13 | 2024-11-18 | 2024-11-18 | 1 | 1 | 45 | 33 | 29 | 21 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 144.05 | 144.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-31 | 44 | 33 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-28 | 2023-04-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4334.82 | -8 | Unknown | Unknown | Unknown | 4342.82 | 3981 | 467.52 | 4334.82 | -3867.3 | Yes | N/A | N/A | 2022-06-28 | 2023-04-28 | 305 | 219 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | 2023-06-27 | Unknown | Unknown | Unknown | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2023-07-14 | 1 | 1 | 305 | 219 | 1 | 1 | 306 | 220 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-12 | -300 | -215 | No | 2024-12-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | 2025-04-30 | IOU Designed & Installed | N/A | Yes | 22 | -364.12 | 350.24 | Unknown | Unknown | -1677 | 962.64 | Unknown | Not available | -364.12 | Unknown | Yes | N/A | N/A | 2024-09-25 | 2024-10-16 | 22 | 16 | 2024-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-04-30 | 125 | 89 | Unknown | 2025-04-25 | Unknown | Unknown | 2025-04-30 | 2025-05-16 | 1900-01-16 | 13 | 2025-05-16 | 2025-05-16 | 1 | 1 | 147 | 105 | 18 | 14 | 165 | 119 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | -801 | -574 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | -5.24 | -4.25 | Unknown | Unknown | Unknown | -0.99 | 27365 | 344.88 | -5.24 | 350.12 | Yes | N/A | N/A | 2024-02-08 | 2023-08-16 | Unknown | Unknown | 2023-08-16 | 2024-02-08 | 177 | 127 | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-05-14 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-05-28 | 1900-01-14 | 11 | 2024-05-28 | 2024-05-28 | 1 | 1 | 97 | 69 | 193 | 139 | 290 | 208 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-05 | -671 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | 2024-11-06 | IOU Designed & Installed | N/A | No | N/A | 10.22 | Unknown | Unknown | Unknown | Unknown | 10.22 | 3981 | 197.01 | 10.22 | 186.79 | Yes | N/A | N/A | 2024-10-29 | 2024-10-22 | Unknown | Unknown | 2024-10-22 | 2024-10-31 | 10 | 8 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-06 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-12-03 | 1900-01-27 | 20 | 2024-12-03 | 2024-12-03 | 1 | 1 | 7 | 5 | 39 | 29 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-11 | -866 | -619 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-06-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.57 | -10.54 | Unknown | Unknown | Unknown | 6.97 | 3981 | 814.37 | -3.57 | 817.94 | Yes | N/A | N/A | 2023-06-02 | 2023-06-06 | 5 | 3 | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | Unknown | Unknown | 2023-06-29 | 2023-06-29 | 1 | 1 | 5 | 3 | 1 | 1 | 6 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 2370 | 2370 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-01-12 | 313 | 224 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | -408.12 | -9.19 | Unknown | Unknown | -637 | 238.07 | Unknown | 544.87 | -408.12 | 952.99 | Yes | N/A | N/A | 2023-06-07 | 2023-06-08 | 2 | 2 | 2023-06-08 | 2023-11-01 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2023-08-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2023-11-21 | Unknown | Unknown | 2 | 2 | 147 | 105 | 149 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-30 | -239 | -172 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-21 | 2025-05-29 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1077.51 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-02-06 | Unknown | Unknown | 2025-02-06 | 2025-02-21 | 16 | 12 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-05-29 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-05 | 1900-01-07 | 6 | 2025-06-05 | 2025-06-05 | 1 | 1 | 98 | 70 | 25 | 19 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-15 | 307 | 220 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-06-21 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 4153.34 | Unknown | Unknown | Unknown | -1140 | 5293.34 | Unknown | 1140.48 | 4153.34 | -3012.86 | Yes | N/A | N/A | 2024-01-11 | 2024-06-07 | 149 | 107 | 2024-06-07 | 2024-11-06 | 153 | 109 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | 2025-03-18 | 2025-04-18 | 1900-01-31 | 24 | 2025-04-18 | 2025-04-18 | 1 | 1 | 149 | 107 | 186 | 134 | 335 | 241 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-15 | 395 | 282 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-24 | 2023-09-12 | IOU Designed & Installed | N/A | No | N/A | 2363.3 | Unknown | Unknown | Unknown | -397 | 2760.3 | Unknown | 446.46 | 2363.3 | -1916.84 | Yes | N/A | N/A | 2023-05-19 | 2023-03-20 | Unknown | Unknown | 2023-03-20 | 2023-08-22 | 156 | 112 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | 2023-10-03 | 43 | 31 | Unknown | 2023-09-08 | Unknown | Unknown | 2023-09-12 | 2023-10-03 | 1900-01-21 | 16 | 2023-10-03 | 2023-11-14 | 43 | 31 | 43 | 31 | 221 | 159 | 264 | 190 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-11 | -310 | -223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-05 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | -1894.54 | 1095.44 | Unknown | 96.2 | -3697 | 610.82 | Unknown | 3697.13 | -1894.54 | 5591.67 | Yes | N/A | N/A | 2025-03-05 | 2025-03-05 | 1 | 1 | 2025-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-04-02 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-04-07 | 1899-12-31 | 1 | 2025-04-07 | 2025-04-07 | 1 | 1 | 1 | 1 | 25 | 19 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 55.05 | 55.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -345 | -248 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-12 | 2025-05-30 | IOU Designed & Installed | N/A | No | N/A | -1022.9 | -15.68 | Unknown | Unknown | -1803 | 795.78 | Unknown | 1663.61 | -1022.9 | 2686.51 | Yes | N/A | N/A | 2024-12-12 | 2024-12-05 | Unknown | Unknown | 2024-12-05 | 2024-12-12 | 8 | 6 | 2024-12-12 | 2024-12-19 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-05-30 | 163 | 117 | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-04 | 1900-01-05 | 4 | 2025-06-04 | 2025-06-04 | 1 | 1 | 171 | 123 | 15 | 11 | 186 | 134 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2020-09-30 | 1384 | 989 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2024-03-28 | 2024-05-20 | IOU Designed & Installed | N/A | No | N/A | 712.06 | 2840.3 | Unknown | 260.94 | -3803 | 1413.82 | Unknown | 3802.5 | 712.06 | 3090.44 | Yes | N/A | N/A | 2023-02-02 | 2024-03-05 | 398 | 284 | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-07-15 | 1900-02-25 | 41 | 2024-07-15 | 2024-07-15 | 1 | 1 | 398 | 284 | 58 | 42 | 456 | 326 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 109.4 | 109.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-18 | -152 | -110 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 452.91 | Unknown | Unknown | Unknown | 20.51 | 432.4 | 0 | 1208.96 | 452.91 | 756.05 | Yes | N/A | N/A | 2023-11-09 | 2024-04-03 | 147 | 105 | 2024-04-03 | 2024-04-05 | 3 | 3 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | Unknown | 2025-05-20 | Unknown | Unknown | 2025-05-20 | 2025-05-19 | Unknown | Unknown | 147 | 105 | 3 | 3 | 150 | 108 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | -536 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-06-14 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | -1573.71 | Unknown | Unknown | Unknown | -1623 | 49.29 | Unknown | 1623.21 | -1573.71 | 3196.92 | Yes | N/A | N/A | 2024-03-20 | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-07-16 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-08-13 | 1900-01-28 | 21 | 2024-08-13 | 2024-08-13 | 1 | 1 | 0 | 0 | 150 | 108 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 24.05 | 24.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | -422 | -302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1523.32 | -53.04 | Unknown | Unknown | 19.75 | 1556.61 | 3981 | 314.19 | 1523.32 | -1209.13 | Yes | N/A | N/A | 2024-08-22 | 2024-12-19 | 120 | 86 | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | Unknown | Unknown | 2025-03-27 | 2025-03-27 | 1 | 1 | 120 | 86 | 2 | 2 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | 293 | 210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-09-25 | 2023-11-28 | IOU Designed & Installed | N/A | No | N/A | 1526.33 | 84.69 | Unknown | Unknown | 1.06 | 1440.58 | Unknown | 5139.85 | 1526.33 | 3613.52 | Yes | N/A | N/A | 2023-08-22 | 2023-08-22 | 1 | 1 | 2023-08-22 | 2023-10-24 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-10-19 | 12 | 10 | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2023-12-19 | 1900-01-21 | 16 | 2023-12-19 | 2023-12-19 | 1 | 1 | 1 | 1 | 99 | 73 | 100 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | -390 | -279 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-02-23 | 2024-11-04 | IOU Designed & Installed | N/A | No | N/A | 3201.39 | 611 | Unknown | Unknown | 16.48 | 2573.91 | 0 | 782.17 | 3201.39 | -2419.22 | Yes | N/A | N/A | 2024-02-23 | 2023-12-19 | Unknown | Unknown | 2023-12-19 | 2024-03-06 | 79 | 57 | 2024-03-06 | 2024-11-11 | 251 | 179 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-11-04 | 244 | 174 | Unknown | 2024-11-04 | Unknown | Unknown | 2024-11-04 | 2024-11-12 | 1900-01-08 | 7 | 2024-11-12 | 2024-11-12 | 1 | 1 | 495 | 353 | 89 | 65 | 584 | 418 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-04 | -507 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-15 | 2024-03-24 | 2024-08-05 | IOU Designed & Installed | N/A | No | N/A | 2138.89 | 694.83 | Unknown | 40.53 | Unknown | 1403.53 | Unknown | 1465.45 | 2138.89 | -673.44 | Yes | N/A | N/A | 2024-03-15 | 2024-01-17 | Unknown | Unknown | 2024-01-17 | 2024-03-24 | 68 | 48 | 2024-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-08-05 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-08-15 | 1900-01-10 | 9 | 2024-08-15 | 2024-08-15 | 1 | 1 | 134 | 96 | 80 | 58 | 214 | 154 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 89 | 89 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-25 | -184 | -131 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-10-02 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 633.56 | -12.99 | Unknown | Unknown | Unknown | 646.55 | 3981 | 1338.83 | 633.56 | 705.27 | Yes | N/A | N/A | 2023-10-02 | 2023-11-20 | 50 | 36 | 2023-11-20 | 2024-01-05 | 47 | 35 | 2024-01-05 | 2024-02-14 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-03-25 | 81 | 57 | Unknown | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-04-03 | 1900-01-09 | 8 | 2024-04-03 | 2024-11-22 | 234 | 168 | 172 | 122 | 291 | 211 | 463 | 333 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | -690 | -494 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | 2024-11-01 | IOU Designed & Installed | N/A | No | N/A | 69.29 | -0.31 | Unknown | Unknown | Unknown | 69.6 | 3981 | 1622.61 | 69.29 | 1553.32 | Yes | N/A | N/A | 2024-10-30 | 2024-10-27 | Unknown | Unknown | 2024-10-27 | 2024-10-30 | 4 | 3 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2024-11-01 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2024-11-19 | 1900-01-18 | 13 | 2024-11-19 | 2024-11-19 | 1 | 1 | 3 | 3 | 24 | 17 | 27 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-09 | 597 | 428 | No | 2023-06-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | 2023-12-19 | IOU Designed & Installed | N/A | Yes | 87 | 892.13 | -16.46 | Unknown | Unknown | 12.11 | 896.48 | 3981 | 916.45 | 892.13 | 24.32 | Yes | N/A | N/A | 2023-06-20 | 2023-09-08 | 81 | 59 | 2023-09-08 | 2023-09-15 | 8 | 6 | 2023-06-20 | 2023-08-09 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | 2023-12-19 | 183 | 131 | Unknown | 2023-12-18 | Unknown | Unknown | 2023-12-19 | 2023-12-27 | 1900-01-08 | 7 | 2023-12-27 | 2023-12-27 | 1 | 1 | 315 | 227 | 18 | 14 | 333 | 241 | Steps 2,3,5,6,7 | 87 | 63 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-12 | -695 | -498 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-27 | 2025-05-27 | 2025-05-29 | IOU Designed & Installed | N/A | No | N/A | 32.39 | Unknown | Unknown | Unknown | Unknown | 32.39 | 3981 | 1044.6 | 32.39 | 1012.21 | Yes | N/A | N/A | 2025-05-27 | 2025-05-27 | 1 | 1 | 2025-05-27 | 2025-05-27 | 1 | 1 | 2025-05-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | 2025-05-29 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-16 | 1900-01-18 | 13 | 2025-06-16 | 2025-06-16 | 1 | 1 | 4 | 4 | 21 | 15 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-06 | -111 | -80 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-05 | 2023-09-29 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | -9.39 | -7.09 | Unknown | Unknown | Unknown | -2.3 | Unknown | 500.87 | -9.39 | 510.26 | Yes | N/A | N/A | 2023-08-05 | 2023-09-29 | 56 | 40 | 2023-09-29 | 2023-09-29 | 1 | 1 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-10-13 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-11-16 | 1900-02-03 | 25 | 2023-11-16 | 2023-11-16 | 1 | 1 | 71 | 51 | 37 | 27 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-13 | -283 | -203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-22 | 2024-02-26 | IOU Designed & Installed | N/A | No | N/A | 108.76 | -0.94 | Unknown | Unknown | 0.09 | 109.61 | 0 | 1081.23 | 108.76 | 972.47 | Yes | N/A | N/A | 2024-02-20 | 2023-12-15 | Unknown | Unknown | 2023-12-15 | 2024-02-22 | 70 | 50 | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-02-26 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2025-03-05 | 1901-01-08 | 268 | 2025-03-05 | 2025-03-05 | 1 | 1 | 5 | 3 | 445 | 319 | 450 | 322 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-26 | -166 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-08-29 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | -14.52 | -11.43 | Unknown | Unknown | Unknown | -3.09 | Unknown | 496.37 | -14.52 | 510.89 | Yes | N/A | N/A | 2023-08-29 | 2023-08-29 | 1 | 1 | 2023-08-29 | 2023-08-29 | 1 | 1 | 2023-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2023-12-04 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2024-01-12 | 1900-02-08 | 30 | 2024-01-12 | 2024-01-12 | 1 | 1 | 99 | 71 | 42 | 32 | 141 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-05 | -580 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | 96.06 | -1.5 | Unknown | Unknown | Unknown | 97.56 | 3981 | 1496.59 | 96.06 | 1400.53 | Yes | N/A | N/A | 2024-12-09 | 2024-12-06 | Unknown | Unknown | 2024-12-06 | 2024-12-09 | 4 | 2 | 2024-12-09 | Unknown | Unknown | Unknown | 2024-12-09 | 2024-12-19 | 11 | 9 | 2024-12-09 | 2025-02-26 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-03-04 | 1900-01-06 | 5 | 2025-03-04 | 2025-03-04 | 1 | 1 | 80 | 58 | 23 | 17 | 103 | 75 | Steps 2,3,5,6,7 | 10 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | -568 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-25 | 2024-01-26 | IOU Designed & Installed | N/A | No | N/A | 10.76 | -13.01 | Unknown | Unknown | Unknown | 23.77 | 3981 | 933.24 | 10.76 | 922.48 | Yes | N/A | N/A | 2024-01-25 | 2023-10-26 | Unknown | Unknown | 2023-10-26 | 2023-12-20 | 56 | 40 | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-01-26 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-02-08 | 1900-01-13 | 10 | 2024-02-08 | 2024-02-08 | 1 | 1 | 2 | 2 | 71 | 51 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-07 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | 2025-01-16 | IOU Designed & Installed | N/A | No | N/A | -786.03 | -15.3 | Unknown | Unknown | -1565 | 794.27 | Unknown | 1442.19 | -786.03 | 2228.22 | Yes | N/A | N/A | 2024-11-05 | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-11-05 | 19 | 13 | 2024-11-05 | 2024-11-11 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2025-01-16 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-01-24 | 1900-01-08 | 7 | 2025-01-24 | 2025-02-27 | 35 | 25 | 80 | 58 | 63 | 45 | 143 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-14 | -596 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-04-05 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 33.41 | -16.21 | Unknown | Unknown | Unknown | 49.62 | Unknown | 1077.17 | 33.41 | 1043.76 | Yes | N/A | N/A | 2024-03-21 | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-04-05 | 17 | 13 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-04-15 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-05-28 | 1900-02-12 | 32 | 2024-05-28 | 2024-05-28 | 1 | 1 | 11 | 7 | 62 | 46 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | -585 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-24 | 2025-05-15 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1012.58 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-28 | 6 | 4 | 2025-04-28 | 2025-04-28 | 1 | 1 | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | 2025-05-15 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-06-16 | 1900-02-01 | 23 | 2025-06-16 | 2025-06-16 | 1 | 1 | 24 | 18 | 35 | 25 | 59 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 20.1 | 20.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -38 | -29 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-03-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1295.42 | Unknown | Unknown | Unknown | 39.91 | 1255.51 | Unknown | Not available | 1295.42 | Unknown | Yes | N/A | N/A | 2024-03-26 | 2024-03-08 | Unknown | Unknown | 2024-03-08 | 2024-06-10 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-12 | 27 | 19 | 2024-06-10 | 2024-12-17 | 191 | 137 | Unknown | 2024-12-10 | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | 2024-12-18 | 2024-12-17 | Unknown | Unknown | 191 | 137 | 122 | 86 | 313 | 223 | Steps 2,3,5,6,7 | 2 | 2 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 18.1 | 18.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-02 | -181 | -130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-13 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 27823.16 | 962.09 | Unknown | Unknown | 18.48 | 26842.59 | 0 | 13377.64 | 27823.16 | -14445.52 | Yes | N/A | N/A | 2024-05-06 | 2024-04-17 | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-12 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-05-05 | 1900-02-17 | 35 | 2025-05-05 | 2025-05-05 | 1 | 1 | 0 | 0 | 77 | 55 | 77 | 55 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 32.1 | 32.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-12 | -571 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-02-16 | 2024-03-06 | IOU Designed & Installed | N/A | No | N/A | 1616.07 | -42.91 | Unknown | Unknown | Unknown | 1658.98 | 3981 | 1205.27 | 1616.07 | -410.8 | Yes | N/A | N/A | 2024-01-16 | 2024-02-16 | 32 | 24 | 2024-02-16 | 2024-02-16 | 1 | 1 | 2024-02-16 | Unknown | Unknown | Unknown | 2024-02-16 | 2024-03-01 | 15 | 11 | 2024-02-16 | 2024-03-06 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-03-21 | 1900-01-15 | 12 | 2024-03-21 | 2024-03-20 | Unknown | Unknown | 52 | 38 | 32 | 24 | 84 | 62 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | RAMONA | RAMONA | 46.4 | 46.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-02 | 288 | 207 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-05-30 | 2024-09-05 | IOU Designed & Installed | N/A | No | N/A | 21501.62 | 5587.4 | Unknown | Unknown | -9641 | 25555.22 | 3430 | 22711.94 | 21501.62 | 1210.32 | Yes | N/A | N/A | 2023-03-31 | 2023-05-26 | 57 | 41 | 2023-05-26 | 2024-07-25 | 427 | 305 | 2023-06-08 | 2024-07-10 | 373 | 267 | 2023-06-06 | 2024-10-02 | 360 | 256 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2024-10-16 | 1900-02-10 | 30 | 2024-10-16 | 2024-10-16 | 1 | 1 | 430 | 308 | 830 | 592 | 1260 | 900 | Steps 2,3,5,6,7 | 813 | 581 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 135.05 | 135.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-09 | 159 | 115 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1003.55 | Unknown | Unknown | Unknown | -1135 | 131.45 | 3981 | 3206.95 | -1003.55 | 4210.5 | Yes | N/A | N/A | 2024-03-21 | 2024-02-12 | Unknown | Unknown | 2024-02-12 | 2024-08-26 | 197 | 141 | 2024-08-08 | 2024-08-08 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-11-06 | 73 | 53 | Unknown | 2024-11-07 | Unknown | Unknown | Unknown | 2024-11-18 | Unknown | Unknown | 2024-11-18 | 2024-11-15 | Unknown | Unknown | 74 | 54 | 197 | 141 | 271 | 195 | Steps 2,3,5,6,7 | 18 | 12 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-04 | 305 | 218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-09 | 2022-10-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 392.25 | -3.4 | Unknown | Unknown | Unknown | 395.65 | 3981 | 729.58 | 392.25 | 337.33 | Yes | N/A | N/A | 2022-09-09 | 2023-04-26 | 230 | 164 | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | Unknown | Unknown | 2023-06-05 | 2023-06-05 | 1 | 1 | 230 | 164 | 1 | 1 | 231 | 165 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-28 | -261 | -188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-04-24 | IOU Designed & Installed | N/A | No | N/A | -5.23 | -3.78 | Unknown | Unknown | Unknown | -1.45 | Unknown | 793.74 | -5.23 | 798.97 | Yes | N/A | N/A | 2023-04-24 | 2023-04-24 | 1 | 1 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | 2023-04-24 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | 2023-06-12 | 1900-02-18 | 36 | 2023-06-12 | 2023-06-12 | 1 | 1 | 2 | 2 | 51 | 37 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-30 | -434 | -311 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4038.6 | 470.34 | Unknown | 60.1 | 93.91 | 3414.25 | 3981 | 1776.09 | 4038.6 | -2262.51 | Yes | N/A | N/A | 2024-06-19 | 2024-05-07 | Unknown | Unknown | 2024-05-07 | 2024-05-07 | 1 | 1 | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-02-20 | 2 | 2 | 0 | 0 | 3 | 3 | 3 | 3 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 86 | 86 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-25 | 135 | 98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-17 | 2023-11-17 | 2024-04-25 | IOU Designed & Installed | N/A | No | N/A | 7.58 | -6.73 | Unknown | Unknown | Unknown | 14.31 | 3981 | 912.22 | 7.58 | 904.64 | Yes | N/A | N/A | 2023-11-17 | 2023-10-12 | Unknown | Unknown | 2023-10-12 | 2023-11-17 | 37 | 27 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2024-04-25 | 161 | 115 | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-05-06 | 1900-01-11 | 8 | 2024-05-06 | 2024-05-08 | 3 | 3 | 161 | 115 | 52 | 38 | 213 | 153 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 75.05 | 75.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-06 | -381 | -272 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1554.51 | -10.92 | Unknown | Unknown | 59.78 | 1505.65 | 3941 | 691.73 | 1554.51 | -862.78 | Yes | N/A | N/A | 2023-07-10 | 2023-04-28 | Unknown | Unknown | 2023-04-28 | 2023-08-11 | 106 | 76 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | Unknown | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-03-21 | 1 | 1 | 0 | 0 | 107 | 77 | 107 | 77 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-16 | 31 | 22 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | 2023-09-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 32.33 | Unknown | Unknown | Unknown | Unknown | 32.33 | 3981 | 977.78 | 32.33 | 945.45 | Yes | N/A | N/A | 2023-09-05 | 2023-09-13 | 9 | 7 | 2023-09-13 | 2023-10-09 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | 2024-10-15 | 28 | 20 | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | Unknown | Unknown | 2024-09-16 | 2024-09-16 | 1 | 1 | 9 | 7 | 56 | 40 | 65 | 47 | Steps 2,3,5,6,7 | 372 | 266 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-03 | -573 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-23 | 2024-12-23 | 2025-03-10 | IOU Designed & Installed | N/A | No | N/A | 1573.34 | 460.58 | Unknown | Unknown | -430 | 1542.76 | 3981 | 1578.54 | 1573.34 | 5.2 | Yes | N/A | N/A | 2024-12-23 | 2024-12-20 | Unknown | Unknown | 2024-12-20 | 2024-12-23 | 4 | 2 | 2024-12-23 | 2025-04-28 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-03-10 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-05-09 | 1900-03-01 | 45 | 2025-05-09 | 2025-05-09 | 1 | 1 | 205 | 147 | 66 | 48 | 271 | 195 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | -282 | -203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | 2023-04-10 | IOU Designed & Installed | N/A | No | N/A | 3419.64 | 953.5 | Unknown | 330.38 | Unknown | 2135.76 | 3981 | 1585.62 | 3419.64 | -1834.02 | Yes | N/A | N/A | 2023-02-15 | 2023-02-15 | 1 | 1 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | 2023-04-10 | 55 | 39 | Unknown | 2023-04-20 | Unknown | Unknown | 2023-04-10 | 2023-04-24 | 1900-01-14 | 11 | 2023-04-24 | 2023-04-24 | 1 | 1 | 56 | 40 | 16 | 12 | 72 | 52 | Steps 2,3,5,6,7 | 10 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 160 | 160 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-11 | -594 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-10 | 2024-05-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5152.35 | 298.65 | Unknown | Unknown | Unknown | 4853.7 | 230898 | 1189.12 | 5152.35 | -3963.23 | Yes | N/A | N/A | 2024-05-10 | 2024-05-30 | 21 | 15 | 2024-05-30 | 2024-07-10 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2958465 | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-02-24 | 1 | 1 | 21 | 15 | 43 | 31 | 64 | 46 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-30 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-27 | 2023-10-20 | IOU Designed & Installed | N/A | No | N/A | 1728.95 | 1216.84 | Unknown | Unknown | Unknown | 512.11 | Unknown | 153.87 | 1728.95 | -1575.08 | Yes | N/A | N/A | 2023-06-27 | 2023-07-14 | 18 | 14 | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-10-20 | 96 | 70 | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2023-10-30 | 1900-01-10 | 7 | 2023-10-30 | 2023-10-30 | 1 | 1 | 114 | 84 | 13 | 9 | 127 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-25 | 296 | 211 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-12-05 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 1221.63 | Unknown | Unknown | Unknown | Unknown | 1221.63 | Unknown | 933.22 | 1221.63 | -288.41 | Yes | N/A | N/A | 2024-10-30 | 2024-12-05 | 37 | 27 | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-03-17 | 1900-02-18 | 36 | 2025-03-17 | 2025-03-17 | 1 | 1 | 37 | 27 | 51 | 37 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-27 | -564 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-02-07 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 616.87 | -11.7 | Unknown | Unknown | Unknown | 628.57 | 3981 | 1762.7 | 616.87 | 1145.83 | Yes | N/A | N/A | 2025-01-09 | 2025-02-06 | 29 | 21 | 2025-02-06 | 2025-02-07 | 2 | 2 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-03-05 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-12 | 1900-01-07 | 6 | 2025-03-12 | 2025-03-12 | 1 | 1 | 56 | 40 | 11 | 9 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-05 | -312 | -223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | 2025-05-22 | 2025-06-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 4172.88 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-22 | 2025-05-22 | 1 | 1 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-06-27 | 1900-01-02 | 3 | 2025-06-27 | 2025-06-27 | 1 | 1 | 1 | 1 | 4 | 4 | 5 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-08 | -495 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-30 | 2024-12-30 | 2025-05-01 | IOU Designed & Installed | N/A | No | N/A | 1894.26 | Unknown | Unknown | Unknown | 19.97 | 1874.29 | 3981 | 1168.47 | 1894.26 | -725.79 | Yes | N/A | N/A | 2024-12-30 | 2025-01-23 | 25 | 19 | 2025-01-23 | 2025-01-31 | 9 | 7 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-05-01 | 67 | 49 | Unknown | 2025-04-25 | Unknown | Unknown | 2025-05-01 | 2025-05-31 | 1900-01-30 | 22 | 2025-05-31 | 2025-05-31 | 1 | 0 | 92 | 68 | 41 | 29 | 133 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | -668 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | 2024-08-19 | IOU Designed & Installed | N/A | No | N/A | 43.4 | Unknown | Unknown | Unknown | Unknown | 43.4 | 3981 | 1639.56 | 43.4 | 1596.16 | Yes | N/A | N/A | 2024-08-06 | 2024-08-02 | Unknown | Unknown | 2024-08-02 | 2024-08-06 | 5 | 3 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-19 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-09-24 | 1900-02-05 | 27 | 2024-09-24 | 2024-09-24 | 1 | 1 | 14 | 10 | 43 | 31 | 57 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-10 | -630 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 722.76 | 196.92 | Unknown | Unknown | Unknown | 525.84 | Unknown | 1635.81 | 722.76 | 913.05 | Yes | N/A | N/A | 2024-10-17 | 2024-09-20 | Unknown | Unknown | 2024-09-20 | 2024-11-15 | 57 | 41 | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-11-15 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-19 | 1900-02-03 | 25 | 2024-12-19 | 2024-12-19 | 1 | 1 | 1 | 1 | 93 | 67 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-20 | 204 | 147 | No | 2023-05-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-07-03 | Unknown | IOU Designed & Installed | N/A | Yes | 210 | 25.77 | Unknown | Unknown | Unknown | Unknown | 25.77 | 3981 | 628.24 | 25.77 | 602.47 | Yes | N/A | N/A | 2023-05-15 | 2023-12-01 | 201 | 145 | 2023-12-01 | 2023-07-03 | Unknown | Unknown | 2023-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | 2024-10-10 | 2024-10-10 | 1 | 1 | 201 | 145 | 1 | 1 | 202 | 146 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-06-10 | 1077 | 770 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 401.16 | -17.92 | Unknown | Unknown | Unknown | 419.08 | Unknown | 848.2 | 401.16 | 447.04 | Yes | N/A | N/A | 2024-01-30 | 2024-01-30 | 1 | 1 | 2024-01-30 | 2024-05-07 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2024-04-20 | 2024-05-16 | 27 | 19 | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-05-22 | 1 | 1 | 1 | 1 | 127 | 91 | 128 | 92 | Steps 2,3,5,6,7 | 9 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 72 | 72 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | -226 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -7.36 | -5.31 | Unknown | Unknown | Unknown | -2.05 | Unknown | 153.75 | -7.36 | 161.11 | Yes | N/A | N/A | 2023-05-03 | 2023-05-11 | 9 | 7 | 2023-05-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | Unknown | Unknown | 2023-07-13 | 2023-07-13 | 1 | 1 | 9 | 7 | 1 | 1 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-24 | 9 | 8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-03-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1289.5 | -20.66 | Unknown | Unknown | -1576 | 307.16 | 0 | 1410.59 | -1289.5 | 2700.09 | Yes | N/A | N/A | 2024-02-26 | 2024-03-05 | 9 | 7 | 2024-03-05 | 2024-08-15 | 164 | 118 | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2025-03-12 | 21 | 15 | 2024-08-15 | 2025-02-06 | 176 | 126 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | Unknown | Unknown | 2025-04-04 | 2025-04-02 | Unknown | Unknown | 185 | 133 | 185 | 133 | 370 | 266 | Steps 2,3,5,6,7 | 209 | 149 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 117.05 | 117.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-27 | 432 | 309 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-09-28 | 2025-05-22 | IOU Designed & Installed | N/A | No | N/A | 1269.63 | Unknown | Unknown | Unknown | 35.49 | 1234.14 | 3885 | 707.74 | 1269.63 | -561.89 | Yes | N/A | N/A | 2023-09-28 | 2023-09-19 | Unknown | Unknown | 2023-09-19 | 2023-09-29 | 11 | 9 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2025-05-22 | 602 | 430 | Unknown | 2025-05-07 | Unknown | Unknown | 2025-05-22 | 2025-06-02 | 1900-01-11 | 8 | 2025-06-02 | 2025-06-02 | 1 | 1 | 602 | 430 | 24 | 18 | 626 | 448 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-04 | -578 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | 2024-03-07 | IOU Designed & Installed | N/A | No | N/A | 205.15 | -10.3 | Unknown | Unknown | -692.68 | 908.13 | Unknown | 708.72 | 205.15 | 503.57 | Yes | N/A | N/A | 2023-12-11 | 2023-11-22 | Unknown | Unknown | 2023-11-22 | 2023-12-13 | 22 | 16 | 2023-12-13 | 2024-01-05 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-03-07 | 86 | 62 | Unknown | 2024-02-27 | Unknown | Unknown | 2024-03-07 | 2024-04-05 | 1900-01-29 | 22 | 2024-04-05 | 2024-04-05 | 1 | 1 | 110 | 80 | 53 | 39 | 163 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-12 | -505 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-24 | 2024-03-28 | IOU Designed & Installed | N/A | No | N/A | 1268.39 | 416.11 | Unknown | Unknown | Unknown | 852.28 | Unknown | 987.89 | 1268.39 | -280.5 | Yes | N/A | N/A | 2024-01-23 | 2023-10-03 | Unknown | Unknown | 2023-10-03 | 2024-01-24 | 114 | 82 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-03-28 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-04-25 | 1900-01-28 | 21 | 2024-04-25 | 2024-04-25 | 1 | 1 | 65 | 47 | 144 | 104 | 209 | 151 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -342 | -245 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-07-07 | 2024-04-21 | IOU Designed & Installed | N/A | No | N/A | 3239.48 | 1651.48 | Unknown | 235.52 | -1101 | 2453.48 | 3981 | 3822.03 | 3239.48 | 582.55 | Yes | N/A | N/A | 2023-06-30 | 2023-06-26 | Unknown | Unknown | 2023-06-26 | 2023-07-07 | 12 | 10 | 2023-07-07 | 2023-09-25 | 81 | 57 | Unknown | Unknown | Unknown | Unknown | 2023-07-12 | 2024-04-21 | 285 | 203 | Unknown | 2024-03-11 | Unknown | Unknown | 2024-04-21 | 2024-04-24 | 1900-01-03 | 3 | 2024-04-24 | 2024-04-24 | 1 | 1 | 366 | 260 | 17 | 14 | 383 | 274 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 29 | 29 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-04 | -595 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-27 | 2024-12-13 | 2025-03-12 | IOU Designed & Installed | N/A | No | N/A | 7.37 | Unknown | Unknown | Unknown | Unknown | 7.37 | 3981 | 1032.15 | 7.37 | 1024.78 | Yes | N/A | N/A | 2024-11-27 | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-11-27 | 16 | 12 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-03-12 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-03-19 | 1900-01-07 | 6 | 2025-03-19 | 2025-03-19 | 1 | 1 | 90 | 64 | 25 | 19 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-04 | -612 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-11 | 2025-02-18 | IOU Designed & Installed | N/A | No | N/A | 866.64 | -17.41 | Unknown | Unknown | Unknown | 884.05 | 3981 | 1680.74 | 866.64 | 814.1 | Yes | N/A | N/A | 2025-02-11 | 2025-02-11 | 1 | 1 | 2025-02-11 | 2025-02-11 | 1 | 1 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-02-18 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-04-01 | 1900-02-11 | 31 | 2025-04-01 | 2025-04-01 | 1 | 1 | 9 | 7 | 45 | 33 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-12 | -273 | -196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-05 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 1764.9 | -13.29 | Unknown | Unknown | 9.14 | 1769.05 | 3981 | 783.95 | 1764.9 | -980.95 | Yes | N/A | N/A | 2024-04-03 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2024-04-17 | 37 | 27 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-06-06 | 51 | 37 | Unknown | 2024-06-05 | Unknown | Unknown | 2024-06-06 | 2024-06-12 | 1900-01-06 | 5 | 2024-06-12 | 2024-06-12 | 1 | 1 | 51 | 37 | 45 | 33 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-27 | 305 | 219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1061.73 | -7.71 | Unknown | Unknown | 63.65 | 1005.79 | 3991 | 296.68 | 1061.73 | -765.05 | Yes | N/A | N/A | 2023-01-24 | 2023-02-26 | 34 | 24 | 2023-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-26 | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2023-09-28 | 1 | 1 | 34 | 24 | 1 | 1 | 35 | 25 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-11 | -405 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-20 | 2024-09-30 | IOU Designed & Installed | N/A | No | N/A | 598.43 | Unknown | Unknown | Unknown | Unknown | 598.43 | Unknown | 745.57 | 598.43 | 147.14 | Yes | N/A | N/A | 2024-09-20 | 2024-09-20 | 1 | 1 | 2024-09-20 | 2025-03-03 | 165 | 117 | 2025-03-03 | Unknown | Unknown | Unknown | 2024-09-23 | Unknown | Unknown | Unknown | 2024-09-24 | 2024-09-30 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-10-02 | 1900-01-02 | 3 | 2024-10-02 | 2024-10-02 | 1 | 1 | 8 | 6 | 169 | 121 | 177 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 93 | 93 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-19 | -348 | -250 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-10-30 | 2024-04-25 | IOU Designed & Installed | N/A | No | N/A | -17.78 | -14.46 | Unknown | Unknown | Unknown | -3.32 | 3981 | 940.94 | -17.78 | 958.72 | Yes | N/A | N/A | 2023-07-26 | 2023-10-24 | 91 | 65 | 2023-10-24 | 2023-10-30 | 7 | 5 | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2024-04-25 | 179 | 129 | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-05-07 | 1900-01-12 | 9 | 2024-05-07 | 2024-05-06 | Unknown | Unknown | 270 | 194 | 20 | 14 | 290 | 208 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-07 | -184 | -133 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-07-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -7.32 | -5.29 | Unknown | Unknown | Unknown | -2.03 | 3981 | 465.44 | -7.32 | 472.76 | Yes | N/A | N/A | 2023-06-27 | 2023-07-13 | 17 | 13 | 2023-07-13 | 2023-07-13 | 1 | 1 | 2023-07-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-07 | Unknown | Unknown | 2023-08-07 | 2023-08-07 | 1 | 1 | 17 | 13 | 2 | 2 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 99.1 | 99.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-12 | -676 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | 2025-04-15 | 2025-04-23 | IOU Designed & Installed | N/A | No | N/A | 1664.2 | 400.32 | Unknown | 85.13 | Unknown | 1178.75 | 3981 | 1614.88 | 1664.2 | -49.32 | Yes | N/A | N/A | 2025-04-15 | 2025-03-18 | Unknown | Unknown | 2025-03-18 | 2025-04-17 | 31 | 23 | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-04-23 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-05-05 | 1900-01-12 | 9 | 2025-05-05 | 2025-05-05 | 1 | 1 | 7 | 5 | 45 | 33 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-31 | -138 | -99 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2024-01-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12.25 | -10.92 | Unknown | Unknown | Unknown | 23.17 | 3981 | 2125.22 | 12.25 | 2112.97 | Yes | N/A | N/A | 2023-09-19 | 2023-12-29 | 102 | 74 | 2023-12-29 | 2024-01-03 | 6 | 4 | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 102 | 74 | 7 | 5 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | -483 | -346 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-05-18 | 2023-07-21 | IOU Designed & Installed | N/A | No | N/A | -5.49 | -6.85 | Unknown | Unknown | Unknown | 1.36 | Unknown | 148.62 | -5.49 | 154.11 | Yes | N/A | N/A | 2023-05-18 | 2023-06-01 | 15 | 11 | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | 2023-07-21 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2023-10-13 | 1900-03-25 | 61 | 2023-10-13 | 2023-10-13 | 1 | 1 | 66 | 48 | 86 | 62 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-29 | -313 | -225 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-19 | 2023-07-19 | 2023-07-20 | IOU Designed & Installed | N/A | No | N/A | 120.88 | -8.85 | Unknown | Unknown | Unknown | 129.73 | 3981 | 833.62 | 120.88 | 712.74 | Yes | N/A | N/A | 2023-07-19 | 2023-04-07 | Unknown | Unknown | 2023-04-07 | 2023-07-19 | 104 | 74 | 2023-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | 2023-07-20 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-07-25 | 1900-01-05 | 4 | 2023-07-25 | 2024-05-20 | 301 | 215 | 2 | 2 | 411 | 293 | 413 | 295 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 626.4 | 626.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 69 | 50 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2024-02-08 | 2024-05-07 | IOU Designed & Installed | N/A | No | N/A | 7995.1 | Unknown | Unknown | Unknown | Unknown | 7995.1 | 43791 | 1212.36 | 7995.1 | -6782.74 | Yes | N/A | N/A | 2023-08-08 | 2023-06-05 | Unknown | Unknown | 2023-06-05 | 2024-04-09 | 310 | 222 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-05-13 | 1900-01-06 | 5 | 2024-05-13 | 2024-05-09 | Unknown | Unknown | 0 | 0 | 317 | 227 | 317 | 227 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-06 | -617 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-08 | 2023-12-19 | IOU Designed & Installed | N/A | No | N/A | 995.13 | 582.92 | Unknown | Unknown | Unknown | 412.21 | Unknown | 496.75 | 995.13 | -498.38 | Yes | N/A | N/A | 2023-11-08 | 2023-11-08 | 1 | 1 | 2023-11-08 | 2023-11-08 | 1 | 1 | 2023-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2023-12-19 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2023-12-29 | 1900-01-10 | 9 | 2023-12-29 | 2023-12-29 | 1 | 1 | 43 | 31 | 13 | 11 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 448.05 | 448.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-20 | -145 | -104 | No | 2023-05-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | 2023-05-26 | Unknown | IOU Designed & Installed | N/A | Yes | 426 | 1766.46 | Unknown | Unknown | Unknown | 13.4 | 1753.06 | Unknown | 1000.44 | 1766.46 | -766.02 | Yes | N/A | N/A | 2023-05-26 | 2024-06-11 | 383 | 273 | 2024-06-11 | 2024-07-25 | 45 | 33 | 2024-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | Unknown | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | 2024-08-28 | 2024-08-28 | 1 | 1 | 383 | 273 | 46 | 34 | 429 | 307 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 21 | 21 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-03 | -640 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-02-27 | 2025-03-24 | IOU Designed & Installed | N/A | No | N/A | 2140.2 | 509.4 | Unknown | 128.91 | Unknown | 1501.89 | 3981 | 1720.99 | 2140.2 | -419.21 | Yes | N/A | N/A | 2025-01-16 | 2025-02-03 | 19 | 13 | 2025-02-03 | 2025-02-27 | 25 | 19 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-03-24 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-04-03 | 1900-01-10 | 9 | 2025-04-03 | 2025-04-03 | 1 | 1 | 45 | 31 | 37 | 29 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 6.75 | 6.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-16 | -447 | -320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2024-03-11 | IOU Designed & Installed | N/A | No | N/A | 783.27 | -6.36 | Unknown | Unknown | 9.74 | 779.89 | 3981 | 734.46 | 783.27 | -48.81 | Yes | N/A | N/A | 2023-09-29 | 2023-10-27 | 29 | 21 | 2023-10-27 | 2023-10-30 | 4 | 2 | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2024-03-11 | 134 | 96 | Unknown | 2024-03-08 | Unknown | Unknown | 2024-03-11 | 2024-03-26 | 1900-01-15 | 12 | 2024-03-26 | 2024-03-26 | 1 | 1 | 163 | 117 | 21 | 15 | 184 | 132 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-18 | -42 | -31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | 2024-01-04 | IOU Designed & Installed | N/A | No | N/A | 151.88 | -5.5 | Unknown | Unknown | Unknown | 157.38 | 3981 | 998.5 | 151.88 | 846.62 | Yes | N/A | N/A | 2023-09-11 | 2023-12-19 | 100 | 72 | 2023-12-19 | 2023-12-19 | 1 | 1 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-01-04 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-03-07 | 1900-03-04 | 46 | 2024-03-07 | 2024-03-07 | 1 | 1 | 117 | 85 | 66 | 48 | 183 | 133 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-26 | -538 | -385 | No | 2023-01-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-09 | 2023-01-09 | 2023-03-06 | IOU Designed & Installed | N/A | Yes | 23 | 331.62 | 121.66 | Unknown | Unknown | Unknown | 209.96 | Unknown | 379.71 | 331.62 | 48.09 | Yes | N/A | N/A | 2023-01-09 | 2023-02-01 | 24 | 18 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-30 | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-06 | 2023-03-07 | 1900-01-01 | 2 | 2023-03-07 | 2023-03-07 | 1 | 1 | 24 | 18 | 3 | 3 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-15 | -501 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-18 | 2023-09-22 | IOU Designed & Installed | N/A | No | N/A | 1021.91 | 258.4 | Unknown | 81.16 | 1.83 | 680.52 | 3981 | 656.7 | 1021.91 | -365.21 | Yes | N/A | N/A | 2023-04-18 | 2023-08-07 | 112 | 80 | 2023-08-07 | 2023-08-11 | 5 | 5 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2023-09-22 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2023-10-03 | 1900-01-11 | 8 | 2023-10-03 | 2023-10-03 | 1 | 1 | 155 | 111 | 18 | 14 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | La Mesa | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-09 | 245 | 176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-10-16 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 1815.64 | 303.79 | Unknown | Unknown | Unknown | 1511.85 | 0 | 17077.87 | 1815.64 | 15262.23 | Yes | N/A | N/A | 2024-09-19 | 2023-11-30 | Unknown | Unknown | 2023-11-30 | 2025-04-09 | 497 | 355 | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2025-05-09 | 58 | 42 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-12 | 1899-12-31 | 1 | 2025-05-12 | 2025-05-12 | 1 | 1 | 0 | 0 | 557 | 399 | 557 | 399 | Steps 2,3,5,6,7 | 30 | 22 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-17 | -675 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | 2025-04-28 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 986.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-04-28 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | 2025-06-11 | 1900-02-13 | 33 | 2025-06-11 | 2025-06-11 | 1 | 1 | 7 | 5 | 47 | 35 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 320 | 320 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-27 | 17 | 14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | 2023-03-13 | IOU Designed & Installed | N/A | No | N/A | 1068.21 | 238.26 | Unknown | 88.1 | Unknown | 741.85 | Unknown | 271.63 | 1068.21 | -796.58 | Yes | N/A | N/A | 2023-03-01 | 2023-03-07 | 7 | 5 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | 2023-03-13 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-03-13 | 2023-03-16 | 1900-01-03 | 4 | 2023-03-16 | 2023-03-16 | 1 | 1 | 14 | 10 | 5 | 5 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-20 | 702 | 503 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-02-06 | 2024-12-19 | IOU Designed & Installed | N/A | No | N/A | 30763.4 | 1697.2 | Unknown | Unknown | -639.77 | 29705.97 | 40921.44 | 23613.88 | 30763.4 | -7149.52 | Yes | N/A | N/A | 2023-02-06 | 2024-03-13 | 402 | 288 | 2024-03-13 | 2024-10-09 | 211 | 151 | 2024-08-22 | Unknown | Unknown | Unknown | 2024-07-09 | 2024-10-31 | 57 | 43 | 2024-10-09 | Unknown | Unknown | Unknown | 2024-10-15 | 2024-12-09 | 56 | 40 | 2024-12-19 | 2025-02-19 | 1900-03-03 | 45 | 2025-02-19 | 2025-02-19 | 1 | 1 | 402 | 288 | 388 | 280 | 790 | 568 | Steps 2,3,5,6,7 | 70 | 50 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -484 | -347 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | 2023-08-11 | IOU Designed & Installed | N/A | No | N/A | 461.46 | 302.11 | Unknown | Unknown | Unknown | 159.35 | Unknown | 495.75 | 461.46 | 34.29 | Yes | N/A | N/A | 2023-05-16 | 2023-05-16 | 1 | 1 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | 2023-08-11 | 88 | 64 | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2023-09-28 | 1900-02-17 | 35 | 2023-09-28 | 2023-09-28 | 1 | 1 | 89 | 65 | 50 | 36 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | 317.05 | 317.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-30 | -40 | -29 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 8.24 | -7.28 | Unknown | Unknown | Unknown | 15.52 | 3941 | 865.36 | 8.24 | 857.12 | Yes | N/A | N/A | 2023-10-17 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2023-10-17 | 21 | 15 | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2024-06-03 | 231 | 165 | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-06-21 | 1900-01-18 | 15 | 2024-06-21 | 2024-06-20 | Unknown | Unknown | 231 | 165 | 40 | 30 | 271 | 195 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-29 | -426 | -305 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-25 | 2025-02-18 | IOU Designed & Installed | N/A | No | N/A | 36.39 | Unknown | Unknown | Unknown | Unknown | 36.39 | 3981 | 1531.63 | 36.39 | 1495.24 | Yes | N/A | N/A | 2024-09-24 | 2024-09-25 | 2 | 2 | 2024-09-25 | 2024-09-25 | 1 | 1 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2025-02-18 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-02-27 | 1900-01-09 | 8 | 2025-02-27 | 2025-02-27 | 1 | 1 | 149 | 107 | 12 | 10 | 161 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56, ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-10 | -318 | -227 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | 2025-06-02 | 2025-06-20 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 996.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-22 | 2025-06-02 | 12 | 8 | 2025-06-02 | 2025-06-02 | 1 | 1 | 2025-06-02 | 2025-06-10 | 5 | 3 | 2025-06-02 | 2025-06-12 | 10 | 4 | 2025-06-10 | 2025-06-20 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-06-20 | 2025-06-26 | 1900-01-06 | 5 | 2025-06-26 | 2025-06-26 | 1 | 1 | 28 | 20 | 19 | 11 | 47 | 31 | Steps 2,3,5,6,7 | 10 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 104 | 104 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-20 | -166 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 522.08 | 108.72 | Unknown | 58.96 | Unknown | 354.4 | Unknown | 196.27 | 522.08 | -325.81 | Yes | N/A | N/A | 2023-08-23 | 2023-08-23 | 1 | 1 | 2023-08-23 | 2023-08-30 | 8 | 6 | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | Unknown | Unknown | 2023-09-07 | 2023-09-07 | 1 | 1 | 1 | 1 | 9 | 7 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-07 | 282 | 201 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | 2023-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1080.97 | 3282.89 | Unknown | 685.53 | -4278 | 1390.55 | 0 | 4278.18 | 1080.97 | 3197.21 | Yes | N/A | N/A | 2023-05-01 | 2023-04-06 | Unknown | Unknown | 2023-04-06 | 2023-08-15 | 132 | 94 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 133 | 95 | 133 | 95 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | 177.15 | 177.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-08 | 24 | 18 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-05-01 | 2024-09-24 | IOU Designed & Installed | N/A | No | N/A | -898.01 | Unknown | Unknown | Unknown | -967 | 68.99 | 3981 | 2166.7 | -898.01 | 3064.71 | Yes | N/A | N/A | 2024-04-09 | 2024-04-24 | 16 | 12 | 2024-04-24 | 2024-05-01 | 8 | 6 | 2024-05-01 | 2024-05-15 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-09-24 | 132 | 94 | Unknown | 2024-09-09 | Unknown | Unknown | 2024-09-24 | 2024-10-02 | 1900-01-08 | 7 | 2024-10-02 | 2024-10-02 | 1 | 1 | 163 | 117 | 18 | 14 | 181 | 131 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-20 | 926 | 662 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-01-20 | 2021-01-20 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 6458.33 | Unknown | Unknown | Unknown | 449.96 | 6008.37 | 58550 | 23893.87 | 6458.33 | 17435.54 | Yes | N/A | N/A | 2021-01-20 | 2023-02-16 | 758 | 542 | 2023-02-16 | 2023-07-31 | 166 | 118 | 2023-03-06 | 2023-07-28 | 74 | 53 | 2023-06-05 | 2023-08-07 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | Unknown | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2024-08-03 | 1 | 0 | 832 | 595 | 186 | 133 | 1018 | 728 | Steps 2,3,5,6,7 | 200 | 144 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | -230 | -165 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-06-01 | IOU Designed & Installed | N/A | No | N/A | -6.19 | -5.14 | Unknown | Unknown | Unknown | -1.05 | Unknown | 153.75 | -6.19 | 159.94 | Yes | N/A | N/A | 2023-03-20 | 2023-05-31 | 73 | 53 | 2023-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | 2023-06-01 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | 2023-06-15 | 1900-01-14 | 11 | 2023-06-15 | 2023-06-15 | 1 | 1 | 75 | 55 | 16 | 12 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-03 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-10 | 2024-05-20 | 2024-07-31 | IOU Designed & Installed | N/A | No | N/A | 11159.66 | 3410.5 | Unknown | Unknown | -1096.6 | 8845.76 | Unknown | 2218.71 | 11159.66 | -8940.95 | Yes | N/A | N/A | 2024-05-10 | 2024-06-06 | 28 | 20 | 2024-06-06 | 2024-06-10 | 5 | 3 | 2024-06-10 | 2024-06-20 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-07-31 | 2 | 2 | Unknown | 2024-07-30 | Unknown | Unknown | 2024-07-31 | 2024-09-05 | 1900-02-05 | 27 | 2024-09-05 | 2024-09-05 | 1 | 1 | 41 | 31 | 43 | 31 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | -627 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | 112.76 | -1.5 | Unknown | Unknown | Unknown | 114.26 | Unknown | 1820.78 | 112.76 | 1708.02 | Yes | N/A | N/A | 2024-07-16 | 2024-07-16 | 1 | 1 | 2024-07-16 | 2024-07-18 | 3 | 3 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-09-16 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-09-23 | 1900-01-07 | 6 | 2024-09-23 | 2024-09-23 | 1 | 1 | 62 | 44 | 12 | 10 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | Both | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | 17 | 13 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-01 | 2022-12-01 | 2024-09-18 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 113343.4 | 15365.13 | Unknown | Unknown | 5961.61 | 92016.66 | 151537 | 88727.69 | 113343.4 | -24615.71 | Yes | N/A | N/A | 2022-12-01 | 2023-10-04 | 308 | 220 | 2023-10-04 | 2024-04-22 | 202 | 144 | 2023-10-19 | 2024-03-27 | 56 | 38 | 2023-06-21 | 2024-06-20 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | 2024-09-24 | 82 | 58 | 2024-09-18 | 2024-12-18 | 1900-04-01 | 66 | 2024-12-18 | 2024-12-18 | 1 | 1 | 364 | 258 | 447 | 319 | 811 | 577 | Steps 2,3,5,6,7 | 472 | 336 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-14 | -691 | -494 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | 2025-03-13 | IOU Designed & Installed | N/A | No | N/A | -29.51 | -19.12 | Unknown | Unknown | Unknown | -10.39 | 3981 | 1610.06 | -29.51 | 1639.57 | Yes | N/A | N/A | 2025-02-27 | 2025-02-27 | 1 | 1 | 2025-02-27 | 2025-02-27 | 1 | 1 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-03-13 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-03-25 | 1900-01-12 | 9 | 2025-03-25 | 2025-03-25 | 1 | 1 | 16 | 12 | 15 | 11 | 31 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-31 | -261 | -186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-05-16 | 2024-11-22 | IOU Designed & Installed | N/A | No | N/A | 1984.19 | 569.54 | Unknown | Unknown | Unknown | 1414.65 | 3981 | 1165.37 | 1984.19 | -818.82 | Yes | N/A | N/A | 2024-01-16 | 2024-05-16 | 122 | 88 | 2024-05-16 | 2024-05-16 | 1 | 1 | 2024-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-11-22 | 191 | 137 | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2024-12-13 | 1900-01-21 | 16 | 2024-12-13 | 2024-12-13 | 1 | 1 | 313 | 225 | 24 | 18 | 337 | 243 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 7.42 | 7.42 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-21 | 177 | 128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 0.24 | -3.64 | Unknown | Unknown | Unknown | 3.88 | 3981 | 637.91 | 0.24 | 637.67 | Yes | N/A | N/A | 2023-09-22 | 2023-09-22 | 1 | 1 | 2023-09-22 | 2023-09-22 | 1 | 1 | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | Unknown | Unknown | 2024-02-12 | 2023-12-15 | Unknown | Unknown | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-11 | -626 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-08-20 | 2024-09-04 | IOU Designed & Installed | N/A | No | N/A | 33.94 | Unknown | Unknown | Unknown | Unknown | 33.94 | 3981 | 1066.04 | 33.94 | 1032.1 | Yes | N/A | N/A | 2024-07-19 | 2024-08-16 | 29 | 21 | 2024-08-16 | 2024-08-20 | 5 | 3 | 2024-08-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-09-04 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-23 | 1900-01-19 | 14 | 2024-09-23 | 2024-09-23 | 1 | 1 | 45 | 33 | 26 | 18 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-27 | -290 | -207 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-14 | 2023-10-09 | IOU Designed & Installed | N/A | No | N/A | 20.64 | -5.12 | Unknown | Unknown | 20.47 | 5.29 | 0 | 898.21 | 20.64 | 877.57 | Yes | N/A | N/A | 2023-08-14 | 2023-08-03 | Unknown | Unknown | 2023-08-03 | 2023-10-20 | 79 | 57 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2023-10-09 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2024-10-10 | 1901-01-02 | 264 | 2024-10-10 | 2024-10-10 | 1 | 1 | 57 | 41 | 448 | 322 | 505 | 363 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-24 | 336 | 241 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 7155.35 | 1431.61 | Unknown | Unknown | 7.5 | 5716.24 | 103255 | 7143.66 | 7155.35 | -11.69 | Yes | N/A | N/A | 2023-09-18 | 2023-09-18 | 1 | 1 | 2023-09-18 | 2024-03-20 | 185 | 133 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2025-03-28 | 374 | 268 | Unknown | 2025-03-28 | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | 2025-05-06 | 2025-04-25 | Unknown | Unknown | 375 | 269 | 185 | 133 | 560 | 402 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-20 | -656 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | Unknown | 2024-07-01 | IOU Designed & Installed | N/A | No | N/A | 773.86 | 246.68 | Unknown | Unknown | Unknown | 527.18 | 3981 | 1055.91 | 773.86 | 282.05 | Yes | N/A | N/A | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | 2024-04-29 | 1 | 1 | 2024-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-07-01 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-07-03 | 1900-01-02 | 3 | 2024-07-03 | 2024-07-03 | 1 | 1 | 65 | 47 | 5 | 5 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA | 175.1 | 175.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-04 | -401 | -288 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1608.88 | Unknown | Unknown | Unknown | -1741 | 132.12 | Unknown | 2293.89 | -1608.88 | 3902.77 | Yes | N/A | N/A | 2024-11-13 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-12-13 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-12-04 | 21 | 15 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | 2025-01-27 | 2025-01-27 | 1 | 1 | 0 | 0 | 58 | 42 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 153.05 | 153.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -514 | -368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-05-17 | 2023-09-01 | IOU Designed & Installed | N/A | No | N/A | 21.74 | -4.85 | Unknown | Unknown | 24.19 | 2.4 | 3981 | 936.41 | 21.74 | 914.67 | Yes | N/A | N/A | 2023-05-17 | 2023-07-13 | 58 | 42 | 2023-07-13 | 2023-09-05 | 55 | 39 | 2023-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | 2023-09-01 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2025-08-14 | 1901-12-14 | 510 | 2025-08-14 | 2023-09-06 | Unknown | Unknown | 166 | 120 | 769 | 549 | 935 | 669 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-12-13 | 1403 | 1002 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2304.32 | -32.74 | Unknown | Unknown | -3509 | 1237.42 | Unknown | 3302.03 | -2304.32 | 5606.35 | Yes | N/A | N/A | 2023-06-06 | 2023-06-06 | 1 | 1 | 2023-06-06 | 2023-07-17 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | 2023-06-15 | 10 | 8 | 2023-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2023-10-16 | 1 | 1 | 1 | 1 | 53 | 39 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | -671 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | 2025-01-24 | IOU Designed & Installed | N/A | No | N/A | 20.1 | Unknown | Unknown | Unknown | Unknown | 20.1 | 3981 | 1223.14 | 20.1 | 1203.04 | Yes | N/A | N/A | 2023-12-18 | 2023-10-18 | Unknown | Unknown | 2023-10-18 | 2023-12-18 | 62 | 44 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2025-01-24 | 404 | 290 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-01-30 | 1900-01-06 | 5 | 2025-01-30 | 2025-01-29 | Unknown | Unknown | 404 | 290 | 69 | 49 | 473 | 339 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | 65 | 65 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-01 | -401 | -287 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-02-18 | 2025-06-16 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1247.19 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-09 | 2025-02-05 | 28 | 20 | 2025-02-05 | 2025-02-18 | 14 | 10 | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-06-16 | 119 | 85 | Unknown | 2025-06-10 | Unknown | Unknown | 2025-06-16 | 2025-06-26 | 1900-01-10 | 9 | 2025-06-26 | 2025-06-26 | 1 | 1 | 147 | 105 | 26 | 20 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-26 | -701 | -502 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-06 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | -3.95 | -16.48 | Unknown | Unknown | Unknown | 12.53 | 3981 | 1610.49 | -3.95 | 1614.44 | Yes | N/A | N/A | 2025-03-06 | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-03-06 | 3 | 3 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-03-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-03-27 | 1900-01-21 | 16 | 2025-03-27 | 2025-03-27 | 1 | 1 | 1 | 1 | 26 | 20 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-14 | -546 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-02-27 | 2023-04-21 | IOU Designed & Installed | N/A | No | N/A | 1096.08 | 365.56 | Unknown | 128.31 | Unknown | 602.21 | Unknown | 676.44 | 1096.08 | -419.64 | Yes | N/A | N/A | 2023-02-27 | 2023-03-06 | 8 | 6 | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-06 | 2023-04-21 | 47 | 35 | Unknown | Unknown | Unknown | Unknown | 2023-04-21 | 2023-05-18 | 1900-01-27 | 20 | 2023-05-18 | 2023-05-18 | 1 | 1 | 55 | 41 | 29 | 21 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-14 | -269 | -193 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-16 | 2023-03-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 451.35 | -7.41 | Unknown | Unknown | -483 | 941.76 | 0 | 482.64 | 451.35 | 31.29 | Yes | N/A | N/A | 2023-02-16 | 2023-03-14 | 27 | 19 | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | Unknown | Unknown | Unknown | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-03-20 | 1 | 1 | 27 | 19 | 1 | 1 | 28 | 20 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-09 | -233 | -168 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | 2023-09-18 | IOU Designed & Installed | N/A | No | N/A | 9660.39 | 2861.27 | Unknown | 1217.16 | Unknown | 5581.96 | Unknown | 1255.29 | 9660.39 | -8405.1 | Yes | N/A | N/A | 2023-05-19 | 2023-05-19 | 1 | 1 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2023-09-18 | 123 | 87 | Unknown | 2023-08-29 | Unknown | Unknown | 2023-09-18 | 2023-09-19 | 1900-01-01 | 2 | 2023-09-19 | 2023-09-19 | 1 | 1 | 124 | 88 | 3 | 3 | 127 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56, ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-18 | -549 | -394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | 669 | Unknown | Unknown | Unknown | Unknown | 669 | 3981 | 1578.54 | 669 | 909.54 | Yes | N/A | N/A | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | Unknown | Unknown | Unknown | 2025-01-14 | 2025-01-25 | 11 | 6 | 2025-01-09 | 2025-06-03 | 146 | 104 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-17 | 1900-01-14 | 11 | 2025-06-17 | 2025-06-17 | 1 | 1 | 147 | 105 | 28 | 19 | 175 | 124 | Steps 2,3,5,6,7 | 16 | 11 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 261 | 261 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-12 | -246 | -177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | 2024-03-15 | IOU Designed & Installed | N/A | No | N/A | 44782.42 | 7700.63 | Unknown | Unknown | -4711.36 | 41793.15 | 3981 | 33907.46 | 44782.42 | -10874.96 | Yes | N/A | N/A | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-11-16 | 2023-12-28 | 43 | 31 | 2023-11-17 | 2023-12-28 | 2 | 0 | 2023-12-28 | 2024-01-09 | 13 | 9 | 2023-12-28 | 2024-03-18 | 82 | 58 | 2024-01-10 | 2024-03-13 | 64 | 46 | 2024-03-15 | 2024-05-08 | 1900-02-23 | 39 | 2024-05-08 | 2024-04-10 | Unknown | Unknown | 85 | 59 | 175 | 125 | 260 | 184 | Steps 2,3,5,6,7 | 121 | 85 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | -572 | -409 | No | 2024-11-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | 2025-01-13 | IOU Designed & Installed | N/A | Yes | 78 | 16030.42 | 3849 | Unknown | 1000.45 | Unknown | 11180.97 | 3981 | 2066.24 | 16030.42 | -13964.18 | Yes | N/A | N/A | 2024-11-05 | 2025-01-27 | 84 | 60 | 2025-01-27 | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-01-27 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-13 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-02-28 | 1900-02-15 | 35 | 2025-02-28 | 2025-02-28 | 1 | 1 | 110 | 78 | 48 | 36 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 96 | 96 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-10 | -663 | -474 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-25 | 2025-04-15 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1608.36 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-25 | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-02-27 | 4 | 4 | 2025-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-15 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-04-19 | 1900-01-04 | 4 | 2025-04-19 | 2025-04-18 | Unknown | Unknown | 13 | 9 | 9 | 8 | 22 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 160.05 | 160.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-30 | -605 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-10-16 | 2023-10-24 | IOU Designed & Installed | N/A | No | N/A | 1406.37 | 494.4 | Unknown | Unknown | Unknown | 911.97 | 3241 | 989.53 | 1406.37 | -416.84 | Yes | N/A | N/A | 2023-09-29 | 2023-10-16 | 18 | 12 | 2023-10-16 | 2023-10-16 | 1 | 1 | 2023-10-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2023-10-24 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2023-11-03 | 1900-01-10 | 9 | 2023-11-03 | 2023-11-03 | 1 | 1 | 23 | 15 | 13 | 11 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | -489 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-12-17 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 503.85 | -26.38 | Unknown | Unknown | Unknown | 530.23 | 3981 | 2058.4 | 503.85 | 1554.55 | Yes | N/A | N/A | 2024-09-10 | 2024-12-17 | 99 | 71 | 2024-12-17 | 2024-12-17 | 1 | 1 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-03-18 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-04-07 | 1900-01-20 | 15 | 2025-04-07 | 2025-03-20 | Unknown | Unknown | 191 | 137 | 22 | 16 | 213 | 153 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-25 | -362 | -259 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2023-09-28 | IOU Designed & Installed | N/A | No | N/A | 3246.25 | 894.52 | Unknown | 556.08 | Unknown | 1795.65 | Unknown | 509.9 | 3246.25 | -2736.35 | Yes | N/A | N/A | 2023-09-27 | 2023-09-25 | Unknown | Unknown | 2023-09-25 | 2023-09-27 | 3 | 3 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-09-28 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-09-29 | 1900-01-01 | 2 | 2023-09-29 | 2023-09-29 | 1 | 1 | 2 | 2 | 6 | 6 | 8 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-18 | -227 | -164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 6.32 | Unknown | Unknown | Unknown | Unknown | 6.32 | Unknown | 506.24 | 6.32 | 499.92 | Yes | N/A | N/A | 2025-01-28 | 2025-01-24 | Unknown | Unknown | 2025-01-24 | 2025-01-28 | 5 | 3 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-01-28 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-03 | 1900-01-06 | 5 | 2025-02-03 | 2025-02-03 | 1 | 1 | 1 | 1 | 13 | 9 | 14 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | OCEANSIDE | N/A | 63.2 | 63.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-26 | 46 | 33 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-05-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4526.66 | Unknown | Unknown | Unknown | -497 | 5023.66 | Unknown | 496.51 | 4526.66 | -4030.15 | Yes | N/A | N/A | 2023-04-03 | 2023-05-22 | 50 | 36 | 2023-05-22 | 2023-11-03 | 166 | 120 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | Unknown | Unknown | 2024-03-12 | 2024-03-12 | 1 | 1 | 50 | 36 | 167 | 121 | 217 | 157 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-10 | -266 | -191 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-03 | 2024-03-03 | 2024-05-16 | IOU Designed & Installed | N/A | No | N/A | 246.74 | -12.97 | Unknown | Unknown | Unknown | 259.71 | 3981 | 766.01 | 246.74 | 519.27 | Yes | N/A | N/A | 2024-03-03 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-03-04 | 19 | 13 | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-05-16 | 74 | 54 | Unknown | 2024-05-16 | Unknown | Unknown | 2024-05-16 | 2024-05-20 | 1900-01-04 | 3 | 2024-05-20 | 2024-05-20 | 1 | 1 | 74 | 54 | 25 | 17 | 99 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 21.05 | 21.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-15 | -93 | -68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 226.73 | Unknown | Unknown | Unknown | 3.6 | 223.13 | 3981 | 1809.98 | 226.73 | 1583.25 | Yes | N/A | N/A | 2023-11-29 | 2024-05-21 | 175 | 125 | 2024-05-21 | 2024-05-21 | 1 | 1 | 2024-05-21 | Unknown | Unknown | Unknown | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | Unknown | Unknown | 2025-01-03 | 2025-05-14 | 132 | 94 | 175 | 125 | 134 | 96 | 309 | 221 | Steps 2,3,5,6,7 | 84 | 60 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 57 | 57 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-13 | -310 | -223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-10-23 | 2024-08-05 | IOU Designed & Installed | N/A | No | N/A | 867.68 | Unknown | Unknown | Unknown | 27.03 | 840.65 | 1000 | 725.76 | 867.68 | -141.92 | Yes | N/A | N/A | 2023-10-23 | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-12-14 | 123 | 89 | 2023-12-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2024-08-05 | 236 | 168 | Unknown | 2024-08-02 | Unknown | Unknown | 2024-08-05 | 2024-08-07 | 1900-01-02 | 3 | 2024-08-07 | 2024-08-07 | 1 | 1 | 236 | 168 | 127 | 93 | 363 | 261 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-27 | 14 | 11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-26 | 2022-10-26 | 2023-09-20 | IOU Designed & Installed | N/A | No | N/A | 2444.2 | 536.02 | Unknown | 866.71 | Unknown | 1041.47 | 3981 | 2046.95 | 2444.2 | -397.25 | Yes | N/A | N/A | 2022-10-26 | 2023-04-19 | 176 | 126 | 2023-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-19 | 2023-09-20 | 155 | 111 | Unknown | 2023-09-06 | Unknown | Unknown | 2023-09-20 | 2023-10-11 | 1900-01-21 | 16 | 2023-10-11 | 2023-10-11 | 1 | 1 | 331 | 237 | 23 | 17 | 354 | 254 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-07 | -606 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-03-10 | 2025-05-21 | IOU Designed & Installed | N/A | No | N/A | 533.27 | -11 | Unknown | Unknown | Unknown | 544.27 | 3981 | 2063.03 | 533.27 | 1529.76 | Yes | N/A | N/A | 2025-02-20 | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-03-10 | 21 | 15 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-05-21 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-06-11 | 1900-01-21 | 16 | 2025-06-11 | 2025-06-11 | 1 | 1 | 73 | 53 | 44 | 32 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-13 | -579 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 30.08 | Unknown | Unknown | Unknown | Unknown | 30.08 | 3981 | 1444.08 | 30.08 | 1414 | Yes | N/A | N/A | 2024-07-03 | 2024-07-02 | Unknown | Unknown | 2024-07-02 | 2024-07-09 | 8 | 6 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-10-29 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-11-11 | 1900-01-13 | 10 | 2024-11-11 | 2024-11-11 | 1 | 1 | 119 | 85 | 23 | 17 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-07 | -274 | -196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-13 | 2023-12-01 | IOU Designed & Installed | N/A | No | N/A | -820.64 | -5.02 | Unknown | Unknown | -821 | 5.38 | Unknown | 820.54 | -820.64 | 1641.18 | Yes | N/A | N/A | 2023-11-07 | 2023-10-02 | Unknown | Unknown | 2023-10-02 | 2023-11-13 | 43 | 31 | 2023-11-13 | 2023-12-01 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2023-12-01 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2023-12-08 | 1900-01-07 | 6 | 2023-12-08 | 2023-12-08 | 1 | 1 | 20 | 16 | 52 | 38 | 72 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 99 | 99 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-01 | -575 | -412 | No | 2022-03-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-15 | 2022-03-15 | 2025-05-02 | IOU Designed & Installed | N/A | Yes | 1127 | 9043.4 | 1535.21 | Unknown | 67.52 | 54.87 | 7385.8 | 3885 | 716.88 | 9043.4 | -8326.52 | Yes | N/A | N/A | 2022-03-15 | 2025-04-15 | 1128 | 806 | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-03-18 | 2025-05-02 | Unknown | Unknown | Unknown | 2025-05-01 | Unknown | Unknown | 2025-05-02 | 2025-05-05 | 1900-01-03 | 2 | 2025-05-05 | 2025-05-05 | 1 | 1 | 1128 | 806 | 5 | 3 | 1133 | 809 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 83 | 83 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-08 | -380 | -273 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-01-30 | 2024-07-05 | IOU Designed & Installed | N/A | No | N/A | 2997.12 | 467.13 | Unknown | Unknown | 14.92 | 2515.07 | 3981 | 1237.78 | 2997.12 | -1759.34 | Yes | N/A | N/A | 2024-01-30 | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2024-02-13 | 121 | 87 | 2024-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-07-05 | 136 | 98 | Unknown | 2024-06-27 | Unknown | Unknown | 2024-07-05 | 2024-07-24 | 1900-01-19 | 14 | 2024-07-24 | 2024-07-24 | 1 | 1 | 136 | 98 | 142 | 102 | 278 | 200 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-19 | 235 | 169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | 2024-06-10 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 14745.06 | 781.84 | Unknown | Unknown | 153.93 | 13809.29 | 44938 | 24221.53 | 14745.06 | 9476.47 | Yes | N/A | N/A | 2023-02-03 | 2023-05-12 | 99 | 71 | 2023-05-12 | 2023-12-20 | 223 | 159 | 2023-05-22 | 2023-06-21 | 31 | 23 | 2023-06-07 | 2024-07-18 | 363 | 261 | 2023-12-20 | Unknown | Unknown | Unknown | 2024-01-03 | 2024-06-06 | 156 | 112 | 2024-06-10 | 2024-07-11 | 1900-01-31 | 24 | 2024-07-11 | 2024-07-11 | 1 | 1 | 130 | 94 | 775 | 557 | 905 | 651 | Steps 2,3,5,6,7 | 437 | 313 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | POTRERO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-23 | -44 | -33 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | 2023-10-05 | IOU Designed & Installed | N/A | No | N/A | 550.89 | 189.35 | Unknown | 28.34 | Unknown | 333.2 | 3981 | 593.37 | 550.89 | 42.48 | Yes | N/A | N/A | 2023-08-23 | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-08-23 | 2 | 2 | 2023-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | 2023-10-05 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-10-09 | 1900-01-04 | 3 | 2023-10-09 | 2024-07-10 | 276 | 198 | 44 | 32 | 283 | 203 | 327 | 235 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-15 | -507 | -363 | No | 2023-04-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-10 | 2023-09-11 | IOU Designed & Installed | N/A | Yes | 158 | 507.53 | -13.32 | Unknown | Unknown | 86.86 | 433.99 | 3981 | 641.97 | 507.53 | 134.44 | Yes | N/A | N/A | 2023-04-10 | 2023-09-14 | 158 | 114 | 2023-09-14 | 2023-09-15 | 2 | 2 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | 2023-09-11 | 96 | 68 | Unknown | 2023-09-19 | Unknown | Unknown | 2023-09-11 | 2024-10-08 | 1901-01-28 | 282 | 2024-10-08 | 2023-09-27 | Unknown | Unknown | 254 | 182 | 396 | 284 | 650 | 466 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-11 | 311 | 222 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | 2024-03-13 | IOU Designed & Installed | N/A | No | N/A | 15882.51 | 13294.88 | Unknown | 989.57 | -6465 | 8063.06 | Unknown | 6465.48 | 15882.51 | -9417.03 | Yes | N/A | N/A | 2024-02-20 | 2024-03-05 | 15 | 11 | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-03-17 | 1900-01-04 | 3 | 2024-03-17 | 2024-03-17 | 1 | 0 | 15 | 11 | 6 | 3 | 21 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 130 | 130 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | -647 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-27 | 2024-08-15 | IOU Designed & Installed | N/A | No | N/A | 63.42 | Unknown | Unknown | Unknown | Unknown | 63.42 | 3981 | 1418.12 | 63.42 | 1354.7 | Yes | N/A | N/A | 2024-06-13 | 2024-06-26 | 14 | 10 | 2024-06-26 | 2024-06-28 | 3 | 3 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-08-15 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-08-21 | 1900-01-06 | 5 | 2024-08-21 | 2024-08-21 | 1 | 1 | 64 | 46 | 11 | 9 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-19 | 2025-03-28 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 196.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-19 | 2025-03-06 | Unknown | Unknown | 2025-03-06 | 2025-03-28 | 23 | 17 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-22 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-08 | 1900-01-16 | 13 | 2025-05-08 | 2025-05-08 | 1 | 1 | 26 | 18 | 41 | 31 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | SPRING VALLEY | 115.05 | 115.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | -660 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | 14.74 | -11.36 | Unknown | Unknown | Unknown | 26.1 | 3941 | 1024.02 | 14.74 | 1009.28 | Yes | N/A | N/A | 2024-06-25 | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-06-25 | 42 | 30 | 2024-06-25 | 2025-04-28 | 308 | 220 | 2024-07-30 | 2024-07-31 | 2 | 2 | 2024-06-25 | 2024-07-16 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-07-18 | 1900-01-02 | 3 | 2024-07-18 | 2024-07-17 | Unknown | Unknown | 330 | 236 | 47 | 35 | 377 | 271 | Steps 2,3,5,6,7 | 308 | 220 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | 13 | 13 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-04 | 32 | 25 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-18 | 2024-11-26 | IOU Designed & Installed | N/A | No | N/A | 1778.64 | Unknown | Unknown | Unknown | 37.55 | 1741.09 | 3981 | 798.56 | 1778.64 | -980.08 | Yes | N/A | N/A | 2024-03-13 | 2024-03-13 | 1 | 1 | 2024-03-13 | 2024-03-18 | 6 | 4 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | 2024-11-26 | 254 | 182 | Unknown | 2024-11-25 | Unknown | Unknown | 2024-11-26 | 2024-12-06 | 1900-01-10 | 9 | 2024-12-06 | 2024-12-06 | 1 | 1 | 255 | 183 | 18 | 14 | 273 | 197 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 204.1 | 204.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-15 | 119 | 86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1300.56 | -39.74 | Unknown | Unknown | Unknown | 1340.3 | 7962 | 2590.06 | 1300.56 | 1289.5 | Yes | N/A | N/A | 2024-03-07 | 2024-03-07 | 1 | 1 | 2024-03-07 | 2024-03-08 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-03-25 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | Unknown | Unknown | 2024-04-15 | 2024-04-12 | Unknown | Unknown | 19 | 13 | 2 | 2 | 21 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-14 | -451 | -322 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-10 | 2023-07-10 | 2023-07-25 | IOU Designed & Installed | N/A | No | N/A | -6.88 | -5.83 | Unknown | Unknown | Unknown | -1.05 | Unknown | 153.87 | -6.88 | 160.75 | Yes | N/A | N/A | 2023-07-10 | 2023-05-04 | Unknown | Unknown | 2023-05-04 | 2023-07-21 | 79 | 57 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-22 | 2023-07-25 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2024-01-19 | 1900-06-27 | 129 | 2024-01-19 | 2024-01-19 | 1 | 1 | 4 | 2 | 259 | 187 | 263 | 189 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-03 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2024-11-01 | 2025-01-06 | IOU Designed & Installed | N/A | No | N/A | 994.05 | Unknown | Unknown | Unknown | Unknown | 994.05 | 3981 | 770.94 | 994.05 | -223.11 | Yes | N/A | N/A | 2024-10-31 | 2024-11-01 | 2 | 2 | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2025-01-06 | 67 | 47 | Unknown | 2024-12-19 | Unknown | Unknown | 2025-01-06 | 2025-01-22 | 1900-01-16 | 13 | 2025-01-22 | 2025-01-22 | 1 | 1 | 69 | 49 | 19 | 15 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-25 | -546 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-21 | 2024-12-21 | 2025-02-13 | IOU Designed & Installed | N/A | No | N/A | 437.76 | -8.05 | Unknown | Unknown | Unknown | 445.81 | 3981 | 1962.61 | 437.76 | 1524.85 | Yes | N/A | N/A | 2024-12-21 | 2024-12-20 | Unknown | Unknown | 2024-12-20 | 2024-12-21 | 2 | 1 | 2024-12-21 | Unknown | Unknown | Unknown | 2024-12-21 | 2025-01-30 | 41 | 29 | 2024-12-21 | 2025-02-13 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-02-25 | 1900-01-12 | 9 | 2025-02-25 | 2025-02-25 | 1 | 1 | 55 | 39 | 57 | 40 | 112 | 79 | Steps 2,3,5,6,7 | 40 | 28 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-15 | 37 | 27 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2024-12-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 46.21 | Unknown | Unknown | Unknown | Unknown | 46.21 | Unknown | 7076.28 | 46.21 | 7030.07 | Yes | N/A | N/A | 2024-12-16 | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2025-01-09 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | 2025-01-21 | 2025-01-21 | 1 | 1 | 0 | 0 | 67 | 49 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 61.05 | 61.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | -539 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-14 | 2025-03-26 | IOU Designed & Installed | N/A | No | N/A | 2764.21 | 606.24 | Unknown | 425.45 | Unknown | 1732.52 | 3981 | 1092.9 | 2764.21 | -1671.31 | Yes | N/A | N/A | 2024-10-14 | 2024-09-27 | Unknown | Unknown | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2025-03-26 | 164 | 118 | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-03-27 | 1900-01-01 | 2 | 2025-03-27 | 2025-03-27 | 1 | 1 | 164 | 118 | 3 | 3 | 167 | 121 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Commercial | Underserved Community | El Cajon | El Cajon | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | 30 | 23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-05-07 | 2024-10-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 22826.53 | 34766.87 | Unknown | 3380.92 | -81156 | 65834.74 | Unknown | 87742.85 | 22826.53 | 64916.32 | Yes | N/A | N/A | 2024-03-20 | 2024-05-15 | 57 | 41 | 2024-05-15 | 2024-10-09 | 148 | 106 | 2024-05-28 | 2025-04-28 | 246 | 176 | 2024-10-04 | 2024-10-16 | 13 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2024-10-31 | 1900-01-06 | 5 | 2024-10-31 | 2024-10-31 | 1 | 1 | 303 | 217 | 169 | 119 | 472 | 336 | Steps 2,3,5,6,7 | 340 | 242 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-07 | -192 | -139 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.83 | -5.45 | Unknown | Unknown | Unknown | 3.62 | 3885 | 493.4 | -1.83 | 495.23 | Yes | N/A | N/A | 2023-02-09 | 2023-02-09 | 1 | 1 | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | Unknown | Unknown | 2023-03-03 | 2023-02-27 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 109 | 109 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-27 | -705 | -504 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | 2025-01-14 | IOU Designed & Installed | N/A | No | N/A | 904.38 | 385.62 | Unknown | Unknown | Unknown | 518.76 | 11943 | 1032.11 | 904.38 | 127.73 | Yes | N/A | N/A | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | 2024-11-21 | 11 | 9 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2025-01-14 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-01-21 | 1900-01-07 | 6 | 2025-01-21 | 2025-01-21 | 1 | 1 | 56 | 40 | 20 | 16 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | SD 1189-J2 PA2 WO2 (E) | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 769 | 550 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-07-05 | 2025-04-26 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 37006.55 | 8755.55 | Unknown | 988.52 | 2031.03 | 25231.45 | 0 | 30226.89 | 37006.55 | -6779.66 | Yes | N/A | N/A | 2022-04-27 | 2023-05-01 | 370 | 264 | 2023-05-01 | 2023-09-11 | 134 | 96 | 2023-05-23 | 2024-04-08 | 243 | 175 | 2023-09-12 | 2023-10-31 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-26 | 2025-04-27 | 1900-01-01 | 0 | 2025-04-27 | 2025-04-27 | 1 | 0 | 613 | 439 | 187 | 132 | 800 | 571 | Steps 2,3,5,6,7 | 320 | 228 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 115.05 | 115.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-06 | -393 | -282 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-06-28 | 2024-12-23 | IOU Designed & Installed | N/A | No | N/A | 339.93 | -6.89 | Unknown | Unknown | Unknown | 346.82 | Unknown | 1049.43 | 339.93 | 709.5 | Yes | N/A | N/A | 2024-06-28 | 2024-06-28 | 1 | 1 | 2024-06-28 | 2024-06-28 | 1 | 1 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-12-23 | 179 | 127 | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-02-06 | 1900-02-14 | 34 | 2025-02-06 | 2025-02-06 | 1 | 1 | 180 | 128 | 48 | 36 | 228 | 164 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-14 | -663 | -474 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-18 | 2025-03-19 | 2025-04-15 | IOU Designed & Installed | N/A | No | N/A | 1214.68 | -21.54 | Unknown | Unknown | Unknown | 1236.22 | 3981 | 1851.52 | 1214.68 | 636.84 | Yes | N/A | N/A | 2025-03-18 | 2025-03-19 | 2 | 2 | 2025-03-19 | 2025-03-19 | 1 | 1 | 2025-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-04-15 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-04-22 | 1900-01-07 | 6 | 2025-04-22 | 2025-04-22 | 1 | 1 | 30 | 22 | 10 | 8 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -478 | -343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-08-05 | 2025-01-06 | IOU Designed & Installed | N/A | No | N/A | 35.09 | Unknown | Unknown | Unknown | Unknown | 35.09 | 3981 | 1521.7 | 35.09 | 1486.61 | Yes | N/A | N/A | 2024-07-09 | 2024-06-06 | Unknown | Unknown | 2024-06-06 | 2024-08-05 | 61 | 43 | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2025-01-06 | 155 | 111 | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-01-22 | 1900-01-16 | 13 | 2025-01-22 | 2025-01-22 | 1 | 1 | 155 | 111 | 79 | 57 | 234 | 168 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | -584 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-05 | 2024-03-13 | IOU Designed & Installed | N/A | No | N/A | -6.74 | -6.52 | Unknown | Unknown | Unknown | -0.22 | 3981 | 163.83 | -6.74 | 170.57 | Yes | N/A | N/A | 2024-02-05 | 2024-02-07 | 3 | 3 | 2024-02-07 | 2024-02-16 | 10 | 8 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-03-13 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-04-10 | 1900-01-28 | 21 | 2024-04-10 | 2024-04-10 | 1 | 1 | 30 | 22 | 40 | 30 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 108 | 108 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-12 | -100 | -73 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-01-19 | 2024-08-27 | IOU Designed & Installed | N/A | No | N/A | 22.49 | Unknown | Unknown | Unknown | Unknown | 22.49 | 3981 | 643.06 | 22.49 | 620.57 | Yes | N/A | N/A | 2024-01-19 | 2023-12-28 | Unknown | Unknown | 2023-12-28 | 2024-01-19 | 23 | 17 | 2024-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-08-27 | 222 | 158 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-03 | 1900-01-07 | 6 | 2024-09-03 | 2024-09-03 | 1 | 1 | 222 | 158 | 32 | 24 | 254 | 182 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-03 | 207 | 148 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-09-26 | 2025-02-12 | IOU Designed & Installed | N/A | No | N/A | 3827.47 | 869.3 | Unknown | 109.73 | -1596.65 | 4445.09 | Unknown | 1519.35 | 3827.47 | -2308.12 | Yes | N/A | N/A | 2024-09-26 | 2024-09-30 | 5 | 3 | 2024-09-30 | 2024-11-05 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2025-02-04 | 92 | 66 | Unknown | 2025-02-12 | Unknown | Unknown | 2025-02-12 | 2025-02-27 | 1900-01-15 | 12 | 2025-02-27 | 2025-02-26 | Unknown | Unknown | 97 | 69 | 53 | 39 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 303 | 303 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | 283 | 202 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2025-03-07 | IOU Designed & Installed | N/A | No | N/A | 41396.92 | 10725.11 | Unknown | Unknown | Unknown | 30671.81 | 58342 | 21783.38 | 41396.92 | -19613.54 | Yes | N/A | N/A | 2024-01-09 | 2023-12-13 | Unknown | Unknown | 2023-12-13 | 2024-01-23 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-01-23 | 2025-02-28 | 403 | 289 | Unknown | 2025-02-24 | Unknown | Unknown | 2025-03-07 | 2025-03-17 | 1900-01-10 | 7 | 2025-03-17 | 2025-03-11 | Unknown | Unknown | 403 | 289 | 54 | 38 | 457 | 327 | Steps 2,3,5,6,7 | 231 | 165 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 184.05 | 184.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-10 | 451 | 322 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 80685.3 | 15532.04 | Unknown | Unknown | -15939.76 | 81093.02 | 2435 | 26269.77 | 80685.3 | -54415.53 | Yes | N/A | N/A | 2023-03-14 | 2023-03-14 | 1 | 1 | 2023-03-14 | 2024-01-10 | 303 | 217 | 2024-01-09 | 2024-03-29 | 2 | 2 | 2023-08-28 | 2024-01-18 | 26 | 20 | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | Unknown | Unknown | 2024-05-06 | 2024-05-06 | 1 | 1 | 3 | 3 | 330 | 238 | 333 | 241 | Steps 2,3,5,6,7 | 223 | 161 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-18 | -556 | -399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 1809.24 | -35.76 | Unknown | Unknown | Unknown | 1845 | 3981 | 1641.81 | 1809.24 | -167.43 | Yes | N/A | N/A | 2024-11-14 | 2024-11-14 | 1 | 1 | 2024-11-14 | 2024-11-14 | 1 | 1 | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-11-15 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-09 | 1900-01-24 | 17 | 2024-12-09 | 2024-12-09 | 1 | 1 | 3 | 3 | 27 | 19 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-02 | 182 | 131 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | 2023-11-30 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 650.52 | -24.05 | Unknown | Unknown | Unknown | 674.57 | 3981 | 943.97 | 650.52 | 293.45 | Yes | N/A | N/A | 2023-11-30 | 2023-11-30 | 1 | 1 | 2023-11-30 | 2023-11-30 | 1 | 1 | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2024-03-25 | 117 | 83 | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-04-02 | 1900-01-08 | 7 | 2024-04-02 | 2024-04-01 | Unknown | Unknown | 118 | 84 | 10 | 8 | 128 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-25 | -463 | -332 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-08-30 | 2023-12-20 | IOU Designed & Installed | N/A | No | N/A | 1013.19 | -27.9 | Unknown | Unknown | Unknown | 1041.09 | Unknown | Not available | 1013.19 | Unknown | Yes | N/A | N/A | 2023-08-30 | 2023-08-31 | 2 | 2 | 2023-08-31 | 2023-09-17 | 18 | 12 | 2023-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-17 | 2023-12-20 | 95 | 68 | Unknown | 2023-12-20 | Unknown | Unknown | 2023-12-20 | 2024-01-18 | 1900-01-29 | 22 | 2024-01-18 | 2024-01-18 | 1 | 1 | 97 | 70 | 49 | 35 | 146 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-01 | 550 | 394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | 2023-10-30 | IOU Designed & Installed | N/A | No | N/A | 10999.57 | Unknown | Unknown | Unknown | -377 | 11376.57 | Unknown | 430.61 | 10999.57 | -10568.96 | Yes | N/A | N/A | 2023-09-18 | 2023-10-11 | 24 | 18 | 2023-10-11 | 2023-10-25 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | 2023-10-27 | 3 | 3 | Unknown | 2023-10-26 | Unknown | Unknown | 2023-10-30 | 2023-11-06 | 1900-01-07 | 6 | 2023-11-06 | 2023-11-02 | Unknown | Unknown | 27 | 21 | 23 | 17 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-05 | 193 | 138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-01-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6429.71 | Unknown | Unknown | Unknown | Unknown | 6429.71 | 3981 | 586.31 | 6429.71 | -5843.4 | Yes | N/A | N/A | 2024-01-26 | 2024-04-23 | 89 | 63 | 2024-04-23 | 2024-04-25 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-12-19 | 239 | 171 | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-04-16 | 10 | 8 | 328 | 234 | 13 | 11 | 341 | 245 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | -592 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | 2024-06-28 | IOU Designed & Installed | N/A | No | N/A | 1081.59 | -15.78 | Unknown | Unknown | 7.74 | 1089.63 | 3981 | 1113.94 | 1081.59 | 32.35 | Yes | N/A | N/A | 2024-04-16 | 2024-04-18 | 3 | 3 | 2024-04-18 | 2024-04-22 | 5 | 3 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-06-28 | 68 | 50 | Unknown | 2025-03-05 | Unknown | Unknown | 2024-06-28 | 2024-07-15 | 1900-01-17 | 12 | 2024-07-15 | 2024-07-15 | 1 | 1 | 71 | 53 | 24 | 16 | 95 | 69 | Steps 2,3,5,6,7 | 250 | 178 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-11 | 182 | 131 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2024-01-24 | 2024-04-01 | IOU Designed & Installed | N/A | No | N/A | 11.89 | -10.54 | Unknown | Unknown | Unknown | 22.43 | 3981 | 910.75 | 11.89 | 898.86 | Yes | N/A | N/A | 2023-12-26 | 2023-10-14 | Unknown | Unknown | 2023-10-14 | 2024-01-24 | 103 | 73 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-04-01 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-04-11 | 1900-01-10 | 9 | 2024-04-11 | 2024-04-10 | Unknown | Unknown | 69 | 49 | 114 | 82 | 183 | 131 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 510.05 | 510.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | 115 | 82 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | 2023-11-03 | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | 30.15 | Unknown | Unknown | Unknown | Unknown | 30.15 | 3981 | 934.48 | 30.15 | 904.33 | Yes | N/A | N/A | 2023-11-03 | 2023-11-03 | 1 | 1 | 2023-11-03 | 2023-11-03 | 1 | 1 | 2023-11-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | 2024-09-03 | 306 | 218 | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-09-17 | 1900-01-14 | 11 | 2024-09-17 | 2024-09-23 | 7 | 5 | 307 | 219 | 23 | 17 | 330 | 236 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2273.27 | 2273.27 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-02-27 | -89 | -64 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-04-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3.53 | -48 | Unknown | Unknown | Unknown | 51.53 | 99525 | 657.36 | 3.53 | 653.83 | Yes | N/A | N/A | 2023-04-24 | 2023-04-24 | 1 | 1 | 2023-04-24 | 2023-05-09 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-09 | 2023-11-06 | 182 | 130 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2023-11-30 | Unknown | Unknown | 183 | 131 | 16 | 12 | 199 | 143 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-26 | -638 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | 2024-06-13 | IOU Designed & Installed | N/A | No | N/A | 2260.7 | -14.03 | Unknown | Unknown | Unknown | 2274.73 | 3981 | 919.34 | 2260.7 | -1341.36 | Yes | N/A | N/A | 2024-05-20 | 2024-03-29 | Unknown | Unknown | 2024-03-29 | 2024-05-20 | 53 | 37 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-06-13 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-06-26 | 1900-01-13 | 10 | 2024-06-26 | 2024-06-26 | 1 | 1 | 25 | 19 | 68 | 48 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-10 | -383 | -274 | No | 2022-04-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-07 | 2022-04-07 | Unknown | IOU Designed & Installed | N/A | Yes | 706 | 2772.14 | Unknown | Unknown | Unknown | 133.86 | 2638.28 | 3885 | 1049.77 | 2772.14 | -1722.37 | Yes | N/A | N/A | 2022-04-07 | 2024-03-13 | 707 | 505 | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-05-04 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | Unknown | 2025-02-19 | Unknown | Unknown | 2025-02-19 | 2025-02-20 | 2 | 2 | 707 | 505 | 2 | 2 | 709 | 507 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-04 | -633 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 2025-05-29 | IOU Designed & Installed | N/A | No | N/A | 2045.62 | 1230.57 | Unknown | Unknown | Unknown | 815.05 | Unknown | 118.25 | 2045.62 | -1927.37 | Yes | N/A | N/A | 2025-04-07 | 2025-05-02 | 26 | 20 | 2025-05-02 | 2025-05-16 | 15 | 11 | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-05-29 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-09 | 1900-01-11 | 8 | 2025-06-09 | 2025-06-09 | 1 | 1 | 40 | 30 | 28 | 20 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5.05 | 5.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | -687 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-31 | 2025-03-31 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | 325.28 | -6.54 | Unknown | Unknown | Unknown | 331.82 | 3981 | 1621.67 | 325.28 | 1296.39 | Yes | N/A | N/A | 2025-03-31 | 2025-03-31 | 1 | 1 | 2025-03-31 | 2025-03-31 | 1 | 1 | 2025-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-09 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-17 | 1900-01-08 | 7 | 2025-04-17 | 2025-04-17 | 1 | 1 | 11 | 9 | 11 | 9 | 22 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-05 | -566 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-20 | 2024-12-04 | IOU Designed & Installed | N/A | No | N/A | 1195.43 | Unknown | Unknown | Unknown | 5.75 | 1189.68 | Unknown | 1514.86 | 1195.43 | 319.43 | Yes | N/A | N/A | 2024-08-07 | 2024-08-14 | 8 | 6 | 2024-08-14 | 2024-10-11 | 59 | 43 | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-12-04 | 55 | 39 | Unknown | 2024-12-02 | Unknown | Unknown | 2024-12-04 | 2024-12-16 | 1900-01-12 | 9 | 2024-12-16 | 2024-12-16 | 1 | 1 | 63 | 45 | 73 | 53 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-14 | -482 | -345 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | 2024-11-11 | IOU Designed & Installed | N/A | No | N/A | 36.16 | Unknown | Unknown | Unknown | Unknown | 36.16 | 3981 | 1634.63 | 36.16 | 1598.47 | Yes | N/A | N/A | 2024-09-25 | 2024-06-17 | Unknown | Unknown | 2024-06-17 | 2024-09-26 | 102 | 74 | 2024-09-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-11-11 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2024-12-18 | 1900-02-06 | 28 | 2024-12-18 | 2024-12-18 | 1 | 1 | 47 | 33 | 141 | 103 | 188 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | 357 | 357 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-20 | 3 | 3 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-24 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | 4.15 | Unknown | Unknown | Unknown | Unknown | 4.15 | 3981 | 1015.58 | 4.15 | 1011.43 | Yes | N/A | N/A | 2024-07-24 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-07-24 | 8 | 6 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-10-21 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-10-24 | 1900-01-03 | 4 | 2024-10-24 | 2024-10-23 | Unknown | Unknown | 90 | 64 | 12 | 10 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-18 | -611 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-03 | 2024-08-01 | IOU Designed & Installed | N/A | No | N/A | 956.66 | Unknown | Unknown | Unknown | 3.93 | 952.73 | Unknown | 1319.03 | 956.66 | 362.37 | Yes | N/A | N/A | 2024-06-03 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-06-13 | 57 | 41 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-08-01 | 50 | 36 | Unknown | 2024-07-30 | Unknown | Unknown | 2024-08-01 | 2024-08-15 | 1900-01-14 | 11 | 2024-08-15 | 2024-08-15 | 1 | 1 | 50 | 36 | 73 | 53 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-06 | -428 | -306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-04 | 2022-10-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 31.93 | -6.78 | Unknown | Unknown | Unknown | 38.71 | Unknown | 95.13 | 31.93 | 63.2 | Yes | N/A | N/A | 2022-10-04 | 2023-03-14 | 162 | 116 | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | Unknown | Unknown | 2023-05-05 | 2023-05-05 | 1 | 1 | 162 | 116 | 1 | 1 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 129.05 | 129.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-08 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-07 | 2024-11-21 | IOU Designed & Installed | N/A | No | N/A | 605.43 | -11.8 | Unknown | Unknown | Unknown | 617.23 | 3981 | 1534.53 | 605.43 | 929.1 | Yes | N/A | N/A | 2024-11-07 | 2024-11-07 | 1 | 1 | 2024-11-07 | 2024-11-07 | 1 | 1 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-11-21 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-12-12 | 1900-01-21 | 16 | 2024-12-12 | 2024-12-12 | 1 | 1 | 16 | 12 | 24 | 18 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 72 | 72 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | 80 | 57 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-24 | 2025-03-06 | 2025-05-05 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1699.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-24 | 2025-02-07 | Unknown | Unknown | 2025-02-07 | 2025-03-06 | 28 | 20 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-05-05 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | 2025-05-16 | 1900-01-11 | 10 | 2025-05-16 | 2025-05-13 | Unknown | Unknown | 61 | 43 | 40 | 30 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-11 | 60 | 43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-17 | 2024-01-16 | 2024-03-07 | IOU Designed & Installed | N/A | No | N/A | 643.64 | -22.16 | Unknown | Unknown | Unknown | 665.8 | 3981 | 1165.66 | 643.64 | 522.02 | Yes | N/A | N/A | 2023-12-17 | 2023-11-27 | Unknown | Unknown | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2024-03-06 | 7 | 5 | 2024-01-16 | 2024-03-07 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-03-08 | 1900-01-01 | 2 | 2024-03-08 | 2024-03-11 | 4 | 2 | 52 | 38 | 13 | 9 | 65 | 47 | Steps 2,3,5,6,7 | 50 | 36 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-02 | -412 | -295 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2023-12-26 | 2024-08-07 | IOU Designed & Installed | N/A | No | N/A | 306.58 | Unknown | Unknown | Unknown | -1277 | 1583.58 | Unknown | 1277.24 | 306.58 | 970.66 | Yes | N/A | N/A | 2023-12-26 | 2023-10-17 | Unknown | Unknown | 2023-10-17 | 2024-02-12 | 119 | 85 | 2024-02-12 | 2024-02-22 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-08-07 | 1 | 1 | Unknown | 2024-07-30 | Unknown | Unknown | 2024-08-07 | 2024-08-16 | 1900-01-09 | 8 | 2024-08-16 | 2024-08-16 | 1 | 1 | 12 | 10 | 130 | 94 | 142 | 104 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | BOULEVARD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-10 | -349 | -250 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-03-23 | IOU Designed & Installed | N/A | No | N/A | 1215.83 | 387.94 | Unknown | 176.2 | Unknown | 651.69 | Unknown | 389.6 | 1215.83 | -826.23 | Yes | N/A | N/A | 2023-03-20 | 2023-03-20 | 1 | 1 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | 2023-03-23 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | 2023-03-27 | 1900-01-04 | 3 | 2023-03-27 | 2023-03-27 | 1 | 1 | 5 | 5 | 6 | 4 | 11 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-29 | 300 | 215 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-07-28 | 2024-06-20 | IOU Designed & Installed | N/A | No | N/A | 83871.87 | 28910.77 | Unknown | Unknown | 114.59 | 54846.51 | 142027 | 25383.46 | 83871.87 | -58488.41 | Yes | N/A | N/A | 2023-05-02 | 2023-07-07 | 67 | 49 | 2023-07-07 | Unknown | Unknown | Unknown | 2023-08-22 | 2024-02-06 | 3 | 3 | 2023-11-10 | 2023-11-17 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | 2024-06-20 | 2024-07-25 | 1900-02-04 | 26 | 2024-07-25 | 2024-07-25 | 1 | 1 | 70 | 52 | 45 | 33 | 115 | 85 | Steps 2,3,5,6,7 | 88 | 62 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 153 | 153 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | -247 | -177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-09-05 | 2025-01-14 | IOU Designed & Installed | N/A | No | N/A | 21712.91 | 3500.99 | Unknown | Unknown | -5859.51 | 24071.43 | 3981 | 14333.52 | 21712.91 | -7379.39 | Yes | N/A | N/A | 2024-05-01 | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-09-05 | 191 | 137 | 2024-09-05 | 2024-10-16 | 42 | 30 | 2024-11-18 | 2024-11-26 | 9 | 7 | 2024-10-16 | 2025-01-14 | 91 | 65 | Unknown | 2024-11-13 | Unknown | Unknown | 2025-01-14 | 2025-02-13 | 1900-01-30 | 23 | 2025-02-13 | 2025-01-30 | Unknown | Unknown | 133 | 95 | 231 | 167 | 364 | 262 | Steps 2,3,5,6,7 | 41 | 29 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-28 | -464 | -333 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | 2023-02-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -18.77 | -13.61 | Unknown | Unknown | Unknown | -5.16 | 3991 | 671.41 | -18.77 | 690.18 | Yes | N/A | N/A | 2023-02-10 | 2023-02-10 | 1 | 1 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-08-22 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | 87 | 87 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-16 | 966 | 691 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 17143.37 | 304.36 | Unknown | Unknown | -1214.8 | 18053.81 | 258689 | 6464.14 | 17143.37 | -10679.23 | Yes | N/A | N/A | 2024-02-02 | 2024-02-02 | 1 | 1 | 2024-02-02 | 2024-03-01 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-04-08 | 12 | 8 | 2024-03-01 | 2024-07-10 | 132 | 94 | Unknown | 2024-07-10 | Unknown | Unknown | 2024-07-30 | 2024-08-12 | 1900-01-13 | 10 | 2024-08-12 | 2024-08-08 | Unknown | Unknown | 133 | 95 | 55 | 39 | 188 | 134 | Steps 2,3,5,6,7 | 38 | 26 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 80 | 80 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-18 | -444 | -319 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-03 | 2024-07-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1993.72 | -15.16 | Unknown | Unknown | 20.78 | 1988.1 | 3981 | 1278.82 | 1993.72 | -714.9 | Yes | N/A | N/A | 2024-07-03 | 2024-07-31 | 29 | 21 | 2024-07-31 | 2024-08-09 | 10 | 8 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | 2025-03-31 | 2025-03-31 | 1 | 1 | 29 | 21 | 11 | 9 | 40 | 30 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-01 | -47 | -34 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-18 | 2024-09-13 | IOU Designed & Installed | N/A | No | N/A | -24813.57 | 892.16 | Unknown | 166.04 | -27728 | 1856.23 | Unknown | 30163.55 | -24813.57 | 54977.12 | Yes | N/A | N/A | 2024-01-17 | 2024-01-21 | 5 | 3 | 2024-01-21 | 2024-06-13 | 145 | 104 | 2024-01-24 | 2024-06-07 | 111 | 81 | 2024-06-10 | 2024-07-12 | 33 | 25 | 2024-06-13 | Unknown | Unknown | Unknown | 2024-08-07 | 2024-10-04 | 59 | 43 | 2024-09-13 | 2024-10-15 | 1900-02-01 | 23 | 2024-10-15 | 2024-10-15 | 1 | 1 | 116 | 84 | 271 | 196 | 387 | 280 | Steps 2,3,5,6,7 | 191 | 137 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 31 | 31 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-27 | -246 | -177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-03 | 2024-10-04 | IOU Designed & Installed | N/A | No | N/A | 1080.86 | Unknown | Unknown | Unknown | 15.27 | 1065.59 | 3981 | 1066.08 | 1080.86 | -14.78 | Yes | N/A | N/A | 2024-04-02 | 2024-05-30 | 59 | 43 | 2024-05-30 | 2024-06-21 | 23 | 17 | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-10-04 | 106 | 76 | Unknown | 2024-10-03 | Unknown | Unknown | 2024-10-04 | 2024-10-24 | 1900-01-20 | 15 | 2024-10-24 | 2024-10-24 | 1 | 1 | 165 | 119 | 45 | 33 | 210 | 152 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-14 | -676 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 106.74 | -1.5 | Unknown | Unknown | Unknown | 108.24 | 3981 | 1545.38 | 106.74 | 1438.64 | Yes | N/A | N/A | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-01-27 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-02-06 | 1900-01-10 | 9 | 2025-02-06 | 2025-02-06 | 1 | 1 | 41 | 29 | 13 | 11 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-28 | 206 | 149 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | 2023-02-10 | 2023-09-21 | IOU Designed & Installed | N/A | No | N/A | 676.73 | -6.71 | Unknown | Unknown | 13.87 | 669.57 | 3981 | 1034.7 | 676.73 | 357.97 | Yes | N/A | N/A | 2023-02-10 | 2023-03-07 | 26 | 18 | 2023-03-07 | Unknown | Unknown | Unknown | 2023-06-20 | 2023-06-20 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-09-21 | 84 | 60 | Unknown | 2023-09-19 | Unknown | Unknown | 2023-09-21 | 2023-09-22 | 1900-01-01 | 2 | 2023-09-22 | 2023-09-22 | 1 | 1 | 111 | 79 | 3 | 3 | 114 | 82 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-27 | 91 | 66 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-09-05 | 2023-10-05 | IOU Designed & Installed | N/A | No | N/A | 15.42 | -3.92 | Unknown | Unknown | 15.29 | 4.05 | 0 | 759.93 | 15.42 | 744.51 | Yes | N/A | N/A | 2023-08-30 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2023-09-05 | 70 | 50 | 2023-09-05 | Unknown | Unknown | Unknown | 2023-09-05 | 2023-09-15 | 11 | 9 | 2023-09-05 | 2023-10-05 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2024-09-26 | 1900-12-23 | 256 | 2024-09-26 | 2024-09-26 | 1 | 1 | 31 | 23 | 440 | 316 | 471 | 339 | Steps 2,3,5,6,7 | 10 | 8 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-14 | -69 | -50 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | 2025-04-06 | IOU Designed & Installed | N/A | No | N/A | -3019.84 | 1134.24 | Unknown | 103.97 | -4742 | 483.95 | Unknown | 4741.58 | -3019.84 | 7761.42 | Yes | N/A | N/A | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-06 | 2025-04-06 | 1899-12-31 | 0 | 2025-04-06 | 2025-04-06 | 1 | 0 | 1 | 1 | 2 | 0 | 3 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | 357 | 357 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-20 | 3 | 3 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-24 | 2024-10-07 | IOU Designed & Installed | N/A | No | N/A | 7718.84 | 714.57 | Unknown | 1248.99 | 43.93 | 5711.35 | 3981 | 1416.22 | 7718.84 | -6302.62 | Yes | N/A | N/A | 2024-07-24 | 2024-07-12 | Unknown | Unknown | 2024-07-12 | 2024-07-24 | 13 | 9 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-10-07 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-24 | 1900-01-17 | 14 | 2024-10-24 | 2024-10-23 | Unknown | Unknown | 76 | 54 | 31 | 23 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | -367 | -264 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 0 | Unknown | Unknown | Unknown | Unknown | Unkonwn | Unknown | 1703.27 | Unknown | 1703.27 | Yes | N/A | N/A | 2024-03-27 | 2024-03-27 | 1 | 1 | 2024-03-27 | 2024-08-05 | 132 | 94 | 2024-08-05 | Unknown | Unknown | Unknown | 2024-08-05 | 2024-08-20 | 16 | 12 | 2024-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | 2025-01-27 | 2025-01-27 | 1 | 1 | 1 | 1 | 149 | 107 | 150 | 108 | Steps 2,3,5,6,7 | 146 | 104 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-13 | -708 | -507 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-21 | 2025-01-21 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 68.79 | -0.63 | Unknown | Unknown | Unknown | 69.42 | 3981 | 1846.19 | 68.79 | 1777.4 | Yes | N/A | N/A | 2025-01-21 | 2025-01-21 | 1 | 1 | 2025-01-21 | 2025-01-21 | 1 | 1 | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | 2025-01-28 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-04 | 1900-01-07 | 6 | 2025-02-04 | 2025-02-04 | 1 | 1 | 9 | 7 | 10 | 8 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | CORONADO | 2376.1 | 2376.1 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-04-17 | -609 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-05-28 | 2024-11-22 | IOU Designed & Installed | N/A | No | N/A | 281.47 | -26.87 | Unknown | Unknown | -1105.81 | 1414.15 | 3981 | 1959.98 | 281.47 | 1678.51 | Yes | N/A | N/A | 2024-05-28 | 2024-05-28 | 1 | 1 | 2024-05-28 | 2024-05-28 | 1 | 1 | 2024-05-28 | 2024-05-30 | 3 | 3 | 2024-05-28 | 2024-12-02 | 21 | 15 | 2024-05-30 | 2024-11-22 | 177 | 127 | Unknown | 2024-08-01 | Unknown | Unknown | 2024-11-22 | 2024-12-02 | 1900-01-10 | 7 | 2024-12-02 | 2024-08-16 | Unknown | Unknown | 181 | 131 | 33 | 23 | 214 | 154 | Steps 2,3,5,6,7 | 188 | 134 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 55.05 | 55.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-05 | -659 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-02-12 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 1405.37 | -28.23 | Unknown | Unknown | Unknown | 1433.6 | 3981 | 1605.77 | 1405.37 | 200.4 | Yes | N/A | N/A | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-14 | 29 | 21 | 2025-02-12 | 2025-03-17 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-04-17 | 1900-01-31 | 24 | 2025-04-17 | 2025-04-17 | 1 | 1 | 35 | 25 | 63 | 47 | 98 | 72 | Steps 2,3,5,6,7 | 30 | 22 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-16 | -572 | -410 | No | 2024-07-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-10 | 2024-10-16 | IOU Designed & Installed | N/A | Yes | 24 | 1059.2 | Unknown | Unknown | Unknown | 5.31 | 1053.89 | 3961 | 1377.49 | 1059.2 | 318.29 | Yes | N/A | N/A | 2024-07-10 | 2024-08-16 | 38 | 28 | 2024-08-16 | 2024-08-19 | 4 | 2 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-10-16 | 83 | 59 | Unknown | 2024-10-02 | Unknown | Unknown | 2024-10-16 | 2024-10-21 | 1900-01-05 | 4 | 2024-10-21 | 2024-10-21 | 1 | 1 | 121 | 87 | 11 | 7 | 132 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-30 | 128 | 93 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-04-06 | IOU Designed & Installed | N/A | No | N/A | 815.31 | 243.32 | Unknown | 155.78 | Unknown | 416.21 | Unknown | 217.6 | 815.31 | -597.71 | Yes | N/A | N/A | 2023-02-13 | 2023-02-15 | 3 | 3 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | 2023-04-06 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-04-07 | 1900-01-01 | 2 | 2023-04-07 | 2023-04-07 | 1 | 1 | 54 | 40 | 3 | 3 | 57 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 4272 | 4272 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-07-13 | -59 | -43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-08-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1734.34 | 415.23 | Unknown | 32.18 | 26.8 | 1260.13 | 3981 | 2521.7 | 1734.34 | 787.36 | Yes | N/A | N/A | 2023-08-29 | 2023-10-11 | 44 | 32 | 2023-10-11 | 2023-10-17 | 7 | 5 | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | Unknown | Unknown | Unknown | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-05-15 | 1 | 1 | 44 | 32 | 8 | 6 | 52 | 38 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-13 | -58 | -43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | 2024-12-20 | IOU Designed & Installed | N/A | No | N/A | 1058.65 | -16.8 | Unknown | Unknown | 92.36 | 983.09 | Unknown | 900.73 | 1058.65 | -157.92 | Yes | N/A | N/A | 2024-05-09 | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-05-09 | 56 | 40 | 2024-05-09 | Unknown | Unknown | Unknown | 2024-05-10 | 2024-05-30 | 21 | 15 | 2024-05-09 | 2024-12-20 | 226 | 162 | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-01-14 | 1900-01-25 | 18 | 2025-01-14 | 2025-01-14 | 1 | 1 | 226 | 162 | 104 | 74 | 330 | 236 | Steps 2,3,5,6,7 | 21 | 15 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-28 | -310 | -221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 441.25 | -7.84 | Unknown | Unknown | 3.54 | 445.55 | Unknown | 966.75 | 441.25 | 525.5 | Yes | N/A | N/A | 2024-04-11 | 2024-04-11 | 1 | 1 | 2024-04-11 | 2025-03-06 | 330 | 236 | 2025-03-06 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-07-22 | 103 | 73 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2025-02-21 | 1900-08-02 | 155 | 2025-02-21 | 2025-02-21 | 1 | 1 | 104 | 74 | 546 | 392 | 650 | 466 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | SAN CLEMENTE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-16 | 232 | 167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-19 | 2022-09-19 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 19486.23 | 2312.54 | Unknown | 1668.15 | 402.03 | 15103.51 | 3981 | 905.36 | 19486.23 | -18580.87 | Yes | N/A | N/A | 2022-09-19 | 2023-08-16 | 332 | 238 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-26 | 2024-03-19 | 16 | 10 | 2023-08-26 | 2024-03-25 | 213 | 151 | Unknown | 2024-03-11 | Unknown | Unknown | 2024-03-25 | 2024-04-04 | 1900-01-10 | 9 | 2024-04-04 | 2024-04-04 | 1 | 1 | 545 | 389 | 28 | 20 | 573 | 409 | Steps 2,3,5,6,7 | 206 | 146 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-16 | -516 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-10 | 2023-08-01 | IOU Designed & Installed | N/A | No | N/A | 25.62 | -15.14 | Unknown | Unknown | Unknown | 40.76 | 3981 | 932.93 | 25.62 | 907.31 | Yes | N/A | N/A | 2023-05-10 | 2023-05-10 | 1 | 1 | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-10 | 2023-08-01 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-06-19 | Unknown | Unknown | 2023-06-19 | 2023-06-19 | 1 | 1 | 85 | 61 | 1 | 1 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-20 | -497 | -356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-04-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -40.62 | -29.43 | Unknown | Unknown | Unknown | -11.19 | 3981 | 468.73 | -40.62 | 509.35 | Yes | N/A | N/A | 2023-03-06 | 2023-04-06 | 32 | 24 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | 2023-08-11 | 2023-08-11 | 1 | 1 | 32 | 24 | 1 | 1 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 80 | 80 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | -330 | -237 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-07 | 2024-04-08 | IOU Designed & Installed | N/A | No | N/A | 164.91 | -18.37 | Unknown | Unknown | 71.87 | 111.41 | 3981 | 1127.62 | 164.91 | 962.71 | Yes | N/A | N/A | 2024-03-07 | 2024-02-01 | Unknown | Unknown | 2024-02-01 | 2024-03-07 | 36 | 26 | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-04-08 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | 2025-02-20 | 1900-11-14 | 229 | 2025-02-20 | 2025-02-20 | 1 | 1 | 33 | 23 | 356 | 256 | 389 | 279 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA HILLS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-12-31 | 1735 | 1240 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | 2024-09-27 | IOU Designed & Installed | N/A | No | N/A | 8920.64 | 986.58 | Unknown | 2733.3 | Unknown | 5200.76 | 2875.23 | 453.01 | 8920.64 | -8467.63 | Yes | N/A | N/A | 2024-03-12 | 2024-03-18 | 7 | 5 | 2024-03-18 | 2024-06-28 | 103 | 75 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-23 | 26 | 18 | Unknown | 2024-09-03 | Unknown | Unknown | 2024-09-27 | 2024-09-30 | 1900-01-03 | 2 | 2024-09-30 | 2024-09-30 | 1 | 1 | 33 | 23 | 108 | 78 | 141 | 101 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-28 | -633 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-04 | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | -153.36 | Unknown | Unknown | Unknown | -178 | 24.64 | Unknown | 1435.28 | -153.36 | 1588.64 | Yes | N/A | N/A | 2024-09-04 | 2024-07-03 | Unknown | Unknown | 2024-07-03 | 2024-09-04 | 64 | 46 | 2024-09-04 | 2024-09-06 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-17 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-10-04 | 1900-01-17 | 14 | 2024-10-04 | 2024-10-03 | Unknown | Unknown | 17 | 13 | 82 | 60 | 99 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12.15 | 12.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | -401 | -288 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | 2025-05-08 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1678.56 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-07 | 2025-01-07 | 1 | 1 | 2025-01-07 | 2025-01-07 | 1 | 1 | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-05-08 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-05-20 | 1900-01-12 | 9 | 2025-05-20 | 2025-05-19 | Unknown | Unknown | 123 | 89 | 14 | 10 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 1021.05 | 1021.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-03-08 | 301 | 216 | No | 2023-08-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | 2023-05-11 | 2024-12-17 | IOU Designed & Installed | N/A | Yes | 468 | 1353.97 | Unknown | Unknown | Unknown | 45.99 | 1307.98 | 3981 | 758.33 | 1353.97 | -595.64 | Yes | N/A | N/A | 2023-05-11 | 2024-11-21 | 561 | 401 | 2024-11-21 | 2023-08-11 | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2024-12-17 | 495 | 353 | Unknown | 2024-12-09 | Unknown | Unknown | 2024-12-17 | 2025-01-06 | 1900-01-20 | 15 | 2025-01-06 | 2025-01-03 | Unknown | Unknown | 1056 | 754 | 21 | 15 | 1077 | 769 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Pala | COUNTY OF SAN DIEGO-NORTH of 56 | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-29 | -423 | -304 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-03-22 | 2023-05-30 | IOU Designed & Installed | N/A | No | N/A | 37448.69 | 9532.94 | Unknown | Unknown | -12419.97 | 40335.72 | 2545 | 27847.8 | 37448.69 | -9600.89 | Yes | N/A | N/A | 2023-02-14 | 2023-02-14 | 1 | 1 | 2023-02-14 | 2023-04-10 | 56 | 40 | 2023-04-04 | 2023-04-05 | 2 | 2 | 2023-04-05 | 2023-04-10 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | 2023-07-03 | 1900-02-03 | 25 | 2023-07-03 | 2023-07-03 | 1 | 1 | 3 | 3 | 98 | 70 | 101 | 73 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-11 | -635 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2025-01-24 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | 735.12 | -13.66 | Unknown | Unknown | Unknown | 748.78 | 3981 | 1894.27 | 735.12 | 1159.15 | Yes | N/A | N/A | 2024-12-19 | 2025-01-17 | 30 | 22 | 2025-01-17 | 2025-01-24 | 8 | 6 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-01-29 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-14 | 1900-01-16 | 13 | 2025-02-14 | 2025-02-14 | 1 | 1 | 36 | 26 | 26 | 20 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-07-22 | 622 | 445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 382.05 | -8.22 | Unknown | Unknown | Unknown | 390.27 | 3981 | Not available | 382.05 | Unknown | Yes | N/A | N/A | 2023-11-01 | 2023-08-31 | Unknown | Unknown | 2023-08-31 | 2023-12-26 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | 2024-03-22 | 88 | 64 | Unknown | 2024-03-21 | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | 2024-04-08 | 2024-04-04 | Unknown | Unknown | 88 | 64 | 118 | 84 | 206 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-05 | -565 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | 2025-05-15 | IOU Designed & Installed | N/A | No | N/A | 519.6 | -10.43 | Unknown | Unknown | Unknown | 530.03 | 3981 | 1865.22 | 519.6 | 1345.62 | Yes | N/A | N/A | 2025-02-19 | 2025-02-19 | 1 | 1 | 2025-02-19 | 2025-02-19 | 1 | 1 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-05-15 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-05-19 | 1900-01-04 | 3 | 2025-05-19 | 2025-05-19 | 1 | 1 | 87 | 63 | 7 | 5 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-06 | 518 | 371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 746.69 | -14.41 | Unknown | Unknown | Unknown | 761.1 | 3981 | 3263.21 | 746.69 | 2516.52 | Yes | N/A | N/A | 2023-09-06 | 2023-09-05 | Unknown | Unknown | 2023-09-05 | 2024-11-15 | 438 | 314 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-05 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | Unknown | Unknown | 2024-11-26 | 2025-02-05 | 72 | 52 | 21 | 15 | 510 | 366 | 531 | 381 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JULIAN | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-13 | -548 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | 2025-04-23 | IOU Designed & Installed | N/A | No | N/A | 6770.33 | 1216.6 | Unknown | 1394.76 | Unknown | 4158.97 | Unknown | 3813.94 | 6770.33 | -2956.39 | Yes | N/A | N/A | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | Unknown | Unknown | Unknown | 2024-12-19 | 2024-12-31 | 13 | 9 | 2025-02-28 | 2025-04-23 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-05-14 | 1900-01-21 | 16 | 2025-05-14 | 2025-05-14 | 1 | 1 | 56 | 40 | 37 | 27 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 778 | 778 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-20 | -6 | -5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-05-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 392.79 | 131.91 | Unknown | Unknown | 3.66 | 257.22 | 3981 | 1525.16 | 392.79 | 1132.37 | Yes | N/A | N/A | 2023-05-31 | 2023-07-21 | 52 | 38 | 2023-07-21 | 2023-07-21 | 1 | 1 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-14 | 1 | 1 | 52 | 38 | 2 | 2 | 54 | 40 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 289.35 | 289.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-09 | 40 | 29 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-12-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 796.31 | -33.37 | Unknown | Unknown | Unknown | 829.68 | 7962 | 1400.89 | 796.31 | 604.58 | Yes | N/A | N/A | 2023-11-29 | 2023-11-29 | 1 | 1 | 2023-11-29 | 2023-12-27 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2023-12-19 | 12 | 8 | 2023-12-27 | 2024-02-27 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-03-20 | Unknown | Unknown | 64 | 46 | 41 | 29 | 105 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 265 | 265 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-28 | -370 | -265 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-14 | 2023-09-20 | IOU Designed & Installed | N/A | No | N/A | -1642.54 | -18.58 | Unknown | Unknown | -1633 | 9.04 | 3981 | 1774.06 | -1642.54 | 3416.6 | Yes | N/A | N/A | 2023-07-14 | 2023-07-12 | Unknown | Unknown | 2023-07-12 | 2023-07-14 | 3 | 3 | 2023-07-14 | 2023-07-31 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2023-09-20 | 52 | 38 | Unknown | 2023-09-18 | Unknown | Unknown | 2023-09-20 | 2023-10-24 | 1900-02-03 | 25 | 2023-10-24 | 2023-10-24 | 1 | 1 | 70 | 50 | 39 | 29 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2030-12-31 | -2630 | -1879 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-06-08 | 2023-09-25 | IOU Designed & Installed | N/A | No | N/A | -6484.09 | 469.79 | Unknown | Unknown | -21204 | 14250.12 | Unknown | 21438.72 | -6484.09 | 27922.81 | Yes | N/A | N/A | 2023-06-08 | 2023-06-12 | 5 | 3 | 2023-06-12 | 2023-09-08 | 89 | 65 | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2023-08-17 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | 2023-10-19 | 1900-01-24 | 19 | 2023-10-19 | 2023-10-19 | 1 | 1 | 5 | 3 | 119 | 89 | 124 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 229 | 229 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-13 | -652 | -467 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-02-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 775.49 | -7.55 | Unknown | Unknown | Unknown | 783.04 | 6481 | 1007.6 | 775.49 | 232.11 | Yes | N/A | N/A | 2023-02-06 | 2023-02-06 | 1 | 1 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | Unknown | Unknown | 2023-03-31 | 2023-03-02 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-14 | -588 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-02 | 2023-11-02 | 2023-12-26 | IOU Designed & Installed | N/A | No | N/A | 723.56 | 244.9 | Unknown | Unknown | Unknown | 478.66 | 3885 | 1037.05 | 723.56 | 313.49 | Yes | N/A | N/A | 2023-11-02 | 2023-11-02 | 1 | 1 | 2023-11-02 | 2023-11-02 | 1 | 1 | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2023-12-26 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | 2024-01-03 | 1900-01-08 | 7 | 2024-01-03 | 2024-01-04 | 2 | 2 | 56 | 40 | 12 | 10 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-28 | 751 | 537 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | 1629.73 | -15.62 | Unknown | Unknown | Unknown | 1645.35 | 41506 | 2886.06 | 1629.73 | 1256.33 | Yes | N/A | N/A | 2024-08-22 | 2024-08-22 | 1 | 1 | 2024-08-22 | 2024-08-28 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-06-06 | 22 | 16 | 2024-08-28 | 2025-05-12 | 258 | 184 | Unknown | 2025-05-13 | Unknown | Unknown | 2025-06-05 | 2025-06-18 | 1900-01-13 | 10 | 2025-06-18 | 2025-06-17 | Unknown | Unknown | 259 | 185 | 43 | 31 | 302 | 216 | Steps 2,3,5,6,7 | 282 | 202 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-03 | -565 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 56.56 | Unknown | Unknown | Unknown | Unknown | 56.56 | Unknown | 1700.5 | 56.56 | 1643.94 | Yes | N/A | N/A | 2024-10-01 | 2024-05-23 | Unknown | Unknown | 2024-05-23 | 2024-10-01 | 132 | 94 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | 2024-10-15 | 2024-10-15 | 1 | 1 | 0 | 0 | 133 | 95 | 133 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | -66 | -47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-08-31 | 2024-01-23 | IOU Designed & Installed | N/A | No | N/A | 2.85 | -3.57 | Unknown | Unknown | Unknown | 6.42 | 7962 | 883.57 | 2.85 | 880.72 | Yes | N/A | N/A | 2023-08-31 | 2023-08-31 | 1 | 1 | 2023-08-31 | 2023-08-31 | 1 | 1 | 2023-08-31 | 2023-11-30 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2024-01-23 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-01-26 | 1900-01-03 | 4 | 2024-01-26 | 2024-01-26 | 1 | 1 | 149 | 107 | 6 | 6 | 155 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-23 | -181 | -130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | 2024-04-12 | IOU Designed & Installed | N/A | No | N/A | 1881.29 | -21.57 | Unknown | Unknown | 72.49 | 1830.37 | 3981 | 366.13 | 1881.29 | -1515.16 | Yes | N/A | N/A | 2023-11-01 | 2023-11-07 | 7 | 5 | 2023-11-07 | 2023-11-07 | 1 | 1 | 2023-11-07 | Unknown | Unknown | Unknown | 2023-11-07 | 2024-02-21 | 107 | 77 | 2023-11-07 | 2024-04-12 | 158 | 114 | Unknown | 2024-03-29 | Unknown | Unknown | 2024-04-12 | 2024-04-29 | 1900-01-17 | 12 | 2024-04-29 | 2024-04-25 | Unknown | Unknown | 165 | 119 | 126 | 90 | 291 | 209 | Steps 2,3,5,6,7 | 106 | 76 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 170 | 170 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | -10 | -9 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-07 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | 72483.82 | 8447.48 | Unknown | Unknown | 32.46 | 64003.88 | Unknown | 49007.17 | 72483.82 | -23476.65 | Yes | N/A | N/A | 2024-03-04 | 2023-11-20 | Unknown | Unknown | 2023-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-08-19 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-09-23 | 1900-01-26 | 19 | 2024-09-23 | 2024-09-23 | 1 | 1 | 0 | 0 | 49 | 35 | 49 | 35 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-18 | -279 | -200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-04-03 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 7407.04 | 3118.18 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-26 | 2025-04-02 | 8 | 6 | 2025-04-02 | 2025-04-03 | 2 | 2 | 2025-04-03 | 2025-04-24 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-06-03 | 55 | 39 | Unknown | 2025-05-12 | Unknown | Unknown | 2025-06-03 | 2025-06-12 | 1900-01-09 | 8 | 2025-06-12 | 2025-06-12 | 1 | 1 | 85 | 61 | 13 | 11 | 98 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 1344 | 1344 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-09-01 | -3 | -2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-11-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 518.15 | -14.28 | Unknown | Unknown | Unknown | 532.43 | 11943 | 1036.48 | 518.15 | 518.33 | Yes | N/A | N/A | 2023-10-17 | 2024-11-02 | 383 | 274 | 2024-11-02 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2024-08-08 | 276 | 198 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | Unknown | Unknown | 2024-08-30 | 2024-08-29 | Unknown | Unknown | 659 | 472 | 0 | 0 | 659 | 472 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-28 | -599 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-12 | 2023-08-12 | 2023-08-25 | IOU Designed & Installed | N/A | No | N/A | -5.15 | -3.74 | Unknown | Unknown | Unknown | -1.41 | Unknown | 425.49 | -5.15 | 430.64 | Yes | N/A | N/A | 2023-08-12 | 2023-08-12 | 1 | 0 | 2023-08-12 | 2023-08-12 | 1 | 0 | 2023-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-12 | 2023-08-25 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-08-25 | 2023-09-07 | 1900-01-13 | 10 | 2023-09-07 | 2023-09-07 | 1 | 1 | 15 | 10 | 16 | 11 | 31 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-18 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | 2025-04-18 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2025.41 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-03-10 | 1 | 1 | 2025-03-10 | 2025-03-10 | 1 | 1 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-04-18 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-04-24 | 1900-01-06 | 5 | 2025-04-24 | 2025-04-24 | 1 | 1 | 41 | 31 | 9 | 7 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-09 | 648 | 463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-11 | 2023-05-17 | 2025-06-16 | IOU Designed & Installed | N/A | No | N/A | 1285.95 | -8.69 | Unknown | Unknown | 1.18 | 1293.46 | 4200 | 3858.49 | 1285.95 | 2572.54 | Yes | N/A | N/A | 2022-02-11 | 2023-05-17 | 461 | 329 | 2023-05-17 | 2023-06-13 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-02-15 | 20 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-06-18 | 1900-01-02 | 3 | 2025-06-18 | 2025-06-18 | 1 | 1 | 461 | 329 | 52 | 39 | 513 | 368 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-29 | 269 | 194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-06 | 2023-11-15 | 2024-04-05 | IOU Designed & Installed | N/A | No | N/A | 11679.98 | 549.52 | Unknown | 123.84 | -7939 | 18945.62 | Unknown | 7938.99 | 11679.98 | -3740.99 | Yes | N/A | N/A | 2022-09-06 | 2023-10-19 | 409 | 293 | 2023-10-19 | 2024-01-23 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | Unknown | Unknown | 2024-04-05 | 2024-05-24 | 1900-02-18 | 36 | 2024-05-24 | 2024-05-24 | 1 | 1 | 409 | 293 | 148 | 106 | 557 | 399 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-20 | 485 | 346 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-02 | 2022-11-02 | 2024-07-08 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 59022.86 | 11168.12 | Unknown | 221.58 | 287.72 | 47345.44 | 82450 | 28321.6 | 59022.86 | -30701.26 | Yes | N/A | N/A | 2022-11-02 | 2023-09-20 | 323 | 231 | 2023-09-20 | 2024-04-04 | 198 | 142 | 2023-10-05 | 2024-02-16 | 67 | 49 | 2023-10-11 | 2024-04-23 | 74 | 54 | 2024-05-22 | Unknown | Unknown | Unknown | 2024-05-22 | 2025-02-28 | 283 | 203 | 2024-07-08 | 2024-09-16 | 1900-03-11 | 51 | 2024-09-16 | 2024-09-16 | 1 | 1 | 390 | 280 | 627 | 451 | 1017 | 731 | Steps 2,3,5,6,7 | 545 | 391 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-13 | -188 | -135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-06-03 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | -1335.56 | 1939.56 | Unknown | 358.55 | -4512 | 878.33 | Unknown | 4511.76 | -1335.56 | 5847.32 | Yes | N/A | N/A | 2024-05-23 | 2024-05-22 | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-06 | 1900-01-06 | 5 | 2024-11-06 | 2024-11-06 | 1 | 1 | 0 | 0 | 8 | 6 | 8 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 92.1 | 92.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-21 | -44 | -33 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-06-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1986.79 | -37.23 | Unknown | Unknown | 40.84 | 1983.18 | 23886 | 1526.95 | 1986.79 | -459.84 | Yes | N/A | N/A | 2024-02-05 | 2024-05-09 | 95 | 69 | 2024-05-09 | 2024-07-17 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-24 | 30 | 22 | 2024-07-17 | 2024-10-08 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | Unknown | Unknown | 2025-02-07 | 2024-10-08 | Unknown | Unknown | 179 | 129 | 100 | 72 | 279 | 201 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | POWAY | 64512 | 64512 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-01 | 159 | 114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-31 | 2024-12-31 | IOU Designed & Installed | N/A | No | N/A | 667.26 | 124.03 | Unknown | Unknown | Unknown | 543.23 | Unknown | 449.58 | 667.26 | -217.68 | Yes | N/A | N/A | 2024-07-29 | 2024-07-26 | Unknown | Unknown | 2024-07-26 | 2024-09-11 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-11-14 | 42 | 32 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | 2024-12-31 | 2025-01-07 | 1900-01-07 | 6 | 2025-01-07 | 2025-01-07 | 1 | 1 | 0 | 0 | 99 | 73 | 99 | 73 | Steps 2,3,5,6,7 | 170 | 122 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-09 | -555 | -398 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-27 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | 631.81 | -11.7 | Unknown | Unknown | Unknown | 643.51 | 3981 | 2044.77 | 631.81 | 1412.96 | Yes | N/A | N/A | 2024-09-23 | 2024-11-21 | 60 | 44 | 2024-11-21 | 2024-11-22 | 2 | 2 | 2024-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-02-26 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-03-04 | 1900-01-06 | 5 | 2025-03-04 | 2025-03-03 | Unknown | Unknown | 157 | 113 | 9 | 7 | 166 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-09-04 | 1312 | 937 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1559.57 | Unknown | Unknown | Unknown | Unknown | 1559.57 | 3981 | 656.28 | 1559.57 | -903.29 | Yes | N/A | N/A | 2024-02-12 | 2023-11-05 | Unknown | Unknown | 2023-11-05 | 2024-02-22 | 110 | 79 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2025-03-25 | 398 | 284 | Unknown | 2025-03-21 | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | 2025-04-08 | 2025-04-08 | 1 | 1 | 398 | 284 | 111 | 80 | 509 | 364 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-29 | -619 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | 2024-04-01 | IOU Designed & Installed | N/A | No | N/A | 1511.5 | 498.79 | Unknown | Unknown | Unknown | 1012.71 | 3981 | 1023.84 | 1511.5 | -487.66 | Yes | N/A | N/A | 2024-02-14 | 2023-10-18 | Unknown | Unknown | 2023-10-18 | 2024-03-15 | 150 | 108 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-04-01 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-04-19 | 1900-01-18 | 15 | 2024-04-19 | 2024-04-19 | 1 | 1 | 18 | 12 | 170 | 124 | 188 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-17 | -473 | -339 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | Unknown | 2024-01-25 | IOU Designed & Installed | N/A | No | N/A | 225.42 | -7.86 | Unknown | Unknown | Unknown | 233.28 | 3885 | 909.97 | 225.42 | 684.55 | Yes | N/A | N/A | 2023-11-30 | 2023-11-30 | 1 | 1 | 2023-11-30 | 2023-12-08 | 9 | 7 | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2024-01-25 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-01-30 | 1900-01-05 | 4 | 2024-01-30 | 2024-01-30 | 1 | 1 | 57 | 41 | 16 | 12 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | 220 | 220 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | 18 | 14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2329.88 | -12.92 | Unknown | Unknown | -3073 | 756.04 | Unknown | 1222.27 | -2329.88 | 3552.15 | Yes | N/A | N/A | 2024-09-11 | 2024-09-18 | 8 | 6 | 2024-09-18 | 2024-09-19 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-12-12 | 85 | 61 | Unknown | 2024-12-12 | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | 2025-01-24 | 2025-01-23 | Unknown | Unknown | 93 | 67 | 2 | 2 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-04 | -362 | -260 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | 2024-01-08 | IOU Designed & Installed | N/A | No | N/A | 3.77 | -4.76 | Unknown | Unknown | Unknown | 8.53 | Unknown | 906.77 | 3.77 | 903 | Yes | N/A | N/A | 2024-01-04 | 2024-01-04 | 1 | 1 | 2024-01-04 | 2024-01-04 | 1 | 1 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-08 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | 2024-01-08 | 1899-12-31 | 1 | 2024-01-08 | 2024-01-08 | 1 | 1 | 6 | 4 | 3 | 3 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-04 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 40.37 | Unknown | Unknown | Unknown | Unknown | 40.37 | Unknown | 1463.84 | 40.37 | 1423.47 | Yes | N/A | N/A | 2024-08-13 | 2024-06-04 | Unknown | Unknown | 2024-06-04 | 2024-08-13 | 71 | 51 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-10-31 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-06 | 1900-01-06 | 5 | 2024-11-06 | 2024-11-06 | 1 | 1 | 80 | 58 | 79 | 57 | 159 | 115 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | -411 | -294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 375.32 | Unknown | Unknown | Unknown | 25.38 | 349.94 | 3981 | 1444.55 | 375.32 | 1069.23 | Yes | N/A | N/A | 2024-08-22 | 2024-08-27 | 6 | 4 | 2024-08-27 | 2024-09-06 | 11 | 9 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2025-01-28 | 145 | 103 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-04-28 | 1900-03-31 | 65 | 2025-04-28 | 2025-04-25 | Unknown | Unknown | 151 | 107 | 102 | 74 | 253 | 181 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | -604 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 865.11 | -12.92 | Unknown | Unknown | Unknown | 878.03 | 3981 | 1768.82 | 865.11 | 903.71 | Yes | N/A | N/A | 2024-12-03 | 2024-12-03 | 1 | 1 | 2024-12-03 | 2024-12-03 | 1 | 1 | 2024-12-03 | Unknown | Unknown | Unknown | 2024-12-05 | 2025-01-08 | 35 | 25 | 2024-12-03 | 2025-01-30 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-03-27 | 1900-02-25 | 41 | 2025-03-27 | 2025-03-27 | 1 | 1 | 60 | 44 | 94 | 68 | 154 | 112 | Steps 2,3,5,6,7 | 36 | 26 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-16 | -566 | -405 | No | 2024-06-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-13 | 2024-08-05 | IOU Designed & Installed | N/A | Yes | 48 | 123.89 | Unknown | Unknown | Unknown | 2.64 | 121.25 | 3981 | 1417.82 | 123.89 | 1293.93 | Yes | N/A | N/A | 2024-06-13 | 2024-07-31 | 49 | 35 | 2024-07-31 | 2024-06-13 | Unknown | Unknown | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-08-05 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-08-27 | 1900-01-22 | 17 | 2024-08-27 | 2024-08-27 | 1 | 1 | 103 | 73 | 24 | 18 | 127 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-02 | -281 | -202 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-30 | 2025-01-03 | 2025-01-31 | IOU Designed & Installed | N/A | No | N/A | 12254.34 | Unknown | Unknown | Unknown | Unknown | 12254.34 | Unknown | 545.62 | 12254.34 | -11708.72 | Yes | N/A | N/A | 2024-12-30 | 2024-12-23 | Unknown | Unknown | 2024-12-23 | 2025-01-27 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-02-24 | 1900-01-24 | 17 | 2025-02-24 | 2025-02-24 | 1 | 1 | 0 | 0 | 62 | 44 | 62 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-29 | -462 | -331 | No | 2024-03-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-03-01 | 2024-07-18 | IOU Designed & Installed | N/A | Yes | 132 | 19.33 | Unknown | Unknown | Unknown | -807 | 826.33 | Unknown | 806.87 | 19.33 | 787.54 | Yes | N/A | N/A | 2024-03-01 | 2024-07-11 | 133 | 95 | 2024-07-11 | 2024-03-06 | Unknown | Unknown | 2024-03-06 | 2024-03-12 | 7 | 5 | 2024-07-24 | 2024-07-24 | 1 | 1 | 2024-03-12 | 2024-07-18 | 129 | 93 | Unknown | 2024-07-18 | Unknown | Unknown | 2024-07-18 | 2024-07-24 | 1900-01-06 | 5 | 2024-07-24 | 2024-07-24 | 1 | 1 | 269 | 193 | 9 | 7 | 278 | 200 | Steps 2,3,5,6,7 | 134 | 96 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-30 | -24 | -17 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-12 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 0 | Unknown | Unknown | Unknown | Unknown | Unkonwn | 3981 | 1717.48 | Unknown | 1717.48 | Yes | N/A | N/A | 2024-11-12 | 2024-10-30 | Unknown | Unknown | 2024-10-30 | 2024-11-12 | 14 | 10 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2024-11-15 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-06 | 1900-01-21 | 16 | 2024-12-06 | 2024-12-06 | 1 | 1 | 4 | 4 | 37 | 27 | 41 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56, LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-01 | -658 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | Unknown | 2024-06-25 | IOU Designed & Installed | N/A | No | N/A | 2020.34 | -39.9 | Unknown | Unknown | Unknown | 2060.24 | 3981 | 1635.34 | 2020.34 | -385 | Yes | N/A | N/A | 2024-05-31 | 2024-05-31 | 1 | 1 | 2024-05-31 | 2024-05-31 | 1 | 1 | 2024-05-31 | Unknown | Unknown | Unknown | 2024-05-31 | 2024-06-27 | 28 | 20 | 2024-05-31 | 2024-06-25 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-12 | 1900-01-17 | 14 | 2024-07-12 | 2024-07-12 | 1 | 1 | 27 | 19 | 48 | 36 | 75 | 55 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 1185.05 | 1185.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-10-20 | -2 | -1 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1705.67 | -5.11 | Unknown | Unknown | 2.75 | 1708.03 | 3981 | 2294.04 | 1705.67 | 588.37 | Yes | N/A | N/A | 2024-01-17 | 2024-05-15 | 120 | 86 | 2024-05-15 | 2024-05-20 | 6 | 4 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-10-18 | 1 | 1 | 120 | 86 | 7 | 5 | 127 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-27 | -674 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | Unknown | 2024-10-07 | IOU Designed & Installed | N/A | No | N/A | 4.85 | Unknown | Unknown | Unknown | Unknown | 4.85 | Unknown | 197.01 | 4.85 | 192.16 | Yes | N/A | N/A | 2024-09-24 | 2024-09-06 | Unknown | Unknown | 2024-09-06 | 2024-10-01 | 26 | 18 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-07 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-22 | 1900-01-15 | 12 | 2024-10-22 | 2024-10-22 | 1 | 1 | 7 | 5 | 43 | 31 | 50 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-24 | -278 | -199 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1784.89 | Unknown | Unknown | Unknown | 1.89 | 1783 | 3981 | 1662.17 | 1784.89 | -122.72 | Yes | N/A | N/A | 2023-12-13 | 2024-09-10 | 273 | 195 | 2024-09-10 | 2024-09-19 | 10 | 8 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | Unknown | Unknown | Unknown | 2024-11-19 | Unknown | Unknown | 2024-11-19 | 2024-11-19 | 1 | 1 | 273 | 195 | 11 | 9 | 284 | 204 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -819 | -586 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-12 | 2023-09-22 | IOU Designed & Installed | N/A | No | N/A | 8662.34 | 78.75 | Unknown | Unknown | 2.19 | 8581.4 | Unknown | 5051.35 | 8662.34 | -3610.99 | Yes | N/A | N/A | 2023-09-08 | 2023-09-09 | 2 | 1 | 2023-09-09 | 2023-09-20 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2023-09-21 | 7 | 5 | 2023-09-20 | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | Unknown | Unknown | 2023-09-22 | 2023-10-04 | 1900-01-12 | 9 | 2023-10-04 | 2023-10-04 | 1 | 1 | 2 | 1 | 33 | 23 | 35 | 24 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | 201 | 144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-13 | 2024-12-18 | IOU Designed & Installed | N/A | No | N/A | 1129.17 | 620.07 | Unknown | 64.57 | Unknown | 444.53 | 3981 | 918.66 | 1129.17 | -210.51 | Yes | N/A | N/A | 2023-10-05 | 2023-10-06 | 2 | 2 | 2023-10-06 | 2023-10-13 | 8 | 6 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2024-12-18 | 433 | 309 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2024-12-19 | 1900-01-01 | 2 | 2024-12-19 | 2024-12-19 | 1 | 1 | 435 | 311 | 11 | 9 | 446 | 320 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 56 | 56 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-11 | 13 | 10 | No | 2023-09-29 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-11-30 | 2024-05-08 | IOU Designed & Installed | N/A | Yes | 73 | 687.2 | -3.31 | Unknown | Unknown | Unknown | 690.51 | 3981 | 783.83 | 687.2 | 96.63 | Yes | N/A | N/A | 2023-09-29 | 2023-12-11 | 74 | 52 | 2023-12-11 | 2023-11-30 | Unknown | Unknown | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2024-05-08 | 161 | 115 | Unknown | 2024-05-06 | Unknown | Unknown | 2024-05-08 | 2024-05-22 | 1900-01-14 | 11 | 2024-05-22 | 2024-05-24 | 3 | 3 | 235 | 167 | 18 | 14 | 253 | 181 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 88.1 | 88.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-24 | -224 | -161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 571.48 | -27.95 | Unknown | Unknown | 69.87 | 529.56 | 7962 | 774.7 | 571.48 | 203.22 | Yes | N/A | N/A | 2023-05-30 | 2023-05-30 | 1 | 1 | 2023-05-30 | 2023-06-08 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | 2023-09-29 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2023-11-13 | Unknown | Unknown | 115 | 83 | 10 | 8 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-19 | -239 | -172 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-11 | 2024-07-08 | IOU Designed & Installed | N/A | No | N/A | -1080.04 | -11.53 | Unknown | Unknown | -1095 | 26.49 | 3981 | 2130.33 | -1080.04 | 3210.37 | Yes | N/A | N/A | 2024-06-11 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-06-11 | 62 | 44 | 2024-06-11 | 2024-06-18 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-07-08 | 21 | 15 | Unknown | 2024-06-26 | Unknown | Unknown | 2024-07-08 | 2024-07-16 | 1900-01-08 | 7 | 2024-07-16 | 2024-07-23 | 8 | 6 | 29 | 21 | 79 | 57 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-08 | 490 | 351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2023-07-24 | 2024-10-03 | IOU Designed & Installed | N/A | No | N/A | 444.26 | Unknown | Unknown | Unknown | 21.32 | 422.94 | 3941 | 902.93 | 444.26 | 458.67 | Yes | N/A | N/A | 2023-07-24 | 2023-05-19 | Unknown | Unknown | 2023-05-19 | 2023-08-04 | 78 | 56 | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | 2024-10-03 | 427 | 305 | Unknown | 2024-09-16 | Unknown | Unknown | 2024-10-03 | 2024-10-09 | 1900-01-06 | 5 | 2024-10-09 | 2024-10-10 | 2 | 2 | 427 | 305 | 87 | 63 | 514 | 368 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-13 | -234 | -169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-17 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | 21.47 | -19.06 | Unknown | Unknown | Unknown | 40.53 | 3981 | 924.57 | 21.47 | 903.1 | Yes | N/A | N/A | 2024-04-16 | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-04-17 | 50 | 36 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-04-22 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-05-20 | 1900-01-28 | 21 | 2024-05-20 | 2024-06-24 | 36 | 26 | 6 | 4 | 115 | 83 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BS 1068-A4 (E) | N/A | 142 | 142 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-08 | -86 | -63 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-03-22 | 2025-04-17 | IOU Designed & Installed | N/A | No | N/A | -6918.89 | 2142.82 | Unknown | Unknown | -12344 | 3282.29 | 2922 | 15266.21 | -6918.89 | 22185.1 | Yes | N/A | N/A | 2024-02-20 | 2024-02-20 | 1 | 1 | 2024-02-20 | 2024-11-20 | 275 | 197 | 2024-04-18 | 2024-04-25 | 8 | 6 | 2024-10-24 | 2025-04-03 | 162 | 116 | 2024-11-20 | Unknown | Unknown | Unknown | 2025-01-27 | 2025-03-24 | 57 | 41 | 2025-04-17 | 2025-05-14 | 1900-01-27 | 20 | 2025-05-14 | 2025-05-14 | 1 | 1 | 9 | 7 | 523 | 375 | 532 | 382 | Steps 2,3,5,6,7 | 350 | 250 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 47.75 | 47.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-17 | -623 | -446 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-01-24 | 2025-01-31 | IOU Designed & Installed | N/A | No | N/A | 8.33 | -37.6 | Unknown | Unknown | Unknown | 45.93 | Unknown | 2108.47 | 8.33 | 2100.14 | Yes | N/A | N/A | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | 2025-01-24 | 1 | 1 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-01-31 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-04-03 | 1900-03-03 | 45 | 2025-04-03 | 2025-04-03 | 1 | 1 | 9 | 7 | 65 | 47 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 165.1 | 165.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-26 | -209 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-13 | 2024-04-25 | IOU Designed & Installed | N/A | No | N/A | 892.61 | -30.13 | Unknown | Unknown | 3.26 | 919.48 | 7882 | 920.32 | 892.61 | 27.71 | Yes | N/A | N/A | 2024-03-13 | 2024-02-02 | Unknown | Unknown | 2024-02-02 | 2024-03-13 | 41 | 29 | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-04-25 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-06-03 | 1900-02-08 | 28 | 2024-06-03 | 2024-05-31 | Unknown | Unknown | 44 | 32 | 81 | 57 | 125 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-16 | -647 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-03-24 | 2023-04-05 | IOU Designed & Installed | N/A | No | N/A | 1496.68 | 472.08 | Unknown | 220.68 | Unknown | 803.92 | 3981 | 808.84 | 1496.68 | -687.84 | Yes | N/A | N/A | 2023-03-13 | 2023-03-24 | 12 | 10 | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | 2023-04-05 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-04-05 | 2023-04-10 | 1900-01-05 | 4 | 2023-04-10 | 2023-04-10 | 1 | 1 | 25 | 19 | 7 | 5 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 77 | 77 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | -487 | -348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-30 | 2024-11-18 | IOU Designed & Installed | N/A | No | N/A | 975.73 | Unknown | Unknown | Unknown | Unknown | 975.73 | 3981 | 1101.03 | 975.73 | 125.3 | Yes | N/A | N/A | 2024-05-16 | 2024-05-20 | 5 | 3 | 2024-05-20 | 2024-05-30 | 11 | 9 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-11-18 | 173 | 123 | Unknown | 2024-11-14 | Unknown | Unknown | 2024-11-18 | 2024-12-04 | 1900-01-16 | 13 | 2024-12-04 | 2024-12-04 | 1 | 1 | 178 | 126 | 29 | 23 | 207 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 82.05 | 82.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-28 | -653 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-25 | 2024-02-07 | IOU Designed & Installed | N/A | No | N/A | 13.86 | -12.33 | Unknown | Unknown | Unknown | 26.19 | Unknown | 922.06 | 13.86 | 908.2 | Yes | N/A | N/A | 2024-01-25 | 2024-01-04 | Unknown | Unknown | 2024-01-04 | 2024-01-25 | 22 | 16 | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-02-07 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-03-15 | 1900-02-06 | 28 | 2024-03-15 | 2024-03-15 | 1 | 1 | 14 | 10 | 61 | 45 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-17 | -445 | -318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | 2024-05-15 | IOU Designed & Installed | N/A | No | N/A | 13.28 | -11.78 | Unknown | Unknown | Unknown | 25.06 | 3981 | 708.72 | 13.28 | 695.44 | Yes | N/A | N/A | 2023-11-13 | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-12-05 | 99 | 71 | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2024-05-15 | 163 | 117 | Unknown | 2024-05-03 | Unknown | Unknown | 2024-05-15 | 2024-05-29 | 1900-01-14 | 11 | 2024-05-29 | 2024-05-29 | 1 | 1 | 163 | 117 | 115 | 83 | 278 | 200 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-14 | -662 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | 311.24 | Unknown | Unknown | Unknown | Unknown | 311.24 | Unknown | 498.17 | 311.24 | 186.93 | Yes | N/A | N/A | 2025-03-04 | 2025-03-03 | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-03-21 | 18 | 14 | 2025-03-10 | 2025-04-09 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-23 | 1900-01-14 | 11 | 2025-04-23 | 2025-04-23 | 1 | 1 | 31 | 23 | 34 | 26 | 65 | 49 | Steps 2,3,5,6,7 | 11 | 9 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-15 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-07 | 2024-01-07 | 2024-07-05 | IOU Designed & Installed | N/A | No | N/A | 2800.68 | 246.68 | Unknown | Unknown | 148.94 | 2405.06 | 3981 | 414.28 | 2800.68 | -2386.4 | Yes | N/A | N/A | 2024-01-07 | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2024-02-27 | 153 | 109 | 2024-02-27 | Unknown | Unknown | Unknown | 2024-02-28 | 2024-05-22 | 85 | 61 | 2024-02-27 | 2024-07-05 | 130 | 94 | Unknown | 2024-04-23 | Unknown | Unknown | 2024-07-05 | 2024-07-09 | 1900-01-04 | 3 | 2024-07-09 | 2024-07-09 | 1 | 1 | 130 | 94 | 244 | 174 | 374 | 268 | Steps 2,3,5,6,7 | 85 | 61 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-23 | -637 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | -5.41 | -22.57 | Unknown | Unknown | Unknown | 17.16 | 3981 | 2121.87 | -5.41 | 2127.28 | Yes | N/A | N/A | 2025-02-03 | 2025-02-05 | 3 | 3 | 2025-02-05 | 2025-02-10 | 6 | 4 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-26 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-03-26 | 1900-01-28 | 21 | 2025-03-26 | 2025-03-26 | 1 | 1 | 20 | 16 | 36 | 26 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Disadvantaged Community,Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-14 | 636 | 455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-22 | 2022-02-24 | 2025-05-12 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 245140.69 | 34119.39 | Unknown | Unknown | 59167.96 | 151853.34 | 0 | 125752.57 | 245140.69 | -119388.12 | Yes | N/A | N/A | 2022-02-22 | 2023-05-01 | 434 | 310 | 2023-05-01 | 2024-07-18 | 445 | 319 | 2023-06-28 | 2024-07-02 | 181 | 129 | 2024-07-12 | 2024-08-13 | 33 | 23 | 2024-09-13 | Unknown | Unknown | Unknown | 2024-09-13 | 2025-05-06 | 236 | 168 | 2025-05-12 | 2025-06-11 | 1900-01-30 | 23 | 2025-06-11 | 2025-06-11 | 1 | 1 | 615 | 439 | 746 | 534 | 1361 | 973 | Steps 2,3,5,6,7 | 386 | 276 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 21.05 | 21.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-28 | 427 | 306 | No | 2023-07-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-07-12 | 2024-06-21 | IOU Designed & Installed | N/A | Yes | 322 | 2162.55 | -7.67 | Unknown | Unknown | Unknown | 2170.22 | 3941 | 804.45 | 2162.55 | -1358.1 | Yes | N/A | N/A | 2023-07-12 | 2024-05-29 | 323 | 231 | 2024-05-29 | 2023-07-12 | Unknown | Unknown | 2023-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-12 | 2024-06-21 | 346 | 248 | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-06-28 | 1900-01-07 | 6 | 2024-06-28 | 2024-06-28 | 1 | 1 | 669 | 479 | 9 | 7 | 678 | 486 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-04 | -262 | -187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-03-03 | IOU Designed & Installed | N/A | No | N/A | 4154.45 | -20.79 | Unknown | Unknown | Unknown | 4175.24 | Unknown | 2450.69 | 4154.45 | -1703.76 | Yes | N/A | N/A | 2023-02-13 | 2023-02-13 | 1 | 1 | 2023-02-13 | 2023-02-22 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | 2023-03-17 | 1900-01-14 | 11 | 2023-03-17 | 2023-03-17 | 1 | 1 | 1 | 1 | 26 | 20 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 1309.05 | 1309.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-07-31 | -555 | -398 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2023-12-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 810.44 | 254.58 | Unknown | 88.44 | Unknown | 467.42 | Unknown | 206.56 | 810.44 | -603.88 | Yes | N/A | N/A | 2023-12-21 | 2023-11-09 | Unknown | Unknown | 2023-11-09 | 2023-12-21 | 43 | 31 | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | Unknown | Unknown | 2024-01-23 | 2024-01-23 | 1 | 1 | 0 | 0 | 44 | 32 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | 65 | 47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-08-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3056.02 | -70.81 | Unknown | Unknown | 47.21 | 3079.62 | 3981 | 2409.7 | 3056.02 | -646.32 | Yes | N/A | N/A | 2023-08-23 | 2023-08-23 | 1 | 1 | 2023-08-23 | 2023-09-25 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | 2024-02-01 | 130 | 94 | Unknown | 2024-01-12 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-05 | Unknown | Unknown | 131 | 95 | 34 | 24 | 165 | 119 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | -261 | -186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-17 | 2022-08-17 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | 873743.23 | 226313.39 | Unknown | 3897.99 | 24143.2 | 619388.65 | 3070018.15 | 349844.4 | 873743.23 | -523898.83 | Yes | N/A | N/A | 2022-08-17 | 2023-05-01 | 258 | 184 | 2023-05-01 | 2024-01-22 | 267 | 191 | 2023-09-18 | 2025-06-23 | 14 | 10 | 2023-10-13 | 2024-01-31 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2025-05-30 | 486 | 348 | 2025-04-07 | 2025-05-16 | 1900-02-08 | 30 | 2025-05-16 | 2025-05-16 | 1 | 1 | 272 | 194 | 812 | 584 | 1084 | 778 | Steps 2,3,5,6,7 | 798 | 570 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | -605 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-12 | 2024-11-12 | IOU Designed & Installed | N/A | No | N/A | 2188.53 | Unknown | Unknown | Unknown | 5.25 | 2183.28 | 3981 | 1130.51 | 2188.53 | -1058.02 | Yes | N/A | N/A | 2024-08-09 | 2024-07-24 | Unknown | Unknown | 2024-07-24 | 2024-09-19 | 58 | 42 | 2024-09-19 | 2024-10-11 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-11-12 | 55 | 39 | Unknown | 2024-11-08 | Unknown | Unknown | 2024-11-12 | 2024-11-21 | 1900-01-09 | 8 | 2024-11-21 | 2024-11-21 | 1 | 1 | 78 | 56 | 69 | 51 | 147 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 97 | 97 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-08 | 75 | 55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-16 | 2024-11-22 | IOU Designed & Installed | N/A | No | N/A | 2383.46 | 825.48 | Unknown | Unknown | Unknown | 1557.98 | 3981 | 987.21 | 2383.46 | -1396.25 | Yes | N/A | N/A | 2024-02-16 | 2024-02-22 | 7 | 5 | 2024-02-22 | 2024-02-23 | 2 | 2 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-11-22 | 274 | 196 | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2024-11-22 | 1899-12-31 | 1 | 2024-11-22 | 2024-11-22 | 1 | 1 | 281 | 201 | 4 | 4 | 285 | 205 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | -479 | -343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 415.1 | -15.11 | Unknown | Unknown | -419 | 849.21 | 1786.6 | 2083.25 | 415.1 | 1668.15 | Yes | N/A | N/A | 2024-09-23 | 2024-09-20 | Unknown | Unknown | 2024-09-20 | 2024-12-05 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-12-02 | 55 | 39 | 2024-12-05 | 2025-01-16 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | Unknown | Unknown | 2025-02-12 | 2025-02-12 | 1 | 1 | 43 | 31 | 133 | 95 | 176 | 126 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-22 | -695 | -498 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2024-10-31 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 662.41 | -13.2 | Unknown | Unknown | Unknown | 675.61 | 3981 | 1558.09 | 662.41 | 895.68 | Yes | N/A | N/A | 2024-10-31 | 2024-10-31 | 1 | 1 | 2024-10-31 | 2024-10-31 | 1 | 1 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2024-11-05 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2024-11-26 | 1900-01-21 | 16 | 2024-11-26 | 2024-11-26 | 1 | 1 | 7 | 5 | 24 | 18 | 31 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-30 | 33 | 24 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-09 | 2024-02-09 | 2024-04-30 | IOU Designed & Installed | N/A | No | N/A | 648.21 | -21.82 | Unknown | Unknown | Unknown | 670.03 | 3981 | 627.73 | 648.21 | -20.48 | Yes | N/A | N/A | 2024-02-09 | 2024-02-09 | 1 | 1 | 2024-02-09 | 2024-02-12 | 4 | 2 | 2024-02-12 | Unknown | Unknown | Unknown | 2024-02-12 | 2024-02-16 | 5 | 5 | 2024-02-09 | 2024-04-30 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2024-05-02 | 1900-01-02 | 3 | 2024-05-02 | 2024-05-02 | 1 | 1 | 83 | 59 | 13 | 11 | 96 | 70 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | DEL MAR | 81 | 81 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-21 | -530 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-03-01 | 2024-06-18 | IOU Designed & Installed | N/A | No | N/A | 15593.04 | 3974.5 | Unknown | Unknown | Unknown | 11618.54 | 3981 | 2909.18 | 15593.04 | -12683.86 | Yes | N/A | N/A | 2024-02-21 | 2023-12-27 | Unknown | Unknown | 2023-12-27 | 2024-03-06 | 71 | 51 | 2024-03-06 | Unknown | Unknown | Unknown | 2024-03-06 | 2024-03-25 | 20 | 14 | 2024-03-06 | 2024-06-18 | 105 | 75 | Unknown | 2024-05-22 | Unknown | Unknown | 2024-06-18 | 2024-07-09 | 1900-01-21 | 16 | 2024-07-09 | 2024-07-09 | 1 | 1 | 105 | 75 | 114 | 82 | 219 | 157 | Steps 2,3,5,6,7 | 19 | 13 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-02 | -37 | -27 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-12 | 2023-06-12 | 2023-12-21 | IOU Designed & Installed | N/A | No | N/A | 712.78 | -11.44 | Unknown | Unknown | 20.53 | 703.69 | Unknown | 922.26 | 712.78 | 209.48 | Yes | N/A | N/A | 2023-06-12 | 2023-06-28 | 17 | 13 | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-12-21 | 177 | 127 | Unknown | 2023-12-20 | Unknown | Unknown | 2023-12-21 | 2024-01-26 | 1900-02-05 | 27 | 2024-01-26 | 2024-01-25 | Unknown | Unknown | 194 | 140 | 37 | 27 | 231 | 167 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-02 | -566 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-16 | 2024-02-09 | IOU Designed & Installed | N/A | No | N/A | -6.32 | -5.12 | Unknown | Unknown | Unknown | -1.2 | 3981 | 483.59 | -6.32 | 489.91 | Yes | N/A | N/A | 2024-01-02 | 2023-10-20 | Unknown | Unknown | 2023-10-20 | 2024-01-16 | 89 | 63 | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-02-09 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-03-15 | 1900-02-04 | 26 | 2024-03-15 | 2024-03-15 | 1 | 1 | 25 | 19 | 126 | 90 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | -549 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-10-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 327.24 | -12.86 | Unknown | Unknown | Unknown | 340.1 | 3981 | 829.06 | 327.24 | 501.82 | Yes | N/A | N/A | 2023-10-18 | 2023-07-15 | Unknown | Unknown | 2023-07-15 | 2023-10-20 | 98 | 70 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | Unknown | Unknown | 2024-05-17 | 2024-05-15 | Unknown | Unknown | 0 | 0 | 98 | 70 | 98 | 70 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-17 | -469 | -336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2023-12-08 | 2024-03-26 | IOU Designed & Installed | N/A | No | N/A | -6.07 | -6 | Unknown | Unknown | Unknown | -0.07 | 3981 | 163.83 | -6.07 | 169.9 | Yes | N/A | N/A | 2023-12-08 | 2023-12-12 | 5 | 3 | 2023-12-12 | 2024-03-02 | 82 | 59 | 2024-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-02 | 2024-03-26 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-06-05 | 1900-03-12 | 52 | 2024-06-05 | 2024-06-05 | 1 | 1 | 30 | 20 | 155 | 112 | 185 | 132 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-27 | -612 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-17 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | 307.4 | -15.78 | Unknown | Unknown | 2.17 | 321.01 | 3981 | 788.11 | 307.4 | 480.71 | Yes | N/A | N/A | 2024-04-10 | 2024-03-13 | Unknown | Unknown | 2024-03-13 | 2024-04-25 | 44 | 32 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-05-30 | 36 | 26 | Unknown | 2024-05-29 | Unknown | Unknown | 2024-05-30 | 2024-06-25 | 1900-01-26 | 19 | 2024-06-25 | 2024-06-25 | 1 | 1 | 36 | 26 | 72 | 52 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-31 | -150 | -109 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-23 | 2024-09-24 | 2025-05-30 | IOU Designed & Installed | N/A | No | N/A | 429.39 | Unknown | Unknown | Unknown | 24.16 | 405.23 | 3941 | 298.35 | 429.39 | -131.04 | Yes | N/A | N/A | 2024-09-23 | 2024-10-23 | 31 | 23 | 2024-10-23 | 2024-11-01 | 10 | 8 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2025-05-30 | 211 | 151 | Unknown | 2025-05-01 | Unknown | Unknown | 2025-05-30 | 2025-06-04 | 1900-01-05 | 4 | 2025-06-04 | 2025-06-03 | Unknown | Unknown | 242 | 174 | 16 | 12 | 258 | 186 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-24 | -544 | -389 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-04-08 | 2024-04-23 | IOU Designed & Installed | N/A | No | N/A | 342.98 | -26.85 | Unknown | Unknown | Unknown | 369.83 | 3981 | 850.42 | 342.98 | 507.44 | Yes | N/A | N/A | 2024-04-08 | 2023-12-06 | Unknown | Unknown | 2023-12-06 | 2024-04-17 | 134 | 96 | 2024-04-17 | Unknown | Unknown | Unknown | 2024-04-17 | 2024-05-03 | 17 | 13 | 2024-04-17 | 2024-04-23 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-05-29 | 1900-02-05 | 27 | 2024-05-29 | 2024-05-29 | 1 | 1 | 7 | 5 | 189 | 137 | 196 | 142 | Steps 2,3,5,6,7 | 16 | 12 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-06 | -28 | -21 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3833.71 | 1133.83 | Unknown | 9.55 | 27.96 | 2662.37 | 3981 | 2653.76 | 3833.71 | -1179.95 | Yes | N/A | N/A | 2023-03-06 | 2023-06-07 | 94 | 68 | 2023-06-07 | Unknown | Unknown | Unknown | 2024-09-11 | 2024-09-11 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | Unknown | Unknown | Unknown | 2024-09-28 | Unknown | Unknown | 2024-09-28 | 2024-08-09 | Unknown | Unknown | 95 | 69 | 0 | 0 | 95 | 69 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 113.05 | 113.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-25 | -322 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 982.88 | 319 | Unknown | 75.73 | -480 | 1068.15 | 3981 | 2636.63 | 982.88 | 1653.75 | Yes | N/A | N/A | 2024-02-20 | 2024-02-20 | 1 | 1 | 2024-02-20 | 2024-02-20 | 1 | 1 | 2024-02-20 | 2024-06-06 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-07-25 | 50 | 36 | Unknown | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-08-07 | 1900-01-13 | 10 | 2024-08-07 | 2024-08-07 | 1 | 1 | 159 | 115 | 16 | 12 | 175 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-06 | 100 | 71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-18 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 3810.62 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-18 | 2023-04-18 | 1 | 1 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 41 | 41 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | 230 | 165 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-17 | 2025-03-13 | IOU Designed & Installed | N/A | No | N/A | 12255.85 | Unknown | Unknown | Unknown | Unknown | 12255.85 | 7962 | 958.67 | 12255.85 | -11297.18 | Yes | N/A | N/A | 2024-05-17 | 2024-05-21 | 5 | 3 | 2024-05-21 | 2024-10-22 | 155 | 111 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2025-02-18 | 120 | 86 | Unknown | 2025-02-21 | Unknown | Unknown | 2025-03-13 | 2025-04-07 | 1900-01-25 | 18 | 2025-04-07 | 2025-04-02 | Unknown | Unknown | 125 | 89 | 181 | 129 | 306 | 218 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-15 | 167 | 120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-06-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 66.79 | Unknown | Unknown | Unknown | Unknown | 66.79 | 3981 | 1157.53 | 66.79 | 1090.74 | Yes | N/A | N/A | 2024-06-28 | 2024-08-13 | 47 | 33 | 2024-08-13 | 2024-08-29 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-09-13 | 32 | 24 | 2024-08-29 | 2024-10-29 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | Unknown | Unknown | 2024-10-30 | 2024-10-29 | Unknown | Unknown | 109 | 77 | 49 | 37 | 158 | 114 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-19 | -247 | -178 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-04 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | -13.8 | -10.13 | Unknown | Unknown | Unknown | -3.67 | Unknown | 149.82 | -13.8 | 163.62 | Yes | N/A | N/A | 2023-10-04 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2023-10-04 | 8 | 6 | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-10-11 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2023-11-15 | 1900-02-04 | 26 | 2023-11-15 | 2023-11-15 | 1 | 1 | 7 | 5 | 45 | 33 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-02-25 | 616 | 441 | No | 2019-03-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2019-03-12 | 2019-03-12 | Unknown | IOU Designed & Installed | N/A | Yes | 1562 | -6.54 | -4.42 | Unknown | Unknown | Unknown | -2.12 | 13817 | 295.72 | -6.54 | 302.26 | Yes | N/A | N/A | 2019-03-12 | 2023-06-21 | 1563 | 1117 | 2023-06-21 | 2023-06-21 | 1 | 1 | 2023-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2019-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-11-02 | Unknown | Unknown | 2021-11-02 | 2021-11-02 | Unknown | Unknown | 1563 | 1117 | 1 | 1 | 1564 | 1118 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | -535 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-08 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 1175.16 | 378.69 | Unknown | Unknown | Unknown | 796.47 | Unknown | 1022.67 | 1175.16 | -152.49 | Yes | N/A | N/A | 2024-02-07 | 2023-10-17 | Unknown | Unknown | 2023-10-17 | 2024-02-08 | 115 | 83 | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-04-15 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-04-17 | 1900-01-02 | 3 | 2024-04-17 | 2024-04-17 | 1 | 1 | 68 | 48 | 119 | 87 | 187 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-19 | -356 | -255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-08 | 2024-04-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 656.34 | Unknown | Unknown | Unknown | 44.16 | 612.18 | 3981 | 1883.61 | 656.34 | 1227.27 | Yes | N/A | N/A | 2024-04-08 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-04-12 | 44 | 32 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | 2025-02-26 | 2025-02-28 | 3 | 3 | 0 | 0 | 47 | 35 | 47 | 35 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-09 | -559 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-05-26 | IOU Designed & Installed | N/A | No | N/A | 647.19 | 237.76 | Unknown | Unknown | Unknown | 409.43 | 3981 | 363.72 | 647.19 | -283.47 | Yes | N/A | N/A | 2023-03-20 | 2023-03-20 | 1 | 1 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | 2023-05-26 | 68 | 50 | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | 2023-05-30 | 1900-01-04 | 3 | 2023-05-30 | 2023-05-30 | 1 | 1 | 69 | 51 | 6 | 4 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 79.05 | 79.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-14 | -457 | -326 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-14 | 2025-02-14 | IOU Designed & Installed | N/A | No | N/A | 38.37 | Unknown | Unknown | Unknown | Unknown | 38.37 | 3981 | 1650.5 | 38.37 | 1612.13 | Yes | N/A | N/A | 2024-11-13 | 2024-11-14 | 2 | 2 | 2024-11-14 | 2024-11-14 | 1 | 1 | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2025-02-14 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-02-20 | 1900-01-06 | 5 | 2025-02-20 | 2025-03-14 | 23 | 17 | 95 | 69 | 31 | 23 | 126 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-27 | -677 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-08-31 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 397.19 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-31 | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-09-01 | 4 | 4 | 2023-09-01 | Unknown | Unknown | Unknown | 2023-08-31 | 2023-09-29 | 30 | 22 | 2023-09-01 | 2023-10-13 | 43 | 31 | Unknown | 2023-09-12 | Unknown | Unknown | 2023-10-13 | 2025-07-16 | 1901-10-04 | 459 | 2025-07-16 | 2023-10-20 | Unknown | Unknown | 43 | 31 | 677 | 485 | 720 | 516 | Steps 2,3,5,6,7 | 28 | 20 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-24 | -172 | -124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -7.45 | -5.39 | Unknown | Unknown | Unknown | -2.06 | 3981 | 153.75 | -7.45 | 161.2 | Yes | N/A | N/A | 2023-04-21 | 2023-05-18 | 28 | 20 | 2023-05-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | Unknown | Unknown | 2023-09-05 | 2023-09-05 | 1 | 1 | 28 | 20 | 1 | 1 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | N/A | POWAY | POWAY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-06 | -25 | -19 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-17 | 2024-02-20 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 8937.81 | 882.63 | Unknown | Unknown | -9990 | 18045.18 | 97623.22 | 40843.93 | 8937.81 | 31906.12 | Yes | N/A | N/A | 2023-05-09 | 2023-08-15 | 99 | 71 | 2023-08-15 | 2023-10-17 | 64 | 46 | 2023-08-29 | 2023-09-21 | 24 | 18 | 2023-08-31 | 2023-10-20 | 6 | 6 | 2023-10-17 | Unknown | Unknown | Unknown | 2023-10-31 | 2023-12-07 | 38 | 28 | 2024-02-20 | 2024-03-12 | 1900-01-21 | 16 | 2024-03-12 | 2024-03-12 | 1 | 1 | 123 | 89 | 131 | 97 | 254 | 186 | Steps 2,3,5,6,7 | 73 | 53 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 695.05 | 695.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-29 | -288 | -207 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 32.2 | Unknown | Unknown | Unknown | Unknown | 32.2 | 3941 | 832.35 | 32.2 | 800.15 | Yes | N/A | N/A | 2023-12-12 | 2023-11-09 | Unknown | Unknown | 2023-11-09 | 2023-12-12 | 34 | 24 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2024-07-11 | 213 | 153 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-08-07 | 1900-01-27 | 20 | 2024-08-07 | 2024-08-14 | 8 | 6 | 213 | 153 | 70 | 50 | 283 | 203 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-27 | -532 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-27 | 2024-02-23 | IOU Designed & Installed | N/A | No | N/A | 892.21 | 290.64 | Unknown | 28.33 | Unknown | 573.24 | 3981 | 1062.15 | 892.21 | 169.94 | Yes | N/A | N/A | 2023-12-13 | 2023-12-27 | 15 | 11 | 2023-12-27 | 2023-12-27 | 1 | 1 | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2024-02-23 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-03-13 | 1900-01-19 | 14 | 2024-03-13 | 2024-03-13 | 1 | 1 | 74 | 54 | 22 | 16 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -224 | -161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 388.34 | -7.44 | Unknown | Unknown | Unknown | 395.78 | Unknown | 466.88 | 388.34 | 78.54 | Yes | N/A | N/A | 2024-04-30 | 2024-05-02 | 3 | 3 | 2024-05-02 | 2024-07-10 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-12 | 27 | 19 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | 2024-09-11 | 2024-09-11 | 1 | 1 | 3 | 3 | 98 | 70 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 221.1 | 221.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | -330 | -237 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-08-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2427.28 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-11 | 2024-07-30 | 50 | 36 | 2024-07-30 | 2024-09-30 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2025-01-15 | 108 | 78 | Unknown | 2025-05-16 | Unknown | Unknown | Unknown | 2025-05-21 | Unknown | Unknown | 2025-05-21 | 2025-05-20 | Unknown | Unknown | 158 | 114 | 63 | 45 | 221 | 159 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-10 | -565 | -404 | No | 2024-06-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-08-05 | 2024-10-08 | IOU Designed & Installed | N/A | Yes | 119 | 28.47 | Unknown | Unknown | Unknown | Unknown | 28.47 | 3981 | 951.76 | 28.47 | 923.29 | Yes | N/A | N/A | 2024-06-19 | 2024-10-16 | 120 | 86 | 2024-10-16 | 2024-08-06 | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | Unknown | 2024-08-07 | 2024-09-04 | 29 | 21 | 2024-08-07 | 2024-10-08 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-22 | 1900-01-14 | 11 | 2024-10-22 | 2024-10-22 | 1 | 1 | 183 | 131 | 45 | 33 | 228 | 164 | Steps 2,3,5,6,7 | 28 | 20 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-27 | 109 | 78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.79 | -20.11 | Unknown | Unknown | Unknown | 15.32 | 0 | 1196.35 | -4.79 | 1201.14 | Yes | N/A | N/A | 2024-04-10 | 2024-04-23 | 14 | 10 | 2024-04-23 | 2024-04-25 | 3 | 3 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | 2025-04-15 | 2025-04-15 | 1 | 1 | 14 | 10 | 4 | 4 | 18 | 14 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-04 | -106 | -77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-29 | 2023-12-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4969.94 | -5.91 | Unknown | Unknown | -5871 | 906.97 | Unknown | 4191.42 | -4969.94 | 9161.36 | Yes | N/A | N/A | 2023-12-29 | 2023-12-29 | 1 | 1 | 2023-12-29 | 2024-02-07 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | 2024-01-03 | 6 | 4 | 2024-02-07 | 2024-08-19 | 195 | 139 | Unknown | 2024-06-12 | Unknown | Unknown | Unknown | 2024-08-20 | Unknown | Unknown | 2024-08-20 | 2024-08-20 | 1 | 1 | 196 | 140 | 48 | 34 | 244 | 174 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-19 | -343 | -246 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | 2024-08-20 | IOU Designed & Installed | N/A | No | N/A | 1620.22 | -31.4 | Unknown | Unknown | Unknown | 1651.62 | Unknown | 2248.91 | 1620.22 | 628.69 | Yes | N/A | N/A | 2024-08-20 | 2024-08-19 | Unknown | Unknown | 2024-08-19 | 2024-08-20 | 2 | 2 | 2024-08-20 | 2024-09-04 | 15 | 11 | 2024-09-04 | 2024-09-05 | 2 | 2 | 2024-08-20 | 2024-08-20 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-09-10 | 1900-01-21 | 16 | 2024-09-10 | 2024-09-10 | 1 | 1 | 16 | 12 | 27 | 21 | 43 | 33 | Steps 2,3,5,6,7 | 16 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-02 | -475 | -340 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-01-30 | 2025-02-27 | IOU Designed & Installed | N/A | No | N/A | 21025.77 | 273.47 | Unknown | Unknown | -1549 | 22301.3 | 3981 | 2800.14 | 21025.77 | -18225.63 | Yes | N/A | N/A | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | 2025-01-30 | 1 | 1 | 2025-01-30 | 2025-02-03 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-27 | 25 | 19 | Unknown | 2025-02-21 | Unknown | Unknown | 2025-02-27 | 2025-04-21 | 1900-02-22 | 38 | 2025-04-21 | 2025-04-14 | Unknown | Unknown | 31 | 23 | 55 | 39 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | -562 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-22 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 5.01 | -3.88 | Unknown | Unknown | Unknown | 8.89 | Unknown | 308.87 | 5.01 | 303.86 | Yes | N/A | N/A | 2024-03-12 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | 2024-03-22 | 44 | 32 | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-07-02 | 103 | 73 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-18 | 1900-01-16 | 13 | 2024-07-18 | 2024-07-18 | 1 | 1 | 103 | 73 | 62 | 46 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-15 | -408 | -292 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | 2023-11-29 | IOU Designed & Installed | N/A | No | N/A | 3030.69 | Unknown | Unknown | Unknown | Unknown | 3030.69 | Unknown | 467.99 | 3030.69 | -2562.7 | Yes | N/A | N/A | 2023-10-31 | 2023-10-31 | 1 | 1 | 2023-10-31 | 2023-11-02 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2024-01-04 | 1900-02-05 | 27 | 2024-01-04 | 2024-01-04 | 1 | 1 | 1 | 1 | 41 | 31 | 42 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-22 | 83 | 60 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-02-07 | 2024-03-04 | IOU Designed & Installed | N/A | No | N/A | -7.98 | -6.47 | Unknown | Unknown | Unknown | -1.51 | Unknown | 534.53 | -7.98 | 542.51 | Yes | N/A | N/A | 2024-01-24 | 2024-02-07 | 15 | 11 | 2024-02-07 | 2024-02-07 | 1 | 1 | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-03-04 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-03-15 | 1900-01-11 | 10 | 2024-03-15 | 2024-03-14 | Unknown | Unknown | 42 | 30 | 13 | 11 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 55.05 | 55.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -446 | -319 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 109.55 | Unknown | Unknown | Unknown | Unknown | 109.55 | 3981 | 1426.17 | 109.55 | 1316.62 | Yes | N/A | N/A | 2023-08-08 | 2023-09-11 | 35 | 25 | 2023-09-11 | 2023-10-30 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2024-09-11 | 318 | 228 | Unknown | 2024-08-27 | Unknown | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | 2024-09-11 | 2024-09-10 | Unknown | Unknown | 353 | 253 | 50 | 36 | 403 | 289 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1182.25 | -32.51 | Unknown | Unknown | Unknown | 1214.76 | Unknown | 499.96 | 1182.25 | -682.29 | Yes | N/A | N/A | 2023-04-06 | 2023-04-06 | 1 | 1 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | Unknown | Unknown | 2023-06-29 | 2023-06-29 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-08 | -1117 | -800 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.37 | -4.07 | Unknown | Unknown | Unknown | -1.3 | 23991 | 324.29 | -5.37 | 329.66 | Yes | N/A | N/A | 2023-03-02 | 2023-03-10 | 9 | 7 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | Unknown | Unknown | 2023-12-18 | 2023-12-18 | 1 | 1 | 9 | 7 | 1 | 1 | 10 | 8 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | -687 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-18 | 2024-09-20 | IOU Designed & Installed | N/A | No | N/A | 528.23 | -10.2 | Unknown | Unknown | Unknown | 538.43 | 3981 | 1168.21 | 528.23 | 639.98 | Yes | N/A | N/A | 2024-09-04 | 2024-09-04 | 1 | 1 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-09-26 | 9 | 7 | 2024-09-18 | 2024-09-20 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-09-25 | 1900-01-05 | 4 | 2024-09-25 | 2024-09-26 | 2 | 2 | 4 | 4 | 17 | 13 | 21 | 17 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | CARLSBAD | 260 | 260 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-11 | -22 | -16 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2024-01-05 | 2024-04-10 | IOU Designed & Installed | N/A | No | N/A | 12086.41 | Unknown | Unknown | Unknown | Unknown | 12086.41 | 3981 | 1057.28 | 12086.41 | -11029.13 | Yes | N/A | N/A | 2023-09-07 | 2023-09-18 | 12 | 8 | 2023-09-18 | 2024-04-08 | 204 | 146 | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-04-03 | 79 | 57 | 2024-04-08 | 2024-06-12 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-04-19 | 1900-01-09 | 8 | 2024-04-19 | 2024-04-19 | 1 | 1 | 78 | 56 | 294 | 212 | 372 | 268 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | -341 | -245 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | 2025-03-19 | IOU Designed & Installed | N/A | No | N/A | -4.5 | -18.79 | Unknown | Unknown | Unknown | 14.29 | 3981 | 2710.1 | -4.5 | 2714.6 | Yes | N/A | N/A | 2025-03-17 | 2025-03-14 | Unknown | Unknown | 2025-03-14 | 2025-03-17 | 4 | 2 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-03-19 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-04-07 | 1900-01-19 | 14 | 2025-04-07 | 2025-04-07 | 1 | 1 | 3 | 3 | 25 | 17 | 28 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | -391 | -280 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | 2025-02-27 | IOU Designed & Installed | N/A | No | N/A | 5919.94 | Unknown | Unknown | Unknown | Unknown | 5919.94 | Unknown | 2703.59 | 5919.94 | -3216.35 | Yes | N/A | N/A | 2025-02-05 | 2025-02-07 | 3 | 3 | 2025-02-07 | 2025-02-26 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-03-10 | 1900-01-11 | 8 | 2025-03-10 | 2025-03-10 | 1 | 1 | 3 | 3 | 33 | 23 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-05 | -710 | -509 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-06-10 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 82.83 | -9.04 | Unknown | Unknown | Unknown | 91.87 | 3981 | 1352.55 | 82.83 | 1269.72 | Yes | N/A | N/A | 2024-06-07 | 2024-06-10 | 4 | 2 | 2024-06-10 | 2024-06-10 | 1 | 1 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-06-10 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-06-25 | 1900-01-15 | 12 | 2024-06-25 | 2024-06-25 | 1 | 1 | 5 | 3 | 18 | 14 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-12 | -98 | -71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-06-21 | IOU Designed & Installed | N/A | No | N/A | 917.41 | -12.9 | Unknown | Unknown | 9.87 | 920.44 | 1000 | 642.13 | 917.41 | -275.28 | Yes | N/A | N/A | 2023-03-21 | 2023-03-21 | 1 | 1 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-06-21 | 93 | 67 | Unknown | 2023-05-17 | Unknown | Unknown | 2023-06-21 | 2023-07-06 | 1900-01-15 | 12 | 2023-07-06 | 2023-07-06 | 1 | 1 | 94 | 68 | 17 | 13 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-17 | 507 | 362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-06-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4966.45 | 352.1 | Unknown | 34.94 | -1529 | 6108.41 | 0 | 1529.2 | 4966.45 | -3437.25 | Yes | N/A | N/A | 2023-04-28 | 2023-03-01 | Unknown | Unknown | 2023-03-01 | 2025-03-10 | 741 | 529 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-04-07 | 1 | 1 | 0 | 0 | 742 | 530 | 742 | 530 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | -667 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-09-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4313.77 | 761.23 | Unknown | Unknown | 2.77 | 3549.77 | 3981 | 1206.27 | 4313.77 | -3107.5 | Yes | N/A | N/A | 2024-09-16 | 2024-09-09 | Unknown | Unknown | 2024-09-09 | 2024-09-25 | 17 | 13 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | Unknown | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | 2024-11-06 | 2024-11-06 | 1 | 1 | 0 | 0 | 18 | 14 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-01 | 783 | 560 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | 2024-02-20 | IOU Designed & Installed | N/A | No | N/A | 434.39 | -7.77 | Unknown | Unknown | 11.78 | 430.38 | 3885 | 621.49 | 434.39 | 187.1 | Yes | N/A | N/A | 2023-10-27 | 2023-08-25 | Unknown | Unknown | 2023-08-25 | 2023-10-31 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2023-12-07 | 38 | 28 | Unknown | 2023-11-22 | Unknown | Unknown | 2024-02-20 | 2024-03-15 | 1900-01-24 | 19 | 2024-03-15 | 2024-02-23 | Unknown | Unknown | 38 | 28 | 93 | 67 | 131 | 95 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 76 | 76 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-16 | -389 | -279 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 377.12 | -16.27 | Unknown | Unknown | -493 | 886.39 | 3981 | 1863.01 | 377.12 | 1485.89 | Yes | N/A | N/A | 2023-12-05 | 2023-12-05 | 1 | 1 | 2023-12-05 | 2023-12-11 | 7 | 5 | 2023-12-11 | 2024-05-16 | 158 | 114 | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | Unknown | Unknown | Unknown | 2024-07-24 | Unknown | Unknown | 2024-07-24 | 2024-07-23 | Unknown | Unknown | 159 | 115 | 7 | 5 | 166 | 120 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 3.2 | 3.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-14 | -529 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-03 | 2024-08-16 | IOU Designed & Installed | N/A | No | N/A | 1306.38 | 379.76 | Unknown | Unknown | Unknown | 926.62 | 3981 | 996.55 | 1306.38 | -309.83 | Yes | N/A | N/A | 2024-05-03 | 2024-05-04 | 2 | 1 | 2024-05-04 | 2024-05-06 | 3 | 1 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-04 | 2024-08-16 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-09-04 | 1900-01-19 | 14 | 2024-09-04 | 2024-09-03 | Unknown | Unknown | 107 | 76 | 23 | 15 | 130 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-25 | -266 | -191 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | 2023-10-05 | IOU Designed & Installed | N/A | No | N/A | 132.43 | -7.89 | Unknown | Unknown | Unknown | 140.32 | 3981 | 828.2 | 132.43 | 695.77 | Yes | N/A | N/A | 2023-09-22 | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-09-27 | 50 | 36 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-10-05 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-11-02 | 1900-01-28 | 21 | 2023-11-02 | 2023-11-02 | 1 | 1 | 9 | 7 | 80 | 58 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | LA JOLLA | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-11 | 341 | 244 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-02-29 | 2025-03-10 | IOU Designed & Installed | N/A | No | N/A | 24316.62 | 1266.05 | Unknown | Unknown | -12710 | 35760.57 | 3981 | 20458.27 | 24316.62 | -3858.35 | Yes | N/A | N/A | 2024-01-09 | 2024-02-28 | 51 | 37 | 2024-02-28 | 2024-07-09 | 133 | 95 | 2024-04-22 | 2024-04-25 | 4 | 4 | 2024-05-07 | 2025-03-10 | 277 | 199 | 2024-07-09 | Unknown | Unknown | Unknown | 2024-11-01 | 2025-02-27 | 119 | 85 | 2025-03-10 | 2025-03-18 | 1900-01-08 | 7 | 2025-03-18 | 2025-03-18 | 1 | 1 | 55 | 41 | 539 | 387 | 594 | 428 | Steps 2,3,5,6,7 | 322 | 230 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-03 | -467 | -334 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-08-02 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 260.01 | -4.39 | Unknown | Unknown | Unknown | 264.4 | 3981 | 2060.96 | 260.01 | 1800.95 | Yes | N/A | N/A | 2024-07-23 | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-08-02 | 52 | 38 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2025-02-05 | 188 | 134 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-02-21 | 1900-01-16 | 13 | 2025-02-21 | 2025-02-21 | 1 | 1 | 188 | 134 | 70 | 52 | 258 | 186 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 16.35 | 16.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | -553 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-14 | 2023-09-29 | IOU Designed & Installed | N/A | No | N/A | 688.47 | -12.47 | Unknown | Unknown | 6.68 | 694.26 | 3961 | 850.27 | 688.47 | 161.8 | Yes | N/A | N/A | 2023-08-14 | 2023-06-05 | Unknown | Unknown | 2023-06-05 | 2023-09-14 | 102 | 74 | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-09-29 | 16 | 12 | Unknown | 2023-09-28 | Unknown | Unknown | 2023-09-29 | 2023-11-28 | 1900-03-01 | 43 | 2023-11-28 | 2023-11-09 | Unknown | Unknown | 16 | 12 | 163 | 117 | 179 | 129 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-27 | -326 | -235 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-11 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 668.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-01 | 2025-03-07 | Unknown | Unknown | 2025-03-07 | 2025-04-24 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-05 | 1900-01-11 | 8 | 2025-05-05 | 2025-05-05 | 1 | 1 | 0 | 0 | 62 | 44 | 62 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-02 | 644 | 461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1385.67 | -61.89 | Unknown | Unknown | Unknown | 1447.56 | 607874 | 29673.32 | 1385.67 | 28287.65 | Yes | N/A | N/A | 2024-03-21 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2024-03-27 | 258 | 184 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-05-03 | 38 | 28 | Unknown | 2024-05-10 | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | 2024-06-10 | 2024-06-07 | Unknown | Unknown | 38 | 28 | 258 | 184 | 296 | 212 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -562 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-10 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 7.15 | Unknown | Unknown | Unknown | Unknown | 7.15 | 3961 | 192.51 | 7.15 | 185.36 | Yes | N/A | N/A | 2024-07-10 | 2024-05-31 | Unknown | Unknown | 2024-05-31 | 2024-07-26 | 57 | 41 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-10-18 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-11-05 | 1900-01-18 | 13 | 2024-11-05 | 2024-11-05 | 1 | 1 | 85 | 61 | 77 | 55 | 162 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 77 | 77 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | -473 | -338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-05-17 | 2023-08-18 | IOU Designed & Installed | N/A | No | N/A | -5.51 | -17.51 | Unknown | Unknown | 2.42 | 9.58 | 6481 | 509.4 | -5.51 | 514.91 | Yes | N/A | N/A | 2023-05-17 | 2023-05-17 | 1 | 1 | 2023-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | 2023-08-18 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | 2023-10-11 | 1900-02-23 | 39 | 2023-10-11 | 2023-10-11 | 1 | 1 | 95 | 69 | 56 | 40 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | San Ysidro | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-03-19 | 1340 | 957 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-08-25 | 2024-11-06 | IOU Designed & Installed | N/A | No | N/A | 6959.3 | 273.47 | Unknown | Unknown | -1763.35 | 8449.18 | 0 | 1404.19 | 6959.3 | -5555.11 | Yes | N/A | N/A | 2023-08-25 | 2023-08-25 | 1 | 1 | 2023-08-25 | 2023-10-02 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2023-09-01 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | Unknown | Unknown | 2024-11-06 | 2024-11-18 | 1900-01-12 | 9 | 2024-11-18 | 2024-11-18 | 1 | 1 | 1 | 1 | 58 | 42 | 59 | 43 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | San Marcos | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | 309 | 222 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-25 | 2023-05-25 | 2025-04-01 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 654601.06 | 222138.85 | Unknown | 62.91 | -110972.71 | 543372.01 | 0 | 217674.3 | 654601.06 | -436926.76 | Yes | N/A | N/A | 2023-05-25 | 2023-11-15 | 175 | 125 | 2023-11-15 | 2024-10-02 | 323 | 231 | 2024-01-24 | 2024-10-22 | 49 | 35 | 2024-01-25 | 2024-11-12 | 53 | 39 | 2024-10-09 | Unknown | Unknown | Unknown | 2024-10-09 | 2025-03-28 | 171 | 123 | 2025-04-01 | 2025-05-06 | 1900-02-04 | 26 | 2025-05-06 | 2025-05-06 | 1 | 1 | 224 | 160 | 584 | 420 | 808 | 580 | Steps 2,3,5,6,7 | 557 | 397 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-10 | -605 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-25 | 2024-02-09 | IOU Designed & Installed | N/A | No | N/A | -4.4 | -4.62 | Unknown | Unknown | Unknown | 0.22 | Unknown | 163.83 | -4.4 | 168.23 | Yes | N/A | N/A | 2024-01-25 | 2023-11-20 | Unknown | Unknown | 2023-11-20 | 2024-02-08 | 81 | 59 | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-02-09 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-03-15 | 1900-02-04 | 26 | 2024-03-15 | 2024-03-15 | 1 | 1 | 2 | 2 | 118 | 86 | 120 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 11.35 | 11.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-27 | -605 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-25 | 2025-04-21 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2379.65 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-25 | 2025-03-17 | 21 | 15 | 2025-03-17 | 2025-04-02 | 17 | 13 | 2025-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-21 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | 2025-05-01 | 1900-01-10 | 9 | 2025-05-01 | 2025-05-01 | 1 | 1 | 41 | 29 | 29 | 23 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | -500 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-04 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 6707.06 | 171.93 | Unknown | 172.73 | Unknown | 6362.4 | 3981 | 1721.69 | 6707.06 | -4985.37 | Yes | N/A | N/A | 2024-09-04 | 2024-09-17 | 14 | 10 | 2024-09-17 | 2024-09-17 | 1 | 1 | 2024-09-17 | Unknown | Unknown | Unknown | 2024-11-06 | 2024-11-20 | 15 | 11 | 2024-09-17 | 2024-11-14 | 59 | 43 | Unknown | 2024-11-13 | Unknown | Unknown | 2024-11-14 | 2024-11-21 | 1900-01-07 | 6 | 2024-11-21 | 2024-11-21 | 1 | 1 | 73 | 53 | 25 | 19 | 98 | 72 | Steps 2,3,5,6,7 | 64 | 46 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-07 | -426 | -305 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | 2024-09-11 | IOU Designed & Installed | N/A | No | N/A | 2712.55 | -3.77 | Unknown | Unknown | 86.01 | 2630.31 | 3981 | 1187.82 | 2712.55 | -1524.73 | Yes | N/A | N/A | 2024-04-02 | 2024-04-09 | 8 | 6 | 2024-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-09-11 | 148 | 106 | Unknown | 2024-09-05 | Unknown | Unknown | 2024-09-11 | 2024-10-07 | 1900-01-26 | 19 | 2024-10-07 | 2024-10-07 | 1 | 1 | 156 | 112 | 28 | 20 | 184 | 132 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | -134 | -96 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-06-02 | 2023-10-25 | IOU Designed & Installed | N/A | No | N/A | 2551.22 | 637.18 | Unknown | 736.86 | Unknown | 1177.18 | 3981 | 924.94 | 2551.22 | -1626.28 | Yes | N/A | N/A | 2023-05-23 | 2023-06-02 | 11 | 9 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | 2023-10-25 | 146 | 104 | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | 2023-11-03 | 1900-01-09 | 8 | 2023-11-03 | 2023-11-03 | 1 | 1 | 157 | 113 | 11 | 9 | 168 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-09-16 | 2025-01-08 | IOU Designed & Installed | N/A | No | N/A | 1407.11 | Unknown | Unknown | Unknown | 7.82 | 1399.29 | 3981 | 1426.22 | 1407.11 | 19.11 | Yes | N/A | N/A | 2024-09-16 | 2024-09-26 | 11 | 9 | 2024-09-26 | 2024-09-26 | 1 | 1 | 2024-09-26 | 2024-11-27 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2025-01-08 | 105 | 75 | Unknown | 2025-01-02 | Unknown | Unknown | 2025-01-08 | 2025-01-14 | 1900-01-06 | 5 | 2025-01-14 | 2025-01-14 | 1 | 1 | 179 | 129 | 9 | 7 | 188 | 136 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 96.05 | 96.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | -104 | -75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | 2023-05-08 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 1062.19 | Unknown | Unknown | Unknown | 15.54 | 1046.65 | 3981 | 2606.19 | 1062.19 | 1544 | Yes | N/A | N/A | 2023-05-08 | 2023-07-16 | 70 | 50 | 2023-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-16 | 2024-10-18 | 461 | 330 | Unknown | 2024-10-17 | Unknown | Unknown | 2024-10-18 | 2024-11-18 | 1900-01-31 | 22 | 2024-11-18 | 2024-11-15 | Unknown | Unknown | 531 | 380 | 32 | 22 | 563 | 402 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-23 | -588 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | Unknown | 2024-11-11 | IOU Designed & Installed | N/A | No | N/A | 15.58 | Unknown | Unknown | Unknown | Unknown | 15.58 | 3981 | 1752.37 | 15.58 | 1736.79 | Yes | N/A | N/A | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-11-11 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2024-12-12 | 1900-01-31 | 24 | 2024-12-12 | 2024-12-12 | 1 | 1 | 92 | 66 | 34 | 26 | 126 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 169 | 169 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | -553 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-07-20 | IOU Designed & Installed | N/A | No | N/A | -5.1 | -9.92 | Unknown | Unknown | Unknown | 4.82 | 3981 | 941.98 | -5.1 | 947.08 | Yes | N/A | N/A | 2023-04-20 | 2023-04-20 | 1 | 1 | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | 2023-07-20 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-08-04 | 1900-01-15 | 12 | 2023-08-04 | 2023-08-04 | 1 | 1 | 93 | 67 | 17 | 13 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 94.05 | 94.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-15 | -606 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | 2023-06-28 | 2023-07-18 | IOU Designed & Installed | N/A | No | N/A | -5.12 | -9.92 | Unknown | Unknown | Unknown | 4.8 | Unknown | 2686 | -5.12 | 2691.12 | Yes | N/A | N/A | 2023-06-28 | 2023-06-28 | 1 | 1 | 2023-06-28 | 2023-06-28 | 1 | 1 | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-07-18 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-07-18 | 1899-12-31 | 1 | 2023-07-18 | 2023-07-18 | 1 | 1 | 22 | 16 | 3 | 3 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 585 | 420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 4382.94 | Unknown | Unknown | Unknown | -1226 | 5608.94 | Unknown | 1038.92 | 4382.94 | -3344.02 | Yes | N/A | N/A | 2024-03-11 | 2024-03-11 | 1 | 1 | 2024-03-11 | 2024-04-29 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | 2024-09-24 | 149 | 107 | Unknown | 2024-10-01 | Unknown | Unknown | 2024-10-24 | 2024-11-14 | 1900-01-21 | 16 | 2024-11-14 | 2024-10-25 | Unknown | Unknown | 150 | 108 | 72 | 52 | 222 | 160 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-09 | -209 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-08 | 2022-12-08 | 2024-02-28 | IOU Designed & Installed | N/A | No | N/A | 712.56 | -6.54 | Unknown | Unknown | 21.78 | 697.32 | 3981 | 1162.45 | 712.56 | 449.89 | Yes | N/A | N/A | 2022-12-08 | 2023-04-17 | 131 | 93 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | 2024-02-28 | 318 | 228 | Unknown | 2024-01-26 | Unknown | Unknown | 2024-02-28 | 2024-03-14 | 1900-01-15 | 12 | 2024-03-14 | 2024-03-14 | 1 | 1 | 449 | 321 | 17 | 13 | 466 | 334 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | -539 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 2212.75 | Unknown | Unknown | Unknown | 25.87 | 2186.88 | 3981 | 1166.16 | 2212.75 | -1046.59 | Yes | N/A | N/A | 2024-10-29 | 2024-11-13 | 16 | 12 | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2025-03-06 | 114 | 82 | Unknown | 2025-03-03 | Unknown | Unknown | 2025-03-06 | 2025-04-01 | 1900-01-26 | 19 | 2025-04-01 | 2025-03-21 | Unknown | Unknown | 130 | 94 | 28 | 20 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | -526 | -377 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-03-03 | 2025-05-14 | IOU Designed & Installed | N/A | No | N/A | 602.91 | -1.5 | Unknown | Unknown | Unknown | 604.41 | Unknown | 1912.16 | 602.91 | 1309.25 | Yes | N/A | N/A | 2025-02-18 | 2025-02-19 | 2 | 2 | 2025-02-19 | 2025-03-03 | 13 | 9 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-05-14 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-05-22 | 1900-01-08 | 7 | 2025-05-22 | 2025-05-22 | 1 | 1 | 75 | 55 | 23 | 17 | 98 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | 72.05 | 72.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | 79 | 56 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-22 | 2023-11-21 | IOU Designed & Installed | N/A | No | N/A | 2012.59 | 483.86 | Unknown | 578.27 | 23.73 | 926.73 | 3241 | 817.72 | 2012.59 | -1194.87 | Yes | N/A | N/A | 2023-08-02 | 2023-08-22 | 21 | 15 | 2023-08-22 | 2023-08-22 | 1 | 1 | 2023-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | 2023-11-21 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2024-02-06 | 1900-03-18 | 56 | 2024-02-06 | 2023-12-18 | Unknown | Unknown | 113 | 81 | 79 | 57 | 192 | 138 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 76 | 76 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | -675 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-08 | 2025-04-16 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | 2931.23 | 521.68 | Unknown | 206.26 | Unknown | 2203.29 | Unknown | 2197.7 | 2931.23 | -733.53 | Yes | N/A | N/A | 2025-04-08 | 2025-03-31 | Unknown | Unknown | 2025-03-31 | 2025-04-16 | 17 | 13 | 2025-04-16 | Unknown | Unknown | Unknown | 2025-04-16 | 2025-05-07 | 22 | 16 | 2025-04-16 | 2025-05-20 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-05-20 | 1899-12-31 | 1 | 2025-05-20 | 2025-05-20 | 1 | 1 | 35 | 25 | 41 | 31 | 76 | 56 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-12 | -511 | -366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | 2023-09-05 | 2023-12-15 | IOU Designed & Installed | N/A | No | N/A | -5.12 | -4.96 | Unknown | Unknown | Unknown | -0.16 | Unknown | 153.83 | -5.12 | 158.95 | Yes | N/A | N/A | 2023-09-05 | 2023-09-21 | 17 | 13 | 2023-09-21 | 2023-09-21 | 1 | 1 | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2023-12-15 | 86 | 62 | Unknown | 2023-12-12 | Unknown | Unknown | 2023-12-15 | 2024-01-18 | 1900-02-03 | 25 | 2024-01-18 | 2024-01-18 | 1 | 1 | 103 | 75 | 37 | 27 | 140 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | -264 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-10-23 | 2025-03-12 | IOU Designed & Installed | N/A | No | N/A | 20763.38 | 2603.43 | Unknown | Unknown | 8.95 | 18151 | Unknown | 13357.08 | 20763.38 | -7406.3 | Yes | N/A | N/A | 2024-06-06 | 2024-10-03 | 120 | 86 | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-02-14 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-03-31 | 1900-01-19 | 14 | 2025-03-31 | 2025-03-31 | 1 | 1 | 120 | 86 | 63 | 45 | 183 | 131 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | San Diego | San Diego | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-03 | -118 | -85 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-07-12 | 2024-02-12 | IOU Designed & Installed | N/A | No | N/A | 63427.95 | 32388.14 | Unknown | 385.13 | -123551 | 154205.68 | Unknown | 117993.14 | 63427.95 | 54565.19 | Yes | N/A | N/A | 2023-07-12 | 2023-07-13 | 2 | 2 | 2023-07-13 | 2023-12-19 | 160 | 114 | 2023-08-15 | Unknown | Unknown | Unknown | 2023-11-02 | 2024-01-08 | 26 | 18 | 2024-02-07 | Unknown | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | Unknown | 2024-02-12 | 2024-03-07 | 1900-01-24 | 19 | 2024-03-07 | 2024-03-07 | 1 | 1 | 2 | 2 | 212 | 152 | 214 | 154 | Steps 2,3,5,6,7 | 126 | 90 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | 184 | 132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-27 | 2021-12-27 | 2024-12-03 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 328311.16 | 75437.25 | Unknown | Unknown | 15504.98 | 237368.93 | 0 | 99040.01 | 328311.16 | -229271.15 | Yes | N/A | N/A | 2021-12-27 | 2023-06-28 | 549 | 393 | 2023-06-28 | 2024-04-16 | 294 | 210 | 2023-09-12 | 2024-03-28 | 103 | 75 | 2024-04-03 | 2024-05-15 | 29 | 21 | 2024-04-23 | Unknown | Unknown | Unknown | 2024-04-23 | 2024-11-05 | 197 | 141 | 2024-12-03 | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2024-08-03 | 1 | 0 | 652 | 468 | 521 | 372 | 1173 | 840 | Steps 2,3,5,6,7 | 239 | 171 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | -673 | -482 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | 2024-10-18 | IOU Designed & Installed | N/A | No | N/A | 43.84 | Unknown | Unknown | Unknown | Unknown | 43.84 | 3981 | 1667.18 | 43.84 | 1623.34 | Yes | N/A | N/A | 2024-10-02 | 2024-10-02 | 1 | 1 | 2024-10-02 | 2024-10-02 | 1 | 1 | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-10-18 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-11-07 | 1900-01-20 | 15 | 2024-11-07 | 2024-11-07 | 1 | 1 | 18 | 14 | 23 | 17 | 41 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | -637 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | 2024-10-30 | IOU Designed & Installed | N/A | No | N/A | 23.76 | Unknown | Unknown | Unknown | Unknown | 23.76 | 3981 | 1364.84 | 23.76 | 1341.08 | Yes | N/A | N/A | 2024-09-03 | 2024-09-03 | 1 | 1 | 2024-09-03 | 2024-09-04 | 2 | 2 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-10-30 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2024-11-15 | 1900-01-16 | 13 | 2024-11-15 | 2024-11-15 | 1 | 1 | 59 | 43 | 20 | 16 | 79 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | 310 | 223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-08-07 | 2025-05-01 | IOU Designed & Installed | N/A | No | N/A | 1858.71 | Unknown | Unknown | Unknown | -474 | 2332.71 | 0 | 1107.29 | 1858.71 | -751.42 | Yes | N/A | N/A | 2023-05-18 | 2023-03-22 | Unknown | Unknown | 2023-03-22 | 2024-05-29 | 435 | 311 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | 2025-05-01 | 2025-05-07 | 1900-01-06 | 5 | 2025-05-07 | 2025-05-07 | 1 | 1 | 0 | 0 | 443 | 317 | 443 | 317 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-29 | -625 | -446 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-16 | 2024-06-28 | IOU Designed & Installed | N/A | No | N/A | 647.91 | -18.94 | Unknown | Unknown | Unknown | 666.85 | 3981 | 1206.42 | 647.91 | 558.51 | Yes | N/A | N/A | 2024-05-14 | 2024-04-08 | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-05-22 | 7 | 5 | 2024-05-16 | 2024-06-28 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-15 | 1900-01-17 | 12 | 2024-07-15 | 2024-07-12 | Unknown | Unknown | 44 | 32 | 25 | 17 | 69 | 49 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -366 | -262 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-04-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | -861.74 | -16.5 | Unknown | Unknown | -863 | 17.76 | 3981 | 1296.42 | -861.74 | 2158.16 | Yes | N/A | N/A | 2023-03-15 | 2023-04-11 | 28 | 20 | 2023-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | Unknown | Unknown | Unknown | 2024-02-01 | Unknown | Unknown | 2024-02-01 | 2024-02-01 | 1 | 1 | 28 | 20 | 1 | 1 | 29 | 21 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -508 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | 2025-03-27 | IOU Designed & Installed | N/A | No | N/A | 1121.8 | Unknown | Unknown | Unknown | -1134.52 | 2256.32 | Unknown | 1150.65 | 1121.8 | 28.85 | Yes | N/A | N/A | 2024-10-17 | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2024-11-15 | 52 | 38 | 2024-11-15 | 2025-02-04 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-03-27 | 49 | 35 | Unknown | 2025-03-10 | Unknown | Unknown | 2025-03-27 | 2025-04-09 | 1900-01-13 | 10 | 2025-04-09 | 2025-04-08 | Unknown | Unknown | 131 | 93 | 66 | 48 | 197 | 141 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-11 | -604 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1798.53 | -8.72 | Unknown | Unknown | Unknown | 1807.25 | Unknown | 363.72 | 1798.53 | -1434.81 | Yes | N/A | N/A | 2023-03-15 | 2023-03-15 | 1 | 1 | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 28.35 | 28.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-15 | -218 | -157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2025-03-21 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | 2376.38 | -47.63 | Unknown | Unknown | 6.57 | 2417.44 | 3981 | 1111.41 | 2376.38 | -1264.97 | Yes | N/A | N/A | 2024-12-13 | 2025-03-21 | 99 | 71 | 2025-03-21 | 2025-03-21 | 1 | 1 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-06-10 | 82 | 58 | Unknown | 2025-04-17 | Unknown | Unknown | 2025-06-10 | 2025-06-11 | 1900-01-01 | 2 | 2025-06-11 | 2025-06-11 | 1 | 1 | 181 | 129 | 4 | 4 | 185 | 133 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | -619 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 588.71 | -5.85 | Unknown | Unknown | Unknown | 594.56 | 3621 | 788.11 | 588.71 | 199.4 | Yes | N/A | N/A | 2024-03-12 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-03-21 | 42 | 30 | 2024-03-21 | 2024-05-13 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | Unknown | Unknown | Unknown | 2024-05-28 | Unknown | Unknown | 2024-05-28 | 2024-05-23 | Unknown | Unknown | 54 | 38 | 42 | 30 | 96 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-11 | -649 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | 2024-03-26 | IOU Designed & Installed | N/A | No | N/A | 1727.41 | 568.04 | Unknown | 73.2 | Unknown | 1086.17 | Unknown | 911.19 | 1727.41 | -816.22 | Yes | N/A | N/A | 2024-03-20 | 2024-03-20 | 1 | 1 | 2024-03-20 | 2024-03-20 | 1 | 1 | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-03-26 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-04-02 | 1900-01-07 | 6 | 2024-04-02 | 2024-04-02 | 1 | 1 | 8 | 6 | 10 | 8 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 134.05 | 134.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-14 | -15 | -12 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | 997.5 | -8.21 | Unknown | Unknown | 10.06 | 995.65 | 3981 | 742.97 | 997.5 | -254.53 | Yes | N/A | N/A | 2023-11-27 | 2023-12-07 | 11 | 9 | 2023-12-07 | 2023-12-08 | 2 | 2 | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2024-04-22 | 137 | 97 | Unknown | 2024-04-22 | Unknown | Unknown | 2024-04-22 | 2024-05-30 | 1900-02-07 | 29 | 2024-05-30 | 2024-05-30 | 1 | 1 | 148 | 106 | 42 | 32 | 190 | 138 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-03 | -264 | -189 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | 2023-05-02 | 2023-05-09 | IOU Designed & Installed | N/A | No | N/A | 1975.42 | -49.85 | Unknown | Unknown | Unknown | 2025.27 | Unknown | 803.33 | 1975.42 | -1172.09 | Yes | N/A | N/A | 2023-05-02 | 2023-05-02 | 1 | 1 | 2023-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | 2023-05-09 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-05-09 | 2023-06-13 | 1900-02-04 | 26 | 2023-06-13 | 2023-06-13 | 1 | 1 | 9 | 7 | 37 | 27 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-22 | -23 | -18 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-31 | 2023-07-03 | IOU Designed & Installed | N/A | No | N/A | 15.6 | -16.06 | Unknown | Unknown | 10.73 | 20.93 | Unknown | 700.82 | 15.6 | 685.22 | Yes | N/A | N/A | 2023-03-30 | 2023-03-31 | 2 | 2 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | 2023-07-03 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | 2023-07-03 | 2024-01-30 | 1900-07-30 | 152 | 2024-01-30 | 2024-01-30 | 1 | 1 | 97 | 69 | 213 | 153 | 310 | 222 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-30 | -403 | -288 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2023-08-16 | IOU Designed & Installed | N/A | No | N/A | -82.83 | 248.3 | Unknown | 117.92 | -1554.75 | 1105.7 | Unknown | 1555.22 | -82.83 | 1638.05 | Yes | N/A | N/A | 2023-03-08 | 2023-03-21 | 14 | 10 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-08-16 | 149 | 107 | Unknown | 2023-08-15 | Unknown | Unknown | 2023-08-16 | 2023-08-24 | 1900-01-08 | 7 | 2023-08-24 | 2023-08-24 | 1 | 1 | 163 | 117 | 10 | 8 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -217 | -156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 352.79 | -6.7 | Unknown | Unknown | Unknown | 359.49 | Unknown | 466.88 | 352.79 | 114.09 | Yes | N/A | N/A | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | 2024-08-28 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-06-03 | 26 | 18 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | Unknown | Unknown | 2024-09-18 | 2024-09-18 | 1 | 1 | 2 | 2 | 147 | 105 | 149 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | National City | National City | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -274 | -197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-11-29 | 2024-03-06 | IOU Designed & Installed | N/A | No | N/A | 62704.94 | 8638.52 | Unknown | Unknown | 2888.78 | 51177.64 | 121965.35 | 18742.49 | 62704.94 | -43962.45 | Yes | N/A | N/A | 2023-03-10 | 2024-01-23 | 320 | 228 | 2024-01-23 | 2024-02-14 | 23 | 17 | 2024-02-15 | 2024-02-15 | 1 | 1 | 2024-01-19 | 2024-03-15 | 30 | 21 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-04-25 | 1900-02-19 | 37 | 2024-04-25 | 2024-04-25 | 1 | 1 | 321 | 229 | 105 | 76 | 426 | 305 | Steps 2,3,5,6,7 | 57 | 41 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 72.05 | 72.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-16 | -706 | -505 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-03-09 | IOU Designed & Installed | N/A | No | N/A | 1539.82 | 475.2 | Unknown | 104.97 | Unknown | 959.65 | Unknown | 821.9 | 1539.82 | -717.92 | Yes | N/A | N/A | 2023-02-28 | 2023-02-24 | Unknown | Unknown | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-28 | 2023-03-09 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | 2023-03-13 | 1900-01-04 | 3 | 2023-03-13 | 2023-03-13 | 1 | 1 | 10 | 8 | 6 | 4 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-21 | -583 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 441.22 | -7.94 | Unknown | Unknown | 1.82 | 447.34 | 3981 | 553.66 | 441.22 | 112.44 | Yes | N/A | N/A | 2023-03-01 | 2023-03-17 | 17 | 13 | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 17 | 13 | 1 | 1 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 19 | 19 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-17 | -165 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | Unknown | 2023-08-08 | IOU Designed & Installed | N/A | No | N/A | 663.59 | -10.75 | Unknown | Unknown | 2.73 | 671.61 | 3981 | 1930.34 | 663.59 | 1266.75 | Yes | N/A | N/A | 2023-05-08 | 2023-05-08 | 1 | 1 | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | 2023-08-08 | 93 | 67 | Unknown | 2023-08-08 | Unknown | Unknown | 2023-08-08 | 2023-09-05 | 1900-01-28 | 21 | 2023-09-05 | 2023-09-05 | 1 | 1 | 94 | 68 | 30 | 22 | 124 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-02 | -216 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-29 | 2023-08-10 | IOU Designed & Installed | N/A | No | N/A | -6.11 | -4.43 | Unknown | Unknown | Unknown | -1.68 | Unknown | 496.45 | -6.11 | 502.56 | Yes | N/A | N/A | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | 2023-08-10 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-08-30 | 1900-01-20 | 15 | 2023-08-30 | 2023-08-30 | 1 | 1 | 44 | 32 | 23 | 17 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-18 | 465 | 334 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 800.5 | Unknown | Unknown | Unknown | -11593.3 | 12393.8 | 6691 | 893.94 | 800.5 | 93.44 | Yes | N/A | N/A | 2024-02-06 | 2024-02-06 | 1 | 1 | 2024-02-06 | 2024-02-12 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-02-25 | 2 | 2 | 2024-02-12 | 2025-03-05 | 388 | 278 | Unknown | 2025-03-13 | Unknown | Unknown | Unknown | 2025-04-01 | Unknown | Unknown | 2025-04-01 | 2025-03-27 | Unknown | Unknown | 389 | 279 | 9 | 7 | 398 | 286 | Steps 2,3,5,6,7 | 379 | 271 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-21 | -527 | -377 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 912.54 | -15.22 | Unknown | Unknown | 7.15 | 920.61 | 3981 | 615.01 | 912.54 | -297.53 | Yes | N/A | N/A | 2023-03-06 | 2023-03-28 | 23 | 17 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | Unknown | Unknown | Unknown | 2023-07-13 | Unknown | Unknown | 2023-07-13 | 2023-07-13 | 1 | 1 | 23 | 17 | 1 | 1 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-16 | -173 | -124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-10-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 897.29 | -27.53 | Unknown | Unknown | 98.66 | 826.16 | 17612.43 | 270.68 | 897.29 | -626.61 | Yes | N/A | N/A | 2023-08-30 | 2023-11-13 | 76 | 54 | 2023-11-13 | 2024-02-02 | 82 | 60 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2023-12-15 | 11 | 9 | 2024-02-02 | 2024-11-21 | 294 | 210 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | 2025-01-24 | 2025-01-24 | 1 | 1 | 370 | 264 | 94 | 70 | 464 | 334 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-14 | 12 | 9 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | 2024-06-12 | IOU Designed & Installed | N/A | No | N/A | -4.53 | -10.23 | Unknown | Unknown | Unknown | 5.7 | 0 | 793.86 | -4.53 | 798.39 | Yes | N/A | N/A | 2023-10-12 | 2023-06-26 | Unknown | Unknown | 2023-06-26 | 2023-10-12 | 109 | 79 | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2024-06-12 | 245 | 175 | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-06-26 | 1900-01-14 | 11 | 2024-06-26 | 2024-06-26 | 1 | 1 | 245 | 175 | 125 | 91 | 370 | 266 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-16 | -507 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-27 | 2023-01-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2.7 | -4.27 | Unknown | Unknown | Unknown | 1.57 | Unknown | 95.13 | -2.7 | 97.83 | Yes | N/A | N/A | 2023-01-27 | 2023-03-10 | 43 | 31 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | Unknown | Unknown | 2023-07-28 | 2023-07-28 | 1 | 1 | 43 | 31 | 1 | 1 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-03 | -597 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-04-15 | 2024-05-10 | IOU Designed & Installed | N/A | No | N/A | 4.92 | -4.36 | Unknown | Unknown | Unknown | 9.28 | 3981 | 807.26 | 4.92 | 802.34 | Yes | N/A | N/A | 2024-03-07 | 2024-04-10 | 35 | 25 | 2024-04-10 | 2024-04-15 | 6 | 4 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-05-10 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-05-17 | 1900-01-07 | 6 | 2024-05-17 | 2024-05-16 | Unknown | Unknown | 61 | 45 | 14 | 10 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 403.1 | 403.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | -621 | -444 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-02 | 2024-08-09 | IOU Designed & Installed | N/A | No | N/A | 104.98 | -1.5 | Unknown | Unknown | Unknown | 106.48 | 3981 | 1830.51 | 104.98 | 1725.53 | Yes | N/A | N/A | 2024-08-02 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-08-05 | 20 | 14 | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-08-09 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-08-15 | 1900-01-06 | 5 | 2024-08-15 | 2024-08-23 | 9 | 7 | 5 | 5 | 36 | 26 | 41 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-18 | -671 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-21 | 2024-12-11 | IOU Designed & Installed | N/A | No | N/A | 1178.75 | -21.9 | Unknown | Unknown | Unknown | 1200.65 | 3981 | 1480.41 | 1178.75 | 301.66 | Yes | N/A | N/A | 2024-11-21 | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-11-21 | 2 | 2 | 2024-11-21 | Unknown | Unknown | Unknown | 2024-11-21 | 2024-12-10 | 20 | 14 | 2024-11-21 | 2024-12-11 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2025-01-16 | 1900-02-05 | 27 | 2025-01-16 | 2025-01-16 | 1 | 1 | 21 | 15 | 60 | 44 | 81 | 59 | Steps 2,3,5,6,7 | 19 | 13 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-30 | 134 | 97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2664.59 | -16.53 | Unknown | Unknown | 5.91 | 2675.21 | 15924 | 999.96 | 2664.59 | -1664.63 | Yes | N/A | N/A | 2024-03-12 | 2024-06-04 | 85 | 61 | 2024-06-04 | 2024-07-24 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2025-02-05 | 197 | 141 | Unknown | 2025-02-06 | Unknown | Unknown | Unknown | 2025-02-11 | Unknown | Unknown | 2025-02-11 | 2025-02-11 | 1 | 1 | 282 | 202 | 52 | 38 | 334 | 240 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | -614 | -440 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 1287.5 | 380.61 | Unknown | Unknown | Unknown | 906.89 | Unknown | 1251.52 | 1287.5 | -35.98 | Yes | N/A | N/A | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-08-26 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-09-30 | 1900-02-04 | 26 | 2024-09-30 | 2024-09-30 | 1 | 1 | 27 | 19 | 37 | 27 | 64 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-19 | -180 | -129 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-30 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 993.17 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-18 | 2024-01-29 | 12 | 8 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-07-23 | 176 | 126 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-08-23 | 1900-01-31 | 24 | 2024-08-23 | 2024-08-23 | 1 | 1 | 188 | 134 | 33 | 25 | 221 | 159 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-23 | 43 | 32 | No | 2022-06-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-17 | 2022-06-17 | 2023-05-05 | IOU Designed & Installed | N/A | Yes | 311 | 1988 | 583.44 | Unknown | Unknown | Unknown | 1404.56 | 6481 | 729.58 | 1988 | -1258.42 | Yes | N/A | N/A | 2022-06-17 | 2023-04-24 | 312 | 222 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-06-17 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | 2023-05-05 | 1899-12-31 | 1 | 2023-05-05 | 2023-05-05 | 1 | 1 | 312 | 222 | 2 | 2 | 314 | 224 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-30 | -27 | -20 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1143.21 | -18.8 | Unknown | Unknown | -269 | 1431.01 | 773 | 433.69 | 1143.21 | -709.52 | Yes | N/A | N/A | 2023-03-30 | 2023-03-30 | 1 | 1 | 2023-03-30 | 2023-06-28 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2024-04-19 | 297 | 213 | Unknown | 2024-05-21 | Unknown | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | 2024-05-31 | 2024-06-03 | 4 | 2 | 298 | 214 | 95 | 67 | 393 | 281 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 88 | 88 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-04 | -117 | -85 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1660.09 | -31.79 | Unknown | Unknown | Unknown | 1691.88 | Unknown | 1810.58 | 1660.09 | 150.49 | Yes | N/A | N/A | 2024-06-11 | 2024-06-26 | 16 | 12 | 2024-06-26 | 2024-07-11 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-09-09 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | Unknown | Unknown | 2024-09-10 | 2024-09-09 | Unknown | Unknown | 77 | 55 | 16 | 12 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-30 | -661 | -474 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-15 | 2024-03-19 | IOU Designed & Installed | N/A | No | N/A | -8.75 | -7.09 | Unknown | Unknown | Unknown | -1.66 | 3981 | 797.75 | -8.75 | 806.5 | Yes | N/A | N/A | 2024-03-07 | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-03-15 | 38 | 28 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-03-19 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-04-09 | 1900-01-21 | 16 | 2024-04-09 | 2024-04-09 | 1 | 1 | 5 | 3 | 61 | 45 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-06 | -554 | -397 | No | 2024-03-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-29 | 2024-06-18 | IOU Designed & Installed | N/A | Yes | 12 | 345.31 | -13.82 | Unknown | Unknown | Unknown | 359.13 | 3981 | 501.18 | 345.31 | 155.87 | Yes | N/A | N/A | 2024-03-20 | 2024-03-29 | 10 | 8 | 2024-03-29 | 2024-04-01 | 4 | 2 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-06-18 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-08-01 | 1900-02-13 | 33 | 2024-08-01 | 2024-08-01 | 1 | 1 | 89 | 65 | 50 | 36 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-12 | -173 | -125 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-19 | 2024-04-01 | IOU Designed & Installed | N/A | No | N/A | 9.81 | -8.71 | Unknown | Unknown | Unknown | 18.52 | 3981 | 558.25 | 9.81 | 548.44 | Yes | N/A | N/A | 2024-03-19 | 2024-03-19 | 1 | 1 | 2024-03-19 | 2024-03-19 | 1 | 1 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-04-01 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-04-22 | 1900-01-21 | 16 | 2024-04-22 | 2024-04-22 | 1 | 1 | 14 | 10 | 24 | 18 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-05 | -598 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-13 | 2025-01-31 | IOU Designed & Installed | N/A | No | N/A | 1205.7 | -23.42 | Unknown | Unknown | Unknown | 1229.12 | 3981 | 1795.36 | 1205.7 | 589.66 | Yes | N/A | N/A | 2024-12-13 | 2024-12-01 | Unknown | Unknown | 2024-12-01 | 2024-12-17 | 17 | 12 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-01-31 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-03-17 | 1900-02-14 | 32 | 2025-03-17 | 2025-03-17 | 1 | 1 | 50 | 36 | 64 | 45 | 114 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 14.7 | 14.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-13 | -598 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-05-14 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 90.25 | -9.45 | Unknown | Unknown | Unknown | 99.7 | 3981 | 761.95 | 90.25 | 671.7 | Yes | N/A | N/A | 2024-04-18 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-03-26 | 34 | 24 | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-06-10 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-06-12 | 1900-01-02 | 3 | 2024-06-12 | 2024-06-25 | 14 | 10 | 28 | 20 | 51 | 37 | 79 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-25 | -626 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-07-02 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | 36.8 | Unknown | Unknown | Unknown | Unknown | 36.8 | 3981 | 1690.2 | 36.8 | 1653.4 | Yes | N/A | N/A | 2024-06-26 | 2024-07-02 | 7 | 5 | 2024-07-02 | 2024-07-02 | 1 | 1 | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-16 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-08-08 | 1900-01-23 | 18 | 2024-08-08 | 2024-08-07 | Unknown | Unknown | 22 | 16 | 25 | 19 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-28 | -261 | -188 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-07 | 2023-11-13 | IOU Designed & Installed | N/A | No | N/A | 591.07 | -15.93 | Unknown | Unknown | Unknown | 607 | 3981 | 844.57 | 591.07 | 253.5 | Yes | N/A | N/A | 2023-11-06 | 2023-10-05 | Unknown | Unknown | 2023-10-05 | 2023-11-07 | 34 | 24 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2023-11-13 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2023-12-11 | 1900-01-28 | 21 | 2023-12-11 | 2023-12-11 | 1 | 1 | 7 | 5 | 64 | 46 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-10 | 231 | 166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-10-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1047.83 | -11.17 | Unknown | Unknown | Unknown | 1059 | 7962 | Not available | 1047.83 | Unknown | Yes | N/A | N/A | 2024-05-31 | 2024-01-22 | Unknown | Unknown | 2024-01-22 | 2024-12-10 | 324 | 232 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2025-02-26 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | 2025-02-27 | 2025-02-26 | Unknown | Unknown | 79 | 57 | 324 | 232 | 403 | 289 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 1006.1 | 1006.1 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-03-29 | -215 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-09 | 2024-06-11 | 2024-07-15 | IOU Designed & Installed | N/A | No | N/A | 4903.82 | 1491.57 | Unknown | Unknown | Unknown | 3412.25 | 3241 | 1527.23 | 4903.82 | -3376.59 | Yes | N/A | N/A | 2024-06-09 | 2024-06-11 | 3 | 2 | 2024-06-11 | 2024-06-11 | 1 | 1 | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-07-15 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-08-16 | 1900-02-01 | 25 | 2024-08-16 | 2024-08-26 | 11 | 7 | 38 | 27 | 45 | 33 | 83 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-14 | -473 | -340 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | 2023-08-31 | 2023-09-14 | IOU Designed & Installed | N/A | No | N/A | -10.29 | -7.54 | Unknown | Unknown | Unknown | -2.75 | 3981 | 465.36 | -10.29 | 475.65 | Yes | N/A | N/A | 2023-06-05 | 2023-08-31 | 88 | 64 | 2023-08-31 | 2023-08-31 | 1 | 1 | 2023-08-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | 2023-09-14 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-10-30 | 1900-02-15 | 33 | 2023-10-30 | 2023-10-30 | 1 | 1 | 103 | 75 | 49 | 35 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-20 | -670 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | 2025-03-26 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1578.42 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-03-07 | Unknown | Unknown | 2025-03-07 | 2025-03-13 | 7 | 5 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-03-26 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-04-21 | 1900-01-26 | 19 | 2025-04-21 | 2025-04-21 | 1 | 1 | 14 | 10 | 35 | 25 | 49 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | 24 | 18 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-27 | 2024-12-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1369.41 | -14.74 | Unknown | Unknown | Unknown | 1384.15 | Unknown | 499.14 | 1369.41 | -870.27 | Yes | N/A | N/A | 2024-11-27 | 2024-12-02 | 6 | 4 | 2024-12-02 | 2025-02-18 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-05 | 1 | 1 | 6 | 4 | 80 | 58 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-11-04 | 563 | 402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | 2024-04-17 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 19510.5 | 2255.04 | Unknown | 188.93 | -10327 | 27393.53 | 2875.23 | 13152.98 | 19510.5 | -6357.52 | Yes | N/A | N/A | 2023-03-24 | 2023-04-03 | 11 | 7 | 2023-04-03 | 2023-07-31 | 120 | 86 | 2023-04-03 | 2023-08-31 | 123 | 85 | 2023-04-04 | 2023-08-02 | 70 | 52 | 2023-07-31 | 2024-04-10 | 255 | 183 | 2023-11-27 | 2024-04-08 | 134 | 96 | 2024-04-17 | 2024-05-22 | 1900-02-04 | 26 | 2024-05-22 | 2024-05-20 | Unknown | Unknown | 389 | 275 | 360 | 260 | 749 | 535 | Steps 2,3,5,6,7 | 405 | 291 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-28 | -166 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-07 | 2024-01-29 | IOU Designed & Installed | N/A | No | N/A | -7.16 | -5.81 | Unknown | Unknown | Unknown | -1.35 | Unknown | 496.75 | -7.16 | 503.91 | Yes | N/A | N/A | 2023-11-07 | 2023-09-14 | Unknown | Unknown | 2023-09-14 | 2023-11-07 | 55 | 39 | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2024-01-29 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-03-15 | 1900-02-15 | 35 | 2024-03-15 | 2024-03-15 | 1 | 1 | 84 | 60 | 103 | 75 | 187 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | -126 | -91 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-30 | 2023-11-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -249.38 | -23.66 | Unknown | Unknown | -469 | 243.28 | 3981 | 1185.06 | -249.38 | 1434.44 | Yes | N/A | N/A | 2022-11-30 | 2023-09-06 | 281 | 201 | 2023-09-06 | 2023-12-26 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | Unknown | Unknown | Unknown | 2024-05-29 | Unknown | Unknown | 2024-05-29 | 2024-05-28 | Unknown | Unknown | 281 | 201 | 112 | 80 | 393 | 281 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-07 | -191 | -138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-03 | 2023-05-03 | 2023-08-28 | IOU Designed & Installed | N/A | No | N/A | 1919.94 | 544.38 | Unknown | 278.01 | Unknown | 1097.55 | 3981 | 666.23 | 1919.94 | -1253.71 | Yes | N/A | N/A | 2023-05-03 | 2023-05-19 | 17 | 13 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2023-08-28 | 102 | 72 | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2023-08-29 | 1900-01-01 | 2 | 2023-08-29 | 2023-08-29 | 1 | 1 | 119 | 85 | 3 | 3 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | -647 | -464 | No | 2024-08-29 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | 2024-09-16 | IOU Designed & Installed | N/A | Yes | 21 | 84.91 | -1.5 | Unknown | Unknown | Unknown | 86.41 | 3981 | 1852.47 | 84.91 | 1767.56 | Yes | N/A | N/A | 2024-08-29 | 2024-09-19 | 22 | 16 | 2024-09-19 | 2024-08-29 | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-09-16 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-10-29 | 1900-02-12 | 32 | 2024-10-29 | 2024-10-29 | 1 | 1 | 41 | 29 | 45 | 33 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-16 | 292 | 209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-12-15 | 2024-07-24 | IOU Designed & Installed | N/A | No | N/A | 4501.66 | Unknown | Unknown | Unknown | 19.24 | 4482.42 | 3981 | 2476.9 | 4501.66 | -2024.76 | Yes | N/A | N/A | 2023-08-30 | 2024-01-11 | 135 | 97 | 2024-01-11 | 2024-04-29 | 110 | 78 | 2024-01-04 | 2024-01-04 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | 2024-07-24 | 2024-09-03 | 1900-02-10 | 30 | 2024-09-03 | 2024-09-03 | 1 | 1 | 136 | 98 | 153 | 109 | 289 | 207 | Steps 2,3,5,6,7 | 116 | 82 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 18501.35 | 18501.35 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-10-26 | -563 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 4277.48 | 499.65 | Unknown | Unknown | 0.63 | 3777.2 | 3981 | 1997.24 | 4277.48 | -2280.24 | Yes | N/A | N/A | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | 2024-12-19 | 1 | 1 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-02-10 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-04-11 | 1900-03-01 | 45 | 2025-04-11 | 2025-04-11 | 1 | 1 | 55 | 39 | 63 | 47 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-13 | -452 | -323 | No | 2024-01-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2024-05-23 | IOU Designed & Installed | N/A | Yes | 94 | 323.44 | 179.74 | Unknown | 16.29 | Unknown | 127.41 | 3961 | 163.83 | 323.44 | -159.61 | Yes | N/A | N/A | 2024-01-09 | 2024-04-11 | 94 | 68 | 2024-04-11 | 2024-04-12 | 2 | 2 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-05-23 | 116 | 84 | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-07-18 | 1900-02-25 | 41 | 2024-07-18 | 2024-07-18 | 1 | 1 | 210 | 152 | 60 | 44 | 270 | 196 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-02 | -237 | -170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | 2024-07-15 | IOU Designed & Installed | N/A | No | N/A | 401.14 | Unknown | Unknown | Unknown | 1.98 | 399.16 | Unknown | 1136.34 | 401.14 | 735.2 | Yes | N/A | N/A | 2024-05-20 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-06-28 | 79 | 57 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-15 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-08-08 | 1900-01-24 | 19 | 2024-08-08 | 2024-08-08 | 1 | 1 | 18 | 12 | 105 | 77 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-29 | -509 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-09-06 | 2024-11-18 | IOU Designed & Installed | N/A | No | N/A | 19.39 | Unknown | Unknown | Unknown | Unknown | 19.39 | Unknown | 1183.14 | 19.39 | 1163.75 | Yes | N/A | N/A | 2024-08-09 | 2024-07-19 | Unknown | Unknown | 2024-07-19 | 2024-09-06 | 50 | 36 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-11-18 | 74 | 52 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-12-06 | 1900-01-18 | 15 | 2024-12-06 | 2024-12-06 | 1 | 1 | 74 | 52 | 70 | 52 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RANCHITA | N/A | 810.05 | 810.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-07 | 79 | 56 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-02 | 2023-03-03 | 2024-10-31 | IOU Designed & Installed | N/A | No | N/A | 6047.97 | 291.77 | Unknown | Unknown | -681 | 6437.2 | 3981 | 1186.04 | 6047.97 | -4861.93 | Yes | N/A | N/A | 2022-11-02 | 2023-05-19 | 199 | 143 | 2023-05-19 | 2024-05-31 | 379 | 271 | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2024-11-20 | 1 | 1 | 2024-05-31 | 2024-09-18 | 111 | 79 | Unknown | 2024-09-13 | Unknown | Unknown | 2024-10-31 | 2024-11-26 | 1900-01-26 | 19 | 2024-11-26 | 2024-11-25 | Unknown | Unknown | 310 | 222 | 407 | 291 | 717 | 513 | Steps 2,3,5,6,7 | 173 | 123 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 139.05 | 139.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-14 | -640 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-08-14 | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | 376.54 | Unknown | Unknown | Unknown | Unknown | 376.54 | Unknown | 1386.38 | 376.54 | 1009.84 | Yes | N/A | N/A | 2024-07-31 | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2024-08-21 | 57 | 41 | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-09-03 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-09-12 | 1900-01-09 | 8 | 2024-09-12 | 2024-09-12 | 1 | 1 | 14 | 10 | 68 | 50 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 46.05 | 46.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-03 | -591 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2024-11-25 | 2025-01-30 | IOU Designed & Installed | N/A | No | N/A | 708.53 | -13.2 | Unknown | Unknown | Unknown | 721.73 | 3981 | 1980.56 | 708.53 | 1272.03 | Yes | N/A | N/A | 2024-11-08 | 2024-11-25 | 18 | 12 | 2024-11-25 | 2024-11-25 | 1 | 1 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-01-30 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-14 | 1900-01-15 | 12 | 2025-02-14 | 2025-02-19 | 6 | 4 | 85 | 61 | 23 | 17 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-16 | -554 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-02-22 | 2023-05-11 | IOU Designed & Installed | N/A | No | N/A | 1917.66 | 234.53 | Unknown | Unknown | 6.24 | 1676.89 | 3885 | 538.63 | 1917.66 | -1379.03 | Yes | N/A | N/A | 2023-02-22 | 2023-03-21 | 28 | 20 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-05-11 | 52 | 38 | Unknown | 2023-05-10 | Unknown | Unknown | 2023-05-11 | 2023-05-12 | 1900-01-01 | 2 | 2023-05-12 | 2023-05-12 | 1 | 1 | 80 | 58 | 3 | 3 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-31 | -569 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-04 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 2371.72 | 505.28 | Unknown | Unknown | Unknown | 1866.44 | Unknown | 1833.22 | 2371.72 | -538.5 | Yes | N/A | N/A | 2024-12-04 | 2024-12-19 | 16 | 12 | 2024-12-19 | 2025-02-13 | 57 | 41 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-03-06 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-04-10 | 1900-02-04 | 26 | 2025-04-10 | 2025-04-10 | 1 | 1 | 38 | 28 | 94 | 68 | 132 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | 102.15 | 102.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-30 | -700 | -501 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-19 | 2023-10-27 | IOU Designed & Installed | N/A | No | N/A | 466.03 | -11.29 | Unknown | Unknown | 14.73 | 462.59 | 3981 | 1219.22 | 466.03 | 753.19 | Yes | N/A | N/A | 2023-05-10 | 2023-05-19 | 10 | 8 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2023-10-27 | 162 | 116 | Unknown | 2023-10-20 | Unknown | Unknown | 2023-10-27 | 2023-11-01 | 1900-01-05 | 4 | 2023-11-01 | 2023-10-31 | Unknown | Unknown | 172 | 124 | 6 | 4 | 178 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | Rancho Viejo | N/A | 372.6 | 372.6 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-15 | 497 | 356 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-04-27 | 2024-01-09 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 116276.16 | 14804.7 | Unknown | 1632.39 | 30389.67 | 69449.4 | 0 | 50641.53 | 116276.16 | -65634.63 | Yes | N/A | N/A | 2022-04-27 | 2023-02-01 | 281 | 201 | 2023-02-01 | 2023-08-15 | 196 | 140 | 2023-06-30 | 2023-10-02 | 63 | 45 | 2023-06-27 | 2023-07-26 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | 2024-01-09 | 2024-09-23 | 1900-09-15 | 185 | 2024-09-23 | 2024-09-23 | 1 | 1 | 344 | 246 | 486 | 348 | 830 | 594 | Steps 2,3,5,6,7 | 319 | 227 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-04 | -297 | -214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-19 | 2024-05-20 | IOU Designed & Installed | N/A | No | N/A | 789.24 | 2251.62 | Unknown | 221.02 | -2729 | 1045.6 | Unknown | 2729.42 | 789.24 | 1940.18 | Yes | N/A | N/A | 2024-04-10 | 2024-04-19 | 10 | 8 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-06-11 | 1900-01-22 | 17 | 2024-06-11 | 2024-06-11 | 1 | 1 | 10 | 8 | 24 | 18 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | -21 | -16 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | Unknown | 2023-10-26 | IOU Designed & Installed | N/A | No | N/A | 600.9 | 479.6 | Unknown | 235.84 | -1544 | 1429.46 | Unknown | 1642.77 | 600.9 | 1041.87 | Yes | N/A | N/A | 2023-05-01 | 2023-05-01 | 1 | 1 | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2023-11-01 | 3 | 3 | 2023-05-01 | 2023-10-26 | 179 | 129 | Unknown | 2023-10-20 | Unknown | Unknown | 2023-10-26 | 2023-11-10 | 1900-01-15 | 12 | 2023-11-10 | 2023-11-10 | 1 | 1 | 180 | 130 | 20 | 16 | 200 | 146 | Steps 2,3,5,6,7 | 184 | 132 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 48.1 | 48.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-20 | -468 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | 2024-09-26 | IOU Designed & Installed | N/A | No | N/A | 66.86 | Unknown | Unknown | Unknown | Unknown | 66.86 | 7882 | 1034.48 | 66.86 | 967.62 | Yes | N/A | N/A | 2024-03-21 | 2024-01-30 | Unknown | Unknown | 2024-01-30 | 2024-03-21 | 52 | 38 | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-09-26 | 190 | 136 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-10-10 | 1900-01-14 | 11 | 2024-10-10 | 2024-10-09 | Unknown | Unknown | 190 | 136 | 67 | 49 | 257 | 185 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-16 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 750.07 | -4.97 | Unknown | Unknown | 28.59 | 726.45 | 3981 | 572.83 | 750.07 | -177.24 | Yes | N/A | N/A | 2023-02-01 | 2023-02-22 | 22 | 16 | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 22 | 16 | 1 | 1 | 23 | 17 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | -676 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | 2024-11-19 | IOU Designed & Installed | N/A | No | N/A | 48.14 | Unknown | Unknown | Unknown | Unknown | 48.14 | 3981 | 1515.34 | 48.14 | 1467.2 | Yes | N/A | N/A | 2024-11-14 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-11-14 | 7 | 5 | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-11-19 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2024-12-16 | 1900-01-27 | 20 | 2024-12-16 | 2024-12-16 | 1 | 1 | 6 | 4 | 36 | 26 | 42 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | -584 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-11 | 2024-05-22 | IOU Designed & Installed | N/A | No | N/A | -8.15 | -8.33 | Unknown | Unknown | Unknown | 0.18 | Unknown | 162.34 | -8.15 | 170.49 | Yes | N/A | N/A | 2024-04-03 | 2024-03-13 | Unknown | Unknown | 2024-03-13 | 2024-04-26 | 45 | 33 | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2024-05-22 | 27 | 19 | Unknown | 2024-05-21 | Unknown | Unknown | 2024-05-22 | 2024-07-22 | 1900-03-02 | 44 | 2024-07-22 | 2024-07-22 | 1 | 1 | 27 | 19 | 108 | 78 | 135 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2027-12-31 | -1043 | -746 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | 2025-02-12 | IOU Designed & Installed | N/A | No | N/A | 45444.49 | 12017.58 | Unknown | Unknown | Unknown | 33426.91 | 1017073 | 14953.92 | 45444.49 | -30490.57 | Yes | N/A | N/A | 2023-09-22 | 2023-10-05 | 14 | 10 | 2023-10-05 | 2023-10-17 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-01-08 | 48 | 34 | 2023-10-17 | 2025-02-04 | 477 | 341 | Unknown | 2025-01-17 | Unknown | Unknown | 2025-02-12 | 2025-02-25 | 1900-01-13 | 10 | 2025-02-25 | 2025-02-21 | Unknown | Unknown | 491 | 351 | 75 | 53 | 566 | 404 | Steps 2,3,5,6,7 | 449 | 321 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-22 | 314 | 225 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-28 | 2023-08-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 125984.61 | 11810.29 | Unknown | 15.27 | -9301.28 | 123460.33 | 67677 | 85719.05 | 125984.61 | -40265.56 | Yes | N/A | N/A | 2023-06-28 | 2023-08-11 | 45 | 33 | 2023-08-11 | 2024-06-26 | 321 | 229 | 2023-08-11 | 2024-10-23 | -29 | -25 | 2024-02-02 | 2024-07-10 | 81 | 57 | 2024-06-26 | 2025-08-29 | 430 | 308 | 2024-10-25 | 2025-05-06 | 194 | 138 | Unknown | 2025-04-01 | Unknown | Unknown | 2025-04-01 | 2025-04-01 | 1 | 1 | 446 | 316 | 597 | 425 | 1043 | 741 | Steps 2,3,5,6,7 | 906 | 646 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-29 | -270 | -193 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 1369.69 | 692.26 | Unknown | Unknown | -1164 | 1841.43 | 0 | 1164.12 | 1369.69 | -205.57 | Yes | N/A | N/A | 2023-10-31 | 2023-08-08 | Unknown | Unknown | 2023-08-08 | 2023-12-01 | 116 | 84 | 2023-12-01 | 2023-12-08 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2024-10-29 | 327 | 233 | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-11-01 | 1900-01-03 | 4 | 2024-11-01 | 2024-11-01 | 1 | 1 | 335 | 239 | 121 | 89 | 456 | 328 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-31 | 794 | 567 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | 2025-05-28 | IOU Designed & Installed | N/A | No | N/A | -524.63 | Unknown | Unknown | Unknown | -1421 | 896.37 | 0 | 1420.64 | -524.63 | 1945.27 | Yes | N/A | N/A | 2024-01-11 | 2023-05-17 | Unknown | Unknown | 2023-05-17 | 2025-03-21 | 675 | 483 | 2025-03-21 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2025-05-28 | 393 | 281 | Unknown | 2025-03-19 | Unknown | Unknown | 2025-05-28 | 2025-06-02 | 1900-01-05 | 4 | 2025-06-02 | 2025-06-02 | 1 | 1 | 393 | 281 | 682 | 488 | 1075 | 769 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | 348.05 | 348.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-07 | 5 | 4 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-18 | 2023-06-18 | 2023-10-09 | IOU Designed & Installed | N/A | No | N/A | 672.66 | -36.26 | Unknown | Unknown | 186.86 | 522.06 | 3991 | 697.76 | 672.66 | 25.1 | Yes | N/A | N/A | 2023-06-18 | 2023-06-18 | 1 | 0 | 2023-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-18 | 2023-10-09 | 114 | 81 | Unknown | 2023-10-05 | Unknown | Unknown | 2023-10-09 | 2024-11-12 | 1901-02-04 | 287 | 2024-11-12 | 2024-11-12 | 1 | 1 | 115 | 81 | 402 | 288 | 517 | 369 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | -528 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-05 | 2024-04-05 | 2024-04-24 | IOU Designed & Installed | N/A | No | N/A | 15.12 | -13.44 | Unknown | Unknown | Unknown | 28.56 | 3241 | 878.93 | 15.12 | 863.81 | Yes | N/A | N/A | 2024-04-05 | 2024-04-05 | 1 | 1 | 2024-04-05 | 2024-04-05 | 1 | 1 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-04-24 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-13 | 1900-01-19 | 14 | 2024-05-13 | 2024-05-13 | 1 | 1 | 21 | 15 | 22 | 16 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-07 | -598 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-07 | 2024-06-24 | IOU Designed & Installed | N/A | No | N/A | 15.03 | -11.6 | Unknown | Unknown | Unknown | 26.63 | Unknown | 1669.8 | 15.03 | 1654.77 | Yes | N/A | N/A | 2024-06-06 | 2024-06-07 | 2 | 2 | 2024-06-07 | 2024-06-07 | 1 | 1 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-06-24 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-07-17 | 1900-01-23 | 18 | 2024-07-17 | 2024-07-17 | 1 | 1 | 20 | 14 | 26 | 20 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-21 | 368 | 263 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-08 | 2023-10-19 | IOU Designed & Installed | N/A | No | N/A | 3081.73 | 1019.04 | Unknown | 173.52 | Unknown | 1889.17 | 3981 | 760.07 | 3081.73 | -2321.66 | Yes | N/A | N/A | 2023-03-06 | 2023-03-06 | 1 | 1 | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | 2023-10-19 | 226 | 162 | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2023-11-03 | 1900-01-15 | 12 | 2023-11-03 | 2023-10-24 | Unknown | Unknown | 227 | 163 | 16 | 12 | 243 | 175 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-02 | 167 | 120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-28 | 2023-09-11 | 2024-04-26 | IOU Designed & Installed | N/A | No | N/A | 144102.91 | 24228.74 | Unknown | Unknown | -139422.25 | 259296.42 | 537139.77 | 172810.77 | 144102.91 | 28707.86 | Yes | N/A | N/A | 2023-04-28 | 2023-09-11 | 137 | 97 | 2023-09-11 | 2024-03-27 | 199 | 143 | 2023-12-12 | 2023-12-20 | 9 | 7 | 2024-01-30 | 2024-04-03 | 65 | 47 | 2024-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2024-06-17 | 1900-02-21 | 37 | 2024-06-17 | 2024-06-17 | 1 | 1 | 146 | 104 | 318 | 228 | 464 | 332 | Steps 2,3,5,6,7 | 113 | 81 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-31 | -572 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-05 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | -7.65 | -31.89 | Unknown | Unknown | Unknown | 24.24 | Unknown | 1919.6 | -7.65 | 1927.25 | Yes | N/A | N/A | 2024-12-04 | 2024-12-19 | 16 | 12 | 2024-12-19 | 2025-02-13 | 57 | 41 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-03-06 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-04-07 | 1900-02-01 | 23 | 2025-04-07 | 2025-04-07 | 1 | 1 | 38 | 28 | 91 | 65 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 13455.4 | 13455.4 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-06-16 | -352 | -251 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | 2023-06-20 | 2023-06-28 | IOU Designed & Installed | N/A | No | N/A | -4.87 | -14.54 | Unknown | Unknown | Unknown | 9.67 | 3981 | 802.49 | -4.87 | 807.36 | Yes | N/A | N/A | 2023-06-20 | 2023-06-20 | 1 | 1 | 2023-06-20 | 2023-06-20 | 1 | 1 | 2023-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | 2023-06-28 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-06-30 | 1900-01-02 | 3 | 2023-06-30 | 2023-06-30 | 1 | 1 | 10 | 8 | 5 | 5 | 15 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 108.05 | 108.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | -356 | -255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-08-15 | 2025-01-24 | IOU Designed & Installed | N/A | No | N/A | 887.77 | Unknown | Unknown | Unknown | Unknown | 887.77 | 3981 | 1244.23 | 887.77 | 356.46 | Yes | N/A | N/A | 2024-03-25 | 2024-08-15 | 144 | 104 | 2024-08-15 | 2024-08-15 | 1 | 1 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2025-01-24 | 163 | 117 | Unknown | 2024-12-12 | Unknown | Unknown | 2025-01-24 | 2025-01-31 | 1900-01-07 | 6 | 2025-01-31 | 2025-01-31 | 1 | 1 | 307 | 221 | 10 | 8 | 317 | 229 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-16 | -310 | -223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | 2024-06-07 | IOU Designed & Installed | N/A | No | N/A | -1517.35 | 603.72 | Unknown | Unknown | -2532 | 410.93 | Unknown | 2532.46 | -1517.35 | 4049.81 | Yes | N/A | N/A | 2024-05-14 | 2024-05-13 | Unknown | Unknown | 2024-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-06-10 | 1900-01-03 | 2 | 2024-06-10 | 2024-06-10 | 1 | 1 | 0 | 0 | 5 | 3 | 5 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 17.05 | 17.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | 175 | 126 | No | 2023-10-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-10-03 | 2023-12-04 | IOU Designed & Installed | N/A | Yes | 59 | 7181.21 | 1936.95 | Unknown | Unknown | 505.6 | 4738.66 | 3981 | 904.28 | 7181.21 | -6276.93 | Yes | N/A | N/A | 2023-10-03 | 2023-11-29 | 58 | 42 | 2023-11-29 | 2023-12-01 | 3 | 3 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2023-12-04 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2025-06-25 | 1901-07-23 | 408 | 2025-06-25 | 2025-06-25 | 1 | 1 | 65 | 47 | 574 | 412 | 639 | 459 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 1.28 | 1.28 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | -652 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-06-25 | 2024-07-18 | IOU Designed & Installed | N/A | No | N/A | 5.69 | Unknown | Unknown | Unknown | Unknown | 5.69 | 3981 | 1375.94 | 5.69 | 1370.25 | Yes | N/A | N/A | 2024-06-25 | 2024-05-29 | Unknown | Unknown | 2024-05-29 | 2024-06-25 | 28 | 20 | 2024-06-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-18 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-08-09 | 1900-01-22 | 17 | 2024-08-09 | 2024-08-09 | 1 | 1 | 24 | 18 | 52 | 38 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-16 | -351 | -251 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2025-05-15 | 2025-05-27 | IOU Designed & Installed | N/A | No | N/A | 764.57 | -15.37 | Unknown | Unknown | Unknown | 779.94 | 3981 | 1653.85 | 764.57 | 889.28 | Yes | N/A | N/A | 2024-07-09 | 2025-05-08 | 304 | 218 | 2025-05-08 | 2025-05-09 | 2 | 2 | 2025-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-05-27 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | 2025-05-30 | 1900-01-03 | 4 | 2025-05-30 | 2025-05-30 | 1 | 1 | 317 | 227 | 7 | 7 | 324 | 234 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 72 | 72 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-07 | -190 | -137 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-04-07 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | -11.47 | -8.97 | Unknown | Unknown | Unknown | -2.5 | Unknown | 153.75 | -11.47 | 165.22 | Yes | N/A | N/A | 2023-03-09 | 2023-04-28 | 51 | 37 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | 2023-07-17 | 81 | 57 | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-08-01 | 1900-01-15 | 12 | 2023-08-01 | 2023-08-01 | 1 | 1 | 132 | 94 | 17 | 13 | 149 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-19 | -576 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-28 | 2025-01-23 | IOU Designed & Installed | N/A | No | N/A | 1777.86 | 249.97 | Unknown | Unknown | 9.73 | 1518.16 | 3981 | 1372.19 | 1777.86 | -405.67 | Yes | N/A | N/A | 2024-10-28 | 2024-09-19 | Unknown | Unknown | 2024-09-19 | 2024-11-11 | 54 | 38 | 2024-11-11 | 2024-12-09 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2025-01-23 | 74 | 54 | Unknown | 2025-01-16 | Unknown | Unknown | 2025-01-23 | 2025-02-20 | 1900-01-28 | 21 | 2025-02-20 | 2025-02-20 | 1 | 1 | 103 | 75 | 84 | 60 | 187 | 135 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-02 | -691 | -494 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-08-15 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 26.84 | Unknown | Unknown | Unknown | Unknown | 26.84 | 3981 | 1545.54 | 26.84 | 1518.7 | Yes | N/A | N/A | 2024-08-15 | 2024-08-13 | Unknown | Unknown | 2024-08-13 | 2024-08-16 | 4 | 4 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-08-26 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-09-10 | 1900-01-15 | 12 | 2024-09-10 | 2024-09-10 | 1 | 1 | 12 | 8 | 21 | 17 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-19 | -519 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.93 | -11.6 | Unknown | Unknown | Unknown | 7.67 | 3981 | 443.99 | -3.93 | 447.92 | Yes | N/A | N/A | 2023-03-03 | 2023-03-31 | 29 | 21 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-05-19 | Unknown | Unknown | 29 | 21 | 0 | 0 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | -376 | -270 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 931.38 | 253.74 | Unknown | Unknown | Unknown | 677.64 | 3981 | 1635.65 | 931.38 | 704.27 | Yes | N/A | N/A | 2024-09-24 | 2024-09-24 | 1 | 1 | 2024-09-24 | 2024-09-24 | 1 | 1 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-11-14 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-12-09 | 1900-01-25 | 18 | 2024-12-09 | 2024-12-09 | 1 | 1 | 53 | 39 | 28 | 20 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-15 | -34 | -25 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-10 | 2023-12-21 | IOU Designed & Installed | N/A | No | N/A | 6.15 | -7.76 | Unknown | Unknown | Unknown | 13.91 | 3941 | 422.43 | 6.15 | 416.28 | Yes | N/A | N/A | 2023-10-10 | 2023-08-28 | Unknown | Unknown | 2023-08-28 | 2023-10-10 | 44 | 32 | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-12-21 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-01-12 | 1900-01-22 | 17 | 2024-01-12 | 2024-01-12 | 1 | 1 | 73 | 53 | 68 | 50 | 141 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-08 | -322 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | 2025-01-23 | IOU Designed & Installed | N/A | No | N/A | 1682.94 | -33.2 | Unknown | Unknown | Unknown | 1716.14 | 3981 | 1797.26 | 1682.94 | 114.32 | Yes | N/A | N/A | 2025-01-22 | 2025-01-17 | Unknown | Unknown | 2025-01-17 | 2025-01-22 | 6 | 4 | 2025-01-22 | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-11 | 21 | 15 | 2025-01-22 | 2025-01-23 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-02-20 | 1900-01-28 | 21 | 2025-02-20 | 2025-02-20 | 1 | 1 | 2 | 2 | 57 | 41 | 59 | 43 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Chula Vista | CHULA VISTA | 93.4 | 93.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-19 | -58 | -43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | 2024-06-11 | IOU Designed & Installed | N/A | No | N/A | 2895.34 | 340.82 | Unknown | Unknown | Unknown | 2554.52 | Unknown | 6107.76 | 2895.34 | 3212.42 | Yes | N/A | N/A | 2024-01-18 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2024-06-05 | 190 | 136 | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-05-03 | 79 | 57 | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-07-23 | 1900-02-11 | 31 | 2024-07-23 | 2024-07-23 | 1 | 1 | 0 | 0 | 313 | 225 | 313 | 225 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -640 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-10-14 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 144.12 | -2.5 | Unknown | Unknown | Unknown | 146.62 | 3981 | 1541.05 | 144.12 | 1396.93 | Yes | N/A | N/A | 2024-09-25 | 2024-10-14 | 20 | 14 | 2024-10-14 | 2024-10-14 | 1 | 1 | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2024-11-07 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-12-05 | 1900-01-28 | 21 | 2024-12-05 | 2024-11-27 | Unknown | Unknown | 45 | 33 | 30 | 22 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-14 | -523 | -374 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-09-27 | IOU Designed & Installed | N/A | No | N/A | 2113.76 | 367.35 | Unknown | 353.25 | 17.1 | 1376.06 | 3981 | 948.04 | 2113.76 | -1165.72 | Yes | N/A | N/A | 2023-06-13 | 2023-07-13 | 31 | 23 | 2023-07-13 | 2023-07-13 | 1 | 1 | 2023-07-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | 2023-09-27 | 77 | 55 | Unknown | 2023-09-19 | Unknown | Unknown | 2023-09-27 | 2023-11-08 | 1900-02-11 | 31 | 2023-11-08 | 2023-11-08 | 1 | 1 | 108 | 78 | 45 | 33 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-07 | 784 | 561 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-25 | 2025-05-21 | IOU Designed & Installed | N/A | No | N/A | 1670.61 | -12.92 | Unknown | Unknown | 20.17 | 1663.36 | 3661.75 | 510.15 | 1670.61 | -1160.46 | Yes | N/A | N/A | 2024-01-25 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-13 | 2 | 2 | 2025-03-28 | 2025-05-21 | 55 | 39 | 2024-01-26 | 2025-05-21 | 482 | 344 | Unknown | 2025-03-06 | Unknown | Unknown | 2025-05-21 | 2025-05-30 | 1900-01-09 | 8 | 2025-05-30 | 2025-05-30 | 1 | 1 | 484 | 346 | 66 | 48 | 550 | 394 | Steps 2,3,5,6,7 | 527 | 375 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | 9480 | 9480 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-11-27 | -622 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | 2024-01-16 | IOU Designed & Installed | N/A | No | N/A | 968.71 | -20.53 | Unknown | Unknown | Unknown | 989.24 | 3981 | 840.33 | 968.71 | -128.38 | Yes | N/A | N/A | 2023-12-20 | 2023-12-06 | Unknown | Unknown | 2023-12-06 | 2023-12-20 | 15 | 11 | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-01-16 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-03-15 | 1900-02-28 | 44 | 2024-03-15 | 2024-03-15 | 1 | 1 | 28 | 20 | 76 | 56 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | -427 | -306 | No | 2024-11-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | 2025-05-16 | IOU Designed & Installed | N/A | Yes | 112 | 608.5 | 344.88 | Unknown | Unknown | -1262.79 | 1526.41 | Unknown | 1263.56 | 608.5 | 655.06 | Yes | N/A | N/A | 2024-11-14 | 2025-02-27 | 106 | 76 | 2025-02-27 | 2024-11-27 | Unknown | Unknown | 2024-11-27 | 2025-04-11 | 136 | 98 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-05-16 | 150 | 108 | Unknown | 2025-05-15 | Unknown | Unknown | 2025-05-16 | 2025-05-29 | 1900-01-13 | 10 | 2025-05-29 | 2025-05-29 | 1 | 1 | 392 | 282 | 15 | 11 | 407 | 293 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 17.05 | 17.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | -533 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-12-02 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 178.62 | -2.82 | Unknown | Unknown | 0.55 | 180.89 | Unknown | 1721.9 | 178.62 | 1543.28 | Yes | N/A | N/A | 2024-10-29 | 2024-10-11 | Unknown | Unknown | 2024-10-11 | 2024-12-02 | 53 | 37 | 2024-12-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2025-02-10 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-04-03 | 1900-02-21 | 39 | 2025-04-03 | 2025-04-03 | 1 | 1 | 71 | 51 | 107 | 77 | 178 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | -542 | -388 | No | 2024-02-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | 2024-04-05 | IOU Designed & Installed | N/A | Yes | 47 | -4.58 | -8.73 | Unknown | Unknown | Unknown | 4.15 | 3961 | 684.1 | -4.58 | 688.68 | Yes | N/A | N/A | 2024-02-02 | 2024-03-12 | 40 | 28 | 2024-03-12 | 2024-03-20 | 9 | 7 | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-04-05 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-05-09 | 1900-02-03 | 25 | 2024-05-09 | 2024-05-08 | Unknown | Unknown | 104 | 74 | 44 | 32 | 148 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-28 | -45 | -32 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-16 | 2023-09-19 | IOU Designed & Installed | N/A | No | N/A | 26.15 | -6.76 | Unknown | Unknown | 29.6 | 3.31 | 3981 | 804.49 | 26.15 | 778.34 | Yes | N/A | N/A | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2023-09-19 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2025-03-14 | 1901-06-26 | 389 | 2025-03-14 | 2025-03-14 | 1 | 1 | 36 | 26 | 545 | 391 | 581 | 417 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -490 | -351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2557.46 | -12.9 | Unknown | Unknown | 13.54 | 2556.82 | 3981 | 2557.47 | 2557.46 | 0.01 | Yes | N/A | N/A | 2024-09-03 | 2024-06-10 | Unknown | Unknown | 2024-06-10 | 2024-12-26 | 200 | 144 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | 2025-01-16 | 22 | 16 | Unknown | 2025-01-03 | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | 2025-01-17 | 2025-01-16 | Unknown | Unknown | 22 | 16 | 200 | 144 | 222 | 160 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | Rancho Santa Fe | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-20 | -137 | -99 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-01 | 2023-03-04 | IOU Designed & Installed | N/A | No | N/A | -518.19 | 1037.26 | Unknown | 264.3 | -2317 | 497.25 | Unknown | 2317.16 | -518.19 | 2835.35 | Yes | N/A | N/A | 2023-02-01 | 2023-02-01 | 1 | 1 | 2023-02-01 | 2023-09-05 | 217 | 155 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | Unknown | Unknown | Unknown | 2023-09-05 | 2023-09-05 | 1 | 1 | 2023-03-04 | 2023-09-05 | 1900-07-04 | 132 | 2023-09-05 | 2023-09-05 | 1 | 1 | 1 | 1 | 405 | 289 | 406 | 290 | Steps 2,3,5,6,7 | 185 | 131 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56, EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | 221 | 160 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-27 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 6787.72 | 1126.44 | Unknown | 825.77 | 74.02 | 4761.49 | 2875.23 | 1334.68 | 6787.72 | -5453.04 | Yes | N/A | N/A | 2024-03-27 | 2024-04-30 | 35 | 25 | 2024-04-30 | 2024-05-06 | 7 | 5 | 2024-06-03 | 2024-06-04 | 2 | 2 | 2024-05-02 | 2024-06-21 | 51 | 37 | 2024-05-06 | 2025-01-21 | 261 | 187 | Unknown | 2024-12-31 | Unknown | Unknown | 2025-02-10 | 2025-02-10 | 1899-12-31 | 1 | 2025-02-10 | 2025-02-07 | Unknown | Unknown | 298 | 214 | 59 | 43 | 357 | 257 | Steps 2,3,5,6,7 | 79 | 57 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 21 | 21 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-25 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | 16950.17 | 4447.61 | Unknown | 739.75 | 419.72 | 11343.09 | 3981 | 4521.33 | 16950.17 | -12428.84 | Yes | N/A | N/A | 2024-11-25 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-26 | 14 | 10 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-04-22 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-02 | 1900-01-10 | 9 | 2025-05-02 | 2025-05-01 | Unknown | Unknown | 148 | 106 | 25 | 19 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | -410 | -293 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 9157.51 | 2215.78 | Unknown | Unknown | Unknown | 6941.73 | 7962 | 2800.37 | 9157.51 | -6357.14 | Yes | N/A | N/A | 2024-08-14 | 2024-08-13 | Unknown | Unknown | 2024-08-13 | 2024-08-19 | 7 | 5 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | 2025-05-19 | 2025-06-04 | 17 | 13 | 0 | 0 | 24 | 18 | 24 | 18 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 208 | 208 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-14 | -469 | -336 | No | 2024-01-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-02-07 | Unknown | IOU Designed & Installed | N/A | Yes | 121 | -1120.94 | -14.65 | Unknown | Unknown | -2146.72 | 1040.43 | 3981 | 2630.42 | -1120.94 | 3751.36 | Yes | N/A | N/A | 2024-01-24 | 2024-05-24 | 122 | 88 | 2024-05-24 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-05-30 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | Unknown | 2024-07-02 | Unknown | Unknown | 2024-07-02 | 2024-07-02 | 1 | 1 | 221 | 159 | 1 | 1 | 222 | 160 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-25 | -457 | -327 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 3594.31 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-28 | 2025-02-11 | 15 | 11 | 2025-02-11 | 2025-02-13 | 3 | 3 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | 2025-04-24 | 2025-04-24 | 1 | 1 | 15 | 11 | 4 | 4 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | -618 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 326.48 | Unknown | Unknown | Unknown | 4.53 | 321.95 | 3981 | 1197.95 | 326.48 | 871.47 | Yes | N/A | N/A | 2024-05-29 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-06-06 | 50 | 36 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-06-06 | 1 | 1 | Unknown | 2024-06-26 | Unknown | Unknown | 2024-06-06 | 2024-08-01 | 1900-02-25 | 41 | 2024-08-01 | 2024-07-31 | Unknown | Unknown | 1 | 1 | 107 | 77 | 108 | 78 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-07 | -133 | -96 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-22 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 1257.37 | -6.9 | Unknown | Unknown | 79.03 | 1185.24 | 3981 | 1024.37 | 1257.37 | -233 | Yes | N/A | N/A | 2024-11-22 | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2024-12-05 | 15 | 11 | 2024-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | 2025-01-22 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-06-27 | 1900-06-05 | 113 | 2025-06-27 | 2025-06-27 | 1 | 1 | 49 | 35 | 173 | 125 | 222 | 160 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-30 | 915 | 654 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | 2025-02-28 | IOU Designed & Installed | N/A | No | N/A | -2545.16 | 947.6 | Unknown | Unknown | -16493 | 13000.24 | 3981 | 19848.85 | -2545.16 | 22394.01 | Yes | N/A | N/A | 2023-11-29 | 2023-11-21 | Unknown | Unknown | 2023-11-21 | 2024-10-09 | 324 | 232 | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-03-13 | 13 | 9 | 2024-10-09 | 2025-02-13 | 128 | 92 | 2025-01-07 | 2025-01-22 | 16 | 12 | 2025-02-28 | 2025-04-07 | 1900-02-07 | 27 | 2025-04-07 | 2025-04-02 | Unknown | Unknown | 128 | 92 | 392 | 280 | 520 | 372 | Steps 2,3,5,6,7 | 37 | 27 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-19 | -294 | -211 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2023-09-29 | IOU Designed & Installed | N/A | No | N/A | 696.76 | 392.28 | Unknown | 117.92 | Unknown | 186.56 | Unknown | 149.82 | 696.76 | -546.94 | Yes | N/A | N/A | 2023-09-27 | 2023-08-31 | Unknown | Unknown | 2023-08-31 | 2023-09-27 | 28 | 20 | 2023-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2023-09-29 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-10-30 | 1900-01-31 | 22 | 2023-10-30 | 2023-10-30 | 1 | 1 | 3 | 3 | 61 | 43 | 64 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | -477 | -341 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2025-01-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 660.33 | -12.88 | Unknown | Unknown | 0.19 | 673.02 | Unknown | 1183.52 | 660.33 | 523.19 | Yes | N/A | N/A | 2024-09-09 | 2024-09-09 | 1 | 1 | 2024-09-09 | 2025-01-08 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-01-25 | 23 | 16 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | 2025-03-28 | 2025-03-28 | 1 | 1 | 1 | 1 | 146 | 105 | 147 | 106 | Steps 2,3,5,6,7 | 17 | 12 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-14 | -246 | -177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | 2023-06-09 | IOU Designed & Installed | N/A | No | N/A | 242.93 | -15.29 | Unknown | Unknown | Unknown | 258.22 | Unknown | 776.47 | 242.93 | 533.54 | Yes | N/A | N/A | 2023-05-19 | 2023-05-22 | 4 | 2 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | 2023-06-09 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2023-07-12 | 1900-02-02 | 24 | 2023-07-12 | 2023-07-12 | 1 | 1 | 23 | 17 | 35 | 25 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | -270 | -194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-06-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 11333.24 | -11.82 | Unknown | Unknown | Unknown | 11345.06 | 3981 | 1554.56 | 11333.24 | -9778.68 | Yes | N/A | N/A | 2024-03-28 | 2024-05-22 | 56 | 40 | 2024-05-22 | 2025-03-05 | 288 | 206 | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-01-01 | 41 | 29 | 2025-03-05 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | 2025-03-31 | 2025-03-25 | Unknown | Unknown | 56 | 40 | 329 | 235 | 385 | 275 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-08 | -305 | -220 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3.68 | Unknown | Unknown | Unknown | Unknown | 3.68 | 3981 | 192.83 | 3.68 | 189.15 | Yes | N/A | N/A | 2023-10-31 | 2024-06-14 | 228 | 164 | 2024-06-14 | 2024-06-17 | 4 | 2 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | Unknown | Unknown | 2024-10-07 | 2024-10-07 | 1 | 1 | 228 | 164 | 5 | 3 | 233 | 167 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | DEL MAR | DEL MAR | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-22 | 138 | 99 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-02-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 13.64 | -12.11 | Unknown | Unknown | Unknown | 25.75 | 0 | 993.44 | 13.64 | 979.8 | Yes | N/A | N/A | 2023-02-22 | 2023-02-22 | 1 | 1 | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-04-23 | 42 | 30 | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | Unknown | Unknown | 2024-07-09 | 2024-07-09 | 1 | 1 | 1 | 1 | 43 | 31 | 44 | 32 | Steps 2,3,5,6,7 | 426 | 304 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-28 | -295 | -212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-07 | 2024-12-30 | IOU Designed & Installed | N/A | No | N/A | 1333.45 | Unknown | Unknown | Unknown | 5.91 | 1327.54 | Unknown | 1472.13 | 1333.45 | 138.68 | Yes | N/A | N/A | 2024-11-04 | 2024-11-04 | 1 | 1 | 2024-11-04 | 2024-11-25 | 22 | 16 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-30 | 36 | 26 | Unknown | 2024-12-27 | Unknown | Unknown | 2024-12-30 | 2025-01-06 | 1900-01-07 | 6 | 2025-01-06 | 2025-01-06 | 1 | 1 | 37 | 27 | 31 | 23 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-29 | -586 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-11 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 16.06 | Unknown | Unknown | Unknown | Unknown | 16.06 | Unknown | 2124.26 | 16.06 | 2108.2 | Yes | N/A | N/A | 2024-06-11 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-06-11 | 70 | 50 | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-07-09 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-08-20 | 1900-02-11 | 31 | 2024-08-20 | 2024-08-20 | 1 | 1 | 29 | 21 | 114 | 82 | 143 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-11 | -626 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 1525.72 | -29.59 | Unknown | Unknown | Unknown | 1555.31 | 3981 | 1815.96 | 1525.72 | 290.24 | Yes | N/A | N/A | 2025-01-29 | 2025-01-29 | 1 | 1 | 2025-01-29 | 2025-01-30 | 2 | 2 | 2025-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-03 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-03-25 | 1900-02-19 | 37 | 2025-03-25 | 2025-03-25 | 1 | 1 | 6 | 4 | 54 | 40 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-24 | -260 | -187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-29 | 2023-09-13 | IOU Designed & Installed | N/A | No | N/A | -212.03 | 2519.84 | Unknown | 494.75 | -4278 | 1051.38 | Unknown | 4277.9 | -212.03 | 4489.93 | Yes | N/A | N/A | 2023-08-16 | 2023-08-22 | 7 | 5 | 2023-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2023-11-07 | 1900-02-24 | 40 | 2023-11-07 | 2023-11-07 | 1 | 1 | 7 | 5 | 57 | 41 | 64 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | 24 | 18 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-27 | 2024-12-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 711.57 | -1.83 | Unknown | Unknown | Unknown | 713.4 | Unknown | 499.14 | 711.57 | -212.43 | Yes | N/A | N/A | 2024-11-27 | 2024-12-03 | 7 | 5 | 2024-12-03 | 2025-02-25 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-05 | 1 | 1 | 7 | 5 | 86 | 62 | 93 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-01 | 110 | 79 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-04 | 2024-09-04 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 18.62 | Unknown | Unknown | Unknown | Unknown | 18.62 | 3981 | 1003.26 | 18.62 | 984.64 | Yes | N/A | N/A | 2023-01-04 | 2024-08-23 | 598 | 428 | 2024-08-23 | 2024-09-04 | 13 | 9 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-10 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-19 | 1900-01-09 | 8 | 2024-09-19 | 2024-09-19 | 1 | 1 | 605 | 433 | 24 | 18 | 629 | 451 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-25 | -306 | -219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | -4.49 | -18.81 | Unknown | Unknown | Unknown | 14.32 | 3981 | 1455.31 | -4.49 | 1459.8 | Yes | N/A | N/A | 2025-03-04 | 2025-03-04 | 1 | 1 | 2025-03-04 | 2025-03-04 | 1 | 1 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-03-17 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-03-25 | 1900-01-08 | 7 | 2025-03-25 | 2025-03-25 | 1 | 1 | 15 | 11 | 11 | 9 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-08 | -618 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-02-11 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | 275.43 | 88.41 | Unknown | Unknown | Unknown | 187.02 | 3981 | 2272.21 | 275.43 | 1996.78 | Yes | N/A | N/A | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | 2025-02-11 | 15 | 11 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-04-22 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-04-30 | 1900-01-08 | 7 | 2025-04-30 | 2025-04-30 | 1 | 1 | 72 | 52 | 25 | 19 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | -345 | -248 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 318.43 | -8.35 | Unknown | Unknown | 12.06 | 314.72 | 3981 | 422.05 | 318.43 | 103.62 | Yes | N/A | N/A | 2023-04-19 | 2023-08-15 | 119 | 85 | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-02-21 | Unknown | Unknown | 119 | 85 | 0 | 0 | 119 | 85 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | -369 | -265 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-05 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 1760.09 | 194.21 | Unknown | Unknown | 64.9 | 1500.98 | 3981 | 1297.43 | 1760.09 | -462.66 | Yes | N/A | N/A | 2024-06-05 | 2024-06-11 | 7 | 5 | 2024-06-11 | 2024-06-11 | 1 | 1 | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2025-03-05 | 268 | 192 | Unknown | 2025-02-24 | Unknown | Unknown | 2025-03-05 | 2025-03-10 | 1900-01-05 | 4 | 2025-03-10 | 2025-03-10 | 1 | 1 | 275 | 197 | 8 | 6 | 283 | 203 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | -399 | -286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-07-14 | 2023-08-31 | IOU Designed & Installed | N/A | No | N/A | 688.13 | -13.33 | Unknown | Unknown | 58.48 | 642.98 | 3981 | 408.69 | 688.13 | -279.44 | Yes | N/A | N/A | 2023-06-29 | 2023-07-14 | 16 | 12 | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | 2023-08-31 | 49 | 35 | Unknown | 2023-08-30 | Unknown | Unknown | 2023-08-31 | 2024-01-19 | 1900-05-21 | 102 | 2024-01-19 | 2024-01-19 | 1 | 1 | 65 | 47 | 144 | 104 | 209 | 151 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-09 | 570 | 408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | -106.17 | 2991.08 | Unknown | Unknown | -9286 | 6188.75 | 1755875 | 68696.9 | -106.17 | 68803.07 | Yes | N/A | N/A | 2023-05-10 | 2023-05-10 | 1 | 1 | 2023-05-10 | 2024-03-22 | 318 | 228 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-05-16 | 56 | 40 | Unknown | 2024-05-21 | Unknown | Unknown | Unknown | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-06-01 | Unknown | Unknown | 57 | 41 | 318 | 228 | 375 | 269 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 92.1 | 92.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | -263 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-06-12 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | 22.78 | -20.18 | Unknown | Unknown | Unknown | 42.96 | 3981 | 1739.06 | 22.78 | 1716.28 | Yes | N/A | N/A | 2023-03-22 | 2023-08-10 | 142 | 102 | 2023-08-10 | 2023-08-10 | 1 | 1 | 2023-08-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-12 | 2024-04-22 | 316 | 226 | Unknown | 2024-04-19 | Unknown | Unknown | 2024-04-22 | 2024-05-14 | 1900-01-22 | 17 | 2024-05-14 | 2024-05-13 | Unknown | Unknown | 458 | 328 | 24 | 18 | 482 | 346 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-13 | -252 | -181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-17 | 2024-05-22 | IOU Designed & Installed | N/A | No | N/A | 18.06 | -16.05 | Unknown | Unknown | Unknown | 34.11 | 3981 | 871.7 | 18.06 | 853.64 | Yes | N/A | N/A | 2024-05-17 | 2024-02-28 | Unknown | Unknown | 2024-02-28 | 2024-05-17 | 80 | 58 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-05-22 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-06-07 | 1900-01-16 | 13 | 2024-06-07 | 2024-06-06 | Unknown | Unknown | 6 | 4 | 97 | 71 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | -570 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-02-12 | 2024-03-20 | IOU Designed & Installed | N/A | No | N/A | 935.39 | -33.59 | Unknown | Unknown | Unknown | 968.98 | Unknown | 952.8 | 935.39 | 17.41 | Yes | N/A | N/A | 2024-01-19 | 2024-02-12 | 25 | 17 | 2024-02-12 | 2024-02-12 | 1 | 1 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-03-20 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-04-15 | 1900-01-26 | 19 | 2024-04-15 | 2024-04-15 | 1 | 1 | 63 | 45 | 29 | 21 | 92 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | COTO DE CAZA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-19 | 97 | 70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 74.16 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-17 | 2024-05-22 | 6 | 4 | 2024-05-22 | 2024-05-22 | 1 | 1 | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | 2025-06-24 | 2025-06-24 | 1 | 1 | 6 | 4 | 2 | 2 | 8 | 6 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-28 | -486 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-22 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | 279.4 | -7.74 | Unknown | Unknown | 2.57 | 284.57 | 3981 | 1109.09 | 279.4 | 829.69 | Yes | N/A | N/A | 2024-02-22 | 2024-03-07 | 15 | 11 | 2024-03-07 | 2024-03-07 | 1 | 1 | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-04-22 | 47 | 33 | Unknown | 2024-04-16 | Unknown | Unknown | 2024-04-22 | 2024-04-29 | 1900-01-07 | 6 | 2024-04-29 | 2024-04-29 | 1 | 1 | 62 | 44 | 10 | 8 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-18 | -648 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-16 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | 571.47 | -10.89 | Unknown | Unknown | Unknown | 582.36 | Unknown | 1989.82 | 571.47 | 1418.35 | Yes | N/A | N/A | 2025-01-15 | 2025-03-03 | 48 | 34 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-03-03 | 41 | 29 | 2025-03-03 | 2025-03-03 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | 2025-03-10 | 1900-01-07 | 6 | 2025-03-10 | 2025-03-10 | 1 | 1 | 49 | 35 | 50 | 36 | 99 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | 316 | 316 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-27 | 395 | 284 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-19 | 2024-04-14 | IOU Designed & Installed | N/A | No | N/A | 33022 | 4527.53 | Unknown | Unknown | Unknown | 28494.47 | 168041 | 30758.42 | 33022 | -2263.58 | Yes | N/A | N/A | 2023-10-17 | 2023-10-13 | Unknown | Unknown | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-04-03 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-14 | 2024-04-25 | 1900-01-11 | 9 | 2024-04-25 | 2024-04-25 | 1 | 1 | 0 | 0 | 41 | 30 | 41 | 30 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-22 | -455 | -326 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-02 | 2024-05-22 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 23.59 | Unknown | Unknown | Unknown | Unknown | 23.59 | 3981 | 1020.01 | 23.59 | 996.42 | Yes | N/A | N/A | 2024-03-02 | 2024-05-22 | 82 | 58 | 2024-05-22 | 2024-05-22 | 1 | 1 | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-09-06 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-24 | 1900-01-18 | 13 | 2024-09-24 | 2024-09-23 | Unknown | Unknown | 190 | 136 | 20 | 14 | 210 | 150 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 7303.05 | 7303.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-06-24 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-15 | 2024-07-18 | 2024-12-02 | IOU Designed & Installed | N/A | No | N/A | 1552.86 | Unknown | Unknown | Unknown | 9.16 | 1543.7 | 3981 | 1271.46 | 1552.86 | -281.4 | Yes | N/A | N/A | 2024-07-15 | 2024-08-09 | 26 | 20 | 2024-08-09 | 2024-08-09 | 1 | 1 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-12-02 | 116 | 82 | Unknown | 2024-12-02 | Unknown | Unknown | 2024-12-02 | 2024-12-10 | 1900-01-08 | 7 | 2024-12-10 | 2024-12-10 | 1 | 1 | 142 | 102 | 11 | 9 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | 220 | 220 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | -94 | -67 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | 2024-08-21 | 2024-10-02 | IOU Designed & Installed | N/A | No | N/A | 3770.36 | 574.42 | Unknown | 280.2 | Unknown | 2915.74 | Unknown | 508.27 | 3770.36 | -3262.09 | Yes | N/A | N/A | 2024-08-19 | 2024-08-19 | 1 | 1 | 2024-08-19 | 2024-09-25 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | 2024-10-02 | 2024-10-03 | 1900-01-01 | 2 | 2024-10-03 | 2024-10-03 | 1 | 1 | 1 | 1 | 41 | 31 | 42 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | 114.1 | 114.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-30 | -15 | -12 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2024-05-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 930.18 | -16.99 | Unknown | Unknown | Unknown | 947.17 | 15495 | 1502.51 | 930.18 | 572.33 | Yes | N/A | N/A | 2023-10-17 | 2024-04-24 | 191 | 137 | 2024-04-24 | 2024-06-25 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-08-05 | 55 | 39 | 2024-06-25 | 2024-08-15 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | 2024-08-16 | 2024-08-15 | Unknown | Unknown | 243 | 175 | 118 | 84 | 361 | 259 | Steps 2,3,5,6,7 | 41 | 29 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-08 | 58 | 41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 565.31 | -11.35 | Unknown | Unknown | Unknown | 576.66 | 3981 | 179.5 | 565.31 | -385.81 | Yes | N/A | N/A | 2024-10-21 | 2024-10-23 | 3 | 3 | 2024-10-23 | 2024-10-29 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-11-22 | 31 | 23 | 2024-10-29 | 2025-03-20 | 143 | 103 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | 2025-04-08 | 2025-04-07 | Unknown | Unknown | 146 | 106 | 38 | 28 | 184 | 134 | Steps 2,3,5,6,7 | 24 | 18 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-06 | -533 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2024-11-08 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | 620.9 | Unknown | Unknown | Unknown | -1337.78 | 1958.68 | Unknown | 1338.8 | 620.9 | 717.9 | Yes | N/A | N/A | 2024-11-08 | 2025-01-14 | 68 | 48 | 2025-01-14 | 2025-01-27 | 14 | 10 | 2025-01-27 | 2025-02-12 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-04-09 | 56 | 40 | Unknown | 2025-04-08 | Unknown | Unknown | 2025-04-09 | 2025-04-21 | 1900-01-12 | 9 | 2025-04-21 | 2025-04-21 | 1 | 1 | 141 | 101 | 28 | 20 | 169 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Marcos | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | 282 | 201 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-03 | 2024-06-11 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 34841.82 | 11761.22 | Unknown | Unknown | -21404.13 | 44484.73 | Unknown | 20212.97 | 34841.82 | -14628.85 | Yes | N/A | N/A | 2024-01-03 | 2024-01-18 | 16 | 12 | 2024-01-18 | 2024-03-12 | 55 | 39 | 2024-02-01 | 2024-02-02 | 2 | 2 | 2024-03-11 | 2024-03-26 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | 2024-06-11 | 2024-07-08 | 1900-01-27 | 20 | 2024-07-08 | 2024-07-08 | 1 | 1 | 18 | 14 | 100 | 72 | 118 | 86 | Steps 2,3,5,6,7 | 40 | 28 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-02 | -669 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-22 | 2025-04-22 | 2025-05-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1821.71 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-22 | 2025-04-22 | 1 | 1 | 2025-04-22 | 2025-04-22 | 1 | 1 | 2025-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-05-23 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | 2025-06-02 | 1900-01-10 | 7 | 2025-06-02 | 2025-06-02 | 1 | 1 | 33 | 25 | 13 | 9 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | -550 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | 2024-02-14 | IOU Designed & Installed | N/A | No | N/A | 1422.11 | 473.37 | Unknown | Unknown | Unknown | 948.74 | 3981 | 934.34 | 1422.11 | -487.77 | Yes | N/A | N/A | 2024-01-04 | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2024-01-04 | 114 | 82 | 2024-01-04 | 2024-02-26 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-02-14 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-02-29 | 1900-01-15 | 12 | 2024-02-29 | 2024-02-29 | 1 | 1 | 96 | 68 | 131 | 95 | 227 | 163 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 494 | 494 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | 419 | 300 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2024-01-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 45.28 | Unknown | Unknown | Unknown | Unknown | 45.28 | 0 | 983.09 | 45.28 | 937.81 | Yes | N/A | N/A | 2023-10-17 | 2024-01-18 | 94 | 68 | 2024-01-18 | 2024-01-24 | 7 | 5 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-01-22 | 1 | 1 | 94 | 68 | 8 | 6 | 102 | 74 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-11 | -45 | -33 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | 2024-03-20 | IOU Designed & Installed | N/A | No | N/A | 2223.37 | 458.07 | Unknown | 36.6 | Unknown | 1728.7 | 3981 | 1278.44 | 2223.37 | -944.93 | Yes | N/A | N/A | 2024-02-14 | 2023-07-25 | Unknown | Unknown | 2023-07-25 | 2024-02-14 | 205 | 147 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-03-20 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-03-27 | 1900-01-07 | 6 | 2024-03-27 | 2024-03-27 | 1 | 1 | 36 | 26 | 214 | 154 | 250 | 180 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | -660 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-14 | 2025-04-18 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2192.49 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-14 | 2025-03-13 | Unknown | Unknown | 2025-03-13 | 2025-03-14 | 2 | 2 | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-04-18 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-05-14 | 1900-01-26 | 19 | 2025-05-14 | 2025-05-14 | 1 | 1 | 36 | 26 | 30 | 22 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | RAMONA | N/A | 131 | 131 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-10 | -195 | -140 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-11-13 | 2024-12-03 | IOU Designed & Installed | N/A | No | N/A | 10012.72 | 6446.33 | Unknown | Unknown | -4553.11 | 8119.5 | 3981 | 15168.76 | 10012.72 | 5156.04 | Yes | N/A | N/A | 2023-10-05 | 2023-10-25 | 21 | 15 | 2023-10-25 | 2023-11-13 | 20 | 14 | 2023-11-13 | 2024-02-27 | 107 | 77 | 2024-03-11 | 2024-03-26 | 16 | 12 | 2024-02-27 | 2024-12-03 | 281 | 201 | Unknown | 2024-11-06 | Unknown | Unknown | 2024-12-03 | 2024-12-03 | 1899-12-31 | 1 | 2024-12-03 | 2024-11-27 | Unknown | Unknown | 409 | 293 | 37 | 27 | 446 | 320 | Steps 2,3,5,6,7 | 28 | 20 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | -492 | -353 | No | 2024-11-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-21 | 2025-06-17 | IOU Designed & Installed | N/A | Yes | 69 | -63.05 | Unknown | Unknown | Unknown | -1512.77 | 1449.72 | Unknown | 1369.5 | -63.05 | 1432.55 | Yes | N/A | N/A | 2024-11-21 | 2025-01-29 | 70 | 50 | 2025-01-29 | 2024-12-13 | Unknown | Unknown | 2024-12-13 | 2025-03-19 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-06-17 | 91 | 65 | Unknown | 2025-06-13 | Unknown | Unknown | 2025-06-17 | 2025-06-24 | 1900-01-07 | 6 | 2025-06-24 | 2025-06-23 | Unknown | Unknown | 258 | 184 | 8 | 6 | 266 | 190 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-11 | -179 | -129 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-09-21 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | -1.04 | Unknown | Unknown | Unknown | Unknown | -1.04 | Unknown | 496.37 | -1.04 | 497.41 | Yes | N/A | N/A | 2023-08-04 | 2023-09-21 | 49 | 35 | 2023-09-21 | 2023-09-21 | 1 | 1 | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2023-10-13 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-11-15 | 1900-02-02 | 24 | 2023-11-15 | 2023-11-14 | Unknown | Unknown | 72 | 52 | 35 | 25 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ALISO VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-25 | -326 | -233 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-25 | 2025-04-05 | IOU Designed & Installed | N/A | No | N/A | -8475.6 | 3683.64 | Unknown | Unknown | -13847 | 1687.76 | Unknown | 13846.83 | -8475.6 | 22322.43 | Yes | N/A | N/A | 2025-02-25 | 2025-03-03 | 7 | 5 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-05 | 2025-04-05 | 1899-12-31 | 0 | 2025-04-05 | 2025-04-05 | 1 | 0 | 7 | 5 | 2 | 0 | 9 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 150 | 108 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-05-03 | 2023-11-27 | IOU Designed & Installed | N/A | No | N/A | 2529.37 | Unknown | Unknown | Unknown | Unknown | 2529.37 | Unknown | 1247.74 | 2529.37 | -1281.63 | Yes | N/A | N/A | 2023-04-12 | 2023-10-16 | 188 | 134 | 2023-10-16 | 2023-10-26 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2024-03-13 | 1900-04-17 | 78 | 2024-03-13 | 2024-03-13 | 1 | 1 | 188 | 134 | 120 | 88 | 308 | 222 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | 629 | 450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-07-16 | 2024-10-17 | IOU Designed & Installed | N/A | No | N/A | 121412.36 | 533.76 | Unknown | 57.51 | Unknown | 120821.09 | 12210754 | Not available | 121412.36 | Unknown | Yes | N/A | N/A | 2024-07-09 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-09-10 | 89 | 63 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-23 | 14 | 10 | Unknown | 2024-09-16 | Unknown | Unknown | 2024-10-17 | 2024-11-25 | 1900-02-08 | 28 | 2024-11-25 | 2024-11-19 | Unknown | Unknown | 14 | 10 | 129 | 91 | 143 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | MISSION VIEJO | N/A | 237.1 | 237.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-20 | -664 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 483.77 | Unknown | Unknown | Unknown | 1.41 | 482.36 | 3981 | 2773.5 | 483.77 | 2289.73 | Yes | N/A | N/A | 2025-01-07 | 2025-01-17 | 11 | 9 | 2025-01-17 | 2025-01-21 | 5 | 3 | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-02-24 | 1 | 1 | 11 | 9 | 6 | 4 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-06 | -528 | -377 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | 2023-07-21 | IOU Designed & Installed | N/A | No | N/A | -9.65 | -6.99 | Unknown | Unknown | Unknown | -2.66 | Unknown | 341 | -9.65 | 350.65 | Yes | N/A | N/A | 2023-03-10 | 2023-03-10 | 1 | 1 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | 2023-07-21 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2023-07-28 | 1900-01-07 | 6 | 2023-07-28 | 2023-07-28 | 1 | 1 | 135 | 97 | 9 | 7 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-05 | 15 | 11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | 753.17 | -10.6 | Unknown | Unknown | 17.19 | 746.58 | 15924 | 975.98 | 753.17 | 222.81 | Yes | N/A | N/A | 2023-09-07 | 2023-09-06 | Unknown | Unknown | 2023-09-06 | 2023-10-13 | 38 | 28 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2024-04-17 | 188 | 134 | Unknown | 2024-04-15 | Unknown | Unknown | 2024-04-17 | 2024-05-06 | 1900-01-19 | 14 | 2024-05-06 | 2024-05-20 | 15 | 11 | 188 | 134 | 73 | 53 | 261 | 187 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-25 | -728 | -521 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-04-26 | 2023-04-28 | IOU Designed & Installed | N/A | No | N/A | 863.3 | 332 | Unknown | 44.05 | Unknown | 487.25 | Unknown | 846.74 | 863.3 | -16.56 | Yes | N/A | N/A | 2023-04-26 | 2023-04-26 | 1 | 1 | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-26 | 2023-04-28 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | 2023-04-28 | 1899-12-31 | 1 | 2023-04-28 | 2023-04-28 | 1 | 1 | 4 | 4 | 2 | 2 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-14 | -646 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-08 | 2025-01-08 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 84.66 | Unknown | Unknown | Unknown | 7.45 | 77.21 | Unknown | 2072.29 | 84.66 | 1987.63 | Yes | N/A | N/A | 2025-01-08 | 2024-12-20 | Unknown | Unknown | 2024-12-20 | 2025-01-08 | 20 | 14 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-22 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-06 | 1900-01-15 | 12 | 2025-02-06 | 2025-02-06 | 1 | 1 | 15 | 11 | 37 | 27 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-22 | -191 | -136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-15 | 2024-01-29 | IOU Designed & Installed | N/A | No | N/A | 194.91 | -22.86 | Unknown | Unknown | 0.32 | 217.45 | 3981 | 777.92 | 194.91 | 583.01 | Yes | N/A | N/A | 2023-11-15 | 2023-10-17 | Unknown | Unknown | 2023-10-17 | 2023-11-15 | 30 | 22 | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2024-01-29 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-03-15 | 1900-02-15 | 35 | 2024-03-15 | 2024-03-15 | 1 | 1 | 76 | 54 | 78 | 58 | 154 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-27 | -653 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-21 | 2024-08-02 | IOU Designed & Installed | N/A | No | N/A | 2297.21 | 509.48 | Unknown | 94.54 | Unknown | 1693.19 | Unknown | 1514.42 | 2297.21 | -782.79 | Yes | N/A | N/A | 2024-06-18 | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-07-01 | 29 | 21 | 2024-07-01 | Unknown | Unknown | Unknown | 2024-07-01 | 2024-07-12 | 12 | 10 | 2024-07-01 | 2024-08-02 | 33 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-08-12 | 1900-01-10 | 7 | 2024-08-12 | 2024-08-12 | 1 | 1 | 33 | 25 | 53 | 39 | 86 | 64 | Steps 2,3,5,6,7 | 11 | 9 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | Oceanside | OCEANSIDE | 3104 | 3104 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-10-10 | 221 | 158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | 2025-05-19 | IOU Designed & Installed | N/A | No | N/A | 344840.38 | 98907.58 | Unknown | Unknown | 1641.21 | 244291.59 | 608133.55 | Not available | 344840.38 | Unknown | Yes | N/A | N/A | 2023-03-30 | 2024-02-26 | 334 | 238 | 2024-02-26 | 2025-02-07 | 348 | 250 | 2024-09-03 | 2025-05-14 | 24 | 18 | 2024-07-05 | 2025-05-20 | -70 | -58 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | 2025-05-19 | 1899-12-31 | 1 | 2025-05-19 | 2025-05-19 | 1 | 1 | 358 | 256 | 280 | 194 | 638 | 450 | Steps 2,3,5,6,7 | 470 | 336 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | 194.15 | 194.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-04 | 590 | 423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-26 | 2023-07-21 | 2024-07-08 | IOU Designed & Installed | N/A | No | N/A | 19779.97 | 3033.76 | Unknown | Unknown | -7484.49 | 24230.7 | 7508 | 27214.83 | 19779.97 | 7434.86 | Yes | N/A | N/A | 2023-05-26 | 2023-06-06 | 12 | 8 | 2023-06-06 | 2024-03-29 | 298 | 214 | 2023-10-18 | 2024-07-02 | 217 | 155 | 2023-10-05 | 2024-04-10 | 21 | 15 | 2024-03-29 | Unknown | Unknown | Unknown | 2024-04-09 | 2024-06-11 | 64 | 46 | 2024-07-08 | 2024-08-16 | 1900-02-08 | 30 | 2024-08-16 | 2024-08-16 | 1 | 1 | 229 | 163 | 424 | 306 | 653 | 469 | Steps 2,3,5,6,7 | 446 | 318 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-07 | -292 | -209 | No | 2022-08-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-22 | 2022-08-22 | Unknown | IOU Designed & Installed | N/A | Yes | 238 | 58.7 | -5.86 | Unknown | Unknown | Unknown | 64.56 | Unknown | 1019.55 | 58.7 | 960.85 | Yes | N/A | N/A | 2022-08-22 | 2023-04-17 | 239 | 171 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | Unknown | Unknown | 2023-09-19 | 2023-09-19 | 1 | 1 | 239 | 171 | 1 | 1 | 240 | 172 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-20 | -471 | -338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-06 | 2023-11-15 | IOU Designed & Installed | N/A | No | N/A | -8.92 | -6.75 | Unknown | Unknown | Unknown | -2.17 | Unknown | 480.37 | -8.92 | 489.29 | Yes | N/A | N/A | 2023-09-06 | 2023-03-30 | Unknown | Unknown | 2023-03-30 | 2023-09-06 | 161 | 115 | 2023-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | 2023-11-15 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2023-12-05 | 1900-01-20 | 15 | 2023-12-05 | 2023-12-05 | 1 | 1 | 71 | 51 | 183 | 131 | 254 | 182 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34.4 | 34.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-18 | -597 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-07-09 | 2024-08-23 | IOU Designed & Installed | N/A | No | N/A | 666.87 | Unknown | Unknown | Unknown | 6.6 | 660.27 | 3981 | 1104.02 | 666.87 | 437.15 | Yes | N/A | N/A | 2024-06-06 | 2024-04-29 | Unknown | Unknown | 2024-04-29 | 2024-07-09 | 72 | 52 | 2024-07-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-08-23 | 46 | 34 | Unknown | 2024-08-16 | Unknown | Unknown | 2024-08-23 | 2024-09-03 | 1900-01-11 | 8 | 2024-09-03 | 2024-08-29 | Unknown | Unknown | 46 | 34 | 84 | 60 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-30 | 901 | 644 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 6691 | 768.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-15 | 2024-02-15 | 1 | 1 | 2024-02-15 | 2024-02-22 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-09-04 | 196 | 140 | Unknown | 2025-06-09 | Unknown | Unknown | 2025-06-18 | 2025-06-18 | 1899-12-31 | 1 | 2025-06-18 | 2025-06-18 | 1 | 1 | 197 | 141 | 10 | 8 | 207 | 149 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 78.05 | 78.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-30 | 81 | 59 | No | 2023-05-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-22 | 2023-07-18 | IOU Designed & Installed | N/A | Yes | 2 | 33.22 | -10.75 | Unknown | Unknown | Unknown | 43.97 | 3241 | 479.76 | 33.22 | 446.54 | Yes | N/A | N/A | 2023-05-22 | 2023-05-24 | 3 | 3 | 2023-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | 2023-07-18 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-07-20 | 1900-01-02 | 3 | 2023-07-20 | 2023-07-20 | 1 | 1 | 61 | 45 | 4 | 4 | 65 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-11 | 29 | 21 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-25 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 7957.7 | Unknown | Unknown | Unknown | 1466.78 | 6490.92 | 2225 | 173.51 | 7957.7 | -7784.19 | Yes | N/A | N/A | 2023-04-25 | 2023-04-25 | 1 | 1 | 2023-04-25 | 2024-06-18 | 421 | 301 | 2024-04-19 | 2024-06-11 | 54 | 38 | 2024-08-08 | 2024-08-13 | 6 | 4 | 2024-06-28 | Unknown | Unknown | Unknown | 2024-06-28 | 2024-07-15 | 18 | 12 | 2024-08-22 | 2024-09-09 | 1900-01-18 | 13 | 2024-09-09 | 2024-09-09 | 1 | 1 | 55 | 39 | 465 | 331 | 520 | 370 | Steps 2,3,5,6,7 | 106 | 74 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 698.05 | 698.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-20 | -554 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-18 | 2024-03-04 | IOU Designed & Installed | N/A | No | N/A | 5.82 | -5.19 | Unknown | Unknown | Unknown | 11.01 | Unknown | 1202.46 | 5.82 | 1196.64 | Yes | N/A | N/A | 2024-01-09 | 2023-09-29 | Unknown | Unknown | 2023-09-29 | 2024-01-18 | 112 | 80 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-03-04 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-03-15 | 1900-01-11 | 10 | 2024-03-15 | 2024-03-15 | 1 | 1 | 47 | 33 | 125 | 91 | 172 | 124 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 200.05 | 200.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-09 | -181 | -130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 28.26 | -34.7 | Unknown | Unknown | -490.52 | 553.48 | 3981 | 1966.83 | 28.26 | 1938.57 | Yes | N/A | N/A | 2023-04-26 | 2023-12-12 | 231 | 165 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-06-11 | Unknown | Unknown | 231 | 165 | 0 | 0 | 231 | 165 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-05 | -371 | -266 | No | 2022-11-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-02 | 2022-11-02 | 2023-01-18 | IOU Designed & Installed | N/A | Yes | 93 | 1293.2 | -10.61 | Unknown | Unknown | 55.1 | 1248.71 | 3981 | 537.71 | 1293.2 | -755.49 | Yes | N/A | N/A | 2022-11-02 | 2023-02-03 | 94 | 68 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-30 | 2023-01-18 | Unknown | Unknown | Unknown | 2023-04-12 | Unknown | Unknown | 2023-01-18 | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | 94 | 68 | 1 | 1 | 95 | 69 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -331 | -238 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-29 | 2023-12-29 | 2024-02-07 | IOU Designed & Installed | N/A | No | N/A | -10.33 | -8.4 | Unknown | Unknown | Unknown | -1.93 | 3961 | 158.79 | -10.33 | 169.12 | Yes | N/A | N/A | 2023-12-29 | 2023-12-14 | Unknown | Unknown | 2023-12-14 | 2023-12-29 | 16 | 12 | 2023-12-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | 2024-02-07 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-02-28 | 1900-01-21 | 16 | 2024-02-28 | 2024-02-28 | 1 | 1 | 41 | 29 | 39 | 29 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 118 | 118 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-10 | 60 | 43 | No | 2022-12-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | 2024-08-17 | IOU Designed & Installed | N/A | Yes | 355 | 13202.9 | Unknown | Unknown | Unknown | Unknown | 13202.9 | 3981 | 530.75 | 13202.9 | -12672.15 | Yes | N/A | N/A | 2022-12-07 | 2023-11-27 | 356 | 254 | 2023-11-27 | 2024-03-27 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | 2024-08-17 | 2024-10-11 | 1900-02-24 | 40 | 2024-10-11 | 2024-10-09 | Unknown | Unknown | 356 | 254 | 179 | 129 | 535 | 383 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-20 | -193 | -138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-08-31 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | -1002.32 | -5.16 | Unknown | Unknown | -1009 | 11.84 | Unknown | 1008.9 | -1002.32 | 2011.22 | Yes | N/A | N/A | 2023-08-31 | 2023-08-31 | 1 | 1 | 2023-08-31 | 2023-09-18 | 19 | 13 | 2023-09-18 | 2024-06-03 | 260 | 186 | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2024-07-09 | 293 | 209 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-07-11 | 1900-01-02 | 3 | 2024-07-11 | 2024-07-11 | 1 | 1 | 554 | 396 | 23 | 17 | 577 | 413 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | SAN CLEMENTE | SAN CLEMENTE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-07 | 402 | 287 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-14 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | 5917.53 | 273.47 | Unknown | Unknown | -368.87 | 6012.93 | 3981 | 2325.06 | 5917.53 | -3592.47 | Yes | N/A | N/A | 2024-03-14 | 2023-11-07 | Unknown | Unknown | 2023-11-07 | 2024-04-11 | 157 | 113 | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2024-04-10 | 2 | 2 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-05-13 | 1900-01-26 | 19 | 2024-05-13 | 2024-05-13 | 1 | 1 | 0 | 0 | 187 | 135 | 187 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | -378 | -271 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2024-02-02 | IOU Designed & Installed | N/A | No | N/A | 518.59 | -14.71 | Unknown | Unknown | -580.7 | 1114 | 0 | 618.42 | 518.59 | 99.83 | Yes | N/A | N/A | 2023-04-11 | 2023-04-17 | 7 | 5 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | 2024-02-02 | 262 | 188 | Unknown | 2024-01-31 | Unknown | Unknown | 2024-02-02 | 2024-03-14 | 1900-02-10 | 30 | 2024-03-14 | 2024-03-14 | 1 | 1 | 269 | 193 | 43 | 31 | 312 | 224 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-26 | -602 | -431 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-23 | 2024-10-25 | IOU Designed & Installed | N/A | No | N/A | 33.99 | Unknown | Unknown | Unknown | Unknown | 33.99 | Unknown | 1696.55 | 33.99 | 1662.56 | Yes | N/A | N/A | 2024-08-05 | 2024-08-23 | 19 | 15 | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | Unknown | Unknown | Unknown | 2024-08-23 | 2024-09-17 | 26 | 18 | 2024-10-25 | 2024-10-25 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2024-11-01 | 1900-01-07 | 6 | 2024-11-01 | 2024-11-01 | 1 | 1 | 20 | 16 | 36 | 26 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-18 | -229 | -164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-06-07 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 21.43 | Unknown | Unknown | Unknown | Unknown | 21.43 | 3981 | 1339.17 | 21.43 | 1317.74 | Yes | N/A | N/A | 2024-05-21 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-06-07 | 79 | 57 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-07-29 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-01 | 1900-01-03 | 4 | 2024-08-01 | 2024-08-01 | 1 | 1 | 53 | 37 | 84 | 62 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-20 | -200 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-20 | 2024-11-28 | IOU Designed & Installed | N/A | No | N/A | 1202.36 | 541.49 | Unknown | 52.54 | -1438 | 2046.33 | 0 | 1771.19 | 1202.36 | 568.83 | Yes | N/A | N/A | 2023-12-19 | 2023-09-11 | Unknown | Unknown | 2023-09-11 | 2024-03-05 | 177 | 127 | 2024-03-05 | 2024-10-08 | 218 | 156 | 2024-10-22 | 2024-10-22 | 1 | 1 | 2024-03-05 | 2024-11-28 | 269 | 193 | Unknown | 2024-11-15 | Unknown | Unknown | 2024-11-28 | 2024-12-02 | 1900-01-04 | 3 | 2024-12-02 | 2024-12-02 | 1 | 1 | 487 | 349 | 184 | 132 | 671 | 481 | Steps 2,3,5,6,7 | 231 | 165 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 113.05 | 113.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-20 | -62 | -45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-14 | 2023-01-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.96 | -5.78 | Unknown | Unknown | Unknown | 3.82 | Unknown | 857.31 | -1.96 | 859.27 | Yes | N/A | N/A | 2022-12-14 | 2023-01-31 | 49 | 35 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | Unknown | Unknown | 2023-07-20 | 2023-07-20 | 1 | 1 | 49 | 35 | 1 | 1 | 50 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-13 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | 1859.43 | 705.52 | Unknown | 94.21 | Unknown | 1059.7 | 3981 | 197.01 | 1859.43 | -1662.42 | Yes | N/A | N/A | 2024-12-13 | 2024-11-21 | Unknown | Unknown | 2024-11-21 | 2025-01-07 | 48 | 34 | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-02-26 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-03-01 | 1900-01-03 | 3 | 2025-03-01 | 2025-02-28 | Unknown | Unknown | 51 | 37 | 52 | 37 | 103 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | N/A | 75.05 | 75.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-20 | -607 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2023-10-24 | 2023-11-16 | IOU Designed & Installed | N/A | No | N/A | 1249.83 | 408.26 | Unknown | 82.76 | Unknown | 758.81 | 3241 | 1550.5 | 1249.83 | 300.67 | Yes | N/A | N/A | 2023-10-24 | 2023-10-24 | 1 | 1 | 2023-10-24 | 2023-10-24 | 1 | 1 | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2023-11-16 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2023-11-21 | 1900-01-05 | 4 | 2023-11-21 | 2023-11-21 | 1 | 1 | 25 | 19 | 8 | 6 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 198.05 | 198.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-08 | -301 | -216 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-05-01 | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | 7797.11 | Unknown | Unknown | Unknown | Unknown | 7797.11 | 3981 | 1133 | 7797.11 | -6664.11 | Yes | N/A | N/A | 2024-01-16 | 2024-04-30 | 106 | 76 | 2024-04-30 | 2024-06-05 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | 2024-09-17 | 2024-10-11 | 1900-01-24 | 19 | 2024-10-11 | 2024-10-11 | 1 | 1 | 106 | 76 | 63 | 47 | 169 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-02 | -171 | -123 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1885.76 | 1333.62 | Unknown | 389.35 | -4131 | 522.27 | Unknown | 4130.27 | -1885.76 | 6016.03 | Yes | N/A | N/A | 2023-07-18 | 2023-07-18 | 1 | 1 | 2023-07-18 | 2023-08-04 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | Unknown | Unknown | Unknown | 2023-09-13 | 2023-09-13 | 1 | 1 | Unknown | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2023-09-13 | 1 | 1 | 1 | 1 | 20 | 16 | 21 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-10 | -520 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 1389.06 | Unknown | Unknown | Unknown | 5.73 | 1383.33 | 3980 | 1345.87 | 1389.06 | -43.19 | Yes | N/A | N/A | 2024-10-18 | 2024-11-04 | 18 | 12 | 2024-11-04 | 2025-03-21 | 138 | 100 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-04-02 | 52 | 38 | Unknown | 2025-03-11 | Unknown | Unknown | 2025-04-02 | 2025-04-08 | 1900-01-06 | 5 | 2025-04-08 | 2025-04-08 | 1 | 1 | 70 | 50 | 146 | 106 | 216 | 156 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-09 | -529 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-06-28 | IOU Designed & Installed | N/A | No | N/A | 680.13 | 349.41 | Unknown | 110.7 | Unknown | 220.02 | Unknown | 153.75 | 680.13 | -526.38 | Yes | N/A | N/A | 2023-02-14 | 2023-05-26 | 102 | 74 | 2023-05-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | 2023-06-28 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-06-29 | 1900-01-01 | 2 | 2023-06-29 | 2023-06-29 | 1 | 1 | 136 | 98 | 3 | 3 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 1022 | 1022 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-03-29 | -26 | -20 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-25 | 2024-10-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 7615.84 | Unknown | Unknown | Unknown | Unknown | 7615.84 | 3981 | 785.31 | 7615.84 | -6830.53 | Yes | N/A | N/A | 2024-10-25 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | 2024-11-05 | 355 | 253 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-11-15 | 1 | 1 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | 2025-03-03 | 2025-03-03 | 1 | 1 | 0 | 0 | 357 | 255 | 357 | 255 | Steps 2,3,5,6,7 | 10 | 8 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-31 | 131 | 94 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-05-16 | 2023-10-07 | IOU Designed & Installed | N/A | No | N/A | 6156.87 | 1097.22 | Unknown | 2089.84 | Unknown | 2969.81 | Unknown | 1023.93 | 6156.87 | -5132.94 | Yes | N/A | N/A | 2023-05-15 | 2023-05-16 | 2 | 2 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-09-28 | 10 | 8 | 2023-05-16 | 2023-10-07 | 145 | 104 | Unknown | 2023-10-05 | Unknown | Unknown | 2023-10-07 | 2023-10-09 | 1900-01-02 | 1 | 2023-10-09 | 2023-10-09 | 1 | 1 | 147 | 106 | 14 | 10 | 161 | 116 | Steps 2,3,5,6,7 | 135 | 97 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 125.05 | 125.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-12 | -213 | -154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1.19 | -9.26 | Unknown | Unknown | 1.96 | 8.49 | 3981 | 768.86 | 1.19 | 767.67 | Yes | N/A | N/A | 2023-10-09 | 2023-09-26 | Unknown | Unknown | 2023-09-26 | 2023-10-12 | 17 | 13 | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | Unknown | Unknown | 2024-02-12 | 2024-02-12 | 1 | 1 | 0 | 0 | 18 | 14 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2026-03-05 | -301 | -216 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 57.64 | -0.94 | Unknown | Unknown | Unknown | 58.58 | 54899 | 81.53 | 57.64 | 23.89 | Yes | N/A | N/A | 2024-03-21 | 2024-08-08 | 141 | 101 | 2024-08-08 | 2024-10-31 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-06-17 | 44 | 32 | 2024-10-31 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | Unknown | 2025-05-08 | Unknown | Unknown | 2025-05-08 | 2025-05-08 | 1 | 1 | 141 | 101 | 130 | 94 | 271 | 195 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-03 | -63 | -46 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-14 | 2022-11-14 | 2024-04-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 6430.48 | 153.74 | Unknown | 41.21 | -15284 | 21519.53 | 0 | 14877.73 | 6430.48 | 8447.25 | Yes | N/A | N/A | 2022-11-14 | 2023-03-15 | 122 | 88 | 2023-03-15 | 2024-03-08 | 360 | 258 | 2023-03-22 | 2023-03-28 | 7 | 5 | 2023-03-28 | 2023-05-31 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-04-01 | Unknown | Unknown | 2024-04-01 | 2024-04-01 | 1 | 1 | 129 | 93 | 382 | 274 | 511 | 367 | Steps 2,3,5,6,7 | 352 | 252 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | -484 | -346 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2024-10-02 | IOU Designed & Installed | N/A | No | N/A | 1497.25 | Unknown | Unknown | Unknown | 48.14 | 1449.11 | 3941 | 992.81 | 1497.25 | -504.44 | Yes | N/A | N/A | 2024-04-11 | 2024-05-03 | 23 | 17 | 2024-05-03 | 2024-05-03 | 1 | 1 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-10-02 | 153 | 109 | Unknown | 2024-09-12 | Unknown | Unknown | 2024-10-02 | 2024-10-04 | 1900-01-02 | 3 | 2024-10-04 | 2024-10-04 | 1 | 1 | 176 | 126 | 5 | 5 | 181 | 131 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-03 | -455 | -326 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2024-12-20 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | 990.84 | -19.91 | Unknown | Unknown | Unknown | 1010.75 | Unknown | 2292.31 | 990.84 | 1301.47 | Yes | N/A | N/A | 2024-12-20 | 2024-12-20 | 1 | 1 | 2024-12-20 | 2024-12-20 | 1 | 1 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-04-25 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-05 | 1900-01-10 | 7 | 2025-05-05 | 2025-05-05 | 1 | 1 | 128 | 92 | 13 | 9 | 141 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | San Diego | San Diego | 2615179 | 2615179 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-09-05 | 645 | 462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-04-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | -21317.72 | Unknown | Unknown | Unknown | -24345 | 3027.28 | 0 | 23675.67 | -21317.72 | 44993.39 | Yes | N/A | N/A | 2023-03-22 | 2023-12-15 | 269 | 193 | 2023-12-15 | 2024-04-30 | 138 | 98 | 2023-12-29 | 2024-01-03 | 6 | 4 | 2024-01-26 | 2024-05-15 | 45 | 33 | 2025-05-20 | Unknown | Unknown | Unknown | 2025-05-20 | 2025-05-20 | 1 | 1 | Unknown | 2025-06-11 | Unknown | Unknown | 2025-06-11 | 2025-06-11 | 1 | 1 | 275 | 197 | 185 | 133 | 460 | 330 | Steps 2,3,5,6,7 | 123 | 87 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | Valley Center | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 404 | 289 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-27 | 2022-07-27 | 2024-04-24 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 61610.64 | 14105.84 | Unknown | Unknown | -9872.89 | 57377.69 | 29340 | 48199.33 | 61610.64 | -13411.31 | Yes | N/A | N/A | 2022-07-27 | 2023-02-15 | 204 | 146 | 2023-02-15 | 2023-05-03 | 78 | 56 | 2023-03-15 | 2023-05-24 | 47 | 33 | 2023-03-15 | 2024-02-23 | 20 | 14 | 2023-05-17 | Unknown | Unknown | Unknown | 2023-05-17 | 2024-04-12 | 332 | 238 | 2024-04-24 | 2024-05-09 | 1900-01-15 | 12 | 2024-05-09 | 2024-05-09 | 1 | 1 | 251 | 179 | 447 | 321 | 698 | 500 | Steps 2,3,5,6,7 | 401 | 287 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-22 | -534 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | 2024-09-20 | IOU Designed & Installed | N/A | No | N/A | -1574.76 | Unknown | Unknown | Unknown | -1606 | 31.24 | Unknown | 1606.03 | -1574.76 | 3180.79 | Yes | N/A | N/A | 2024-08-08 | 2024-03-26 | Unknown | Unknown | 2024-03-26 | 2024-08-08 | 136 | 98 | 2024-08-08 | 2024-09-18 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-09-20 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-04 | 1900-01-14 | 11 | 2024-10-04 | 2024-10-04 | 1 | 1 | 45 | 33 | 152 | 110 | 197 | 143 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | 611 | 611 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-11 | -64 | -47 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-19 | 2024-04-19 | 2024-04-24 | IOU Designed & Installed | N/A | No | N/A | 7260.68 | Unknown | Unknown | Unknown | Unknown | 7260.68 | Unknown | 687.87 | 7260.68 | -6572.81 | Yes | N/A | N/A | 2024-04-19 | 2024-03-12 | Unknown | Unknown | 2024-03-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-08 | 1900-01-14 | 11 | 2024-05-08 | 2024-05-08 | 1 | 1 | 0 | 0 | 16 | 12 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-30 | -155 | -111 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-10 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 15.02 | -13.34 | Unknown | Unknown | Unknown | 28.36 | 3981 | 955 | 15.02 | 939.98 | Yes | N/A | N/A | 2024-04-10 | 2023-12-06 | Unknown | Unknown | 2023-12-06 | 2024-04-10 | 127 | 91 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-06-10 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-06-28 | 1900-01-18 | 15 | 2024-06-28 | 2024-06-28 | 1 | 1 | 62 | 44 | 147 | 107 | 209 | 151 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-15 | -659 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-12 | 2024-02-20 | IOU Designed & Installed | N/A | No | N/A | 17.24 | -15.3 | Unknown | Unknown | Unknown | 32.54 | Unknown | 970.67 | 17.24 | 953.43 | Yes | N/A | N/A | 2024-02-12 | 2024-01-19 | Unknown | Unknown | 2024-01-19 | 2023-02-12 | Unknown | Unknown | 2023-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-02-20 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-03-27 | 1900-02-05 | 27 | 2024-03-27 | 2024-03-27 | 1 | 1 | 9 | 7 | 38 | 28 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN CLEMENTE | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-02 | -593 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-17 | 2025-01-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 7962 | 1976.1 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-17 | 2025-01-29 | 13 | 9 | 2025-01-29 | 2025-01-31 | 3 | 3 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | 2025-05-19 | 2025-05-19 | 1 | 1 | 13 | 9 | 4 | 4 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-12 | -234 | -168 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-11-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -351.22 | 985.76 | Unknown | Unknown | -1724 | 387.02 | Unknown | 1723.68 | -351.22 | 2074.9 | Yes | N/A | N/A | 2023-11-13 | 2023-11-08 | Unknown | Unknown | 2023-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-02-21 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-16 | 562 | 401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-03-17 | 2025-06-26 | IOU Designed & Installed | N/A | No | N/A | 2691.29 | Unknown | Unknown | Unknown | 12.84 | 2678.45 | 55868 | 6506.07 | 2691.29 | 3814.78 | Yes | N/A | N/A | 2025-02-18 | 2025-03-17 | 28 | 20 | 2025-03-17 | 2025-06-02 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-06-13 | 24 | 18 | 2025-06-02 | 2025-06-25 | 24 | 18 | Unknown | 2025-06-24 | Unknown | Unknown | 2025-06-26 | 2025-07-01 | 1900-01-05 | 4 | 2025-07-01 | 2025-06-30 | Unknown | Unknown | 52 | 38 | 108 | 78 | 160 | 116 | Steps 2,3,5,6,7 | 11 | 9 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 114 | 114 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-01 | 264 | 189 | No | 2022-10-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-05 | 2022-10-05 | Unknown | IOU Designed & Installed | N/A | Yes | 141 | 495.3 | -15.47 | Unknown | Unknown | Unknown | 510.77 | 6481 | 783.78 | 495.3 | 288.48 | Yes | N/A | N/A | 2022-10-05 | 2023-02-23 | 142 | 102 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-08-22 | 1 | 1 | 142 | 102 | 1 | 1 | 143 | 103 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-14 | -553 | -396 | No | 2025-01-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-09 | 2025-06-04 | IOU Designed & Installed | N/A | Yes | 8 | 1356 | -27.25 | Unknown | Unknown | Unknown | 1383.25 | 3981 | 1959.18 | 1356 | 603.18 | Yes | N/A | N/A | 2025-01-02 | 2025-01-10 | 9 | 7 | 2025-01-10 | 2025-01-10 | 1 | 1 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-06-04 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-06-09 | 1900-01-05 | 4 | 2025-06-09 | 2025-06-09 | 1 | 1 | 156 | 112 | 8 | 6 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-11 | 131 | 94 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-03-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12974.45 | Unknown | Unknown | Unknown | Unknown | 12974.45 | 3981 | 616.21 | 12974.45 | -12358.24 | Yes | N/A | N/A | 2024-01-30 | 2024-02-14 | 16 | 12 | 2024-02-14 | 2024-03-07 | 23 | 17 | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | Unknown | 2025-05-22 | Unknown | Unknown | 2025-05-22 | 2025-05-22 | 1 | 1 | 16 | 12 | 24 | 18 | 40 | 30 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-27 | 539 | 386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-19 | 2023-02-03 | 2025-06-17 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 357.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-01-19 | 2023-02-03 | 16 | 12 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | 2025-06-17 | 866 | 618 | Unknown | 2025-06-05 | Unknown | Unknown | 2025-06-17 | 2025-06-18 | 1900-01-01 | 2 | 2025-06-18 | 2025-06-18 | 1 | 1 | 882 | 630 | 3 | 3 | 885 | 633 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-02 | -508 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-07 | 2024-02-26 | IOU Designed & Installed | N/A | No | N/A | -8.27 | -14.73 | Unknown | Unknown | -796.82 | 803.28 | Unknown | 803.85 | -8.27 | 812.12 | Yes | N/A | N/A | 2023-11-07 | 2023-11-29 | 23 | 17 | 2023-11-29 | 2023-12-04 | 6 | 4 | 2023-12-04 | 2023-12-07 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2024-02-26 | 74 | 52 | Unknown | 2024-03-11 | Unknown | Unknown | 2024-02-26 | 2024-03-12 | 1900-01-15 | 12 | 2024-03-12 | 2024-03-12 | 1 | 1 | 101 | 73 | 23 | 17 | 124 | 90 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-12-28 | 90 | 65 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-14 | 2023-06-14 | 2023-12-19 | IOU Designed & Installed | N/A | No | N/A | 484.28 | -28.94 | Unknown | Unknown | Unknown | 513.22 | 0 | Not available | 484.28 | Unknown | Yes | N/A | N/A | 2023-06-14 | 2023-05-10 | Unknown | Unknown | 2023-05-10 | 2023-06-20 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | Unknown | Unknown | 2023-12-19 | 2024-03-27 | 1900-04-09 | 72 | 2024-03-27 | 2024-03-27 | 1 | 1 | 0 | 0 | 143 | 103 | 143 | 103 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-25 | -46 | -33 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2023-10-26 | 2023-11-06 | IOU Designed & Installed | N/A | No | N/A | 1077.27 | 378.69 | Unknown | Unknown | Unknown | 698.58 | 11943 | 865.02 | 1077.27 | -212.25 | Yes | N/A | N/A | 2023-10-26 | 2023-10-26 | 1 | 1 | 2023-10-26 | 2023-10-26 | 1 | 1 | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2023-11-06 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2023-11-09 | 1900-01-03 | 4 | 2023-11-09 | 2023-11-09 | 1 | 1 | 13 | 9 | 6 | 6 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-11-12 | 1161 | 830 | No | 2020-07-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-07-22 | 2023-02-17 | 2023-11-09 | Customer elected Applicant Design | Step 2 Engineering & Design | Yes | 929 | 291478.88 | 108855.9 | Unknown | Unknown | 1050.03 | 181572.95 | 11702456 | 139725.99 | 291478.88 | -151752.89 | Yes | N/A | N/A | 2020-07-22 | 2023-03-27 | 979 | 699 | 2023-03-27 | 2023-08-24 | 151 | 109 | 2023-06-21 | 2023-08-23 | 3 | 3 | 2023-07-14 | 2023-10-04 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2023-11-07 | 37 | 27 | 2023-11-09 | 2023-12-12 | 1900-02-02 | 24 | 2023-12-12 | 2024-01-17 | 37 | 27 | 982 | 702 | 309 | 223 | 1291 | 925 | Steps 2,3,5,6,7 | 104 | 74 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 616 | 616 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-30 | -493 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-07 | 2023-08-24 | IOU Designed & Installed | N/A | No | N/A | 38.64 | -11.99 | Unknown | Unknown | 44.76 | 5.87 | 3981 | 826.17 | 38.64 | 787.53 | Yes | N/A | N/A | 2023-04-07 | 2023-04-07 | 1 | 1 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-08-24 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | 2024-11-19 | 1901-03-29 | 324 | 2024-11-19 | 2023-08-25 | Unknown | Unknown | 141 | 101 | 454 | 324 | 595 | 425 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 448.05 | 448.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-24 | -247 | -177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-05 | 2023-06-28 | 2023-07-18 | IOU Designed & Installed | N/A | No | N/A | 371.94 | -8.41 | Unknown | Unknown | Unknown | 380.35 | 3981 | 792.99 | 371.94 | 421.05 | Yes | N/A | N/A | 2023-01-05 | 2023-06-28 | 175 | 125 | 2023-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-28 | 2023-07-18 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-08-09 | 1900-01-22 | 17 | 2023-08-09 | 2023-12-21 | 135 | 97 | 196 | 140 | 158 | 114 | 354 | 254 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -557 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | -14.33 | -10.38 | Unknown | Unknown | Unknown | -3.95 | Unknown | 125.42 | -14.33 | 139.75 | Yes | N/A | N/A | 2023-03-24 | 2023-03-24 | 1 | 1 | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | 2023-07-17 | 116 | 82 | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-07-17 | 1899-12-31 | 1 | 2023-07-17 | 2023-07-17 | 1 | 1 | 117 | 83 | 2 | 2 | 119 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 89.05 | 89.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | 24 | 17 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-22 | 2023-09-22 | 2024-03-08 | IOU Designed & Installed | N/A | No | N/A | 1430.72 | -47.59 | Unknown | Unknown | Unknown | 1478.31 | 3981 | 900.88 | 1430.72 | -529.84 | Yes | N/A | N/A | 2023-09-22 | 2023-07-27 | Unknown | Unknown | 2023-07-27 | 2023-09-22 | 58 | 42 | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2024-03-08 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-04-03 | 1900-01-26 | 19 | 2024-04-03 | 2024-06-24 | 83 | 59 | 169 | 121 | 168 | 120 | 337 | 241 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-06 | -585 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 32.19 | Unknown | Unknown | Unknown | Unknown | 32.19 | 3981 | 1533.59 | 32.19 | 1501.4 | Yes | N/A | N/A | 2024-07-02 | 2024-03-22 | Unknown | Unknown | 2024-03-22 | 2024-07-02 | 103 | 73 | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-02 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-29 | 1900-01-27 | 20 | 2024-07-29 | 2024-07-29 | 1 | 1 | 1 | 1 | 132 | 94 | 133 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | POWAY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-16 | -642 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-26 | 2024-09-26 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 1031.92 | 184.3 | Unknown | Unknown | Unknown | 847.62 | Unknown | 2829.19 | 1031.92 | 1797.27 | Yes | N/A | N/A | 2024-09-26 | 2024-09-30 | 5 | 3 | 2024-09-30 | 2024-09-30 | 1 | 1 | 2024-09-30 | Unknown | Unknown | Unknown | 2024-09-30 | 2025-02-04 | 36 | 26 | 2024-10-21 | 2024-11-05 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2024-11-12 | 1900-01-07 | 6 | 2024-11-12 | 2024-11-12 | 1 | 1 | 21 | 15 | 46 | 34 | 67 | 49 | Steps 2,3,5,6,7 | 106 | 76 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | 315 | 226 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 783.11 | -11.93 | Unknown | Unknown | 11.89 | 783.15 | Unknown | 2310.92 | 783.11 | 1527.81 | Yes | N/A | N/A | 2023-11-29 | 2023-11-29 | 1 | 1 | 2023-11-29 | 2023-12-01 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2023-11-29 | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | Unknown | 2024-02-12 | Unknown | Unknown | 2024-02-12 | 2023-12-13 | Unknown | Unknown | 1 | 1 | 3 | 3 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | 1002.05 | 1002.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-08-25 | -193 | -138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-10-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 0.53 | -7.95 | Unknown | Unknown | Unknown | 8.48 | 3981 | 990.14 | 0.53 | 989.61 | Yes | N/A | N/A | 2023-09-28 | 2023-09-24 | Unknown | Unknown | 2023-09-24 | 2023-10-03 | 10 | 7 | 2023-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2024-02-14 | 1 | 1 | 0 | 0 | 11 | 8 | 11 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | MISSION VIEJO | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-01 | -185 | -132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 181.94 | -22.03 | Unknown | Unknown | 2.65 | 201.32 | 3981 | 769.32 | 181.94 | 587.38 | Yes | N/A | N/A | 2023-10-09 | 2023-09-18 | Unknown | Unknown | 2023-09-18 | 2023-10-19 | 32 | 24 | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | Unknown | Unknown | Unknown | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-02-29 | 1 | 1 | 0 | 0 | 33 | 25 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | -541 | -386 | No | 2023-03-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-14 | 2023-07-19 | IOU Designed & Installed | N/A | Yes | 73 | 844.84 | -8.45 | Unknown | Unknown | 14.62 | 838.67 | 3981 | 646.9 | 844.84 | -197.94 | Yes | N/A | N/A | 2023-03-14 | 2023-05-26 | 74 | 54 | 2023-05-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-07-19 | 121 | 87 | Unknown | 2023-06-20 | Unknown | Unknown | 2023-07-19 | 2023-07-14 | Unknown | Unknown | 2023-07-14 | 2023-07-14 | 1 | 1 | 195 | 141 | 1 | 1 | 196 | 142 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | -496 | -355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-09 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 2793.58 | Unknown | Unknown | Unknown | 23.44 | 2770.14 | 3981 | 1205.55 | 2793.58 | -1588.03 | Yes | N/A | N/A | 2024-08-09 | 2024-10-17 | 70 | 50 | 2024-10-17 | 2024-10-18 | 2 | 2 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2025-02-25 | 127 | 91 | Unknown | 2025-02-12 | Unknown | Unknown | 2025-02-25 | 2025-02-27 | 1900-01-02 | 3 | 2025-02-27 | 2025-02-27 | 1 | 1 | 197 | 141 | 6 | 6 | 203 | 147 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | -154 | -111 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-01 | 2024-07-01 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | -1117.84 | Unknown | Unknown | Unknown | -1129 | 11.16 | Unknown | 1015.58 | -1117.84 | 2133.42 | Yes | N/A | N/A | 2024-07-01 | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-07-01 | 49 | 35 | 2024-07-01 | 2024-08-21 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | 2024-09-16 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-09-24 | 1900-01-08 | 7 | 2024-09-24 | 2024-09-26 | 3 | 3 | 79 | 57 | 61 | 45 | 140 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 6300 | 6300 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-10-02 | 520 | 373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-09-10 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | 53214.11 | 13122.83 | Unknown | 114.73 | 151.88 | 39824.67 | Unknown | 20560.86 | 53214.11 | -32653.25 | Yes | N/A | N/A | 2024-07-17 | 2024-08-15 | 30 | 22 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-09 | 2025-01-10 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-03-05 | 1900-02-04 | 26 | 2025-03-05 | 2025-03-05 | 1 | 1 | 30 | 22 | 74 | 54 | 104 | 76 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-30 | -222 | -159 | No | 2024-01-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-03-28 | 2025-02-04 | IOU Designed & Installed | N/A | Yes | 279 | 134.51 | Unknown | Unknown | Unknown | 2.26 | 132.25 | 3981 | 1789.73 | 134.51 | 1655.22 | Yes | N/A | N/A | 2024-01-02 | 2024-10-07 | 280 | 200 | 2024-10-07 | 2024-03-28 | Unknown | Unknown | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2025-02-04 | 314 | 224 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-02-20 | 1900-01-16 | 13 | 2025-02-20 | 2025-02-20 | 1 | 1 | 594 | 424 | 18 | 14 | 612 | 438 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 138.15 | 138.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-14 | -59 | -42 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 544.82 | -13.64 | Unknown | Unknown | Unknown | 558.46 | 11943 | 1087.99 | 544.82 | 543.17 | Yes | N/A | N/A | 2023-08-14 | 2023-07-13 | Unknown | Unknown | 2023-07-13 | 2023-08-31 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | 2023-09-06 | 9 | 7 | 2023-08-31 | 2024-01-29 | 152 | 108 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-02-15 | Unknown | Unknown | 152 | 108 | 59 | 43 | 211 | 151 | Steps 2,3,5,6,7 | 6 | 4 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 80.4 | 80.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-08 | -591 | -424 | No | 2024-11-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-11-06 | 2025-02-11 | IOU Designed & Installed | N/A | Yes | 43 | 1443.49 | 109.68 | Unknown | Unknown | Unknown | 1333.81 | 3981 | 1596.41 | 1443.49 | 152.92 | Yes | N/A | N/A | 2024-11-06 | 2024-12-19 | 44 | 32 | 2024-12-19 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | Unknown | 2024-11-20 | 2025-01-01 | 43 | 31 | 2024-11-13 | 2025-02-11 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-02-24 | 1900-01-13 | 10 | 2025-02-24 | 2025-02-24 | 1 | 1 | 135 | 97 | 58 | 42 | 193 | 139 | Steps 2,3,5,6,7 | 49 | 35 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | 259 | 259 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-29 | -524 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-27 | 2024-10-17 | IOU Designed & Installed | N/A | No | N/A | -737.71 | -6.46 | Unknown | Unknown | -1122 | 390.75 | 3981 | 2257.56 | -737.71 | 2995.27 | Yes | N/A | N/A | 2024-06-20 | 2024-05-07 | Unknown | Unknown | 2024-05-07 | 2024-06-20 | 45 | 33 | 2024-06-20 | 2024-07-03 | 14 | 10 | 2024-11-05 | 2024-11-15 | 11 | 9 | 2024-07-03 | 2024-10-17 | 107 | 77 | Unknown | 2024-09-27 | Unknown | Unknown | 2024-10-17 | 2024-11-21 | 1900-02-04 | 26 | 2024-11-21 | 2024-11-21 | 1 | 1 | 121 | 87 | 93 | 69 | 214 | 156 | Steps 2,3,5,6,7 | 135 | 97 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | -186 | -135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-25 | 2024-03-15 | IOU Designed & Installed | N/A | No | N/A | 6916.69 | 2382.07 | Unknown | 146.15 | Unknown | 4388.47 | 3981 | 1046.83 | 6916.69 | -5869.86 | Yes | N/A | N/A | 2024-01-25 | 2024-02-06 | 13 | 9 | 2024-02-06 | 2024-02-06 | 1 | 1 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-03-15 | 39 | 29 | Unknown | 2024-03-13 | Unknown | Unknown | 2024-03-15 | 2024-03-25 | 1900-01-10 | 7 | 2024-03-25 | 2024-03-25 | 1 | 1 | 52 | 38 | 13 | 9 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 15001.35 | 15001.35 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-09-09 | -588 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-11-26 | 2024-12-23 | IOU Designed & Installed | N/A | No | N/A | 1855.01 | -36.03 | Unknown | Unknown | Unknown | 1891.04 | 3981 | 1731.08 | 1855.01 | -123.93 | Yes | N/A | N/A | 2024-10-24 | 2024-10-03 | Unknown | Unknown | 2024-10-03 | 2024-11-26 | 55 | 39 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2024-12-23 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-01-29 | 1900-02-06 | 28 | 2025-01-29 | 2025-01-29 | 1 | 1 | 28 | 20 | 94 | 68 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-29 | -566 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | 8.18 | Unknown | Unknown | Unknown | Unknown | 8.18 | 3241 | 1561.52 | 8.18 | 1553.34 | Yes | N/A | N/A | 2024-08-07 | 2024-08-07 | 1 | 1 | 2024-08-07 | 2024-08-07 | 1 | 1 | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-09-17 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-09-23 | 1900-01-06 | 5 | 2024-09-23 | 2024-10-10 | 18 | 14 | 43 | 31 | 26 | 20 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 70 | 70 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-31 | 134 | 97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-04-11 | 2023-06-05 | IOU Designed & Installed | N/A | No | N/A | -8.98 | -6.51 | Unknown | Unknown | Unknown | -2.47 | 3241 | 921.76 | -8.98 | 930.74 | Yes | N/A | N/A | 2023-03-07 | 2023-03-31 | 25 | 19 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-11 | 2023-06-05 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2023-06-14 | 1900-01-09 | 8 | 2023-06-14 | 2023-06-14 | 1 | 1 | 81 | 59 | 11 | 9 | 92 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-12 | -44 | -32 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 13.56 | Unknown | Unknown | Unknown | Unknown | 13.56 | 0 | 153.26 | 13.56 | 139.7 | Yes | N/A | N/A | 2024-04-15 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-04-15 | 5 | 3 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | 2025-02-27 | 2025-02-27 | 1 | 1 | 0 | 0 | 6 | 4 | 6 | 4 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JACUMBA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-26 | -289 | -208 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-17 | 2023-09-07 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 785.72 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-04 | 2023-08-17 | 14 | 10 | 2023-08-17 | 2023-08-17 | 1 | 1 | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2023-09-07 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | 2023-09-11 | 1900-01-04 | 3 | 2023-09-11 | 2023-09-11 | 1 | 1 | 36 | 26 | 7 | 5 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 3656 | 3656 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-06-07 | 38 | 27 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 469.41 | -15.74 | Unknown | Unknown | Unknown | 485.15 | 0 | 270.36 | 469.41 | -199.05 | Yes | N/A | N/A | 2023-07-17 | 2023-08-04 | 19 | 15 | 2023-08-04 | 2023-08-28 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-06-25 | 1 | 1 | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 19 | 15 | 27 | 19 | 46 | 34 | Steps 2,3,5,6,7 | 302 | 216 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-18 | 166 | 119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-22 | 2023-10-17 | IOU Designed & Installed | N/A | No | N/A | 698.14 | -28.88 | Unknown | Unknown | Unknown | 727.02 | 3981 | 735.69 | 698.14 | 37.55 | Yes | N/A | N/A | 2023-09-21 | 2023-09-08 | Unknown | Unknown | 2023-09-08 | 2023-09-21 | 14 | 10 | 2023-09-21 | Unknown | Unknown | Unknown | 2023-10-02 | 2023-10-06 | 5 | 5 | 2023-09-22 | 2023-10-17 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2023-11-01 | 1900-01-15 | 12 | 2023-11-01 | 2023-10-31 | Unknown | Unknown | 26 | 18 | 35 | 27 | 61 | 45 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | -638 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-25 | 2024-11-13 | IOU Designed & Installed | N/A | No | N/A | 408.52 | Unknown | Unknown | Unknown | -1206 | 1614.52 | Unknown | 1206.27 | 408.52 | 797.75 | Yes | N/A | N/A | 2024-09-18 | 2024-09-18 | 1 | 1 | 2024-09-18 | 2024-09-25 | 8 | 6 | 2024-09-25 | 2024-10-07 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-11-13 | 29 | 21 | Unknown | 2024-11-12 | Unknown | Unknown | 2024-11-13 | 2024-11-21 | 1900-01-08 | 7 | 2024-11-21 | 2024-11-21 | 1 | 1 | 43 | 31 | 18 | 14 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SANTEE | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-20 | -626 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | 2025-03-27 | IOU Designed & Installed | N/A | No | N/A | 2063.58 | -15.35 | Unknown | Unknown | 17.99 | 2060.94 | 3981 | 1321.81 | 2063.58 | -741.77 | Yes | N/A | N/A | 2025-01-07 | 2025-01-28 | 22 | 16 | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-03-27 | 59 | 43 | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-27 | 2025-04-03 | 1900-01-07 | 6 | 2025-04-03 | 2025-04-03 | 1 | 1 | 81 | 59 | 10 | 8 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | -262 | -189 | No | 2024-02-05 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-05 | 2025-02-03 | IOU Designed & Installed | N/A | Yes | 143 | 1277.14 | 253.74 | Unknown | Unknown | 17.19 | 1006.21 | 3981 | 1372.09 | 1277.14 | 94.95 | Yes | N/A | N/A | 2024-02-05 | 2024-06-27 | 144 | 104 | 2024-06-27 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2025-02-03 | 362 | 258 | Unknown | 2025-01-02 | Unknown | Unknown | 2025-02-03 | 2025-02-03 | 1899-12-31 | 1 | 2025-02-03 | 2025-02-03 | 1 | 1 | 506 | 362 | 2 | 2 | 508 | 364 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-14 | -188 | -135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | 2023-07-13 | IOU Designed & Installed | N/A | No | N/A | 1499.08 | 222.92 | Unknown | 117.92 | Unknown | 1158.24 | 3881 | 682.4 | 1499.08 | -816.68 | Yes | N/A | N/A | 2023-03-30 | 2023-03-30 | 1 | 1 | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | 2023-07-13 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | 2023-08-10 | 1900-01-28 | 21 | 2023-08-10 | 2023-08-10 | 1 | 1 | 107 | 77 | 30 | 22 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-05 | -392 | -281 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-23 | 2025-04-04 | IOU Designed & Installed | N/A | No | N/A | 3610 | 934.04 | Unknown | Unknown | 76.81 | 2599.15 | 3981 | 1166.61 | 3610 | -2443.39 | Yes | N/A | N/A | 2024-07-16 | 2024-09-25 | 72 | 52 | 2024-09-25 | 2024-10-07 | 13 | 9 | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2025-04-04 | 180 | 130 | Unknown | 2025-03-28 | Unknown | Unknown | 2025-04-04 | 2025-05-09 | 1900-02-04 | 26 | 2025-05-09 | 2025-05-09 | 1 | 1 | 252 | 182 | 50 | 36 | 302 | 218 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-30 | -367 | -262 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-18 | 2023-10-18 | 2024-03-20 | IOU Designed & Installed | N/A | No | N/A | -416.64 | -16.6 | Unknown | Unknown | -703.59 | 303.55 | 3981 | 724.08 | -416.64 | 1140.72 | Yes | N/A | N/A | 2023-10-18 | 2023-12-05 | 49 | 35 | 2023-12-05 | 2023-12-05 | 1 | 1 | 2023-12-05 | 2024-02-21 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | 2024-03-20 | 35 | 25 | Unknown | 2025-03-05 | Unknown | Unknown | 2024-03-20 | 2024-03-28 | 1900-01-08 | 7 | 2024-03-28 | 2024-03-28 | 1 | 1 | 163 | 117 | 11 | 9 | 174 | 126 | Steps 2,3,5,6,7 | 350 | 250 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 146.05 | 146.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | 448 | 321 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-14 | 2023-11-08 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 929.12 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-14 | 2023-11-08 | 209 | 149 | 2023-11-08 | 2023-11-08 | 1 | 1 | 2023-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2025-06-23 | 594 | 424 | Unknown | 2025-06-20 | Unknown | Unknown | 2025-06-23 | 2025-06-23 | 1899-12-31 | 1 | 2025-06-23 | 2025-06-23 | 1 | 1 | 803 | 573 | 3 | 3 | 806 | 576 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 40.15 | 40.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-19 | -597 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-04-05 | 2024-04-10 | IOU Designed & Installed | N/A | No | N/A | 346.1 | -12.1 | Unknown | Unknown | Unknown | 358.2 | Unknown | 1047.88 | 346.1 | 701.78 | Yes | N/A | N/A | 2024-03-07 | 2024-01-19 | Unknown | Unknown | 2024-01-19 | 2024-04-05 | 78 | 56 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-04-10 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-05-01 | 1900-01-21 | 16 | 2024-05-01 | 2024-05-01 | 1 | 1 | 6 | 4 | 101 | 73 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-23 | 36 | 26 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 3510.66 | 443.9 | Unknown | 66.43 | -3862.14 | 6862.47 | 100092 | 4611.21 | 3510.66 | 1100.55 | Yes | N/A | N/A | 2023-03-07 | 2023-06-20 | 106 | 76 | 2023-06-20 | 2023-08-16 | 58 | 42 | 2024-01-31 | 2024-02-01 | 2 | 2 | 2024-02-01 | 2024-02-23 | 23 | 17 | 2023-08-16 | 2024-03-18 | 216 | 154 | 2024-03-27 | 2024-03-21 | Unknown | Unknown | Unknown | 2024-04-01 | Unknown | Unknown | 2024-04-01 | 2024-03-30 | Unknown | Unknown | 324 | 232 | 81 | 59 | 405 | 291 | Steps 2,3,5,6,7 | 191 | 137 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-09 | -590 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-18 | 2025-02-27 | IOU Designed & Installed | N/A | No | N/A | 12.52 | Unknown | Unknown | Unknown | Unknown | 12.52 | 3981 | 1743.54 | 12.52 | 1731.02 | Yes | N/A | N/A | 2024-12-17 | 2024-12-17 | 1 | 1 | 2024-12-17 | 2024-12-17 | 1 | 1 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-02-27 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-04-28 | 1900-03-01 | 43 | 2025-04-28 | 2025-04-28 | 1 | 1 | 73 | 53 | 63 | 45 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-21 | -594 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-04 | 2023-12-01 | IOU Designed & Installed | N/A | No | N/A | 374.06 | -3.13 | Unknown | Unknown | Unknown | 377.19 | Unknown | 275.02 | 374.06 | -99.04 | Yes | N/A | N/A | 2023-10-04 | 2023-08-01 | Unknown | Unknown | 2023-08-01 | 2023-11-10 | 102 | 74 | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2023-12-01 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2023-12-05 | 1900-01-04 | 3 | 2023-12-05 | 2023-12-05 | 1 | 1 | 22 | 16 | 108 | 78 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | -599 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-11 | 2024-06-25 | IOU Designed & Installed | N/A | No | N/A | 14.92 | -11.53 | Unknown | Unknown | Unknown | 26.45 | 3981 | 1178.04 | 14.92 | 1163.12 | Yes | N/A | N/A | 2024-04-03 | 2024-03-08 | Unknown | Unknown | 2024-03-08 | 2024-04-11 | 35 | 25 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-06-25 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-10 | 1900-01-15 | 12 | 2024-07-10 | 2024-07-09 | Unknown | Unknown | 76 | 54 | 51 | 37 | 127 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-06 | -485 | -348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-02-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.59 | -4.91 | Unknown | Unknown | Unknown | -0.68 | 3981 | 98.41 | -5.59 | 104 | Yes | N/A | N/A | 2023-02-27 | 2023-03-10 | 12 | 10 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-08-09 | 1 | 1 | 12 | 10 | 1 | 1 | 13 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 135.05 | 135.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-28 | 73 | 54 | No | 2023-02-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-02-06 | Unknown | IOU Designed & Installed | N/A | Yes | 78 | -3.2 | -9.35 | Unknown | Unknown | Unknown | 6.15 | 3981 | 771.43 | -3.2 | 774.63 | Yes | N/A | N/A | 2023-02-06 | 2023-04-25 | 79 | 57 | 2023-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | Unknown | Unknown | 2023-08-10 | 2023-05-12 | Unknown | Unknown | 79 | 57 | 0 | 0 | 79 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-16 | -217 | -156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | 2023-11-15 | IOU Designed & Installed | N/A | No | N/A | -9.63 | -10.21 | Unknown | Unknown | Unknown | 0.58 | Unknown | 158.14 | -9.63 | 167.77 | Yes | N/A | N/A | 2023-11-01 | 2023-11-13 | 13 | 9 | 2023-11-13 | 2023-11-13 | 1 | 1 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2023-11-15 | 3 | 3 | Unknown | 2024-01-04 | Unknown | Unknown | 2023-11-15 | 2024-01-12 | 1900-02-27 | 43 | 2024-01-12 | 2024-01-12 | 1 | 1 | 16 | 12 | 61 | 45 | 77 | 57 | Steps 2,3,5,6,7 | 50 | 36 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-03 | -262 | -189 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-05 | 2024-04-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | -687.08 | 624.72 | Unknown | 17.22 | -1602 | 272.98 | Unknown | 1602.06 | -687.08 | 2289.14 | Yes | N/A | N/A | 2024-04-05 | 2024-04-05 | 1 | 1 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-07 | 13 | 10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-07 | 2023-12-20 | IOU Designed & Installed | N/A | No | N/A | -1144.7 | -3.9 | Unknown | Unknown | -1145 | 4.2 | 3981 | 1664.95 | -1144.7 | 2809.65 | Yes | N/A | N/A | 2023-11-07 | 2023-11-10 | 4 | 4 | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2023-12-20 | 41 | 29 | Unknown | 2023-12-06 | Unknown | Unknown | 2023-12-20 | 2023-12-20 | 1899-12-31 | 1 | 2023-12-20 | 2023-12-20 | 1 | 1 | 45 | 33 | 2 | 2 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-12 | -591 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-08-12 | 2024-08-19 | IOU Designed & Installed | N/A | No | N/A | 28.28 | Unknown | Unknown | Unknown | Unknown | 28.28 | Unknown | 1730.42 | 28.28 | 1702.14 | Yes | N/A | N/A | 2024-07-16 | 2024-08-06 | 22 | 16 | 2024-08-06 | 2024-08-12 | 7 | 5 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-08-19 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-08-29 | 1900-01-10 | 9 | 2024-08-29 | 2024-08-29 | 1 | 1 | 30 | 22 | 19 | 15 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 125 | 125 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-03-29 | 377 | 270 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-19 | 2023-02-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 941.55 | -8.55 | Unknown | Unknown | Unknown | 950.1 | 3885 | 478.83 | 941.55 | -462.72 | Yes | N/A | N/A | 2021-05-19 | 2023-02-09 | 632 | 452 | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-04-10 | Unknown | Unknown | 632 | 452 | 0 | 0 | 632 | 452 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-31 | 180 | 129 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-19 | 2023-07-17 | 2024-02-02 | IOU Designed & Installed | N/A | No | N/A | 4573.51 | 584.37 | Unknown | 808.53 | 14.15 | 3166.46 | 3981 | 723.61 | 4573.51 | -3849.9 | Yes | N/A | N/A | 2022-12-19 | 2023-07-21 | 215 | 155 | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | 2024-02-02 | 197 | 141 | Unknown | 2024-02-01 | Unknown | Unknown | 2024-02-02 | 2024-02-22 | 1900-01-20 | 15 | 2024-02-22 | 2024-02-27 | 6 | 4 | 412 | 296 | 27 | 19 | 439 | 315 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-25 | -322 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-04 | 2023-08-04 | 2023-09-06 | IOU Designed & Installed | N/A | No | N/A | 8.6 | -9.07 | Unknown | Unknown | 13.24 | 4.43 | 3981 | 503.55 | 8.6 | 494.95 | Yes | N/A | N/A | 2023-08-04 | 2023-07-25 | Unknown | Unknown | 2023-07-25 | 2023-08-04 | 11 | 9 | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | 2023-09-06 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | 2024-01-24 | 1900-05-20 | 101 | 2024-01-24 | 2023-09-07 | Unknown | Unknown | 34 | 24 | 152 | 110 | 186 | 134 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-08 | -628 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | 2024-05-02 | IOU Designed & Installed | N/A | No | N/A | 300.22 | -11.36 | Unknown | Unknown | Unknown | 311.58 | Unknown | 783.95 | 300.22 | 483.73 | Yes | N/A | N/A | 2024-03-11 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-03-28 | 45 | 33 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-05-02 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-05-21 | 1900-01-19 | 14 | 2024-05-21 | 2024-05-21 | 1 | 1 | 36 | 26 | 66 | 48 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-21 | 2023-07-20 | IOU Designed & Installed | N/A | No | N/A | 80.46 | -9.21 | Unknown | Unknown | Unknown | 89.67 | Unknown | 495.75 | 80.46 | 415.29 | Yes | N/A | N/A | 2023-06-21 | 2023-06-21 | 1 | 1 | 2023-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | 2023-07-20 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-07-20 | 1899-12-31 | 1 | 2023-07-20 | 2023-07-20 | 1 | 1 | 31 | 23 | 2 | 2 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | -469 | -336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-10 | 2023-11-10 | 2024-03-21 | IOU Designed & Installed | N/A | No | N/A | 817.5 | 252.46 | Unknown | 36.6 | Unknown | 528.44 | 3885 | 835.97 | 817.5 | 18.47 | Yes | N/A | N/A | 2023-11-10 | 2023-11-10 | 1 | 1 | 2023-11-10 | 2023-11-10 | 1 | 1 | 2023-11-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2024-03-21 | 133 | 95 | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-03-29 | 1900-01-08 | 7 | 2024-03-29 | 2024-03-29 | 1 | 1 | 134 | 96 | 11 | 9 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | -461 | -330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | 2024-07-08 | IOU Designed & Installed | N/A | No | N/A | 1054.99 | -3.08 | Unknown | Unknown | 28.38 | 1029.69 | 3981 | 501.62 | 1054.99 | -553.37 | Yes | N/A | N/A | 2024-01-24 | 2023-11-07 | Unknown | Unknown | 2023-11-07 | 2024-02-02 | 88 | 64 | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-07-08 | 158 | 112 | Unknown | 2024-05-29 | Unknown | Unknown | 2024-07-08 | 2024-07-15 | 1900-01-07 | 6 | 2024-07-15 | 2024-07-12 | Unknown | Unknown | 158 | 112 | 96 | 70 | 254 | 182 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-06 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-04-01 | 2024-04-08 | IOU Designed & Installed | N/A | No | N/A | 12.76 | -11.3 | Unknown | Unknown | Unknown | 24.06 | Unknown | 1049.39 | 12.76 | 1036.63 | Yes | N/A | N/A | 2024-03-20 | 2024-04-01 | 13 | 9 | 2024-04-01 | 2024-04-01 | 1 | 1 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-04-08 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | 2024-05-01 | 1900-01-23 | 18 | 2024-05-01 | 2024-05-01 | 1 | 1 | 21 | 15 | 26 | 20 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | 504 | 504 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | -212 | -152 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-06-27 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 2905.32 | 718.26 | Unknown | 212.58 | Unknown | 1974.48 | Unknown | 1659.99 | 2905.32 | -1245.33 | Yes | N/A | N/A | 2024-06-21 | 2024-06-27 | 7 | 5 | 2024-06-27 | 2024-09-12 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-10-31 | 1900-01-03 | 4 | 2024-10-31 | 2024-10-31 | 1 | 1 | 7 | 5 | 83 | 61 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-06 | -199 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-21 | 2024-07-17 | IOU Designed & Installed | N/A | No | N/A | -867.95 | 2417.25 | Unknown | 292.49 | -4660 | 1082.31 | Unknown | 4659.95 | -867.95 | 5527.9 | Yes | N/A | N/A | 2024-06-18 | 2024-06-21 | 4 | 4 | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-11-19 | 1900-05-05 | 90 | 2024-11-19 | 2024-11-19 | 1 | 1 | 4 | 4 | 127 | 91 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community,Tribal Community | ALPINE | COUNTY OF SAN DIEGO-SOUTH of 56 | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-31 | -9 | -6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | 2024-03-19 | IOU Designed & Installed | N/A | No | N/A | 52703.58 | 3184.06 | Unknown | 5547.36 | 690.71 | 43281.45 | 7285.98 | 12771.1 | 52703.58 | -39932.48 | Yes | N/A | N/A | 2023-08-08 | 2023-10-24 | 78 | 56 | 2023-10-24 | 2024-01-03 | 72 | 52 | 2023-11-15 | 2025-02-27 | 3 | 3 | 2023-12-12 | 2024-01-12 | 13 | 11 | 2024-01-03 | 2023-11-13 | Unknown | Unknown | 2024-01-16 | 2024-02-12 | 28 | 20 | 2024-03-19 | 2024-03-22 | 1900-01-03 | 4 | 2024-03-22 | 2024-03-22 | 1 | 1 | 81 | 59 | 118 | 88 | 199 | 147 | Steps 2,3,5,6,7 | 501 | 359 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 203.15 | 203.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-30 | -70 | -51 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4094.68 | 873.41 | Unknown | 568.95 | 123.07 | 2529.25 | 3981 | 1123.38 | 4094.68 | -2971.3 | Yes | N/A | N/A | 2023-12-05 | 2023-12-01 | Unknown | Unknown | 2023-12-01 | 2024-01-05 | 36 | 26 | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-08-21 | 1 | 1 | 0 | 0 | 37 | 27 | 37 | 27 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Commercial | N/A | RANCHO SANTA FE | N/A | 136 | 136 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-18 | 215 | 154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-04-02 | 2025-04-11 | IOU Designed & Installed | N/A | No | N/A | 110712.08 | 28091.02 | Unknown | Unknown | -9471.13 | 92092.19 | 183807 | 60304.8 | 110712.08 | -50407.28 | Yes | N/A | N/A | 2024-02-01 | 2024-02-07 | 7 | 5 | 2024-02-07 | 2025-03-14 | 402 | 288 | 2024-06-24 | 2024-10-16 | 115 | 83 | 2025-03-07 | 2025-04-07 | 30 | 22 | 2025-03-14 | 2025-04-08 | 26 | 18 | 2025-03-28 | 2025-04-11 | 15 | 11 | 2025-04-11 | 2025-05-06 | 1900-01-25 | 18 | 2025-05-06 | 2025-04-21 | Unknown | Unknown | 148 | 106 | 473 | 339 | 621 | 445 | Steps 2,3,5,6,7 | 298 | 212 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-08 | -273 | -196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.19 | -9.52 | Unknown | Unknown | Unknown | 6.33 | 2000 | 811.06 | -3.19 | 814.25 | Yes | N/A | N/A | 2023-03-22 | 2023-03-22 | 1 | 1 | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | 2023-05-25 | Unknown | Unknown | Unknown | 2023-06-09 | Unknown | Unknown | 2023-06-09 | 2023-06-09 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-31 | -126 | -91 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1142.43 | -20.79 | Unknown | Unknown | 26.36 | 1136.86 | 3981 | 1398.56 | 1142.43 | 256.13 | Yes | N/A | N/A | 2023-09-18 | 2023-10-09 | 22 | 16 | 2023-10-09 | 2023-10-10 | 2 | 2 | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | 2025-03-28 | 2025-03-27 | Unknown | Unknown | 22 | 16 | 2 | 2 | 24 | 18 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | 454 | 325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 604.19 | -20.79 | Unknown | Unknown | Unknown | 624.98 | Unknown | 1759.23 | 604.19 | 1155.04 | Yes | N/A | N/A | 2024-01-22 | 2024-01-22 | 1 | 1 | 2024-01-22 | 2024-03-22 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2024-04-09 | 19 | 13 | Unknown | 2024-04-24 | Unknown | Unknown | Unknown | 2024-05-02 | Unknown | Unknown | 2024-05-02 | 2024-04-30 | Unknown | Unknown | 20 | 14 | 61 | 45 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-15 | 790 | 565 | No | 2021-10-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-31 | 2021-10-31 | 2024-11-06 | IOU Designed & Installed | N/A | Yes | 954 | 3.05 | Unknown | Unknown | Unknown | Unknown | 3.05 | Unknown | 1724.57 | 3.05 | 1721.52 | Yes | N/A | N/A | 2021-10-31 | 2024-06-11 | 955 | 682 | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-10-31 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-11-13 | 1900-01-07 | 6 | 2024-11-13 | 2024-11-13 | 1 | 1 | 955 | 682 | 9 | 7 | 964 | 689 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | DEL MAR | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-03 | -573 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-11 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 13822.78 | 990.95 | Unknown | Unknown | 81.82 | 12750.01 | 3981 | 1501.3 | 13822.78 | -12321.48 | Yes | N/A | N/A | 2024-04-10 | 2024-05-08 | 29 | 21 | 2024-05-08 | 2024-05-28 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-07-12 | 31 | 23 | 2024-05-28 | 2024-06-20 | 24 | 18 | Unknown | 2024-07-03 | Unknown | Unknown | 2024-07-30 | 2024-09-03 | 1900-02-04 | 26 | 2024-09-03 | 2024-08-07 | Unknown | Unknown | 53 | 39 | 88 | 64 | 141 | 103 | Steps 2,3,5,6,7 | 45 | 33 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-13 | -190 | -137 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-25 | 2024-04-19 | IOU Designed & Installed | N/A | No | N/A | 344.12 | -10.36 | Unknown | Unknown | Unknown | 354.48 | Unknown | 913.07 | 344.12 | 568.95 | Yes | N/A | N/A | 2024-03-25 | 2024-03-13 | Unknown | Unknown | 2024-03-13 | 2024-03-25 | 13 | 9 | 2024-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-04-19 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2024-05-07 | 1900-01-18 | 13 | 2024-05-07 | 2024-05-07 | 1 | 1 | 26 | 20 | 33 | 23 | 59 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-23 | -655 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 444.54 | Unknown | Unknown | Unknown | 1.84 | 442.7 | 3981 | 2926.44 | 444.54 | 2481.9 | Yes | N/A | N/A | 2025-02-19 | 2025-02-24 | 6 | 4 | 2025-02-24 | 2025-02-26 | 3 | 3 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | 2025-04-08 | 2025-04-08 | 1 | 1 | 6 | 4 | 4 | 4 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-23 | -680 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-08 | 2025-03-08 | 2025-03-20 | IOU Designed & Installed | N/A | No | N/A | 35.81 | Unknown | Unknown | Unknown | Unknown | 35.81 | 3981 | 2192.49 | 35.81 | 2156.68 | Yes | N/A | N/A | 2025-03-08 | 2025-03-02 | Unknown | Unknown | 2025-03-02 | 2025-03-10 | 9 | 6 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-08 | 2025-03-20 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-04-14 | 1900-01-25 | 18 | 2025-04-14 | 2025-04-14 | 1 | 1 | 13 | 9 | 36 | 25 | 49 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 56 | 56 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-11 | 11 | 8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | 2024-05-22 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2263.59 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-20 | 2024-05-20 | 1 | 1 | 2024-05-20 | 2024-05-20 | 1 | 1 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-05-22 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-05-22 | 1899-12-31 | 1 | 2024-05-22 | 2024-05-22 | 1 | 1 | 4 | 4 | 3 | 3 | 7 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-12 | -705 | -504 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-23 | 2024-08-23 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 106.67 | -1.5 | Unknown | Unknown | Unknown | 108.17 | 3981 | 1388.72 | 106.67 | 1282.05 | Yes | N/A | N/A | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | 2024-08-23 | 1 | 1 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-08-26 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-09-06 | 1900-01-11 | 10 | 2024-09-06 | 2024-09-06 | 1 | 1 | 5 | 3 | 14 | 12 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-10 | -366 | -263 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | 2024-09-26 | IOU Designed & Installed | N/A | No | N/A | 1023.47 | 182.98 | Unknown | Unknown | Unknown | 840.49 | 3921 | 982.78 | 1023.47 | -40.69 | Yes | N/A | N/A | 2024-03-28 | 2023-11-10 | Unknown | Unknown | 2023-11-10 | 2024-03-28 | 140 | 100 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-09-26 | 183 | 131 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-10-10 | 1900-01-14 | 11 | 2024-10-10 | 2024-10-09 | Unknown | Unknown | 183 | 131 | 155 | 111 | 338 | 242 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | Chula Vista | CHULA VISTA | 596 | 596 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-14 | 388 | 278 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-22 | 2022-12-22 | 2024-11-12 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 193343.02 | 49316.38 | Unknown | 123.85 | 4620.45 | 139282.34 | 235494.84 | 91695.65 | 193343.02 | -101647.37 | Yes | N/A | N/A | 2022-12-22 | 2023-08-14 | 236 | 168 | 2023-08-14 | 2024-01-22 | 162 | 116 | 2023-08-29 | 2023-12-11 | 105 | 75 | 2023-02-03 | 2025-07-30 | 445 | 319 | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-10-30 | 115 | 83 | 2024-11-12 | 2025-05-07 | 1900-06-25 | 127 | 2025-05-07 | 2025-05-07 | 1 | 1 | 341 | 243 | 900 | 646 | 1241 | 889 | Steps 2,3,5,6,7 | 457 | 325 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 689.15 | 689.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -472 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-06-04 | 2024-07-22 | IOU Designed & Installed | N/A | No | N/A | 6953.2 | Unknown | Unknown | Unknown | Unknown | 6953.2 | 0 | 3722.84 | 6953.2 | -3230.36 | Yes | N/A | N/A | 2023-05-10 | 2023-06-07 | 29 | 21 | 2023-06-07 | 2023-06-21 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-08-15 | 1900-01-24 | 19 | 2024-08-15 | 2024-08-15 | 1 | 1 | 29 | 21 | 41 | 31 | 70 | 52 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-22 | -31 | -24 | No | 2023-12-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | 2024-06-25 | IOU Designed & Installed | N/A | Yes | 128 | 1749.73 | -6.04 | Unknown | Unknown | 64.07 | 1691.7 | Unknown | 925.79 | 1749.73 | -823.94 | Yes | N/A | N/A | 2023-12-18 | 2024-04-18 | 123 | 89 | 2024-04-18 | 2024-02-07 | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-06-25 | 140 | 100 | Unknown | 2024-06-14 | Unknown | Unknown | 2024-06-25 | 2024-07-22 | 1900-01-27 | 20 | 2024-07-22 | 2024-07-22 | 1 | 1 | 263 | 189 | 29 | 21 | 292 | 210 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | -493 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-19 | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 2551.88 | 722.3 | Unknown | Unknown | Unknown | 1829.58 | 3981 | 1048.85 | 2551.88 | -1503.03 | Yes | N/A | N/A | 2024-03-13 | 2024-01-18 | Unknown | Unknown | 2024-01-18 | 2024-04-11 | 85 | 61 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-08-14 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-09-03 | 1900-01-20 | 15 | 2024-09-03 | 2024-09-03 | 1 | 1 | 126 | 90 | 107 | 77 | 233 | 167 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 17.05 | 17.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -448 | -321 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-09-18 | 2025-05-05 | IOU Designed & Installed | N/A | No | N/A | 5262.27 | 748.44 | Unknown | Unknown | 75.33 | 4438.5 | 3981 | 1435.83 | 5262.27 | -3826.44 | Yes | N/A | N/A | 2024-09-17 | 2024-11-25 | 70 | 50 | 2024-11-25 | 2024-11-26 | 2 | 2 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-05-05 | 161 | 115 | Unknown | 2025-05-02 | Unknown | Unknown | 2025-05-05 | 2025-05-14 | 1900-01-09 | 8 | 2025-05-14 | 2025-05-14 | 1 | 1 | 231 | 165 | 13 | 11 | 244 | 176 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 137.05 | 137.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | -67 | -48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-01 | 2025-05-22 | IOU Designed & Installed | N/A | No | N/A | 6395.49 | 613.12 | Unknown | Unknown | -889.5 | 6671.87 | Unknown | 5942.26 | 6395.49 | -453.23 | Yes | N/A | N/A | 2024-11-01 | 2024-10-17 | Unknown | Unknown | 2024-10-17 | 2024-11-04 | 19 | 13 | 2024-11-04 | 2025-01-08 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-05-22 | 135 | 97 | Unknown | 2025-05-19 | Unknown | Unknown | 2025-05-22 | 2025-06-04 | 1900-01-13 | 10 | 2025-06-04 | 2025-06-04 | 1 | 1 | 201 | 145 | 34 | 24 | 235 | 169 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | -592 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-07-15 | IOU Designed & Installed | N/A | No | N/A | 1881.73 | 630.25 | Unknown | 178.72 | Unknown | 1072.76 | 3981 | 761.75 | 1881.73 | -1119.98 | Yes | N/A | N/A | 2023-03-20 | 2023-04-04 | 16 | 12 | 2023-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-04 | 2023-07-15 | 103 | 74 | Unknown | Unknown | Unknown | Unknown | 2023-07-15 | 2023-07-18 | 1900-01-03 | 2 | 2023-07-18 | 2023-07-18 | 1 | 1 | 119 | 86 | 5 | 3 | 124 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-21 | -498 | -356 | No | 2023-02-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-05-11 | IOU Designed & Installed | N/A | Yes | 16 | 627.9 | 229 | Unknown | Unknown | Unknown | 398.9 | Unknown | 311.78 | 627.9 | -316.12 | Yes | N/A | N/A | 2023-02-08 | 2023-02-24 | 17 | 13 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | 2023-05-11 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2023-05-11 | 2023-05-12 | 1900-01-01 | 2 | 2023-05-12 | 2023-05-12 | 1 | 1 | 110 | 80 | 3 | 3 | 113 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | PAUMA VALLEY | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | 44 | 33 | No | 2023-04-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-04-26 | 2023-12-11 | IOU Designed & Installed | N/A | Yes | 203 | 2058.1 | -48.48 | Unknown | Unknown | 24.57 | 2082.01 | 3981 | 788.88 | 2058.1 | -1269.22 | Yes | N/A | N/A | 2023-04-26 | 2023-10-26 | 184 | 132 | 2023-10-26 | 2023-11-15 | 21 | 15 | 2023-10-19 | 2023-10-19 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2023-12-11 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2023-12-15 | 1900-01-04 | 5 | 2023-12-15 | 2023-12-15 | 1 | 1 | 211 | 151 | 27 | 21 | 238 | 172 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-04 | -142 | -103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 487.58 | 906.94 | Unknown | Unknown | -832 | 412.64 | Unknown | 831.57 | 487.58 | 343.99 | Yes | N/A | N/A | 2023-10-12 | 2023-10-11 | Unknown | Unknown | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-25 | -526 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-05 | 2023-05-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | -19.48 | -14.11 | Unknown | Unknown | Unknown | -5.37 | Unknown | 495.75 | -19.48 | 515.23 | Yes | N/A | N/A | 2023-05-05 | 2023-05-05 | 1 | 1 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-04 | -425 | -304 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 680.85 | -39.62 | Unknown | Unknown | Unknown | 720.47 | 11943 | 955.79 | 680.85 | 274.94 | Yes | N/A | N/A | 2024-03-19 | 2024-03-19 | 1 | 1 | 2024-03-19 | 2024-04-18 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-03-29 | 10 | 8 | 2024-04-18 | 2024-05-07 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | Unknown | Unknown | 2024-06-05 | 2024-06-05 | 1 | 1 | 21 | 15 | 42 | 32 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 50.05 | 50.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-14 | -183 | -132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-10 | 2024-05-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 795.53 | 180.1 | Unknown | 204.1 | 13.21 | 398.12 | 3981 | 1236.06 | 795.53 | 440.53 | Yes | N/A | N/A | 2024-05-10 | 2024-05-22 | 13 | 9 | 2024-05-22 | 2024-05-22 | 1 | 1 | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | 2024-09-12 | Unknown | Unknown | 2024-09-12 | 2024-09-12 | 1 | 1 | 13 | 9 | 2 | 2 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | National City | NATIONAL CITY | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-29 | 221 | 158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-25 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 24379.16 | 1718.96 | Unknown | Unknown | 33.23 | 22626.97 | Unknown | 18371.35 | 24379.16 | -6007.81 | Yes | N/A | N/A | 2024-03-25 | 2024-03-25 | 1 | 1 | 2024-03-25 | Unknown | Unknown | Unknown | 2024-07-31 | 2024-08-01 | 2 | 2 | 2024-06-08 | 2024-09-11 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-11-05 | 1900-02-04 | 26 | 2024-11-05 | 2024-11-05 | 1 | 1 | 3 | 3 | 129 | 93 | 132 | 96 | Steps 2,3,5,6,7 | 54 | 38 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | 49 | 49 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-06 | -577 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-02 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | 656.21 | -12.92 | Unknown | Unknown | Unknown | 669.13 | 3981 | 949.27 | 656.21 | 293.06 | Yes | N/A | N/A | 2024-05-02 | 2024-03-13 | Unknown | Unknown | 2024-03-13 | 2024-05-02 | 51 | 37 | 2024-05-02 | Unknown | Unknown | Unknown | 2024-05-03 | 2024-05-31 | 29 | 21 | 2024-05-02 | 2024-07-16 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-08-06 | 1900-01-21 | 16 | 2024-08-06 | 2024-08-06 | 1 | 1 | 76 | 54 | 103 | 75 | 179 | 129 | Steps 2,3,5,6,7 | 29 | 21 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-12 | -472 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-30 | 2024-06-20 | IOU Designed & Installed | N/A | No | N/A | 114.18 | -12.48 | Unknown | Unknown | Unknown | 126.66 | 3981 | 816.85 | 114.18 | 702.67 | Yes | N/A | N/A | 2024-01-04 | 2024-01-30 | 27 | 19 | 2024-01-30 | 2024-01-30 | 1 | 1 | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-06-20 | 143 | 103 | Unknown | 2024-05-29 | Unknown | Unknown | 2024-06-20 | 2024-06-27 | 1900-01-07 | 6 | 2024-06-27 | 2024-06-27 | 1 | 1 | 170 | 122 | 10 | 8 | 180 | 130 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 613 | 438 | No | 2022-12-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-09 | 2022-12-09 | 2025-01-31 | IOU Designed & Installed | N/A | Yes | 521 | 3560.88 | 698.6 | Unknown | 247.83 | Unknown | 2614.45 | 3981 | 1301.05 | 3560.88 | -2259.83 | Yes | N/A | N/A | 2022-12-09 | 2024-05-08 | 517 | 369 | 2024-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-12-09 | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-01-31 | 1899-12-31 | 1 | 2025-01-31 | 2025-02-03 | 4 | 2 | 517 | 369 | 5 | 3 | 522 | 372 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | 105.1 | 105.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-08 | -502 | -360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-05-08 | 2023-09-19 | IOU Designed & Installed | N/A | No | N/A | -5.85 | -11.44 | Unknown | Unknown | Unknown | 5.59 | 3981 | 646.79 | -5.85 | 652.64 | Yes | N/A | N/A | 2023-04-12 | 2023-05-08 | 27 | 19 | 2023-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | 2023-09-19 | 135 | 97 | Unknown | 2023-09-07 | Unknown | Unknown | 2023-09-19 | 2023-09-25 | 1900-01-06 | 5 | 2023-09-25 | 2023-09-25 | 1 | 1 | 162 | 116 | 8 | 6 | 170 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | -140 | -101 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-08-02 | 2024-06-18 | IOU Designed & Installed | N/A | No | N/A | 7507.09 | 317.76 | Unknown | Unknown | -1107.47 | 8296.8 | 3981 | 1889.24 | 7507.09 | -5617.85 | Yes | N/A | N/A | 2023-06-29 | 2023-06-06 | Unknown | Unknown | 2023-06-06 | 2024-01-23 | 232 | 166 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-06-10 | 140 | 100 | Unknown | 2024-05-23 | Unknown | Unknown | 2024-06-18 | 2024-09-04 | 1900-03-19 | 57 | 2024-09-04 | 2024-08-30 | Unknown | Unknown | 140 | 100 | 311 | 223 | 451 | 323 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | 104 | 75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | 2024-04-04 | IOU Designed & Installed | N/A | No | N/A | 9.28 | Unknown | Unknown | Unknown | Unknown | 9.28 | 3981 | 844.42 | 9.28 | 835.14 | Yes | N/A | N/A | 2023-11-21 | 2023-11-06 | Unknown | Unknown | 2023-11-06 | 2023-11-21 | 16 | 12 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2024-04-04 | 136 | 98 | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-11-13 | 1900-08-11 | 160 | 2024-11-13 | 2024-11-13 | 1 | 1 | 136 | 98 | 241 | 173 | 377 | 271 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 396 | 283 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -786.64 | 2147.49 | Unknown | 513.99 | -4425 | 976.88 | Unknown | 4425.1 | -786.64 | 5211.74 | Yes | N/A | N/A | 2023-08-03 | 2024-05-15 | 287 | 205 | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2024-07-23 | 1 | 1 | 287 | 205 | 1 | 1 | 288 | 206 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | -660 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | 2024-10-09 | IOU Designed & Installed | N/A | No | N/A | 475.31 | -7.6 | Unknown | Unknown | Unknown | 482.91 | Unknown | 1502.18 | 475.31 | 1026.87 | Yes | N/A | N/A | 2024-09-19 | 2024-08-22 | Unknown | Unknown | 2024-08-22 | 2024-09-19 | 29 | 21 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-10-09 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-10-17 | 1900-01-08 | 7 | 2024-10-17 | 2024-10-17 | 1 | 1 | 21 | 15 | 39 | 29 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | -276 | -198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1037.02 | -16.2 | Unknown | Unknown | Unknown | 1053.22 | 3981 | 1177.97 | 1037.02 | 140.95 | Yes | N/A | N/A | 2024-04-16 | 2024-03-05 | Unknown | Unknown | 2024-03-05 | 2024-04-16 | 43 | 31 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-05-22 | 1 | 1 | 0 | 0 | 44 | 32 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 64 | 46 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-17 | 2023-01-17 | 2023-11-27 | IOU Designed & Installed | N/A | No | N/A | 3918.58 | Unknown | Unknown | Unknown | Unknown | 3918.58 | Unknown | 2125.61 | 3918.58 | -1792.97 | Yes | N/A | N/A | 2022-11-17 | 2023-09-26 | 314 | 224 | 2023-09-26 | 2023-11-15 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2023-12-18 | 1900-01-21 | 16 | 2023-12-18 | 2023-12-18 | 1 | 1 | 314 | 224 | 74 | 54 | 388 | 278 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-20 | -317 | -228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | 2024-01-05 | IOU Designed & Installed | N/A | No | N/A | 1967.84 | 183.68 | Unknown | Unknown | 10.75 | 1773.41 | Unknown | 902.21 | 1967.84 | -1065.63 | Yes | N/A | N/A | 2023-11-21 | 2023-11-21 | 1 | 1 | 2023-11-21 | 2023-11-22 | 2 | 2 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2024-01-05 | 45 | 33 | Unknown | 2024-01-04 | Unknown | Unknown | 2024-01-05 | 2024-01-08 | 1900-01-03 | 2 | 2024-01-08 | 2024-01-08 | 1 | 1 | 46 | 34 | 7 | 5 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-24 | -495 | -355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-15 | 2024-08-15 | IOU Designed & Installed | N/A | No | N/A | 1222.22 | -24.15 | Unknown | Unknown | Unknown | 1246.37 | 3981 | 1069.95 | 1222.22 | -152.27 | Yes | N/A | N/A | 2024-03-13 | 2024-03-19 | 7 | 5 | 2024-03-19 | 2024-03-19 | 1 | 1 | 2024-03-19 | Unknown | Unknown | Unknown | 2024-03-27 | 2024-07-18 | 114 | 82 | 2024-03-19 | 2024-08-15 | 150 | 108 | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-09-16 | 1900-02-01 | 23 | 2024-09-16 | 2024-09-16 | 1 | 1 | 157 | 113 | 149 | 107 | 306 | 220 | Steps 2,3,5,6,7 | 121 | 87 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | -405 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-01-24 | 2024-08-20 | IOU Designed & Installed | N/A | No | N/A | 1096.85 | Unknown | Unknown | Unknown | 42.98 | 1053.87 | 1786.6 | 466.13 | 1096.85 | -630.72 | Yes | N/A | N/A | 2024-01-16 | 2024-02-05 | 21 | 15 | 2024-02-05 | 2024-02-05 | 1 | 1 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-08-20 | 198 | 142 | Unknown | 2024-08-16 | Unknown | Unknown | 2024-08-20 | 2024-08-30 | 1900-01-10 | 9 | 2024-08-30 | 2024-08-30 | 1 | 1 | 219 | 157 | 13 | 11 | 232 | 168 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 806.05 | 806.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | -427 | -306 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-09-19 | IOU Designed & Installed | N/A | No | N/A | -3.9 | -7.52 | Unknown | Unknown | Unknown | 3.62 | 3981 | 742.58 | -3.9 | 746.48 | Yes | N/A | N/A | 2023-03-21 | 2023-03-22 | 2 | 2 | 2023-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | 2023-09-19 | 182 | 130 | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-10-25 | 1900-02-05 | 27 | 2023-10-25 | 2023-09-29 | Unknown | Unknown | 184 | 132 | 37 | 27 | 221 | 159 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-26 | -368 | -265 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-18 | 2025-06-19 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 12481 | 510.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-08 | 2024-07-18 | 11 | 9 | 2024-07-18 | 2024-07-18 | 1 | 1 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2025-06-19 | 337 | 241 | Unknown | Unknown | Unknown | Unknown | 2025-06-19 | 2025-06-23 | 1900-01-04 | 3 | 2025-06-23 | 2025-06-23 | 1 | 1 | 348 | 250 | 7 | 5 | 355 | 255 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | -319 | -228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-28 | 2024-07-15 | IOU Designed & Installed | N/A | No | N/A | 11.43 | -8.83 | Unknown | Unknown | Unknown | 20.26 | 3981 | 752.5 | 11.43 | 741.07 | Yes | N/A | N/A | 2024-03-25 | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2024-03-28 | 109 | 79 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-07-15 | 110 | 78 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-07-18 | 1900-01-03 | 4 | 2024-07-18 | 2024-07-17 | Unknown | Unknown | 110 | 78 | 113 | 83 | 223 | 161 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | -624 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | 2024-10-22 | IOU Designed & Installed | N/A | No | N/A | 105.13 | -1.5 | Unknown | Unknown | Unknown | 106.63 | 3981 | 1377.6 | 105.13 | 1272.47 | Yes | N/A | N/A | 2024-08-29 | 2024-08-07 | Unknown | Unknown | 2024-08-07 | 2024-08-29 | 23 | 17 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-10-22 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-11-01 | 1900-01-10 | 9 | 2024-11-01 | 2024-11-05 | 5 | 3 | 55 | 39 | 39 | 29 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | -601 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-15 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 2190.64 | 232.51 | Unknown | 64.46 | Unknown | 1893.67 | 3981 | 1813.9 | 2190.64 | -376.74 | Yes | N/A | N/A | 2025-01-15 | 2025-01-10 | Unknown | Unknown | 2025-01-10 | 2025-01-16 | 7 | 5 | 2025-01-16 | Unknown | Unknown | Unknown | 2025-02-27 | 2025-03-06 | 8 | 6 | 2025-01-15 | 2025-01-27 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-04-10 | 1900-03-14 | 54 | 2025-04-10 | 2025-04-10 | 1 | 1 | 13 | 9 | 90 | 66 | 103 | 75 | Steps 2,3,5,6,7 | 50 | 36 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 101.12 | 101.12 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-21 | 280 | 200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-04-29 | 2025-04-16 | IOU Designed & Installed | N/A | No | N/A | 28804.09 | 3295.08 | Unknown | 22.84 | -15167.02 | 40653.19 | 24185.28 | 43397.74 | 28804.09 | 14593.65 | Yes | N/A | N/A | 2024-04-09 | 2024-04-09 | 1 | 1 | 2024-04-09 | 2024-08-29 | 143 | 103 | 2024-06-06 | 2024-06-28 | 2 | 2 | 2024-07-03 | 2024-08-26 | 44 | 32 | 2024-08-29 | 2025-03-18 | 202 | 144 | 2025-03-11 | 2025-04-18 | 39 | 29 | 2025-04-16 | 2025-05-05 | 1900-01-19 | 14 | 2025-05-05 | 2025-04-27 | Unknown | Unknown | 205 | 147 | 246 | 178 | 451 | 325 | Steps 2,3,5,6,7 | 93 | 67 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | ALPINE | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -508 | -363 | No | 2024-01-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-03 | 2024-06-25 | IOU Designed & Installed | N/A | Yes | 92 | -223.01 | -21.3 | Unknown | Unknown | -489.49 | 287.78 | 3981 | 1917.98 | -223.01 | 2140.99 | Yes | N/A | N/A | 2024-01-03 | 2024-04-04 | 93 | 67 | 2024-04-04 | 2024-01-11 | Unknown | Unknown | 2024-01-11 | 2024-03-19 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-06-25 | 167 | 119 | Unknown | 2024-06-25 | Unknown | Unknown | 2024-06-25 | 2024-07-11 | 1900-01-16 | 13 | 2024-07-11 | 2024-07-11 | 1 | 1 | 329 | 235 | 18 | 14 | 347 | 249 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 104 | 104 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-25 | 292 | 210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-08-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 14.31 | -12.73 | Unknown | Unknown | Unknown | 27.04 | 7962 | 1412.46 | 14.31 | 1398.15 | Yes | N/A | N/A | 2023-07-13 | 2023-08-22 | 41 | 29 | 2023-08-22 | 2023-08-31 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | 2024-03-13 | 196 | 140 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | Unknown | Unknown | 2024-04-15 | 2024-04-12 | Unknown | Unknown | 237 | 169 | 10 | 8 | 247 | 177 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-18 | 425 | 304 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-08 | 2024-03-08 | 2024-12-12 | IOU Designed & Installed | N/A | No | N/A | 11890.64 | 273.47 | Unknown | Unknown | -1075 | 12692.17 | 3981 | 2223.51 | 11890.64 | -9667.13 | Yes | N/A | N/A | 2022-11-08 | 2024-03-07 | 486 | 348 | 2024-03-07 | 2024-12-02 | 271 | 193 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2024-11-07 | Unknown | Unknown | Unknown | 2024-12-02 | Unknown | Unknown | 2024-12-12 | 2024-12-27 | 1900-01-15 | 12 | 2024-12-27 | 2024-12-16 | Unknown | Unknown | 486 | 348 | 287 | 205 | 773 | 553 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-26 | -116 | -85 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-21 | 2023-04-26 | 2023-09-15 | IOU Designed & Installed | N/A | No | N/A | 20133.46 | 2212.62 | Unknown | Unknown | 8.63 | 17912.21 | Unknown | 16434.77 | 20133.46 | -3698.69 | Yes | N/A | N/A | 2023-04-21 | 2023-04-13 | Unknown | Unknown | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-09-14 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2023-10-02 | 1900-01-17 | 12 | 2023-10-02 | 2023-10-02 | 1 | 1 | 0 | 0 | 40 | 28 | 40 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | DEL MAR | DEL MAR | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-24 | 305 | 218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-15 | 2025-03-03 | IOU Designed & Installed | N/A | No | N/A | 1252.79 | -20.79 | Unknown | Unknown | -669.09 | 1942.67 | 0 | 692.13 | 1252.79 | -560.66 | Yes | N/A | N/A | 2023-09-15 | 2023-09-18 | 4 | 2 | 2023-09-18 | 2023-10-06 | 19 | 15 | 2024-12-26 | 2025-01-30 | 36 | 26 | 2024-11-06 | 2025-02-27 | 46 | 34 | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | 2025-03-03 | 2025-03-25 | 1900-01-22 | 17 | 2025-03-25 | 2025-03-25 | 1 | 1 | 40 | 28 | 89 | 67 | 129 | 95 | Steps 2,3,5,6,7 | 595 | 425 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-09 | -640 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | 2351.15 | 404.64 | Unknown | 107.23 | Unknown | 1839.28 | 3981 | 1684.42 | 2351.15 | -666.73 | Yes | N/A | N/A | 2025-03-12 | 2025-03-17 | 6 | 4 | 2025-03-17 | 2025-03-17 | 1 | 1 | 2025-03-17 | Unknown | Unknown | Unknown | 2025-03-17 | 2025-03-31 | 15 | 11 | 2025-03-17 | 2025-03-31 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-09 | 1900-01-09 | 8 | 2025-04-09 | 2025-04-09 | 1 | 1 | 21 | 15 | 27 | 21 | 48 | 36 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-24 | -229 | -164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 156.18 | 26.05 | Unknown | Unknown | Unknown | 130.13 | 3981 | 2299.18 | 156.18 | 2143 | Yes | N/A | N/A | 2024-04-16 | 2024-03-06 | Unknown | Unknown | 2024-03-06 | 2024-05-03 | 59 | 43 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | Unknown | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2024-07-10 | 1 | 1 | 0 | 0 | 60 | 44 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 105 | 105 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-30 | 482 | 345 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-29 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1121.6 | -16.57 | Unknown | Unknown | Unknown | 1138.17 | 30092 | 3466.72 | 1121.6 | 2345.12 | Yes | N/A | N/A | 2022-06-29 | 2023-03-07 | 252 | 180 | 2023-03-07 | 2023-07-17 | 133 | 95 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | Unknown | Unknown | Unknown | 2024-04-26 | Unknown | Unknown | 2024-04-26 | 2024-04-25 | Unknown | Unknown | 252 | 180 | 133 | 95 | 385 | 275 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 184.05 | 184.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-10 | 137 | 98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-04-20 | 2023-05-22 | IOU Designed & Installed | N/A | No | N/A | 5100.4 | Unknown | Unknown | Unknown | -720 | 5820.4 | Unknown | 719.83 | 5100.4 | -4380.57 | Yes | N/A | N/A | 2023-04-20 | 2023-04-20 | 1 | 1 | 2023-04-20 | 2023-05-08 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-05-08 | 2023-05-19 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | 2023-06-27 | 1900-02-05 | 27 | 2023-06-27 | 2023-06-27 | 1 | 1 | 1 | 1 | 69 | 51 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -557 | -398 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-04-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 659.26 | -29.13 | Unknown | Unknown | Unknown | 688.39 | 3981 | 400.94 | 659.26 | -258.32 | Yes | N/A | N/A | 2024-04-09 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-04-17 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-05-22 | 1 | 1 | 0 | 0 | 16 | 12 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-22 | -605 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-16 | 2023-07-16 | 2023-08-10 | IOU Designed & Installed | N/A | No | N/A | 823.87 | 244.9 | Unknown | 117.92 | Unknown | 461.05 | 3981 | 771.22 | 823.87 | -52.65 | Yes | N/A | N/A | 2023-07-16 | 2023-07-16 | 1 | 0 | 2023-07-16 | 2023-07-18 | 3 | 2 | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-08-10 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-10-26 | 1900-03-18 | 56 | 2023-10-26 | 2023-10-26 | 1 | 1 | 25 | 18 | 82 | 59 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN YSIDRO | N/A | 361 | 361 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-22 | -428 | -307 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-01 | 2022-11-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1042.33 | -6.36 | Unknown | Unknown | -512.83 | 1561.52 | Unknown | 524.32 | 1042.33 | -518.01 | Yes | N/A | N/A | 2022-11-01 | 2023-02-01 | 93 | 67 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | Unknown | Unknown | Unknown | 2023-06-21 | Unknown | Unknown | 2023-06-21 | 2023-06-21 | 1 | 1 | 93 | 67 | 1 | 1 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | 133.05 | 133.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | -110 | -79 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2909.26 | 546.9 | Unknown | Unknown | 66.25 | 2296.11 | 3981 | 1299.41 | 2909.26 | -1609.85 | Yes | N/A | N/A | 2024-07-10 | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-07-26 | 43 | 31 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | Unknown | Unknown | Unknown | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-02-14 | 1 | 1 | 0 | 0 | 44 | 32 | 44 | 32 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 78 | 78 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-31 | -127 | -91 | No | 2023-01-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-21 | 2023-09-01 | 2024-02-13 | IOU Designed & Installed | N/A | Yes | 241 | 17356.69 | 2956.79 | Unknown | Unknown | -2047.99 | 16447.89 | 3981 | 10596.59 | 17356.69 | -6760.1 | Yes | N/A | N/A | 2023-01-21 | 2023-09-19 | 242 | 172 | 2023-09-19 | 2023-09-19 | 1 | 1 | 2023-09-19 | 2024-03-26 | 190 | 136 | 2023-10-06 | 2023-10-19 | 14 | 10 | 2023-09-01 | 2024-02-13 | 166 | 118 | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-05-01 | 1900-03-19 | 57 | 2024-05-01 | 2024-04-26 | Unknown | Unknown | 598 | 426 | 94 | 68 | 692 | 494 | Steps 2,3,5,6,7 | 220 | 156 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 100.8 | 100.8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | 323 | 232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-14 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 116301.14 | 14052.26 | Unknown | Unknown | 140.34 | 102108.54 | Unknown | 31426.67 | 116301.14 | -84874.47 | Yes | N/A | N/A | 2024-03-06 | 2024-03-06 | 1 | 1 | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-10-16 | 63 | 47 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-11-19 | 1900-01-27 | 20 | 2024-11-19 | 2024-11-19 | 1 | 1 | 1 | 1 | 92 | 68 | 93 | 69 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-13 | 124 | 89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-03-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1719.76 | 1480.57 | Unknown | 463.19 | -1000 | 776 | 0 | 1000.28 | 1719.76 | -719.48 | Yes | N/A | N/A | 2023-03-17 | 2023-04-07 | 22 | 16 | 2023-04-07 | 2023-04-13 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 22 | 16 | 8 | 6 | 30 | 22 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -100 | -72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-09-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 598.37 | -9.87 | Unknown | Unknown | Unknown | 608.24 | Unknown | 477.13 | 598.37 | -121.24 | Yes | N/A | N/A | 2024-08-29 | 2024-08-27 | Unknown | Unknown | 2024-08-27 | 2024-10-08 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2024-10-24 | 1 | 1 | 0 | 0 | 44 | 32 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | -38 | -27 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-29 | 2023-08-08 | IOU Designed & Installed | N/A | No | N/A | 2605.32 | Unknown | Unknown | Unknown | Unknown | 2605.32 | Unknown | 2053.57 | 2605.32 | -551.75 | Yes | N/A | N/A | 2023-06-29 | 2023-06-29 | 1 | 1 | 2023-06-29 | 2023-07-21 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | 2023-08-24 | 1900-01-16 | 13 | 2023-08-24 | 2023-08-24 | 1 | 1 | 1 | 1 | 41 | 31 | 42 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | POWAY | POWAY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-02 | 368 | 263 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-03-21 | 2024-05-28 | IOU Designed & Installed | N/A | No | N/A | 188.63 | -6.99 | Unknown | Unknown | -462 | 657.62 | Unknown | 403.39 | 188.63 | 214.76 | Yes | N/A | N/A | 2024-03-21 | 2024-03-21 | 1 | 1 | 2024-03-21 | 2024-05-21 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-05-21 | 16 | 12 | 2024-05-21 | 2024-05-07 | Unknown | Unknown | Unknown | 2024-05-21 | Unknown | Unknown | 2024-05-28 | 2024-06-19 | 1900-01-22 | 17 | 2024-06-19 | 2024-06-04 | Unknown | Unknown | 1 | 1 | 101 | 73 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | -487 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-11-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 887.58 | -16.48 | Unknown | Unknown | Unknown | 904.06 | 3981 | 2289.62 | 887.58 | 1402.04 | Yes | N/A | N/A | 2024-07-31 | 2024-06-25 | Unknown | Unknown | 2024-06-25 | 2024-12-12 | 171 | 123 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-12-13 | 31 | 23 | 2024-12-12 | 2025-01-13 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-01-21 | Unknown | Unknown | 33 | 23 | 202 | 146 | 235 | 169 | Steps 2,3,5,6,7 | 1 | 1 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | CORONADO | 239 | 239 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-30 | 858 | 613 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-14 | 2023-11-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1213.8 | -32.69 | Unknown | Unknown | 7.73 | 1238.76 | 7962 | 1022.03 | 1213.8 | -191.77 | Yes | N/A | N/A | 2022-04-14 | 2023-10-18 | 553 | 395 | 2023-10-18 | Unknown | Unknown | Unknown | 2023-12-29 | 2023-12-29 | 1 | 1 | 2024-02-05 | 2024-02-15 | 11 | 9 | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | Unknown | Unknown | Unknown | 2024-05-07 | Unknown | Unknown | 2024-05-07 | 2024-05-06 | Unknown | Unknown | 554 | 396 | 11 | 9 | 565 | 405 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | Both | IOU Design | Residential | N/A | Coronado | CORONADO | 1937 | 1937 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-08-13 | 285 | 205 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-28 | 2023-11-03 | 2024-04-12 | IOU Designed & Installed | N/A | No | N/A | 225047.28 | 55136.74 | Unknown | 304.68 | 60.35 | 169545.51 | 15107 | 80652.5 | 225047.28 | -144394.78 | Yes | N/A | N/A | 2023-10-28 | 2023-10-28 | 1 | 0 | 2023-10-28 | 2024-03-19 | 144 | 102 | 2024-03-13 | 2024-03-13 | 1 | 1 | 2023-12-11 | 2024-03-21 | 13 | 11 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | 2024-04-12 | 2024-05-24 | 1900-02-11 | 31 | 2024-05-24 | 2024-05-24 | 1 | 1 | 2 | 1 | 201 | 145 | 203 | 146 | Steps 2,3,5,6,7 | 101 | 73 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -285 | -204 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1210.33 | -8.23 | Unknown | Unknown | -678.01 | 1896.57 | 0 | 718.64 | 1210.33 | -491.69 | Yes | N/A | N/A | 2023-10-13 | 2023-10-13 | 1 | 1 | 2023-10-13 | 2023-12-05 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2025-02-27 | 451 | 323 | Unknown | 2025-03-05 | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-21 | Unknown | Unknown | 452 | 324 | 54 | 38 | 506 | 362 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-07 | -206 | -147 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-09-28 | 2023-11-30 | IOU Designed & Installed | N/A | No | N/A | -14.67 | -11.1 | Unknown | Unknown | Unknown | -3.57 | Unknown | 500.87 | -14.67 | 515.54 | Yes | N/A | N/A | 2023-09-28 | 2023-09-28 | 1 | 1 | 2023-09-28 | 2023-09-28 | 1 | 1 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-11-30 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2023-12-14 | 1900-01-14 | 11 | 2023-12-14 | 2023-12-14 | 1 | 1 | 65 | 47 | 17 | 13 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-15 | -134 | -97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-14 | 2023-04-14 | 2023-08-24 | IOU Designed & Installed | N/A | No | N/A | 422.09 | -19.8 | Unknown | Unknown | 17.82 | 424.07 | 3981 | 623.05 | 422.09 | 200.96 | Yes | N/A | N/A | 2023-04-14 | 2023-05-24 | 41 | 29 | 2023-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-24 | 2023-08-24 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | 2023-10-04 | 1900-02-10 | 30 | 2023-10-04 | 2023-10-04 | 1 | 1 | 134 | 96 | 43 | 31 | 177 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 73 | 73 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-16 | -213 | -154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-06 | 2023-07-18 | IOU Designed & Installed | N/A | No | N/A | 2519.33 | -66.24 | Unknown | Unknown | Unknown | 2585.57 | 3981 | 781.63 | 2519.33 | -1737.7 | Yes | N/A | N/A | 2023-04-06 | 2023-04-06 | 1 | 1 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-07-18 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-07-18 | 1899-12-31 | 1 | 2023-07-18 | 2023-07-18 | 1 | 1 | 105 | 75 | 2 | 2 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | 124 | 89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2023-12-07 | 2025-02-06 | IOU Designed & Installed | N/A | No | N/A | 259.57 | 354.64 | Unknown | 23.33 | -1156 | 1037.6 | 3941 | 1912.66 | 259.57 | 1653.09 | Yes | N/A | N/A | 2023-12-07 | 2023-10-25 | Unknown | Unknown | 2023-10-25 | 2023-12-07 | 44 | 32 | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2025-02-06 | 242 | 174 | Unknown | 2024-06-14 | Unknown | Unknown | 2025-02-06 | 2025-02-11 | 1900-01-05 | 4 | 2025-02-11 | 2025-02-11 | 1 | 1 | 242 | 174 | 51 | 37 | 293 | 211 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-17 | -616 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-02 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 1776.03 | 403.04 | Unknown | Unknown | Unknown | 1372.99 | 3981 | 960.15 | 1776.03 | -815.88 | Yes | N/A | N/A | 2025-01-02 | 2025-01-02 | 1 | 1 | 2025-01-02 | 2025-01-02 | 1 | 1 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-02-20 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-04-10 | 1900-02-18 | 36 | 2025-04-10 | 2025-04-10 | 1 | 1 | 51 | 37 | 52 | 38 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | -545 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-24 | 2024-05-24 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | 2588.12 | 631.87 | Unknown | Unknown | 5.92 | 1950.33 | 3981 | 1376.39 | 2588.12 | -1211.73 | Yes | N/A | N/A | 2024-05-24 | 2024-05-24 | 1 | 1 | 2024-05-24 | 2024-05-24 | 1 | 1 | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-07-10 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-08-16 | 1900-02-06 | 28 | 2024-08-16 | 2024-08-16 | 1 | 1 | 49 | 35 | 40 | 30 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 58878 | 58878 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-10-30 | 310 | 223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-09 | 2022-12-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3242.37 | -16.48 | Unknown | Unknown | 130.95 | 3127.9 | 27867 | 1804.31 | 3242.37 | -1438.06 | Yes | N/A | N/A | 2022-12-09 | 2023-04-03 | 116 | 82 | 2023-04-03 | 2023-06-16 | 75 | 55 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | Unknown | Unknown | Unknown | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2024-09-04 | 1 | 1 | 116 | 82 | 76 | 56 | 192 | 138 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 261 | 261 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-03 | -590 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2025-01-09 | 2025-04-18 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 2186.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-16 | 2025-01-09 | 25 | 19 | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-04-18 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-04-23 | 1900-01-05 | 4 | 2025-04-23 | 2025-04-22 | Unknown | Unknown | 125 | 91 | 7 | 5 | 132 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-25 | -584 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 375.5 | -7.34 | Unknown | Unknown | Unknown | 382.84 | 3891 | 708.98 | 375.5 | 333.48 | Yes | N/A | N/A | 2024-09-18 | 2024-09-25 | 8 | 6 | 2024-09-25 | 2024-10-10 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-10-18 | 30 | 22 | 2024-10-10 | 2024-11-27 | 49 | 35 | Unknown | 2024-12-10 | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | 2024-12-19 | 2024-12-18 | Unknown | Unknown | 57 | 41 | 46 | 34 | 103 | 75 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | LA MESA | 8610 | 8610 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-01-17 | 76 | 55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-09-04 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | -10710.07 | 191.21 | Unknown | 41.64 | -11507 | 564.08 | Unknown | 8809.91 | -10710.07 | 19519.98 | Yes | N/A | N/A | 2024-01-24 | 2024-09-04 | 225 | 161 | 2024-09-04 | 2024-10-17 | 44 | 32 | 2024-10-22 | 2025-01-29 | 100 | 72 | 2024-09-04 | 2025-02-03 | 55 | 39 | 2024-10-17 | 2025-03-11 | 146 | 104 | Unknown | 2025-02-04 | Unknown | Unknown | 2025-03-31 | 2025-04-03 | 1900-01-03 | 4 | 2025-04-03 | 2025-04-03 | 1 | 1 | 471 | 337 | 104 | 76 | 575 | 413 | Steps 2,3,5,6,7 | 256 | 182 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-11 | -562 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-07-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1573.97 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-23 | 2024-07-23 | 1 | 1 | 2024-07-23 | 2024-07-31 | 9 | 7 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | Unknown | Unknown | 2024-11-26 | 2024-11-26 | 1 | 1 | 1 | 1 | 10 | 8 | 11 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-18 | -528 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.92 | -4.43 | Unknown | Unknown | Unknown | -0.49 | Unknown | 98.41 | -4.92 | 103.33 | Yes | N/A | N/A | 2023-03-23 | 2023-03-27 | 5 | 3 | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-08-09 | 1 | 1 | 5 | 3 | 1 | 1 | 6 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 89 | 64 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-11 | 2023-08-09 | IOU Designed & Installed | N/A | No | N/A | -7.46 | -14.68 | Unknown | Unknown | Unknown | 7.22 | 3941 | 784.95 | -7.46 | 792.41 | Yes | N/A | N/A | 2023-07-11 | 2023-05-17 | Unknown | Unknown | 2023-05-17 | 2023-07-11 | 56 | 40 | 2023-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | 2023-08-09 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | 2023-08-30 | 1900-01-21 | 16 | 2023-08-30 | 2023-08-29 | Unknown | Unknown | 30 | 22 | 78 | 56 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | -58 | -43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-04-03 | 2024-10-30 | IOU Designed & Installed | N/A | No | N/A | 20.82 | Unknown | Unknown | Unknown | Unknown | 20.82 | 3981 | 791.01 | 20.82 | 770.19 | Yes | N/A | N/A | 2024-03-29 | 2024-04-03 | 6 | 4 | 2024-04-03 | 2024-04-03 | 1 | 1 | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-10-30 | 211 | 151 | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2024-11-20 | 1900-01-21 | 16 | 2024-11-20 | 2024-11-20 | 1 | 1 | 217 | 155 | 24 | 18 | 241 | 173 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 62.05 | 62.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | -579 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-07-02 | 2024-07-12 | IOU Designed & Installed | N/A | No | N/A | 0.25 | -0.18 | Unknown | Unknown | Unknown | 0.43 | Unknown | 1541.95 | 0.25 | 1541.7 | Yes | N/A | N/A | 2024-06-11 | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-07-02 | 50 | 36 | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-12 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-10-04 | 1900-03-25 | 61 | 2024-10-04 | 2024-10-04 | 1 | 1 | 11 | 9 | 136 | 98 | 147 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | 57 | 41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2024-02-07 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 7030.19 | Unknown | Unknown | Unknown | Unknown | 7030.19 | 3981 | 1375.91 | 7030.19 | -5654.28 | Yes | N/A | N/A | 2023-09-20 | 2024-09-25 | 372 | 266 | 2024-09-25 | 2024-12-03 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2024-12-17 | 15 | 11 | Unknown | 2025-02-06 | Unknown | Unknown | 2025-02-20 | 2025-04-09 | 1900-02-17 | 35 | 2025-04-09 | 2025-04-05 | Unknown | Unknown | 387 | 277 | 119 | 85 | 506 | 362 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-27 | -422 | -303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-03-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.42 | -3.94 | Unknown | Unknown | Unknown | -1.48 | Unknown | 363.72 | -5.42 | 369.14 | Yes | N/A | N/A | 2023-03-13 | 2023-03-13 | 1 | 1 | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | Unknown | Unknown | 2023-08-02 | 2023-08-02 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego PA16 PH1 | San Diego PA16 PH1 | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 399 | 286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-05-24 | 2024-04-24 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 146097.34 | 35006.24 | Unknown | 29.69 | 8728.24 | 102333.17 | 0 | 51979.45 | 146097.34 | -94117.89 | Yes | N/A | N/A | 2022-04-27 | 2023-03-14 | 322 | 230 | 2023-03-14 | 2023-09-11 | 182 | 130 | 2023-05-10 | 2024-05-01 | 220 | 156 | 2023-09-07 | 2024-05-02 | 239 | 171 | 2023-09-19 | Unknown | Unknown | Unknown | 2023-09-19 | 2024-02-20 | 155 | 111 | 2024-04-24 | 2024-04-22 | Unknown | Unknown | 2024-04-22 | 2024-04-22 | 1 | 1 | 542 | 386 | 577 | 413 | 1119 | 799 | Steps 2,3,5,6,7 | 587 | 419 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-30 | -501 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2023-12-15 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 1485.41 | -34.13 | Unknown | Unknown | Unknown | 1519.54 | Unknown | 956.9 | 1485.41 | -528.51 | Yes | N/A | N/A | 2023-12-15 | 2023-12-15 | 1 | 1 | 2023-12-15 | 2023-12-15 | 1 | 1 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2024-03-25 | 102 | 72 | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-04-16 | 1900-01-22 | 17 | 2024-04-16 | 2024-04-16 | 1 | 1 | 103 | 73 | 25 | 19 | 128 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-26 | -213 | -152 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-08-11 | 2023-10-18 | IOU Designed & Installed | N/A | No | N/A | 0.37 | -11.01 | Unknown | Unknown | Unknown | 11.38 | 3981 | 886.68 | 0.37 | 886.31 | Yes | N/A | N/A | 2023-07-14 | 2023-05-02 | Unknown | Unknown | 2023-05-02 | 2023-08-11 | 102 | 74 | 2023-08-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | 2023-10-18 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | 2023-10-30 | 1900-01-12 | 9 | 2023-10-30 | 2023-10-26 | Unknown | Unknown | 69 | 49 | 115 | 83 | 184 | 132 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-25 | -68 | -49 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-02-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -7.62 | -5.52 | Unknown | Unknown | Unknown | -2.1 | Unknown | 98.66 | -7.62 | 106.28 | Yes | N/A | N/A | 2023-01-18 | 2023-04-03 | 76 | 54 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 76 | 54 | 1 | 1 | 77 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-11 | -580 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2023-07-25 | 2023-08-28 | IOU Designed & Installed | N/A | No | N/A | -8.91 | -8.66 | Unknown | Unknown | Unknown | -0.25 | Unknown | 148.7 | -8.91 | 157.61 | Yes | N/A | N/A | 2023-07-25 | 2023-08-16 | 23 | 17 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2023-08-28 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2023-10-09 | 1900-02-11 | 31 | 2023-10-09 | 2023-10-09 | 1 | 1 | 36 | 26 | 44 | 32 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 20.05 | 20.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-12 | -515 | -368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-15 | 2024-02-20 | IOU Designed & Installed | N/A | No | N/A | -173.25 | -13.02 | Unknown | Unknown | -184 | 23.77 | Unknown | 957.31 | -173.25 | 1130.56 | Yes | N/A | N/A | 2023-11-15 | 2023-08-28 | Unknown | Unknown | 2023-08-28 | 2023-12-11 | 106 | 76 | 2023-12-11 | 2023-12-14 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-12-14 | 2024-02-20 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-03-15 | 1900-01-24 | 19 | 2024-03-15 | 2024-03-15 | 1 | 1 | 73 | 53 | 132 | 96 | 205 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Commercial | N/A | Chula Vista | N/A | 1620 | 1620 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-07-28 | 325 | 233 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-10-31 | 2025-04-30 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 577073.49 | 42417.31 | Unknown | Unknown | 2801.63 | 531854.55 | 567285.47 | 288410.31 | 577073.49 | -288663.18 | Yes | N/A | N/A | 2023-10-31 | 2024-04-17 | 170 | 122 | 2024-04-17 | 2025-03-28 | 346 | 248 | 2024-05-10 | 2025-07-22 | 94 | 66 | 2025-03-24 | 2025-04-02 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-06-18 | 1900-02-18 | 36 | 2025-06-18 | 2025-06-18 | 1 | 1 | 264 | 188 | 407 | 293 | 671 | 481 | Steps 2,3,5,6,7 | 442 | 316 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-16 | -284 | -203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-27 | 2024-04-12 | IOU Designed & Installed | N/A | No | N/A | 10.98 | -9.75 | Unknown | Unknown | Unknown | 20.73 | Unknown | 1026.98 | 10.98 | 1016 | Yes | N/A | N/A | 2024-03-27 | 2024-03-27 | 1 | 1 | 2024-03-27 | 2024-03-27 | 1 | 1 | 2024-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-04-12 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-05-09 | 1900-01-27 | 20 | 2024-05-09 | 2024-05-08 | Unknown | Unknown | 18 | 14 | 29 | 21 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-09 | -479 | -342 | No | 2023-04-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-13 | 2023-04-19 | Unknown | IOU Designed & Installed | N/A | Yes | 15 | 1005.52 | -8.71 | Unknown | Unknown | Unknown | 1014.23 | 3885 | 1028.99 | 1005.52 | 23.47 | Yes | N/A | N/A | 2023-04-13 | 2023-04-28 | 16 | 12 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 16 | 12 | 1 | 1 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -531 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-11 | 2024-10-14 | 2024-12-17 | IOU Designed & Installed | N/A | No | N/A | 668.34 | -12.92 | Unknown | Unknown | Unknown | 681.26 | 3981 | 1186.27 | 668.34 | 517.93 | Yes | N/A | N/A | 2024-10-11 | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-10-14 | 67 | 47 | 2024-10-14 | Unknown | Unknown | Unknown | 2024-10-11 | 2024-10-28 | 18 | 12 | 2024-10-14 | 2024-12-17 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-02-20 | 1900-03-06 | 48 | 2025-02-20 | 2025-02-20 | 1 | 1 | 65 | 47 | 152 | 108 | 217 | 155 | Steps 2,3,5,6,7 | 14 | 10 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 113360 | 113360 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-12-01 | 753 | 538 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1579.73 | -30.29 | Unknown | Unknown | Unknown | 1610.02 | 7962 | 555.54 | 1579.73 | -1024.19 | Yes | N/A | N/A | 2024-04-04 | 2024-04-04 | 1 | 1 | 2024-04-04 | 2024-04-30 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-04-25 | 22 | 16 | 2024-04-30 | 2024-05-03 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-26 | Unknown | Unknown | 2024-12-26 | 2024-12-23 | Unknown | Unknown | 5 | 5 | 49 | 35 | 54 | 40 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-08 | -253 | -181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-11 | 2023-08-14 | 2023-08-15 | IOU Designed & Installed | N/A | No | N/A | 249.87 | -16.32 | Unknown | Unknown | Unknown | 266.19 | 3941 | 787.28 | 249.87 | 537.41 | Yes | N/A | N/A | 2023-08-11 | 2023-06-08 | Unknown | Unknown | 2023-06-08 | 2023-08-14 | 68 | 48 | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2023-08-15 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2023-09-29 | 1900-02-14 | 34 | 2023-09-29 | 2023-09-29 | 1 | 1 | 2 | 2 | 115 | 83 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | SANTA YSABEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-23 | -272 | -195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-12-02 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | 1646.39 | 402.36 | Unknown | 222.87 | Unknown | 1021.16 | 3981 | 645.44 | 1646.39 | -1000.95 | Yes | N/A | N/A | 2023-11-08 | 2023-12-01 | 24 | 18 | 2023-12-01 | 2023-12-01 | 1 | 1 | 2023-12-01 | 2024-02-26 | 88 | 62 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-16 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-09-24 | 1900-01-08 | 7 | 2024-09-24 | 2024-09-24 | 1 | 1 | 119 | 85 | 11 | 9 | 130 | 94 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-01 | 402 | 287 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-27 | 2023-07-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 710.3 | Unknown | Unknown | Unknown | -537 | 1247.3 | 0 | 357.5 | 710.3 | -352.8 | Yes | N/A | N/A | 2023-07-27 | 2023-07-12 | Unknown | Unknown | 2023-07-12 | 2023-10-19 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2024-07-22 | 278 | 198 | Unknown | 2024-07-19 | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-08-06 | Unknown | Unknown | 278 | 198 | 100 | 72 | 378 | 270 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -175 | -126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | 2024-08-02 | IOU Designed & Installed | N/A | No | N/A | 17839.15 | 287.04 | Unknown | 163.3 | 16.23 | 17372.58 | 3981 | 969.97 | 17839.15 | -16869.18 | Yes | N/A | N/A | 2024-04-24 | 2024-05-30 | 37 | 27 | 2024-05-30 | 2024-05-30 | 1 | 1 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-08-02 | 65 | 47 | Unknown | 2024-07-25 | Unknown | Unknown | 2024-08-02 | 2024-09-06 | 1900-02-04 | 26 | 2024-09-06 | 2024-09-06 | 1 | 1 | 102 | 74 | 38 | 28 | 140 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-11 | -556 | -397 | No | 2024-11-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-15 | 2025-03-11 | IOU Designed & Installed | N/A | Yes | 79 | 662.81 | -21.9 | Unknown | Unknown | 1.65 | 683.06 | Unknown | 2489.84 | 662.81 | 1827.03 | Yes | N/A | N/A | 2024-11-04 | 2025-01-22 | 80 | 58 | 2025-01-22 | 2024-11-15 | Unknown | Unknown | 2024-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2025-03-11 | 117 | 83 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-04-03 | 1900-01-23 | 18 | 2025-04-03 | 2025-04-03 | 1 | 1 | 197 | 141 | 25 | 19 | 222 | 160 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | JAMUL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-07 | -158 | -115 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-14 | 2025-05-30 | IOU Designed & Installed | N/A | No | N/A | 281.19 | -5.65 | Unknown | Unknown | Unknown | 286.84 | 4167 | 259.56 | 281.19 | -21.63 | Yes | N/A | N/A | 2025-03-14 | 2025-04-09 | 27 | 19 | 2025-04-09 | 2025-05-16 | 38 | 28 | 2025-03-28 | 2025-04-23 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-02 | 1900-01-03 | 2 | 2025-06-02 | 2025-06-02 | 1 | 1 | 54 | 38 | 43 | 31 | 97 | 69 | Steps 2,3,5,6,7 | 49 | 35 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-30 | -75 | -54 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6.7 | Unknown | Unknown | Unknown | Unknown | 6.7 | 3981 | 158.79 | 6.7 | 152.09 | Yes | N/A | N/A | 2023-12-06 | 2023-11-15 | Unknown | Unknown | 2023-11-15 | 2023-12-15 | 31 | 23 | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | 2024-08-16 | 2024-08-16 | 1 | 1 | 0 | 0 | 32 | 24 | 32 | 24 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-05 | -704 | -503 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-11 | 2025-04-11 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | 72.71 | -1.5 | Unknown | Unknown | Unknown | 74.21 | 3981 | 1555.69 | 72.71 | 1482.98 | Yes | N/A | N/A | 2025-04-11 | 2025-04-11 | 1 | 1 | 2025-04-11 | 2025-04-11 | 1 | 1 | 2025-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-04-25 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-01 | 1900-01-06 | 5 | 2025-05-01 | 2025-05-01 | 1 | 1 | 16 | 12 | 9 | 7 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | 8094 | 8094 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-12-01 | 524 | 375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-03 | 2024-04-23 | IOU Designed & Installed | N/A | No | N/A | 16720.75 | 1421.14 | Unknown | 4.99 | 5.5 | 15289.12 | 73012 | 10229.28 | 16720.75 | -6491.47 | Yes | N/A | N/A | 2023-02-02 | 2023-02-03 | 2 | 2 | 2023-02-03 | 2023-03-07 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | 2024-04-16 | 407 | 291 | Unknown | 2024-04-22 | Unknown | Unknown | 2024-04-23 | 2024-05-09 | 1900-01-16 | 13 | 2024-05-09 | 2024-05-08 | Unknown | Unknown | 409 | 293 | 50 | 36 | 459 | 329 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-15 | -507 | -362 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-01 | 2023-10-01 | 2024-01-19 | IOU Designed & Installed | N/A | No | N/A | 2577.97 | 979.6 | Unknown | 942 | -1465 | 2121.37 | 3981 | 2167.14 | 2577.97 | -410.83 | Yes | N/A | N/A | 2023-10-01 | 2023-10-10 | 10 | 7 | 2023-10-10 | 2023-10-10 | 1 | 1 | 2023-10-10 | 2023-12-04 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-01-19 | 38 | 28 | Unknown | 2024-01-17 | Unknown | Unknown | 2024-01-19 | 2024-01-25 | 1900-01-06 | 5 | 2024-01-25 | 2024-01-25 | 1 | 1 | 53 | 40 | 9 | 7 | 62 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-28 | -163 | -117 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | 2023-01-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.67 | -5.68 | Unknown | Unknown | Unknown | -0.99 | Unknown | 98.66 | -6.67 | 105.33 | Yes | N/A | N/A | 2023-01-03 | 2023-03-29 | 86 | 62 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 86 | 62 | 1 | 1 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 51 | 51 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-17 | 131 | 94 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-08-31 | 2023-11-16 | IOU Designed & Installed | N/A | No | N/A | 1784.29 | Unknown | Unknown | Unknown | Unknown | 1784.29 | Unknown | 1091.27 | 1784.29 | -693.02 | Yes | N/A | N/A | 2023-08-30 | 2023-08-30 | 1 | 1 | 2023-08-30 | 2023-10-26 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2023-12-26 | 1900-02-09 | 29 | 2023-12-26 | 2023-12-26 | 1 | 1 | 1 | 1 | 100 | 72 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-31 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-07 | 2024-11-13 | IOU Designed & Installed | N/A | No | N/A | 1.62 | Unknown | Unknown | Unknown | Unknown | 1.62 | 3981 | 197.01 | 1.62 | 195.39 | Yes | N/A | N/A | 2024-10-07 | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2024-10-18 | 24 | 18 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-11-13 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-12-03 | 1900-01-20 | 15 | 2024-12-03 | 2024-12-03 | 1 | 1 | 27 | 19 | 46 | 34 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BONSALL | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -33 | -25 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | 2024-12-18 | IOU Designed & Installed | N/A | No | N/A | 6586.93 | 582.57 | Unknown | 131.73 | Unknown | 5872.63 | 3981 | 700.58 | 6586.93 | -5886.35 | Yes | N/A | N/A | 2024-05-20 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-05-30 | 71 | 51 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-12-18 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2024-12-19 | 1900-01-01 | 2 | 2024-12-19 | 2024-12-30 | 12 | 8 | 94 | 68 | 85 | 61 | 179 | 129 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | -650 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | 2024-12-13 | IOU Designed & Installed | N/A | No | N/A | 437.76 | Unknown | Unknown | Unknown | 2.66 | 435.1 | 3981 | 3144.9 | 437.76 | 2707.14 | Yes | N/A | N/A | 2024-11-18 | 2024-10-31 | Unknown | Unknown | 2024-10-31 | 2024-12-13 | 44 | 32 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2024-12-13 | 1 | 1 | Unknown | 2025-02-28 | Unknown | Unknown | 2024-12-13 | 2025-01-09 | 1900-01-27 | 20 | 2025-01-09 | 2025-01-09 | 1 | 1 | 1 | 1 | 73 | 53 | 74 | 54 | Steps 2,3,5,6,7 | 77 | 55 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | VALLEY CENTER | N/A | 72.05 | 72.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-22 | -553 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-31 | 2024-11-07 | 2025-03-12 | IOU Designed & Installed | N/A | No | N/A | -148.78 | Unknown | Unknown | Unknown | -1170 | 1021.22 | Unknown | 1034.8 | -148.78 | 1183.58 | Yes | N/A | N/A | 2024-10-31 | 2024-10-11 | Unknown | Unknown | 2024-10-11 | 2024-11-07 | 28 | 20 | 2024-11-07 | 2024-11-21 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2025-03-12 | 112 | 80 | Unknown | 2025-03-11 | Unknown | Unknown | 2025-03-12 | 2025-03-19 | 1900-01-07 | 6 | 2025-03-19 | 2025-03-18 | Unknown | Unknown | 127 | 91 | 36 | 26 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-03 | -273 | -196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-06-02 | 2024-05-03 | IOU Designed & Installed | N/A | No | N/A | 6635.47 | 2356.08 | Unknown | 462.58 | -921 | 4737.81 | 0 | 920.61 | 6635.47 | -5714.86 | Yes | N/A | N/A | 2023-06-02 | 2023-06-02 | 1 | 1 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2024-05-03 | 330 | 236 | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-05-06 | 1900-01-03 | 2 | 2024-05-06 | 2024-05-06 | 1 | 1 | 331 | 237 | 5 | 3 | 336 | 240 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -501 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-28 | 2024-07-10 | 2024-10-07 | IOU Designed & Installed | N/A | No | N/A | 31.78 | Unknown | Unknown | Unknown | Unknown | 31.78 | Unknown | 1492.06 | 31.78 | 1460.28 | Yes | N/A | N/A | 2024-06-28 | 2024-07-10 | 13 | 9 | 2024-07-10 | 2024-07-10 | 1 | 1 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-10-07 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2024-10-08 | 1900-01-01 | 2 | 2024-10-08 | 2024-10-08 | 1 | 1 | 103 | 73 | 4 | 4 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-10 | -278 | -199 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-22 | 2023-06-22 | 2023-06-23 | IOU Designed & Installed | N/A | No | N/A | -14.88 | -10.79 | Unknown | Unknown | Unknown | -4.09 | Unknown | 479.76 | -14.88 | 494.64 | Yes | N/A | N/A | 2023-06-22 | 2023-05-02 | Unknown | Unknown | 2023-05-02 | 2023-06-22 | 52 | 38 | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-06-23 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-07-07 | 1900-01-14 | 11 | 2023-07-07 | 2023-07-07 | 1 | 1 | 2 | 2 | 68 | 50 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-22 | 19 | 14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-17 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | 1247.92 | -36.82 | Unknown | Unknown | 7.01 | 1277.73 | 3981 | 975.38 | 1247.92 | -272.54 | Yes | N/A | N/A | 2024-01-17 | 2024-01-17 | 1 | 1 | 2024-01-17 | 2024-01-18 | 2 | 2 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | 2024-01-22 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-03-13 | 1900-02-20 | 38 | 2024-03-13 | 2024-03-12 | Unknown | Unknown | 7 | 5 | 54 | 40 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-02 | -287 | -206 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-04-28 | 2023-07-17 | IOU Designed & Installed | N/A | No | N/A | 1425 | 465.88 | Unknown | 147.6 | Unknown | 811.52 | 7710.44 | 1848.23 | 1425 | 423.23 | Yes | N/A | N/A | 2023-03-29 | 2023-04-28 | 31 | 23 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | 2023-07-17 | 57 | 41 | Unknown | 2023-06-22 | Unknown | Unknown | 2023-07-17 | 2023-07-20 | 1900-01-03 | 4 | 2023-07-20 | 2023-07-20 | 1 | 1 | 88 | 64 | 5 | 5 | 93 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-22 | -338 | -243 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | 2025-05-15 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | 577.19 | -11.6 | Unknown | Unknown | Unknown | 588.79 | Unknown | 1884.94 | 577.19 | 1307.75 | Yes | N/A | N/A | 2025-05-15 | 2025-05-14 | Unknown | Unknown | 2025-05-14 | 2025-05-15 | 2 | 2 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-05-16 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-05-19 | 1900-01-03 | 2 | 2025-05-19 | 2025-05-19 | 1 | 1 | 2 | 2 | 7 | 5 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-03 | -681 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | 2024-11-12 | IOU Designed & Installed | N/A | No | N/A | 601.22 | -11.7 | Unknown | Unknown | Unknown | 612.92 | 3981 | 1475.62 | 601.22 | 874.4 | Yes | N/A | N/A | 2024-10-22 | 2024-10-22 | 1 | 1 | 2024-10-22 | 2024-10-22 | 1 | 1 | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-11-12 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2024-11-21 | 1900-01-09 | 8 | 2024-11-21 | 2024-11-21 | 1 | 1 | 23 | 17 | 12 | 10 | 35 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -202 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-06-04 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | 4360.95 | Unknown | Unknown | Unknown | Unknown | 4360.95 | Unknown | 707.01 | 4360.95 | -3653.94 | Yes | N/A | N/A | 2024-05-30 | 2024-05-30 | 1 | 1 | 2024-05-30 | 2024-06-14 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-06-21 | 1900-01-04 | 5 | 2024-06-21 | 2024-06-21 | 1 | 1 | 1 | 1 | 22 | 18 | 23 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 48.35 | 48.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-17 | -444 | -319 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | 2023-04-05 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | 1087.27 | 413.15 | Unknown | Unknown | Unknown | 674.12 | Unknown | 3559.02 | 1087.27 | 2471.75 | Yes | N/A | N/A | 2023-04-05 | 2023-04-05 | 1 | 1 | 2023-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-05 | 2023-07-27 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-07-31 | 1900-01-04 | 3 | 2023-07-31 | 2023-07-31 | 1 | 1 | 115 | 83 | 6 | 4 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-22 | -592 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-06-06 | 2024-10-03 | IOU Designed & Installed | N/A | No | N/A | -1656.43 | Unknown | Unknown | Unknown | -1710 | 53.57 | Unknown | 1709.69 | -1656.43 | 3366.12 | Yes | N/A | N/A | 2024-05-30 | 2024-06-06 | 8 | 6 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-10-03 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-07 | 1900-01-04 | 3 | 2024-10-07 | 2024-10-07 | 1 | 1 | 72 | 52 | 6 | 4 | 78 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | Solana Beach | SOLANA BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-04 | 410 | 293 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-03 | 2024-01-30 | 2024-04-01 | IOU Designed & Installed | N/A | No | N/A | 8835.78 | 2600.81 | Unknown | 140.67 | Unknown | 6094.3 | Unknown | 14617.32 | 8835.78 | 5781.54 | Yes | N/A | N/A | 2022-05-03 | 2024-01-30 | 638 | 456 | 2024-01-30 | 2024-03-27 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-04-16 | 48 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-04-17 | 1900-01-16 | 13 | 2024-04-17 | 2024-04-17 | 1 | 1 | 638 | 456 | 124 | 92 | 762 | 548 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | 85 | 62 | No | 2024-12-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-02 | 2024-12-02 | 2025-04-30 | IOU Designed & Installed | N/A | Yes | 178 | 642.81 | -12.92 | Unknown | Unknown | Unknown | 655.73 | Unknown | 1621.85 | 642.81 | 979.04 | Yes | N/A | N/A | 2024-12-02 | 2025-05-27 | 177 | 127 | 2025-05-27 | 2025-05-29 | 3 | 3 | 2025-05-29 | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2025-04-30 | 136 | 98 | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-06-25 | 1900-02-25 | 41 | 2025-06-25 | 2025-06-25 | 1 | 1 | 313 | 225 | 61 | 45 | 374 | 270 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-24 | -685 | -490 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-26 | 2025-03-26 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | 2301.08 | 367.15 | Unknown | 51.2 | Unknown | 1882.73 | 3981 | 1778.94 | 2301.08 | -522.14 | Yes | N/A | N/A | 2025-03-26 | 2025-03-14 | Unknown | Unknown | 2025-03-14 | 2025-03-26 | 13 | 9 | 2025-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-04-09 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-10 | 1900-01-01 | 2 | 2025-04-10 | 2025-04-10 | 1 | 1 | 15 | 11 | 16 | 12 | 31 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-31 | 171 | 124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-05 | 2024-02-16 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 848.64 | -15.52 | Unknown | Unknown | Unknown | 864.16 | 3981 | 863.52 | 848.64 | 14.88 | Yes | N/A | N/A | 2024-01-05 | 2024-02-16 | 43 | 31 | 2024-02-16 | 2024-02-16 | 1 | 1 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-03-25 | 39 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-04-22 | 1900-01-28 | 21 | 2024-04-22 | 2024-04-19 | Unknown | Unknown | 82 | 58 | 30 | 22 | 112 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | -576 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | 2025-01-10 | IOU Designed & Installed | N/A | No | N/A | 1228.63 | Unknown | Unknown | Unknown | 7.82 | 1220.81 | 3981 | 1166.16 | 1228.63 | -62.47 | Yes | N/A | N/A | 2024-09-10 | 2024-10-21 | 42 | 30 | 2024-10-21 | 2024-10-23 | 3 | 3 | 2024-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2025-01-10 | 80 | 58 | Unknown | 2025-01-09 | Unknown | Unknown | 2025-01-10 | 2025-01-16 | 1900-01-06 | 5 | 2025-01-16 | 2025-01-15 | Unknown | Unknown | 122 | 88 | 10 | 8 | 132 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 74.05 | 74.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-11 | 187 | 134 | No | 2023-05-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-30 | 2024-04-26 | IOU Designed & Installed | N/A | Yes | 58 | 1293.44 | 404.01 | Unknown | 4.77 | Unknown | 884.66 | 7866 | 1451.73 | 1293.44 | 158.29 | Yes | N/A | N/A | 2023-05-22 | 2023-07-19 | 59 | 43 | 2023-07-19 | 2023-07-19 | 1 | 1 | 2023-07-19 | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | 2024-04-26 | 331 | 237 | Unknown | 2024-04-08 | Unknown | Unknown | 2024-04-26 | 2024-04-29 | 1900-01-03 | 2 | 2024-04-29 | 2024-04-15 | Unknown | Unknown | 390 | 280 | 5 | 3 | 395 | 283 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | 76 | 76 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -331 | -238 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 497.48 | -18.22 | Unknown | Unknown | 0.5 | 515.2 | 7962 | 2182.09 | 497.48 | 1684.61 | Yes | N/A | N/A | 2023-07-18 | 2023-07-18 | 1 | 1 | 2023-07-18 | 2023-08-08 | 22 | 16 | 2023-08-23 | 2024-03-12 | 19 | 13 | 2023-07-18 | 2024-03-13 | 81 | 61 | 2023-08-08 | 2024-03-01 | 207 | 149 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-05 | Unknown | Unknown | 227 | 163 | 103 | 77 | 330 | 240 | Steps 2,3,5,6,7 | 456 | 326 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-07 | -363 | -260 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-09 | 2023-11-10 | IOU Designed & Installed | N/A | No | N/A | 1164.17 | 370.02 | Unknown | 105.63 | Unknown | 688.52 | Unknown | 836.47 | 1164.17 | -327.7 | Yes | N/A | N/A | 2023-11-08 | 2023-11-08 | 1 | 1 | 2023-11-08 | 2023-11-09 | 2 | 2 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-11-10 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2023-11-10 | 1899-12-31 | 1 | 2023-11-10 | 2023-11-10 | 1 | 1 | 3 | 3 | 4 | 4 | 7 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-19 | -302 | -217 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 382.36 | 1157.39 | Unknown | 167.12 | -1564 | 621.85 | Unknown | 1563.84 | 382.36 | 1181.48 | Yes | N/A | N/A | 2024-01-18 | 2024-01-18 | 1 | 1 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-02-21 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | -371 | -266 | No | 2023-12-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2024-01-27 | 2024-02-28 | IOU Designed & Installed | N/A | Yes | 95 | 393.25 | -18.4 | Unknown | Unknown | Unknown | 411.65 | 3981 | 918.4 | 393.25 | 525.15 | Yes | N/A | N/A | 2023-12-07 | 2024-03-11 | 96 | 68 | 2024-03-11 | 2024-03-11 | 1 | 1 | 2024-03-11 | Unknown | Unknown | Unknown | 2024-01-27 | 2024-02-12 | 17 | 11 | 2024-01-27 | 2024-02-28 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-03-12 | 1900-01-13 | 10 | 2024-03-12 | 2024-08-23 | 165 | 119 | 129 | 91 | 197 | 141 | 326 | 232 | Steps 2,3,5,6,7 | 16 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-08 | -530 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-01 | 2024-04-01 | 2024-07-01 | IOU Designed & Installed | N/A | No | N/A | 1865.77 | -10.15 | Unknown | Unknown | 11.22 | 1864.7 | 3941 | 1106.32 | 1865.77 | -759.45 | Yes | N/A | N/A | 2024-04-01 | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-04-01 | 36 | 26 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-07-01 | 92 | 66 | Unknown | 2024-07-01 | Unknown | Unknown | 2024-07-01 | 2024-07-12 | 1900-01-11 | 10 | 2024-07-12 | 2024-08-27 | 47 | 33 | 92 | 66 | 95 | 69 | 187 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-09 | 320 | 230 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | -200.17 | 3611.14 | Unknown | Unknown | -5921 | 2109.69 | Unknown | 5921.02 | -200.17 | 6121.19 | Yes | N/A | N/A | 2025-03-17 | 2025-03-17 | 1 | 1 | 2025-03-17 | 2025-04-24 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | 2025-04-24 | 2025-04-24 | 1 | 1 | 2025-04-25 | 2025-04-25 | 1899-12-31 | 1 | 2025-04-25 | 2025-04-25 | 1 | 1 | 1 | 1 | 42 | 32 | 43 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-20 | -283 | -204 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-02-22 | 2024-04-30 | IOU Designed & Installed | N/A | No | N/A | 1329.79 | -12.52 | Unknown | Unknown | Unknown | 1342.31 | 3981 | 781.31 | 1329.79 | -548.48 | Yes | N/A | N/A | 2024-02-21 | 2024-02-21 | 1 | 1 | 2024-02-21 | 2024-02-22 | 2 | 2 | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-04-30 | 69 | 49 | Unknown | 2024-04-30 | Unknown | Unknown | 2024-04-30 | 2024-05-13 | 1900-01-13 | 10 | 2024-05-13 | 2024-05-13 | 1 | 1 | 70 | 50 | 17 | 13 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | 371 | 266 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2023-12-08 | 2024-03-04 | IOU Designed & Installed | N/A | No | N/A | 5.78 | -5.13 | Unknown | Unknown | Unknown | 10.91 | 716 | 397.48 | 5.78 | 391.7 | Yes | N/A | N/A | 2023-12-08 | 2023-11-09 | Unknown | Unknown | 2023-11-09 | 2023-12-12 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2024-02-28 | 79 | 57 | Unknown | 2024-01-10 | Unknown | Unknown | 2024-03-04 | 2024-03-28 | 1900-01-24 | 19 | 2024-03-28 | 2024-03-06 | Unknown | Unknown | 79 | 57 | 59 | 43 | 138 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-08 | -580 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-11-11 | IOU Designed & Installed | N/A | No | N/A | 82.47 | -0.63 | Unknown | Unknown | Unknown | 83.1 | Unknown | 1517.96 | 82.47 | 1435.49 | Yes | N/A | N/A | 2024-08-27 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-10-08 | 84 | 60 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-11-11 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2024-12-05 | 1900-01-24 | 19 | 2024-12-05 | 2024-12-05 | 1 | 1 | 35 | 25 | 110 | 80 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 1217.25 | 1217.25 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-09-11 | -259 | -186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-10-03 | 2023-12-15 | IOU Designed & Installed | N/A | No | N/A | 3300.32 | 350.69 | Unknown | Unknown | -477 | 3426.63 | 3981 | 1964.25 | 3300.32 | -1336.07 | Yes | N/A | N/A | 2023-10-03 | 2023-10-03 | 1 | 1 | 2023-10-03 | 2023-10-03 | 1 | 1 | 2023-10-03 | 2023-10-16 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | 2023-12-15 | 73 | 53 | Unknown | 2023-11-15 | Unknown | Unknown | 2023-12-15 | 2023-12-28 | 1900-01-13 | 10 | 2023-12-28 | 2023-12-27 | Unknown | Unknown | 88 | 64 | 15 | 11 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -498 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-24 | 2023-10-02 | IOU Designed & Installed | N/A | No | N/A | 4680.27 | Unknown | Unknown | Unknown | Unknown | 4680.27 | 49128 | 3586.59 | 4680.27 | -1093.68 | Yes | N/A | N/A | 2023-05-16 | 2023-05-24 | 9 | 7 | 2023-05-24 | 2023-05-26 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2023-09-13 | 1 | 1 | 2023-05-26 | 2023-09-12 | 110 | 78 | Unknown | 2023-09-27 | Unknown | Unknown | 2023-10-02 | 2023-10-24 | 1900-01-22 | 17 | 2023-10-24 | 2023-10-19 | Unknown | Unknown | 119 | 85 | 27 | 21 | 146 | 106 | Steps 2,3,5,6,7 | 110 | 78 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -208 | -149 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | 2024-08-15 | IOU Designed & Installed | N/A | No | N/A | 822.38 | 195.66 | Unknown | Unknown | -4463 | 5089.72 | Unknown | 8266.36 | 822.38 | 7443.98 | Yes | N/A | N/A | 2024-04-24 | 2024-04-22 | Unknown | Unknown | 2024-04-22 | 2024-08-01 | 102 | 74 | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-08-01 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-09-05 | 1900-01-21 | 16 | 2024-09-05 | 2024-09-05 | 1 | 1 | 0 | 0 | 139 | 101 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-23 | -198 | -143 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2024-01-04 | 2024-03-27 | IOU Designed & Installed | N/A | No | N/A | 13110.18 | 603.79 | Unknown | Unknown | Unknown | 12506.39 | 3981 | 1097.94 | 13110.18 | -12012.24 | Yes | N/A | N/A | 2023-11-29 | 2023-11-29 | 1 | 1 | 2023-11-29 | 2024-01-04 | 37 | 27 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-03-27 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-04-08 | 1900-01-12 | 9 | 2024-04-08 | 2024-04-08 | 1 | 1 | 85 | 61 | 51 | 37 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-17 | -493 | -354 | No | 2023-02-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-13 | 2023-06-12 | IOU Designed & Installed | N/A | Yes | 74 | 1933.06 | 232.94 | Unknown | Unknown | 17.92 | 1682.2 | 3885 | 435.62 | 1933.06 | -1497.44 | Yes | N/A | N/A | 2023-02-13 | 2023-04-28 | 75 | 55 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | 2023-06-12 | 96 | 68 | Unknown | 2023-06-08 | Unknown | Unknown | 2023-06-12 | 2023-06-12 | 1899-12-31 | 1 | 2023-06-12 | 2023-06-12 | 1 | 1 | 171 | 123 | 2 | 2 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-08 | -701 | -502 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | Unknown | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 36.88 | Unknown | Unknown | Unknown | Unknown | 36.88 | 3981 | 1531.63 | 36.88 | 1494.75 | Yes | N/A | N/A | 2024-10-22 | 2024-10-22 | 1 | 1 | 2024-10-22 | 2024-10-22 | 1 | 1 | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-10-23 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-11-06 | 1900-01-14 | 11 | 2024-11-06 | 2024-11-06 | 1 | 1 | 3 | 3 | 17 | 13 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 16.75 | 16.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-16 | -622 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-02-10 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | -2.17 | -9.05 | Unknown | Unknown | Unknown | 6.88 | 3981 | 1845.12 | -2.17 | 1847.29 | Yes | N/A | N/A | 2025-01-02 | 2025-01-08 | 7 | 5 | 2025-01-08 | 2025-02-10 | 34 | 24 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-11 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-04-03 | 1900-02-20 | 38 | 2025-04-03 | 2025-04-03 | 1 | 1 | 9 | 7 | 87 | 63 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-17 | 49 | 36 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-02 | 2025-06-04 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1989.23 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-02 | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-04-22 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-08 | 7 | 5 | 2025-04-22 | 2025-05-28 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-06-06 | 1900-01-02 | 3 | 2025-06-06 | 2025-06-05 | Unknown | Unknown | 37 | 27 | 40 | 30 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community,Tribal Community | WARNER SPRINGS | COUNTY OF SAN DIEGO-NORTH of 56 | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-07 | -245 | -176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-31 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | 26528.79 | 449.36 | Unknown | Unknown | -652.31 | 26731.74 | 3981 | 4639.67 | 26528.79 | -21889.12 | Yes | N/A | N/A | 2024-01-09 | 2024-07-31 | 205 | 147 | 2024-07-31 | 2024-09-13 | 45 | 33 | 2024-06-25 | 2024-06-25 | 1 | 1 | 2024-03-06 | 2024-09-20 | 4 | 4 | 2024-09-13 | 2024-10-28 | 46 | 32 | Unknown | 2024-10-16 | Unknown | Unknown | 2024-10-21 | 2024-11-04 | 1900-01-14 | 11 | 2024-11-04 | 2024-11-04 | 1 | 1 | 252 | 180 | 65 | 49 | 317 | 229 | Steps 2,3,5,6,7 | 198 | 142 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-02 | -134 | -97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5501.26 | -4.94 | Unknown | Unknown | 2.89 | 5503.31 | 3981 | 2861.64 | 5501.26 | -2639.62 | Yes | N/A | N/A | 2024-04-16 | 2024-04-09 | Unknown | Unknown | 2024-04-09 | 2024-05-20 | 42 | 30 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | Unknown | Unknown | Unknown | 2024-11-19 | Unknown | Unknown | 2024-11-19 | 2024-11-19 | 1 | 1 | 0 | 0 | 43 | 31 | 43 | 31 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -357 | -256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-01 | 2024-04-01 | 2024-04-03 | IOU Designed & Installed | N/A | No | N/A | 1024.18 | -23.83 | Unknown | Unknown | Unknown | 1048.01 | Unknown | 900.85 | 1024.18 | -123.33 | Yes | N/A | N/A | 2024-04-01 | 2024-04-01 | 1 | 1 | 2024-04-01 | 2024-04-01 | 1 | 1 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-04-03 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-04-09 | 1900-01-06 | 5 | 2024-04-09 | 2024-04-09 | 1 | 1 | 4 | 4 | 9 | 7 | 13 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 24 | 24 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2024-10-09 | IOU Designed & Installed | N/A | No | N/A | 1475.32 | Unknown | Unknown | Unknown | 4.98 | 1470.34 | 3981 | 1287.27 | 1475.32 | -188.05 | Yes | N/A | N/A | 2024-07-02 | 2024-07-01 | Unknown | Unknown | 2024-07-01 | 2024-08-15 | 46 | 34 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-10-09 | 57 | 41 | Unknown | 2024-10-08 | Unknown | Unknown | 2024-10-09 | 2024-10-24 | 1900-01-15 | 12 | 2024-10-24 | 2024-10-23 | Unknown | Unknown | 57 | 41 | 62 | 46 | 119 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | Both | IOU Design | Commercial | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-10-31 | 1421 | 1016 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-03 | 2022-08-03 | 2023-09-01 | IOU Designed & Installed | N/A | No | N/A | 78543.04 | 6918.14 | Unknown | 54.23 | 44.46 | 71526.21 | Unknown | 30027.73 | 78543.04 | -48515.31 | Yes | N/A | N/A | 2022-08-03 | 2023-03-23 | 233 | 167 | 2023-03-23 | 2023-08-29 | 160 | 114 | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | 2023-08-29 | 169 | 120 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2023-09-21 | 1900-01-20 | 15 | 2023-09-21 | 2023-09-21 | 1 | 1 | 233 | 167 | 351 | 250 | 584 | 417 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-23 | -618 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-25 | 2024-01-26 | IOU Designed & Installed | N/A | No | N/A | 100.45 | -12.14 | Unknown | Unknown | Unknown | 112.59 | Unknown | 959.71 | 100.45 | 859.26 | Yes | N/A | N/A | 2024-01-10 | 2023-10-25 | Unknown | Unknown | 2023-10-25 | 2024-01-25 | 93 | 67 | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-01-26 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-02-13 | 1900-01-18 | 13 | 2024-02-13 | 2024-02-13 | 1 | 1 | 2 | 2 | 113 | 81 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-01 | -539 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-19 | 2024-11-25 | IOU Designed & Installed | N/A | No | N/A | 41.19 | Unknown | Unknown | Unknown | Unknown | 41.19 | 3981 | 283.36 | 41.19 | 242.17 | Yes | N/A | N/A | 2024-06-19 | 2024-06-13 | Unknown | Unknown | 2024-06-13 | 2024-09-24 | 104 | 74 | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-09-24 | 1 | 1 | 2024-09-24 | 2024-11-15 | 53 | 39 | Unknown | 2024-11-25 | Unknown | Unknown | 2024-11-25 | 2024-12-12 | 1900-01-17 | 14 | 2024-12-12 | 2024-12-09 | Unknown | Unknown | 53 | 39 | 123 | 89 | 176 | 128 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-04 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | 2024-11-19 | IOU Designed & Installed | N/A | No | N/A | 43.16 | Unknown | Unknown | Unknown | Unknown | 43.16 | 3981 | 1478.32 | 43.16 | 1435.16 | Yes | N/A | N/A | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2024-11-19 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2025-01-08 | 1900-02-19 | 37 | 2025-01-08 | 2025-01-08 | 1 | 1 | 10 | 8 | 53 | 39 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | 19 | 14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-05 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 265.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-05 | 2025-03-06 | 2 | 2 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-03-21 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-05-12 | 1899-12-31 | 1 | 2025-05-12 | 2025-05-12 | 1 | 1 | 2 | 2 | 17 | 13 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-05 | -695 | -497 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | 2024-09-30 | IOU Designed & Installed | N/A | No | N/A | 41.62 | Unknown | Unknown | Unknown | Unknown | 41.62 | Unknown | 1546.09 | 41.62 | 1504.47 | Yes | N/A | N/A | 2024-09-27 | 2024-09-27 | 1 | 1 | 2024-09-27 | 2024-09-27 | 1 | 1 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-09-30 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-10-10 | 1900-01-10 | 9 | 2024-10-10 | 2024-10-10 | 1 | 1 | 5 | 3 | 13 | 11 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | 591 | 423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | 10486.56 | 371.92 | Unknown | 9.72 | 9.59 | 10095.33 | 214947 | 6051.22 | 10486.56 | -4435.34 | Yes | N/A | N/A | 2023-02-23 | 2023-02-23 | 1 | 1 | 2023-02-23 | 2023-03-07 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | 2024-09-16 | 111 | 79 | 2023-03-07 | 2024-08-21 | 534 | 382 | Unknown | 2024-09-09 | Unknown | Unknown | 2024-10-08 | 2024-11-04 | 1900-01-27 | 20 | 2024-11-04 | 2024-10-12 | Unknown | Unknown | 535 | 383 | 152 | 108 | 687 | 491 | Steps 2,3,5,6,7 | 559 | 399 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-20 | -74 | -55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 69.31 | Unknown | Unknown | Unknown | Unknown | 69.31 | Unknown | 6646.02 | 69.31 | 6576.71 | Yes | N/A | N/A | 2023-06-13 | 2024-09-24 | 470 | 336 | 2024-09-24 | 2024-09-24 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | Unknown | Unknown | 2024-10-07 | 2024-10-07 | 1 | 1 | 470 | 336 | 2 | 2 | 472 | 338 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -674 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 533.71 | -10.2 | Unknown | Unknown | Unknown | 543.91 | 3981 | 1852.47 | 533.71 | 1318.76 | Yes | N/A | N/A | 2024-08-28 | 2024-08-14 | Unknown | Unknown | 2024-08-14 | 2024-08-28 | 15 | 11 | 2024-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-09-23 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-09-30 | 1900-01-07 | 6 | 2024-09-30 | 2024-09-30 | 1 | 1 | 27 | 19 | 24 | 18 | 51 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | -277 | -200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-07-05 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | 1308.59 | Unknown | Unknown | Unknown | 19.22 | 1289.37 | 3981 | 1082.67 | 1308.59 | -225.92 | Yes | N/A | N/A | 2024-06-25 | 2024-05-17 | Unknown | Unknown | 2024-05-17 | 2024-08-01 | 77 | 55 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2025-06-05 | 309 | 221 | Unknown | 2025-06-04 | Unknown | Unknown | 2025-06-05 | 2025-06-09 | 1900-01-04 | 3 | 2025-06-09 | 2025-06-09 | 1 | 1 | 309 | 221 | 83 | 59 | 392 | 280 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | N/A | 103 | 103 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-26 | -163 | -118 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-07 | 2024-08-29 | IOU Designed & Installed | N/A | No | N/A | 2622.5 | 1625.55 | Unknown | 158.48 | Unknown | 838.47 | 0 | 1009.67 | 2622.5 | -1612.83 | Yes | N/A | N/A | 2023-08-07 | 2023-08-07 | 1 | 1 | 2023-08-07 | 2023-08-07 | 1 | 1 | 2023-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-07 | 2024-08-29 | 389 | 279 | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-09-16 | 1900-01-18 | 13 | 2024-09-16 | 2024-09-16 | 1 | 1 | 390 | 280 | 21 | 15 | 411 | 295 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | -486 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-17 | 2024-10-23 | 2025-04-03 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1577.29 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-17 | 2024-09-06 | Unknown | Unknown | 2024-09-06 | 2024-10-23 | 48 | 34 | 2024-10-23 | 2025-03-25 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-04-03 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-17 | 1900-01-14 | 11 | 2025-04-17 | 2025-04-15 | Unknown | Unknown | 164 | 118 | 63 | 45 | 227 | 163 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | -709 | -508 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-07 | 2024-11-08 | IOU Designed & Installed | N/A | No | N/A | 6456.97 | 1666.88 | Unknown | 212.72 | Unknown | 4577.37 | Unknown | 1423.75 | 6456.97 | -5033.22 | Yes | N/A | N/A | 2024-11-07 | 2024-11-07 | 1 | 1 | 2024-11-07 | 2024-11-07 | 1 | 1 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-11-08 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | 2024-11-20 | 1900-01-12 | 9 | 2024-11-20 | 2024-11-20 | 1 | 1 | 3 | 3 | 15 | 11 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-25 | -37 | -27 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2024-03-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | -10.69 | -8.68 | Unknown | Unknown | Unknown | -2.01 | 3981 | 1044.73 | -10.69 | 1055.42 | Yes | N/A | N/A | 2023-09-25 | 2024-03-19 | 177 | 127 | 2024-03-19 | 2024-03-19 | 1 | 1 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-04-18 | 1 | 1 | 177 | 127 | 2 | 2 | 179 | 129 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | La Mesa | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-21 | -249 | -180 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 7738.05 | 5351.64 | Unknown | 1146.94 | -2357 | 3596.47 | Unknown | 2357.06 | 7738.05 | -5380.99 | Yes | N/A | N/A | 2024-03-27 | 2024-03-27 | 1 | 1 | 2024-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-28 | -234 | -167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-03-01 | IOU Designed & Installed | N/A | No | N/A | -11.1 | -8.04 | Unknown | Unknown | Unknown | -3.06 | Unknown | 341 | -11.1 | 352.1 | Yes | N/A | N/A | 2023-02-27 | 2023-02-28 | 2 | 2 | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-28 | 2023-03-01 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | 2023-04-08 | 1900-02-07 | 28 | 2023-04-08 | 2023-04-08 | 1 | 0 | 4 | 4 | 40 | 28 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-25 | 20 | 15 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2023-12-06 | IOU Designed & Installed | N/A | No | N/A | 0.73 | -9.92 | Unknown | Unknown | Unknown | 10.65 | 3941 | 794.22 | 0.73 | 793.49 | Yes | N/A | N/A | 2023-09-29 | 2023-07-19 | Unknown | Unknown | 2023-07-19 | 2023-09-29 | 73 | 53 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-12-06 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2023-12-15 | 1900-01-09 | 8 | 2023-12-15 | 2023-12-15 | 1 | 1 | 69 | 49 | 84 | 62 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-03-24 | 621 | 444 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | -62.62 | -13.25 | Unknown | Unknown | -297.57 | 248.2 | Unknown | 270.46 | -62.62 | 333.08 | Yes | N/A | N/A | 2023-02-23 | 2023-02-23 | 1 | 1 | 2023-02-23 | 2023-11-17 | 268 | 192 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2023-11-20 | 4 | 2 | Unknown | 2023-12-04 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2023-12-05 | Unknown | Unknown | 5 | 3 | 268 | 192 | 273 | 195 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 202.05 | 202.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | 161 | 116 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-02 | 2024-12-02 | IOU Designed & Installed | N/A | No | N/A | 2118.01 | 585.21 | Unknown | 8.31 | Unknown | 1524.49 | 3981 | 2251.27 | 2118.01 | 133.26 | Yes | N/A | N/A | 2024-05-01 | 2024-07-01 | 62 | 44 | 2024-07-01 | 2024-07-09 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-10-02 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2024-12-02 | 1899-12-31 | 1 | 2024-12-02 | 2024-12-09 | 8 | 6 | 148 | 106 | 18 | 14 | 166 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 11.4 | 11.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-19 | -584 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-08-21 | 2024-12-03 | IOU Designed & Installed | N/A | No | N/A | 2723.34 | Unknown | Unknown | Unknown | 15.77 | 2707.57 | 3981 | 1130.51 | 2723.34 | -1592.83 | Yes | N/A | N/A | 2024-08-21 | 2024-08-07 | Unknown | Unknown | 2024-08-07 | 2024-08-29 | 23 | 17 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-12-03 | 97 | 69 | Unknown | 2024-11-20 | Unknown | Unknown | 2024-12-03 | 2024-12-12 | 1900-01-09 | 8 | 2024-12-12 | 2024-12-12 | 1 | 1 | 97 | 69 | 34 | 26 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-28 | -314 | -225 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 474.17 | Unknown | Unknown | Unknown | 2.95 | 471.22 | 3981 | 1195.95 | 474.17 | 721.78 | Yes | N/A | N/A | 2025-02-03 | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-02-06 | 7 | 5 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-03-05 | 28 | 20 | Unknown | 2025-03-04 | Unknown | Unknown | 2025-03-05 | 2025-03-20 | 1900-01-15 | 12 | 2025-03-20 | 2025-03-20 | 1 | 1 | 28 | 20 | 24 | 18 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-04-03 | 156 | 113 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-12 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 4194.06 | 801.06 | Unknown | Unknown | 140.19 | 3252.81 | 3981 | 2314.46 | 4194.06 | -1879.6 | Yes | N/A | N/A | 2023-04-03 | 2023-04-19 | 17 | 13 | 2023-04-19 | 2024-02-09 | 297 | 213 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-07-26 | 169 | 121 | Unknown | 2024-08-30 | Unknown | Unknown | 2024-08-22 | 2024-09-11 | 1900-01-20 | 15 | 2024-09-11 | 2024-09-06 | Unknown | Unknown | 186 | 134 | 318 | 228 | 504 | 362 | Steps 2,3,5,6,7 | 8 | 6 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-09 | -302 | -216 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-20 | 2023-11-20 | 2024-01-03 | IOU Designed & Installed | N/A | No | N/A | -805.73 | 1998.62 | Unknown | 708.93 | -4468 | 954.72 | Unknown | 4468.32 | -805.73 | 5274.05 | Yes | N/A | N/A | 2023-11-20 | 2023-11-28 | 9 | 7 | 2023-11-28 | 2024-01-12 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | Unknown | Unknown | Unknown | 2024-01-12 | 2024-01-12 | 1 | 1 | 2024-01-03 | 2024-01-12 | 1900-01-09 | 8 | 2024-01-12 | 2024-01-12 | 1 | 1 | 9 | 7 | 58 | 44 | 67 | 51 | Steps 2,3,5,6,7 | 9 | 7 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | Both | Applicant Design | Residential | N/A | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-05 | 115 | 82 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-02-17 | 2024-08-27 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 102656.29 | 13237.39 | Unknown | 36.45 | -45308 | 134690.45 | 13246.26 | 57797.2 | 102656.29 | -44859.09 | Yes | N/A | N/A | 2023-02-17 | 2024-01-02 | 320 | 228 | 2024-01-02 | 2024-05-29 | 149 | 107 | 2024-01-16 | 2024-03-18 | 63 | 45 | 2024-03-19 | 2025-08-04 | 89 | 63 | 2024-05-29 | Unknown | Unknown | Unknown | 2024-06-05 | 2025-01-13 | 223 | 159 | 2024-08-27 | 2024-10-28 | 1900-03-03 | 45 | 2024-10-28 | 2024-10-28 | 1 | 1 | 383 | 273 | 525 | 375 | 908 | 648 | Steps 2,3,5,6,7 | 705 | 503 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 147.05 | 147.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-26 | -491 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-03-27 | 2024-07-01 | IOU Designed & Installed | N/A | No | N/A | 2100.49 | Unknown | Unknown | Unknown | Unknown | 2100.49 | Unknown | 1231.98 | 2100.49 | -868.51 | Yes | N/A | N/A | 2024-03-27 | 2024-03-27 | 1 | 1 | 2024-03-27 | 2024-04-10 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | Unknown | Unknown | 2024-07-01 | 2024-07-23 | 1900-01-22 | 17 | 2024-07-23 | 2024-07-23 | 1 | 1 | 1 | 1 | 39 | 29 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-16 | -380 | -271 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 10.68 | Unknown | Unknown | Unknown | Unknown | 10.68 | 0 | 163.83 | 10.68 | 153.15 | Yes | N/A | N/A | 2024-01-29 | 2023-11-21 | Unknown | Unknown | 2023-11-21 | 2024-02-06 | 78 | 56 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | 2024-11-01 | 2024-11-01 | 1 | 1 | 0 | 0 | 79 | 57 | 79 | 57 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-28 | -522 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | 2023-05-24 | IOU Designed & Installed | N/A | No | N/A | 806.99 | 238.58 | Unknown | Unknown | Unknown | 568.41 | 3981 | 935.05 | 806.99 | 128.06 | Yes | N/A | N/A | 2023-03-06 | 2023-03-06 | 1 | 1 | 2023-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-06 | 2023-05-24 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2023-05-24 | 2023-05-25 | 1900-01-01 | 2 | 2023-05-25 | 2023-05-25 | 1 | 1 | 81 | 59 | 3 | 3 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-26 | -478 | -342 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-09 | 2023-07-03 | IOU Designed & Installed | N/A | No | N/A | 750.83 | 376.21 | Unknown | 134.04 | Unknown | 240.58 | Unknown | 625.47 | 750.83 | -125.36 | Yes | N/A | N/A | 2023-03-09 | 2023-03-09 | 1 | 1 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | 2023-07-03 | 67 | 47 | Unknown | Unknown | Unknown | Unknown | 2023-07-03 | 2023-07-06 | 1900-01-03 | 4 | 2023-07-06 | 2023-07-06 | 1 | 1 | 68 | 48 | 5 | 5 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | 8.05 | 8.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-27 | -14 | -11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-02 | 2023-03-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 495.92 | Unknown | Unknown | Unknown | 44.99 | 450.93 | 3981 | 958.34 | 495.92 | 462.42 | Yes | N/A | N/A | 2023-03-02 | 2023-03-02 | 1 | 1 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | 2025-01-13 | 2025-01-13 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 17 | 17 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | -403 | -289 | No | 2024-07-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | Yes | 90 | 1342.54 | Unknown | Unknown | Unknown | 16.22 | 1326.32 | 3981 | 1122.44 | 1342.54 | -220.1 | Yes | N/A | N/A | 2024-07-25 | 2024-10-23 | 91 | 65 | 2024-10-23 | 2024-08-21 | Unknown | Unknown | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-21 | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | Unknown | Unknown | Unknown | 2025-04-29 | Unknown | Unknown | 2025-04-29 | 2025-04-29 | 1 | 1 | 91 | 65 | 1 | 1 | 92 | 66 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | -445 | -320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-21 | 2024-10-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 737.7 | -13.96 | Unknown | Unknown | Unknown | 751.66 | 7962 | 1147.75 | 737.7 | 410.05 | Yes | N/A | N/A | 2024-08-21 | 2024-10-04 | 45 | 33 | 2024-10-04 | 2024-10-15 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-11-11 | 32 | 22 | 2024-10-15 | 2025-02-03 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-03-24 | Unknown | Unknown | 157 | 113 | 44 | 30 | 201 | 143 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 1117.05 | 1117.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2026-03-15 | -521 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2024-09-30 | IOU Designed & Installed | N/A | No | N/A | 33.68 | Unknown | Unknown | Unknown | Unknown | 33.68 | 3981 | 192.95 | 33.68 | 159.27 | Yes | N/A | N/A | 2024-07-02 | 2024-08-12 | 42 | 30 | 2024-08-12 | 2024-08-12 | 1 | 1 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-09-30 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-10-08 | 1900-01-08 | 7 | 2024-10-08 | 2024-10-10 | 3 | 3 | 92 | 66 | 13 | 11 | 105 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | -585 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-19 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | 3315.91 | 504.26 | Unknown | 35.51 | 7.11 | 2769.03 | 3981 | 1136.34 | 3315.91 | -2179.57 | Yes | N/A | N/A | 2024-06-19 | 2024-06-28 | 10 | 8 | 2024-06-28 | 2024-06-28 | 1 | 1 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-10-11 | 106 | 76 | Unknown | 2024-10-10 | Unknown | Unknown | 2024-10-11 | 2024-10-21 | 1900-01-10 | 7 | 2024-10-21 | 2024-10-21 | 1 | 1 | 116 | 84 | 13 | 9 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | -227 | -164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-29 | 2024-04-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2983.56 | 3896.97 | Unknown | 189.09 | -2969 | 1866.5 | Unknown | 2969.45 | 2983.56 | -14.11 | Yes | N/A | N/A | 2024-03-29 | 2024-03-28 | Unknown | Unknown | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-13 | -696 | -499 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-22 | 2025-05-22 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1203.94 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-22 | 2025-05-22 | 1 | 1 | 2025-05-22 | 2025-05-22 | 1 | 1 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-06-10 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-16 | 1900-01-06 | 5 | 2025-06-16 | 2025-06-16 | 1 | 1 | 21 | 15 | 9 | 7 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 116 | 116 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-23 | -53 | -40 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2023-11-15 | 2024-05-28 | IOU Designed & Installed | N/A | No | N/A | -10.16 | -10.82 | Unknown | Unknown | Unknown | 0.66 | 3981 | 496.75 | -10.16 | 506.91 | Yes | N/A | N/A | 2023-10-25 | 2023-11-14 | 21 | 15 | 2023-11-14 | 2023-11-15 | 2 | 2 | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2024-05-28 | 196 | 140 | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-06-28 | 1900-01-31 | 24 | 2024-06-28 | 2024-07-01 | 4 | 2 | 217 | 155 | 38 | 28 | 255 | 183 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 135.1 | 135.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-28 | -385 | -276 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2025-01-23 | 2025-04-17 | IOU Designed & Installed | N/A | No | N/A | 6156.18 | 121.25 | Unknown | Unknown | 4.29 | 6030.64 | 3981 | 2272.21 | 6156.18 | -3883.97 | Yes | N/A | N/A | 2024-09-10 | 2024-12-23 | 105 | 75 | 2024-12-23 | 2025-04-04 | 103 | 75 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-27 | 22 | 16 | 2025-04-04 | 2025-05-01 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-05-30 | 1900-02-12 | 32 | 2025-05-30 | 2025-05-08 | Unknown | Unknown | 133 | 95 | 169 | 123 | 302 | 218 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | MISSION VIEJO | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-26 | -114 | -83 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 276.18 | 130.28 | Unknown | 55.63 | Unknown | 90.27 | 3981 | 154.99 | 276.18 | -121.19 | Yes | N/A | N/A | 2023-08-07 | 2023-10-02 | 57 | 41 | 2023-10-02 | 2023-10-11 | 10 | 8 | 2023-10-11 | Unknown | Unknown | Unknown | 2023-10-05 | 2023-10-09 | 5 | 3 | 2023-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-03-04 | 1 | 1 | 57 | 41 | 16 | 12 | 73 | 53 | Steps 2,3,5,6,7 | 4 | 2 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-10 | -516 | -369 | No | 2023-05-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-05-17 | Unknown | IOU Designed & Installed | N/A | Yes | 27 | 329.1 | -9.92 | Unknown | Unknown | 3.2 | 335.82 | 3241 | 855.7 | 329.1 | 526.6 | Yes | N/A | N/A | 2023-05-17 | 2023-06-13 | 28 | 20 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | Unknown | Unknown | 2023-07-13 | 2023-07-13 | 1 | 1 | 28 | 20 | 1 | 1 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-25 | 53 | 38 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-14 | 2023-10-09 | IOU Designed & Installed | N/A | No | N/A | 66.21 | -10.76 | Unknown | Unknown | 65.83 | 11.14 | 3981 | 509.8 | 66.21 | 443.59 | Yes | N/A | N/A | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | 2023-10-09 | 88 | 62 | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2024-11-19 | 1901-02-11 | 292 | 2024-11-19 | 2023-10-17 | Unknown | Unknown | 89 | 63 | 409 | 293 | 498 | 356 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-07 | 52 | 37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-08-31 | 2023-10-27 | IOU Designed & Installed | N/A | No | N/A | 790.42 | -16.31 | Unknown | Unknown | Unknown | 806.73 | 0 | 480.37 | 790.42 | -310.05 | Yes | N/A | N/A | 2023-08-31 | 2023-05-22 | Unknown | Unknown | 2023-05-22 | 2023-08-31 | 102 | 74 | 2023-08-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | 2023-10-27 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2025-04-28 | 1901-07-03 | 392 | 2025-04-28 | 2025-04-28 | 1 | 1 | 53 | 39 | 653 | 467 | 706 | 506 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-14 | -30 | -23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 1891.69 | Unknown | Unknown | Yes | N/A | N/A | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-14 | -605 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-08-30 | 2024-09-18 | IOU Designed & Installed | N/A | No | N/A | 1406.4 | 377.04 | Unknown | 122.65 | Unknown | 906.71 | 3981 | 1142 | 1406.4 | -264.4 | Yes | N/A | N/A | 2024-07-18 | 2024-08-16 | 30 | 22 | 2024-08-16 | 2024-08-30 | 15 | 11 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-09-18 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-10-17 | 1900-01-29 | 22 | 2024-10-17 | 2024-10-17 | 1 | 1 | 50 | 36 | 46 | 34 | 96 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R29/R45) | UG | Applicant Design | Commercial | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-05-14 | 1120 | 800 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-14 | 2022-03-31 | 2024-12-23 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 477826.21 | 66063.07 | Unknown | 294.49 | 14549.04 | 396919.61 | 36052 | 278020.55 | 477826.21 | -199805.66 | Yes | N/A | N/A | 2021-05-14 | 2023-04-03 | 690 | 492 | 2023-04-03 | 2024-11-26 | 604 | 432 | 2021-10-14 | 2024-11-26 | 438 | 312 | 2023-03-10 | 2025-06-05 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2025-01-30 | 65 | 47 | 2024-12-23 | 2025-06-07 | 1900-06-15 | 120 | 2025-06-07 | 2025-06-07 | 1 | 0 | 1128 | 804 | 912 | 652 | 2040 | 1456 | Steps 2,3,5,6,7 | 665 | 475 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | -629 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-04 | 2025-03-21 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1564.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-04 | 2025-02-04 | 1 | 1 | 2025-02-04 | 2025-02-04 | 1 | 1 | 2025-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-03-21 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-05-02 | 1900-02-11 | 31 | 2025-05-02 | 2025-05-02 | 1 | 1 | 47 | 35 | 45 | 33 | 92 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -586 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 115.21 | -7.53 | Unknown | Unknown | -474 | 596.74 | Unknown | 414.88 | 115.21 | 299.67 | Yes | N/A | N/A | 2024-03-06 | 2024-03-15 | 10 | 8 | 2024-03-15 | 2024-04-18 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-04-24 | 7 | 5 | Unknown | 2024-05-21 | Unknown | Unknown | Unknown | 2024-05-24 | Unknown | Unknown | 2024-05-24 | 2024-05-24 | 1 | 1 | 17 | 13 | 36 | 26 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 57.05 | 57.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | -382 | -273 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | 2024-01-05 | IOU Designed & Installed | N/A | No | N/A | 1058.72 | 399.84 | Unknown | Unknown | Unknown | 658.88 | 3981 | 872.51 | 1058.72 | -186.21 | Yes | N/A | N/A | 2023-10-17 | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-11-09 | 80 | 58 | 2023-11-09 | 2024-01-05 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2024-01-05 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-01-10 | 1900-01-05 | 4 | 2024-01-10 | 2024-01-10 | 1 | 1 | 116 | 84 | 87 | 63 | 203 | 147 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-17 | -683 | -488 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-14 | 2025-02-20 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 922.54 | 502.72 | Unknown | 67.75 | Unknown | 352.07 | Unknown | 196.69 | 922.54 | -725.85 | Yes | N/A | N/A | 2025-02-14 | 2025-02-05 | Unknown | Unknown | 2025-02-05 | 2025-02-20 | 16 | 12 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-03-05 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-05 | 1899-12-31 | 1 | 2025-03-05 | 2025-03-05 | 1 | 1 | 14 | 10 | 18 | 14 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-07 | -306 | -220 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-23 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2291.58 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-10 | 2024-07-11 | 2 | 2 | 2024-07-11 | 2024-07-23 | 13 | 9 | 2024-07-23 | 2024-07-26 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2025-05-02 | 281 | 201 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-06 | 1900-01-04 | 3 | 2025-05-06 | 2025-05-05 | Unknown | Unknown | 287 | 207 | 18 | 12 | 305 | 219 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | -574 | -411 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | 2023-08-23 | IOU Designed & Installed | N/A | No | N/A | 1308.32 | 370.02 | Unknown | 239.55 | Unknown | 698.75 | 3981 | 801.86 | 1308.32 | -506.46 | Yes | N/A | N/A | 2023-08-09 | 2023-08-10 | 2 | 2 | 2023-08-10 | 2023-08-18 | 9 | 7 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2023-08-23 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | 2023-10-19 | 1900-02-26 | 42 | 2023-10-19 | 2023-10-19 | 1 | 1 | 10 | 8 | 68 | 50 | 78 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 8.1 | 8.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-12-18 | 2025-01-09 | IOU Designed & Installed | N/A | No | N/A | 104.52 | -1.5 | Unknown | Unknown | Unknown | 106.02 | Unknown | 1802.02 | 104.52 | 1697.5 | Yes | N/A | N/A | 2024-11-19 | 2024-11-19 | 1 | 1 | 2024-11-19 | 2024-12-18 | 30 | 22 | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-01-09 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-24 | 1900-01-15 | 12 | 2025-01-24 | 2025-01-24 | 1 | 1 | 24 | 18 | 47 | 35 | 71 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-05 | -444 | -319 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-05 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 1857.72 | 507.48 | Unknown | Unknown | Unknown | 1350.24 | Unknown | 1857.36 | 1857.72 | -0.36 | Yes | N/A | N/A | 2024-09-04 | 2024-06-07 | Unknown | Unknown | 2024-06-07 | 2024-09-06 | 92 | 66 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2025-03-18 | 194 | 138 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-03-18 | 1899-12-31 | 1 | 2025-03-18 | 2025-03-18 | 1 | 1 | 194 | 138 | 94 | 68 | 288 | 206 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-04 | -690 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1605.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-04-28 | 19 | 13 | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | 2025-05-02 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-14 | 1900-01-12 | 9 | 2025-05-14 | 2025-05-14 | 1 | 1 | 5 | 5 | 33 | 23 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego | San Diego | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 813 | 582 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-05-24 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 72404.91 | 22048.64 | Unknown | Unknown | 7812.65 | 42543.62 | 0 | 29176.38 | 72404.91 | -43228.53 | Yes | N/A | N/A | 2022-04-27 | 2023-05-15 | 384 | 274 | 2023-05-15 | 2024-08-16 | 460 | 330 | 2023-05-24 | 2024-04-08 | 294 | 210 | 2023-05-25 | 2024-01-16 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | 2025-07-17 | 2025-06-10 | Unknown | Unknown | 2025-06-10 | 2025-06-10 | 1 | 1 | 678 | 484 | 609 | 437 | 1287 | 921 | Steps 2,3,5,6,7 | 769 | 549 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-17 | -667 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-26 | 2024-06-26 | 2024-06-27 | IOU Designed & Installed | N/A | No | N/A | 1251 | 246.06 | Unknown | Unknown | Unknown | 1004.94 | Unknown | 1928.78 | 1251 | 677.78 | Yes | N/A | N/A | 2024-06-26 | 2024-06-26 | 1 | 1 | 2024-06-26 | 2024-06-26 | 1 | 1 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-06-27 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-07-19 | 1900-01-22 | 17 | 2024-07-19 | 2024-07-19 | 1 | 1 | 3 | 3 | 25 | 19 | 28 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community,Tribal Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -190 | -137 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 427420 | 29210.73 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-23 | 2025-04-25 | 3 | 3 | 2025-04-25 | 2025-05-19 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-05-17 | 2025-05-29 | 13 | 9 | 2025-05-19 | 2024-10-10 | Unknown | Unknown | 2025-06-04 | 2025-06-06 | 3 | 3 | Unknown | 2025-08-28 | Unknown | Unknown | 2025-08-28 | 2025-06-24 | Unknown | Unknown | 3 | 3 | 41 | 29 | 44 | 32 | Steps 2,3,5,6,7 | 10 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 102.2 | 102.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-30 | -331 | -238 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | 2898.64 | 757.95 | Unknown | Unknown | 15.75 | 2124.94 | 3981 | 1327.17 | 2898.64 | -1571.47 | Yes | N/A | N/A | 2023-03-08 | 2023-06-29 | 114 | 82 | 2023-06-29 | 2023-07-27 | 29 | 21 | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | 2024-05-30 | 269 | 193 | Unknown | 2024-05-20 | Unknown | Unknown | 2024-05-30 | 2024-06-03 | 1900-01-04 | 3 | 2024-06-03 | 2024-06-03 | 1 | 1 | 383 | 275 | 35 | 25 | 418 | 300 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-17 | -254 | -183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-11 | 2023-07-11 | IOU Designed & Installed | N/A | No | N/A | 35393.55 | 17638.48 | Unknown | Unknown | Unknown | 17755.07 | Unknown | 480.44 | 35393.55 | -34913.11 | Yes | N/A | N/A | 2023-07-11 | 2023-05-03 | Unknown | Unknown | 2023-05-03 | 2023-07-11 | 70 | 50 | 2023-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | 2023-07-11 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | 2023-08-07 | 1900-01-27 | 20 | 2023-08-07 | 2023-08-07 | 1 | 1 | 1 | 1 | 99 | 71 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | -115 | -84 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-21 | 2024-06-04 | IOU Designed & Installed | N/A | No | N/A | 2720.99 | Unknown | Unknown | Unknown | 9.38 | 2711.61 | 3981 | 416.96 | 2720.99 | -2304.03 | Yes | N/A | N/A | 2024-02-15 | 2024-02-15 | 1 | 1 | 2024-02-15 | 2024-03-26 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-03-29 | 2024-03-29 | 1 | 1 | 2024-03-26 | 2024-05-29 | 65 | 47 | Unknown | 2024-06-04 | Unknown | Unknown | 2024-06-04 | 2024-07-25 | 1900-02-20 | 38 | 2024-07-25 | 2024-07-08 | Unknown | Unknown | 66 | 48 | 94 | 68 | 160 | 116 | Steps 2,3,5,6,7 | 3 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-24 | -535 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-11 | 2024-05-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1021.94 | Unknown | Unknown | Unknown | -1110 | 88.06 | 47982 | 2252.7 | -1021.94 | 3274.64 | Yes | N/A | N/A | 2024-05-11 | 2024-05-11 | 1 | 0 | 2024-05-11 | 2024-05-11 | 1 | 0 | 2024-05-11 | 2024-09-13 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | Unknown | 2024-11-05 | Unknown | Unknown | 2024-11-05 | 2024-11-05 | 1 | 1 | 127 | 90 | 2 | 1 | 129 | 91 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 32.05 | 32.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | -377 | -270 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-06-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1086.8 | -17.93 | Unknown | Unknown | -1101 | 32.13 | 3981 | 1786.61 | -1086.8 | 2873.41 | Yes | N/A | N/A | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | 2024-01-17 | 202 | 144 | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | Unknown | Unknown | Unknown | 2024-01-26 | Unknown | Unknown | 2024-01-26 | 2024-01-26 | 1 | 1 | 203 | 145 | 2 | 2 | 205 | 147 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-13 | -179 | -128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6.26 | Unknown | Unknown | Unknown | Unknown | 6.26 | 3961 | 163.83 | 6.26 | 157.57 | Yes | N/A | N/A | 2024-01-24 | 2024-02-13 | 21 | 15 | 2024-02-13 | 2024-04-22 | 70 | 50 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | Unknown | Unknown | 2025-04-17 | 2025-04-17 | 1 | 1 | 21 | 15 | 71 | 51 | 92 | 66 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | DEL MAR | DEL MAR | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-10 | -441 | -316 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2024-03-12 | 2024-04-30 | IOU Designed & Installed | N/A | No | N/A | 3882.38 | Unknown | Unknown | Unknown | Unknown | 3882.38 | Unknown | 879.09 | 3882.38 | -3003.29 | Yes | N/A | N/A | 2023-12-13 | 2024-01-03 | 22 | 16 | 2024-01-03 | 2024-01-09 | 7 | 5 | 2024-01-09 | Unknown | Unknown | Unknown | 2024-04-19 | Unknown | Unknown | Unknown | 2024-03-12 | 2024-04-30 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2024-06-26 | 1900-02-26 | 42 | 2024-06-26 | 2024-06-26 | 1 | 1 | 72 | 52 | 66 | 48 | 138 | 100 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 17 | 17 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-25 | -79 | -58 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-02-10 | 2023-07-19 | IOU Designed & Installed | N/A | No | N/A | -1450.84 | -7.41 | Unknown | Unknown | -1447 | 3.57 | Unknown | 1266.91 | -1450.84 | 2717.75 | Yes | N/A | N/A | 2023-01-24 | 2023-02-10 | 18 | 14 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-07-19 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2023-07-19 | 2023-08-07 | 1900-01-19 | 14 | 2023-08-07 | 2023-08-07 | 1 | 1 | 20 | 16 | 21 | 15 | 41 | 31 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-16 | -238 | -171 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | 2023-09-06 | IOU Designed & Installed | N/A | No | N/A | 219.17 | -8.9 | Unknown | Unknown | Unknown | 228.07 | 3981 | 1267.63 | 219.17 | 1048.46 | Yes | N/A | N/A | 2023-08-08 | 2023-09-01 | 25 | 19 | 2023-09-01 | 2023-09-01 | 1 | 1 | 2023-09-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2023-09-06 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | 2023-09-21 | 1900-01-15 | 12 | 2023-09-21 | 2023-09-21 | 1 | 1 | 31 | 23 | 18 | 14 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 132 | 132 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-18 | -257 | -184 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-22 | 2023-02-22 | 2024-03-05 | IOU Designed & Installed | N/A | No | N/A | 1967.84 | 252.46 | Unknown | 55.15 | 5.64 | 1654.59 | 0 | 1171.85 | 1967.84 | -795.99 | Yes | N/A | N/A | 2023-02-22 | 2023-03-28 | 35 | 25 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | 2024-03-05 | 344 | 246 | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | 2024-03-06 | 1900-01-01 | 2 | 2024-03-06 | 2024-03-06 | 1 | 1 | 379 | 271 | 3 | 3 | 382 | 274 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 1525.35 | 1525.35 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-03-09 | 24 | 18 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-07 | 2023-10-07 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | -3.32 | -13.87 | Unknown | Unknown | Unknown | 10.55 | 3981 | 671.11 | -3.32 | 674.43 | Yes | N/A | N/A | 2023-10-07 | 2023-10-06 | Unknown | Unknown | 2023-10-06 | 2023-10-06 | 1 | 1 | 2023-10-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-07 | 2025-03-31 | 542 | 386 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-02 | 1900-01-02 | 3 | 2025-04-02 | 2025-04-02 | 1 | 1 | 542 | 386 | 5 | 5 | 547 | 391 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | -527 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | 2024-12-10 | IOU Designed & Installed | N/A | No | N/A | 913.17 | 479.58 | Unknown | 98.06 | Unknown | 335.53 | Unknown | 197.01 | 913.17 | -716.16 | Yes | N/A | N/A | 2024-11-18 | 2024-11-18 | 1 | 1 | 2024-11-18 | 2024-11-18 | 1 | 1 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-12-10 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2025-02-10 | 1900-03-03 | 45 | 2025-02-10 | 2025-02-10 | 1 | 1 | 24 | 18 | 65 | 47 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-17 | -680 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | 2024-11-08 | IOU Designed & Installed | N/A | No | N/A | 1446.11 | -28.63 | Unknown | Unknown | Unknown | 1474.74 | 3981 | 1641.81 | 1446.11 | 195.7 | Yes | N/A | N/A | 2024-10-30 | 2024-10-30 | 1 | 1 | 2024-10-30 | 2024-10-30 | 1 | 1 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2024-11-08 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | 2024-12-06 | 1900-01-28 | 21 | 2024-12-06 | 2024-12-06 | 1 | 1 | 11 | 9 | 31 | 23 | 42 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BOULEVARD | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | -661 | -474 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-16 | 2025-05-19 | IOU Designed & Installed | N/A | No | N/A | 2532.8 | 427.01 | Unknown | Unknown | 8.01 | 2097.78 | 3981 | 1151.76 | 2532.8 | -1381.04 | Yes | N/A | N/A | 2025-04-16 | 2025-04-03 | Unknown | Unknown | 2025-04-03 | 2025-04-25 | 23 | 17 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-19 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | 2025-06-09 | 1900-01-21 | 16 | 2025-06-09 | 2025-06-09 | 1 | 1 | 25 | 17 | 46 | 34 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-13 | -137 | -98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | 2024-04-23 | IOU Designed & Installed | N/A | No | N/A | 18.22 | -16.16 | Unknown | Unknown | Unknown | 34.38 | Unknown | 815.96 | 18.22 | 797.74 | Yes | N/A | N/A | 2023-12-01 | 2023-10-25 | Unknown | Unknown | 2023-10-25 | 2023-12-01 | 38 | 28 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2024-04-23 | 145 | 103 | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-05-29 | 1900-02-05 | 27 | 2024-05-29 | 2024-05-29 | 1 | 1 | 145 | 103 | 76 | 56 | 221 | 159 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | -397 | -285 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-03-28 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 594.24 | 267.92 | Unknown | 131.84 | Unknown | 194.48 | Unknown | 501.18 | 594.24 | -93.06 | Yes | N/A | N/A | 2024-03-26 | 2024-01-02 | Unknown | Unknown | 2024-01-02 | 2024-04-01 | 91 | 65 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-11-14 | 228 | 164 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-11-18 | 1900-01-04 | 3 | 2024-11-18 | 2024-11-18 | 1 | 1 | 228 | 164 | 97 | 69 | 325 | 233 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-12-31 | 2101 | 1502 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | -877.24 | -9.15 | Unknown | Unknown | -1407 | 538.91 | 3981 | 1782.39 | -877.24 | 2659.63 | Yes | N/A | N/A | 2024-03-25 | 2024-03-25 | 1 | 1 | 2024-03-25 | 2024-09-11 | 171 | 123 | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-27 | 29 | 21 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | Unknown | Unknown | Unknown | 2024-10-01 | Unknown | Unknown | 2024-10-01 | 2024-10-01 | 1 | 1 | 1 | 1 | 201 | 145 | 202 | 146 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-10 | -681 | -488 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-20 | 2024-09-20 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | 46.04 | Unknown | Unknown | Unknown | Unknown | 46.04 | 3981 | 1401.93 | 46.04 | 1355.89 | Yes | N/A | N/A | 2024-09-20 | 2024-09-19 | Unknown | Unknown | 2024-09-19 | 2024-09-23 | 5 | 3 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-21 | 32 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-10-29 | 1900-01-08 | 7 | 2024-10-29 | 2024-10-29 | 1 | 1 | 32 | 22 | 15 | 11 | 47 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | 269 | 192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-10 | 2022-02-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | -550.26 | 1597.89 | Unknown | 619.08 | -3442 | 674.77 | Unknown | 3441.93 | -550.26 | 3992.19 | Yes | N/A | N/A | 2022-02-10 | 2023-06-23 | 499 | 357 | 2023-06-23 | 2023-08-29 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 499 | 357 | 69 | 49 | 568 | 406 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | -463 | -332 | No | 2024-07-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-26 | 2024-07-26 | Unknown | IOU Designed & Installed | N/A | Yes | 7 | 68.71 | -25.9 | Unknown | Unknown | Unknown | 94.61 | 3981 | 2073.08 | 68.71 | 2004.37 | Yes | N/A | N/A | 2024-07-26 | 2024-08-02 | 8 | 6 | 2024-08-02 | 2024-07-26 | Unknown | Unknown | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | Unknown | Unknown | 2025-03-20 | 2025-03-19 | Unknown | Unknown | 8 | 6 | 0 | 0 | 8 | 6 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 19680 | 19680 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-04-25 | -546 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | 2023-10-23 | IOU Designed & Installed | N/A | No | N/A | 0.5 | -13.16 | Unknown | Unknown | Unknown | 13.66 | 3941 | 988.74 | 0.5 | 988.24 | Yes | N/A | N/A | 2023-09-07 | 2023-05-12 | Unknown | Unknown | 2023-05-12 | 2023-09-07 | 119 | 85 | 2023-09-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-07 | 2023-10-23 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2023-10-27 | 1900-01-04 | 5 | 2023-10-27 | 2023-10-27 | 1 | 1 | 47 | 33 | 125 | 91 | 172 | 124 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-02 | 126 | 91 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 543.52 | -10.2 | Unknown | Unknown | Unknown | 553.72 | 3981 | 1251.64 | 543.52 | 708.12 | Yes | N/A | N/A | 2024-08-07 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-08-07 | 34 | 24 | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-10-28 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-06 | 1900-01-09 | 8 | 2024-11-06 | 2024-11-05 | Unknown | Unknown | 83 | 59 | 44 | 32 | 127 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-20 | -508 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-24 | 2024-11-25 | 2025-04-08 | IOU Designed & Installed | N/A | No | N/A | 602.92 | -12.12 | Unknown | Unknown | Unknown | 615.04 | Unknown | 1714.97 | 602.92 | 1112.05 | Yes | N/A | N/A | 2024-10-24 | 2024-09-27 | Unknown | Unknown | 2024-09-27 | 2024-11-25 | 60 | 42 | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-04-08 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-30 | 1900-01-22 | 17 | 2025-04-30 | 2025-04-30 | 1 | 1 | 135 | 97 | 84 | 60 | 219 | 157 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-22 | -285 | -204 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-30 | 2024-07-02 | 2024-07-05 | IOU Designed & Installed | N/A | No | N/A | 233.23 | -6.73 | Unknown | Unknown | Unknown | 239.96 | Unknown | 571.46 | 233.23 | 338.23 | Yes | N/A | N/A | 2024-06-30 | 2024-06-30 | 1 | 0 | 2024-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-05 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | 2024-07-11 | 1900-01-06 | 5 | 2024-07-11 | 2024-07-11 | 1 | 1 | 5 | 4 | 8 | 6 | 13 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-05 | -450 | -323 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-08-26 | 2023-09-11 | IOU Designed & Installed | N/A | No | N/A | -5.28 | -10.26 | Unknown | Unknown | Unknown | 4.98 | 3981 | 1149.04 | -5.28 | 1154.32 | Yes | N/A | N/A | 2023-06-19 | 2023-08-26 | 69 | 50 | 2023-08-26 | 2023-08-26 | 1 | 0 | 2023-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-26 | 2023-09-11 | 17 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-12-11 | 1900-04-01 | 66 | 2023-12-11 | 2023-12-11 | 1 | 1 | 86 | 61 | 94 | 67 | 180 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-26 | -549 | -394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-07-29 | 2024-08-20 | IOU Designed & Installed | N/A | No | N/A | 78.79 | -0.94 | Unknown | Unknown | Unknown | 79.73 | 3981 | 1539.95 | 78.79 | 1461.16 | Yes | N/A | N/A | 2024-04-03 | 2024-07-29 | 118 | 84 | 2024-07-29 | 2024-07-29 | 1 | 1 | 2024-07-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-20 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-08-27 | 1900-01-07 | 6 | 2024-08-27 | 2024-08-26 | Unknown | Unknown | 141 | 101 | 9 | 7 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 56 | 41 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-09 | 2023-07-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 282.53 | Unknown | Unknown | Yes | N/A | N/A | 2023-02-08 | 2023-02-13 | 6 | 4 | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | Unknown | Unknown | Unknown | 2023-07-10 | Unknown | Unknown | 2023-07-12 | 2023-07-21 | 1900-01-09 | 8 | 2023-07-21 | 2023-07-27 | 7 | 5 | 6 | 4 | 17 | 13 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-25 | -650 | -465 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-14 | 2025-06-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1944.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-10 | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-04-14 | 8 | 6 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | 2025-06-12 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-06-13 | 1900-01-01 | 2 | 2025-06-13 | 2025-06-13 | 1 | 1 | 60 | 44 | 11 | 9 | 71 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-17 | -244 | -175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2024-04-17 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 50.4 | Unknown | Unknown | Unknown | Unknown | 50.4 | 0 | 1180.62 | 50.4 | 1130.22 | Yes | N/A | N/A | 2023-12-05 | 2023-07-28 | Unknown | Unknown | 2023-07-28 | 2024-04-16 | 264 | 188 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-10-24 | 191 | 137 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-15 | 1900-01-22 | 17 | 2024-11-15 | 2024-11-15 | 1 | 1 | 191 | 137 | 288 | 206 | 479 | 343 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-30 | 283 | 203 | No | 2024-12-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | Yes | 20 | -958.65 | -0.94 | Unknown | Unknown | -1140 | 182.29 | Unknown | 2397.26 | -958.65 | 3355.91 | Yes | N/A | N/A | 2024-12-18 | 2025-01-28 | 42 | 30 | 2025-01-28 | 2025-02-11 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2025-01-22 | 34 | 24 | 2025-02-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | 2025-04-09 | 2025-04-09 | 1 | 1 | 42 | 30 | 50 | 36 | 92 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-23 | -320 | -229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 13.22 | Unknown | Unknown | Unknown | Unknown | 13.22 | 3981 | 2273.86 | 13.22 | 2260.64 | Yes | N/A | N/A | 2024-04-02 | 2024-01-09 | Unknown | Unknown | 2024-01-09 | 2024-04-02 | 85 | 61 | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2025-01-27 | 301 | 215 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-02-06 | 1900-01-10 | 9 | 2025-02-06 | 2025-02-06 | 1 | 1 | 301 | 215 | 97 | 71 | 398 | 286 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-16 | -333 | -239 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | Unknown | 2024-09-04 | IOU Designed & Installed | N/A | No | N/A | 580.47 | -11.7 | Unknown | Unknown | Unknown | 592.17 | 3981 | 1686.98 | 580.47 | 1106.51 | Yes | N/A | N/A | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-03 | 8 | 6 | 2024-08-26 | 2024-09-04 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-09-17 | 1900-01-13 | 10 | 2024-09-17 | 2024-09-17 | 1 | 1 | 11 | 9 | 24 | 18 | 35 | 27 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-13 | -660 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-05 | 2025-03-05 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 3742.87 | 853.04 | Unknown | Unknown | Unknown | 2889.83 | Unknown | 1984.98 | 3742.87 | -1757.89 | Yes | N/A | N/A | 2025-03-05 | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-03-14 | 11 | 9 | 2025-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-03-18 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-04-24 | 1900-02-06 | 28 | 2025-04-24 | 2025-04-24 | 1 | 1 | 5 | 3 | 50 | 38 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-09 | 249 | 178 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-08 | 2023-05-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1018.17 | 1423.05 | Unknown | 446.8 | -3488 | 599.98 | 0 | 3487.84 | -1018.17 | 4506.01 | Yes | N/A | N/A | 2023-05-08 | 2023-05-09 | 2 | 2 | 2023-05-09 | 2023-05-30 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 2 | 2 | 23 | 17 | 25 | 19 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-09 | -72 | -52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-04 | 2023-01-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | -15.68 | -11.78 | Unknown | Unknown | 0.63 | -4.53 | 3981 | 1517.87 | -15.68 | 1533.55 | Yes | N/A | N/A | 2023-01-04 | 2023-02-01 | 29 | 21 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2023-09-28 | 1 | 1 | 29 | 21 | 1 | 1 | 30 | 22 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-22 | -118 | -85 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 281.71 | -17.4 | Unknown | Unknown | Unknown | 299.11 | Unknown | 994.94 | 281.71 | 713.23 | Yes | N/A | N/A | 2023-10-12 | 2023-11-02 | 22 | 16 | 2023-11-02 | 2023-12-20 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-01-08 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-01-25 | Unknown | Unknown | 42 | 30 | 49 | 35 | 91 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-26 | -280 | -201 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-16 | 2023-07-15 | IOU Designed & Installed | N/A | No | N/A | 300.7 | 774.75 | Unknown | 367.43 | -1324 | 482.52 | Unknown | 1324.36 | 300.7 | 1023.66 | Yes | N/A | N/A | 2023-05-10 | 2023-05-16 | 7 | 5 | 2023-05-16 | 2023-07-14 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-15 | 2023-07-21 | 1900-01-06 | 5 | 2023-07-21 | 2023-07-21 | 1 | 1 | 7 | 5 | 68 | 50 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 7.35 | 7.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-09 | -555 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-11-21 | 2024-12-11 | IOU Designed & Installed | N/A | No | N/A | 13.03 | Unknown | Unknown | Unknown | Unknown | 13.03 | Unknown | 1680.62 | 13.03 | 1667.59 | Yes | N/A | N/A | 2024-10-15 | 2024-11-26 | 43 | 31 | 2024-11-26 | 2024-11-27 | 2 | 2 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2024-12-11 | Unknown | Unknown | Unknown | 2025-01-17 | Unknown | Unknown | 2024-12-11 | 2025-01-31 | 1900-02-20 | 38 | 2025-01-31 | 2025-01-31 | 1 | 1 | 43 | 31 | 55 | 41 | 98 | 72 | Steps 2,3,5,6,7 | 37 | 27 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 566.05 | 566.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-23 | -59 | -42 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 22.86 | Unknown | Unknown | Unknown | Unknown | 22.86 | 7962 | 863.27 | 22.86 | 840.41 | Yes | N/A | N/A | 2024-05-08 | 2024-05-13 | 6 | 4 | 2024-05-13 | 2024-06-20 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2024-06-10 | 34 | 24 | 2024-06-20 | 2024-09-25 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-07-29 | 1900-01-04 | 3 | 2024-07-29 | 2024-07-26 | Unknown | Unknown | 104 | 74 | 78 | 56 | 182 | 130 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | Rancho Santa Fe | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-07 | -345 | -246 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-21 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | -941.75 | 1287.3 | Unknown | 138.59 | -2965 | 597.36 | Unknown | 2965.43 | -941.75 | 3907.18 | Yes | N/A | N/A | 2023-07-18 | 2023-07-18 | 1 | 1 | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-07-28 | 1900-01-01 | 2 | 2023-07-28 | 2023-07-28 | 1 | 1 | 1 | 1 | 3 | 3 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-03 | 567 | 406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2024-01-02 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | 58092.99 | 6636.55 | Unknown | Unknown | 100.09 | 51356.35 | 1217165 | 75242.98 | 58092.99 | 17149.99 | Yes | N/A | N/A | 2023-05-22 | 2023-10-30 | 162 | 116 | 2023-10-30 | 2024-04-15 | 169 | 121 | 2023-11-09 | 2024-01-02 | 55 | 39 | 2024-04-15 | 2024-04-19 | 5 | 5 | 2024-04-15 | 2025-01-21 | 282 | 202 | 2024-04-24 | 2025-01-24 | 276 | 198 | 2025-02-05 | 2025-02-24 | 1900-01-19 | 14 | 2025-02-24 | 2025-02-20 | Unknown | Unknown | 499 | 357 | 470 | 338 | 969 | 695 | Steps 2,3,5,6,7 | 434 | 310 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-22 | -596 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-03-07 | 2025-05-23 | IOU Designed & Installed | N/A | No | N/A | 1511.33 | Unknown | Unknown | Unknown | Unknown | 1511.33 | 3981 | 1236.71 | 1511.33 | -274.62 | Yes | N/A | N/A | 2025-02-19 | 2025-03-06 | 16 | 12 | 2025-03-06 | 2025-03-07 | 2 | 2 | 2025-03-07 | 2025-03-07 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | 2025-05-23 | 78 | 56 | Unknown | 2025-05-21 | Unknown | Unknown | 2025-05-23 | 2025-06-05 | 1900-01-13 | 10 | 2025-06-05 | 2025-06-05 | 1 | 1 | 95 | 69 | 17 | 13 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-11 | -619 | -444 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-26 | 2024-03-08 | IOU Designed & Installed | N/A | No | N/A | -5.68 | -4.61 | Unknown | Unknown | Unknown | -1.07 | 3981 | 855.22 | -5.68 | 860.9 | Yes | N/A | N/A | 2024-02-07 | 2023-12-20 | Unknown | Unknown | 2023-12-20 | 2024-02-26 | 69 | 49 | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-03-08 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-04-01 | 1900-01-24 | 17 | 2024-04-01 | 2024-04-01 | 1 | 1 | 12 | 10 | 95 | 67 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | -417 | -300 | No | 2024-03-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-12 | 2024-07-10 | IOU Designed & Installed | N/A | Yes | 3 | 714.41 | -6.39 | Unknown | Unknown | 141.41 | 579.39 | 3981 | 732.63 | 714.41 | 18.22 | Yes | N/A | N/A | 2024-03-11 | 2024-03-25 | 15 | 11 | 2024-03-25 | 2024-03-26 | 2 | 2 | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-07-10 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2025-05-12 | 1900-11-02 | 219 | 2025-05-12 | 2024-11-25 | Unknown | Unknown | 135 | 97 | 309 | 221 | 444 | 318 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 54.4 | 54.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-26 | -621 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 477.23 | Unknown | Unknown | Unknown | 2.99 | 474.24 | 3981 | 2626.25 | 477.23 | 2149.02 | Yes | N/A | N/A | 2024-10-30 | 2024-11-06 | 8 | 6 | 2024-11-06 | 2024-11-07 | 2 | 2 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | Unknown | 2025-01-13 | Unknown | Unknown | 2025-01-13 | 2025-01-13 | 1 | 1 | 8 | 6 | 3 | 3 | 11 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-15 | -518 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | 2023-11-14 | IOU Designed & Installed | N/A | No | N/A | 415.48 | -11.85 | Unknown | Unknown | 7.38 | 419.95 | 3981 | 591.49 | 415.48 | 176.01 | Yes | N/A | N/A | 2023-10-17 | 2023-10-21 | 5 | 4 | 2023-10-21 | 2023-10-21 | 1 | 0 | 2023-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-21 | 2023-11-14 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2024-03-15 | 1900-05-02 | 89 | 2024-03-15 | 2024-03-15 | 1 | 1 | 30 | 21 | 125 | 90 | 155 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | 70.1 | 70.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | 348 | 249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-22 | 2023-11-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 496.22 | Unknown | Unknown | Unknown | Unknown | 496.22 | 3981 | 734.46 | 496.22 | 238.24 | Yes | N/A | N/A | 2023-11-22 | 2023-11-20 | Unknown | Unknown | 2023-11-20 | 2023-11-22 | 3 | 3 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-11-12 | 1 | 1 | 0 | 0 | 4 | 4 | 4 | 4 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 9.6 | 9.6 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | -274 | -196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-29 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | 463.68 | Unknown | Unknown | Unknown | 6.44 | 457.24 | Unknown | 1331.86 | 463.68 | 868.18 | Yes | N/A | N/A | 2025-01-23 | 2025-01-21 | Unknown | Unknown | 2025-01-21 | 2025-02-13 | 24 | 18 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-02-19 | 6 | 4 | Unknown | 2025-03-11 | Unknown | Unknown | 2025-02-19 | 2025-04-11 | 1900-02-20 | 38 | 2025-04-11 | 2025-04-11 | 1 | 1 | 6 | 4 | 77 | 57 | 83 | 61 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 64 | 46 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-17 | 2023-05-05 | 2023-11-27 | IOU Designed & Installed | N/A | No | N/A | 3339.82 | Unknown | Unknown | Unknown | Unknown | 3339.82 | Unknown | 1867.41 | 3339.82 | -1472.41 | Yes | N/A | N/A | 2022-11-17 | 2023-05-05 | 170 | 122 | 2023-05-05 | 2023-11-15 | 195 | 139 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2023-12-18 | 1900-01-21 | 16 | 2023-12-18 | 2023-12-18 | 1 | 1 | 170 | 122 | 218 | 156 | 388 | 278 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | -352 | -252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-06 | 2024-09-10 | 2025-01-09 | IOU Designed & Installed | N/A | No | N/A | 5188.56 | 81.79 | Unknown | Unknown | -5310 | 10416.77 | 1826 | 5636.09 | 5188.56 | 447.53 | Yes | N/A | N/A | 2024-09-06 | 2024-09-10 | 5 | 3 | 2024-09-10 | 2024-12-06 | 88 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-11-27 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-02-13 | 1900-02-04 | 26 | 2025-02-13 | 2025-02-13 | 1 | 1 | 5 | 3 | 132 | 96 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 95.05 | 95.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-07 | 61 | 44 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-07 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 21697.88 | 1065.57 | Unknown | 21.99 | -4374.11 | 24984.43 | 0 | 4437.05 | 21697.88 | -17260.83 | Yes | N/A | N/A | 2024-05-01 | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2025-02-06 | 310 | 222 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-04-09 | 1900-02-17 | 35 | 2025-04-09 | 2025-04-09 | 1 | 1 | 0 | 0 | 360 | 258 | 360 | 258 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -568 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2023-05-24 | 2023-08-01 | IOU Designed & Installed | N/A | No | N/A | 1124.74 | 431.31 | Unknown | Unknown | Unknown | 693.43 | 3981 | 925 | 1124.74 | -199.74 | Yes | N/A | N/A | 2023-05-22 | 2023-05-24 | 3 | 3 | 2023-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-24 | 2023-08-01 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-08-10 | 1900-01-09 | 8 | 2023-08-10 | 2023-08-10 | 1 | 1 | 73 | 53 | 11 | 9 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-22 | 145 | 105 | No | 2023-11-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-07 | 2025-02-10 | IOU Designed & Installed | N/A | Yes | 373 | 3730.14 | 391.96 | Unknown | 50.09 | 41.96 | 3246.13 | 3981 | 922.94 | 3730.14 | -2807.2 | Yes | N/A | N/A | 2023-11-07 | 2024-11-14 | 374 | 268 | 2024-11-14 | 2023-12-04 | Unknown | Unknown | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2025-07-28 | 603 | 431 | Unknown | 2025-02-05 | Unknown | Unknown | 2025-07-28 | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-02-14 | 1 | 1 | 977 | 699 | 1 | 1 | 978 | 700 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | Applicant Design | Commercial | N/A | Del Mar | DEL MAR | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-24 | 132 | 95 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2024-08-12 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 90690.31 | 6442.53 | Unknown | Unknown | 583.61 | 83664.17 | 138678 | 27686.64 | 90690.31 | -63003.67 | Yes | N/A | N/A | 2023-02-14 | 2023-09-22 | 221 | 159 | 2023-09-22 | 2024-03-20 | 181 | 129 | 2023-09-25 | 2024-01-31 | 103 | 71 | 2023-10-03 | 2024-09-03 | 84 | 62 | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-10-03 | 1900-02-21 | 39 | 2024-10-03 | 2024-10-03 | 1 | 1 | 324 | 230 | 319 | 231 | 643 | 461 | Steps 2,3,5,6,7 | 464 | 332 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 36.05 | 36.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-05-15 | 2024-07-24 | IOU Designed & Installed | N/A | No | N/A | 2.94 | Unknown | Unknown | Unknown | Unknown | 2.94 | Unknown | 529.2 | 2.94 | 526.26 | Yes | N/A | N/A | 2024-04-25 | 2024-05-15 | 21 | 15 | 2024-05-15 | 2024-05-15 | 1 | 1 | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | 2024-07-24 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-08-01 | 1900-01-08 | 7 | 2024-08-01 | 2024-08-01 | 1 | 1 | 92 | 66 | 11 | 9 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LADERA RANCH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-18 | -346 | -249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3363.3 | 1031.28 | Unknown | Unknown | Unknown | 2332.02 | Unknown | 449.58 | 3363.3 | -2913.72 | Yes | N/A | N/A | 2024-07-29 | 2024-07-30 | 2 | 2 | 2024-07-30 | 2024-07-30 | 1 | 1 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | 2024-08-06 | 2024-08-06 | 1 | 1 | 2 | 2 | 2 | 2 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 119.4 | 119.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-09 | -535 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-08 | 2024-10-30 | IOU Designed & Installed | N/A | No | N/A | 1192 | Unknown | Unknown | Unknown | 5.42 | 1186.58 | 3981 | 1106.45 | 1192 | -85.55 | Yes | N/A | N/A | 2024-08-05 | 2024-09-04 | 31 | 23 | 2024-09-04 | 2024-09-04 | 1 | 1 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-10-30 | 57 | 41 | Unknown | 2024-10-29 | Unknown | Unknown | 2024-10-30 | 2024-11-20 | 1900-01-21 | 16 | 2024-11-20 | 2024-11-20 | 1 | 1 | 88 | 64 | 24 | 18 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | -333 | -239 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-16 | 2024-11-13 | IOU Designed & Installed | N/A | No | N/A | 931.38 | 253.74 | Unknown | Unknown | Unknown | 677.64 | 3981 | 853.76 | 931.38 | -77.62 | Yes | N/A | N/A | 2024-02-16 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | 2024-02-16 | 92 | 66 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-11-13 | 272 | 194 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2024-12-10 | 1900-01-27 | 20 | 2024-12-10 | 2024-12-10 | 1 | 1 | 272 | 194 | 121 | 87 | 393 | 281 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-08 | -34 | -25 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-10-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3313.12 | 897.68 | Unknown | 607.44 | 84.22 | 1723.78 | 3981 | 1069.18 | 3313.12 | -2243.94 | Yes | N/A | N/A | 2023-10-30 | 2023-12-13 | 45 | 33 | 2023-12-13 | 2023-12-19 | 7 | 5 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | Unknown | Unknown | Unknown | 2024-08-05 | Unknown | Unknown | 2024-08-05 | 2024-08-05 | 1 | 1 | 45 | 33 | 8 | 6 | 53 | 39 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | SAN DIEGO | 180 | 180 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-11 | -200 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1004.07 | -18.79 | Unknown | Unknown | Unknown | 1022.86 | 3981 | 800.33 | 1004.07 | -203.74 | Yes | N/A | N/A | 2024-03-20 | 2024-01-31 | Unknown | Unknown | 2024-01-31 | 2024-03-28 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2025-01-13 | 25 | 19 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-03-25 | 1 | 1 | 0 | 0 | 84 | 62 | 84 | 62 | Steps 2,3,5,6,7 | 291 | 207 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | 24 | 18 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-27 | 2024-12-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 423.98 | -1.83 | Unknown | Unknown | Unknown | 425.81 | Unknown | 499.14 | 423.98 | 75.16 | Yes | N/A | N/A | 2024-11-27 | 2024-12-03 | 7 | 5 | 2024-12-03 | 2025-02-18 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-05 | 1 | 1 | 7 | 5 | 79 | 57 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | -603 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2025-01-13 | 2025-02-04 | IOU Designed & Installed | N/A | No | N/A | 1366.46 | -27.49 | Unknown | Unknown | Unknown | 1393.95 | 3981 | 1956 | 1366.46 | 589.54 | Yes | N/A | N/A | 2024-12-19 | 2024-12-10 | Unknown | Unknown | 2024-12-10 | 2025-01-13 | 35 | 25 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-02-04 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-03-26 | 1900-02-19 | 37 | 2025-03-26 | 2025-03-26 | 1 | 1 | 23 | 17 | 87 | 63 | 110 | 80 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-01 | -559 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 418.73 | Unknown | Unknown | Unknown | 17.07 | 401.66 | 3981 | 676.79 | 418.73 | 258.06 | Yes | N/A | N/A | 2024-11-19 | 2024-11-20 | 2 | 2 | 2024-11-20 | 2024-11-27 | 8 | 6 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | Unknown | Unknown | Unknown | 2025-04-21 | Unknown | Unknown | 2025-04-21 | 2025-04-21 | 1 | 1 | 2 | 2 | 9 | 7 | 11 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-17 | -226 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | 2023-06-23 | IOU Designed & Installed | N/A | No | N/A | -2.24 | -6.65 | Unknown | Unknown | Unknown | 4.41 | Unknown | 642.58 | -2.24 | 644.82 | Yes | N/A | N/A | 2023-03-23 | 2023-03-23 | 1 | 1 | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | 2023-06-23 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-07-06 | 1900-01-13 | 10 | 2023-07-06 | 2023-07-06 | 1 | 1 | 94 | 68 | 15 | 11 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | -137 | -98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-10-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 253.84 | -5.1 | Unknown | Unknown | Unknown | 258.94 | Unknown | 1451.5 | 253.84 | 1197.66 | Yes | N/A | N/A | 2024-09-10 | 2024-10-07 | 28 | 20 | 2024-10-07 | 2025-02-05 | 122 | 88 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-01-10 | 47 | 35 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-03-26 | 1 | 1 | 28 | 20 | 170 | 124 | 198 | 144 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-07 | -389 | -278 | No | 2023-11-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-07 | 2023-12-12 | IOU Designed & Installed | N/A | Yes | 77 | 967.93 | -22.18 | Unknown | Unknown | Unknown | 990.11 | Unknown | 1052.52 | 967.93 | 84.59 | Yes | N/A | N/A | 2023-11-07 | 2024-01-23 | 78 | 56 | 2024-01-23 | 2023-11-07 | Unknown | Unknown | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-07 | 2023-12-12 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2024-03-14 | 1900-04-03 | 68 | 2024-03-14 | 2024-03-14 | 1 | 1 | 114 | 82 | 95 | 69 | 209 | 151 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | -525 | -376 | No | 2024-09-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-04 | 2025-02-07 | IOU Designed & Installed | N/A | Yes | 148 | -1011.53 | Unknown | Unknown | Unknown | -1135 | 123.47 | 3941 | 2353.68 | -1011.53 | 3365.21 | Yes | N/A | N/A | 2024-09-04 | 2025-01-30 | 149 | 107 | 2025-01-30 | 2024-09-04 | Unknown | Unknown | 2024-09-04 | 2025-02-06 | 156 | 112 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-07 | 2 | 2 | Unknown | 2025-02-06 | Unknown | Unknown | 2025-02-07 | 2025-02-14 | 1900-01-07 | 6 | 2025-02-14 | 2025-02-14 | 1 | 1 | 307 | 221 | 9 | 7 | 316 | 228 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-17 | -577 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-23 | 2023-09-21 | 2023-10-09 | IOU Designed & Installed | N/A | No | N/A | 21.39 | -7.4 | Unknown | Unknown | Unknown | 28.79 | Unknown | 973.99 | 21.39 | 952.6 | Yes | N/A | N/A | 2023-08-23 | 2023-06-06 | Unknown | Unknown | 2023-06-06 | 2023-09-21 | 108 | 78 | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2023-10-09 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2024-01-30 | 1900-04-23 | 82 | 2024-01-30 | 2023-10-18 | Unknown | Unknown | 19 | 13 | 222 | 160 | 241 | 173 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 18.75 | 18.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-14 | -521 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-09 | 2024-07-09 | 2024-12-30 | IOU Designed & Installed | N/A | No | N/A | 1927.43 | -1.26 | Unknown | Unknown | 4.64 | 1924.05 | 3981 | 1376.75 | 1927.43 | -550.68 | Yes | N/A | N/A | 2024-07-09 | 2024-07-15 | 7 | 5 | 2024-07-15 | 2024-07-16 | 2 | 2 | 2024-07-16 | 2024-11-15 | 123 | 89 | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2024-12-30 | 60 | 42 | Unknown | 2024-12-18 | Unknown | Unknown | 2024-12-30 | 2025-01-09 | 1900-01-10 | 9 | 2025-01-09 | 2025-01-09 | 1 | 1 | 190 | 136 | 14 | 12 | 204 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-23 | 236 | 169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-08-31 | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 2472.28 | Unknown | Unknown | Unknown | -2035 | 4507.28 | 0 | 1112.48 | 2472.28 | -1359.8 | Yes | N/A | N/A | 2023-08-31 | 2023-10-02 | 33 | 23 | 2023-10-02 | 2023-11-08 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2023-10-11 | 10 | 8 | 2023-11-08 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | Unknown | Unknown | 2024-09-09 | 2024-10-16 | 1900-02-06 | 28 | 2024-10-16 | 2024-10-16 | 1 | 1 | 33 | 23 | 87 | 65 | 120 | 88 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 403.05 | 403.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | -512 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-02-06 | 2025-05-30 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1101.17 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-09 | 2025-01-31 | 23 | 17 | 2025-01-31 | 2025-02-06 | 7 | 5 | 2025-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-05-30 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-05 | 1900-01-06 | 5 | 2025-06-05 | 2025-06-05 | 1 | 1 | 137 | 99 | 15 | 11 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-31 | -169 | -122 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-18 | 2022-11-18 | 2023-05-09 | IOU Designed & Installed | N/A | No | N/A | 2773.26 | 534.8 | Unknown | 201.07 | Unknown | 2037.39 | 3981 | 1206.08 | 2773.26 | -1567.18 | Yes | N/A | N/A | 2022-11-18 | 2023-02-27 | 102 | 72 | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-27 | 2023-05-09 | 72 | 52 | Unknown | 2023-05-08 | Unknown | Unknown | 2023-05-09 | 2023-05-15 | 1900-01-06 | 5 | 2023-05-15 | 2023-05-15 | 1 | 1 | 174 | 124 | 8 | 6 | 182 | 130 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | 140 | 140 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -396 | -283 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-06-08 | 2024-02-23 | IOU Designed & Installed | N/A | No | N/A | 498.94 | -3.75 | Unknown | Unknown | 11.83 | 490.86 | 3981 | 775.5 | 498.94 | 276.56 | Yes | N/A | N/A | 2023-06-08 | 2023-06-08 | 1 | 1 | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | 2024-02-23 | 261 | 187 | Unknown | 2024-02-28 | Unknown | Unknown | 2024-02-23 | 2024-03-01 | 1900-01-07 | 6 | 2024-03-01 | 2024-03-01 | 1 | 1 | 262 | 188 | 9 | 7 | 271 | 195 | Steps 2,3,5,6,7 | 5 | 3 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-07 | -166 | -120 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | -1646.68 | 1832.01 | Unknown | 306.64 | -4613 | 827.67 | Unknown | 4613.18 | -1646.68 | 6259.86 | Yes | N/A | N/A | 2024-01-24 | 2024-01-24 | 1 | 1 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-03-25 | 1899-12-31 | 1 | 2024-03-25 | 2024-03-25 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | Carlsbad | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-16 | -209 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | 2024-03-07 | IOU Designed & Installed | N/A | No | N/A | -1743.71 | 1883.88 | Unknown | 135.15 | -4613 | 850.26 | Unknown | 4613.18 | -1743.71 | 6356.89 | Yes | N/A | N/A | 2024-01-24 | 2024-01-23 | Unknown | Unknown | 2024-01-23 | 2024-06-21 | 151 | 109 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | Unknown | Unknown | Unknown | 2024-06-21 | 2024-06-21 | 1 | 1 | 2024-03-07 | 2024-06-21 | 1900-04-16 | 77 | 2024-06-21 | 2024-06-21 | 1 | 1 | 0 | 0 | 260 | 188 | 260 | 188 | Steps 2,3,5,6,7 | 106 | 76 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-04 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-08 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 7.46 | Unknown | Unknown | Unknown | Unknown | 7.46 | Unknown | 1634.63 | 7.46 | 1627.17 | Yes | N/A | N/A | 2024-08-06 | 2024-08-15 | 10 | 8 | 2024-08-15 | 2024-09-27 | 44 | 32 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2025-02-03 | 130 | 92 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-25 | 1900-01-22 | 17 | 2025-02-25 | 2025-02-25 | 1 | 1 | 140 | 100 | 68 | 50 | 208 | 150 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-08 | -439 | -314 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-02-26 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 16803.5 | 2499.46 | Unknown | 397.52 | 772.7 | 13133.82 | 3981 | 482.43 | 16803.5 | -16321.07 | Yes | N/A | N/A | 2024-02-26 | 2024-02-12 | Unknown | Unknown | 2024-02-12 | 2024-04-11 | 60 | 44 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-11-15 | 219 | 157 | Unknown | 2024-11-08 | Unknown | Unknown | 2024-11-15 | 2024-11-27 | 1900-01-12 | 9 | 2024-11-27 | 2024-11-26 | Unknown | Unknown | 219 | 157 | 73 | 53 | 292 | 210 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-30 | -396 | -283 | No | 2024-08-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-07 | 2025-04-30 | IOU Designed & Installed | N/A | Yes | 91 | 1432.47 | Unknown | Unknown | Unknown | 58.88 | 1373.59 | Unknown | 1521.96 | 1432.47 | 89.49 | Yes | N/A | N/A | 2024-08-07 | 2024-11-05 | 91 | 65 | 2024-11-05 | 2024-11-06 | 2 | 2 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2025-04-30 | 189 | 135 | Unknown | 2025-01-21 | Unknown | Unknown | 2025-04-30 | 2025-05-30 | 1900-01-30 | 23 | 2025-05-30 | 2025-05-30 | 1 | 1 | 280 | 200 | 34 | 26 | 314 | 226 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | 112 | 81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | 2025-03-11 | IOU Designed & Installed | N/A | No | N/A | 2730.65 | 735.15 | Unknown | Unknown | Unknown | 1995.5 | 3981 | 2057.45 | 2730.65 | -673.2 | Yes | N/A | N/A | 2024-12-11 | 2025-01-27 | 48 | 34 | 2025-01-27 | 2025-02-10 | 15 | 11 | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-03-11 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-03-21 | 1900-01-10 | 9 | 2025-03-21 | 2025-03-21 | 1 | 1 | 78 | 56 | 27 | 21 | 105 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | -742 | -531 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-10 | 2025-03-14 | IOU Designed & Installed | N/A | No | N/A | 996.43 | 253.74 | Unknown | Unknown | Unknown | 742.69 | Unknown | 1395.56 | 996.43 | 399.13 | Yes | N/A | N/A | 2025-03-10 | 2025-03-10 | 1 | 1 | 2025-03-10 | 2025-03-10 | 1 | 1 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-03-14 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-03-14 | 1899-12-31 | 1 | 2025-03-14 | 2025-03-14 | 1 | 1 | 6 | 6 | 3 | 3 | 9 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 98.1 | 98.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-08 | -54 | -40 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1023.76 | -11.82 | Unknown | Unknown | -1632 | 620.06 | Unknown | Not available | -1023.76 | Unknown | Yes | N/A | N/A | 2024-05-08 | 2024-03-07 | Unknown | Unknown | 2024-03-07 | 2024-08-23 | 170 | 122 | 2024-08-23 | 2024-11-22 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | Unknown | Unknown | 2024-12-18 | 2024-12-16 | Unknown | Unknown | 92 | 66 | 170 | 122 | 262 | 188 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-10 | 130 | 94 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 616.45 | -12.39 | Unknown | Unknown | Unknown | 628.84 | 3981 | 937.79 | 616.45 | 321.34 | Yes | N/A | N/A | 2024-12-05 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | 2024-12-13 | 310 | 222 | 2024-12-12 | 2024-12-18 | 7 | 5 | 2024-12-11 | 2024-12-30 | 15 | 11 | 2024-12-13 | 2025-02-25 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | Unknown | Unknown | 2025-03-21 | 2025-03-20 | Unknown | Unknown | 82 | 58 | 325 | 233 | 407 | 291 | Steps 2,3,5,6,7 | 25 | 17 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-23 | -591 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-26 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | 1370.71 | -7.16 | Unknown | Unknown | 21.77 | 1356.1 | Unknown | 1590.23 | 1370.71 | 219.52 | Yes | N/A | N/A | 2025-02-25 | 2025-02-06 | Unknown | Unknown | 2025-02-06 | 2025-02-26 | 21 | 15 | 2025-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-06-03 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-11 | 1900-01-08 | 7 | 2025-06-11 | 2025-06-11 | 1 | 1 | 98 | 70 | 31 | 23 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | El Cajon | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | -117 | -84 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-05-31 | 2023-08-24 | IOU Designed & Installed | N/A | No | N/A | 3063.42 | -40.21 | Unknown | Unknown | -1552 | 4655.63 | Unknown | 1551.81 | 3063.42 | -1511.61 | Yes | N/A | N/A | 2023-05-31 | 2023-05-26 | Unknown | Unknown | 2023-05-26 | 2023-08-23 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2023-08-16 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | 2023-09-06 | 1900-01-13 | 10 | 2023-09-06 | 2023-09-06 | 1 | 1 | 0 | 0 | 108 | 78 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-14 | -609 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-02-21 | 2024-02-27 | IOU Designed & Installed | N/A | No | N/A | -12.14 | -9.85 | Unknown | Unknown | Unknown | -2.29 | 3981 | 501.14 | -12.14 | 513.28 | Yes | N/A | N/A | 2024-01-24 | 2023-11-29 | Unknown | Unknown | 2023-11-29 | 2024-02-21 | 85 | 61 | 2024-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-02-27 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-15 | 1900-01-17 | 14 | 2024-03-15 | 2024-03-15 | 1 | 1 | 7 | 5 | 104 | 76 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-31 | -318 | -229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | 2024-11-25 | IOU Designed & Installed | N/A | No | N/A | 1684.43 | 821.47 | Unknown | Unknown | Unknown | 862.96 | 3981 | 1981.47 | 1684.43 | 297.04 | Yes | N/A | N/A | 2024-11-05 | 2024-10-16 | Unknown | Unknown | 2024-10-16 | 2024-11-05 | 21 | 15 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2024-11-25 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-17 | 1900-01-22 | 17 | 2024-12-17 | 2024-12-17 | 1 | 1 | 21 | 15 | 45 | 33 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | -166 | -119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | 2023-07-18 | IOU Designed & Installed | N/A | No | N/A | 463.09 | -14.03 | Unknown | Unknown | Unknown | 477.12 | Unknown | 635.81 | 463.09 | 172.72 | Yes | N/A | N/A | 2023-03-23 | 2023-03-23 | 1 | 1 | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | 2023-07-18 | 118 | 84 | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-07-18 | 1899-12-31 | 1 | 2023-07-18 | 2023-07-18 | 1 | 1 | 119 | 85 | 2 | 2 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-03 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | 2024-08-29 | IOU Designed & Installed | N/A | No | N/A | -1558.62 | Unknown | Unknown | Unknown | -1622 | 63.38 | Unknown | 1498.25 | -1558.62 | 3056.87 | Yes | N/A | N/A | 2024-08-20 | 2024-08-20 | 1 | 1 | 2024-08-20 | 2024-08-20 | 1 | 1 | 2024-08-20 | 2024-08-27 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-08-29 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-09-06 | 1900-01-08 | 7 | 2024-09-06 | 2024-09-05 | Unknown | Unknown | 12 | 10 | 10 | 8 | 22 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-02 | -479 | -342 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-23 | 2025-04-02 | IOU Designed & Installed | N/A | No | N/A | 14761.6 | 3278.25 | Unknown | 264.46 | 70.44 | 11148.45 | 3981 | 1158.77 | 14761.6 | -13602.83 | Yes | N/A | N/A | 2024-09-10 | 2024-09-18 | 9 | 7 | 2024-09-18 | 2024-10-08 | 21 | 15 | 2024-10-08 | Unknown | Unknown | Unknown | 2024-10-09 | 2024-11-06 | 29 | 21 | 2024-10-08 | 2025-04-02 | 177 | 127 | Unknown | 2025-03-17 | Unknown | Unknown | 2025-04-02 | 2025-04-10 | 1900-01-08 | 7 | 2025-04-10 | 2025-04-10 | 1 | 1 | 186 | 134 | 60 | 44 | 246 | 178 | Steps 2,3,5,6,7 | 29 | 21 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | -627 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-12 | 2024-09-27 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 21.36 | Unknown | Unknown | Unknown | Unknown | 21.36 | 3981 | 1577.5 | 21.36 | 1556.14 | Yes | N/A | N/A | 2024-08-12 | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2024-09-27 | 58 | 42 | 2024-09-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-10-28 | 32 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-04 | 1900-01-07 | 6 | 2024-11-04 | 2024-11-04 | 1 | 1 | 32 | 22 | 67 | 49 | 99 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-04 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-21 | 2024-03-01 | 2024-03-19 | IOU Designed & Installed | N/A | No | N/A | -13.28 | -10.78 | Unknown | Unknown | Unknown | -2.5 | 3981 | 977.8 | -13.28 | 991.08 | Yes | N/A | N/A | 2024-02-21 | 2024-01-17 | Unknown | Unknown | 2024-01-17 | 2024-03-01 | 45 | 33 | 2024-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-03-19 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-04-08 | 1900-01-20 | 15 | 2024-04-08 | 2024-04-08 | 1 | 1 | 19 | 13 | 67 | 49 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-20 | -508 | -365 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-28 | 2023-09-28 | 2024-01-24 | IOU Designed & Installed | N/A | No | N/A | 13.74 | -17.38 | Unknown | Unknown | Unknown | 31.12 | 3981 | 908.03 | 13.74 | 894.29 | Yes | N/A | N/A | 2023-09-28 | 2023-07-03 | Unknown | Unknown | 2023-07-03 | 2023-10-23 | 113 | 81 | 2023-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2024-01-24 | 94 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-01-29 | 1900-01-05 | 4 | 2024-01-29 | 2024-01-29 | 1 | 1 | 94 | 68 | 120 | 86 | 214 | 154 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 61.05 | 61.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-25 | -700 | -501 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | 2024-01-18 | IOU Designed & Installed | N/A | No | N/A | 691.49 | 17.3 | Unknown | Unknown | 2.03 | 672.16 | 3981 | 717.17 | 691.49 | 25.68 | Yes | N/A | N/A | 2023-11-28 | 2023-12-15 | 18 | 14 | 2023-12-15 | 2023-12-20 | 6 | 4 | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-01-18 | 30 | 22 | Unknown | 2024-01-18 | Unknown | Unknown | 2024-01-18 | 2024-01-25 | 1900-01-07 | 6 | 2024-01-25 | 2024-01-25 | 1 | 1 | 48 | 36 | 15 | 11 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-21 | -362 | -259 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 113.84 | -1.25 | Unknown | Unknown | Unknown | 115.09 | 3981 | 1376.14 | 113.84 | 1262.3 | Yes | N/A | N/A | 2024-01-08 | 2024-01-17 | 10 | 8 | 2024-01-17 | 2024-02-22 | 37 | 27 | 2024-02-22 | Unknown | Unknown | Unknown | 2024-01-11 | 2024-02-16 | 37 | 27 | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | Unknown | Unknown | 2024-08-26 | 2024-08-24 | Unknown | Unknown | 10 | 8 | 74 | 54 | 84 | 62 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | -177 | -128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | -303.15 | -15.79 | Unknown | Unknown | -1146 | 858.64 | 0 | 1145.74 | -303.15 | 1448.89 | Yes | N/A | N/A | 2023-10-10 | 2024-02-13 | 127 | 91 | 2024-02-13 | 2024-09-16 | 217 | 155 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | Unknown | Unknown | 2025-01-15 | 2025-01-15 | 1 | 1 | 127 | 91 | 218 | 156 | 345 | 247 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | 41805 | 41805 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-12-27 | 89 | 64 | No | 2023-08-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-10-27 | 2024-03-05 | IOU Designed & Installed | N/A | Yes | 77 | 19605.56 | 252.81 | Unknown | Unknown | Unknown | 19352.75 | 600836 | 41684.81 | 19605.56 | 22079.25 | Yes | N/A | N/A | 2023-08-08 | 2023-10-24 | 78 | 56 | 2023-10-24 | 2023-12-04 | 42 | 30 | 2023-11-07 | Unknown | Unknown | Unknown | 2023-11-29 | 2023-11-30 | 2 | 2 | 2023-12-04 | 2024-02-29 | 88 | 64 | Unknown | 2024-03-08 | Unknown | Unknown | 2024-03-05 | 2024-03-27 | 1900-01-22 | 17 | 2024-03-27 | 2024-03-25 | Unknown | Unknown | 166 | 120 | 67 | 49 | 233 | 169 | Steps 2,3,5,6,7 | 30 | 22 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego PA9 PH2 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 771 | 552 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-07-05 | 2024-11-01 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 57874.41 | 2741.06 | Unknown | Unknown | 12182.42 | 42950.93 | 0 | 28359.46 | 57874.41 | -29514.95 | Yes | N/A | N/A | 2022-04-27 | 2023-02-15 | 295 | 211 | 2023-02-15 | 2023-06-08 | 114 | 82 | 2023-02-28 | 2024-04-08 | 398 | 284 | 2023-06-07 | 2023-08-03 | 58 | 42 | 2023-11-09 | Unknown | Unknown | Unknown | 2023-11-09 | 2024-11-01 | 359 | 257 | 2024-11-01 | 2025-04-29 | 1900-06-28 | 128 | 2025-04-29 | 2025-04-29 | 1 | 1 | 693 | 495 | 712 | 510 | 1405 | 1005 | Steps 2,3,5,6,7 | 406 | 290 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -413 | -296 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-10-11 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | 914.74 | Unknown | Unknown | Unknown | 6.36 | 908.38 | 3981 | 1334.71 | 914.74 | 419.97 | Yes | N/A | N/A | 2024-07-29 | 2024-10-11 | 75 | 55 | 2024-10-11 | 2024-10-11 | 1 | 1 | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2025-05-02 | 204 | 146 | Unknown | 2025-03-28 | Unknown | Unknown | 2025-05-02 | 2025-05-14 | 1900-01-12 | 9 | 2025-05-14 | 2025-05-14 | 1 | 1 | 279 | 201 | 15 | 11 | 294 | 212 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | -324 | -233 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-08-16 | 2023-10-31 | IOU Designed & Installed | N/A | No | N/A | -7.2 | -5.78 | Unknown | Unknown | Unknown | -1.42 | Unknown | 480.37 | -7.2 | 487.57 | Yes | N/A | N/A | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | 2023-08-16 | 1 | 1 | 2023-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-16 | 2023-10-31 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2024-04-09 | 1900-06-10 | 116 | 2024-04-09 | 2024-04-09 | 1 | 1 | 78 | 56 | 164 | 118 | 242 | 174 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 170.05 | 170.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-13 | -340 | -245 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | 2023-01-03 | 2023-10-05 | IOU Designed & Installed | N/A | No | N/A | 1007.29 | -10.57 | Unknown | Unknown | 37.39 | 980.47 | 3981 | 1144.2 | 1007.29 | 136.91 | Yes | N/A | N/A | 2023-01-03 | 2023-06-15 | 164 | 118 | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | 2023-10-05 | 113 | 81 | Unknown | 2023-10-05 | Unknown | Unknown | 2023-10-05 | 2023-10-09 | 1900-01-04 | 3 | 2023-10-09 | 2023-10-09 | 1 | 1 | 277 | 199 | 6 | 4 | 283 | 203 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 29.35 | 29.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-01 | -372 | -266 | No | 2023-10-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | 2024-02-13 | IOU Designed & Installed | N/A | Yes | 124 | 747.34 | -10.3 | Unknown | Unknown | 7.84 | 749.8 | Unknown | 763.53 | 747.34 | 16.19 | Yes | N/A | N/A | 2023-10-13 | 2024-02-13 | 124 | 88 | 2024-02-13 | 2024-02-14 | 2 | 2 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2024-02-13 | 75 | 53 | Unknown | 2024-02-08 | Unknown | Unknown | 2024-02-13 | 2024-02-23 | 1900-01-10 | 9 | 2024-02-23 | 2024-02-23 | 1 | 1 | 199 | 141 | 14 | 12 | 213 | 153 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-12 | 164 | 119 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2025-04-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 13490.06 | 3248.6 | Unknown | 249.01 | 0.32 | 9992.13 | 31441 | Not available | 13490.06 | Unknown | Yes | N/A | N/A | 2024-04-25 | 2024-03-26 | Unknown | Unknown | 2024-03-26 | 2024-04-30 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2025-03-27 | 332 | 238 | Unknown | 2025-04-14 | Unknown | Unknown | 2025-04-25 | 2025-04-25 | 1899-12-31 | 1 | 2025-04-25 | 2025-04-25 | 1 | 1 | 332 | 238 | 38 | 28 | 370 | 266 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 18 | 18 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-09 | 147 | 106 | No | 2022-09-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-12 | 2022-09-20 | Unknown | IOU Designed & Installed | N/A | Yes | 431 | 1225.73 | -28.28 | Unknown | Unknown | Unknown | 1254.01 | 3885 | 1119.76 | 1225.73 | -105.97 | Yes | N/A | N/A | 2022-09-12 | 2023-10-18 | 402 | 288 | 2023-10-18 | 2023-11-17 | 31 | 23 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | Unknown | Unknown | 2024-01-05 | 2024-01-03 | Unknown | Unknown | 402 | 288 | 31 | 23 | 433 | 311 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | -589 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-02 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 94.59 | -1.89 | Unknown | Unknown | Unknown | 96.48 | Unknown | 1244.35 | 94.59 | 1149.76 | Yes | N/A | N/A | 2025-01-02 | 2024-11-29 | Unknown | Unknown | 2024-11-29 | 2025-01-02 | 35 | 25 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-02-10 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-28 | 1900-01-18 | 15 | 2025-02-28 | 2025-02-28 | 1 | 1 | 40 | 28 | 55 | 41 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-07 | -592 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | 2025-01-06 | IOU Designed & Installed | N/A | No | N/A | 1490.29 | -18.5 | Unknown | Unknown | 14.6 | 1494.19 | 3981 | 1158.77 | 1490.29 | -331.52 | Yes | N/A | N/A | 2024-10-01 | 2024-09-11 | Unknown | Unknown | 2024-09-11 | 2024-10-08 | 28 | 20 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2025-01-06 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-01-23 | 1900-01-17 | 14 | 2025-01-23 | 2025-01-23 | 1 | 1 | 91 | 65 | 47 | 35 | 138 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-04-13 | 397 | 284 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 626.9 | -1.26 | Unknown | Unknown | -245.67 | 873.83 | 0 | 263.54 | 626.9 | -363.36 | Yes | N/A | N/A | 2023-06-21 | 2023-06-21 | 1 | 1 | 2023-06-21 | 2024-09-04 | 442 | 316 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2025-03-18 | 196 | 140 | Unknown | 2025-04-25 | Unknown | Unknown | Unknown | 2025-05-16 | Unknown | Unknown | 2025-05-16 | 2025-05-15 | Unknown | Unknown | 197 | 141 | 442 | 316 | 639 | 457 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | 504 | 504 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | -212 | -152 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-08-01 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | -3012.07 | 800.95 | Unknown | 212.58 | -6628 | 2602.4 | Unknown | 8910.47 | -3012.07 | 11922.54 | Yes | N/A | N/A | 2024-06-21 | 2024-06-21 | 1 | 1 | 2024-06-21 | 2024-10-25 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2024-10-26 | 2024-10-29 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-10-31 | 1900-01-03 | 4 | 2024-10-31 | 2024-10-31 | 1 | 1 | 1 | 1 | 136 | 98 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-18 | -96 | -69 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | 2025-03-14 | IOU Designed & Installed | N/A | No | N/A | 700.95 | 1436.52 | Unknown | 212.22 | -1940 | 992.21 | Unknown | 2871.49 | 700.95 | 2170.54 | Yes | N/A | N/A | 2025-02-19 | 2025-02-19 | 1 | 1 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-03-14 | 1899-12-31 | 1 | 2025-03-14 | 2025-03-14 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 33.05 | 33.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-10 | -455 | -326 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2023-08-18 | IOU Designed & Installed | N/A | No | N/A | -5.13 | -4.62 | Unknown | Unknown | Unknown | -0.51 | Unknown | 98.41 | -5.13 | 103.54 | Yes | N/A | N/A | 2023-02-14 | 2023-03-01 | 16 | 12 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | 2023-08-18 | 171 | 123 | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | 2023-09-12 | 1900-01-25 | 18 | 2023-09-12 | 2023-09-12 | 1 | 1 | 187 | 135 | 27 | 19 | 214 | 154 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-12 | -540 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | 2025-06-16 | IOU Designed & Installed | N/A | No | N/A | 82.58 | Unknown | Unknown | Unknown | 24.26 | 58.32 | 3981 | 1675.57 | 82.58 | 1592.99 | Yes | N/A | N/A | 2025-01-22 | 2025-01-10 | Unknown | Unknown | 2025-01-10 | 2025-01-22 | 13 | 9 | 2025-01-22 | Unknown | Unknown | Unknown | 2025-01-27 | 2025-01-31 | 5 | 5 | 2025-01-22 | 2025-06-16 | 146 | 104 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-06-20 | 1900-01-04 | 5 | 2025-06-20 | 2025-06-20 | 1 | 1 | 146 | 104 | 24 | 20 | 170 | 124 | Steps 2,3,5,6,7 | 9 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 134 | 134 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-09 | -562 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-23 | 2025-01-14 | IOU Designed & Installed | N/A | No | N/A | 1933.61 | Unknown | Unknown | Unknown | Unknown | 1933.61 | 3981 | 1152.99 | 1933.61 | -780.62 | Yes | N/A | N/A | 2024-09-11 | 2024-08-20 | Unknown | Unknown | 2024-08-20 | 2024-09-24 | 36 | 26 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2025-01-14 | 113 | 81 | Unknown | 2024-12-20 | Unknown | Unknown | 2025-01-14 | 2025-01-24 | 1900-01-10 | 9 | 2025-01-24 | 2025-01-24 | 1 | 1 | 113 | 81 | 48 | 36 | 161 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | -499 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | 2025-04-23 | IOU Designed & Installed | N/A | No | N/A | -652.67 | Unknown | Unknown | Unknown | -1297 | 644.33 | Unknown | 1153.9 | -652.67 | 1806.57 | Yes | N/A | N/A | 2024-10-30 | 2025-02-04 | 98 | 70 | 2025-02-04 | 2025-02-07 | 4 | 4 | 2025-02-07 | 2025-03-07 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-04-23 | 43 | 31 | Unknown | 2025-04-02 | Unknown | Unknown | 2025-04-23 | 2025-04-30 | 1900-01-07 | 6 | 2025-04-30 | 2025-04-30 | 1 | 1 | 170 | 122 | 13 | 11 | 183 | 133 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JACUMBA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-14 | -224 | -161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | Unknown | 2023-07-02 | IOU Designed & Installed | N/A | No | N/A | 2263.76 | 957.09 | Unknown | 17.75 | 7.48 | 1281.44 | 3981 | 613.09 | 2263.76 | -1650.67 | Yes | N/A | N/A | 2023-04-19 | 2023-04-19 | 1 | 1 | 2023-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-19 | 2023-07-02 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | 2023-07-02 | 2023-07-05 | 1900-01-03 | 3 | 2023-07-05 | 2023-07-05 | 1 | 1 | 76 | 54 | 5 | 4 | 81 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-27 | -282 | -203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-14 | 2024-10-16 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 334.28 | Unknown | Unknown | Unknown | Unknown | 334.28 | Unknown | 538.38 | 334.28 | 204.1 | Yes | N/A | N/A | 2024-10-14 | 2024-10-15 | 2 | 2 | 2024-10-15 | 2025-03-03 | 140 | 100 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-10-28 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-18 | 1900-01-21 | 16 | 2024-11-18 | 2024-11-18 | 1 | 1 | 9 | 7 | 163 | 117 | 172 | 124 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-09 | -521 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.94 | -11.64 | Unknown | Unknown | Unknown | 7.7 | Unknown | 953.54 | -3.94 | 957.48 | Yes | N/A | N/A | 2023-04-12 | 2023-04-14 | 3 | 3 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | Unknown | Unknown | 2023-07-07 | 2023-07-07 | 1 | 1 | 3 | 3 | 1 | 1 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | 508 | 365 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-27 | 2023-04-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1310.31 | Unknown | Unknown | Unknown | -1404 | 93.69 | 3981 | 1408.58 | -1310.31 | 2718.89 | Yes | N/A | N/A | 2023-04-27 | 2023-04-27 | 1 | 1 | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | 2024-09-20 | 2024-09-20 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | Carlsbad | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2020-11-05 | 1324 | 947 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-26 | 2024-01-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 4613.18 | Unknown | Unknown | Yes | N/A | N/A | 2024-01-26 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-06-21 | 149 | 107 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | Unknown | Unknown | Unknown | 2024-06-21 | 2024-06-21 | 1 | 1 | Unknown | 2024-06-21 | Unknown | Unknown | 2024-06-21 | 2024-06-21 | 1 | 1 | 0 | 0 | 151 | 109 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-31 | -169 | -121 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-03-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 30.1 | Unknown | Unknown | Unknown | Unknown | 30.1 | Unknown | 1088.68 | 30.1 | 1058.58 | Yes | N/A | N/A | 2024-03-25 | 2024-04-23 | 30 | 22 | 2024-04-23 | 2024-04-25 | 3 | 3 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | Unknown | Unknown | 2024-12-13 | 2024-12-13 | 1 | 1 | 30 | 22 | 4 | 4 | 34 | 26 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-08 | -109 | -78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-20 | 2023-08-15 | 2024-02-13 | IOU Designed & Installed | N/A | No | N/A | 548.49 | -47.5 | Unknown | Unknown | Unknown | 595.99 | 26990 | 330.93 | 548.49 | -217.56 | Yes | N/A | N/A | 2022-12-20 | 2023-08-01 | 225 | 161 | 2023-08-01 | 2023-12-04 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-07-02 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-06-21 | 1900-05-09 | 94 | 2024-06-21 | 2024-06-21 | 1 | 1 | 225 | 161 | 290 | 208 | 515 | 369 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 431.05 | 431.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-12 | -442 | -317 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-05-01 | 2023-08-17 | IOU Designed & Installed | N/A | No | N/A | -2.65 | -5.19 | Unknown | Unknown | Unknown | 2.54 | 3981 | 557.18 | -2.65 | 559.83 | Yes | N/A | N/A | 2023-04-06 | 2023-05-01 | 26 | 18 | 2023-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | 2023-08-17 | 109 | 79 | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2023-08-29 | 1900-01-12 | 9 | 2023-08-29 | 2023-08-28 | Unknown | Unknown | 135 | 97 | 13 | 9 | 148 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 82 | 82 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-17 | -525 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | 2024-03-01 | IOU Designed & Installed | N/A | No | N/A | 1568.97 | -11.26 | Unknown | Unknown | 24.27 | 1555.96 | 3981 | 763.78 | 1568.97 | -805.19 | Yes | N/A | N/A | 2023-12-01 | 2024-01-25 | 56 | 40 | 2024-01-25 | 2024-01-29 | 5 | 3 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-03-01 | 33 | 25 | Unknown | 2024-02-29 | Unknown | Unknown | 2024-03-01 | 2024-04-10 | 1900-02-09 | 29 | 2024-04-10 | 2024-04-10 | 1 | 1 | 89 | 65 | 47 | 33 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | -122 | -88 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | 2023-05-12 | 2024-08-06 | IOU Designed & Installed | N/A | No | N/A | 479.47 | 302.11 | Unknown | Unknown | Unknown | 177.36 | 0 | 495.75 | 479.47 | 16.28 | Yes | N/A | N/A | 2023-05-11 | 2023-05-11 | 1 | 1 | 2023-05-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-12 | 2024-08-06 | 453 | 323 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-07 | 1900-01-01 | 2 | 2024-08-07 | 2024-08-07 | 1 | 1 | 454 | 324 | 3 | 3 | 457 | 327 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-26 | -697 | -498 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | Unknown | 2024-08-12 | IOU Designed & Installed | N/A | No | N/A | 575.81 | -11.17 | Unknown | Unknown | Unknown | 586.98 | 3981 | 1744.74 | 575.81 | 1168.93 | Yes | N/A | N/A | 2024-08-09 | 2024-08-09 | 1 | 1 | 2024-08-09 | 2024-08-09 | 1 | 1 | 2024-08-09 | Unknown | Unknown | Unknown | 2024-08-09 | 2024-09-12 | 35 | 25 | 2024-08-09 | 2024-08-12 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-08-28 | 1900-01-16 | 13 | 2024-08-28 | 2024-08-28 | 1 | 1 | 5 | 3 | 54 | 40 | 59 | 43 | Steps 2,3,5,6,7 | 34 | 24 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-03 | -111 | -80 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-06 | 2024-02-28 | IOU Designed & Installed | N/A | No | N/A | 289.24 | 2139.23 | Unknown | 51.25 | -2915 | 1013.76 | Unknown | 2914.67 | 289.24 | 2625.43 | Yes | N/A | N/A | 2023-12-06 | 2024-02-06 | 63 | 45 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-07-15 | 1900-05-18 | 99 | 2024-07-15 | 2024-07-15 | 1 | 1 | 63 | 45 | 140 | 100 | 203 | 145 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-29 | 281 | 202 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | 2024-05-20 | IOU Designed & Installed | N/A | No | N/A | 512.44 | -16.46 | Unknown | Unknown | Unknown | 528.9 | Unknown | 789.38 | 512.44 | 276.94 | Yes | N/A | N/A | 2023-11-16 | 2023-09-12 | Unknown | Unknown | 2023-09-12 | 2023-11-16 | 66 | 48 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2024-05-20 | 187 | 133 | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-06-05 | 1900-01-16 | 13 | 2024-06-05 | 2024-06-05 | 1 | 1 | 187 | 133 | 84 | 62 | 271 | 195 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 37.05 | 37.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-30 | 189 | 136 | No | 2022-08-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-12 | 2022-08-12 | 2023-07-24 | IOU Designed & Installed | N/A | Yes | 195 | -2.49 | -4.85 | Unknown | Unknown | Unknown | 2.36 | 3885 | 834.69 | -2.49 | 837.18 | Yes | N/A | N/A | 2022-08-12 | 2023-02-23 | 196 | 140 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-08-12 | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2023-08-07 | 1900-01-14 | 11 | 2023-08-07 | 2023-08-07 | 1 | 1 | 196 | 140 | 16 | 12 | 212 | 152 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | -500 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | 2023-09-11 | IOU Designed & Installed | N/A | No | N/A | -14.77 | -10.71 | Unknown | Unknown | Unknown | -4.06 | Unknown | 479.76 | -14.77 | 494.53 | Yes | N/A | N/A | 2023-05-23 | 2023-05-23 | 1 | 1 | 2023-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | 2023-09-11 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-10-12 | 1900-01-31 | 24 | 2023-10-12 | 2023-10-12 | 1 | 1 | 113 | 81 | 33 | 25 | 146 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-26 | -370 | -265 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-26 | 2024-12-02 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | 455.61 | -33 | Unknown | Unknown | Unknown | 488.61 | 3981 | 1635.24 | 455.61 | 1179.63 | Yes | N/A | N/A | 2024-11-26 | 2024-10-15 | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2025-04-07 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-04-21 | 1900-01-14 | 11 | 2025-04-21 | 2025-04-21 | 1 | 1 | 127 | 91 | 16 | 12 | 143 | 103 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | La Mesa | COUNTY OF SAN DIEGO-SOUTH of 56 | 76.25 | 76.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-23 | 81 | 59 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-04-30 | 2024-08-13 | IOU Designed & Installed | N/A | No | N/A | 84352.65 | 21382.46 | Unknown | Unknown | -5572.91 | 68543.1 | Unknown | 20613.89 | 84352.65 | -63738.76 | Yes | N/A | N/A | 2024-02-14 | 2024-03-19 | 35 | 25 | 2024-03-19 | 2024-07-22 | 126 | 90 | 2024-06-06 | 2024-07-03 | 28 | 20 | 2024-05-15 | 2024-07-22 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | 2024-09-12 | 1900-01-30 | 23 | 2024-09-12 | 2024-09-12 | 1 | 1 | 63 | 45 | 192 | 138 | 255 | 183 | Steps 2,3,5,6,7 | 95 | 67 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-22 | -340 | -243 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-08 | 2024-12-17 | IOU Designed & Installed | N/A | No | N/A | 332.41 | -6.53 | Unknown | Unknown | Unknown | 338.94 | 3981 | 1504.33 | 332.41 | 1171.92 | Yes | N/A | N/A | 2024-07-02 | 2024-04-25 | Unknown | Unknown | 2024-04-25 | 2024-07-08 | 75 | 53 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-12-17 | 163 | 117 | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-04-17 | 1900-05-01 | 88 | 2025-04-17 | 2025-04-16 | Unknown | Unknown | 163 | 117 | 197 | 141 | 360 | 258 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-24 | 108 | 77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-23 | 2024-08-15 | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | -1513.39 | -1.56 | Unknown | Unknown | -1627 | 115.17 | Unknown | 1508.11 | -1513.39 | 3021.5 | Yes | N/A | N/A | 2024-07-23 | 2024-08-15 | 24 | 18 | 2024-08-15 | 2024-08-15 | 1 | 1 | 2024-08-15 | 2024-08-29 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-09-03 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-09-10 | 1900-01-07 | 6 | 2024-09-10 | 2024-09-09 | Unknown | Unknown | 45 | 33 | 9 | 7 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 13.05 | 13.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | 243 | 174 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | 292.99 | Unknown | Unknown | Unknown | 17.75 | 275.24 | 3981 | 912.38 | 292.99 | 619.39 | Yes | N/A | N/A | 2023-11-14 | 2023-10-17 | Unknown | Unknown | 2023-10-17 | 2023-11-17 | 32 | 24 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2024-09-16 | 305 | 217 | Unknown | 2024-09-10 | Unknown | Unknown | 2024-09-16 | 2024-09-25 | 1900-01-09 | 8 | 2024-09-25 | 2024-10-01 | 7 | 5 | 305 | 217 | 49 | 37 | 354 | 254 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-28 | -676 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-13 | 2024-09-13 | 2024-10-08 | IOU Designed & Installed | N/A | No | N/A | 26.32 | Unknown | Unknown | Unknown | Unknown | 26.32 | 3981 | 1558.07 | 26.32 | 1531.75 | Yes | N/A | N/A | 2024-09-13 | 2024-09-10 | Unknown | Unknown | 2024-09-10 | 2024-09-13 | 4 | 4 | 2024-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-13 | 2024-10-08 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-21 | 1900-01-13 | 10 | 2024-10-21 | 2024-10-21 | 1 | 1 | 26 | 18 | 19 | 15 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-08-27 | 984 | 703 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-04-24 | IOU Designed & Installed | N/A | No | N/A | 1108.13 | Unknown | Unknown | Unknown | Unknown | 1108.13 | 3981 | 672.91 | 1108.13 | -435.22 | Yes | N/A | N/A | 2023-03-20 | 2023-03-20 | 1 | 1 | 2023-03-20 | 2023-03-30 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | 2023-05-02 | 1 | 1 | 2023-03-30 | 2023-05-03 | 35 | 25 | Unknown | 2023-04-20 | Unknown | Unknown | 2023-04-24 | 2023-05-17 | 1900-01-23 | 18 | 2023-05-17 | 2023-05-08 | Unknown | Unknown | 36 | 26 | 36 | 28 | 72 | 54 | Steps 2,3,5,6,7 | 33 | 23 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | -618 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-12 | 2024-09-20 | IOU Designed & Installed | N/A | No | N/A | 3.33 | Unknown | Unknown | Unknown | Unknown | 3.33 | Unknown | 1050.75 | 3.33 | 1047.42 | Yes | N/A | N/A | 2024-08-06 | 2024-08-12 | 7 | 5 | 2024-08-12 | 2024-08-12 | 1 | 1 | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-09-20 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-09-27 | 1900-01-07 | 6 | 2024-09-27 | 2024-09-30 | 4 | 2 | 47 | 35 | 13 | 9 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-02 | 803 | 574 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-21 | 2022-10-21 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 79478.26 | 17046.5 | Unknown | 34.76 | 13.34 | 62383.66 | 565510 | 56459.26 | 79478.26 | -23019 | Yes | N/A | N/A | 2022-10-21 | 2023-03-27 | 158 | 112 | 2023-03-27 | 2023-10-16 | 204 | 146 | 2023-04-04 | 2023-04-20 | 17 | 13 | 2023-10-16 | 2023-11-15 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-10-21 | 91 | 65 | Unknown | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-13 | 1 | 1 | 175 | 125 | 327 | 235 | 502 | 360 | Steps 2,3,5,6,7 | 195 | 139 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | -596 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 51.28 | -0.62 | Unknown | Unknown | Unknown | 51.9 | 3981 | 1619.93 | 51.28 | 1568.65 | Yes | N/A | N/A | 2024-10-02 | 2024-07-08 | Unknown | Unknown | 2024-07-08 | 2024-10-02 | 87 | 63 | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-10-28 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-06 | 1900-01-09 | 8 | 2024-11-06 | 2024-11-06 | 1 | 1 | 27 | 19 | 98 | 72 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 32.4 | 32.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-12 | -258 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-05-20 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | 545.86 | -10.97 | Unknown | Unknown | Unknown | 556.83 | 3981 | 1803.73 | 545.86 | 1257.87 | Yes | N/A | N/A | 2024-03-21 | 2024-03-20 | Unknown | Unknown | 2024-03-20 | 2024-05-20 | 62 | 44 | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2025-04-09 | 325 | 233 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-29 | 1900-01-20 | 15 | 2025-04-29 | 2025-04-29 | 1 | 1 | 325 | 233 | 84 | 60 | 409 | 293 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | 374 | 374 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-12 | -38 | -27 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | Unknown | 2024-01-02 | IOU Designed & Installed | N/A | No | N/A | 4290.12 | 1556.24 | Unknown | Unknown | Unknown | 2733.88 | 3981 | 2495.84 | 4290.12 | -1794.28 | Yes | N/A | N/A | 2023-05-18 | 2023-05-18 | 1 | 1 | 2023-05-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | 2024-01-02 | 230 | 164 | Unknown | 2023-11-29 | Unknown | Unknown | 2024-01-02 | 2024-01-05 | 1900-01-03 | 4 | 2024-01-05 | 2024-01-05 | 1 | 1 | 231 | 165 | 5 | 5 | 236 | 170 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | CARLSBAD | 7303.05 | 7303.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-06-24 | -519 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-08 | 2024-11-11 | IOU Designed & Installed | N/A | No | N/A | 9262.23 | -110.34 | Unknown | Unknown | 48.96 | 9323.61 | Unknown | 4916.25 | 9262.23 | -4345.98 | Yes | N/A | N/A | 2024-08-08 | 2024-08-08 | 1 | 1 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-08-27 | 19 | 13 | 2024-08-09 | 2024-11-11 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2025-01-21 | 1900-03-12 | 52 | 2025-01-21 | 2025-01-21 | 1 | 1 | 96 | 68 | 92 | 66 | 188 | 134 | Steps 2,3,5,6,7 | 18 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 17.05 | 17.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-20 | -524 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-15 | 2023-06-16 | 2023-08-10 | IOU Designed & Installed | N/A | No | N/A | -2.7 | -5.2 | Unknown | Unknown | Unknown | 2.5 | 3981 | 529.95 | -2.7 | 532.65 | Yes | N/A | N/A | 2023-06-15 | 2023-06-16 | 2 | 2 | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-08-10 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-08-16 | 1900-01-06 | 5 | 2023-08-16 | 2023-08-15 | Unknown | Unknown | 58 | 42 | 7 | 5 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | ENCINITAS | 600 | 600 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-22 | 413 | 296 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-24 | 2023-07-19 | 2024-08-19 | IOU Designed & Installed | N/A | No | N/A | 36797.24 | 4440.37 | Unknown | 9.28 | 210.23 | 32137.36 | 70454 | 56471.44 | 36797.24 | 19674.2 | Yes | N/A | N/A | 2022-08-24 | 2023-04-21 | 241 | 173 | 2023-04-21 | 2023-10-04 | 167 | 119 | 2023-07-03 | 2024-07-31 | 17 | 13 | 2023-08-03 | 2024-10-04 | 96 | 70 | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2024-08-08 | 281 | 201 | 2024-08-19 | 2024-10-23 | 1900-03-06 | 48 | 2024-10-23 | 2024-10-08 | Unknown | Unknown | 258 | 186 | 610 | 438 | 868 | 624 | Steps 2,3,5,6,7 | 456 | 326 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-04 | -605 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-13 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 2563.71 | 618.76 | Unknown | Unknown | Unknown | 1944.95 | 3981 | 1538.16 | 2563.71 | -1025.55 | Yes | N/A | N/A | 2024-06-13 | 2024-06-13 | 1 | 1 | 2024-06-13 | 2024-06-13 | 1 | 1 | 2024-06-13 | Unknown | Unknown | Unknown | 2024-06-13 | 2024-07-15 | 33 | 23 | 2024-06-13 | 2024-10-01 | 111 | 79 | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-07 | 1900-01-06 | 5 | 2024-10-07 | 2024-10-07 | 1 | 1 | 112 | 80 | 42 | 30 | 154 | 110 | Steps 2,3,5,6,7 | 32 | 22 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-19 | -595 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-15 | 2024-05-09 | IOU Designed & Installed | N/A | No | N/A | 2147.27 | 660.29 | Unknown | Unknown | Unknown | 1486.98 | Unknown | 1116.63 | 2147.27 | -1030.64 | Yes | N/A | N/A | 2024-03-14 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2024-03-15 | 52 | 38 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-05-09 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-06-03 | 1900-01-25 | 18 | 2024-06-03 | 2024-06-03 | 1 | 1 | 56 | 40 | 79 | 57 | 135 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2020-12-30 | 988 | 707 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2020-01-15 | 2020-01-15 | 2024-01-16 | IOU Designed & Installed | N/A | No | N/A | 12.13 | -20.73 | Unknown | Unknown | 22.7 | 10.16 | 3981 | 1372.86 | 12.13 | 1360.73 | Yes | N/A | N/A | 2020-01-15 | 2023-08-14 | 1308 | 934 | 2023-08-14 | 2023-08-14 | 1 | 1 | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2024-01-16 | 156 | 112 | Unknown | 2023-08-30 | Unknown | Unknown | 2024-01-16 | 2024-01-16 | 1899-12-31 | 1 | 2024-01-16 | 2023-09-14 | Unknown | Unknown | 1464 | 1046 | 2 | 2 | 1466 | 1048 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | -511 | -366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-22 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | 990.22 | Unknown | Unknown | Unknown | 12.68 | 977.54 | 3981 | 1146.68 | 990.22 | 156.46 | Yes | N/A | N/A | 2024-08-16 | 2024-08-21 | 6 | 4 | 2024-08-21 | 2024-08-22 | 2 | 2 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2025-02-24 | 181 | 129 | Unknown | 2024-12-30 | Unknown | Unknown | 2025-02-24 | 2025-03-05 | 1900-01-09 | 8 | 2025-03-05 | 2025-03-05 | 1 | 1 | 187 | 133 | 13 | 11 | 200 | 144 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | 50 | 50 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-04 | -187 | -134 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5251.64 | 1052.69 | Unknown | 163.3 | 5.61 | 4030.04 | 3981 | 2357.45 | 5251.64 | -2894.19 | Yes | N/A | N/A | 2024-05-08 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-06-24 | 96 | 68 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2024-08-29 | 1 | 1 | 0 | 0 | 97 | 69 | 97 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-04 | -399 | -286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-28 | 2023-12-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 27.36 | Unknown | Unknown | Unknown | Unknown | 27.36 | 3981 | 839.09 | 27.36 | 811.73 | Yes | N/A | N/A | 2023-12-28 | 2023-09-11 | Unknown | Unknown | 2023-09-11 | 2023-12-29 | 110 | 80 | 2023-12-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2024-08-01 | 1 | 1 | 0 | 0 | 111 | 81 | 111 | 81 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Residential | N/A | Encinitas | ENCINITAS | 281 | 281 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | 285 | 204 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-04-30 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 9299.66 | -22.71 | Unknown | Unknown | -1787 | 11109.37 | Unknown | 2467.25 | 9299.66 | -6832.41 | Yes | N/A | N/A | 2024-03-14 | 2024-03-01 | Unknown | Unknown | 2024-03-01 | 2024-07-08 | 130 | 92 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-07-08 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-08-12 | 1900-01-20 | 15 | 2024-08-12 | 2024-08-12 | 1 | 1 | 0 | 0 | 202 | 144 | 202 | 144 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-24 | 2024-09-03 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 111585.48 | 54163.49 | Unknown | 97.6 | -120534 | 177858.39 | 0 | 119594.12 | 111585.48 | 8008.64 | Yes | N/A | N/A | 2023-01-24 | 2023-06-09 | 137 | 99 | 2023-06-09 | 2023-10-13 | 127 | 91 | 2023-06-26 | 2023-08-09 | 45 | 33 | 2023-02-28 | 2024-01-24 | 110 | 80 | 2024-05-10 | Unknown | Unknown | Unknown | 2024-05-10 | 2024-08-14 | 97 | 69 | 2024-09-03 | 2024-10-24 | 1900-02-20 | 38 | 2024-10-24 | 2024-10-24 | 1 | 1 | 182 | 132 | 387 | 279 | 569 | 411 | Steps 2,3,5,6,7 | 271 | 195 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 151.05 | 151.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-20 | -2 | -3 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-06-06 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 6705.35 | Unknown | Unknown | Unknown | 1229.37 | 5475.98 | 3981 | 1391.66 | 6705.35 | -5313.69 | Yes | N/A | N/A | 2023-05-18 | 2023-10-20 | 156 | 112 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2025-02-11 | 478 | 342 | Unknown | 2025-01-22 | Unknown | Unknown | 2025-02-11 | 2025-02-20 | 1900-01-09 | 8 | 2025-02-20 | 2025-02-18 | Unknown | Unknown | 634 | 454 | 10 | 8 | 644 | 462 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-27 | -158 | -113 | No | 2024-08-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-09 | Unknown | IOU Designed & Installed | N/A | Yes | 220 | Unknown |  | Unknown | Unknown | Unknown | Unknown | 7862 | 3229.15 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-09 | 2025-03-05 | 209 | 149 | 2025-03-05 | 2025-03-17 | 13 | 9 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-05-22 | Unknown | Unknown | 209 | 149 | 13 | 9 | 222 | 158 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 64.05 | 64.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-15 | 327 | 234 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2024-01-25 | 2024-06-05 | IOU Designed & Installed | N/A | No | N/A | 5128.39 | -11.09 | Unknown | Unknown | Unknown | 5139.48 | 3981 | 1373.5 | 5128.39 | -3754.89 | Yes | N/A | N/A | 2023-11-21 | 2024-01-25 | 66 | 48 | 2024-01-25 | 2024-01-25 | 1 | 1 | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-06-05 | 132 | 94 | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2024-08-19 | 1900-03-16 | 54 | 2024-08-19 | 2024-08-07 | Unknown | Unknown | 198 | 142 | 77 | 55 | 275 | 197 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 24.05 | 24.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-08 | -265 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | 2025-06-14 | IOU Designed & Installed | N/A | No | N/A | 1597.45 | Unknown | Unknown | Unknown | 3.9 | 1593.55 | 3981 | 1388.71 | 1597.45 | -208.74 | Yes | N/A | N/A | 2024-04-23 | 2024-11-13 | 205 | 147 | 2024-11-13 | 2024-11-20 | 8 | 6 | 2024-11-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2025-06-14 | 207 | 148 | Unknown | 2025-05-29 | Unknown | Unknown | 2025-06-14 | 2025-06-16 | 1900-01-02 | 1 | 2025-06-16 | 2025-06-16 | 1 | 1 | 412 | 295 | 12 | 8 | 424 | 303 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-05-13 | 1159 | 828 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-02-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 721.95 | 1920.75 | Unknown | 381.75 | -2429 | 848.45 | 0 | 2428.81 | 721.95 | 1706.86 | Yes | N/A | N/A | 2023-01-31 | 2023-02-21 | 22 | 16 | 2023-02-21 | 2023-02-24 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 22 | 16 | 5 | 5 | 27 | 21 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-22 | 339 | 242 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-10 | 2023-08-21 | IOU Designed & Installed | N/A | No | N/A | -9.06 | -6.58 | Unknown | Unknown | Unknown | -2.48 | Unknown | 483.84 | -9.06 | 492.9 | Yes | N/A | N/A | 2023-04-10 | 2023-04-10 | 1 | 1 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | 2023-08-21 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2023-09-26 | 1900-02-05 | 27 | 2023-09-26 | 2023-09-26 | 1 | 1 | 135 | 97 | 38 | 28 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 1296 | 1296 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-01-08 | 511 | 366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | 3494.89 | 2082.47 | Unknown | Unknown | -1154.14 | 2566.56 | 0 | 1038.83 | 3494.89 | -2456.06 | Yes | N/A | N/A | 2024-08-26 | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2024-11-15 | 129 | 93 | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | 2024-12-04 | 1 | 1 | 2024-11-15 | 2025-04-14 | 151 | 107 | Unknown | 2025-05-07 | Unknown | Unknown | 2025-06-10 | 2025-06-10 | 1899-12-31 | 1 | 2025-06-10 | 2025-06-02 | Unknown | Unknown | 151 | 107 | 131 | 95 | 282 | 202 | Steps 2,3,5,6,7 | 19 | 13 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 2715 | 2715 | Not Available | >2MW | No | N/A | N/A | N/A | 2026-04-30 | -675 | -484 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2.44 | -2.17 | Unknown | Unknown | Unknown | 4.61 | Unknown | 362.22 | 2.44 | 359.78 | Yes | N/A | N/A | 2024-06-12 | 2024-04-23 | Unknown | Unknown | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | Unknown | Unknown | 2024-06-24 | 2024-06-24 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-05 | -660 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | 2023-12-12 | IOU Designed & Installed | N/A | No | N/A | 1.27 | -17.46 | Unknown | Unknown | Unknown | 18.73 | Unknown | 284.51 | 1.27 | 283.24 | Yes | N/A | N/A | 2023-11-16 | 2023-09-10 | Unknown | Unknown | 2023-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2023-12-15 | 1900-01-03 | 4 | 2023-12-15 | 2023-12-15 | 1 | 1 | 0 | 0 | 5 | 5 | 5 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | 315 | 226 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2023-10-24 | 2023-11-13 | IOU Designed & Installed | N/A | No | N/A | 6501.74 | 633.26 | Unknown | Unknown | Unknown | 5868.48 | 7512 | 1587.94 | 6501.74 | -4913.8 | Yes | N/A | N/A | 2023-10-24 | 2023-10-24 | 1 | 1 | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | Unknown | Unknown | Unknown | 2023-11-07 | Unknown | Unknown | 2023-11-13 | 2023-11-20 | 1900-01-07 | 6 | 2023-11-20 | 2023-12-13 | 24 | 18 | 1 | 1 | 32 | 24 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-08 | 226 | 163 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-07 | 2023-03-07 | 2023-08-30 | IOU Designed & Installed | N/A | No | N/A | -4.63 | -9.12 | Unknown | Unknown | Unknown | 4.49 | 3981 | 633.67 | -4.63 | 638.3 | Yes | N/A | N/A | 2023-03-07 | 2023-03-07 | 1 | 1 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | 2023-08-30 | 177 | 127 | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2023-09-22 | 1900-01-23 | 18 | 2023-09-22 | 2023-09-22 | 1 | 1 | 178 | 128 | 25 | 19 | 203 | 147 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-15 | -577 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-06-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.78 | -13.17 | Unknown | Unknown | Unknown | 6.39 | 3885 | 957.22 | -6.78 | 964 | Yes | N/A | N/A | 2023-06-02 | 2023-06-08 | 7 | 5 | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-20 | Unknown | Unknown | 2023-08-20 | 2023-07-19 | Unknown | Unknown | 7 | 5 | 0 | 0 | 7 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 180.2 | 180.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-05 | 50 | 37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3456.98 | 883.31 | Unknown | 258.28 | 77.79 | 2237.6 | 47772 | 1669.66 | 3456.98 | -1787.32 | Yes | N/A | N/A | 2023-09-18 | 2023-09-18 | 1 | 1 | 2023-09-18 | 2023-10-09 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | 2023-09-30 | 12 | 9 | 2023-10-09 | 2024-07-11 | 277 | 199 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | Unknown | Unknown | 2024-08-01 | 2024-07-25 | Unknown | Unknown | 278 | 200 | 34 | 25 | 312 | 225 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-18 | -689 | -494 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-02 | 2025-04-08 | 2025-04-16 | IOU Designed & Installed | N/A | No | N/A | 827.25 | -16.62 | Unknown | Unknown | Unknown | 843.87 | Unknown | 1782.6 | 827.25 | 955.35 | Yes | N/A | N/A | 2025-04-02 | 2025-04-08 | 7 | 5 | 2025-04-08 | 2025-04-08 | 1 | 1 | 2025-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-16 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-04-28 | 1900-01-12 | 9 | 2025-04-28 | 2025-04-28 | 1 | 1 | 16 | 12 | 15 | 11 | 31 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | -601 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-14 | 2025-05-29 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1010.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-14 | 2025-04-28 | Unknown | Unknown | 2025-04-28 | 2025-05-14 | 17 | 13 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-05-29 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-20 | 1900-01-22 | 17 | 2025-06-20 | 2025-06-20 | 1 | 1 | 16 | 12 | 41 | 31 | 57 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-16 | -221 | -158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | 1377.61 | -35.44 | Unknown | Unknown | Unknown | 1413.05 | Unknown | 287.46 | 1377.61 | -1090.15 | Yes | N/A | N/A | 2024-01-29 | 2024-01-15 | Unknown | Unknown | 2024-01-15 | 2024-01-29 | 15 | 11 | 2024-01-29 | Unknown | Unknown | Unknown | 2024-01-29 | 2024-10-08 | 25 | 19 | 2024-01-29 | 2024-05-17 | 110 | 80 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-11-07 | 1900-06-23 | 125 | 2024-11-07 | 2024-11-07 | 1 | 1 | 110 | 80 | 216 | 156 | 326 | 236 | Steps 2,3,5,6,7 | 253 | 181 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | Escondido | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | 200 | 143 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-11-11 | IOU Designed & Installed | N/A | No | N/A | 32829.96 | 2044.2 | Unknown | Unknown | 1044.76 | 29741 | 3981 | Not available | 32829.96 | Unknown | Yes | N/A | N/A | 2024-08-27 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2024-09-10 | 231 | 165 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2025-03-18 | 190 | 136 | Unknown | 2025-03-24 | Unknown | Unknown | 2024-11-11 | 2025-04-28 | 1900-06-17 | 121 | 2025-04-28 | 2025-04-28 | 1 | 1 | 190 | 136 | 401 | 287 | 591 | 423 | Steps 2,3,5,6,7 | 133 | 95 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 117.05 | 117.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-15 | -367 | -262 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | 2025-02-18 | IOU Designed & Installed | N/A | No | N/A | 11.03 | -18.81 | Unknown | Unknown | Unknown | 29.84 | 3981 | 1832.33 | 11.03 | 1821.3 | Yes | N/A | N/A | 2024-11-19 | 2024-10-03 | Unknown | Unknown | 2024-10-03 | 2024-11-19 | 48 | 34 | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2025-02-18 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-03-26 | 1900-02-05 | 27 | 2025-03-26 | 2025-06-13 | 80 | 58 | 92 | 66 | 165 | 119 | 257 | 185 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | 782 | 559 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5236.94 | 934.08 | Unknown | 90.99 | 25.21 | 4186.66 | 330423 | 13813.91 | 5236.94 | 8576.97 | Yes | N/A | N/A | 2023-03-06 | 2023-03-07 | 2 | 2 | 2023-03-07 | 2023-04-18 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | 2025-01-17 | 641 | 459 | Unknown | 2025-01-16 | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 643 | 461 | 44 | 32 | 687 | 493 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 29 | 29 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-17 | -509 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-06-16 | 2023-08-09 | IOU Designed & Installed | N/A | No | N/A | -7.33 | -5.28 | Unknown | Unknown | Unknown | -2.05 | Unknown | 464.78 | -7.33 | 472.11 | Yes | N/A | N/A | 2023-05-30 | 2023-06-16 | 18 | 14 | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-08-09 | 55 | 39 | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | 2023-10-25 | 1900-03-18 | 56 | 2023-10-25 | 2023-10-25 | 1 | 1 | 73 | 53 | 79 | 57 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-25 | -652 | -467 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-22 | 2024-11-18 | IOU Designed & Installed | N/A | No | N/A | 965.2 | -18.08 | Unknown | Unknown | Unknown | 983.28 | Unknown | 1597.97 | 965.2 | 632.77 | Yes | N/A | N/A | 2024-10-21 | 2024-10-01 | Unknown | Unknown | 2024-10-01 | 2024-10-22 | 22 | 16 | 2024-10-22 | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-04 | 12 | 8 | 2024-10-22 | 2024-11-18 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-12-12 | 1900-01-24 | 19 | 2024-12-12 | 2024-12-12 | 1 | 1 | 28 | 20 | 60 | 44 | 88 | 64 | Steps 2,3,5,6,7 | 13 | 9 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-17 | -555 | -398 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-08-15 | 2024-11-19 | IOU Designed & Installed | N/A | No | N/A | 386.83 | Unknown | Unknown | Unknown | 7.2 | 379.63 | 3981 | 1059.29 | 386.83 | 672.46 | Yes | N/A | N/A | 2024-07-30 | 2024-09-20 | 53 | 39 | 2024-09-20 | 2024-09-20 | 1 | 1 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-11-19 | 61 | 43 | Unknown | 2024-11-18 | Unknown | Unknown | 2024-11-19 | 2024-12-09 | 1900-01-20 | 15 | 2024-12-09 | 2024-12-09 | 1 | 1 | 114 | 82 | 23 | 17 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-14 | -262 | -189 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-04-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 761.49 | -38.1 | Unknown | Unknown | Unknown | 799.59 | 7962 | 433.58 | 761.49 | -327.91 | Yes | N/A | N/A | 2023-03-29 | 2023-03-29 | 1 | 1 | 2023-03-29 | 2023-04-14 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | 2023-06-09 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | Unknown | Unknown | 2023-09-22 | 2023-06-26 | Unknown | Unknown | 58 | 42 | 17 | 13 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-25 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-30 | 2023-09-30 | 2023-12-11 | IOU Designed & Installed | N/A | No | N/A | 2569.33 | 686.5 | Unknown | Unknown | Unknown | 1882.83 | Unknown | 5281.75 | 2569.33 | 2712.42 | Yes | N/A | N/A | 2023-09-30 | 2023-09-30 | 1 | 0 | 2023-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2023-11-21 | 2 | 2 | 2023-10-06 | 2023-12-11 | 67 | 47 | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2024-01-25 | 1900-02-14 | 34 | 2024-01-25 | 2024-01-25 | 1 | 1 | 68 | 47 | 49 | 37 | 117 | 84 | Steps 2,3,5,6,7 | 46 | 32 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | -603 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-06-04 | 2024-07-19 | IOU Designed & Installed | N/A | No | N/A | 333.74 | Unknown | Unknown | Unknown | 2.49 | 331.25 | 3981 | 1251.97 | 333.74 | 918.23 | Yes | N/A | N/A | 2024-05-21 | 2024-07-09 | 50 | 36 | 2024-07-09 | 2024-07-10 | 2 | 2 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-07-19 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-08-15 | 1900-01-27 | 20 | 2024-08-15 | 2024-08-15 | 1 | 1 | 60 | 44 | 31 | 23 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-17 | -453 | -325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-30 | 2024-07-30 | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | -2233.07 | Unknown | Unknown | Unknown | -2290 | 56.93 | Unknown | 2032.89 | -2233.07 | 4265.96 | Yes | N/A | N/A | 2024-07-30 | 2024-07-30 | 1 | 1 | 2024-07-30 | 2024-09-06 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | 2024-10-10 | 2024-10-21 | 1900-01-11 | 8 | 2024-10-21 | 2024-10-21 | 1 | 1 | 1 | 1 | 52 | 38 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | -596 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-20 | 2024-10-16 | IOU Designed & Installed | N/A | No | N/A | 9.51 | Unknown | Unknown | Unknown | Unknown | 9.51 | Unknown | 186.52 | 9.51 | 177.01 | Yes | N/A | N/A | 2024-08-20 | 2024-09-04 | 16 | 12 | 2024-09-04 | 2024-09-04 | 1 | 1 | 2024-09-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2024-10-16 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-22 | 1900-01-06 | 5 | 2024-10-22 | 2024-10-22 | 1 | 1 | 59 | 43 | 9 | 7 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-01 | 1265 | 904 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-03-20 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 4155.04 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-20 | 2025-03-07 | Unknown | Unknown | 2025-03-07 | 2025-05-19 | 74 | 52 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | Unknown | Unknown | 2025-06-03 | 2025-06-19 | 1900-01-16 | 13 | 2025-06-19 | 2025-06-19 | 1 | 1 | 0 | 0 | 92 | 66 | 92 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-17 | -328 | -235 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | 2024-01-09 | IOU Designed & Installed | N/A | No | N/A | 797.41 | -7.28 | Unknown | Unknown | 9.2 | 795.49 | 3981 | 572.95 | 797.41 | -224.46 | Yes | N/A | N/A | 2023-03-06 | 2023-03-24 | 19 | 15 | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | 2024-01-09 | 292 | 208 | Unknown | 2023-12-28 | Unknown | Unknown | 2024-01-09 | 2024-01-24 | 1900-01-15 | 12 | 2024-01-24 | 2024-01-24 | 1 | 1 | 311 | 223 | 17 | 13 | 328 | 236 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-31 | -83 | -60 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2024-04-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -223.98 | 278.88 | Unknown | Unknown | -1198 | 695.14 | 3981 | 1659.82 | -223.98 | 1883.8 | Yes | N/A | N/A | 2023-08-30 | 2024-02-23 | 178 | 128 | 2024-02-23 | 2024-04-01 | 39 | 27 | 2024-04-01 | 2024-05-09 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-01-07 | Unknown | Unknown | 217 | 157 | 39 | 27 | 256 | 184 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | -50 | -37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2556.72 | -10.73 | Unknown | Unknown | Unknown | 2567.45 | 0 | 613.42 | 2556.72 | -1943.3 | Yes | N/A | N/A | 2023-06-06 | 2023-06-06 | 1 | 1 | 2023-06-06 | 2025-04-04 | 669 | 479 | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | 2023-06-15 | 10 | 8 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | Unknown | Unknown | 2025-05-12 | 2025-05-12 | 1 | 1 | 1 | 1 | 680 | 488 | 681 | 489 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | -414 | -297 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | 2025-02-07 | IOU Designed & Installed | N/A | No | N/A | 1479.91 | 245.04 | Unknown | Unknown | Unknown | 1234.87 | Unknown | 1869.27 | 1479.91 | 389.36 | Yes | N/A | N/A | 2024-12-03 | 2024-12-03 | 1 | 1 | 2024-12-03 | 2024-12-03 | 1 | 1 | 2024-12-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2025-02-07 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-02-25 | 1900-01-18 | 13 | 2025-02-25 | 2025-02-25 | 1 | 1 | 68 | 50 | 21 | 15 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-29 | -486 | -348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-20 | 2023-07-20 | 2023-10-05 | IOU Designed & Installed | N/A | No | N/A | 0.84 | -10.95 | Unknown | Unknown | Unknown | 11.79 | Unknown | 823.4 | 0.84 | 822.56 | Yes | N/A | N/A | 2023-07-20 | 2023-07-20 | 1 | 1 | 2023-07-20 | 2023-07-20 | 1 | 1 | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-10-05 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-11-29 | 1900-02-24 | 40 | 2023-11-29 | 2023-11-29 | 1 | 1 | 79 | 57 | 58 | 42 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-02 | 658 | 471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-07-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 24870.89 | 9831.17 | Unknown | Unknown | Unknown | 15039.72 | 948476 | 24794.16 | 24870.89 | -76.73 | Yes | N/A | N/A | 2023-07-14 | 2023-07-14 | 1 | 1 | 2023-07-14 | 2024-05-21 | 313 | 223 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2024-05-07 | Unknown | Unknown | 2024-05-28 | 2024-05-28 | 1 | 1 | Unknown | 2024-06-24 | Unknown | Unknown | 2024-06-24 | 2024-06-21 | Unknown | Unknown | 1 | 1 | 314 | 224 | 315 | 225 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-12 | 659 | 472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-02-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1963.93 | -16.9 | Unknown | Unknown | 38.11 | 1942.72 | Unknown | 722.04 | 1963.93 | -1241.89 | Yes | N/A | N/A | 2024-02-29 | 2024-02-29 | 1 | 1 | 2024-02-29 | 2024-06-13 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2024-03-31 | 2024-09-17 | 72 | 51 | 2024-06-13 | 2024-09-10 | 90 | 64 | Unknown | 2024-08-05 | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | 2024-10-02 | 2024-10-01 | Unknown | Unknown | 91 | 65 | 178 | 127 | 269 | 192 | Steps 2,3,5,6,7 | 96 | 68 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-12-15 | 46 | 34 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 605.07 | -12.05 | Unknown | Unknown | Unknown | 617.12 | Unknown | Not available | 605.07 | Unknown | Yes | N/A | N/A | 2024-09-10 | 2024-09-10 | 1 | 1 | 2024-09-10 | 2024-10-30 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2025-01-16 | 38 | 28 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | 2025-01-30 | 2025-01-30 | 1 | 1 | 1 | 1 | 90 | 66 | 91 | 67 | Steps 2,3,5,6,7 | 78 | 56 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-06-17 | 768 | 549 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-29 | 2023-07-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1047.12 | Unknown | Unknown | Unknown | -1728 | 680.88 | 0 | 406.27 | -1047.12 | 1453.39 | Yes | N/A | N/A | 2022-09-29 | 2023-07-25 | 300 | 214 | 2023-07-25 | 2023-11-21 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-04-16 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-07-24 | Unknown | Unknown | 300 | 214 | 121 | 87 | 421 | 301 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-06 | -124 | -90 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1540.17 | 3516.55 | Unknown | 803.45 | -4279 | 1499.17 | Unknown | 4278.86 | 1540.17 | 2738.69 | Yes | N/A | N/A | 2023-07-11 | 2023-07-11 | 1 | 1 | 2023-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-03-04 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | SOLANA BEACH | 130.05 | 130.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-06 | -669 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-03-17 | 2025-04-18 | IOU Designed & Installed | N/A | No | N/A | 1170.14 | -24.15 | Unknown | Unknown | Unknown | 1194.29 | 3981 | 2072.23 | 1170.14 | 902.09 | Yes | N/A | N/A | 2025-03-17 | 2025-03-17 | 1 | 1 | 2025-03-17 | 2025-03-17 | 1 | 1 | 2025-03-17 | Unknown | Unknown | Unknown | 2025-04-16 | 2025-04-17 | 2 | 2 | 2025-03-17 | 2025-04-18 | 33 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-05-06 | 1900-01-18 | 13 | 2025-05-06 | 2025-05-06 | 1 | 1 | 34 | 26 | 23 | 17 | 57 | 43 | Steps 2,3,5,6,7 | 31 | 23 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-26 | -281 | -202 | No | 2024-01-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-24 | 2024-01-24 | 2024-02-28 | IOU Designed & Installed | N/A | Yes | 30 | 143.96 | -15.84 | Unknown | Unknown | Unknown | 159.8 | 3981 | 1107.6 | 143.96 | 963.64 | Yes | N/A | N/A | 2024-01-24 | 2024-02-23 | 31 | 23 | 2024-02-23 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-02-28 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-03-20 | 1900-01-21 | 16 | 2024-03-20 | 2024-03-20 | 1 | 1 | 67 | 49 | 23 | 17 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 60.05 | 60.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-21 | 606 | 433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | 2023-08-30 | IOU Designed & Installed | N/A | No | N/A | 1051.73 | -23.68 | Unknown | Unknown | 17.64 | 1057.77 | 3941 | 778.96 | 1051.73 | -272.77 | Yes | N/A | N/A | 2023-08-08 | 2023-06-01 | Unknown | Unknown | 2023-06-01 | 2023-08-08 | 69 | 49 | 2023-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | 2023-08-30 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | 2024-01-19 | 1900-05-22 | 103 | 2024-01-19 | 2025-03-18 | 425 | 303 | 23 | 17 | 637 | 455 | 660 | 472 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | DEL MAR | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-14 | -607 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-02-01 | 2024-02-05 | IOU Designed & Installed | N/A | No | N/A | -4.85 | -3.92 | Unknown | Unknown | Unknown | -0.93 | Unknown | 552.98 | -4.85 | 557.83 | Yes | N/A | N/A | 2024-01-10 | 2024-02-01 | 23 | 17 | 2024-02-01 | 2024-02-01 | 1 | 1 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-02-05 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-02-15 | 1900-01-10 | 9 | 2024-02-15 | 2024-02-15 | 1 | 1 | 28 | 20 | 13 | 11 | 41 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 140.05 | 140.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-31 | -457 | -328 | No | 2024-10-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-08 | 2025-04-22 | IOU Designed & Installed | N/A | Yes | 34 | 1008.56 | Unknown | Unknown | Unknown | Unknown | 1008.56 | 3981 | 1319.1 | 1008.56 | 310.54 | Yes | N/A | N/A | 2024-10-08 | 2024-10-09 | 2 | 2 | 2024-10-09 | 2024-11-11 | 34 | 24 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2025-04-22 | 163 | 117 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-04-30 | 1900-01-08 | 7 | 2025-04-30 | 2025-04-30 | 1 | 1 | 165 | 119 | 44 | 32 | 209 | 151 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-22 | -120 | -87 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-05-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4.15 | Unknown | Unknown | Unknown | Unknown | 4.15 | Unknown | 443.54 | 4.15 | 439.39 | Yes | N/A | N/A | 2024-05-31 | 2024-05-09 | Unknown | Unknown | 2024-05-09 | 2024-05-31 | 23 | 17 | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | Unknown | Unknown | 2024-07-25 | 2024-07-25 | 1 | 1 | 0 | 0 | 24 | 18 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 19 | 19 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-20 | -532 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-11 | 2023-12-26 | IOU Designed & Installed | N/A | No | N/A | 0.27 | -3.75 | Unknown | Unknown | Unknown | 4.02 | 3981 | 919.24 | 0.27 | 918.97 | Yes | N/A | N/A | 2023-10-11 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2023-10-11 | 104 | 74 | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2023-12-26 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | 2024-01-05 | 1900-01-10 | 9 | 2024-01-05 | 2024-01-05 | 1 | 1 | 77 | 55 | 116 | 84 | 193 | 139 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | 145 | 104 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-10 | 2022-03-18 | 2023-08-08 | IOU Designed & Installed | N/A | No | N/A | 134.72 | -12.38 | Unknown | Unknown | -464.3 | 611.4 | Unknown | 883.79 | 134.72 | 749.07 | Yes | N/A | N/A | 2022-03-10 | 2023-03-20 | 376 | 268 | 2023-03-20 | 2023-05-26 | 68 | 50 | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | Unknown | Unknown | 2023-08-08 | 2024-08-11 | 1901-01-04 | 264 | 2024-08-11 | 2023-08-09 | Unknown | Unknown | 376 | 268 | 438 | 314 | 814 | 582 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | -314 | -225 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-04-23 | 2024-05-28 | IOU Designed & Installed | N/A | No | N/A | 852.16 | -34.32 | Unknown | Unknown | Unknown | 886.48 | Unknown | 1016.46 | 852.16 | 164.3 | Yes | N/A | N/A | 2024-04-23 | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2024-04-23 | 8 | 6 | 2024-04-23 | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-14 | 21 | 15 | 2024-04-23 | 2024-05-28 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-05-28 | 2024-05-30 | 1900-01-02 | 3 | 2024-05-30 | 2024-05-31 | 2 | 2 | 36 | 26 | 34 | 26 | 70 | 52 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-22 | -559 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-08 | 2023-12-05 | IOU Designed & Installed | N/A | No | N/A | 699.32 | -12.28 | Unknown | Unknown | 5.34 | 706.26 | 3981 | 734.14 | 699.32 | 34.82 | Yes | N/A | N/A | 2023-09-08 | 2023-06-15 | Unknown | Unknown | 2023-06-15 | 2023-09-29 | 107 | 77 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-12-05 | 68 | 48 | Unknown | 2023-12-04 | Unknown | Unknown | 2023-12-05 | 2023-12-11 | 1900-01-06 | 5 | 2023-12-11 | 2023-12-11 | 1 | 1 | 68 | 48 | 115 | 83 | 183 | 131 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2030-12-31 | -2518 | -1799 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-04-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2802.83 | 643.51 | Unknown | 235.84 | -376.28 | 2299.76 | Unknown | 389.87 | 2802.83 | -2412.96 | Yes | N/A | N/A | 2023-04-26 | 2023-04-26 | 1 | 1 | 2023-04-26 | 2023-05-04 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | 2023-12-19 | 230 | 164 | Unknown | 2024-02-01 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-02-08 | Unknown | Unknown | 231 | 165 | 9 | 7 | 240 | 172 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-18 | -616 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-25 | 2025-04-08 | IOU Designed & Installed | N/A | No | N/A | 113.07 | -1.5 | Unknown | Unknown | Unknown | 114.57 | Unknown | 1714.29 | 113.07 | 1601.22 | Yes | N/A | N/A | 2025-03-14 | 2025-03-25 | 12 | 8 | 2025-03-25 | 2025-03-25 | 1 | 1 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-04-08 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-11 | 1900-01-03 | 4 | 2025-04-11 | 2025-04-11 | 1 | 1 | 27 | 19 | 6 | 6 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 28401 | 28401 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-09-21 | -612 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-21 | 2024-01-11 | IOU Designed & Installed | N/A | No | N/A | 449.89 | -9.37 | Unknown | Unknown | Unknown | 459.26 | Unknown | 961.13 | 449.89 | 511.24 | Yes | N/A | N/A | 2023-12-13 | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2023-12-21 | 85 | 61 | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-01-11 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-01-18 | 1900-01-07 | 6 | 2024-01-18 | 2024-01-18 | 1 | 1 | 22 | 16 | 94 | 68 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-20 | -556 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | 2023-12-21 | IOU Designed & Installed | N/A | No | N/A | 1076.79 | 406.84 | Unknown | Unknown | Unknown | 669.95 | Unknown | 1024.91 | 1076.79 | -51.88 | Yes | N/A | N/A | 2023-11-27 | 2023-11-27 | 1 | 1 | 2023-11-27 | 2023-11-27 | 1 | 1 | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2023-12-21 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-01-11 | 1900-01-21 | 16 | 2024-01-11 | 2024-01-11 | 1 | 1 | 26 | 20 | 24 | 18 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-03 | 203 | 146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 566.23 | Unknown | Unknown | Unknown | 40.75 | 525.48 | 3981 | 483.07 | 566.23 | -83.16 | Yes | N/A | N/A | 2024-09-27 | 2024-10-18 | 22 | 16 | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | Unknown | Unknown | Unknown | 2025-06-24 | Unknown | Unknown | 2025-06-24 | 2025-06-24 | 1 | 1 | 22 | 16 | 2 | 2 | 24 | 18 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 99 | 99 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-18 | -172 | -123 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2024-01-23 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | -371.61 | Unknown | Unknown | Unknown | -469 | 97.39 | 3981 | 2272.52 | -371.61 | 2644.13 | Yes | N/A | N/A | 2023-10-31 | 2023-10-31 | 1 | 1 | 2023-10-31 | 2024-01-23 | 85 | 61 | 2024-01-23 | 2024-02-01 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | 2025-02-11 | 327 | 233 | Unknown | 2024-07-12 | Unknown | Unknown | 2025-02-11 | 2025-02-20 | 1900-01-09 | 8 | 2025-02-20 | 2025-02-27 | 8 | 6 | 338 | 242 | 103 | 75 | 441 | 317 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-10 | -694 | -497 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-14 | 2025-02-14 | 2025-03-10 | IOU Designed & Installed | N/A | No | N/A | 362.35 | -6.6 | Unknown | Unknown | Unknown | 368.95 | 3981 | 1622.51 | 362.35 | 1260.16 | Yes | N/A | N/A | 2025-02-14 | 2025-02-14 | 1 | 1 | 2025-02-14 | 2025-02-14 | 1 | 1 | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-10 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-03-18 | 1900-01-08 | 7 | 2025-03-18 | 2025-03-18 | 1 | 1 | 26 | 18 | 11 | 9 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | 2024-08-23 | IOU Designed & Installed | N/A | No | N/A | 65.7 | Unknown | Unknown | Unknown | Unknown | 65.7 | 7882 | 1420.16 | 65.7 | 1354.46 | Yes | N/A | N/A | 2024-06-06 | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-06-06 | 57 | 41 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-08-23 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-09-04 | 1900-01-12 | 9 | 2024-09-04 | 2024-09-10 | 7 | 5 | 79 | 57 | 77 | 55 | 156 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-08 | -516 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-15 | 2024-05-21 | IOU Designed & Installed | N/A | No | N/A | 12.23 | -10.86 | Unknown | Unknown | Unknown | 23.09 | 3981 | 1012.27 | 12.23 | 1000.04 | Yes | N/A | N/A | 2024-04-15 | 2023-12-08 | Unknown | Unknown | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-05-21 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2024-06-10 | 1900-01-20 | 15 | 2024-06-10 | 2024-06-10 | 1 | 1 | 37 | 27 | 22 | 16 | 59 | 43 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-11 | -320 | -230 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-26 | 2024-02-13 | IOU Designed & Installed | N/A | No | N/A | 1658.4 | 504.92 | Unknown | 81.68 | Unknown | 1071.8 | 3981 | 737.9 | 1658.4 | -920.5 | Yes | N/A | N/A | 2024-01-25 | 2024-01-11 | Unknown | Unknown | 2024-01-11 | 2024-01-26 | 16 | 12 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-02-13 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | 2024-02-26 | 1900-01-13 | 10 | 2024-02-26 | 2024-02-26 | 1 | 1 | 19 | 13 | 31 | 23 | 50 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-19 | -473 | -338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-05-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 252.27 | -49.37 | Unknown | Unknown | -879 | 1180.64 | Unknown | 878.6 | 252.27 | 626.33 | Yes | N/A | N/A | 2023-05-31 | 2023-05-31 | 1 | 1 | 2023-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | Unknown | Unknown | 2023-08-04 | 2023-08-04 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-30 | 467 | 335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 14.25 | Unknown | Unknown | Unknown | Unknown | 14.25 | 4539 | 502.36 | 14.25 | 488.11 | Yes | N/A | N/A | 2024-01-04 | 2023-11-03 | Unknown | Unknown | 2023-11-03 | 2024-03-01 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-10-25 | 239 | 171 | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-11-08 | Unknown | Unknown | 239 | 171 | 120 | 86 | 359 | 257 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | -681 | -488 | No | 2025-03-20 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-20 | 2025-04-07 | Unknown | IOU Designed & Installed | N/A | Yes | 18 | -1110.76 | -21.78 | Unknown | Unknown | -1105.56 | 16.58 | Unknown | 1738.87 | -1110.76 | 2849.63 | Yes | N/A | N/A | 2025-03-20 | 2025-04-01 | 13 | 9 | 2025-04-01 | 2025-04-01 | 1 | 1 | 2025-04-01 | 2025-04-09 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | Unknown | Unknown | 2025-04-23 | 2025-04-23 | 1 | 1 | 22 | 16 | 2 | 2 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-03 | -488 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | 2025-04-21 | IOU Designed & Installed | N/A | No | N/A | 1145.05 | -23.01 | Unknown | Unknown | 0.26 | 1167.8 | 3981 | 1946.43 | 1145.05 | 801.38 | Yes | N/A | N/A | 2024-10-30 | 2024-11-04 | 6 | 4 | 2024-11-04 | 2024-12-27 | 54 | 40 | 2024-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-04-21 | 116 | 82 | Unknown | Unknown | Unknown | Unknown | 2025-04-21 | 2025-06-02 | 1900-02-11 | 31 | 2025-06-02 | 2025-06-02 | 1 | 1 | 122 | 86 | 98 | 72 | 220 | 158 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-02 | 809 | 578 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-17 | 2022-08-17 | 2024-11-11 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 15726.19 | 5206.34 | Unknown | 164.43 | 77.18 | 10278.24 | 1648302 | 18886.15 | 15726.19 | 3159.96 | Yes | N/A | N/A | 2022-08-17 | 2023-03-28 | 224 | 160 | 2023-03-28 | 2024-06-26 | 457 | 327 | 2023-04-04 | 2024-06-11 | 24 | 18 | 2024-06-26 | 2024-07-17 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2024-11-19 | 1900-01-08 | 7 | 2024-11-19 | 2024-11-19 | 1 | 1 | 248 | 178 | 489 | 351 | 737 | 529 | Steps 2,3,5,6,7 | 449 | 321 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-24 | -467 | -334 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-11-21 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 3.64 | Unknown | Unknown | Unknown | Unknown | 3.64 | 3981 | 1697.82 | 3.64 | 1694.18 | Yes | N/A | N/A | 2024-08-28 | 2024-11-19 | 84 | 60 | 2024-11-19 | 2024-11-21 | 3 | 3 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2025-01-27 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-02-11 | 1900-01-15 | 12 | 2025-02-11 | 2025-02-11 | 1 | 1 | 152 | 108 | 20 | 16 | 172 | 124 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-06 | 8 | 7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | Unknown | 2023-08-22 | IOU Designed & Installed | N/A | No | N/A | -7 | -13.75 | Unknown | Unknown | Unknown | 6.75 | 3981 | 859.71 | -7 | 866.71 | Yes | N/A | N/A | 2023-08-08 | 2023-05-10 | Unknown | Unknown | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-10 | 2023-08-22 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | 2023-09-14 | 1900-01-23 | 18 | 2023-09-14 | 2023-09-14 | 1 | 1 | 13 | 9 | 25 | 19 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-05 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-26 | 2025-04-14 | IOU Designed & Installed | N/A | No | N/A | 445.63 | Unknown | Unknown | Unknown | 2.9 | 442.73 | 3981 | 1253.06 | 445.63 | 807.43 | Yes | N/A | N/A | 2025-02-20 | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-03-10 | 21 | 15 | 2025-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-04-14 | 36 | 26 | Unknown | 2025-04-10 | Unknown | Unknown | 2025-04-14 | 2025-04-30 | 1900-01-16 | 13 | 2025-04-30 | 2025-04-30 | 1 | 1 | 36 | 26 | 39 | 29 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-19 | -336 | -241 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 2025-04-17 | IOU Designed & Installed | N/A | No | N/A | 2300.59 | 3376.84 | Unknown | 176.34 | -2714 | 1461.41 | Unknown | 2714.43 | 2300.59 | 413.84 | Yes | N/A | N/A | 2025-04-07 | 2025-04-07 | 1 | 1 | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-04-17 | 1899-12-31 | 1 | 2025-04-17 | 2025-04-17 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | 589 | 421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 18.68 | Unknown | Unknown | Unknown | Unknown | 18.68 | Unknown | 807.18 | 18.68 | 788.5 | Yes | N/A | N/A | 2024-07-18 | 2024-07-18 | 1 | 1 | 2024-07-18 | 2024-07-25 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-04-30 | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | Unknown | 2024-08-12 | Unknown | Unknown | 2024-08-12 | 2024-08-12 | 1 | 1 | 1 | 1 | 9 | 7 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-15 | -623 | -446 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-27 | 2025-01-24 | IOU Designed & Installed | N/A | No | N/A | 1376.02 | 188.85 | Unknown | Unknown | Unknown | 1187.17 | 3981 | 1771 | 1376.02 | 394.98 | Yes | N/A | N/A | 2024-11-12 | 2024-11-27 | 16 | 12 | 2024-11-27 | 2024-11-27 | 1 | 1 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2025-01-24 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-01-30 | 1900-01-06 | 5 | 2025-01-30 | 2025-01-30 | 1 | 1 | 75 | 55 | 9 | 7 | 84 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-27 | -564 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-10 | 2024-01-05 | IOU Designed & Installed | N/A | No | N/A | 1442.5 | 399.84 | Unknown | Unknown | 9.89 | 1032.77 | 3981 | 1167.71 | 1442.5 | -274.79 | Yes | N/A | N/A | 2023-10-10 | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-11-16 | 91 | 65 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2024-01-05 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-01-10 | 1900-01-05 | 4 | 2024-01-10 | 2024-01-10 | 1 | 1 | 51 | 37 | 98 | 70 | 149 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 695.05 | 695.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-28 | -445 | -318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-04 | 2023-11-01 | IOU Designed & Installed | N/A | No | N/A | 930.99 | -11.04 | Unknown | Unknown | 21.77 | 920.26 | 3981 | 885.08 | 930.99 | -45.91 | Yes | N/A | N/A | 2023-04-04 | 2023-06-22 | 80 | 58 | 2023-06-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-11-01 | 133 | 95 | Unknown | 2023-11-01 | Unknown | Unknown | 2023-11-01 | 2023-11-08 | 1900-01-07 | 6 | 2023-11-08 | 2023-11-10 | 3 | 3 | 213 | 153 | 11 | 9 | 224 | 162 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 110.05 | 110.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | -425 | -304 | No | 2024-06-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-10 | 2024-06-10 | 2025-02-24 | IOU Designed & Installed | N/A | Yes | 22 | 2937.72 | Unknown | Unknown | Unknown | 68.71 | 2869.01 | 3981 | 1361.26 | 2937.72 | -1576.46 | Yes | N/A | N/A | 2024-06-10 | 2024-07-08 | 29 | 21 | 2024-07-08 | 2024-07-22 | 15 | 11 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2025-02-24 | 201 | 143 | Unknown | 2025-02-21 | Unknown | Unknown | 2025-02-24 | 2025-03-07 | 1900-01-11 | 10 | 2025-03-07 | 2025-03-07 | 1 | 1 | 230 | 164 | 28 | 22 | 258 | 186 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN MARCOS | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-26 | -542 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2024-01-09 | IOU Designed & Installed | N/A | No | N/A | 1608.12 | 437.19 | Unknown | 233.55 | Unknown | 937.38 | 3981 | 359.91 | 1608.12 | -1248.21 | Yes | N/A | N/A | 2023-09-29 | 2023-09-29 | 1 | 1 | 2023-09-29 | 2023-09-29 | 1 | 1 | 2023-09-29 | 2023-10-26 | 11 | 9 | 2023-10-02 | 2023-11-03 | 24 | 18 | 2023-09-29 | 2024-01-09 | 103 | 73 | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-01-31 | 1900-01-22 | 17 | 2024-01-31 | 2024-01-31 | 1 | 1 | 115 | 83 | 49 | 37 | 164 | 120 | Steps 2,3,5,6,7 | 59 | 43 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARDIFF | ENCINITAS | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-02 | -469 | -336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-30 | 2025-01-30 | 2025-03-25 | IOU Designed & Installed | N/A | No | N/A | -15.81 | -20.77 | Unknown | Unknown | Unknown | 4.96 | 3000 | 287.88 | -15.81 | 303.69 | Yes | N/A | N/A | 2025-01-30 | 2025-01-02 | Unknown | Unknown | 2025-01-02 | 2025-03-11 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-03-03 | 29 | 21 | 2025-03-11 | 2025-05-12 | 63 | 45 | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-25 | 2025-05-21 | 1900-02-26 | 42 | 2025-05-21 | 2025-05-21 | 1 | 1 | 63 | 45 | 157 | 113 | 220 | 158 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-24 | -600 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | 343.84 | -25.28 | Unknown | Unknown | Unknown | 369.12 | 3981 | 1534.24 | 343.84 | 1190.4 | Yes | N/A | N/A | 2024-12-05 | 2024-12-05 | 1 | 1 | 2024-12-05 | 2024-12-05 | 1 | 1 | 2024-12-05 | Unknown | Unknown | Unknown | 2024-12-05 | 2025-01-17 | 44 | 32 | 2024-12-05 | 2025-02-19 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-04-03 | 1900-02-12 | 32 | 2025-04-03 | 2025-04-03 | 1 | 1 | 78 | 56 | 90 | 66 | 168 | 122 | Steps 2,3,5,6,7 | 43 | 31 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 10.05 | 10.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-03 | -384 | -275 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-30 | 2024-07-11 | IOU Designed & Installed | N/A | No | N/A | 17.68 | -13.63 | Unknown | Unknown | Unknown | 31.31 | 3981 | 887.86 | 17.68 | 870.18 | Yes | N/A | N/A | 2024-01-18 | 2023-09-12 | Unknown | Unknown | 2023-09-12 | 2024-01-30 | 141 | 101 | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-07-11 | 164 | 118 | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-07-16 | 1900-01-05 | 4 | 2024-07-16 | 2024-07-15 | Unknown | Unknown | 164 | 118 | 147 | 105 | 311 | 223 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 33.05 | 33.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-13 | 217 | 156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-25 | 2024-12-26 | IOU Designed & Installed | N/A | No | N/A | 1135.6 | 390.24 | Unknown | 117.73 | -479 | 1106.63 | 3981 | 1298.09 | 1135.6 | 162.49 | Yes | N/A | N/A | 2023-09-25 | 2023-09-25 | 1 | 1 | 2023-09-25 | 2023-09-25 | 1 | 1 | 2023-09-25 | 2024-08-07 | 318 | 228 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-12-26 | 142 | 102 | Unknown | 2024-12-19 | Unknown | Unknown | 2024-12-26 | 2025-01-16 | 1900-01-21 | 16 | 2025-01-16 | 2025-01-16 | 1 | 1 | 461 | 331 | 24 | 18 | 485 | 349 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-22 | -256 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-30 | 2023-06-02 | IOU Designed & Installed | N/A | No | N/A | -10.06 | -7.3 | Unknown | Unknown | Unknown | -2.76 | Unknown | 495.75 | -10.06 | 505.81 | Yes | N/A | N/A | 2023-05-30 | 2023-05-30 | 1 | 1 | 2023-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | 2023-06-02 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | 2023-07-10 | 1900-02-07 | 27 | 2023-07-10 | 2023-07-10 | 1 | 1 | 5 | 5 | 40 | 28 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN MARCOS | N/A | 72 | 72 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | -599 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-20 | 2024-11-20 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 2064.68 | 251.36 | Unknown | 64.46 | Unknown | 1748.86 | 3981 | 1292.36 | 2064.68 | -772.32 | Yes | N/A | N/A | 2024-11-20 | 2024-11-20 | 1 | 1 | 2024-11-20 | 2024-11-27 | 8 | 6 | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2025-03-05 | 99 | 71 | Unknown | 2025-02-20 | Unknown | Unknown | 2025-03-05 | 2025-03-17 | 1900-01-12 | 9 | 2025-03-17 | 2025-03-17 | 1 | 1 | 100 | 72 | 22 | 16 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | -542 | -389 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-07 | 2024-04-02 | IOU Designed & Installed | N/A | No | N/A | 1389.8 | 437.19 | Unknown | Unknown | Unknown | 952.61 | Unknown | 1139.71 | 1389.8 | -250.09 | Yes | N/A | N/A | 2024-03-07 | 2023-11-21 | Unknown | Unknown | 2023-11-21 | 2024-04-02 | 134 | 96 | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-04-02 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-05-13 | 1900-02-10 | 30 | 2024-05-13 | 2024-05-13 | 1 | 1 | 1 | 1 | 177 | 127 | 178 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | -597 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-13 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 612.54 | -11.7 | Unknown | Unknown | Unknown | 624.24 | 3981 | 1680.28 | 612.54 | 1067.74 | Yes | N/A | N/A | 2025-01-09 | 2024-12-16 | Unknown | Unknown | 2024-12-16 | 2025-01-13 | 29 | 21 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-01-22 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-01-27 | 1900-01-05 | 4 | 2025-01-27 | 2025-01-27 | 1 | 1 | 10 | 8 | 36 | 26 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-13 | 78 | 56 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-05-03 | 2024-11-25 | IOU Designed & Installed | N/A | No | N/A | 25547.77 | 1102.91 | Unknown | 86.98 | 74.84 | 24283.04 | 0 | 12644.56 | 25547.77 | -12903.21 | Yes | N/A | N/A | 2024-01-02 | 2023-11-09 | Unknown | Unknown | 2023-11-09 | 2024-07-18 | 253 | 181 | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-08-01 | 68 | 50 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-30 | 1900-02-04 | 26 | 2024-12-30 | 2024-12-30 | 1 | 1 | 0 | 0 | 358 | 258 | 358 | 258 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-13 | -675 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-27 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | 3564.13 | 923.29 | Unknown | Unknown | Unknown | 2640.84 | 3981 | 1655.68 | 3564.13 | -1908.45 | Yes | N/A | N/A | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | 2025-03-27 | 1 | 1 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-05-06 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-07 | 1900-01-01 | 2 | 2025-05-07 | 2025-05-07 | 1 | 1 | 42 | 30 | 4 | 4 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 138544 | 138544 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-06-02 | -257 | -184 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-06 | 2024-04-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 24.65 | Unknown | Unknown | Unknown | Unknown | 24.65 | 11943 | 756.96 | 24.65 | 732.31 | Yes | N/A | N/A | 2024-04-06 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2024-05-02 | 308 | 220 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-08-15 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | 2024-09-19 | 2024-09-18 | Unknown | Unknown | 106 | 76 | 308 | 220 | 414 | 296 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-05 | -141 | -102 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-07-03 | 2023-08-02 | IOU Designed & Installed | N/A | No | N/A | -5.58 | -10.78 | Unknown | Unknown | Unknown | 5.2 | Unknown | 802.8 | -5.58 | 808.38 | Yes | N/A | N/A | 2023-02-21 | 2023-02-21 | 1 | 1 | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-03 | 2023-08-02 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | 2023-08-17 | 1900-01-15 | 12 | 2023-08-17 | 2023-08-17 | 1 | 1 | 32 | 24 | 17 | 13 | 49 | 37 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 157 | 157 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-26 | -444 | -317 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-07 | 2023-09-14 | IOU Designed & Installed | N/A | No | N/A | -14.45 | -10.57 | Unknown | Unknown | Unknown | -3.88 | Unknown | 483.84 | -14.45 | 498.29 | Yes | N/A | N/A | 2023-04-06 | 2023-04-07 | 2 | 2 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | 2023-09-14 | 161 | 115 | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2023-11-09 | 1900-02-25 | 41 | 2023-11-09 | 2023-11-09 | 1 | 1 | 163 | 117 | 58 | 42 | 221 | 159 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-02 | -508 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | 2024-05-23 | IOU Designed & Installed | N/A | No | N/A | 15.44 | -13.75 | Unknown | Unknown | Unknown | 29.19 | 3981 | 977.96 | 15.44 | 962.52 | Yes | N/A | N/A | 2024-03-28 | 2023-12-06 | Unknown | Unknown | 2023-12-06 | 2024-04-21 | 138 | 98 | 2024-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-21 | 2024-05-23 | 33 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-06-13 | 1900-01-21 | 16 | 2024-06-13 | 2024-06-12 | Unknown | Unknown | 33 | 24 | 160 | 114 | 193 | 138 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-14 | -456 | -326 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-06 | 2024-01-23 | IOU Designed & Installed | N/A | No | N/A | -2.15 | -5.65 | Unknown | Unknown | Unknown | 3.5 | Unknown | 153.49 | -2.15 | 155.64 | Yes | N/A | N/A | 2023-12-06 | 2023-12-27 | 22 | 16 | 2023-12-27 | 2023-12-27 | 1 | 1 | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2024-01-23 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-03-15 | 1900-02-21 | 39 | 2024-03-15 | 2024-03-15 | 1 | 1 | 50 | 36 | 55 | 41 | 105 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-11-01 | 1066 | 763 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-04 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 631.46 | Unknown | Unknown | Unknown | Unknown | 631.46 | 1192.8 | 471.38 | 631.46 | -160.08 | Yes | N/A | N/A | 2024-09-03 | 2024-09-03 | 1 | 1 | 2024-09-03 | 2024-09-09 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2024-10-01 | 23 | 17 | Unknown | 2024-09-23 | Unknown | Unknown | 2024-10-01 | 2024-10-03 | 1900-01-02 | 3 | 2024-10-03 | 2024-10-02 | Unknown | Unknown | 24 | 18 | 10 | 8 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-14 | 2025-05-19 | 2025-06-17 | IOU Designed & Installed | N/A | No | N/A | 48.53 | Unknown | Unknown | Unknown | Unknown | 48.53 | 3981 | 1197.55 | 48.53 | 1149.02 | Yes | N/A | N/A | 2025-05-14 | 2025-05-19 | 6 | 4 | 2025-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | 2025-06-17 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-06-17 | 2025-06-17 | 1899-12-31 | 1 | 2025-06-17 | 2025-06-17 | 1 | 1 | 36 | 26 | 2 | 2 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 75.75 | 75.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-10 | -475 | -340 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2025-01-29 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | 1140.23 | -22.92 | Unknown | Unknown | Unknown | 1163.15 | 3981 | 1881.28 | 1140.23 | 741.05 | Yes | N/A | N/A | 2024-10-10 | 2025-01-21 | 104 | 74 | 2025-01-21 | 2025-01-29 | 9 | 7 | 2025-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-05-06 | 98 | 70 | Unknown | 2025-05-02 | Unknown | Unknown | 2025-05-06 | 2025-05-23 | 1900-01-17 | 14 | 2025-05-23 | 2025-05-23 | 1 | 1 | 202 | 144 | 28 | 22 | 230 | 166 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 13 | 13 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-10 | -537 | -384 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1094.26 | -16 | Unknown | Unknown | 3.46 | 1106.8 | 3981 | 623.05 | 1094.26 | -471.21 | Yes | N/A | N/A | 2023-03-22 | 2023-06-09 | 80 | 58 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | Unknown | Unknown | Unknown | 2023-08-23 | Unknown | Unknown | 2023-08-23 | 2023-08-23 | 1 | 1 | 80 | 58 | 1 | 1 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-29 | 987 | 706 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-30 | 2024-02-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 824.9 | -15.1 | Unknown | Unknown | Unknown | 840 | 16506 | 2181.15 | 824.9 | 1356.25 | Yes | N/A | N/A | 2024-01-30 | 2024-02-02 | 4 | 4 | 2024-02-02 | 2024-05-30 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-04-19 | 24 | 18 | 2024-05-30 | 2024-11-08 | 163 | 117 | Unknown | 2024-12-19 | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | 2025-01-10 | 2025-01-10 | 1 | 1 | 167 | 121 | 144 | 104 | 311 | 225 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-10 | -564 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-28 | 2024-01-12 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | 201.77 | -8.71 | Unknown | Unknown | Unknown | 210.48 | Unknown | 1001.18 | 201.77 | 799.41 | Yes | N/A | N/A | 2023-12-28 | 2024-01-16 | 20 | 14 | 2024-01-16 | 2024-01-16 | 1 | 1 | 2024-01-16 | Unknown | Unknown | Unknown | 2024-01-12 | 2024-02-23 | 43 | 31 | 2024-01-16 | 2024-03-14 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-03-25 | 1900-01-11 | 8 | 2024-03-25 | 2024-03-25 | 1 | 1 | 79 | 57 | 57 | 41 | 136 | 98 | Steps 2,3,5,6,7 | 38 | 28 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | -520 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | 2025-03-07 | IOU Designed & Installed | N/A | No | N/A | -469.21 | Unknown | Unknown | Unknown | -1147.27 | 678.06 | Unknown | 1158.4 | -469.21 | 1627.61 | Yes | N/A | N/A | 2024-10-02 | 2024-11-05 | 35 | 25 | 2024-11-05 | 2024-11-07 | 3 | 3 | 2024-11-07 | 2025-02-03 | 89 | 63 | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-03-07 | 31 | 23 | Unknown | 2025-02-27 | Unknown | Unknown | 2025-03-07 | 2025-04-09 | 1900-02-02 | 24 | 2025-04-09 | 2025-04-09 | 1 | 1 | 155 | 111 | 38 | 28 | 193 | 139 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-19 | -486 | -347 | No | 2024-05-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | Yes | 99 | 335.98 | Unknown | Unknown | Unknown | 22.63 | 313.35 | 3981 | 942.86 | 335.98 | 606.88 | Yes | N/A | N/A | 2024-05-02 | 2024-08-07 | 98 | 70 | 2024-08-07 | 2024-08-09 | 3 | 3 | 2024-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | 2024-12-19 | 2024-12-19 | 1 | 1 | 98 | 70 | 4 | 4 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 365.05 | 365.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-16 | -530 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-11 | 2023-12-11 | 2024-02-28 | IOU Designed & Installed | N/A | No | N/A | 1833.09 | 484.15 | Unknown | 48.93 | 4.72 | 1295.29 | 3981 | 231.98 | 1833.09 | -1601.11 | Yes | N/A | N/A | 2023-12-11 | 2023-12-21 | 11 | 9 | 2023-12-21 | 2024-01-12 | 23 | 17 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | 2024-02-28 | 48 | 34 | Unknown | 2024-03-01 | Unknown | Unknown | 2024-02-28 | 2024-03-04 | 1900-01-05 | 4 | 2024-03-04 | 2024-03-04 | 1 | 1 | 59 | 43 | 30 | 22 | 89 | 65 | Steps 2,3,5,6,7 | 2 | 2 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-28 | -134 | -97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-07-25 | IOU Designed & Installed | N/A | No | N/A | -901.69 | -15.58 | Unknown | Unknown | -1806 | 919.89 | Unknown | 1805.74 | -901.69 | 2707.43 | Yes | N/A | N/A | 2023-02-08 | 2023-02-08 | 1 | 1 | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | 2023-07-25 | 71 | 51 | Unknown | 2023-07-24 | Unknown | Unknown | 2023-07-25 | 2023-08-16 | 1900-01-22 | 17 | 2023-08-16 | 2023-08-16 | 1 | 1 | 72 | 52 | 24 | 18 | 96 | 70 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-19 | -536 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | -487.62 | -6.54 | Unknown | Unknown | -1304.86 | 823.78 | Unknown | 1305.74 | -487.62 | 1793.36 | Yes | N/A | N/A | 2024-01-11 | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2024-01-25 | 46 | 34 | 2024-01-25 | 2024-02-08 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-03-25 | 47 | 33 | Unknown | 2024-03-22 | Unknown | Unknown | 2024-03-25 | 2024-04-01 | 1900-01-07 | 6 | 2024-04-01 | 2024-04-01 | 1 | 1 | 62 | 44 | 55 | 41 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-11-30 | -578 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-05 | 2024-03-05 | 2024-04-19 | IOU Designed & Installed | N/A | No | N/A | 390.2 | 122.45 | Unknown | Unknown | Unknown | 267.75 | 3941 | 898.63 | 390.2 | 508.43 | Yes | N/A | N/A | 2024-03-05 | 2024-01-03 | Unknown | Unknown | 2024-01-03 | 2024-03-05 | 63 | 45 | 2024-03-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-05 | 2024-04-19 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2024-05-01 | 1900-01-12 | 9 | 2024-05-01 | 2024-05-01 | 1 | 1 | 46 | 34 | 77 | 55 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | -654 | -469 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | 2024-11-12 | IOU Designed & Installed | N/A | No | N/A | 2012.93 | Unknown | Unknown | Unknown | Unknown | 2012.93 | 3981 | 1401.8 | 2012.93 | -611.13 | Yes | N/A | N/A | 2024-10-18 | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2024-10-18 | 24 | 18 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-11-12 | 26 | 18 | Unknown | 2024-11-08 | Unknown | Unknown | 2024-11-12 | 2024-12-02 | 1900-01-20 | 15 | 2024-12-02 | 2024-12-02 | 1 | 1 | 26 | 18 | 46 | 34 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | N/A | Encinitas | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-17 | 399 | 286 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-30 | 2022-12-13 | 2023-06-29 | IOU Designed & Installed | N/A | No | N/A | -4173.5 | 4214.9 | Unknown | Unknown | -34358.92 | 25970.52 | Unknown | 37258.31 | -4173.5 | 41431.81 | Yes | N/A | N/A | 2022-11-30 | 2023-03-14 | 105 | 75 | 2023-03-14 | 2023-05-22 | 70 | 50 | 2023-02-16 | 2023-05-15 | 42 | 28 | 2023-02-06 | 2023-05-19 | 32 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-29 | 2023-07-21 | 1900-01-22 | 17 | 2023-07-21 | 2023-07-21 | 1 | 1 | 147 | 103 | 126 | 94 | 273 | 197 | Steps 2,3,5,6,7 | 193 | 137 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LADERA RANCH | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | -252 | -181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 9.38 | Unknown | Unknown | Unknown | Unknown | 9.38 | 3981 | 192.51 | 9.38 | 183.13 | Yes | N/A | N/A | 2024-06-19 | 2024-06-21 | 3 | 3 | 2024-06-21 | 2024-07-12 | 22 | 16 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | Unknown | Unknown | 2024-09-05 | 2024-09-05 | 1 | 1 | 3 | 3 | 23 | 17 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 47.1 | 47.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-31 | 302 | 217 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-10-23 | 2024-03-15 | IOU Designed & Installed | N/A | No | N/A | 912.77 | -34.54 | Unknown | Unknown | Unknown | 947.31 | 3981 | 1067.31 | 912.77 | 154.54 | Yes | N/A | N/A | 2023-10-05 | 2023-10-19 | 15 | 11 | 2023-10-19 | 2023-10-23 | 5 | 3 | 2023-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2024-03-15 | 145 | 105 | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-04-01 | 1900-01-17 | 12 | 2024-04-01 | 2024-03-28 | Unknown | Unknown | 160 | 116 | 23 | 15 | 183 | 131 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | POWAY | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-21 | -700 | -501 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-08 | 2025-05-08 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1102.57 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-08 | 2025-04-28 | Unknown | Unknown | 2025-04-28 | 2025-05-08 | 11 | 9 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-05-16 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-05-21 | 1900-01-05 | 4 | 2025-05-21 | 2025-05-21 | 1 | 1 | 9 | 7 | 18 | 14 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-16 | -672 | -481 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-01 | 2025-04-14 | IOU Designed & Installed | N/A | No | N/A | 2114.46 | 466.05 | Unknown | 262.64 | Unknown | 1385.77 | 3981 | 1733.11 | 2114.46 | -381.35 | Yes | N/A | N/A | 2025-04-01 | 2025-03-18 | Unknown | Unknown | 2025-03-18 | 2025-04-10 | 24 | 18 | 2025-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-14 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | 2025-05-13 | 1900-01-29 | 22 | 2025-05-13 | 2025-05-13 | 1 | 1 | 6 | 4 | 55 | 41 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 56.4 | 56.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-08 | -109 | -79 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | -17.84 | -13.5 | Unknown | Unknown | Unknown | -4.34 | Unknown | 468.93 | -17.84 | 486.77 | Yes | N/A | N/A | 2023-09-15 | 2023-11-01 | 48 | 34 | 2023-11-01 | 2023-12-12 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2023-11-28 | 8 | 6 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | Unknown | Unknown | 2024-02-20 | 2024-02-20 | 1 | 1 | 48 | 34 | 51 | 37 | 99 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-11 | -668 | -479 | No | 2025-03-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-04-02 | 2025-04-03 | IOU Designed & Installed | N/A | Yes | 20 | 536.48 | -10.2 | Unknown | Unknown | Unknown | 546.68 | 3981 | 1147.11 | 536.48 | 610.63 | Yes | N/A | N/A | 2025-03-13 | 2025-04-02 | 21 | 15 | 2025-04-02 | 2025-04-02 | 1 | 1 | 2025-04-02 | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-08 | 6 | 4 | 2025-04-02 | 2025-04-03 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-14 | 1900-01-11 | 8 | 2025-04-14 | 2025-04-14 | 1 | 1 | 23 | 17 | 20 | 14 | 43 | 31 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | -412 | -295 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-01 | 2023-07-03 | 2023-08-03 | IOU Designed & Installed | N/A | No | N/A | 3649.14 | Unknown | Unknown | Unknown | Unknown | 3649.14 | Unknown | 270.38 | 3649.14 | -3378.76 | Yes | N/A | N/A | 2023-07-01 | 2023-07-18 | 18 | 12 | 2023-07-18 | 2023-07-20 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-03 | 2023-08-18 | 1900-01-15 | 12 | 2023-08-18 | 2023-08-18 | 1 | 1 | 18 | 12 | 20 | 16 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 2096.1 | 2096.1 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-05-10 | 45 | 32 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | 2024-03-19 | IOU Designed & Installed | N/A | No | N/A | 7.65 | -6.83 | Unknown | Unknown | Unknown | 14.48 | 7882 | 838.38 | 7.65 | 830.73 | Yes | N/A | N/A | 2023-08-08 | 2023-05-19 | Unknown | Unknown | 2023-05-19 | 2023-08-08 | 82 | 58 | 2023-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | 2024-03-19 | 225 | 161 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-03-28 | 1900-01-09 | 8 | 2024-03-28 | 2024-06-24 | 89 | 63 | 225 | 161 | 181 | 129 | 406 | 290 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-25 | -597 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-02-09 | 2023-03-07 | IOU Designed & Installed | N/A | No | N/A | 418.75 | 243.32 | Unknown | Unknown | Unknown | 175.43 | Unknown | 471.05 | 418.75 | 52.3 | Yes | N/A | N/A | 2023-01-31 | 2023-02-09 | 10 | 8 | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-09 | 2023-03-07 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | 2023-03-08 | 1900-01-01 | 2 | 2023-03-08 | 2023-03-08 | 1 | 1 | 37 | 27 | 3 | 3 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 566.05 | 566.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-23 | -161 | -116 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-02-06 | 2024-03-28 | IOU Designed & Installed | N/A | No | N/A | 3012.2 | Unknown | Unknown | Unknown | Unknown | 3012.2 | 3981 | 1123.64 | 3012.2 | -1888.56 | Yes | N/A | N/A | 2024-01-03 | 2024-01-02 | Unknown | Unknown | 2024-01-02 | 2024-02-22 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-03-25 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-04-17 | 1900-01-20 | 15 | 2024-04-17 | 2024-04-15 | Unknown | Unknown | 33 | 23 | 73 | 53 | 106 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-22 | 348 | 249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2025-03-14 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 2094.49 | Unknown | Unknown | Yes | N/A | N/A | 2023-10-19 | 2023-10-19 | 1 | 1 | 2023-10-19 | Unknown | Unknown | Unknown | 2025-03-20 | 2025-03-21 | 2 | 2 | 2025-03-21 | 2025-03-26 | 6 | 4 | Unknown | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-04-25 | 1899-12-31 | 1 | 2025-04-25 | 2025-06-05 | 42 | 30 | 3 | 3 | 49 | 35 | 52 | 38 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-25 | 1 | 1 | No | 2023-01-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-09 | 2023-01-09 | 2023-09-27 | IOU Designed & Installed | N/A | Yes | 98 | 1393.02 | -3.71 | Unknown | Unknown | 88.24 | 1308.49 | 0 | 680.98 | 1393.02 | -712.04 | Yes | N/A | N/A | 2023-01-09 | 2023-04-17 | 99 | 71 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-21 | 2023-09-27 | 219 | 157 | Unknown | 2024-07-12 | Unknown | Unknown | 2023-09-27 | 2024-08-26 | 1900-11-30 | 239 | 2024-08-26 | 2024-08-26 | 1 | 1 | 318 | 228 | 336 | 240 | 654 | 468 | Steps 2,3,5,6,7 | 289 | 207 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 119.05 | 119.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-06 | -319 | -228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-07-10 | 2024-08-18 | IOU Designed & Installed | N/A | No | N/A | 3106.61 | 706.11 | Unknown | 247.46 | Unknown | 2153.04 | 3981 | 1457.53 | 3106.61 | -1649.08 | Yes | N/A | N/A | 2023-03-21 | 2023-07-11 | 113 | 81 | 2023-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | 2024-08-18 | 405 | 289 | Unknown | 2024-08-02 | Unknown | Unknown | 2024-08-18 | 2024-08-21 | 1900-01-03 | 3 | 2024-08-21 | 2024-08-21 | 1 | 1 | 518 | 370 | 5 | 4 | 523 | 374 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-31 | -571 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 443.98 | -7.84 | Unknown | Unknown | Unknown | 451.82 | 7962 | 1132.73 | 443.98 | 688.75 | Yes | N/A | N/A | 2025-02-04 | 2025-02-04 | 1 | 1 | 2025-02-04 | 2025-02-04 | 1 | 1 | 2025-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | 2025-04-09 | 2025-04-08 | Unknown | Unknown | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-29 | 176 | 126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-09 | 2023-09-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2479.52 | -87.69 | Unknown | Unknown | -589.91 | 3157.12 | 0 | 777.02 | 2479.52 | -1702.5 | Yes | N/A | N/A | 2023-06-09 | 2023-08-24 | 77 | 55 | 2023-08-24 | 2023-10-12 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-21 | Unknown | Unknown | 2024-09-21 | 2024-09-21 | 1 | 0 | 77 | 55 | 51 | 36 | 128 | 91 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 194 | 194 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-16 | -191 | -138 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.48 | -4.27 | Unknown | Unknown | Unknown | 2.79 | 3981 | 995.25 | -1.48 | 996.73 | Yes | N/A | N/A | 2023-03-31 | 2023-04-07 | 8 | 6 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-08-09 | 1 | 1 | 8 | 6 | 1 | 1 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | Encinitas | N/A | 30000 | 30000 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-11-01 | 364 | 261 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-23 | 2022-09-27 | 2023-10-17 | IOU Designed & Installed | N/A | No | N/A | 24663.43 | 680.07 | Unknown | Unknown | 1821.24 | 22162.12 | Unknown | 16499.29 | 24663.43 | -8164.14 | Yes | N/A | N/A | 2022-02-23 | 2023-06-20 | 483 | 345 | 2023-06-20 | 2023-08-01 | 43 | 31 | 2023-06-13 | 2023-07-19 | 37 | 27 | 2023-08-04 | 2023-08-14 | 11 | 7 | 2023-09-11 | Unknown | Unknown | Unknown | 2023-09-11 | 2023-10-16 | 36 | 26 | 2023-10-17 | 2023-10-31 | 1900-01-14 | 11 | 2023-10-31 | 2023-10-31 | 1 | 1 | 520 | 372 | 106 | 76 | 626 | 448 | Steps 2,3,5,6,7 | 49 | 35 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-05 | -175 | -126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-22 | 2023-11-22 | 2023-12-20 | IOU Designed & Installed | N/A | No | N/A | 0.25 | -0.57 | Unknown | Unknown | Unknown | 0.82 | 3459 | 619.73 | 0.25 | 619.48 | Yes | N/A | N/A | 2023-11-22 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | 2023-11-22 | 6 | 4 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2023-12-20 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-01-12 | 1900-01-23 | 18 | 2024-01-12 | 2024-01-12 | 1 | 1 | 29 | 21 | 31 | 23 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 131.05 | 131.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-30 | -144 | -103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-08-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 391.01 | 217.63 | Unknown | 32.18 | Unknown | 141.2 | 3981 | 158.14 | 391.01 | -232.87 | Yes | N/A | N/A | 2023-08-29 | 2023-11-01 | 65 | 47 | 2023-11-01 | 2023-11-02 | 2 | 2 | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2024-02-07 | 1 | 1 | 65 | 47 | 3 | 3 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-06 | -533 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-14 | 2025-02-14 | 2025-05-08 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 506.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-14 | 2025-02-14 | 1 | 1 | 2025-02-14 | 2025-02-14 | 1 | 1 | 2025-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-05-08 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-05-22 | 1900-01-14 | 11 | 2025-05-22 | 2025-05-22 | 1 | 1 | 85 | 61 | 17 | 13 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -554 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 603.82 | Unknown | Unknown | Unknown | 8.56 | 595.26 | 3981 | 1186.58 | 603.82 | 582.76 | Yes | N/A | N/A | 2024-06-12 | 2024-06-20 | 9 | 7 | 2024-06-20 | 2024-06-20 | 1 | 1 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-30 | 41 | 29 | Unknown | 2025-03-05 | Unknown | Unknown | 2024-07-30 | 2024-08-16 | 1900-01-17 | 14 | 2024-08-16 | 2024-08-24 | 9 | 6 | 50 | 36 | 28 | 21 | 78 | 57 | Steps 2,3,5,6,7 | 218 | 156 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Residential | N/A | SD 1187-G1 SOLANA HGLND PH1 (E) | SOLANA BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 611 | 437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-07 | 2021-09-07 | 2025-04-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 588693.06 | 237759.4 | Unknown | Unknown | 2074.72 | 348858.94 | 749292 | 262231.89 | 588693.06 | -326461.17 | Yes | N/A | N/A | 2021-09-07 | 2023-11-17 | 802 | 574 | 2023-11-17 | 2024-07-31 | 258 | 184 | 2024-01-24 | 2025-04-16 | 401 | 287 | 2023-06-06 | 2025-05-22 | 527 | 375 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2025-04-10 | 238 | 170 | 2025-04-25 | 2025-06-17 | 1900-02-22 | 38 | 2025-06-17 | 2025-06-17 | 1 | 1 | 1203 | 861 | 1078 | 768 | 2281 | 1629 | Steps 2,3,5,6,7 | 869 | 621 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-06 | -276 | -198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-08 | 2023-09-28 | IOU Designed & Installed | N/A | No | N/A | -739.8 | 1400.14 | Unknown | 261.57 | -3179 | 777.49 | Unknown | 3178.68 | -739.8 | 3918.48 | Yes | N/A | N/A | 2023-09-08 | 2023-09-08 | 1 | 1 | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-10-04 | 1900-01-06 | 5 | 2023-10-04 | 2023-10-04 | 1 | 1 | 1 | 1 | 8 | 6 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-28 | -638 | -456 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-17 | 2024-06-17 | IOU Designed & Installed | N/A | No | N/A | 14.51 | -12.88 | Unknown | Unknown | Unknown | 27.39 | Unknown | 904.8 | 14.51 | 890.29 | Yes | N/A | N/A | 2024-05-17 | 2024-04-02 | Unknown | Unknown | 2024-04-02 | 2024-05-17 | 46 | 34 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-17 | 32 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-06-28 | 1900-01-11 | 10 | 2024-06-28 | 2024-06-28 | 1 | 1 | 32 | 22 | 59 | 45 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2018-08-30 | 2260 | 1615 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 399.98 | -7.02 | Unknown | Unknown | Unknown | 407 | 0 | 3710.53 | 399.98 | 3310.55 | Yes | N/A | N/A | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | 2023-11-13 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | 2024-11-04 | 358 | 256 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | Unknown | Unknown | 2024-11-11 | 2024-11-06 | Unknown | Unknown | 359 | 257 | 8 | 6 | 367 | 263 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 74 | 74 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-05 | -519 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-10-13 | 2023-10-20 | IOU Designed & Installed | N/A | No | N/A | -11.65 | -8.82 | Unknown | Unknown | Unknown | -2.83 | Unknown | 514.57 | -11.65 | 526.22 | Yes | N/A | N/A | 2023-09-29 | 2023-10-13 | 15 | 11 | 2023-10-13 | 2023-10-13 | 1 | 1 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-10-20 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2024-02-02 | 1900-04-15 | 76 | 2024-02-02 | 2024-02-02 | 1 | 1 | 23 | 17 | 108 | 78 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-25 | -575 | -411 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-20 | 2024-12-16 | IOU Designed & Installed | N/A | No | N/A | 49.56 | Unknown | Unknown | Unknown | Unknown | 49.56 | 3981 | 2037.04 | 49.56 | 1987.48 | Yes | N/A | N/A | 2024-09-05 | 2024-09-16 | 12 | 8 | 2024-09-16 | 2024-09-20 | 5 | 5 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-12-16 | 88 | 62 | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2024-12-30 | 1900-01-14 | 11 | 2024-12-30 | 2024-12-27 | Unknown | Unknown | 100 | 70 | 20 | 16 | 120 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-18 | -699 | -500 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-01 | 2025-05-14 | IOU Designed & Installed | N/A | No | N/A | 62.21 | -1.25 | Unknown | Unknown | Unknown | 63.46 | 3981 | 1256.86 | 62.21 | 1194.65 | Yes | N/A | N/A | 2025-05-01 | 2025-05-01 | 1 | 1 | 2025-05-01 | 2025-05-01 | 1 | 1 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-14 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-05-19 | 1900-01-05 | 4 | 2025-05-19 | 2025-05-19 | 1 | 1 | 15 | 11 | 8 | 6 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-06 | -570 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-11 | 2024-10-15 | 2024-12-02 | IOU Designed & Installed | N/A | No | N/A | 2160.92 | 513.54 | Unknown | Unknown | Unknown | 1647.38 | 3981 | 1619.93 | 2160.92 | -540.99 | Yes | N/A | N/A | 2024-10-11 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-10-15 | 91 | 65 | 2024-10-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-12-02 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-12-02 | 2024-12-13 | 1900-01-11 | 10 | 2024-12-13 | 2024-12-13 | 1 | 1 | 49 | 35 | 104 | 76 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-26 | -80 | -59 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-27 | 2023-01-27 | 2023-08-01 | IOU Designed & Installed | N/A | No | N/A | -8.27 | -9.61 | Unknown | Unknown | Unknown | 1.34 | Unknown | 148.62 | -8.27 | 156.89 | Yes | N/A | N/A | 2023-01-27 | 2023-05-18 | 112 | 80 | 2023-05-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | 2023-08-01 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-08-07 | 1900-01-06 | 5 | 2023-08-07 | 2023-08-07 | 1 | 1 | 188 | 134 | 8 | 6 | 196 | 140 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 72.05 | 72.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-27 | -373 | -267 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | 2024-05-22 | 2024-12-16 | IOU Designed & Installed | N/A | No | N/A | 2418.33 | 620.07 | Unknown | 131.73 | Unknown | 1666.53 | 3981 | 1297.91 | 2418.33 | -1120.42 | Yes | N/A | N/A | 2024-05-16 | 2024-05-22 | 7 | 5 | 2024-05-22 | 2024-05-22 | 1 | 1 | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-12-16 | 209 | 149 | Unknown | Unknown | Unknown | Unknown | 2024-12-16 | 2024-12-19 | 1900-01-03 | 4 | 2024-12-19 | 2024-12-19 | 1 | 1 | 216 | 154 | 6 | 6 | 222 | 160 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | SAN CLEMENTE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-03 | 15 | 12 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4974.95 | 1373.48 | Unknown | 672.8 | 91.93 | 2836.74 | 3981 | 684.72 | 4974.95 | -4290.23 | Yes | N/A | N/A | 2023-03-21 | 2023-03-31 | 11 | 9 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | 2023-04-03 | 4 | 2 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 11 | 9 | 5 | 3 | 16 | 12 | Steps 2,3,5,6,7 | 3 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-08 | -588 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-15 | 2025-01-14 | IOU Designed & Installed | N/A | No | N/A | 5104.63 | 1024.86 | Unknown | 154.96 | 18.43 | 3906.38 | Unknown | 1545.31 | 5104.63 | -3559.32 | Yes | N/A | N/A | 2024-11-11 | 2024-10-31 | Unknown | Unknown | 2024-10-31 | 2024-11-15 | 16 | 12 | 2024-11-15 | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-05 | 21 | 15 | 2024-11-15 | 2025-01-14 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-02-27 | 1900-02-13 | 33 | 2025-02-27 | 2025-02-27 | 1 | 1 | 61 | 43 | 83 | 61 | 144 | 104 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-21 | -551 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-15 | 2023-09-15 | 2023-10-22 | IOU Designed & Installed | N/A | No | N/A | -384.14 | Unknown | Unknown | Unknown | Unknown | -384.14 | Unknown | 55.17 | -384.14 | 439.31 | Yes | N/A | N/A | 2023-09-15 | 2023-06-29 | Unknown | Unknown | 2023-06-29 | 2023-10-06 | 100 | 72 | 2023-10-06 | Unknown | Unknown | Unknown | 2023-11-16 | 2023-11-20 | 5 | 3 | 2023-10-06 | 2023-10-22 | 17 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-10-22 | 2023-12-18 | 1900-02-26 | 41 | 2023-12-18 | 2023-12-18 | 1 | 1 | 17 | 11 | 164 | 117 | 181 | 128 | Steps 2,3,5,6,7 | 45 | 31 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-17 | -617 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-02 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 1540.2 | 397.1 | Unknown | Unknown | Unknown | 1143.1 | 3981 | 987.03 | 1540.2 | -553.17 | Yes | N/A | N/A | 2025-01-02 | 2025-01-02 | 1 | 1 | 2025-01-02 | 2025-01-02 | 1 | 1 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-02-20 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-04-09 | 1900-02-17 | 35 | 2025-04-09 | 2025-04-09 | 1 | 1 | 51 | 37 | 51 | 37 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | 6.05 | 6.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-15 | 229 | 164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-01 | 2024-03-01 | 2025-01-28 | IOU Designed & Installed | N/A | No | N/A | 2159.78 | 418.58 | Unknown | 271.12 | Unknown | 1470.08 | 3981 | 1058.95 | 2159.78 | -1100.83 | Yes | N/A | N/A | 2024-03-01 | 2024-01-26 | Unknown | Unknown | 2024-01-26 | 2024-03-01 | 36 | 26 | 2024-03-01 | 2024-03-20 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2025-01-28 | 273 | 195 | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-01-29 | 1900-01-01 | 2 | 2025-01-29 | 2025-01-30 | 2 | 2 | 274 | 196 | 40 | 30 | 314 | 226 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 1550 | 1550 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-09-01 | 262 | 187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | 2024-04-26 | IOU Designed & Installed | N/A | No | N/A | -727.86 | -39.41 | Unknown | Unknown | -1145 | 456.55 | 3981 | 1754.85 | -727.86 | 2482.71 | Yes | N/A | N/A | 2023-10-27 | 2023-10-27 | 1 | 1 | 2023-10-27 | 2023-10-27 | 1 | 1 | 2023-10-27 | 2023-11-06 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2024-04-26 | 179 | 129 | Unknown | 2024-02-21 | Unknown | Unknown | 2024-04-26 | 2024-05-15 | 1900-01-19 | 14 | 2024-05-15 | 2024-05-20 | 6 | 4 | 191 | 137 | 27 | 19 | 218 | 156 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | Both | IOU Design | Residential | Underserved Community | VALLEY CENTER | COUNTY OF SAN DIEGO-NORTH of 56 | 115.05 | 115.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | -449 | -321 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-31 | 2023-09-18 | 2023-11-07 | IOU Designed & Installed | N/A | No | N/A | 18329.03 | 2774.48 | Unknown | Unknown | -3922.05 | 19476.6 | 3981 | 12031.55 | 18329.03 | -6297.48 | Yes | N/A | N/A | 2023-08-31 | 2023-03-08 | Unknown | Unknown | 2023-03-08 | 2023-09-18 | 195 | 139 | 2023-09-18 | 2023-10-02 | 15 | 11 | 2023-09-25 | 2023-10-13 | 11 | 9 | 2023-10-02 | 2023-11-07 | 37 | 27 | Unknown | 2023-10-25 | Unknown | Unknown | 2023-11-07 | 2024-02-27 | 1900-04-22 | 81 | 2024-02-27 | 2023-12-01 | Unknown | Unknown | 52 | 38 | 319 | 229 | 371 | 267 | Steps 2,3,5,6,7 | 18 | 14 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 91.05 | 91.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-31 | -557 | -399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-15 | 2025-04-08 | IOU Designed & Installed | N/A | No | N/A | -1397.33 | -9.98 | Unknown | Unknown | -1910 | 522.65 | Unknown | 1770.12 | -1397.33 | 3167.45 | Yes | N/A | N/A | 2025-01-15 | 2025-01-15 | 1 | 1 | 2025-01-15 | 2025-01-15 | 1 | 1 | 2025-01-15 | 2025-03-04 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-04-08 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-22 | 1900-01-14 | 11 | 2025-04-22 | 2025-04-22 | 1 | 1 | 86 | 62 | 17 | 13 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-29 | -195 | -140 | No | 2023-02-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-12-15 | IOU Designed & Installed | N/A | Yes | 282 | 4228.09 | 682.14 | Unknown | 324.64 | 43.59 | 3177.72 | 3981 | 828.63 | 4228.09 | -3399.46 | Yes | N/A | N/A | 2023-02-08 | 2023-11-08 | 274 | 196 | 2023-11-08 | 2023-11-17 | 10 | 8 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | 2023-12-15 | 311 | 223 | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2024-03-14 | 1900-03-31 | 65 | 2024-03-14 | 2024-03-18 | 5 | 3 | 585 | 419 | 106 | 76 | 691 | 495 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-08 | -570 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | 2023-04-15 | IOU Designed & Installed | N/A | No | N/A | 1677.36 | 561.84 | Unknown | 176.2 | Unknown | 939.32 | 3981 | 663.87 | 1677.36 | -1013.49 | Yes | N/A | N/A | 2023-02-03 | 2023-02-03 | 1 | 1 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | 2023-04-15 | 72 | 51 | Unknown | Unknown | Unknown | Unknown | 2023-04-15 | 2023-04-18 | 1900-01-03 | 2 | 2023-04-18 | 2023-04-18 | 1 | 1 | 73 | 52 | 5 | 3 | 78 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-15 | -319 | -228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2025-01-08 | 2025-03-19 | IOU Designed & Installed | N/A | No | N/A | 23648.13 | 6815.08 | Unknown | 814.59 | 333.21 | 15685.25 | 3981 | 2014 | 23648.13 | -21634.13 | Yes | N/A | N/A | 2024-12-19 | 2025-01-06 | 19 | 13 | 2025-01-06 | 2025-01-08 | 3 | 3 | 2025-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-03-19 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-04-03 | 1900-01-15 | 12 | 2025-04-03 | 2025-04-02 | Unknown | Unknown | 90 | 64 | 19 | 15 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | 8 | 7 | No | 2022-05-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-03 | 2022-05-19 | Unknown | IOU Designed & Installed | N/A | Yes | 274 | 1462.08 | -28.46 | Unknown | Unknown | Unknown | 1490.54 | 3885 | 852.46 | 1462.08 | -609.62 | Yes | N/A | N/A | 2022-05-03 | 2023-02-01 | 275 | 197 | 2023-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-01-08 | 1 | 1 | 275 | 197 | 1 | 1 | 276 | 198 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | DEL MAR | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-28 | -610 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-04-25 | 2024-05-09 | IOU Designed & Installed | N/A | No | N/A | 923.04 | 511.99 | Unknown | Unknown | Unknown | 411.05 | Unknown | 1068.07 | 923.04 | 145.03 | Yes | N/A | N/A | 2024-04-15 | 2024-04-25 | 11 | 9 | 2024-04-25 | 2024-04-25 | 1 | 1 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-05-09 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-05-28 | 1900-01-19 | 14 | 2024-05-28 | 2024-05-28 | 1 | 1 | 26 | 20 | 22 | 16 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-12 | -578 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-07 | 2024-06-06 | 2024-08-19 | IOU Designed & Installed | N/A | No | N/A | 123.05 | -1.88 | Unknown | Unknown | Unknown | 124.93 | Unknown | 1440.48 | 123.05 | 1317.43 | Yes | N/A | N/A | 2024-05-07 | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2024-06-06 | 52 | 38 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-08-19 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-09-11 | 1900-01-23 | 18 | 2024-09-11 | 2024-09-11 | 1 | 1 | 75 | 53 | 77 | 57 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | -226 | -163 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-17 | 2023-04-17 | 2023-06-27 | IOU Designed & Installed | N/A | No | N/A | 421.37 | -20.47 | Unknown | Unknown | -357.26 | 799.1 | Unknown | 613.57 | 421.37 | 192.2 | Yes | N/A | N/A | 2023-04-17 | 2023-04-28 | 12 | 10 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2023-06-27 | 23 | 17 | Unknown | 2023-06-23 | Unknown | Unknown | 2023-06-27 | 2023-07-19 | 1900-01-22 | 17 | 2023-07-19 | 2023-07-19 | 1 | 1 | 35 | 27 | 24 | 18 | 59 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-08 | -35 | -26 | No | 2023-03-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-11-02 | IOU Designed & Installed | N/A | Yes | 177 | 416.16 | 146.28 | Unknown | Unknown | Unknown | 269.88 | 3981 | 944.56 | 416.16 | 528.4 | Yes | N/A | N/A | 2023-03-21 | 2023-09-14 | 178 | 128 | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-11-02 | 227 | 163 | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2023-11-03 | 1900-01-01 | 2 | 2023-11-03 | 2023-11-03 | 1 | 1 | 405 | 291 | 3 | 3 | 408 | 294 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -200 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-11-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 213.4 | -10.16 | Unknown | Unknown | Unknown | 223.56 | 3981 | 899.23 | 213.4 | 685.83 | Yes | N/A | N/A | 2023-10-16 | 2023-07-28 | Unknown | Unknown | 2023-07-28 | 2025-03-06 | 588 | 420 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | Unknown | Unknown | 2024-07-09 | 2024-07-08 | Unknown | Unknown | 0 | 0 | 588 | 420 | 588 | 420 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community,Tribal Community | WARNER SPRINGS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -105 | -76 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-05-04 | 2024-08-23 | IOU Designed & Installed | N/A | No | N/A | 7201.57 | Unknown | Unknown | Unknown | Unknown | 7201.57 | 6691 | 391.04 | 7201.57 | -6810.53 | Yes | N/A | N/A | 2023-04-19 | 2023-05-04 | 16 | 12 | 2023-05-04 | 2024-03-26 | 328 | 234 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-08-06 | 134 | 96 | Unknown | 2024-08-09 | Unknown | Unknown | 2024-08-23 | 2024-09-24 | 1900-02-01 | 23 | 2024-09-24 | 2024-09-17 | Unknown | Unknown | 150 | 108 | 361 | 257 | 511 | 365 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-12-31 | 1532 | 1095 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 405.06 | -6.7 | Unknown | Unknown | Unknown | 411.76 | 0 | 2013.04 | 405.06 | 1607.98 | Yes | N/A | N/A | 2024-03-07 | 2024-03-19 | 13 | 9 | 2024-03-19 | 2024-04-17 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-04-04 | 16 | 12 | 2024-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | Unknown | Unknown | 2025-03-12 | 2025-03-12 | 1 | 1 | 13 | 9 | 47 | 35 | 60 | 44 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 60.05 | 60.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-07 | -472 | -337 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | 27.59 | Unknown | Unknown | Unknown | Unknown | 27.59 | Unknown | 1449.92 | 27.59 | 1422.33 | Yes | N/A | N/A | 2024-08-29 | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-08-29 | 79 | 57 | 2024-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2025-02-11 | 167 | 119 | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-02-20 | 1900-01-09 | 8 | 2025-02-20 | 2025-02-20 | 1 | 1 | 167 | 119 | 90 | 66 | 257 | 185 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-21 | -308 | -221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | 2025-01-02 | IOU Designed & Installed | N/A | No | N/A | -2861.83 | 969.78 | Unknown | 112.47 | -4356 | 411.92 | Unknown | 4356.38 | -2861.83 | 7218.21 | Yes | N/A | N/A | 2024-12-05 | 2024-12-05 | 1 | 1 | 2024-12-05 | 2025-01-02 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | Unknown | Unknown | Unknown | 2025-01-02 | 2025-01-02 | 1 | 1 | 2025-01-02 | 2025-01-17 | 1900-01-15 | 12 | 2025-01-17 | 2025-01-17 | 1 | 1 | 1 | 1 | 47 | 35 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-09 | -671 | -480 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 1690.86 | -33.2 | Unknown | Unknown | Unknown | 1724.06 | 3981 | 1874.32 | 1690.86 | 183.46 | Yes | N/A | N/A | 2024-12-17 | 2024-12-17 | 1 | 1 | 2024-12-17 | 2024-12-17 | 1 | 1 | 2024-12-17 | Unknown | Unknown | Unknown | 2024-12-19 | 2025-01-13 | 26 | 18 | 2024-12-17 | 2025-02-03 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-06 | 1900-01-03 | 4 | 2025-02-06 | 2025-02-06 | 1 | 1 | 50 | 36 | 32 | 24 | 82 | 60 | Steps 2,3,5,6,7 | 27 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-03 | -518 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | 1039.61 | Unknown | Unknown | Unknown | 18.55 | 1021.06 | Unknown | 1263.9 | 1039.61 | 224.29 | Yes | N/A | N/A | 2024-04-30 | 2024-03-13 | Unknown | Unknown | 2024-03-13 | 2024-05-09 | 58 | 42 | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-09-16 | 131 | 93 | Unknown | 2024-09-09 | Unknown | Unknown | 2024-09-16 | 2024-10-01 | 1900-01-15 | 12 | 2024-10-01 | 2024-10-01 | 1 | 1 | 131 | 93 | 75 | 55 | 206 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-01-19 | 434 | 311 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | 2024-03-05 | IOU Designed & Installed | N/A | No | N/A | 38.52 | -11.09 | Unknown | Unknown | -590 | 639.61 | Unknown | 590.12 | 38.52 | 551.6 | Yes | N/A | N/A | 2023-12-05 | 2023-12-05 | 1 | 1 | 2023-12-05 | 2024-01-11 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | 2024-03-05 | 2024-03-28 | 1900-01-23 | 18 | 2024-03-28 | 2024-03-28 | 1 | 1 | 1 | 1 | 63 | 47 | 64 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | COUNTY OF SAN DIEGO-SOUTH of 56 | 640 | 640 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 181 | 130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-21 | 2024-01-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 375.2 | -15.81 | Unknown | Unknown | Unknown | 391.01 | 15924 | 902.95 | 375.2 | 527.75 | Yes | N/A | N/A | 2023-07-21 | 2023-09-28 | 70 | 50 | 2023-09-28 | 2024-01-30 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-02-01 | 22 | 16 | 2024-01-30 | 2024-05-07 | 99 | 71 | Unknown | 2024-05-21 | Unknown | Unknown | Unknown | 2024-05-30 | Unknown | Unknown | 2024-05-30 | 2024-05-30 | 1 | 1 | 169 | 121 | 148 | 106 | 317 | 227 | Steps 2,3,5,6,7 | 2 | 2 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 49.05 | 49.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-27 | -140 | -101 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-10-23 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | 579.96 | -11.87 | Unknown | Unknown | 8.22 | 583.61 | Unknown | 769.32 | 579.96 | 189.36 | Yes | N/A | N/A | 2023-10-23 | 2023-09-08 | Unknown | Unknown | 2023-09-08 | 2023-10-31 | 54 | 38 | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | 2024-03-14 | 136 | 98 | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-04-09 | 1900-01-26 | 19 | 2024-04-09 | 2024-04-09 | 1 | 1 | 136 | 98 | 82 | 58 | 218 | 156 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | La Mesa | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-11-13 | 643 | 460 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-18 | 2023-08-18 | IOU Designed & Installed | N/A | No | N/A | -2367.3 | 5775.47 | Unknown | 2105.51 | -13317 | 3068.72 | Unknown | 13316.7 | -2367.3 | 15684 | Yes | N/A | N/A | 2023-07-18 | 2023-08-17 | 31 | 23 | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1899-12-31 | 1 | 2023-08-18 | 2023-08-18 | 1 | 1 | 31 | 23 | 2 | 2 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-24 | -271 | -194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1574.43 | -8.45 | Unknown | Unknown | 2.45 | 1580.43 | 3981 | 999.59 | 1574.43 | -574.84 | Yes | N/A | N/A | 2023-03-09 | 2024-03-18 | 376 | 268 | 2024-03-18 | 2024-03-22 | 5 | 5 | 2024-03-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | Unknown | Unknown | Unknown | 2024-05-29 | Unknown | Unknown | 2024-05-29 | 2024-05-29 | 1 | 1 | 376 | 268 | 6 | 6 | 382 | 274 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-02 | -553 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | Unknown | 2024-09-17 | IOU Designed & Installed | N/A | No | N/A | 27.36 | Unknown | Unknown | Unknown | Unknown | 27.36 | 3981 | 1587.31 | 27.36 | 1559.95 | Yes | N/A | N/A | 2024-08-16 | 2024-08-16 | 1 | 1 | 2024-08-16 | 2024-08-16 | 1 | 1 | 2024-08-16 | Unknown | Unknown | Unknown | 2024-08-16 | 2024-08-23 | 8 | 6 | 2024-08-16 | 2024-09-17 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2024-09-26 | 1900-01-09 | 8 | 2024-09-26 | 2024-09-26 | 1 | 1 | 34 | 24 | 20 | 16 | 54 | 40 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -252 | -181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-10-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 785.71 | -45.51 | Unknown | Unknown | -1119 | 1950.22 | 3981 | 1719.66 | 785.71 | 933.95 | Yes | N/A | N/A | 2023-05-15 | 2023-02-23 | Unknown | Unknown | 2023-02-23 | 2023-11-08 | 259 | 185 | 2023-11-08 | 2024-01-30 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | 2024-03-22 | Unknown | Unknown | Unknown | 2024-05-20 | Unknown | Unknown | 2024-05-20 | 2024-05-17 | Unknown | Unknown | 84 | 60 | 259 | 185 | 343 | 245 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | -472 | -339 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-08 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 663.19 | Unknown | Unknown | Unknown | 29.63 | 633.56 | 3981 | 1442.64 | 663.19 | 779.45 | Yes | N/A | N/A | 2024-05-08 | 2024-05-21 | 14 | 10 | 2024-05-21 | 2024-05-21 | 1 | 1 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | Unknown | Unknown | 2024-10-31 | 2024-10-28 | Unknown | Unknown | 14 | 10 | 1 | 1 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 143.05 | 143.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -199 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-12-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1106.69 | Unknown | Unknown | Unknown | -1156 | 49.31 | 3981 | 2051.31 | -1106.69 | 3158 | Yes | N/A | N/A | 2023-11-29 | 2023-08-08 | Unknown | Unknown | 2023-08-08 | 2023-12-01 | 116 | 84 | 2023-12-01 | 2023-12-08 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | Unknown | Unknown | Unknown | 2024-08-14 | Unknown | Unknown | 2024-08-14 | 2024-08-13 | Unknown | Unknown | 8 | 6 | 116 | 84 | 124 | 90 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-19 | -599 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-07-24 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | -4.27 | -8.39 | Unknown | Unknown | Unknown | 4.12 | Unknown | 880.32 | -4.27 | 884.59 | Yes | N/A | N/A | 2023-07-07 | 2023-05-04 | Unknown | Unknown | 2023-05-04 | 2023-07-24 | 82 | 58 | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2023-07-27 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-08-29 | 1900-02-02 | 24 | 2023-08-29 | 2023-08-29 | 1 | 1 | 4 | 4 | 117 | 83 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | -554 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-16 | 2023-09-30 | 2023-10-24 | IOU Designed & Installed | N/A | No | N/A | 972.58 | 347.14 | Unknown | Unknown | Unknown | 625.44 | Unknown | 875.75 | 972.58 | -96.83 | Yes | N/A | N/A | 2023-08-16 | 2023-09-30 | 46 | 33 | 2023-09-30 | 2023-09-30 | 1 | 0 | 2023-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-30 | 2023-10-24 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2023-11-08 | 1900-01-15 | 12 | 2023-11-08 | 2023-11-08 | 1 | 1 | 71 | 50 | 18 | 13 | 89 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 102 | 102 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-17 | -57 | -42 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-01 | 2023-09-07 | IOU Designed & Installed | N/A | No | N/A | 1405.41 | -8.14 | Unknown | Unknown | 305.97 | 1107.58 | 3981 | 645.28 | 1405.41 | -760.13 | Yes | N/A | N/A | 2023-02-01 | 2023-02-09 | 9 | 7 | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-09 | 2023-09-07 | 211 | 151 | Unknown | 2023-08-11 | Unknown | Unknown | 2023-09-07 | 2024-11-12 | 1901-03-08 | 309 | 2024-11-12 | 2023-09-21 | Unknown | Unknown | 220 | 158 | 433 | 309 | 653 | 467 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-07 | -541 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-20 | 2024-08-20 | IOU Designed & Installed | N/A | No | N/A | 16678.22 | 2947.34 | Unknown | Unknown | Unknown | 13730.88 | Unknown | 10144.52 | 16678.22 | -6533.7 | Yes | N/A | N/A | 2024-06-20 | 2024-06-20 | 1 | 1 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-07-22 | 11 | 7 | 2024-06-21 | 2024-08-20 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-09-12 | 1900-01-23 | 18 | 2024-09-12 | 2024-09-12 | 1 | 1 | 62 | 44 | 36 | 26 | 98 | 70 | Steps 2,3,5,6,7 | 31 | 21 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 24.35 | 24.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | -414 | -297 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-01 | 2025-05-08 | 2025-06-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1075.72 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-01 | 2025-05-07 | 7 | 5 | 2025-05-07 | 2025-05-08 | 2 | 2 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-06-25 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-06-25 | 1899-12-31 | 1 | 2025-06-25 | 2025-06-25 | 1 | 1 | 56 | 40 | 4 | 4 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-18 | -58 | -43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-08 | 2024-10-14 | IOU Designed & Installed | N/A | No | N/A | 717.16 | Unknown | Unknown | Unknown | 7.26 | 709.9 | 3981 | 2248.58 | 717.16 | 1531.42 | Yes | N/A | N/A | 2024-01-08 | 2024-02-27 | 51 | 37 | 2024-02-27 | 2024-02-27 | 1 | 1 | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-10-14 | 249 | 177 | Unknown | 2024-09-10 | Unknown | Unknown | 2024-10-14 | 2024-10-22 | 1900-01-08 | 7 | 2024-10-22 | 2024-10-21 | Unknown | Unknown | 300 | 214 | 10 | 8 | 310 | 222 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 7.7 | 7.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-29 | -213 | -154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-24 | 2025-06-20 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1019.89 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-03-18 | 6 | 4 | 2025-03-18 | 2025-03-21 | 4 | 4 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | 2025-06-20 | 89 | 65 | Unknown | 2025-06-20 | Unknown | Unknown | 2025-06-20 | 2025-06-30 | 1900-01-10 | 7 | 2025-06-30 | 2025-06-30 | 1 | 1 | 95 | 69 | 16 | 12 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Oceanside | OCEANSIDE | 14670 | 14670 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-04-01 | -203 | -146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-12-12 | 2024-06-28 | IOU Designed & Installed | N/A | No | N/A | 8492.38 | 521.57 | Unknown | Unknown | -6745 | 14715.81 | Unknown | 7228.91 | 8492.38 | -1263.47 | Yes | N/A | N/A | 2023-11-28 | 2023-11-28 | 1 | 1 | 2023-11-28 | 2024-06-26 | 212 | 152 | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-05-28 | 23 | 17 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-09-10 | 1900-03-15 | 53 | 2024-09-10 | 2024-09-10 | 1 | 1 | 1 | 1 | 311 | 223 | 312 | 224 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 14.05 | 14.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | -666 | -477 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-12 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | 26.34 | -20.75 | Unknown | Unknown | Unknown | 47.09 | 3981 | 1834.15 | 26.34 | 1807.81 | Yes | N/A | N/A | 2025-02-06 | 2025-01-30 | Unknown | Unknown | 2025-01-30 | 2025-02-12 | 14 | 10 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-02-24 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-02-24 | 2025-03-26 | 1900-01-30 | 23 | 2025-03-26 | 2025-03-26 | 1 | 1 | 13 | 9 | 46 | 34 | 59 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-23 | 467 | 334 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-04-30 | 2025-06-04 | IOU Designed & Installed | N/A | No | N/A | 906.92 | -18.23 | Unknown | Unknown | Unknown | 925.15 | 43791 | 3075.18 | 906.92 | 2168.26 | Yes | N/A | N/A | 2024-04-30 | 2024-05-20 | 21 | 15 | 2024-05-20 | 2024-06-20 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-23 | 18 | 14 | 2024-06-20 | 2025-05-08 | 323 | 231 | Unknown | 2025-05-01 | Unknown | Unknown | 2025-06-04 | 2025-06-04 | 1899-12-31 | 1 | 2025-06-04 | 2025-06-04 | 1 | 1 | 344 | 246 | 52 | 40 | 396 | 286 | Steps 2,3,5,6,7 | 337 | 241 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-08-27 | 993 | 710 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-20 | 2023-04-24 | IOU Designed & Installed | N/A | No | N/A | 29693.31 | 8757.57 | Unknown | Unknown | 314.41 | 20621.33 | 5853 | 9045.9 | 29693.31 | -20647.41 | Yes | N/A | N/A | 2023-03-20 | 2023-03-20 | 1 | 1 | 2023-03-20 | 2023-03-30 | 11 | 9 | 2023-03-20 | 2023-03-30 | 9 | 5 | 2023-03-31 | 2023-04-14 | 15 | 11 | 2023-04-13 | Unknown | Unknown | Unknown | 2023-04-13 | 2023-04-20 | 8 | 6 | 2023-04-24 | 2023-05-17 | 1900-01-23 | 18 | 2023-05-17 | 2023-05-17 | 1 | 1 | 10 | 6 | 59 | 45 | 69 | 51 | Steps 2,3,5,6,7 | 11 | 9 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-01 | 239 | 172 | No | 2023-11-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | 2024-03-07 | IOU Designed & Installed | N/A | Yes | 76 | 516.39 | -21.47 | Unknown | Unknown | Unknown | 537.86 | 3941 | 1014.52 | 516.39 | 498.13 | Yes | N/A | N/A | 2023-11-01 | 2024-01-16 | 77 | 55 | 2024-01-16 | 2023-11-01 | Unknown | Unknown | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2024-03-07 | 128 | 92 | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-03-27 | 1900-01-20 | 15 | 2024-03-27 | 2024-03-27 | 1 | 1 | 205 | 147 | 22 | 16 | 227 | 163 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 1860.1 | 1860.1 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-09-21 | 40 | 29 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-02 | 2024-10-25 | IOU Designed & Installed | N/A | No | N/A | 3.17 | Unknown | Unknown | Unknown | Unknown | 3.17 | Unknown | 529.2 | 3.17 | 526.03 | Yes | N/A | N/A | 2024-05-02 | 2024-05-02 | 1 | 1 | 2024-05-02 | 2024-05-02 | 1 | 1 | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | 2024-10-25 | 177 | 127 | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2024-10-31 | 1900-01-06 | 5 | 2024-10-31 | 2024-10-31 | 1 | 1 | 178 | 128 | 9 | 7 | 187 | 135 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 112.1 | 112.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-01 | -462 | -331 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-07 | 2025-06-23 | IOU Designed & Installed | N/A | No | N/A | 3682.51 | -9.76 | Unknown | Unknown | 72.42 | 3619.85 | 3981 | 1228.97 | 3682.51 | -2453.54 | Yes | N/A | N/A | 2024-11-07 | 2025-01-23 | 78 | 56 | 2025-01-23 | 2025-01-27 | 5 | 3 | 2025-01-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-06-23 | 148 | 106 | Unknown | 2025-06-20 | Unknown | Unknown | 2025-06-23 | 2025-06-26 | 1900-01-03 | 4 | 2025-06-26 | 2025-06-26 | 1 | 1 | 226 | 162 | 10 | 8 | 236 | 170 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-11 | -521 | -374 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | 2024-03-29 | IOU Designed & Installed | N/A | No | N/A | 798.48 | -11.44 | Unknown | Unknown | 5.89 | 804.03 | 3981 | 708.72 | 798.48 | -89.76 | Yes | N/A | N/A | 2023-12-01 | 2024-01-12 | 43 | 31 | 2024-01-12 | 2024-01-17 | 6 | 4 | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | 2024-03-29 | 73 | 53 | Unknown | 2024-03-27 | Unknown | Unknown | 2024-03-29 | 2024-04-08 | 1900-01-10 | 7 | 2024-04-08 | 2024-04-08 | 1 | 1 | 116 | 84 | 18 | 12 | 134 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | N/A | 163.25 | 163.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | 416 | 298 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-04-19 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 10235.74 | 2051.34 | Unknown | Unknown | 258.13 | 7926.27 | 3981 | 847.17 | 10235.74 | -9388.57 | Yes | N/A | N/A | 2023-01-31 | 2023-04-10 | 70 | 50 | 2023-04-10 | 2023-06-29 | 81 | 59 | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2024-09-18 | 1 | 1 | 2023-06-29 | 2024-10-24 | 484 | 346 | Unknown | 2024-11-01 | Unknown | Unknown | 2024-11-07 | 2025-04-24 | 1900-06-17 | 121 | 2025-04-24 | 2024-11-20 | Unknown | Unknown | 554 | 396 | 251 | 181 | 805 | 577 | Steps 2,3,5,6,7 | 447 | 319 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | -666 | -477 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-30 | 2024-05-31 | IOU Designed & Installed | N/A | No | N/A | -21.72 | -17.64 | Unknown | Unknown | Unknown | -4.08 | Unknown | 1016.73 | -21.72 | 1038.45 | Yes | N/A | N/A | 2024-05-30 | 2024-04-23 | Unknown | Unknown | 2024-04-23 | 2024-05-30 | 38 | 28 | 2024-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-05-31 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | 2024-06-13 | 1900-01-13 | 10 | 2024-06-13 | 2024-06-13 | 1 | 1 | 2 | 2 | 53 | 39 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-03 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-17 | 2023-11-17 | 2024-01-17 | IOU Designed & Installed | N/A | No | N/A | 421.52 | 291.46 | Unknown | Unknown | Unknown | 130.06 | Unknown | 496.75 | 421.52 | 75.23 | Yes | N/A | N/A | 2023-11-17 | 2023-11-17 | 1 | 1 | 2023-11-17 | 2023-11-17 | 1 | 1 | 2023-11-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2024-01-17 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | 2024-01-23 | 1900-01-06 | 5 | 2024-01-23 | 2024-01-23 | 1 | 1 | 63 | 45 | 9 | 7 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -12 | -9 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 91.85 | -7 | Unknown | Unknown | Unknown | 98.85 | 0 | 466.88 | 91.85 | 375.03 | Yes | N/A | N/A | 2024-04-30 | 2024-05-01 | 2 | 2 | 2024-05-01 | 2024-06-19 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-12 | 27 | 19 | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | Unknown | Unknown | 2025-04-11 | 2025-04-11 | 1 | 1 | 2 | 2 | 78 | 56 | 80 | 58 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-20 | -318 | -229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-08 | 2024-02-02 | IOU Designed & Installed | N/A | No | N/A | -2138.02 | 2122.26 | Unknown | 566.1 | -5829 | 1002.62 | Unknown | 5829.3 | -2138.02 | 7967.32 | Yes | N/A | N/A | 2024-01-08 | 2024-01-08 | 1 | 1 | 2024-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-02-06 | 1900-01-04 | 3 | 2024-02-06 | 2024-02-06 | 1 | 1 | 1 | 1 | 6 | 4 | 7 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | 266 | 266 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-07 | -615 | -440 | No | 2025-04-09 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-04-09 | 2025-06-25 | IOU Designed & Installed | N/A | Yes | 36 | 489.12 | 489.12 | Unknown | Unknown | -602.78 | 602.78 | 3981 | 2586.11 | 489.12 | 2096.99 | Yes | N/A | N/A | 2025-04-09 | 2025-05-15 | 37 | 27 | 2025-05-15 | 2025-04-09 | Unknown | Unknown | 2025-04-09 | 2025-06-02 | 55 | 39 | 2025-04-23 | 2025-04-28 | 6 | 4 | 2025-04-09 | 2025-06-25 | 78 | 56 | Unknown | 2025-06-25 | Unknown | Unknown | 2025-06-25 | 2025-06-30 | 1900-01-05 | 4 | 2025-06-30 | 2025-06-30 | 1 | 1 | 170 | 122 | 13 | 9 | 183 | 131 | Steps 2,3,5,6,7 | 59 | 41 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego PA10 PH3 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 575 | 412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-07-05 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 90835.84 | 4874.16 | Unknown | Unknown | 4901.17 | 81060.51 | 0 | 31521.57 | 90835.84 | -59314.27 | Yes | N/A | N/A | 2022-04-27 | 2023-04-18 | 357 | 255 | 2023-04-18 | 2023-07-26 | 100 | 72 | 2023-05-23 | 2024-04-08 | 22 | 14 | 2023-07-27 | 2023-08-11 | 16 | 12 | 2023-11-09 | Unknown | Unknown | Unknown | 2023-11-09 | 2024-10-08 | 335 | 239 | Unknown | 2024-10-15 | Unknown | Unknown | 2024-10-15 | 2024-10-15 | 1 | 1 | 379 | 269 | 452 | 324 | 831 | 593 | Steps 2,3,5,6,7 | 320 | 228 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | -486 | -349 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-08-12 | 2025-01-10 | IOU Designed & Installed | N/A | No | N/A | -636.07 | Unknown | Unknown | Unknown | -1083 | 446.93 | Unknown | 1082.67 | -636.07 | 1718.74 | Yes | N/A | N/A | 2024-08-09 | 2024-07-26 | Unknown | Unknown | 2024-07-26 | 2024-09-09 | 46 | 32 | 2024-09-09 | 2024-11-14 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2025-01-10 | 45 | 33 | Unknown | 2024-11-27 | Unknown | Unknown | 2025-01-10 | 2025-02-11 | 1900-02-01 | 23 | 2025-02-11 | 2025-02-11 | 1 | 1 | 112 | 82 | 80 | 56 | 192 | 138 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | -247 | -177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | 2024-03-21 | IOU Designed & Installed | N/A | No | N/A | -9.43 | -7.66 | Unknown | Unknown | Unknown | -1.77 | Unknown | 501.14 | -9.43 | 510.57 | Yes | N/A | N/A | 2024-03-11 | 2023-12-15 | Unknown | Unknown | 2023-12-15 | 2024-03-18 | 95 | 67 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | 2024-03-21 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-04-04 | 1900-01-14 | 11 | 2024-04-04 | 2024-04-04 | 1 | 1 | 4 | 4 | 111 | 79 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-20 | 359 | 256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-04-06 | 2024-04-11 | IOU Designed & Installed | N/A | No | N/A | 98712.21 | 17360.16 | Unknown | Unknown | -46302.28 | 127654.33 | 455 | 85665.93 | 98712.21 | -13046.28 | Yes | N/A | N/A | 2023-02-08 | 2023-04-10 | 62 | 44 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | 2024-04-08 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-05-13 | 1900-02-01 | 23 | 2024-05-13 | 2024-05-13 | 1 | 1 | 62 | 44 | 168 | 120 | 230 | 164 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-16 | -317 | -228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-10-27 | 2023-11-30 | IOU Designed & Installed | N/A | No | N/A | 1793.67 | 673.12 | Unknown | Unknown | Unknown | 1120.55 | Unknown | 599.77 | 1793.67 | -1193.9 | Yes | N/A | N/A | 2023-10-27 | 2023-10-27 | 1 | 1 | 2023-10-27 | 2023-10-27 | 1 | 1 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2023-11-30 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2023-12-04 | 1900-01-04 | 3 | 2023-12-04 | 2023-12-04 | 1 | 1 | 36 | 26 | 7 | 5 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-11 | -214 | -153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-29 | 2025-01-29 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 15776.86 | Unknown | Unknown | Unknown | Unknown | 15776.86 | 3981 | 1815.96 | 15776.86 | -13960.9 | Yes | N/A | N/A | 2025-01-29 | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2025-02-20 | 149 | 107 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-02-20 | 23 | 17 | 2025-02-20 | 2025-04-10 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | 2025-04-15 | 1900-01-28 | 21 | 2025-04-15 | 2025-04-11 | Unknown | Unknown | 50 | 36 | 201 | 145 | 251 | 181 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-18 | -259 | -186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | 2023-10-09 | IOU Designed & Installed | N/A | No | N/A | -12.86 | -10.29 | Unknown | Unknown | Unknown | -2.57 | Unknown | 153.83 | -12.86 | 166.69 | Yes | N/A | N/A | 2023-09-19 | 2023-09-22 | 4 | 4 | 2023-09-22 | 2023-09-22 | 1 | 1 | 2023-09-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2023-10-09 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2023-11-02 | 1900-01-24 | 19 | 2023-11-02 | 2023-11-02 | 1 | 1 | 22 | 16 | 27 | 21 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-08 | -216 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-25 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | -748.79 | -19.83 | Unknown | Unknown | -1735 | 1006.04 | Unknown | 1734.87 | -748.79 | 2483.66 | Yes | N/A | N/A | 2025-02-19 | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-03-17 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-02-26 | 2025-03-12 | 15 | 11 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-06-06 | 1900-01-01 | 2 | 2025-06-06 | 2025-06-06 | 1 | 1 | 0 | 0 | 46 | 34 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | -534 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-06-19 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | 1204.32 | Unknown | Unknown | Unknown | Unknown | 1204.32 | Unknown | 1080.07 | 1204.32 | -124.25 | Yes | N/A | N/A | 2024-05-31 | 2024-07-01 | 32 | 22 | 2024-07-01 | 2024-07-11 | 11 | 9 | 2024-07-11 | 2024-09-19 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-10-21 | 33 | 23 | Unknown | 2024-10-18 | Unknown | Unknown | 2024-10-21 | 2024-10-28 | 1900-01-07 | 6 | 2024-10-28 | 2024-10-28 | 1 | 1 | 136 | 96 | 20 | 16 | 156 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN JUAN CAPISTRANO | N/A | 6503 | 6503 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-01 | -17 | -14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-05-15 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 14995.89 | Unknown | Unknown | Unknown | Unknown | 14995.89 | Unknown | 2556.03 | 14995.89 | -12439.86 | Yes | N/A | N/A | 2024-04-03 | 2024-04-03 | 1 | 1 | 2024-04-03 | 2024-06-28 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | Unknown | Unknown | 2024-07-02 | 2024-07-15 | 1900-01-13 | 10 | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 102 | 74 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 599 | 430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 14239.64 | -133.74 | Unknown | Unknown | -4825 | 19198.38 | Unknown | 3087.05 | 14239.64 | -11152.59 | Yes | N/A | N/A | 2024-10-22 | 2024-10-22 | 1 | 1 | 2024-10-22 | 2024-10-29 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-11-04 | 7 | 5 | Unknown | 2024-11-07 | Unknown | Unknown | Unknown | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-08 | Unknown | Unknown | 8 | 6 | 8 | 6 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 1210 | 1210 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2024-08-11 | -117 | -84 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2142.23 | 182.67 | Unknown | 88.44 | 4.82 | 1866.3 | 3981 | 2128.18 | 2142.23 | -14.05 | Yes | N/A | N/A | 2023-09-11 | 2023-10-31 | 51 | 37 | 2023-10-31 | 2023-10-31 | 1 | 1 | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-31 | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2024-04-16 | 1 | 1 | 51 | 37 | 2 | 2 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-05 | -574 | -411 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-07-01 | 2024-07-19 | IOU Designed & Installed | N/A | No | N/A | 4.79 | Unknown | Unknown | Unknown | Unknown | 4.79 | 3981 | 983.86 | 4.79 | 979.07 | Yes | N/A | N/A | 2024-04-17 | 2024-07-01 | 76 | 54 | 2024-07-01 | 2024-07-01 | 1 | 1 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-07-19 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-08-08 | 1900-01-20 | 15 | 2024-08-08 | 2024-08-08 | 1 | 1 | 95 | 69 | 23 | 17 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN YSIDRO | SAN YSIDRO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | 319 | 230 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5.46 | -6.87 | Unknown | Unknown | Unknown | 12.33 | Unknown | 459.32 | 5.46 | 453.86 | Yes | N/A | N/A | 2023-12-04 | 2023-12-15 | 12 | 10 | 2023-12-15 | 2024-01-09 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2023-12-27 | 9 | 7 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 12 | 10 | 36 | 26 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN JUAN CAPISTRANO | N/A | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-02 | 618 | 441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-08 | 2023-11-29 | IOU Designed & Installed | N/A | No | N/A | 10807.08 | Unknown | Unknown | Unknown | Unknown | 10807.08 | 3981 | 432.82 | 10807.08 | -10374.26 | Yes | N/A | N/A | 2023-11-08 | 2023-11-08 | 1 | 1 | 2023-11-08 | 2023-11-08 | 1 | 1 | 2023-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2023-11-29 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2023-12-12 | 1900-01-13 | 10 | 2023-12-12 | 2023-12-11 | Unknown | Unknown | 23 | 17 | 15 | 11 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-09-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 362.3 | 101.47 | Unknown | Unknown | 2.37 | 258.46 | 3981 | 1221.77 | 362.3 | 859.47 | Yes | N/A | N/A | 2024-09-30 | 2024-09-25 | Unknown | Unknown | 2024-09-25 | 2024-10-09 | 15 | 11 | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | Unknown | Unknown | 2024-11-20 | 2024-11-20 | 1 | 1 | 0 | 0 | 16 | 12 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JULIAN | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-18 | -612 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-15 | 2024-08-20 | 2024-11-04 | IOU Designed & Installed | N/A | No | N/A | 1284.69 | 667.2 | Unknown | 134.86 | -1183 | 1665.63 | Unknown | 1063.54 | 1284.69 | -221.15 | Yes | N/A | N/A | 2024-08-15 | 2024-07-30 | Unknown | Unknown | 2024-07-30 | 2024-08-15 | 17 | 13 | 2024-08-15 | 2024-10-28 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-04 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-11-13 | 1900-01-09 | 8 | 2024-11-13 | 2024-11-13 | 1 | 1 | 83 | 59 | 28 | 22 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 21.1 | 21.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-29 | -514 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.39 | -12.88 | Unknown | Unknown | Unknown | 8.49 | 3981 | 741.86 | -4.39 | 746.25 | Yes | N/A | N/A | 2023-02-08 | 2023-02-08 | 1 | 1 | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | Unknown | Unknown | 2023-08-08 | 2023-05-04 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-14 | -625 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-12 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | 1999.46 | 379.67 | Unknown | Unknown | Unknown | 1619.79 | Unknown | 2002.22 | 1999.46 | 2.76 | Yes | N/A | N/A | 2025-02-11 | 2025-02-04 | Unknown | Unknown | 2025-02-04 | 2025-02-12 | 9 | 7 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-04-09 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-29 | 1900-01-20 | 15 | 2025-04-29 | 2025-04-29 | 1 | 1 | 57 | 41 | 31 | 23 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 35.05 | 35.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-14 | -338 | -242 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | -447.24 | Unknown | Unknown | Unknown | -518 | 70.76 | 3981 | 2600.46 | -447.24 | 3047.7 | Yes | N/A | N/A | 2024-11-04 | 2024-10-29 | Unknown | Unknown | 2024-10-29 | 2025-03-03 | 126 | 90 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-04-09 | 64 | 46 | Unknown | 2025-02-25 | Unknown | Unknown | 2025-04-09 | 2025-04-10 | 1900-01-01 | 2 | 2025-04-10 | 2025-04-10 | 1 | 1 | 64 | 46 | 129 | 93 | 193 | 139 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-08 | -503 | -360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-09 | 2023-03-22 | IOU Designed & Installed | N/A | No | N/A | 5762.63 | 1824.89 | Unknown | 853.58 | Unknown | 3084.16 | 3981 | 1002.25 | 5762.63 | -4760.38 | Yes | N/A | N/A | 2023-02-08 | 2023-02-09 | 2 | 2 | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-09 | 2023-03-22 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-03-22 | 2023-03-24 | 1900-01-02 | 3 | 2023-03-24 | 2023-03-24 | 1 | 1 | 44 | 32 | 4 | 4 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-14 | 129 | 93 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 4327.28 | Unknown | Unknown | Unknown | Unknown | 4327.28 | 3981 | 842.41 | 4327.28 | -3484.87 | Yes | N/A | N/A | 2023-06-13 | 2023-06-13 | 1 | 1 | 2023-06-13 | 2023-12-18 | 189 | 135 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-07-17 | 213 | 153 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | Unknown | Unknown | 2024-08-27 | 2024-08-21 | Unknown | Unknown | 214 | 154 | 189 | 135 | 403 | 289 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-13 | -585 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-12 | 2024-03-27 | IOU Designed & Installed | N/A | No | N/A | 356.83 | -21.66 | Unknown | Unknown | Unknown | 378.49 | 3981 | 900.8 | 356.83 | 543.97 | Yes | N/A | N/A | 2024-01-10 | 2023-12-19 | Unknown | Unknown | 2023-12-19 | 2024-01-12 | 25 | 19 | 2024-01-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | 2024-03-27 | 76 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-05-06 | 1900-02-09 | 29 | 2024-05-06 | 2024-05-07 | 2 | 2 | 76 | 54 | 68 | 50 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-07 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | 2024-12-30 | IOU Designed & Installed | N/A | No | N/A | 2200.16 | 343.99 | Unknown | Unknown | Unknown | 1856.17 | 3981 | 1739.29 | 2200.16 | -460.87 | Yes | N/A | N/A | 2024-11-14 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-14 | 2 | 2 | 2024-11-14 | Unknown | Unknown | Unknown | 2024-11-14 | 2024-12-17 | 34 | 24 | 2024-11-14 | 2024-12-30 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | 2024-12-30 | 1899-12-31 | 1 | 2024-12-30 | 2024-12-30 | 1 | 1 | 47 | 33 | 38 | 28 | 85 | 61 | Steps 2,3,5,6,7 | 33 | 23 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-23 | -516 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-11 | 2024-03-08 | IOU Designed & Installed | N/A | No | N/A | 11.17 | -9.92 | Unknown | Unknown | Unknown | 21.09 | 3981 | 1043.73 | 11.17 | 1032.56 | Yes | N/A | N/A | 2024-01-08 | 2024-01-11 | 4 | 4 | 2024-01-11 | 2024-01-11 | 1 | 1 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-03-08 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-03-25 | 1900-01-17 | 12 | 2024-03-25 | 2024-03-25 | 1 | 1 | 62 | 46 | 20 | 14 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Commercial | Underserved Community | La Mesa | La Mesa | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -310 | -223 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-09 | 2023-08-09 | 2024-10-29 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 136547.99 | 25420.35 | Unknown | Unknown | -61388.82 | 172516.46 | 0 | 67862.47 | 136547.99 | -68685.52 | Yes | N/A | N/A | 2023-08-09 | 2023-11-14 | 98 | 70 | 2023-11-14 | 2024-07-10 | 240 | 172 | 2023-12-05 | 2025-01-14 | 52 | 38 | 2023-12-20 | 2025-01-16 | 70 | 52 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2025-02-24 | 1900-04-28 | 85 | 2025-02-24 | 2025-02-24 | 1 | 1 | 150 | 108 | 430 | 310 | 580 | 418 | Steps 2,3,5,6,7 | 609 | 435 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-26 | -584 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-27 | 2024-04-27 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | 12.91 | -11.47 | Unknown | Unknown | Unknown | 24.38 | 3981 | 636.84 | 12.91 | 623.93 | Yes | N/A | N/A | 2024-04-27 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-05-14 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-05-22 | 1900-01-08 | 7 | 2024-05-22 | 2024-05-21 | Unknown | Unknown | 1 | 1 | 9 | 7 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-10 | 805 | 576 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-01 | 2024-05-15 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | 1099.72 | Unknown | Unknown | Unknown | -542 | 1641.72 | Unknown | 542.5 | 1099.72 | -557.22 | Yes | N/A | N/A | 2024-05-01 | 2024-05-15 | 15 | 11 | 2024-05-15 | 2024-06-04 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-07-05 | 32 | 24 | Unknown | 2024-07-09 | Unknown | Unknown | 2024-07-16 | 2024-07-24 | 1900-01-08 | 7 | 2024-07-24 | 2024-07-23 | Unknown | Unknown | 47 | 35 | 30 | 22 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-24 | -71 | -52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-08-02 | 2024-02-27 | IOU Designed & Installed | N/A | No | N/A | -1208.1 | -18.1 | Unknown | Unknown | -1679 | 489 | Unknown | 1678.62 | -1208.1 | 2886.72 | Yes | N/A | N/A | 2023-07-26 | 2023-07-26 | 1 | 1 | 2023-07-26 | 2023-11-13 | 111 | 79 | 2023-09-29 | 2023-09-29 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2024-02-27 | 2024-03-14 | 1900-01-16 | 13 | 2024-03-14 | 2024-03-14 | 1 | 1 | 2 | 2 | 129 | 93 | 131 | 95 | Steps 2,3,5,6,7 | 45 | 31 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 56 | 56 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-16 | -445 | -319 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-06 | 2023-07-06 | 2023-08-28 | IOU Designed & Installed | N/A | No | N/A | 37.8 | -10.78 | Unknown | Unknown | 43.29 | 5.29 | 3981 | 1061.99 | 37.8 | 1024.19 | Yes | N/A | N/A | 2023-07-06 | 2023-04-10 | Unknown | Unknown | 2023-04-10 | 2023-07-31 | 113 | 81 | 2023-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2023-08-28 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2024-11-12 | 1901-03-18 | 317 | 2024-11-12 | 2023-08-29 | Unknown | Unknown | 29 | 21 | 556 | 398 | 585 | 419 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-15 | -542 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-13 | 2024-12-13 | IOU Designed & Installed | N/A | No | N/A | 1166.76 | Unknown | Unknown | Unknown | 15.68 | 1151.08 | 3981 | 1106.45 | 1166.76 | -60.31 | Yes | N/A | N/A | 2024-08-01 | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2024-08-19 | 55 | 39 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-12-13 | 117 | 85 | Unknown | 2024-11-06 | Unknown | Unknown | 2024-12-13 | 2024-12-20 | 1900-01-07 | 6 | 2024-12-20 | 2024-12-20 | 1 | 1 | 117 | 85 | 64 | 46 | 181 | 131 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-04 | -376 | -269 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-04 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 639.72 | 190.31 | Unknown | Unknown | Unknown | 449.41 | 3941 | 863.73 | 639.72 | 224.01 | Yes | N/A | N/A | 2024-03-04 | 2023-12-06 | Unknown | Unknown | 2023-12-06 | 2024-10-08 | 308 | 220 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-10-23 | 234 | 168 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-10-24 | 1900-01-01 | 2 | 2024-10-24 | 2024-10-24 | 1 | 1 | 234 | 168 | 311 | 223 | 545 | 391 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-11 | -623 | -446 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-31 | 2023-11-02 | 2023-11-14 | IOU Designed & Installed | N/A | No | N/A | 61.75 | -12.34 | Unknown | Unknown | Unknown | 74.09 | Unknown | 770.76 | 61.75 | 709.01 | Yes | N/A | N/A | 2023-10-31 | 2023-08-21 | Unknown | Unknown | 2023-08-21 | 2023-11-02 | 74 | 54 | 2023-11-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2023-11-14 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2023-11-27 | 1900-01-13 | 10 | 2023-11-27 | 2023-11-27 | 1 | 1 | 13 | 9 | 89 | 65 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA MESA | COUNTY OF SAN DIEGO-SOUTH of 56 | 184.05 | 184.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-10 | 559 | 400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-26 | 2023-09-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | -699.52 | -16.54 | Unknown | Unknown | -1123 | 440.02 | 3981 | 2423.81 | -699.52 | 3123.33 | Yes | N/A | N/A | 2022-09-26 | 2023-09-29 | 369 | 265 | 2023-09-29 | 2024-02-29 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | 2023-10-03 | 2023-10-06 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | Unknown | Unknown | Unknown | 2024-08-23 | Unknown | Unknown | 2024-08-23 | 2024-08-22 | Unknown | Unknown | 369 | 265 | 158 | 114 | 527 | 379 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-15 | -11 | -8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | 2023-04-20 | IOU Designed & Installed | N/A | No | N/A | -14.25 | -10.33 | Unknown | Unknown | Unknown | -3.92 | 3981 | 661.15 | -14.25 | 675.4 | Yes | N/A | N/A | 2023-03-24 | 2023-03-28 | 5 | 3 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | 2023-04-20 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | 2023-06-12 | 1900-02-22 | 38 | 2023-06-12 | 2023-05-04 | Unknown | Unknown | 29 | 21 | 54 | 38 | 83 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | -6 | -5 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-01 | 2022-11-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -375.55 | 1816.66 | Unknown | 491.5 | -3436 | 752.29 | Unknown | 3436.31 | -375.55 | 3811.86 | Yes | N/A | N/A | 2022-11-01 | 2023-05-17 | 198 | 142 | 2023-05-17 | 2023-05-25 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2023-06-10 | Unknown | Unknown | 198 | 142 | 9 | 7 | 207 | 149 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-31 | -569 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | 2024-02-06 | IOU Designed & Installed | N/A | No | N/A | 779.64 | 252.46 | Unknown | Unknown | Unknown | 527.18 | 3981 | 897.93 | 779.64 | 118.29 | Yes | N/A | N/A | 2023-11-16 | 2023-09-01 | Unknown | Unknown | 2023-09-01 | 2023-11-16 | 77 | 55 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2024-02-06 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-02-09 | 1900-01-03 | 4 | 2024-02-09 | 2024-02-09 | 1 | 1 | 83 | 59 | 82 | 60 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 130.05 | 130.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-20 | -538 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | 2023-05-31 | IOU Designed & Installed | N/A | No | N/A | 647.21 | 237.76 | Unknown | Unknown | Unknown | 409.45 | 3241 | 611.42 | 647.21 | -35.79 | Yes | N/A | N/A | 2023-05-16 | 2023-05-16 | 1 | 1 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | 2023-05-31 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | 2023-06-01 | 1900-01-01 | 2 | 2023-06-01 | 2023-06-01 | 1 | 1 | 17 | 13 | 3 | 3 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -624 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-13 | 2023-04-17 | 2023-05-16 | IOU Designed & Installed | N/A | No | N/A | 491.25 | 280.92 | Unknown | 67.03 | Unknown | 143.3 | Unknown | 483.84 | 491.25 | -7.41 | Yes | N/A | N/A | 2023-04-13 | 2023-04-14 | 2 | 2 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | 2023-05-16 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2023-05-16 | 2023-05-17 | 1900-01-01 | 2 | 2023-05-17 | 2023-05-17 | 1 | 1 | 32 | 24 | 3 | 3 | 35 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 470.05 | 470.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-24 | -476 | -341 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-05-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 411.19 | -12.61 | Unknown | Unknown | 0.78 | 423.02 | 3981 | 813.19 | 411.19 | 402 | Yes | N/A | N/A | 2023-05-18 | 2023-06-12 | 26 | 18 | 2023-06-12 | 2023-07-06 | 25 | 19 | 2023-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | Unknown | Unknown | 2024-03-01 | 2024-01-04 | Unknown | Unknown | 26 | 18 | 25 | 19 | 51 | 37 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | -527 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | 2023-09-05 | IOU Designed & Installed | N/A | No | N/A | 436.27 | -11.56 | Unknown | Unknown | 25.16 | 422.67 | 3981 | 481.4 | 436.27 | 45.13 | Yes | N/A | N/A | 2023-03-01 | 2023-04-19 | 50 | 36 | 2023-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-19 | 2023-09-05 | 140 | 100 | Unknown | 2023-06-21 | Unknown | Unknown | 2023-09-05 | 2023-09-12 | 1900-01-07 | 6 | 2023-09-12 | 2023-09-13 | 2 | 2 | 190 | 136 | 10 | 8 | 200 | 144 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | -296 | -213 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-07-23 | 2024-08-19 | IOU Designed & Installed | N/A | No | N/A | 14554.2 | Unknown | Unknown | Unknown | Unknown | 14554.2 | 3981 | 1426.09 | 14554.2 | -13128.11 | Yes | N/A | N/A | 2024-06-20 | 2024-07-01 | 12 | 8 | 2024-07-01 | 2024-08-12 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-09-09 | 13 | 11 | 2024-08-12 | 2024-08-13 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-09-24 | 1900-02-05 | 27 | 2024-09-24 | 2024-09-18 | Unknown | Unknown | 14 | 10 | 93 | 69 | 107 | 79 | Steps 2,3,5,6,7 | 28 | 20 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-19 | -337 | -242 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-07 | 2025-04-07 | 2025-04-16 | IOU Designed & Installed | N/A | No | N/A | 1732.37 | 2831.69 | Unknown | 181.2 | -2714 | 1433.48 | Unknown | 2714.43 | 1732.37 | 982.06 | Yes | N/A | N/A | 2025-04-07 | 2025-04-07 | 1 | 1 | 2025-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-04-16 | 1899-12-31 | 1 | 2025-04-16 | 2025-04-16 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community,Tribal Community | ALPINE | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 210 | 151 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2996.57 | 88.75 | Unknown | Unknown | 24.22 | 2883.6 | 3981 | 1418.18 | 2996.57 | -1578.39 | Yes | N/A | N/A | 2024-02-05 | 2024-02-15 | 11 | 9 | 2024-02-15 | 2024-02-20 | 6 | 4 | 2024-04-15 | 2024-04-15 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-02-20 | 2024-02-02 | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | Unknown | 2024-07-08 | Unknown | Unknown | 2024-07-08 | 2024-06-28 | Unknown | Unknown | 12 | 10 | 6 | 4 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-02 | -682 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 100.03 | 68.47 | Unknown | Unknown | Unknown | 31.56 | Unknown | 440.01 | 100.03 | 339.98 | Yes | N/A | N/A | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | 2023-11-06 | 1 | 1 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | Unknown | Unknown | 2023-12-21 | 2023-12-21 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-31 | -584 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-24 | 2025-05-05 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1192.46 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-24 | 2025-05-05 | 43 | 31 | 2025-05-05 | 2025-05-05 | 1 | 1 | 2025-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-05 | 2025-06-05 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-06-26 | 1900-01-21 | 16 | 2025-06-26 | 2025-06-26 | 1 | 1 | 75 | 55 | 24 | 18 | 99 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | Rancho Mission Viejo | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-01 | 600 | 429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-29 | 2023-05-17 | 2024-01-29 | IOU Designed & Installed | N/A | No | N/A | 140201.34 | 24488.36 | Unknown | 5829.15 | 39595.71 | 70288.12 | 0 | 50637.56 | 140201.34 | -89563.78 | Yes | N/A | N/A | 2022-11-29 | 2023-05-16 | 169 | 121 | 2023-05-16 | 2023-10-24 | 162 | 116 | 2023-08-23 | 2024-03-04 | 30 | 21 | 2023-10-10 | 2024-03-06 | 149 | 107 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | 2024-01-29 | 2024-09-23 | 1900-08-26 | 171 | 2024-09-23 | 2024-09-23 | 1 | 1 | 199 | 142 | 551 | 395 | 750 | 537 | Steps 2,3,5,6,7 | 212 | 152 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-28 | -180 | -130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-09 | 2022-12-09 | 2023-04-27 | IOU Designed & Installed | N/A | No | N/A | -2.64 | -7.71 | Unknown | Unknown | Unknown | 5.07 | 3885 | 1142.62 | -2.64 | 1145.26 | Yes | N/A | N/A | 2022-12-09 | 2023-03-02 | 84 | 60 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | 2023-04-27 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | 2023-06-12 | 1900-02-15 | 33 | 2023-06-12 | 2023-05-01 | Unknown | Unknown | 141 | 101 | 47 | 33 | 188 | 134 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-08 | 360 | 257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1351.91 | -0.94 | Unknown | Unknown | -1454 | 103.03 | Unknown | 2916.1 | -1351.91 | 4268.01 | Yes | N/A | N/A | 2024-02-29 | 2024-11-14 | 260 | 186 | 2024-11-14 | 2024-11-27 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | 2025-02-13 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-03 | Unknown | Unknown | 339 | 243 | 14 | 10 | 353 | 253 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -675 | -482 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2023-08-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -61.24 | -26.89 | Unknown | Unknown | -1109 | 1074.65 | 3981 | 2122.47 | -61.24 | 2183.71 | Yes | N/A | N/A | 2023-08-02 | 2023-08-02 | 1 | 1 | 2023-08-02 | 2023-08-04 | 3 | 3 | 2023-08-04 | 2023-11-20 | 109 | 77 | Unknown | Unknown | Unknown | Unknown | 2023-08-02 | Unknown | Unknown | Unknown | Unknown | 2024-01-12 | Unknown | Unknown | Unknown | 2024-01-26 | Unknown | Unknown | 2024-01-26 | 2024-01-26 | 1 | 1 | 110 | 78 | 4 | 4 | 114 | 82 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 103.05 | 103.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-01 | 122 | 88 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-05 | 2023-08-19 | 2023-09-06 | IOU Designed & Installed | N/A | No | N/A | -15.39 | -11.49 | Unknown | Unknown | Unknown | -3.9 | Unknown | 496.37 | -15.39 | 511.76 | Yes | N/A | N/A | 2023-08-05 | 2023-08-19 | 15 | 10 | 2023-08-19 | 2023-08-19 | 1 | 0 | 2023-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-19 | 2023-09-06 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | 2024-01-31 | 1900-05-27 | 106 | 2024-01-31 | 2024-01-31 | 1 | 1 | 34 | 23 | 150 | 107 | 184 | 130 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-17 | 154 | 111 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-10-23 | 2023-11-10 | IOU Designed & Installed | N/A | No | N/A | 16425.79 | 9929.68 | Unknown | 1626.08 | -6423 | 11293.03 | Unknown | 6422.77 | 16425.79 | -10003.02 | Yes | N/A | N/A | 2023-10-23 | 2023-09-28 | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2024-03-19 | 1900-05-10 | 93 | 2024-03-19 | 2024-03-19 | 1 | 1 | 0 | 0 | 132 | 94 | 132 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 79.05 | 79.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-21 | -14 | -11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-01 | Unknown | 2023-06-22 | IOU Designed & Installed | N/A | No | N/A | -4.9 | -14.53 | Unknown | Unknown | Unknown | 9.63 | 3981 | 882.42 | -4.9 | 887.32 | Yes | N/A | N/A | 2022-10-01 | 2023-05-22 | 234 | 166 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | 2023-06-22 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-07-07 | 1900-01-15 | 12 | 2023-07-07 | 2023-07-07 | 1 | 1 | 249 | 177 | 17 | 13 | 266 | 190 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | CORONADO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-08 | -132 | -95 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-10-11 | 2024-03-11 | IOU Designed & Installed | N/A | No | N/A | 16129.05 | 864.04 | Unknown | Unknown | Unknown | 15265.01 | Unknown | 13197.69 | 16129.05 | -2931.36 | Yes | N/A | N/A | 2023-05-15 | 2023-09-29 | 138 | 100 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-02-15 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | 2024-03-29 | 1900-01-18 | 15 | 2024-03-29 | 2024-03-29 | 1 | 1 | 138 | 100 | 51 | 39 | 189 | 139 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-02 | -590 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-18 | 2025-04-04 | 2025-05-08 | IOU Designed & Installed | N/A | No | N/A | 74.7 | -1.5 | Unknown | Unknown | Unknown | 76.2 | Unknown | 1717.92 | 74.7 | 1643.22 | Yes | N/A | N/A | 2025-03-18 | 2025-03-18 | 1 | 1 | 2025-03-18 | 2025-04-04 | 18 | 14 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-05-08 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-05-22 | 1900-01-14 | 11 | 2025-05-22 | 2025-05-22 | 1 | 1 | 36 | 26 | 34 | 26 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-22 | -263 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-27 | 2023-04-27 | 2023-06-30 | IOU Designed & Installed | N/A | No | N/A | -3.9 | -11.46 | Unknown | Unknown | Unknown | 7.56 | 3241 | 798.29 | -3.9 | 802.19 | Yes | N/A | N/A | 2023-04-27 | 2023-04-27 | 1 | 1 | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | 2023-06-30 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-07-03 | 1900-01-03 | 2 | 2023-07-03 | 2023-07-03 | 1 | 1 | 66 | 48 | 5 | 3 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 276 | 197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-02 | 2022-11-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3065.04 | 5570.26 | Unknown | 464.79 | -5546 | 2575.99 | 0 | 2749.08 | 3065.04 | -315.96 | Yes | N/A | N/A | 2022-11-02 | 2023-05-02 | 182 | 130 | 2023-05-02 | 2023-05-04 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-03-25 | 1 | 1 | 182 | 130 | 4 | 4 | 186 | 134 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CORONADO | CORONADO | 107.05 | 107.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -277 | -198 | No | 2024-09-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | 2025-05-28 | IOU Designed & Installed | N/A | Yes | 24 | 1820.06 | Unknown | Unknown | Unknown | 60.73 | 1759.33 | 3941 | 819.5 | 1820.06 | -1000.56 | Yes | N/A | N/A | 2024-09-03 | 2024-09-27 | 25 | 19 | 2024-09-27 | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-10-10 | 3 | 3 | 2024-09-26 | 2025-05-19 | 43 | 29 | 2024-09-26 | 2025-05-28 | 245 | 175 | Unknown | 2025-05-05 | Unknown | Unknown | 2025-05-28 | 2025-05-28 | 1899-12-31 | 1 | 2025-05-28 | 2025-05-28 | 1 | 1 | 273 | 197 | 45 | 31 | 318 | 228 | Steps 2,3,5,6,7 | 249 | 177 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-12 | -683 | -488 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-30 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1453.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-04-18 | Unknown | Unknown | 2025-04-18 | 2025-04-30 | 13 | 9 | 2025-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-30 | 2025-05-16 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-05-29 | 1900-01-13 | 10 | 2025-05-29 | 2025-05-29 | 1 | 1 | 17 | 13 | 28 | 20 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12.05 | 12.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-30 | -626 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-07-02 | 2024-07-18 | IOU Designed & Installed | N/A | No | N/A | 29.59 | Unknown | Unknown | Unknown | Unknown | 29.59 | Unknown | 1514.42 | 29.59 | 1484.83 | Yes | N/A | N/A | 2024-06-12 | 2024-05-10 | Unknown | Unknown | 2024-05-10 | 2024-07-02 | 54 | 38 | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-18 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-08-12 | 1900-01-25 | 18 | 2024-08-12 | 2024-08-12 | 1 | 1 | 17 | 13 | 81 | 57 | 98 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-05 | -658 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-04-04 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | 554.12 | -11.14 | Unknown | Unknown | Unknown | 565.26 | 3981 | 2064.37 | 554.12 | 1510.25 | Yes | N/A | N/A | 2025-03-21 | 2025-03-28 | 8 | 6 | 2025-03-28 | 2025-04-04 | 8 | 6 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-09 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-05-16 | 1900-02-06 | 28 | 2025-05-16 | 2025-05-16 | 1 | 1 | 14 | 10 | 47 | 35 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-20 | 137 | 100 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 223.89 | -20.61 | Unknown | Unknown | 17.38 | 227.12 | 9504 | 1597.43 | 223.89 | 1373.54 | Yes | N/A | N/A | 2023-03-24 | 2023-03-20 | Unknown | Unknown | 2023-03-20 | 2023-03-31 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | 2023-05-26 | 57 | 41 | Unknown | 2023-06-22 | Unknown | Unknown | Unknown | 2023-10-04 | Unknown | Unknown | 2023-10-04 | 2023-07-07 | Unknown | Unknown | 57 | 41 | 12 | 10 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 418 | 418 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-23 | -533 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-28 | 2024-08-28 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 9257.92 | 2394.59 | Unknown | 555.97 | Unknown | 6307.36 | Unknown | 1168.63 | 9257.92 | -8089.29 | Yes | N/A | N/A | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | 2024-08-28 | 1 | 1 | 2024-08-28 | 2024-11-06 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2024-08-28 | 2024-10-23 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-11-06 | 1900-01-14 | 11 | 2024-11-06 | 2024-11-06 | 1 | 1 | 129 | 93 | 17 | 13 | 146 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 7.05 | 7.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-15 | -466 | -333 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 652.24 | -10.57 | Unknown | Unknown | 23.75 | 639.06 | 3981 | 522.8 | 652.24 | -129.44 | Yes | N/A | N/A | 2023-03-06 | 2023-03-29 | 24 | 18 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | Unknown | Unknown | Unknown | 2023-09-06 | Unknown | Unknown | 2023-09-06 | 2023-09-06 | 1 | 1 | 24 | 18 | 1 | 1 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-31 | 121 | 88 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-11-29 | 2024-04-11 | IOU Designed & Installed | N/A | No | N/A | 8.96 | -7.93 | Unknown | Unknown | Unknown | 16.89 | 3941 | 801.32 | 8.96 | 792.36 | Yes | N/A | N/A | 2023-11-29 | 2023-10-26 | Unknown | Unknown | 2023-10-26 | 2023-11-29 | 35 | 25 | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2024-04-11 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-04-15 | 1900-01-04 | 3 | 2024-04-15 | 2024-05-31 | 47 | 35 | 135 | 97 | 87 | 63 | 222 | 160 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 374.05 | 374.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-28 | 63 | 46 | No | 2023-04-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-12 | 2025-01-08 | IOU Designed & Installed | N/A | Yes | 299 | 30.48 | Unknown | Unknown | Unknown | Unknown | 30.48 | 3981 | 1024.81 | 30.48 | 994.33 | Yes | N/A | N/A | 2023-04-12 | 2024-02-06 | 301 | 215 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-25 | 2025-01-08 | 625 | 447 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-30 | 1900-01-22 | 17 | 2025-01-30 | 2025-01-30 | 1 | 1 | 926 | 662 | 24 | 18 | 950 | 680 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-08 | -383 | -274 | No | 2024-01-31 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-28 | 2024-05-06 | IOU Designed & Installed | N/A | Yes | 28 | -16.57 | -13.44 | Unknown | Unknown | Unknown | -3.13 | 3241 | 1026.37 | -16.57 | 1042.94 | Yes | N/A | N/A | 2024-01-31 | 2024-02-28 | 29 | 21 | 2024-02-28 | 2024-01-31 | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-05-06 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-05-13 | 1900-01-07 | 6 | 2024-05-13 | 2024-05-21 | 9 | 7 | 98 | 70 | 17 | 13 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-06 | -675 | -483 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-17 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | 7.54 | Unknown | Unknown | Unknown | Unknown | 7.54 | 3961 | 192.51 | 7.54 | 184.97 | Yes | N/A | N/A | 2024-06-13 | 2024-06-13 | 1 | 1 | 2024-06-13 | 2024-06-27 | 15 | 11 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-07-10 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-07-31 | 1900-01-21 | 16 | 2024-07-31 | 2024-07-31 | 1 | 1 | 15 | 11 | 38 | 28 | 53 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-28 | -534 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-22 | 2024-03-18 | IOU Designed & Installed | N/A | No | N/A | 851.18 | -10.43 | Unknown | Unknown | 0.94 | 860.67 | 3981 | 1247.07 | 851.18 | 395.89 | Yes | N/A | N/A | 2024-01-22 | 2024-01-01 | Unknown | Unknown | 2024-01-01 | 2024-03-18 | 78 | 56 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | 2024-03-18 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | 2024-04-12 | 1900-01-25 | 20 | 2024-04-12 | 2024-04-12 | 1 | 1 | 4 | 2 | 105 | 77 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | CORONADO | 119 | 119 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-07 | 696 | 499 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2024-05-02 | IOU Designed & Installed | N/A | No | N/A | 1214.33 | 359.3 | Unknown | Unknown | -354 | 1209.03 | 3981 | 1013.18 | 1214.33 | -201.15 | Yes | N/A | N/A | 2023-02-09 | 2023-03-09 | 29 | 21 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-05-02 | 43 | 31 | Unknown | 2024-04-05 | Unknown | Unknown | 2024-05-02 | 2024-05-03 | 1900-01-01 | 2 | 2024-05-03 | 2024-05-03 | 1 | 1 | 72 | 52 | 3 | 3 | 75 | 55 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | -423 | -304 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-10-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2369.13 | -63.97 | Unknown | Unknown | Unknown | 2433.1 | 19905 | 853.19 | 2369.13 | -1515.94 | Yes | N/A | N/A | 2023-10-23 | 2023-10-25 | 3 | 3 | 2023-10-25 | 2023-11-15 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2023-11-09 | 4 | 4 | 2023-11-15 | 2024-03-18 | 125 | 89 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-03-18 | Unknown | Unknown | 128 | 92 | 26 | 20 | 154 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-06 | -500 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-06 | 2025-02-11 | 2025-03-10 | IOU Designed & Installed | N/A | No | N/A | -1834.14 | Unknown | Unknown | Unknown | -1879 | 44.86 | Unknown | 1736.43 | -1834.14 | 3570.57 | Yes | N/A | N/A | 2025-02-06 | 2025-02-11 | 6 | 4 | 2025-02-11 | 2025-02-11 | 1 | 1 | 2025-02-11 | 2025-02-14 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-10 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-03-10 | 2025-03-24 | 1900-01-14 | 11 | 2025-03-24 | 2025-03-24 | 1 | 1 | 35 | 25 | 17 | 13 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-13 | -326 | -234 | No | 2022-08-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-25 | 2023-05-22 | 2023-08-17 | IOU Designed & Installed | N/A | Yes | 270 | -2.22 | -4.33 | Unknown | Unknown | Unknown | 2.11 | 3981 | 540.82 | -2.22 | 543.04 | Yes | N/A | N/A | 2022-08-25 | 2023-05-22 | 271 | 193 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | 2023-08-17 | 88 | 64 | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2023-08-23 | 1900-01-06 | 5 | 2023-08-23 | 2023-08-22 | Unknown | Unknown | 359 | 257 | 7 | 5 | 366 | 262 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | DEL MAR, SAN DIEGO | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-03 | -546 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-10 | 2024-05-10 | 2024-07-30 | IOU Designed & Installed | N/A | No | N/A | 5057.26 | -40.68 | Unknown | Unknown | Unknown | 5097.94 | Unknown | 5462.52 | 5057.26 | 405.26 | Yes | N/A | N/A | 2024-05-10 | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-07-08 | 62 | 44 | 2024-06-12 | 2024-06-24 | 13 | 9 | 2024-05-16 | 2024-07-24 | 44 | 31 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-09-03 | 1900-02-04 | 26 | 2024-09-03 | 2024-09-03 | 1 | 1 | 13 | 9 | 143 | 102 | 156 | 111 | Steps 2,3,5,6,7 | 81 | 57 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 603.05 | 603.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-13 | -584 | -419 | No | 2024-12-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-12 | 2024-12-12 | 2025-04-02 | IOU Designed & Installed | N/A | Yes | 35 | 31.29 | Unknown | Unknown | Unknown | Unknown | 31.29 | Unknown | 1861.82 | 31.29 | 1830.53 | Yes | N/A | N/A | 2024-12-12 | 2025-01-15 | 35 | 25 | 2025-01-15 | 2025-01-14 | Unknown | Unknown | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-04-02 | 79 | 57 | Unknown | Unknown | Unknown | Unknown | 2025-04-02 | 2025-04-08 | 1900-01-06 | 5 | 2025-04-08 | 2025-04-08 | 1 | 1 | 114 | 82 | 8 | 6 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-24 | -43 | -32 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2025-02-03 | 2025-04-30 | IOU Designed & Installed | N/A | No | N/A | 2368.41 | 303.12 | Unknown | 151.13 | Unknown | 1914.16 | 3981 | 1218.82 | 2368.41 | -1149.59 | Yes | N/A | N/A | 2024-07-24 | 2025-01-31 | 192 | 138 | 2025-01-31 | 2025-02-03 | 4 | 2 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-04-30 | 87 | 63 | Unknown | 2025-04-29 | Unknown | Unknown | 2025-04-30 | 2025-05-12 | 1900-01-12 | 9 | 2025-05-12 | 2025-05-12 | 1 | 1 | 279 | 201 | 18 | 12 | 297 | 213 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-SOUTH of 56 | 81.05 | 81.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-14 | -437 | -314 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-06-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 573.04 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-17 | 2023-06-01 | 16 | 12 | 2023-06-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | 2023-06-12 | 11 | 7 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | Unknown | Unknown | 2023-12-04 | 2023-12-05 | 2 | 2 | 16 | 12 | 13 | 9 | 29 | 21 | Steps 2,3,5,6,7 | 10 | 6 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-19 | -578 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-10 | 2025-03-11 | 2025-05-14 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1789.75 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-10 | 2025-02-25 | Unknown | Unknown | 2025-02-25 | 2025-03-11 | 15 | 11 | 2025-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-05-14 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-05-20 | 1900-01-06 | 5 | 2025-05-20 | 2025-05-20 | 1 | 1 | 65 | 47 | 23 | 17 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 129.05 | 129.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-20 | -390 | -279 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-06 | 2024-07-25 | IOU Designed & Installed | N/A | No | N/A | 2032.27 | Unknown | Unknown | Unknown | 36.67 | 1995.6 | 3981 | 1757.4 | 2032.27 | -274.87 | Yes | N/A | N/A | 2023-06-06 | 2024-04-04 | 304 | 218 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-07-25 | 70 | 50 | Unknown | 2024-07-23 | Unknown | Unknown | 2024-07-25 | 2024-07-29 | 1900-01-04 | 3 | 2024-07-29 | 2024-07-26 | Unknown | Unknown | 374 | 268 | 5 | 3 | 379 | 271 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | COUNTY OF ORANGE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 423 | 302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2752.82 | 150.03 | Unknown | 36.47 | 45.86 | 2520.46 | 3981 | 435.81 | 2752.82 | -2317.01 | Yes | N/A | N/A | 2024-03-08 | 2024-04-11 | 35 | 25 | 2024-04-11 | 2024-04-11 | 1 | 1 | 2024-04-11 | Unknown | Unknown | Unknown | 2024-04-11 | 2024-04-16 | 6 | 4 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | 2025-04-28 | 2025-04-28 | 1 | 1 | 35 | 25 | 8 | 6 | 43 | 31 | Steps 2,3,5,6,7 | 5 | 3 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-02 | -132 | -95 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | 2025-02-10 | IOU Designed & Installed | N/A | No | N/A | 597.37 | Unknown | Unknown | Unknown | Unknown | 597.37 | Unknown | 628.26 | 597.37 | 30.89 | Yes | N/A | N/A | 2024-11-05 | 2024-11-05 | 1 | 1 | 2024-11-05 | 2025-02-10 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-10 | 2025-02-20 | 1900-01-10 | 9 | 2025-02-20 | 2025-02-20 | 1 | 1 | 1 | 1 | 110 | 80 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-02 | 685 | 490 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | 6752.44 | 1833.63 | Unknown | Unknown | Unknown | 4918.81 | 1786.6 | 822.11 | 6752.44 | -5930.33 | Yes | N/A | N/A | 2025-04-10 | 2025-04-10 | 1 | 1 | 2025-04-10 | 2025-05-30 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-10 | 12 | 8 | Unknown | 2025-06-04 | Unknown | Unknown | 2025-06-05 | 2025-06-18 | 1900-01-13 | 10 | 2025-06-18 | 2025-06-17 | Unknown | Unknown | 13 | 9 | 65 | 47 | 78 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-23 | -276 | -198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | 2024-11-20 | IOU Designed & Installed | N/A | No | N/A | 278.78 | 2381.7 | Unknown | 83.8 | -3265 | 1078.28 | Unknown | 3265.12 | 278.78 | 2986.34 | Yes | N/A | N/A | 2024-10-02 | 2024-11-11 | 41 | 29 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-10 | Unknown | Unknown | 2024-11-20 | 2024-11-20 | 1899-12-31 | 1 | 2024-11-20 | 2024-11-20 | 1 | 1 | 41 | 29 | 2 | 2 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-22 | -258 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-30 | 2023-01-30 | 2023-03-28 | IOU Designed & Installed | N/A | No | N/A | 218.32 | -7.2 | Unknown | Unknown | 2.21 | 223.31 | Unknown | 623.85 | 218.32 | 405.53 | Yes | N/A | N/A | 2023-01-30 | 2023-02-02 | 4 | 4 | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-02 | 2023-03-28 | 55 | 39 | Unknown | 2023-04-07 | Unknown | Unknown | 2023-03-28 | 2023-04-08 | 1900-01-11 | 9 | 2023-04-08 | 2023-04-08 | 1 | 0 | 59 | 43 | 13 | 9 | 72 | 52 | Steps 2,3,5,6,7 | 10 | 8 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-06 | -642 | -460 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-25 | 2025-02-25 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | 3.74 | Unknown | Unknown | Unknown | Unknown | 3.74 | 3981 | 196.59 | 3.74 | 192.85 | Yes | N/A | N/A | 2025-02-25 | 2025-04-01 | 36 | 26 | 2025-04-01 | 2025-04-04 | 4 | 4 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-25 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-05 | 1900-01-10 | 7 | 2025-05-05 | 2025-05-05 | 1 | 1 | 58 | 42 | 16 | 12 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-26 | -618 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 865.4 | 209.29 | Unknown | Unknown | 8.63 | 647.48 | 3981 | 2070.92 | 865.4 | 1205.52 | Yes | N/A | N/A | 2024-10-23 | 2024-10-28 | 6 | 4 | 2024-10-28 | 2024-11-04 | 8 | 6 | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | Unknown | Unknown | 2025-01-16 | 2025-01-16 | 1 | 1 | 6 | 4 | 9 | 7 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | -507 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | 2025-06-13 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1744.48 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-19 | 2024-11-26 | Unknown | Unknown | 2024-11-26 | 2024-12-19 | 24 | 18 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-06-13 | 177 | 127 | Unknown | Unknown | Unknown | Unknown | 2025-06-13 | 2025-06-30 | 1900-01-17 | 12 | 2025-06-30 | 2025-06-30 | 1 | 1 | 177 | 127 | 43 | 31 | 220 | 158 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | -136 | -99 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-07 | 2024-06-27 | IOU Designed & Installed | N/A | No | N/A | 20.75 | -16 | Unknown | Unknown | Unknown | 36.75 | Unknown | 907.13 | 20.75 | 886.38 | Yes | N/A | N/A | 2024-05-06 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-05-07 | 48 | 34 | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-06-27 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-07-16 | 1900-01-19 | 14 | 2024-07-16 | 2024-07-16 | 1 | 1 | 52 | 38 | 69 | 49 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-12 | 295 | 212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2024-02-22 | 2024-08-01 | IOU Designed & Installed | N/A | No | N/A | 2272.97 | 657.79 | Unknown | 134.48 | Unknown | 1480.7 | 3981 | 1025.68 | 2272.97 | -1247.29 | Yes | N/A | N/A | 2023-10-25 | 2023-11-21 | 28 | 20 | 2023-11-21 | 2024-02-22 | 94 | 68 | 2024-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-08-01 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-08-01 | 1899-12-31 | 1 | 2024-08-01 | 2024-08-02 | 2 | 2 | 190 | 136 | 97 | 71 | 287 | 207 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 4992 | 4992 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-02-28 | -276 | -199 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | 2024-04-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 473.88 | -25.72 | Unknown | Unknown | Unknown | 499.6 | 31848 | 2601.34 | 473.88 | 2127.46 | Yes | N/A | N/A | 2024-02-27 | 2024-01-18 | Unknown | Unknown | 2024-01-18 | 2024-05-02 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-07-15 | 113 | 81 | 2024-05-02 | 2024-05-13 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | Unknown | Unknown | 2024-05-29 | 2024-05-28 | Unknown | Unknown | 12 | 8 | 219 | 157 | 231 | 165 | Steps 2,3,5,6,7 | 74 | 52 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-01 | 303 | 218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-06 | 2023-10-06 | 2024-12-23 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 63046.09 | 12012.76 | Unknown | Unknown | 223.52 | 50809.81 | 639362.18 | 54273.05 | 63046.09 | -8773.04 | Yes | N/A | N/A | 2023-10-06 | 2023-11-20 | 46 | 32 | 2023-11-20 | 2024-02-20 | 93 | 67 | 2023-11-27 | 2024-04-15 | 25 | 19 | 2023-11-05 | 2024-10-30 | 293 | 210 | 2024-02-20 | Unknown | Unknown | Unknown | 2024-09-03 | 2024-11-27 | 86 | 62 | 2024-12-23 | 2025-01-29 | 1900-02-06 | 28 | 2025-01-29 | 2025-01-29 | 1 | 1 | 71 | 51 | 511 | 368 | 582 | 419 | Steps 2,3,5,6,7 | 500 | 357 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-06 | -601 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-02-16 | 2024-03-01 | IOU Designed & Installed | N/A | No | N/A | 331.12 | -9.06 | Unknown | Unknown | Unknown | 340.18 | Unknown | 983.09 | 331.12 | 651.97 | Yes | N/A | N/A | 2024-01-25 | 2024-01-11 | Unknown | Unknown | 2024-01-11 | 2024-02-16 | 37 | 27 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-03-01 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-03-15 | 1900-01-14 | 11 | 2024-03-15 | 2024-03-15 | 1 | 1 | 15 | 11 | 53 | 39 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | -674 | -482 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | 2024-11-18 | IOU Designed & Installed | N/A | No | N/A | 1736.49 | -35.63 | Unknown | Unknown | Unknown | 1772.12 | 3981 | 1754.39 | 1736.49 | 17.9 | Yes | N/A | N/A | 2024-11-11 | 2024-11-09 | Unknown | Unknown | 2024-11-09 | 2024-11-11 | 3 | 1 | 2024-11-11 | Unknown | Unknown | Unknown | 2024-11-11 | 2024-12-13 | 33 | 25 | 2024-11-11 | 2024-11-18 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-12-05 | 1900-01-17 | 14 | 2024-12-05 | 2024-12-05 | 1 | 1 | 8 | 6 | 55 | 41 | 63 | 47 | Steps 2,3,5,6,7 | 32 | 24 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-30 | -524 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-10-01 | 2025-03-19 | IOU Designed & Installed | N/A | No | N/A | 23.6 | Unknown | Unknown | Unknown | Unknown | 23.6 | 3981 | 1571.84 | 23.6 | 1548.24 | Yes | N/A | N/A | 2024-09-30 | 2024-09-13 | Unknown | Unknown | 2024-09-13 | 2024-10-01 | 19 | 13 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2025-03-19 | 170 | 122 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-04-03 | 1900-01-15 | 12 | 2025-04-03 | 2025-03-24 | Unknown | Unknown | 170 | 122 | 35 | 25 | 205 | 147 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | -126 | -91 | No | 2023-04-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-19 | 2023-06-16 | Unknown | IOU Designed & Installed | N/A | Yes | 149 | -9.15 | -6.64 | Unknown | Unknown | Unknown | -2.51 | 3981 | 464.78 | -9.15 | 473.93 | Yes | N/A | N/A | 2023-04-19 | 2023-09-15 | 150 | 108 | 2023-09-15 | 2023-09-15 | 1 | 1 | 2023-09-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | Unknown | Unknown | 2023-10-27 | 2023-10-27 | 1 | 1 | 150 | 108 | 2 | 2 | 152 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-15 | -595 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-28 | 2024-08-04 | 2024-08-23 | IOU Designed & Installed | N/A | No | N/A | 31.24 | Unknown | Unknown | Unknown | Unknown | 31.24 | Unknown | 1134.45 | 31.24 | 1103.21 | Yes | N/A | N/A | 2024-05-28 | 2024-07-25 | 59 | 43 | 2024-07-25 | 2024-08-04 | 11 | 7 | 2024-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-04 | 2024-08-23 | 20 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-08-28 | 1900-01-05 | 4 | 2024-08-28 | 2024-08-28 | 1 | 1 | 79 | 58 | 18 | 12 | 97 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-18 | -316 | -227 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-25 | 2023-02-06 | 2023-02-19 | IOU Designed & Installed | N/A | No | N/A | 9.41 | -7.73 | Unknown | Unknown | 12.01 | 5.13 | 3981 | 403.04 | 9.41 | 393.63 | Yes | N/A | N/A | 2023-01-25 | 2023-02-06 | 13 | 9 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | 2023-02-19 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-02-19 | 2023-08-23 | 1900-07-04 | 133 | 2023-08-23 | 2023-03-08 | Unknown | Unknown | 27 | 19 | 186 | 133 | 213 | 152 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | COUNTY OF SAN DIEGO-NORTH of 56, POWAY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-13 | -660 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-04 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | 1007.52 | Unknown | Unknown | Unknown | Unknown | 1007.52 | 3241 | 1370.4 | 1007.52 | 362.88 | Yes | N/A | N/A | 2025-04-03 | 2025-03-18 | Unknown | Unknown | 2025-03-18 | 2025-04-04 | 18 | 14 | 2025-04-04 | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-29 | 19 | 11 | 2025-04-04 | 2025-05-06 | 33 | 23 | Unknown | 2025-05-05 | Unknown | Unknown | 2025-05-06 | 2025-05-22 | 1900-01-16 | 13 | 2025-05-22 | 2025-05-22 | 1 | 1 | 33 | 23 | 55 | 39 | 88 | 62 | Steps 2,3,5,6,7 | 25 | 17 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 190000 | 190000 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-24 | 767 | 548 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-12-12 | 2025-03-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2143.5 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-13 | 2024-10-01 | 111 | 79 | 2024-10-01 | 2025-01-22 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-04-22 | 91 | 65 | Unknown | 2025-03-25 | Unknown | Unknown | 2025-03-25 | 2025-04-30 | 1900-02-05 | 27 | 2025-04-30 | 2025-04-29 | Unknown | Unknown | 202 | 144 | 151 | 109 | 353 | 253 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Commercial | Underserved Community | Jamul | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-31 | 539 | 386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-27 | 2023-10-17 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 86754.24 | 12762.01 | Unknown | Unknown | 137.85 | 73854.38 | 0 | 33169.15 | 86754.24 | -53585.09 | Yes | N/A | N/A | 2022-12-27 | 2023-04-19 | 114 | 82 | 2023-04-19 | 2024-07-10 | 449 | 321 | 2024-01-09 | 2024-09-26 | 6 | 6 | 2024-01-18 | 2024-06-12 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-11-20 | 1900-04-30 | 87 | 2024-11-20 | 2024-11-20 | 1 | 1 | 120 | 88 | 579 | 415 | 699 | 503 | Steps 2,3,5,6,7 | 435 | 311 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 25.5 | 25.5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-20 | -604 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2023-12-19 | 2024-01-17 | IOU Designed & Installed | N/A | No | N/A | 51.69 | -8.2 | Unknown | Unknown | Unknown | 59.89 | Unknown | 981.88 | 51.69 | 930.19 | Yes | N/A | N/A | 2023-12-07 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2023-12-19 | 84 | 60 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-01-17 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | 2024-01-25 | 1900-01-08 | 7 | 2024-01-25 | 2024-01-25 | 1 | 1 | 30 | 22 | 94 | 68 | 124 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN JUAN CAPISTRANO | N/A | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-07 | -199 | -143 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-08 | 2024-01-08 | 2024-05-15 | IOU Designed & Installed | N/A | No | N/A | 12974.69 | 138.1 | Unknown | 34.59 | 6.82 | 12795.18 | 3981 | 1325.06 | 12974.69 | -11649.63 | Yes | N/A | N/A | 2024-01-08 | 2024-01-17 | 10 | 8 | 2024-01-17 | 2024-03-11 | 55 | 39 | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | 2024-05-15 | 66 | 48 | Unknown | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-05-22 | 1900-01-07 | 6 | 2024-05-22 | 2024-05-22 | 1 | 1 | 76 | 56 | 64 | 46 | 140 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 87.4 | 87.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | -435 | -311 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2023-12-29 | 2024-05-28 | IOU Designed & Installed | N/A | No | N/A | 3578.3 | -6 | Unknown | Unknown | 171.7 | 3412.6 | 3981 | 937.82 | 3578.3 | -2640.48 | Yes | N/A | N/A | 2023-12-21 | 2024-02-07 | 49 | 35 | 2024-02-07 | 2024-02-07 | 1 | 1 | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-05-28 | 112 | 80 | Unknown | 2024-05-18 | Unknown | Unknown | 2024-05-28 | 2024-06-24 | 1900-01-27 | 20 | 2024-06-24 | 2024-06-23 | Unknown | Unknown | 161 | 115 | 29 | 21 | 190 | 136 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -235 | -168 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 20.64 | Unknown | Unknown | Unknown | Unknown | 20.64 | Unknown | 1736.43 | 20.64 | 1715.79 | Yes | N/A | N/A | 2025-02-13 | 2025-02-18 | 6 | 4 | 2025-02-18 | 2025-02-21 | 4 | 4 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | Unknown | Unknown | 2025-04-09 | 2025-04-09 | 1 | 1 | 6 | 4 | 5 | 5 | 11 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 25 | 25 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-02 | -385 | -276 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-07-07 | 2023-10-26 | IOU Designed & Installed | N/A | No | N/A | 4329.57 | 888.83 | Unknown | 173.52 | Unknown | 3267.22 | 3981 | 1018.68 | 4329.57 | -3310.89 | Yes | N/A | N/A | 2023-03-20 | 2023-06-05 | 78 | 56 | 2023-06-05 | 2023-07-07 | 33 | 25 | 2023-07-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-07 | 2023-10-26 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2023-11-13 | 1900-01-18 | 13 | 2023-11-13 | 2023-11-13 | 1 | 1 | 190 | 136 | 53 | 39 | 243 | 175 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-15 | 361 | 258 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -538.29 | -13.08 | Unknown | Unknown | -537.27 | 12.06 | Unknown | 500.9 | -538.29 | 1039.19 | Yes | N/A | N/A | 2023-03-10 | 2023-03-09 | Unknown | Unknown | 2023-03-09 | 2023-06-22 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-08-18 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-03 | Unknown | Unknown | 2024-08-03 | 2023-12-11 | Unknown | Unknown | 58 | 42 | 106 | 76 | 164 | 118 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 133.05 | 133.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | 138 | 99 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-09-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 823.34 | -8.41 | Unknown | Unknown | Unknown | 831.75 | 3981 | 706.44 | 823.34 | -116.9 | Yes | N/A | N/A | 2023-08-28 | 2023-09-08 | 12 | 10 | 2023-09-08 | 2023-09-08 | 1 | 1 | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | Unknown | Unknown | Unknown | 2024-06-19 | Unknown | Unknown | 2024-06-19 | 2024-06-18 | Unknown | Unknown | 12 | 10 | 1 | 1 | 13 | 11 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | 44 | 33 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-04 | 2024-12-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 430.57 | -8.66 | Unknown | Unknown | Unknown | 439.23 | Unknown | 499.14 | 430.57 | 68.57 | Yes | N/A | N/A | 2024-12-04 | 2025-01-21 | 49 | 35 | 2025-01-21 | 2025-04-21 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2025-01-25 | 46 | 33 | 2025-04-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | Unknown | Unknown | 2025-05-15 | 2025-05-15 | 1 | 1 | 49 | 35 | 138 | 99 | 187 | 134 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-16 | 292 | 209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2024-01-25 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | -1136.48 | Unknown | Unknown | Unknown | -4382 | 3245.52 | Unknown | 4381.84 | -1136.48 | 5518.32 | Yes | N/A | N/A | 2023-08-30 | 2024-01-11 | 135 | 97 | 2024-01-11 | 2024-04-25 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | 2024-04-11 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-09-03 | 1900-02-11 | 31 | 2024-09-03 | 2024-09-03 | 1 | 1 | 135 | 97 | 152 | 110 | 287 | 207 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SD 1189-H1 JUNIPERS PH6 | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-06-01 | 118 | 85 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-25 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 5984.66 | -94.34 | Unknown | Unknown | Unknown | 6079 | 3981 | Not available | 5984.66 | Unknown | Yes | N/A | N/A | 2024-03-18 | 2024-03-19 | 2 | 2 | 2024-03-19 | 2024-05-02 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | 2024-09-25 | 2024-09-27 | 1900-01-02 | 3 | 2024-09-27 | 2024-09-27 | 1 | 1 | 2 | 2 | 49 | 37 | 51 | 39 | Steps 2,3,5,6,7 | 195 | 139 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-16 | -339 | -244 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | 2024-01-31 | IOU Designed & Installed | N/A | No | N/A | 5.87 | -7.39 | Unknown | Unknown | Unknown | 13.26 | 3241 | 887.91 | 5.87 | 882.04 | Yes | N/A | N/A | 2024-01-29 | 2024-01-29 | 1 | 1 | 2024-01-29 | 2024-01-29 | 1 | 1 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-01-31 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-02-12 | 1900-01-12 | 9 | 2024-02-12 | 2024-02-12 | 1 | 1 | 4 | 4 | 15 | 11 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | San Ysidro | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-03-19 | 1340 | 957 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-25 | 2023-08-25 | 2024-11-06 | IOU Designed & Installed | N/A | No | N/A | 8224.32 | 273.47 | Unknown | Unknown | -2728.65 | 10679.5 | 0 | 2369.92 | 8224.32 | -5854.4 | Yes | N/A | N/A | 2023-08-25 | 2023-08-25 | 1 | 1 | 2023-08-25 | 2024-05-14 | 264 | 188 | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2023-09-01 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | 2024-11-06 | 2024-11-18 | 1900-01-12 | 9 | 2024-11-18 | 2024-11-18 | 1 | 1 | 1 | 1 | 283 | 203 | 284 | 204 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | COUNTY OF SAN DIEGO-NORTH of 56 | 217 | 217 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 80 | 57 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 609.19 | -31.36 | Unknown | Unknown | 3.2 | 637.35 | 3981 | 695.06 | 609.19 | 85.87 | Yes | N/A | N/A | 2023-02-24 | 2023-02-24 | 1 | 1 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | 2023-06-16 | 2 | 2 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-06-20 | Unknown | Unknown | 1 | 1 | 2 | 2 | 3 | 3 | Steps 2,3,5,6,7 | 112 | 80 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-16 | -7 | -6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-20 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 616.13 | -11.7 | Unknown | Unknown | Unknown | 627.83 | 3981 | 817.53 | 616.13 | 201.4 | Yes | N/A | N/A | 2023-10-20 | 2023-08-31 | Unknown | Unknown | 2023-08-31 | 2023-10-20 | 51 | 37 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2024-07-23 | 278 | 198 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-08-09 | 1900-01-17 | 14 | 2024-08-09 | 2024-08-09 | 1 | 1 | 278 | 198 | 70 | 52 | 348 | 250 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-09 | -163 | -118 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-09 | 2023-10-09 | 2023-11-20 | IOU Designed & Installed | N/A | No | N/A | 789.94 | 483.36 | Unknown | Unknown | Unknown | 306.58 | Unknown | 158.14 | 789.94 | -631.8 | Yes | N/A | N/A | 2023-10-09 | 2023-05-17 | Unknown | Unknown | 2023-05-17 | 2023-10-26 | 163 | 117 | 2023-10-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2023-11-20 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-11-20 | 2023-11-28 | 1900-01-08 | 7 | 2023-11-28 | 2023-11-28 | 1 | 1 | 26 | 18 | 173 | 125 | 199 | 143 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 43 | 43 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-26 | -301 | -216 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-28 | 2023-08-28 | 2023-09-22 | IOU Designed & Installed | N/A | No | N/A | -13.87 | -10.9 | Unknown | Unknown | Unknown | -2.97 | Unknown | 153.83 | -13.87 | 167.7 | Yes | N/A | N/A | 2023-08-28 | 2023-09-18 | 22 | 16 | 2023-09-18 | 2023-09-20 | 3 | 3 | 2023-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | 2023-09-22 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2023-09-22 | 2023-09-29 | 1900-01-07 | 6 | 2023-09-29 | 2023-09-29 | 1 | 1 | 25 | 19 | 12 | 10 | 37 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | 164 | 164 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-30 | 917 | 656 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-17 | 2023-04-18 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 27242.55 | 1536.87 | Unknown | 76.83 | 446.66 | 25182.19 | 22767.7 | 16348.19 | 27242.55 | -10894.36 | Yes | N/A | N/A | 2023-04-17 | 2024-02-21 | 311 | 223 | 2024-02-21 | 2024-10-10 | 233 | 167 | 2024-07-03 | 2024-09-19 | 79 | 57 | 2024-08-15 | 2024-10-09 | 44 | 32 | 2024-10-10 | Unknown | Unknown | Unknown | 2025-01-30 | 2025-02-27 | 29 | 21 | 2025-03-17 | 2025-04-04 | 1900-01-18 | 15 | 2025-04-04 | 2025-04-04 | 1 | 1 | 390 | 280 | 326 | 236 | 716 | 516 | Steps 2,3,5,6,7 | 134 | 96 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | -494 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-28 | 2025-03-28 | 2025-04-16 | IOU Designed & Installed | N/A | No | N/A | 2564.34 | 662.35 | Unknown | Unknown | Unknown | 1901.99 | Unknown | 1736.05 | 2564.34 | -828.29 | Yes | N/A | N/A | 2025-03-28 | 2025-02-24 | Unknown | Unknown | 2025-02-24 | 2025-03-28 | 33 | 25 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-16 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | 2025-04-30 | 1900-01-14 | 11 | 2025-04-30 | 2025-04-30 | 1 | 1 | 20 | 14 | 49 | 37 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-25 | 144 | 103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-02-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | 544.1 | -16.04 | Unknown | Unknown | Unknown | 560.14 | 0 | 1168.15 | 544.1 | 624.05 | Yes | N/A | N/A | 2023-01-31 | 2023-02-02 | 3 | 3 | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | Unknown | Unknown | 2024-06-18 | 2024-06-17 | Unknown | Unknown | 3 | 3 | 0 | 0 | 3 | 3 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-28 | 605 | 434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-06-20 | 2023-10-12 | IOU Designed & Installed | N/A | No | N/A | 11420.39 | 441.82 | Unknown | 51.39 | -2692 | 13619.18 | Unknown | 2643.13 | 11420.39 | -8777.26 | Yes | N/A | N/A | 2023-05-23 | 2023-05-02 | Unknown | Unknown | 2023-05-02 | 2023-08-09 | 100 | 72 | 2023-06-26 | 2023-10-17 | 4 | 2 | 2023-08-03 | 2023-08-11 | 5 | 0 | 2023-10-12 | Unknown | Unknown | Unknown | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | 2023-10-26 | 1900-01-14 | 11 | 2023-10-26 | 2023-10-26 | 1 | 1 | 4 | 2 | 122 | 85 | 126 | 87 | Steps 2,3,5,6,7 | 119 | 85 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 116.05 | 116.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-20 | 451 | 322 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-07-18 | 2025-01-14 | IOU Designed & Installed | N/A | No | N/A | 32808.64 | 1931.13 | Unknown | Unknown | -8987.98 | 39865.49 | Unknown | 9761.79 | 32808.64 | -23046.85 | Yes | N/A | N/A | 2024-02-22 | 2024-07-17 | 147 | 105 | 2024-07-17 | 2024-12-31 | 168 | 120 | 2024-07-12 | 2024-12-20 | -36 | -31 | 2024-08-05 | 2024-12-19 | 70 | 52 | 2024-12-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-04-15 | 1900-04-01 | 66 | 2025-04-15 | 2025-04-15 | 1 | 1 | 111 | 74 | 331 | 239 | 442 | 313 | Steps 2,3,5,6,7 | 309 | 221 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-21 | -416 | -297 | No | 2024-10-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-11-06 | 2025-04-23 | IOU Designed & Installed | N/A | Yes | 52 | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1810.76 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-01 | 2024-11-22 | 53 | 39 | 2024-11-22 | 2024-11-06 | Unknown | Unknown | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2025-04-23 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-05-01 | 1900-01-08 | 7 | 2025-05-01 | 2025-05-01 | 1 | 1 | 222 | 160 | 10 | 8 | 232 | 168 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 54 | 54 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-22 | -307 | -220 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2024-10-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1147.36 | -22 | Unknown | Unknown | Unknown | 1169.36 | 7962 | 1643.98 | 1147.36 | 496.62 | Yes | N/A | N/A | 2023-10-16 | 2024-10-22 | 373 | 267 | 2024-10-22 | 2024-10-22 | 1 | 1 | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | Unknown | Unknown | 2024-12-19 | 2024-12-19 | 1 | 1 | 373 | 267 | 2 | 2 | 375 | 269 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-31 | -592 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-12 | 2023-12-12 | 2024-01-10 | IOU Designed & Installed | N/A | No | N/A | 303.6 | -10.89 | Unknown | Unknown | Unknown | 314.49 | Unknown | 1186.79 | 303.6 | 883.19 | Yes | N/A | N/A | 2023-12-12 | 2023-12-12 | 1 | 1 | 2023-12-12 | 2023-12-12 | 1 | 1 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | 2024-01-10 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-01-17 | 1900-01-07 | 6 | 2024-01-17 | 2024-01-17 | 1 | 1 | 31 | 23 | 10 | 8 | 41 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-22 | -583 | -418 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | 2024-05-13 | 2024-05-29 | IOU Designed & Installed | N/A | No | N/A | 7.07 | -10.84 | Unknown | Unknown | Unknown | 17.91 | Unknown | 516.81 | 7.07 | 509.74 | Yes | N/A | N/A | 2024-05-13 | 2024-05-10 | Unknown | Unknown | 2024-05-10 | 2024-05-13 | 4 | 2 | 2024-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-05-29 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-06-18 | 1900-01-20 | 15 | 2024-06-18 | 2024-06-18 | 1 | 1 | 17 | 13 | 26 | 18 | 43 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-26 | -502 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-02 | 2024-08-21 | IOU Designed & Installed | N/A | No | N/A | 3167.85 | 512.18 | Unknown | Unknown | 20.5 | 2635.17 | 3981 | 1195.74 | 3167.85 | -1972.11 | Yes | N/A | N/A | 2024-03-27 | 2024-04-12 | 17 | 13 | 2024-04-12 | 2024-04-18 | 7 | 5 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-08-21 | 126 | 90 | Unknown | 2024-08-20 | Unknown | Unknown | 2024-08-21 | 2024-09-11 | 1900-01-21 | 16 | 2024-09-11 | 2024-09-11 | 1 | 1 | 143 | 103 | 30 | 22 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-10 | -171 | -124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-04-22 | 2025-03-17 | IOU Designed & Installed | N/A | No | N/A | 5813.18 | -8.94 | Unknown | Unknown | 60.48 | 5761.64 | 3981 | 1236.3 | 5813.18 | -4576.88 | Yes | N/A | N/A | 2024-03-28 | 2024-01-02 | Unknown | Unknown | 2024-01-02 | 2024-04-22 | 112 | 80 | 2024-04-22 | Unknown | Unknown | Unknown | 2024-05-29 | 2024-05-29 | 1 | 1 | 2025-03-17 | 2025-03-17 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-04-22 | 1900-02-05 | 27 | 2025-04-22 | 2025-04-22 | 1 | 1 | 1 | 1 | 151 | 109 | 152 | 110 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | -115 | -84 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-05 | 2023-09-05 | 2024-06-10 | IOU Designed & Installed | N/A | No | N/A | 4148.11 | 272.1 | Unknown | Unknown | -1196 | 5072.01 | 3981 | 1694.26 | 4148.11 | -2453.85 | Yes | N/A | N/A | 2023-09-05 | 2023-09-05 | 1 | 1 | 2023-09-05 | 2023-10-16 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-09-05 | 2024-03-29 | 29 | 21 | 2023-10-16 | 2024-05-29 | 227 | 163 | Unknown | 2024-05-17 | Unknown | Unknown | 2024-06-10 | 2024-07-23 | 1900-02-12 | 32 | 2024-07-23 | 2024-07-08 | Unknown | Unknown | 228 | 164 | 115 | 83 | 343 | 247 | Steps 2,3,5,6,7 | 165 | 119 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-04 | 71 | 51 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-04-25 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 2522.76 | 471.65 | Unknown | Unknown | -6293 | 8344.11 | 3981 | 9680.96 | 2522.76 | 7158.2 | Yes | N/A | N/A | 2023-04-24 | 2023-02-10 | Unknown | Unknown | 2023-02-10 | 2023-06-23 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-06-26 | 4 | 2 | 2023-06-23 | 2023-10-19 | 119 | 85 | 2023-12-21 | 2024-03-07 | 78 | 56 | 2024-03-25 | 2024-04-17 | 1900-01-23 | 18 | 2024-04-17 | 2024-04-15 | Unknown | Unknown | 119 | 85 | 240 | 172 | 359 | 257 | Steps 2,3,5,6,7 | 3 | 1 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-14 | -355 | -254 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-15 | 2025-04-15 | 2025-04-22 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 696.38 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-15 | 2025-04-14 | Unknown | Unknown | 2025-04-14 | 2025-04-15 | 2 | 2 | 2025-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-04-22 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-04-22 | 2025-04-25 | 1900-01-03 | 4 | 2025-04-25 | 2025-04-24 | Unknown | Unknown | 8 | 6 | 6 | 6 | 14 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | -564 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-21 | 2025-03-13 | IOU Designed & Installed | N/A | No | N/A | 72.86 | Unknown | Unknown | Unknown | -1297.1 | 1369.96 | Unknown | 1311.83 | 72.86 | 1238.97 | Yes | N/A | N/A | 2024-11-21 | 2024-12-12 | 22 | 16 | 2024-12-12 | 2024-12-20 | 9 | 7 | 2024-12-20 | 2025-01-14 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-03-13 | 59 | 43 | Unknown | 2025-03-11 | Unknown | Unknown | 2025-03-13 | 2025-04-14 | 1900-02-01 | 23 | 2025-04-14 | 2025-04-14 | 1 | 1 | 107 | 77 | 43 | 31 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 3 | 3 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-13 | 2024-11-11 | IOU Designed & Installed | N/A | No | N/A | 382.37 | Unknown | Unknown | Unknown | 5.78 | 376.59 | Unknown | 1347.42 | 382.37 | 965.05 | Yes | N/A | N/A | 2024-09-11 | 2024-08-21 | Unknown | Unknown | 2024-08-21 | 2024-10-14 | 55 | 39 | 2024-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2024-11-11 | 29 | 21 | Unknown | 2024-11-08 | Unknown | Unknown | 2024-11-11 | 2024-12-04 | 1900-01-23 | 18 | 2024-12-04 | 2024-12-03 | Unknown | Unknown | 29 | 21 | 79 | 57 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-04 | -668 | -479 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-13 | 2025-03-04 | IOU Designed & Installed | N/A | No | N/A | 705.28 | -14.17 | Unknown | Unknown | Unknown | 719.45 | 3981 | 2094.83 | 705.28 | 1389.55 | Yes | N/A | N/A | 2025-02-13 | 2025-02-13 | 1 | 1 | 2025-02-13 | 2025-02-13 | 1 | 1 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-03-04 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-04-07 | 1900-02-03 | 25 | 2025-04-07 | 2025-04-07 | 1 | 1 | 21 | 15 | 37 | 27 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 93 | 93 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-29 | -221 | -158 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 15.46 | -13.71 | Unknown | Unknown | Unknown | 29.17 | 3981 | 720.91 | 15.46 | 705.45 | Yes | N/A | N/A | 2023-03-03 | 2023-03-03 | 1 | 1 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-05-22 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-20 | -508 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-18 | 2023-08-18 | 2023-10-20 | IOU Designed & Installed | N/A | No | N/A | 1658.18 | 582.92 | Unknown | Unknown | Unknown | 1075.26 | Unknown | 899.88 | 1658.18 | -758.3 | Yes | N/A | N/A | 2023-08-18 | 2023-08-18 | 1 | 1 | 2023-08-18 | 2023-08-18 | 1 | 1 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | 2023-10-20 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2023-11-29 | 1900-02-09 | 29 | 2023-11-29 | 2023-11-29 | 1 | 1 | 65 | 47 | 43 | 31 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -539 | -386 | No | 2023-09-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-08 | 2023-10-05 | IOU Designed & Installed | N/A | Yes | 10 | 1233.89 | 489.8 | Unknown | Unknown | Unknown | 744.09 | Unknown | 943.21 | 1233.89 | -290.68 | Yes | N/A | N/A | 2023-09-08 | 2023-09-18 | 11 | 7 | 2023-09-18 | 2023-09-08 | Unknown | Unknown | 2023-09-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | 2023-10-05 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2023-10-05 | 2023-10-10 | 1900-01-05 | 4 | 2023-10-10 | 2023-10-10 | 1 | 1 | 39 | 27 | 7 | 5 | 46 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 139.05 | 139.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | -303 | -218 | No | 2024-08-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | 2024-08-06 | 2024-08-26 | IOU Designed & Installed | N/A | Yes | 20 | 7.3 | Unknown | Unknown | Unknown | Unknown | 7.3 | 3981 | 192.95 | 7.3 | 185.65 | Yes | N/A | N/A | 2024-08-06 | 2024-08-26 | 21 | 15 | 2024-08-26 | 2024-08-12 | Unknown | Unknown | 2024-08-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2024-08-26 | 15 | 11 | Unknown | 2024-08-26 | Unknown | Unknown | 2024-08-26 | 2024-09-11 | 1900-01-16 | 13 | 2024-09-11 | 2024-09-11 | 1 | 1 | 36 | 26 | 18 | 14 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-16 | -620 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-01 | 2024-11-13 | IOU Designed & Installed | N/A | No | N/A | 1749.06 | -34.61 | Unknown | Unknown | Unknown | 1783.67 | 3981 | 1809.84 | 1749.06 | 60.78 | Yes | N/A | N/A | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | 2024-11-01 | 1 | 1 | 2024-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2024-11-13 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2025-02-03 | 1900-03-23 | 59 | 2025-02-03 | 2025-02-03 | 1 | 1 | 14 | 10 | 85 | 61 | 99 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | 298.25 | 298.25 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | 70 | 51 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-05 | 2025-02-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 154.98 | Unknown | Unknown | Unknown | Unknown | 154.98 | Unknown | 506.24 | 154.98 | 351.26 | Yes | N/A | N/A | 2025-02-05 | 2025-01-31 | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | Unknown | Unknown | 2025-03-28 | 2025-03-28 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 3052 | 3052 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-11-27 | -110 | -79 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-06-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 925.64 | -25.22 | Unknown | Unknown | 94.84 | 856.02 | 17710.6 | 2397.38 | 925.64 | 1471.74 | Yes | N/A | N/A | 2023-06-02 | 2023-06-02 | 1 | 1 | 2023-06-02 | 2023-06-09 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2023-07-27 | 49 | 35 | Unknown | 2025-04-15 | Unknown | Unknown | Unknown | 2024-02-01 | Unknown | Unknown | 2024-02-01 | 2023-08-09 | Unknown | Unknown | 50 | 36 | 8 | 6 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-31 | 160 | 115 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 832 | -14.44 | Unknown | Unknown | Unknown | 846.44 | 9749 | 1515.14 | 832 | 683.14 | Yes | N/A | N/A | 2024-11-14 | 2024-11-06 | Unknown | Unknown | 2024-11-06 | 2024-11-26 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-01-22 | 58 | 42 | Unknown | 2025-01-30 | Unknown | Unknown | Unknown | 2025-02-10 | Unknown | Unknown | 2025-02-10 | 2025-02-07 | Unknown | Unknown | 58 | 42 | 21 | 15 | 79 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-12 | -641 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-18 | 2024-11-22 | IOU Designed & Installed | N/A | No | N/A | -1.11 | Unknown | Unknown | Unknown | Unknown | -1.11 | Unknown | 1626.51 | -1.11 | 1627.62 | Yes | N/A | N/A | 2024-10-07 | 2024-10-18 | 12 | 10 | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | Unknown | Unknown | Unknown | 2024-10-18 | 2024-11-04 | 18 | 12 | 2024-10-18 | 2024-11-22 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2024-12-10 | 1900-01-18 | 13 | 2024-12-10 | 2024-12-10 | 1 | 1 | 48 | 36 | 39 | 27 | 87 | 63 | Steps 2,3,5,6,7 | 17 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 100.05 | 100.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-28 | 478 | 342 | No | 2022-05-17 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-17 | Unknown | 2023-08-17 | IOU Designed & Installed | N/A | Yes | 505 | 972.98 | -42.37 | Unknown | Unknown | 7.43 | 1007.92 | 3981 | 830.08 | 972.98 | -142.9 | Yes | N/A | N/A | 2022-05-17 | 2023-10-04 | 506 | 362 | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-06-07 | 2023-08-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2023-12-19 | 1900-05-04 | 89 | 2023-12-19 | 2023-12-19 | 1 | 1 | 506 | 362 | 126 | 90 | 632 | 452 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-24 | 316 | 227 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1142.36 | -7.84 | Unknown | Unknown | -1573.26 | 438.74 | Unknown | 2059.8 | -1142.36 | 3202.16 | Yes | N/A | N/A | 2025-01-14 | 2024-12-10 | Unknown | Unknown | 2024-12-10 | 2025-02-11 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-11 | 2025-02-14 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-07 | Unknown | Unknown | 2025-03-07 | 2025-03-06 | Unknown | Unknown | 4 | 4 | 64 | 46 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | La Mesa | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-22 | -79 | -58 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-08 | 2023-09-11 | 2024-05-03 | IOU Designed & Installed | N/A | No | N/A | -1751.83 | 90.19 | Unknown | Unknown | -20274 | 18431.98 | Unknown | 20274.35 | -1751.83 | 22026.18 | Yes | N/A | N/A | 2023-09-08 | 2023-09-11 | 4 | 2 | 2023-09-11 | 2024-05-02 | 235 | 169 | Unknown | Unknown | Unknown | Unknown | 2023-12-29 | 2024-04-30 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-06-04 | 1900-02-01 | 23 | 2024-06-04 | 2024-06-04 | 1 | 1 | 4 | 2 | 300 | 216 | 304 | 218 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 192.75 | 192.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-04 | -460 | -330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-18 | 2024-06-18 | 2024-11-22 | IOU Designed & Installed | N/A | No | N/A | 1613.39 | 7.2 | Unknown | Unknown | 33.6 | 1572.59 | 3981 | 1449.23 | 1613.39 | -164.16 | Yes | N/A | N/A | 2024-06-18 | 2024-04-08 | Unknown | Unknown | 2024-04-08 | 2024-06-27 | 81 | 59 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-11-22 | 149 | 107 | Unknown | 2025-03-05 | Unknown | Unknown | 2024-11-22 | 2024-12-30 | 1900-02-07 | 27 | 2024-12-30 | 2024-12-30 | 1 | 1 | 149 | 107 | 121 | 87 | 270 | 194 | Steps 2,3,5,6,7 | 103 | 73 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-20 | -582 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -10.65 | -7.71 | Unknown | Unknown | Unknown | -2.94 | 3981 | 341 | -10.65 | 351.65 | Yes | N/A | N/A | 2023-03-01 | 2023-03-01 | 1 | 1 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 261 | 261 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-11-01 | 1270 | 909 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-02-06 | 2025-03-20 | IOU Designed & Installed | N/A | No | N/A | 42978.83 | 6934.25 | Unknown | Unknown | 71.62 | 35972.96 | 0 | 27475.34 | 42978.83 | -15503.49 | Yes | N/A | N/A | 2024-01-22 | 2023-10-03 | Unknown | Unknown | 2023-10-03 | 2025-03-04 | 519 | 371 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2025-03-07 | 34 | 26 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-20 | 2025-04-24 | 1900-02-04 | 26 | 2025-04-24 | 2025-04-24 | 1 | 1 | 0 | 0 | 590 | 424 | 590 | 424 | Steps 2,3,5,6,7 | 3 | 3 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-12 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-31 | 2023-04-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1190.57 | -10.32 | Unknown | Unknown | Unknown | 1200.89 | Unknown | 892.34 | 1190.57 | -298.23 | Yes | N/A | N/A | 2023-03-31 | 2023-04-03 | 4 | 2 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1 | 1 | 4 | 2 | 1 | 1 | 5 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 262171 | 262171 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-09-29 | -565 | -404 | No | 2022-12-01 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-01 | 2022-12-01 | Unknown | IOU Designed & Installed | N/A | Yes | 102 | -1.46 | -4.32 | Unknown | Unknown | Unknown | 2.86 | 3981 | 877.82 | -1.46 | 879.28 | Yes | N/A | N/A | 2022-12-01 | 2023-03-13 | 103 | 73 | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | Unknown | Unknown | 2023-05-17 | 2023-03-14 | Unknown | Unknown | 103 | 73 | 0 | 0 | 103 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-14 | -598 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-13 | 2025-01-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 82.37 | -17.19 | Unknown | Unknown | Unknown | 99.56 | 3981 | 1790.14 | 82.37 | 1707.77 | Yes | N/A | N/A | 2025-01-13 | 2025-01-06 | Unknown | Unknown | 2025-01-06 | 2025-01-21 | 16 | 12 | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | 2025-03-26 | 2025-03-26 | 1 | 1 | 0 | 0 | 17 | 13 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-11 | -636 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2024-12-03 | 2024-12-12 | IOU Designed & Installed | N/A | No | N/A | 28.1 | Unknown | Unknown | Unknown | Unknown | 28.1 | 3981 | 1773.98 | 28.1 | 1745.88 | Yes | N/A | N/A | 2024-12-03 | 2024-10-28 | Unknown | Unknown | 2024-10-28 | 2025-02-28 | 124 | 90 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-03 | 2024-12-12 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-01-13 | 1900-02-01 | 23 | 2025-01-13 | 2025-01-13 | 1 | 1 | 10 | 8 | 158 | 114 | 168 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-30 | 467 | 335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-02 | 2024-01-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 20.25 | Unknown | Unknown | Unknown | Unknown | 20.25 | 4539 | 390.8 | 20.25 | 370.55 | Yes | N/A | N/A | 2023-08-02 | 2023-11-03 | 94 | 68 | 2023-11-03 | 2024-03-01 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-01 | 2024-10-25 | 239 | 171 | Unknown | 2024-10-24 | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-11-08 | Unknown | Unknown | 333 | 239 | 120 | 86 | 453 | 325 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-28 | -259 | -186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | 2024-11-22 | IOU Designed & Installed | N/A | No | N/A | 5865.66 | 1567.91 | Unknown | 152.51 | 183.94 | 3961.3 | Unknown | 2518.9 | 5865.66 | -3346.76 | Yes | N/A | N/A | 2024-11-19 | 2024-11-19 | 1 | 1 | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2024-11-22 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-03-14 | 1900-04-22 | 81 | 2025-03-14 | 2025-03-14 | 1 | 1 | 5 | 5 | 114 | 82 | 119 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | POWAY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-21 | -386 | -277 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2210.72 | Unknown | Unknown | Unknown | 56.44 | 2154.28 | 3981 | 1130.51 | 2210.72 | -1080.21 | Yes | N/A | N/A | 2024-06-19 | 2024-08-09 | 52 | 38 | 2024-08-09 | 2024-08-13 | 5 | 3 | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-13 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | Unknown | Unknown | Unknown | 2025-04-30 | Unknown | Unknown | 2025-04-30 | 2025-04-30 | 1 | 1 | 52 | 38 | 6 | 4 | 58 | 42 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 27.15 | 27.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-31 | -93 | -68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-22 | 2024-07-26 | IOU Designed & Installed | N/A | No | N/A | 24.42 | Unknown | Unknown | Unknown | Unknown | 24.42 | 3981 | 848.51 | 24.42 | 824.09 | Yes | N/A | N/A | 2024-01-22 | 2023-12-28 | Unknown | Unknown | 2023-12-28 | 2024-01-22 | 26 | 18 | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-07-26 | 187 | 135 | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-07-30 | 1900-01-04 | 3 | 2024-07-30 | 2024-07-30 | 1 | 1 | 187 | 135 | 32 | 22 | 219 | 157 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 3200 | 3200 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-09-07 | -517 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-02-16 | 2024-04-03 | IOU Designed & Installed | N/A | No | N/A | 1120.19 | 378.69 | Unknown | Unknown | Unknown | 741.5 | 3885 | 1022.67 | 1120.19 | -97.52 | Yes | N/A | N/A | 2024-02-16 | 2023-09-20 | Unknown | Unknown | 2023-09-20 | 2024-02-16 | 150 | 108 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-04-03 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-04-08 | 1900-01-05 | 4 | 2024-04-08 | 2024-04-08 | 1 | 1 | 48 | 34 | 157 | 113 | 205 | 147 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-22 | 669 | 478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-25 | 2023-06-23 | 2025-05-05 | IOU Designed & Installed | N/A | No | N/A | 65351.79 | 3119.16 | Unknown | 129.83 | -163.63 | 62266.43 | 361351 | 54860.14 | 65351.79 | -10491.65 | Yes | N/A | N/A | 2022-10-25 | 2023-05-23 | 211 | 151 | 2023-05-23 | 2024-02-27 | 281 | 201 | 2023-11-22 | 2023-12-06 | 15 | 11 | 2023-12-06 | 2024-02-27 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2025-04-14 | 288 | 206 | 2025-05-05 | 2025-04-21 | Unknown | Unknown | 2025-04-21 | 2025-04-21 | 1 | 1 | 226 | 162 | 588 | 420 | 814 | 582 | Steps 2,3,5,6,7 | 97 | 69 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-31 | 491 | 352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-03 | 2023-09-02 | IOU Designed & Installed | N/A | No | N/A | -594.05 | 2217.11 | Unknown | 513.38 | -4278 | 953.46 | Unknown | 4277.83 | -594.05 | 4871.88 | Yes | N/A | N/A | 2023-08-03 | 2023-07-19 | Unknown | Unknown | 2023-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-02 | 2023-11-07 | 1900-03-07 | 47 | 2023-11-07 | 2023-10-04 | Unknown | Unknown | 0 | 0 | 67 | 47 | 67 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-13 | -611 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | 2023-08-24 | 2023-10-09 | IOU Designed & Installed | N/A | No | N/A | 366.12 | 244.9 | Unknown | Unknown | Unknown | 121.22 | Unknown | 480.37 | 366.12 | 114.25 | Yes | N/A | N/A | 2023-08-24 | 2023-06-16 | Unknown | Unknown | 2023-06-16 | 2023-08-24 | 70 | 50 | 2023-08-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | 2023-10-09 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2023-10-11 | 1900-01-02 | 3 | 2023-10-11 | 2023-10-11 | 1 | 1 | 47 | 33 | 74 | 54 | 121 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-09 | -249 | -178 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-23 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | 11828.11 | 3059.9 | Unknown | Unknown | Unknown | 8768.21 | 3981 | 1079.4 | 11828.11 | -10748.71 | Yes | N/A | N/A | 2024-05-23 | 2024-03-16 | Unknown | Unknown | 2024-03-16 | 2025-01-02 | 293 | 209 | 2025-01-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-04-07 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-06-05 | 1900-02-28 | 44 | 2025-06-05 | 2025-06-05 | 1 | 1 | 96 | 68 | 354 | 254 | 450 | 322 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | -405 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 689.11 | -10.07 | Unknown | Unknown | 8.83 | 690.35 | 3981 | 475.72 | 689.11 | -213.39 | Yes | N/A | N/A | 2023-08-03 | 2023-11-01 | 91 | 65 | 2023-11-01 | 2023-11-09 | 9 | 7 | 2023-11-09 | 2024-02-05 | 82 | 56 | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-03-01 | Unknown | Unknown | 173 | 121 | 9 | 7 | 182 | 128 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | -119 | -86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-25 | 2024-09-25 | 2024-09-26 | IOU Designed & Installed | N/A | No | N/A | 5185.86 | 1462.76 | Unknown | 453.24 | 160.51 | 3109.35 | Unknown | 2841.57 | 5185.86 | -2344.29 | Yes | N/A | N/A | 2024-09-25 | 2024-09-25 | 1 | 1 | 2024-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-09-26 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2025-03-14 | 1900-06-18 | 122 | 2025-03-14 | 2025-03-14 | 1 | 1 | 3 | 3 | 171 | 123 | 174 | 126 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-23 | -684 | -490 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-18 | 2025-02-19 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 38.75 | Unknown | Unknown | Unknown | Unknown | 38.75 | Unknown | 1676.05 | 38.75 | 1637.3 | Yes | N/A | N/A | 2025-02-18 | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-02-19 | 20 | 14 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-20 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-03-10 | 1900-01-18 | 13 | 2025-03-10 | 2025-03-10 | 1 | 1 | 2 | 2 | 40 | 28 | 42 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-04 | -161 | -116 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6219.47 | Unknown | Unknown | Unknown | 28.27 | 6191.2 | 3981 | 2542.24 | 6219.47 | -3677.23 | Yes | N/A | N/A | 2024-08-08 | 2024-09-26 | 50 | 36 | 2024-09-26 | 2024-10-04 | 9 | 7 | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | 2025-01-24 | Unknown | Unknown | 2025-01-24 | 2025-01-24 | 1 | 1 | 50 | 36 | 10 | 8 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | 605.2 | 605.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-23 | -76 | -55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-02-12 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | 11016.83 | Unknown | Unknown | Unknown | Unknown | 11016.83 | Unknown | 2147.74 | 11016.83 | -8869.09 | Yes | N/A | N/A | 2025-02-12 | 2025-02-11 | Unknown | Unknown | 2025-02-11 | 2025-04-17 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-08 | 1900-01-14 | 11 | 2025-05-08 | 2025-05-08 | 1 | 1 | 0 | 0 | 82 | 60 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-28 | -464 | -331 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-03-26 | 2024-05-30 | IOU Designed & Installed | N/A | No | N/A | 1520.32 | 457 | Unknown | 110.39 | Unknown | 952.93 | Unknown | 1026.98 | 1520.32 | -493.34 | Yes | N/A | N/A | 2024-03-26 | 2024-03-26 | 1 | 1 | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-05-30 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-06-21 | 1900-01-22 | 17 | 2024-06-21 | 2024-06-21 | 1 | 1 | 67 | 49 | 24 | 18 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | N/A | SAN DIEGO | N/A | 111.05 | 111.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | -555 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-04-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | -835.72 | Unknown | Unknown | Unknown | -902 | 66.28 | 7434 | 1757.77 | -835.72 | 2593.49 | Yes | N/A | N/A | 2024-02-16 | 2024-05-01 | 76 | 54 | 2024-05-01 | 2024-05-03 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-07-03 | 62 | 44 | Unknown | 2024-06-26 | Unknown | Unknown | Unknown | 2024-07-29 | Unknown | Unknown | 2024-07-29 | 2024-07-26 | Unknown | Unknown | 138 | 98 | 3 | 3 | 141 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-03 | -564 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-06 | 2024-06-13 | IOU Designed & Installed | N/A | No | N/A | 776.98 | 244.9 | Unknown | Unknown | Unknown | 532.08 | Unknown | 1072.59 | 776.98 | 295.61 | Yes | N/A | N/A | 2024-05-06 | 2024-05-06 | 1 | 1 | 2024-05-06 | 2024-05-06 | 1 | 1 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-06-13 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-06-18 | 1900-01-05 | 4 | 2024-06-18 | 2024-06-18 | 1 | 1 | 40 | 30 | 8 | 6 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 1095.05 | 1095.05 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-06-30 | 305 | 218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-22 | 2023-08-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 14.9 | -13.22 | Unknown | Unknown | Unknown | 28.12 | 3981 | 779.91 | 14.9 | 765.01 | Yes | N/A | N/A | 2023-08-22 | 2023-04-14 | Unknown | Unknown | 2023-04-14 | 2023-08-23 | 132 | 94 | 2023-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-04-30 | Unknown | Unknown | 0 | 0 | 132 | 94 | 132 | 94 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-07 | -432 | -309 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | 2024-01-29 | IOU Designed & Installed | N/A | No | N/A | 246.57 | -12.63 | Unknown | Unknown | 3.73 | 255.47 | 3981 | 769.25 | 246.57 | 522.68 | Yes | N/A | N/A | 2023-11-28 | 2023-07-18 | Unknown | Unknown | 2023-07-18 | 2023-12-11 | 147 | 105 | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2024-01-29 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-02-01 | 1900-01-03 | 4 | 2024-02-01 | 2024-01-31 | Unknown | Unknown | 50 | 36 | 151 | 109 | 201 | 145 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-18 | 186 | 135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-03 | 2024-09-26 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 67099.15 | 7937.56 | Unknown | Unknown | -28627.6 | 87789.19 | 128365 | Not available | 67099.15 | Unknown | Yes | N/A | N/A | 2024-01-03 | 2024-01-04 | 2 | 2 | 2024-01-04 | 2024-05-08 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2025-07-23 | 442 | 316 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-06-21 | Unknown | Unknown | 2024-06-21 | 2024-06-21 | 1 | 1 | 444 | 318 | 127 | 91 | 571 | 409 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 9 | 7 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-05-03 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | 1356.29 | Unknown | Unknown | Unknown | Unknown | 1356.29 | Unknown | 1284.97 | 1356.29 | -71.32 | Yes | N/A | N/A | 2023-04-12 | 2023-09-06 | 148 | 106 | 2023-09-06 | 2023-10-04 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2023-10-24 | 1900-01-13 | 10 | 2023-10-24 | 2023-10-24 | 1 | 1 | 148 | 106 | 44 | 32 | 192 | 138 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | Applicant Design | Residential | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-01-14 | 1385 | 990 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-26 | 2024-07-31 | 2024-10-14 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 6145.28 | -52.68 | Unknown | Unknown | Unknown | 6197.96 | 3981 | 1445.93 | 6145.28 | -4699.35 | Yes | N/A | N/A | 2023-10-26 | 2023-12-11 | 47 | 33 | 2023-12-11 | 2024-10-02 | 297 | 213 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-09-30 | 57 | 41 | 2024-10-02 | 2024-08-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2024-11-05 | 1900-01-22 | 17 | 2024-11-05 | 2024-10-30 | Unknown | Unknown | 47 | 33 | 377 | 271 | 424 | 304 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-21 | -617 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-13 | 2024-11-13 | 2025-01-22 | IOU Designed & Installed | N/A | No | N/A | 1068.97 | 255.83 | Unknown | Unknown | Unknown | 813.14 | 3981 | 1456.46 | 1068.97 | 387.49 | Yes | N/A | N/A | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | 2024-11-13 | 1 | 1 | 2024-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-13 | 2025-01-22 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-11 | 1900-01-20 | 15 | 2025-02-11 | 2025-02-11 | 1 | 1 | 72 | 52 | 23 | 17 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-30 | -651 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-15 | 2025-03-12 | IOU Designed & Installed | N/A | No | N/A | 537.26 | -10.2 | Unknown | Unknown | Unknown | 547.46 | Unknown | 2319.08 | 537.26 | 1781.82 | Yes | N/A | N/A | 2025-01-15 | 2025-01-06 | Unknown | Unknown | 2025-01-06 | 2025-01-15 | 10 | 8 | 2025-01-15 | Unknown | Unknown | Unknown | 2025-01-16 | 2025-01-22 | 7 | 5 | 2025-01-15 | 2025-03-12 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-03-19 | 1900-01-07 | 6 | 2025-03-19 | 2025-03-19 | 1 | 1 | 57 | 41 | 26 | 20 | 83 | 61 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-08 | -695 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2024-11-18 | 2024-11-18 | IOU Designed & Installed | N/A | No | N/A | 905.81 | -17.84 | Unknown | Unknown | Unknown | 923.65 | 3981 | 1470.79 | 905.81 | 564.98 | Yes | N/A | N/A | 2024-11-18 | 2024-11-13 | Unknown | Unknown | 2024-11-13 | 2024-11-18 | 6 | 4 | 2024-11-18 | Unknown | Unknown | Unknown | 2024-11-18 | 2024-12-20 | 33 | 25 | 2024-11-18 | 2024-11-18 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-12-13 | 1900-01-25 | 20 | 2024-12-13 | 2024-12-13 | 1 | 1 | 1 | 1 | 66 | 50 | 67 | 51 | Steps 2,3,5,6,7 | 32 | 24 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 65.05 | 65.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-10 | -546 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | 2025-05-28 | IOU Designed & Installed | N/A | No | N/A | 749.63 | Unknown | Unknown | Unknown | -1553.01 | 2302.64 | Unknown | 1448.2 | 749.63 | 698.57 | Yes | N/A | N/A | 2025-01-09 | 2024-12-20 | Unknown | Unknown | 2024-12-20 | 2025-01-21 | 33 | 23 | 2025-01-21 | 2025-02-03 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-05-28 | 115 | 83 | Unknown | 2025-05-27 | Unknown | Unknown | 2025-05-28 | 2025-06-12 | 1900-01-15 | 12 | 2025-06-12 | 2025-06-12 | 1 | 1 | 129 | 93 | 50 | 36 | 179 | 129 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-29 | 146 | 105 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -6.13 | -4.96 | Unknown | Unknown | Unknown | -1.17 | 3981 | 575.13 | -6.13 | 581.26 | Yes | N/A | N/A | 2023-02-09 | 2023-02-13 | 5 | 3 | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | Unknown | Unknown | 2024-04-23 | 2024-04-23 | 1 | 1 | 5 | 3 | 1 | 1 | 6 | 4 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | -523 | -374 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | 2024-08-06 | IOU Designed & Installed | N/A | No | N/A | 8.01 | Unknown | Unknown | Unknown | Unknown | 8.01 | 3961 | 192.95 | 8.01 | 184.94 | Yes | N/A | N/A | 2024-06-12 | 2024-06-19 | 8 | 6 | 2024-06-19 | 2024-08-06 | 49 | 35 | 2024-08-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-27 | 1900-01-21 | 16 | 2024-08-27 | 2024-08-27 | 1 | 1 | 9 | 7 | 72 | 52 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-27 | -566 | -405 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-11 | 2023-11-11 | 2024-01-03 | IOU Designed & Installed | N/A | No | N/A | 521.62 | 183.68 | Unknown | Unknown | Unknown | 337.94 | 3981 | 1175.87 | 521.62 | 654.25 | Yes | N/A | N/A | 2023-11-11 | 2023-11-11 | 1 | 0 | 2023-11-11 | 2023-11-11 | 1 | 0 | 2023-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-11 | 2024-01-03 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2024-01-08 | 1900-01-05 | 4 | 2024-01-08 | 2024-01-08 | 1 | 1 | 55 | 38 | 8 | 5 | 63 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 2 | 2 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-30 | -359 | -258 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-04-02 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 494.71 | Unknown | Unknown | Unknown | 29.3 | 465.41 | 3981 | 1845.02 | 494.71 | 1350.31 | Yes | N/A | N/A | 2024-03-07 | 2024-03-11 | 5 | 3 | 2024-03-11 | 2024-04-08 | 29 | 21 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | 2024-10-28 | 204 | 146 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-11-05 | 1900-01-08 | 7 | 2024-11-05 | 2024-11-05 | 1 | 1 | 209 | 149 | 39 | 29 | 248 | 178 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-23 | -524 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-19 | 2024-06-14 | IOU Designed & Installed | N/A | No | N/A | 1600.43 | 362.25 | Unknown | Unknown | Unknown | 1238.18 | Unknown | 1115.72 | 1600.43 | -484.71 | Yes | N/A | N/A | 2024-03-19 | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-19 | 5 | 3 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-06-14 | 88 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-06-17 | 1900-01-03 | 2 | 2024-06-17 | 2024-06-17 | 1 | 1 | 88 | 64 | 10 | 6 | 98 | 70 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -549 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-20 | 2024-07-03 | IOU Designed & Installed | N/A | No | N/A | 6.21 | Unknown | Unknown | Unknown | Unknown | 6.21 | Unknown | 1050.61 | 6.21 | 1044.4 | Yes | N/A | N/A | 2024-06-20 | 2024-06-20 | 1 | 1 | 2024-06-20 | 2024-06-20 | 1 | 1 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-03 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-08-21 | 1900-02-18 | 36 | 2024-08-21 | 2024-08-21 | 1 | 1 | 15 | 11 | 52 | 38 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 178 | 127 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-31 | 2022-10-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | -904.57 | 1493.78 | Unknown | 560.12 | -3589 | 630.53 | Unknown | 3589.35 | -904.57 | 4493.92 | Yes | N/A | N/A | 2022-10-31 | 2023-10-23 | 358 | 256 | 2023-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 358 | 256 | 1 | 1 | 359 | 257 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-28 | -617 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-11-19 | 2025-02-04 | IOU Designed & Installed | N/A | No | N/A | 292.43 | -5.5 | Unknown | Unknown | Unknown | 297.93 | Unknown | 499.14 | 292.43 | 206.71 | Yes | N/A | N/A | 2024-11-19 | 2024-11-19 | 1 | 1 | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | 2025-01-17 | 44 | 32 | 2024-12-09 | 2025-02-04 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-02-18 | 1900-01-14 | 11 | 2025-02-18 | 2025-02-18 | 1 | 1 | 59 | 43 | 60 | 44 | 119 | 87 | Steps 2,3,5,6,7 | 39 | 29 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 94.05 | 94.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-05 | -51 | -38 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-29 | 2023-02-24 | 2024-02-01 | IOU Designed & Installed | N/A | No | N/A | 87.6 | -9.3 | Unknown | Unknown | Unknown | 96.9 | 0 | 907.35 | 87.6 | 819.75 | Yes | N/A | N/A | 2022-12-29 | 2023-02-24 | 58 | 42 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-24 | 2024-02-01 | 343 | 245 | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2023-10-13 | Unknown | Unknown | 2023-10-13 | 2024-02-14 | 125 | 89 | 401 | 287 | 125 | 89 | 526 | 376 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | 183 | 183 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-15 | 306 | 219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-08-22 | 2025-02-27 | IOU Designed & Installed | N/A | No | N/A | 7936.05 | Unknown | Unknown | Unknown | Unknown | 7936.05 | 7962 | 1118.34 | 7936.05 | -6817.71 | Yes | N/A | N/A | 2024-04-02 | 2024-08-09 | 130 | 94 | 2024-08-09 | 2025-02-19 | 195 | 139 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-03-18 | 1900-01-19 | 14 | 2025-03-18 | 2025-03-17 | Unknown | Unknown | 130 | 94 | 215 | 153 | 345 | 247 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-01 | 135 | 98 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | -200.53 | Unknown | Unknown | Unknown | -1226.4 | 1025.87 | 3981 | 2392.28 | -200.53 | 2592.81 | Yes | N/A | N/A | 2024-07-18 | 2024-09-17 | 62 | 44 | 2024-09-17 | 2024-09-17 | 1 | 1 | 2024-09-17 | 2024-09-26 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2025-02-11 | 139 | 99 | Unknown | 2024-12-17 | Unknown | Unknown | 2025-02-11 | 2025-02-13 | 1900-01-02 | 3 | 2025-02-13 | 2025-02-13 | 1 | 1 | 211 | 151 | 5 | 5 | 216 | 156 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-20 | -255 | -184 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-08 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 1106.72 | -1.89 | Unknown | Unknown | 15.43 | 1093.18 | 3981 | 1499.17 | 1106.72 | 392.45 | Yes | N/A | N/A | 2024-03-08 | 2024-11-21 | 259 | 185 | 2024-11-21 | 2024-11-22 | 2 | 2 | 2024-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-02-20 | 91 | 65 | Unknown | 2025-02-19 | Unknown | Unknown | 2025-02-20 | 2025-03-10 | 1900-01-18 | 13 | 2025-03-10 | 2025-03-10 | 1 | 1 | 350 | 250 | 22 | 16 | 372 | 266 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -626 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | 2024-02-27 | IOU Designed & Installed | N/A | No | N/A | 969.16 | -25.92 | Unknown | Unknown | Unknown | 995.08 | Unknown | 1305.18 | 969.16 | 336.02 | Yes | N/A | N/A | 2024-02-08 | 2024-02-08 | 1 | 1 | 2024-02-08 | 2024-02-08 | 1 | 1 | 2024-02-08 | Unknown | Unknown | Unknown | 2024-02-09 | 2024-02-21 | 13 | 9 | 2024-02-08 | 2024-02-27 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-15 | 1900-01-17 | 14 | 2024-03-15 | 2024-03-15 | 1 | 1 | 21 | 15 | 33 | 25 | 54 | 40 | Steps 2,3,5,6,7 | 13 | 9 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 2.02 | 2.02 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-24 | -659 | -472 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-30 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | 1267.47 | 606.24 | Unknown | Unknown | -1103 | 1764.23 | Unknown | 1102.67 | 1267.47 | -164.8 | Yes | N/A | N/A | 2025-04-29 | 2025-04-30 | 2 | 2 | 2025-04-30 | 2025-04-30 | 1 | 1 | 2025-04-30 | 2025-05-08 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-05-16 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-06-03 | 1900-01-18 | 13 | 2025-06-03 | 2025-06-03 | 1 | 1 | 20 | 16 | 21 | 15 | 41 | 31 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-12 | -513 | -368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 8718.49 | 273.47 | Unknown | Unknown | -1120 | 9565.02 | 3981 | 1908.26 | 8718.49 | -6810.23 | Yes | N/A | N/A | 2024-06-06 | 2024-05-24 | Unknown | Unknown | 2024-05-24 | 2024-06-06 | 14 | 10 | 2024-06-06 | 2024-09-05 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2024-09-09 | 2024-09-25 | 17 | 13 | Unknown | 2024-09-10 | Unknown | Unknown | 2024-09-25 | 2024-10-17 | 1900-01-22 | 17 | 2024-10-17 | 2024-10-15 | Unknown | Unknown | 109 | 79 | 37 | 27 | 146 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-20 | -549 | -394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-04 | 2024-08-02 | IOU Designed & Installed | N/A | No | N/A | 1026.94 | Unknown | Unknown | Unknown | 21.72 | 1005.22 | 3981 | 1083.36 | 1026.94 | 56.42 | Yes | N/A | N/A | 2024-06-04 | 2024-05-29 | Unknown | Unknown | 2024-05-29 | 2024-06-06 | 9 | 7 | 2024-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-06 | 2024-08-02 | 58 | 42 | Unknown | 2024-08-01 | Unknown | Unknown | 2024-08-02 | 2024-09-17 | 1900-02-15 | 33 | 2024-09-17 | 2024-09-17 | 1 | 1 | 58 | 42 | 57 | 41 | 115 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-07 | -681 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-02-12 | 2025-02-12 | IOU Designed & Installed | N/A | No | N/A | 1642.24 | -45.91 | Unknown | Unknown | Unknown | 1688.15 | 3981 | 1921.6 | 1642.24 | 279.36 | Yes | N/A | N/A | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-02-12 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-03-28 | 1900-02-13 | 33 | 2025-03-28 | 2025-03-28 | 1 | 1 | 2 | 2 | 47 | 35 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-02 | 199 | 144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-18 | 2025-04-18 | 2025-06-18 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1482.64 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-18 | 2025-04-02 | Unknown | Unknown | 2025-04-02 | 2025-04-18 | 17 | 13 | 2025-04-18 | 2025-05-01 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-06-18 | 49 | 35 | Unknown | 2025-06-06 | Unknown | Unknown | 2025-06-18 | 2025-06-20 | 1900-01-02 | 3 | 2025-06-20 | 2025-06-19 | Unknown | Unknown | 63 | 45 | 20 | 16 | 83 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | 35.05 | 35.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-24 | -173 | -124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | 2023-07-19 | IOU Designed & Installed | N/A | No | N/A | 676.5 | -6.19 | Unknown | Unknown | 10.16 | 672.53 | 3981 | 534.56 | 676.5 | -141.94 | Yes | N/A | N/A | 2023-03-06 | 2023-03-14 | 9 | 7 | 2023-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-14 | 2023-07-19 | 128 | 92 | Unknown | 2023-07-17 | Unknown | Unknown | 2023-07-19 | 2023-08-04 | 1900-01-16 | 13 | 2023-08-04 | 2023-08-04 | 1 | 1 | 137 | 99 | 18 | 14 | 155 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-17 | 344 | 247 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-10-31 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | -9806.15 | 592.47 | Unknown | Unknown | -11097 | 698.38 | 0 | 10481.94 | -9806.15 | 20288.09 | Yes | N/A | N/A | 2023-09-19 | 2023-10-17 | 29 | 21 | 2023-10-17 | 2024-09-13 | 333 | 239 | 2023-10-31 | 2023-11-03 | 4 | 4 | 2024-09-02 | 2024-09-05 | 4 | 4 | 2024-09-13 | 2025-04-10 | 210 | 150 | 2025-04-29 | 2025-05-05 | 7 | 5 | 2025-06-10 | 2025-06-10 | 1899-12-31 | 1 | 2025-06-10 | 2025-05-27 | Unknown | Unknown | 243 | 175 | 345 | 249 | 588 | 424 | Steps 2,3,5,6,7 | 318 | 228 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-14 | -460 | -330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-23 | 2023-09-23 | 2023-12-05 | IOU Designed & Installed | N/A | No | N/A | 1319.56 | 448.44 | Unknown | 41.33 | Unknown | 829.79 | 3981 | 1045.64 | 1319.56 | -273.92 | Yes | N/A | N/A | 2023-09-23 | 2023-09-23 | 1 | 0 | 2023-09-23 | 2023-09-23 | 1 | 0 | 2023-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-23 | 2023-12-05 | 74 | 52 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2024-03-11 | 1900-04-07 | 70 | 2024-03-11 | 2024-03-11 | 1 | 1 | 75 | 52 | 100 | 71 | 175 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 5760 | 5760 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-09-24 | -477 | -342 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-13 | 2024-03-19 | 2024-05-07 | IOU Designed & Installed | N/A | No | N/A | 16253.69 | 394.24 | Unknown | Unknown | 3.72 | 15855.73 | Unknown | 12176.68 | 16253.69 | -4077.01 | Yes | N/A | N/A | 2024-03-13 | 2024-02-14 | Unknown | Unknown | 2024-02-14 | 2024-05-06 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-04-09 | 8 | 4 | 2024-05-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-06-04 | 1900-01-28 | 21 | 2024-06-04 | 2024-06-04 | 1 | 1 | 0 | 0 | 121 | 85 | 121 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 46 | 46 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-03 | -386 | -277 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-07-27 | IOU Designed & Installed | N/A | No | N/A | 246.83 | -7.78 | Unknown | Unknown | Unknown | 254.61 | 3981 | 902.42 | 246.83 | 655.59 | Yes | N/A | N/A | 2023-05-16 | 2023-05-16 | 1 | 1 | 2023-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | 2023-07-27 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | 2023-08-01 | 1900-01-05 | 4 | 2023-08-01 | 2023-12-14 | 136 | 98 | 73 | 53 | 142 | 102 | 215 | 155 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CAMPO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-26 | -7 | -6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-30 | 2024-08-02 | 2024-09-05 | IOU Designed & Installed | N/A | No | N/A | 135.53 | Unknown | Unknown | Unknown | 58.33 | 77.2 | 3241 | 1524.45 | 135.53 | 1388.92 | Yes | N/A | N/A | 2024-06-30 | 2024-08-02 | 34 | 25 | 2024-08-02 | 2024-08-02 | 1 | 1 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-09-05 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2025-03-19 | 1900-07-14 | 140 | 2025-03-19 | 2025-03-19 | 1 | 1 | 69 | 50 | 198 | 142 | 267 | 192 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-28 | -226 | -162 | No | 2023-02-13 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-04-10 | 2024-02-14 | IOU Designed & Installed | N/A | Yes | 338 | 584.77 | 189.35 | Unknown | Unknown | Unknown | 395.42 | 3981 | 628.54 | 584.77 | 43.77 | Yes | N/A | N/A | 2023-02-13 | 2024-01-17 | 339 | 243 | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-02-15 | 1900-01-01 | 2 | 2024-02-15 | 2024-02-15 | 1 | 1 | 339 | 243 | 3 | 3 | 342 | 246 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-25 | -218 | -157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-06 | 2023-07-06 | 2023-08-15 | IOU Designed & Installed | N/A | No | N/A | -17.18 | -12.47 | Unknown | Unknown | Unknown | -4.71 | Unknown | 480.44 | -17.18 | 497.62 | Yes | N/A | N/A | 2023-07-06 | 2023-05-08 | Unknown | Unknown | 2023-05-08 | 2023-07-06 | 60 | 44 | 2023-07-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | 2023-08-15 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2023-08-15 | 2023-09-20 | 1900-02-05 | 27 | 2023-09-20 | 2023-09-20 | 1 | 1 | 41 | 29 | 98 | 72 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-19 | -435 | -311 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -20.41 | -14.79 | Unknown | Unknown | Unknown | -5.62 | 3981 | 900.04 | -20.41 | 920.45 | Yes | N/A | N/A | 2023-02-08 | 2023-03-01 | 22 | 16 | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-11 | Unknown | Unknown | 2023-08-11 | 2023-08-11 | 1 | 1 | 22 | 16 | 1 | 1 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 131.1 | 131.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-26 | -68 | -49 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-21 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 508.2 | -8.41 | Unknown | Unknown | Unknown | 516.61 | 3981 | 1075.4 | 508.2 | 567.2 | Yes | N/A | N/A | 2023-12-13 | 2023-12-19 | 7 | 5 | 2023-12-19 | 2023-12-21 | 3 | 3 | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-04-15 | 117 | 83 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-04-22 | 1900-01-07 | 6 | 2024-04-22 | 2024-04-19 | Unknown | Unknown | 124 | 88 | 11 | 9 | 135 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-01 | 199 | 144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | 2024-02-07 | IOU Designed & Installed | N/A | No | N/A | 497.6 | -15.44 | Unknown | Unknown | 2.88 | 510.16 | 3885 | 656.7 | 497.6 | 159.1 | Yes | N/A | N/A | 2023-02-15 | 2023-02-15 | 1 | 1 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | 2024-02-07 | 358 | 256 | Unknown | 2024-01-25 | Unknown | Unknown | 2024-02-07 | 2024-02-16 | 1900-01-09 | 8 | 2024-02-16 | 2024-02-16 | 1 | 1 | 359 | 257 | 11 | 9 | 370 | 266 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 196 | 196 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-20 | -549 | -394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 0.77 | -10.44 | Unknown | Unknown | Unknown | 11.21 | 3981 | 855.36 | 0.77 | 854.59 | Yes | N/A | N/A | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-12-04 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-19 | 1900-01-15 | 12 | 2023-12-19 | 2023-12-19 | 1 | 1 | 86 | 62 | 18 | 14 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-28 | -44 | -33 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-12-11 | 2024-01-31 | IOU Designed & Installed | N/A | No | N/A | 13.1 | -15.87 | Unknown | Unknown | Unknown | 28.97 | 3981 | 903.17 | 13.1 | 890.07 | Yes | N/A | N/A | 2023-11-15 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2023-12-11 | 165 | 117 | 2023-12-11 | Unknown | Unknown | Unknown | 2023-12-11 | 2024-01-18 | 39 | 29 | 2023-12-11 | 2024-01-31 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-02-13 | 1900-01-13 | 10 | 2024-02-13 | 2024-02-13 | 1 | 1 | 52 | 38 | 219 | 157 | 271 | 195 | Steps 2,3,5,6,7 | 38 | 28 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | JULIAN | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-03 | -535 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-20 | 2023-07-20 | 2023-10-10 | IOU Designed & Installed | N/A | No | N/A | 1902.11 | 489.8 | Unknown | 471.68 | Unknown | 940.63 | 3981 | 806.99 | 1902.11 | -1095.12 | Yes | N/A | N/A | 2023-07-20 | 2023-07-20 | 1 | 1 | 2023-07-20 | 2023-07-20 | 1 | 1 | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-10-10 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-11-15 | 1900-02-05 | 27 | 2023-11-15 | 2023-11-15 | 1 | 1 | 84 | 60 | 39 | 29 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | POWAY | POWAY | 137 | 137 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-08-30 | 834 | 597 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 2023-01-31 | 2023-11-15 | IOU Designed & Installed | N/A | No | N/A | 22665.3 | 7123.5 | Unknown | Unknown | -7480.61 | 23022.41 | Unknown | 17885.24 | 22665.3 | -4780.06 | Yes | N/A | N/A | 2023-01-31 | 2023-01-31 | 1 | 1 | 2023-01-31 | Unknown | Unknown | Unknown | 2023-05-08 | 2023-11-02 | 6 | 6 | 2023-04-10 | 2023-10-31 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2023-12-12 | 1900-01-27 | 20 | 2023-12-12 | 2023-12-12 | 1 | 1 | 7 | 7 | 102 | 74 | 109 | 81 | Steps 2,3,5,6,7 | 206 | 148 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | -623 | -446 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | 2024-11-04 | IOU Designed & Installed | N/A | No | N/A | 4.48 | Unknown | Unknown | Unknown | Unknown | 4.48 | 3981 | 192.95 | 4.48 | 188.47 | Yes | N/A | N/A | 2024-08-29 | 2024-09-19 | 22 | 16 | 2024-09-19 | 2024-09-19 | 1 | 1 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-11-04 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-11-14 | 1900-01-10 | 9 | 2024-11-14 | 2024-11-14 | 1 | 1 | 69 | 49 | 13 | 11 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-09 | 220 | 157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | 2024-08-29 | IOU Designed & Installed | N/A | No | N/A | 15.33 | Unknown | Unknown | Unknown | Unknown | 15.33 | 3981 | 690.19 | 15.33 | 674.86 | Yes | N/A | N/A | 2023-03-23 | 2023-03-23 | 1 | 1 | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | 2024-08-29 | 526 | 376 | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-09-10 | 1900-01-12 | 9 | 2024-09-10 | 2024-09-16 | 7 | 5 | 527 | 377 | 20 | 14 | 547 | 391 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 28 | 28 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-10 | -436 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-08-15 | 2024-10-28 | IOU Designed & Installed | N/A | No | N/A | 560.92 | -10.56 | Unknown | Unknown | Unknown | 571.48 | 3981 | 1482.36 | 560.92 | 921.44 | Yes | N/A | N/A | 2024-07-24 | 2024-08-13 | 21 | 15 | 2024-08-13 | 2024-08-16 | 4 | 4 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-10-28 | 74 | 52 | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-10-31 | 1900-01-03 | 4 | 2024-10-31 | 2024-10-31 | 1 | 1 | 95 | 67 | 9 | 9 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-22 | -269 | -194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-04 | 2023-01-04 | 2023-03-27 | IOU Designed & Installed | N/A | No | N/A | 1050.42 | 346.45 | Unknown | 132.15 | Unknown | 571.82 | 3981 | 1576.02 | 1050.42 | 525.6 | Yes | N/A | N/A | 2023-01-04 | 2023-02-03 | 31 | 23 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | 2023-03-27 | 53 | 37 | Unknown | 2023-03-08 | Unknown | Unknown | 2023-03-27 | 2023-03-28 | 1900-01-01 | 2 | 2023-03-28 | 2023-03-28 | 1 | 1 | 84 | 60 | 3 | 3 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-06 | -646 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-03 | 2024-05-13 | IOU Designed & Installed | N/A | No | N/A | 688.35 | -20.83 | Unknown | Unknown | Unknown | 709.18 | Unknown | 906.89 | 688.35 | 218.54 | Yes | N/A | N/A | 2024-04-30 | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-05-03 | 40 | 30 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-05-13 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-05-29 | 1900-01-16 | 13 | 2024-05-29 | 2024-05-29 | 1 | 1 | 11 | 7 | 58 | 44 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 205.05 | 205.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-04 | 12 | 9 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-29 | 2023-09-29 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 5692.95 | 1204.85 | Unknown | 1461.41 | 75.78 | 2950.91 | 3981 | 1361.16 | 5692.95 | -4331.79 | Yes | N/A | N/A | 2023-09-29 | 2023-09-14 | Unknown | Unknown | 2023-09-14 | 2023-11-01 | 49 | 35 | 2023-11-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-01 | 2024-09-06 | 311 | 223 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-16 | 1900-01-10 | 7 | 2024-09-16 | 2024-09-16 | 1 | 1 | 311 | 223 | 61 | 43 | 372 | 266 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | 13 | 13 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-16 | 235 | 170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-06 | 2023-08-18 | IOU Designed & Installed | N/A | No | N/A | 5147.35 | -44.86 | Unknown | Unknown | Unknown | 5192.21 | 109171 | 1643.49 | 5147.35 | -3503.86 | Yes | N/A | N/A | 2023-06-06 | 2023-04-25 | Unknown | Unknown | 2023-04-25 | 2023-08-17 | 115 | 83 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2023-08-17 | 1 | 1 | Unknown | 2023-08-17 | Unknown | Unknown | 2023-08-18 | 2023-09-11 | 1900-01-24 | 17 | 2023-09-11 | 2023-09-08 | Unknown | Unknown | 1 | 1 | 140 | 100 | 141 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community,Tribal Community | BOULEVARD | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-28 | 471 | 338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-06 | 2025-05-07 | 2025-06-13 | IOU Designed & Installed | N/A | No | N/A | 5001.57 | 1347.77 | Unknown | Unknown | Unknown | 3653.8 | 3981 | 3323.8 | 5001.57 | -1677.77 | Yes | N/A | N/A | 2025-05-06 | 2025-05-06 | 1 | 1 | 2025-05-06 | 2025-06-03 | 29 | 21 | 2025-05-09 | 2025-05-09 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-10 | 8 | 6 | Unknown | 2025-06-11 | Unknown | Unknown | 2025-06-13 | 2025-06-13 | 1899-12-31 | 1 | 2025-06-13 | 2025-06-13 | 1 | 1 | 10 | 8 | 31 | 23 | 41 | 31 | Steps 2,3,5,6,7 | 25 | 17 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-04 | -527 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-04 | 2024-09-04 | 2025-03-21 | IOU Designed & Installed | N/A | No | N/A | 1516.07 | 296.12 | Unknown | Unknown | Unknown | 1219.95 | Unknown | 2276.2 | 1516.07 | 760.13 | Yes | N/A | N/A | 2024-09-04 | 2024-06-07 | Unknown | Unknown | 2024-06-07 | 2024-09-06 | 92 | 66 | 2024-09-06 | 2024-12-10 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2025-03-21 | 198 | 142 | Unknown | Unknown | Unknown | Unknown | 2025-03-21 | 2025-03-26 | 1900-01-05 | 4 | 2025-03-26 | 2025-03-26 | 1 | 1 | 294 | 210 | 99 | 71 | 393 | 281 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-31 | -647 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-18 | 2022-05-18 | 2025-02-25 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 175672.12 | 35294.95 | Unknown | Unknown | 10847.72 | 129529.45 | Unknown | 68163.01 | 175672.12 | -107509.11 | Yes | N/A | N/A | 2022-05-18 | 2024-08-08 | 814 | 582 | 2024-08-08 | 2024-10-10 | 64 | 46 | 2024-09-18 | 2025-03-04 | 16 | 12 | 2024-10-02 | 2024-10-25 | 10 | 7 | 2024-10-16 | Unknown | Unknown | Unknown | 2024-10-16 | 2025-02-14 | 122 | 88 | 2025-02-25 | 2025-03-24 | 1900-01-27 | 20 | 2025-03-24 | 2025-03-24 | 1 | 1 | 830 | 594 | 225 | 162 | 1055 | 756 | Steps 2,3,5,6,7 | 184 | 132 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 150 | 107 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 23.85 | Unknown | Unknown | Unknown | Unknown | 23.85 | 3981 | 885.23 | 23.85 | 861.38 | Yes | N/A | N/A | 2023-11-21 | 2023-11-21 | 1 | 1 | 2023-11-21 | 2023-11-21 | 1 | 1 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2024-07-09 | 232 | 166 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-07-30 | 1900-01-21 | 16 | 2024-07-30 | 2024-07-29 | Unknown | Unknown | 233 | 167 | 23 | 17 | 256 | 184 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-21 | -119 | -86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-03-11 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | -37.3 | -5.85 | Unknown | Unknown | -486 | 454.55 | Unknown | 485.71 | -37.3 | 523.01 | Yes | N/A | N/A | 2023-01-18 | 2023-03-11 | 53 | 38 | 2023-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | 2023-07-26 | 38 | 28 | Unknown | 2023-07-20 | Unknown | Unknown | 2023-07-26 | 2023-08-24 | 1900-01-29 | 22 | 2023-08-24 | 2023-08-24 | 1 | 1 | 91 | 66 | 31 | 23 | 122 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 114 | 114 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-28 | -256 | -185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-28 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | 1937.31 | 603.99 | Unknown | 204.18 | Unknown | 1129.14 | 3981 | 833.1 | 1937.31 | -1104.21 | Yes | N/A | N/A | 2023-08-07 | 2023-08-08 | 2 | 2 | 2023-08-08 | 2023-08-28 | 21 | 15 | 2023-08-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-28 | 2023-10-13 | 47 | 35 | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-10-16 | 1900-01-03 | 2 | 2023-10-16 | 2023-10-16 | 1 | 1 | 49 | 37 | 26 | 18 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 52.05 | 52.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-27 | -549 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-03 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1231.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-02-03 | 4 | 2 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-06-05 | 123 | 89 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-06-26 | 1900-01-21 | 16 | 2025-06-26 | 2025-06-26 | 1 | 1 | 123 | 89 | 27 | 19 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 85.05 | 85.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-08 | -502 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-22 | 2024-04-05 | IOU Designed & Installed | N/A | No | N/A | 316.55 | -6.32 | Unknown | Unknown | 10.38 | 312.49 | 3981 | 1109.09 | 316.55 | 792.54 | Yes | N/A | N/A | 2024-02-06 | 2023-12-14 | Unknown | Unknown | 2023-12-14 | 2024-03-02 | 80 | 57 | 2024-03-02 | 2024-05-07 | 67 | 47 | Unknown | Unknown | Unknown | Unknown | 2024-03-02 | 2024-04-05 | 35 | 25 | Unknown | 2024-06-07 | Unknown | Unknown | 2024-04-05 | 2024-07-24 | 1900-04-20 | 79 | 2024-07-24 | 2024-07-24 | 1 | 1 | 102 | 72 | 192 | 137 | 294 | 209 | Steps 2,3,5,6,7 | 63 | 45 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-19 | -52 | -37 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-22 | 2023-06-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | -0.86 | -2.55 | Unknown | Unknown | Unknown | 1.69 | Unknown | 264.34 | -0.86 | 265.2 | Yes | N/A | N/A | 2021-12-22 | 2023-06-15 | 541 | 387 | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2023-09-28 | 1 | 1 | 541 | 387 | 1 | 1 | 542 | 388 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-11 | -128 | -92 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2023-08-01 | 2023-12-26 | IOU Designed & Installed | N/A | No | N/A | 412.25 | 370.02 | Unknown | Unknown | -681 | 723.23 | Unknown | 681.47 | 412.25 | 269.22 | Yes | N/A | N/A | 2023-08-01 | 2023-08-03 | 3 | 3 | 2023-08-03 | 2023-08-22 | 20 | 14 | 2023-08-22 | 2023-10-27 | 67 | 49 | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2023-12-26 | 61 | 43 | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-26 | 2024-01-04 | 1900-01-09 | 8 | 2024-01-04 | 2024-01-04 | 1 | 1 | 131 | 95 | 31 | 23 | 162 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | -599 | -430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-07-08 | 2024-09-03 | IOU Designed & Installed | N/A | No | N/A | 47.49 | Unknown | Unknown | Unknown | Unknown | 47.49 | Unknown | 1395.28 | 47.49 | 1347.79 | Yes | N/A | N/A | 2024-06-25 | 2024-06-04 | Unknown | Unknown | 2024-06-04 | 2024-07-08 | 35 | 25 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-09-03 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-10-07 | 1900-02-03 | 25 | 2024-10-07 | 2024-10-07 | 1 | 1 | 58 | 42 | 71 | 51 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 813 | 582 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-27 | 2022-05-24 | Unknown | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 33689.47 | 2750.34 | Unknown | Unknown | 10725.14 | 20213.99 | 0 | 37257.67 | 33689.47 | 3568.2 | Yes | N/A | N/A | 2022-04-27 | 2023-05-01 | 370 | 264 | 2023-05-01 | 2024-08-14 | 472 | 338 | 2023-05-24 | 2024-04-08 | 250 | 176 | 2023-08-22 | 2024-01-15 | 147 | 105 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | Unknown | Unknown | Unknown | 2025-06-10 | Unknown | Unknown | 2025-06-10 | 2025-06-10 | 1 | 1 | 620 | 440 | 620 | 444 | 1240 | 884 | Steps 2,3,5,6,7 | 678 | 484 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 295.05 | 295.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-23 | -626 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-13 | 2025-02-13 | 2025-05-01 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1610.59 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-13 | 2025-01-24 | Unknown | Unknown | 2025-01-24 | 2025-02-13 | 21 | 15 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-05-01 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-07 | 1900-01-06 | 5 | 2025-05-07 | 2025-05-07 | 1 | 1 | 78 | 56 | 29 | 21 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-09 | -151 | -108 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-07-02 | 2025-02-04 | IOU Designed & Installed | N/A | No | N/A | 1251.14 | 1207.12 | Unknown | Unknown | -1379 | 1423.02 | 3981 | 2910.32 | 1251.14 | 1659.18 | Yes | N/A | N/A | 2024-06-25 | 2024-05-23 | Unknown | Unknown | 2024-05-23 | 2024-09-18 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-18 | 2025-05-14 | 239 | 171 | Unknown | 2025-01-06 | Unknown | Unknown | 2025-02-04 | 2025-06-23 | 1900-05-19 | 100 | 2025-06-23 | 2025-06-11 | Unknown | Unknown | 239 | 171 | 259 | 185 | 498 | 356 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-04 | -718 | -513 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-04 | 2024-10-04 | 2024-10-14 | IOU Designed & Installed | N/A | No | N/A | 1689 | 502.72 | Unknown | 71.69 | -131 | 1245.59 | Unknown | 2101.42 | 1689 | 412.42 | Yes | N/A | N/A | 2024-10-04 | 2024-10-04 | 1 | 1 | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2024-10-14 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2024-10-17 | 1900-01-03 | 4 | 2024-10-17 | 2024-10-16 | Unknown | Unknown | 2 | 2 | 4 | 4 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 54 | 54 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | -591 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-02 | 2024-08-19 | IOU Designed & Installed | N/A | No | N/A | 742.33 | 225.22 | Unknown | Unknown | Unknown | 517.11 | 3981 | 1523.8 | 742.33 | 781.47 | Yes | N/A | N/A | 2024-07-02 | 2024-07-02 | 1 | 1 | 2024-07-02 | 2024-07-02 | 1 | 1 | 2024-07-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-08-19 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-08-19 | 2024-08-27 | 1900-01-08 | 7 | 2024-08-27 | 2024-08-27 | 1 | 1 | 50 | 36 | 11 | 9 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | Carlsbad | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-18 | 98 | 71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-07 | 2022-06-07 | 2024-05-15 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 333700.86 | 42494.36 | Unknown | Unknown | 155849.37 | 135357.13 | Unknown | 94132.62 | 333700.86 | -239568.24 | Yes | N/A | N/A | 2022-06-07 | 2023-05-17 | 345 | 247 | 2023-05-17 | 2023-09-12 | 119 | 85 | 2023-06-23 | 2024-03-06 | 37 | 27 | 2023-09-07 | 2023-09-12 | 6 | 4 | 2023-09-19 | Unknown | Unknown | Unknown | 2023-09-19 | 2024-03-11 | 175 | 125 | 2024-05-15 | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-03-25 | 1 | 1 | 382 | 274 | 301 | 215 | 683 | 489 | Steps 2,3,5,6,7 | 262 | 186 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-25 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-12 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1597.33 | Unknown | Unknown | Yes | N/A | N/A | 2024-12-09 | 2024-11-27 | Unknown | Unknown | 2024-11-27 | 2024-12-12 | 16 | 12 | 2024-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2025-04-07 | 117 | 83 | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-04-23 | 1900-01-16 | 13 | 2025-04-23 | 2025-04-23 | 1 | 1 | 117 | 83 | 34 | 26 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-17 | -692 | -495 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-04 | 2025-03-04 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 72.99 | -21.7 | Unknown | Unknown | Unknown | 94.69 | 3981 | 1871.38 | 72.99 | 1798.39 | Yes | N/A | N/A | 2025-03-04 | 2025-03-04 | 1 | 1 | 2025-03-04 | 2025-03-04 | 1 | 1 | 2025-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-03-05 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-27 | 1900-01-22 | 17 | 2025-03-27 | 2025-03-27 | 1 | 1 | 3 | 3 | 25 | 19 | 28 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | -693 | -496 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-08 | 2023-06-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.27 | -9.74 | Unknown | Unknown | Unknown | 6.47 | 3981 | 1221.03 | -3.27 | 1224.3 | Yes | N/A | N/A | 2023-06-08 | 2023-06-08 | 1 | 1 | 2023-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2023-06-22 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-11 | -139 | -100 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-18 | 2024-01-18 | 2024-06-14 | IOU Designed & Installed | N/A | No | N/A | 33.13 | Unknown | Unknown | Unknown | Unknown | 33.13 | 3981 | 782.9 | 33.13 | 749.77 | Yes | N/A | N/A | 2024-01-18 | 2023-12-27 | Unknown | Unknown | 2023-12-27 | 2024-01-18 | 23 | 17 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-06-14 | 149 | 107 | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-07-25 | 1900-02-10 | 30 | 2024-07-25 | 2024-07-25 | 1 | 1 | 149 | 107 | 66 | 48 | 215 | 155 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 3.35 | 3.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-25 | -429 | -308 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | 899.22 | Unknown | Unknown | Unknown | 14.91 | 884.31 | 3961 | 1138.37 | 899.22 | 239.15 | Yes | N/A | N/A | 2024-01-09 | 2023-10-20 | Unknown | Unknown | 2023-10-20 | 2024-01-23 | 96 | 68 | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-07-16 | 176 | 126 | Unknown | 2024-07-09 | Unknown | Unknown | 2024-07-16 | 2024-07-24 | 1900-01-08 | 7 | 2024-07-24 | 2024-07-23 | Unknown | Unknown | 176 | 126 | 105 | 75 | 281 | 201 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 339.05 | 339.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -343 | -246 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-10-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 965.04 | -21.2 | Unknown | Unknown | 0.59 | 985.65 | 3981 | 739 | 965.04 | -226.04 | Yes | N/A | N/A | 2023-04-26 | 2023-10-24 | 182 | 130 | 2023-10-24 | 2023-11-08 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | 2023-10-27 | 10 | 8 | 2023-11-08 | 2024-02-22 | 107 | 77 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-02-22 | Unknown | Unknown | 289 | 207 | 26 | 20 | 315 | 227 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 61.05 | 61.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-24 | 145 | 104 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-02 | 2023-04-14 | 2023-12-19 | IOU Designed & Installed | N/A | No | N/A | 1465.42 | -38.88 | Unknown | Unknown | 9.2 | 1495.1 | 3981 | 845.46 | 1465.42 | -619.96 | Yes | N/A | N/A | 2022-11-02 | 2023-04-14 | 164 | 118 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | 2023-12-19 | 250 | 178 | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-03-04 | 1900-03-17 | 55 | 2024-03-04 | 2024-01-16 | Unknown | Unknown | 414 | 296 | 77 | 55 | 491 | 351 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-03 | -412 | -295 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-01 | 2023-07-05 | 2023-08-03 | IOU Designed & Installed | N/A | No | N/A | 35.87 | Unknown | Unknown | Unknown | Unknown | 35.87 | Unknown | 270.38 | 35.87 | 234.51 | Yes | N/A | N/A | 2023-07-01 | 2023-07-18 | 18 | 12 | 2023-07-18 | 2023-07-20 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-03 | 2023-08-18 | 1900-01-15 | 12 | 2023-08-18 | 2023-08-18 | 1 | 1 | 18 | 12 | 20 | 16 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-31 | -489 | -350 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-20 | 2022-02-20 | 2023-09-11 | IOU Designed & Installed | N/A | No | N/A | 634.15 | -11.78 | Unknown | Unknown | 10.22 | 635.71 | 3885 | 402.61 | 634.15 | -231.54 | Yes | N/A | N/A | 2022-02-20 | 2023-04-18 | 423 | 302 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-18 | 2023-09-11 | 147 | 105 | Unknown | 2023-08-08 | Unknown | Unknown | 2023-09-11 | 2023-09-11 | 1899-12-31 | 1 | 2023-09-11 | 2023-08-30 | Unknown | Unknown | 570 | 407 | 1 | 1 | 571 | 408 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-28 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | Unknown | 2024-09-11 | IOU Designed & Installed | N/A | No | N/A | 1340.72 | -26.4 | Unknown | Unknown | Unknown | 1367.12 | 3981 | 1499.83 | 1340.72 | 159.11 | Yes | N/A | N/A | 2024-05-29 | 2024-05-29 | 1 | 1 | 2024-05-29 | 2024-05-29 | 1 | 1 | 2024-05-29 | Unknown | Unknown | Unknown | 2024-05-29 | 2024-07-19 | 52 | 38 | 2024-05-29 | 2024-09-11 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2024-10-16 | 1900-02-04 | 26 | 2024-10-16 | 2024-10-16 | 1 | 1 | 107 | 77 | 90 | 66 | 197 | 143 | Steps 2,3,5,6,7 | 51 | 37 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-13 | -208 | -149 | No | 2025-01-28 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-28 | 2025-01-28 | 2025-06-18 | IOU Designed & Installed | N/A | Yes | 44 | 64.74 | Unknown | Unknown | Unknown | Unknown | 64.74 | Unknown | 1769.91 | 64.74 | 1705.17 | Yes | N/A | N/A | 2025-01-28 | 2025-03-11 | 43 | 31 | 2025-03-11 | 2025-03-13 | 3 | 3 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-06-18 | 142 | 102 | Unknown | Unknown | Unknown | Unknown | 2025-06-18 | 2025-06-19 | 1900-01-01 | 2 | 2025-06-19 | 2025-06-19 | 1 | 1 | 185 | 133 | 6 | 6 | 191 | 139 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-28 | -639 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-01-31 | 2024-02-15 | IOU Designed & Installed | N/A | No | N/A | 5.74 | -5.14 | Unknown | Unknown | Unknown | 10.88 | Unknown | 876.45 | 5.74 | 870.71 | Yes | N/A | N/A | 2024-01-31 | 2024-01-31 | 1 | 1 | 2024-01-31 | 2024-01-31 | 1 | 1 | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-02-15 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | 2024-02-28 | 1900-01-13 | 10 | 2024-02-28 | 2024-02-28 | 1 | 1 | 17 | 13 | 16 | 12 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -569 | -408 | No | 2024-10-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-03 | 2024-10-03 | Unknown | IOU Designed & Installed | N/A | Yes | 26 | 1799 | -35.45 | Unknown | Unknown | Unknown | 1834.45 | 7962 | 1707.36 | 1799 | -91.64 | Yes | N/A | N/A | 2024-10-03 | 2024-10-29 | 27 | 19 | 2024-10-29 | 2024-10-03 | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | Unknown | Unknown | 2024-12-09 | 2024-12-09 | 1 | 1 | 27 | 19 | 1 | 1 | 28 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-06-09 | 722 | 517 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1128.27 | -11.12 | Unknown | Unknown | 33.71 | 1105.68 | 2875 | 530.64 | 1128.27 | -597.63 | Yes | N/A | N/A | 2024-02-14 | 2024-03-01 | 17 | 13 | 2024-03-01 | 2024-03-04 | 4 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-05-23 | 81 | 59 | Unknown | 2024-05-13 | Unknown | Unknown | Unknown | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-05-31 | Unknown | Unknown | 98 | 72 | 4 | 2 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-07 | -518 | -371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-03-08 | 2024-05-21 | IOU Designed & Installed | N/A | No | N/A | 9.53 | -8.48 | Unknown | Unknown | Unknown | 18.01 | 3981 | 912.91 | 9.53 | 903.38 | Yes | N/A | N/A | 2024-02-23 | 2023-11-16 | Unknown | Unknown | 2023-11-16 | 2024-03-08 | 114 | 82 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-05-21 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2024-06-07 | 1900-01-17 | 14 | 2024-06-07 | 2024-06-07 | 1 | 1 | 75 | 53 | 133 | 97 | 208 | 150 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 102 | 102 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-09 | -316 | -227 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-08 | 2024-02-08 | 2024-05-15 | IOU Designed & Installed | N/A | No | N/A | 2571.89 | 619.73 | Unknown | 60.92 | 18.66 | 1872.58 | 3941 | 247.58 | 2571.89 | -2324.31 | Yes | N/A | N/A | 2024-02-08 | 2024-03-15 | 37 | 27 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | 2024-06-27 | 1900-02-12 | 32 | 2024-06-27 | 2024-06-27 | 1 | 1 | 37 | 27 | 45 | 33 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-14 | -267 | -192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | 2023-10-19 | IOU Designed & Installed | N/A | No | N/A | 1004.2 | -18.52 | Unknown | Unknown | Unknown | 1022.72 | 3981 | 812.39 | 1004.2 | -191.81 | Yes | N/A | N/A | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | 2023-10-19 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2023-11-21 | 1900-02-02 | 24 | 2023-11-21 | 2023-11-21 | 1 | 1 | 9 | 7 | 36 | 26 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-23 | -853 | -610 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-15 | 2023-03-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2830.59 | -39.33 | Unknown | Unknown | 17.45 | 2852.47 | Unknown | 774.68 | 2830.59 | -2055.91 | Yes | N/A | N/A | 2023-03-15 | 2023-03-15 | 1 | 1 | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | Unknown | Unknown | 2023-07-24 | 2023-07-24 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | -645 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-08 | 2024-10-08 | 2024-12-12 | IOU Designed & Installed | N/A | No | N/A | 643.14 | -12.92 | Unknown | Unknown | Unknown | 656.06 | 3981 | 1462.82 | 643.14 | 819.68 | Yes | N/A | N/A | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-08 | Unknown | Unknown | Unknown | 2024-10-09 | 2024-11-13 | 36 | 26 | 2024-10-08 | 2024-12-12 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-12-12 | 2024-12-17 | 1900-01-05 | 4 | 2024-12-17 | 2024-12-17 | 1 | 1 | 67 | 49 | 44 | 32 | 111 | 81 | Steps 2,3,5,6,7 | 36 | 26 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Residential | Underserved Community | WARNER SPRINGS | N/A | 45 | 45 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-30 | 918 | 656 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-05 | 2023-12-20 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | 95291.43 | 20859.8 | Unknown | Unknown | -22271.46 | 96703.09 | 3981 | 48682.31 | 95291.43 | -46609.12 | Yes | N/A | N/A | 2023-10-05 | 2023-10-09 | 5 | 3 | 2023-10-09 | 2025-04-02 | 542 | 388 | 2023-10-17 | 2025-02-13 | 456 | 324 | 2024-09-30 | 2024-10-07 | 8 | 6 | 2025-04-02 | 2025-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-07 | 1900-01-01 | 2 | 2025-05-07 | 2025-05-05 | Unknown | Unknown | 461 | 327 | 552 | 396 | 1013 | 723 | Steps 2,3,5,6,7 | 669 | 479 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | 43 | 31 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 367.03 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2025-02-13 | 3 | 3 | 2025-02-13 | 2025-03-03 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-03 | 18 | 12 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-24 | Unknown | Unknown | 2025-03-24 | 2025-03-24 | 1 | 1 | 3 | 3 | 38 | 26 | 41 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-06 | -372 | -267 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-17 | 2025-01-31 | IOU Designed & Installed | N/A | No | N/A | 15.61 | Unknown | Unknown | Unknown | Unknown | 15.61 | 3961 | 1005.27 | 15.61 | 989.66 | Yes | N/A | N/A | 2024-07-17 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-07-17 | 78 | 56 | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2025-01-31 | 199 | 143 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-03-03 | 1900-01-31 | 22 | 2025-03-03 | 2025-02-27 | Unknown | Unknown | 199 | 143 | 110 | 78 | 309 | 221 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-26 | -417 | -298 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-14 | 2024-02-14 | 2024-08-30 | IOU Designed & Installed | N/A | No | N/A | 521.83 | 303.12 | Unknown | Unknown | Unknown | 218.71 | 3885 | 192.51 | 521.83 | -329.32 | Yes | N/A | N/A | 2024-02-14 | 2024-07-10 | 148 | 106 | 2024-07-10 | 2024-07-10 | 1 | 1 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-08-30 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-09-04 | 1900-01-05 | 4 | 2024-09-04 | 2024-09-04 | 1 | 1 | 200 | 144 | 8 | 6 | 208 | 150 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 8.05 | 8.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-03 | -302 | -217 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | 2025-05-29 | IOU Designed & Installed | N/A | No | N/A | -97.49 | -0.63 | Unknown | Unknown | -792 | 695.14 | 3981 | 2240.78 | -97.49 | 2338.27 | Yes | N/A | N/A | 2024-11-11 | 2024-12-09 | 29 | 21 | 2024-12-09 | 2024-12-13 | 5 | 5 | 2024-12-13 | 2025-02-13 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-05-29 | 100 | 72 | Unknown | 2025-05-12 | Unknown | Unknown | 2025-05-29 | 2025-06-05 | 1900-01-07 | 6 | 2025-06-05 | 2025-06-05 | 1 | 1 | 192 | 138 | 14 | 12 | 206 | 150 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -507 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-03-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.18 | -3.56 | Unknown | Unknown | Unknown | 2.38 | Unknown | 209.1 | -1.18 | 210.28 | Yes | N/A | N/A | 2023-03-29 | 2023-03-29 | 1 | 1 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-12 | 2023-06-02 | 52 | 38 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2023-09-13 | 1 | 1 | 1 | 1 | 53 | 39 | 54 | 40 | Steps 2,3,5,6,7 | 63 | 45 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | -590 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | 2024-12-09 | IOU Designed & Installed | N/A | No | N/A | 510.65 | -10.2 | Unknown | Unknown | Unknown | 520.85 | 3981 | 1867.13 | 510.65 | 1356.48 | Yes | N/A | N/A | 2024-09-05 | 2024-08-14 | Unknown | Unknown | 2024-08-14 | 2024-09-05 | 23 | 17 | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2024-12-09 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2024-12-26 | 1900-01-17 | 14 | 2024-12-26 | 2024-12-26 | 1 | 1 | 96 | 68 | 42 | 32 | 138 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-30 | -210 | -151 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-02-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2.64 | -16.15 | Unknown | Unknown | Unknown | 18.79 | 0 | 958.73 | 2.64 | 956.09 | Yes | N/A | N/A | 2024-01-23 | 2023-11-21 | Unknown | Unknown | 2023-11-21 | 2024-02-16 | 88 | 64 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | Unknown | Unknown | 2025-04-03 | 2025-04-03 | 1 | 1 | 0 | 0 | 89 | 65 | 89 | 65 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 85.05 | 85.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-10 | -347 | -248 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-10-09 | 2024-06-27 | IOU Designed & Installed | N/A | No | N/A | 18.23 | -16.23 | Unknown | Unknown | Unknown | 34.46 | 3981 | 829.33 | 18.23 | 811.1 | Yes | N/A | N/A | 2023-09-13 | 2023-06-15 | Unknown | Unknown | 2023-06-15 | 2023-10-09 | 117 | 83 | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2024-06-27 | 263 | 189 | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-07-01 | 1900-01-04 | 3 | 2024-07-01 | 2024-06-28 | Unknown | Unknown | 263 | 189 | 122 | 86 | 385 | 275 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 52.66 | 52.66 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-04 | -57 | -42 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 483.5 | Unknown | Unknown | Unknown | -616.2 | 1099.7 | 0 | 651.64 | 483.5 | 168.14 | Yes | N/A | N/A | 2023-05-19 | 2023-05-19 | 1 | 1 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | 2024-07-05 | Unknown | Unknown | Unknown | 2024-08-08 | Unknown | Unknown | 2024-08-08 | 2024-08-08 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-17 | -620 | -444 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-26 | 2024-04-08 | 2024-04-25 | IOU Designed & Installed | N/A | No | N/A | 8.94 | -7.93 | Unknown | Unknown | Unknown | 16.87 | 3981 | 721.31 | 8.94 | 712.37 | Yes | N/A | N/A | 2024-03-26 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2024-04-08 | 76 | 54 | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | 2024-04-25 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-05-07 | 1900-01-12 | 9 | 2024-05-07 | 2024-05-07 | 1 | 1 | 18 | 14 | 90 | 64 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-20 | -219 | -156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-01-25 | 2024-03-04 | IOU Designed & Installed | N/A | No | N/A | 1505.34 | -35.24 | Unknown | Unknown | Unknown | 1540.58 | Unknown | 1030.96 | 1505.34 | -474.38 | Yes | N/A | N/A | 2024-01-02 | 2023-10-24 | Unknown | Unknown | 2023-10-24 | 2024-01-25 | 94 | 68 | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | 2024-03-04 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-03-15 | 1900-01-11 | 10 | 2024-03-15 | 2024-03-15 | 1 | 1 | 40 | 28 | 107 | 79 | 147 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-29 | -587 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-29 | 2024-08-09 | IOU Designed & Installed | N/A | No | N/A | 1284.28 | 695.4 | Unknown | 89.11 | Unknown | 499.77 | Unknown | 192.83 | 1284.28 | -1091.45 | Yes | N/A | N/A | 2024-04-29 | 2024-04-01 | Unknown | Unknown | 2024-04-01 | 2024-06-10 | 71 | 51 | 2024-06-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-10 | 2024-08-09 | 61 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2024-08-19 | 1900-01-10 | 7 | 2024-08-19 | 2024-08-19 | 1 | 1 | 61 | 45 | 83 | 59 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-28 | -22 | -17 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-14 | 2023-06-14 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | 6352.56 | 4711.75 | Unknown | 1755.44 | -2338 | 2223.37 | Unknown | 2562.79 | 6352.56 | -3789.77 | Yes | N/A | N/A | 2023-06-14 | 2023-06-14 | 1 | 1 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-03-25 | 1899-12-31 | 1 | 2024-03-25 | 2023-11-06 | Unknown | Unknown | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-16 | -639 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-13 | 2025-01-06 | IOU Designed & Installed | N/A | No | N/A | 27.79 | Unknown | Unknown | Unknown | Unknown | 27.79 | 3981 | 1874.23 | 27.79 | 1846.44 | Yes | N/A | N/A | 2024-12-13 | 2024-10-25 | Unknown | Unknown | 2024-10-25 | 2024-12-13 | 50 | 36 | 2024-12-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-01-06 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-01-15 | 1900-01-09 | 8 | 2025-01-15 | 2025-01-15 | 1 | 1 | 25 | 17 | 61 | 45 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | 35 | 35 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-09 | 91 | 66 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-23 | 2024-03-18 | IOU Designed & Installed | N/A | No | N/A | 4923.31 | 78.56 | Unknown | Unknown | Unknown | 4844.75 | 0 | 89 | 4923.31 | -4834.31 | Yes | N/A | N/A | 2023-05-10 | 2023-04-19 | Unknown | Unknown | 2023-04-19 | 2023-10-24 | 189 | 135 | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2023-11-01 | 9 | 7 | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | 2024-04-09 | 1900-01-22 | 17 | 2024-04-09 | 2024-04-09 | 1 | 1 | 0 | 0 | 222 | 160 | 222 | 160 | Steps 2,3,5,6,7 | 8 | 6 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 72.05 | 72.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-24 | -512 | -367 | No | 2024-08-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-11-04 | IOU Designed & Installed | N/A | Yes | 8 | 685.3 | -13.2 | Unknown | Unknown | Unknown | 698.5 | 3981 | 2040.37 | 685.3 | 1355.07 | Yes | N/A | N/A | 2024-08-27 | 2024-09-04 | 9 | 7 | 2024-09-04 | 2024-08-27 | Unknown | Unknown | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-11-04 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-11-20 | 1900-01-16 | 13 | 2024-11-20 | 2025-02-27 | 100 | 72 | 79 | 57 | 117 | 85 | 196 | 142 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 25.35 | 25.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-07 | -452 | -323 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-26 | 2024-03-27 | IOU Designed & Installed | N/A | No | N/A | 1248.54 | 371.51 | Unknown | 109.72 | Unknown | 767.31 | 3981 | 1018.42 | 1248.54 | -230.12 | Yes | N/A | N/A | 2024-01-03 | 2024-01-19 | 17 | 13 | 2024-01-19 | 2024-01-26 | 8 | 6 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-03-27 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | 2024-04-02 | 1900-01-06 | 5 | 2024-04-02 | 2024-06-12 | 72 | 52 | 79 | 57 | 87 | 63 | 166 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 135.05 | 135.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-07 | -678 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-18 | 2024-04-18 | 2024-07-17 | IOU Designed & Installed | N/A | No | N/A | 1153.69 | Unknown | Unknown | Unknown | 8.48 | 1145.21 | 3981 | 1327.67 | 1153.69 | 173.98 | Yes | N/A | N/A | 2024-04-18 | 2024-01-22 | Unknown | Unknown | 2024-01-22 | 2024-05-01 | 101 | 73 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-07-17 | 78 | 56 | Unknown | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-07-30 | 1900-01-13 | 10 | 2024-07-30 | 2024-07-29 | Unknown | Unknown | 78 | 56 | 115 | 83 | 193 | 139 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | POWAY | POWAY | 64512 | 64512 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-08-01 | 159 | 114 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-31 | 2024-12-31 | IOU Designed & Installed | N/A | No | N/A | 559.57 | 124.03 | Unknown | Unknown | Unknown | 435.54 | Unknown | 449.58 | 559.57 | -109.99 | Yes | N/A | N/A | 2024-07-29 | 2024-07-30 | 2 | 2 | 2024-07-30 | 2024-09-11 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-11-15 | 43 | 33 | 2024-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | 2025-01-07 | 1900-01-07 | 6 | 2025-01-07 | 2025-01-07 | 1 | 1 | 2 | 2 | 96 | 72 | 98 | 74 | Steps 2,3,5,6,7 | 65 | 47 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-15 | -265 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-30 | 2023-05-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 13.48 | -14.37 | Unknown | Unknown | 20.82 | 7.03 | 7962 | 611.1 | 13.48 | 597.62 | Yes | N/A | N/A | 2023-05-30 | 2023-05-16 | Unknown | Unknown | 2023-05-16 | 2023-08-21 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | 2023-06-21 | 9 | 7 | 2023-08-21 | 2023-08-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2023-08-24 | Unknown | Unknown | 0 | 0 | 107 | 77 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-20 | -578 | -414 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-21 | 2024-04-01 | 2024-04-04 | IOU Designed & Installed | N/A | No | N/A | -6.73 | -5.47 | Unknown | Unknown | Unknown | -1.26 | Unknown | 1075.02 | -6.73 | 1081.75 | Yes | N/A | N/A | 2024-03-21 | 2024-04-01 | 12 | 8 | 2024-04-01 | 2024-04-01 | 1 | 1 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-04-04 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-05-21 | 1900-02-16 | 34 | 2024-05-21 | 2024-05-21 | 1 | 1 | 16 | 12 | 50 | 36 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | LEMON GROVE | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-24 | -213 | -153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-10-25 | 2023-11-22 | IOU Designed & Installed | N/A | No | N/A | 5.07 | -10.36 | Unknown | Unknown | Unknown | 15.43 | Unknown | 1957.57 | 5.07 | 1952.5 | Yes | N/A | N/A | 2023-10-23 | 2023-09-08 | Unknown | Unknown | 2023-09-08 | 2023-10-25 | 48 | 34 | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | 2023-11-22 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2024-01-12 | 1900-02-20 | 38 | 2024-01-12 | 2024-01-24 | 13 | 9 | 29 | 21 | 113 | 81 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | -701 | -502 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-26 | 2024-08-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 136.96 | Unknown | Unknown | Unknown | Unknown | 136.96 | 3981 | 1504.62 | 136.96 | 1367.66 | Yes | N/A | N/A | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | 2024-08-26 | 1 | 1 | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | Unknown | Unknown | 2024-09-11 | 2024-09-11 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2016-12-31 | 2853 | 2038 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2016-04-20 | 2016-04-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | -523.24 | Unknown | Unknown | Unknown | -1467 | 943.76 | Unknown | 1224.72 | -523.24 | 1747.96 | Yes | N/A | N/A | 2016-04-20 | 2024-06-03 | 2967 | 2119 | 2024-06-03 | 2016-10-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-09-16 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2024-10-23 | Unknown | Unknown | 2967 | 2119 | 1 | 1 | 2968 | 2120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-12 | 268 | 193 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-01-12 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | 2896.66 | 537.53 | Unknown | 125.96 | 96.63 | 2136.54 | 3981 | 1557.23 | 2896.66 | -1339.43 | Yes | N/A | N/A | 2024-01-12 | 2024-03-27 | 76 | 54 | 2024-03-27 | 2024-04-05 | 10 | 8 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2025-03-05 | 323 | 231 | Unknown | 2025-02-07 | Unknown | Unknown | 2025-03-05 | 2025-03-10 | 1900-01-05 | 4 | 2025-03-10 | 2025-03-07 | Unknown | Unknown | 399 | 285 | 16 | 12 | 415 | 297 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SD 1190-A2 CMR PA6 WO2 | N/A | 222214 | 222214 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-03-20 | 815 | 584 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-11 | 2024-09-13 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 34187 | Not available | Unknown | Unknown | Yes | N/A | N/A | 2024-09-11 | 2024-09-12 | 2 | 2 | 2024-09-12 | 2024-09-16 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2025-06-04 | 262 | 188 | Unknown | 2025-06-24 | Unknown | Unknown | 2025-06-11 | 2025-06-12 | 1900-01-01 | 2 | 2025-06-12 | 2025-06-12 | 1 | 1 | 264 | 190 | 8 | 6 | 272 | 196 | Steps 2,3,5,6,7 | 13 | 9 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 186.05 | 186.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-26 | -647 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-05-01 | 2025-05-15 | IOU Designed & Installed | N/A | No | N/A | 836.02 | -16.8 | Unknown | Unknown | Unknown | 852.82 | Unknown | 1482.81 | 836.02 | 646.79 | Yes | N/A | N/A | 2025-04-28 | 2025-04-22 | Unknown | Unknown | 2025-04-22 | 2025-05-01 | 10 | 8 | 2025-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-01 | 2025-05-15 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-05-20 | 1900-01-05 | 4 | 2025-05-20 | 2025-05-20 | 1 | 1 | 15 | 11 | 17 | 13 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-10 | 146 | 105 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-06-05 | 2024-10-01 | IOU Designed & Installed | N/A | No | N/A | 1163.68 | Unknown | Unknown | Unknown | 15.07 | 1148.61 | 1192.8 | 694.19 | 1163.68 | -469.49 | Yes | N/A | N/A | 2024-05-31 | 2024-06-21 | 22 | 16 | 2024-06-21 | 2024-06-24 | 4 | 2 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-10-01 | 100 | 72 | Unknown | 2024-09-20 | Unknown | Unknown | 2024-10-01 | 2024-10-04 | 1900-01-03 | 4 | 2024-10-04 | 2024-10-03 | Unknown | Unknown | 122 | 88 | 8 | 6 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Imperial Beach | IMPERIAL BEACH | 92 | 92 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 754 | 539 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-22 | 2025-02-05 | IOU Designed & Installed | N/A | No | N/A | -5276.74 | 803.15 | Unknown | Unknown | -24493.03 | 18413.14 | 11328.81 | 35828.15 | -5276.74 | 41104.89 | Yes | N/A | N/A | 2024-10-16 | 2024-10-16 | 1 | 1 | 2024-10-16 | 2025-01-09 | 86 | 62 | 2024-11-15 | 2024-11-18 | 4 | 2 | 2024-12-04 | 2025-01-10 | 11 | 9 | 2025-01-09 | Unknown | Unknown | Unknown | 2025-02-24 | 2025-03-04 | 9 | 7 | 2025-02-05 | 2025-04-24 | 1900-03-19 | 57 | 2025-04-24 | 2025-04-24 | 1 | 1 | 5 | 3 | 186 | 136 | 191 | 139 | Steps 2,3,5,6,7 | 83 | 59 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 99.05 | 99.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-18 | -645 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-07 | 2024-08-16 | 2024-08-20 | IOU Designed & Installed | N/A | No | N/A | 8.02 | Unknown | Unknown | Unknown | Unknown | 8.02 | 3981 | 1312.73 | 8.02 | 1304.71 | Yes | N/A | N/A | 2024-08-07 | 2024-07-10 | Unknown | Unknown | 2024-07-10 | 2024-08-16 | 38 | 28 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-08-20 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-08-20 | 2024-09-11 | 1900-01-22 | 17 | 2024-09-11 | 2024-09-11 | 1 | 1 | 5 | 3 | 62 | 46 | 67 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 64 | 64 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | -562 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | 2024-10-16 | IOU Designed & Installed | N/A | No | N/A | 2119.64 | 781.75 | Unknown | 49.28 | Unknown | 1288.61 | 3981 | 1445.88 | 2119.64 | -673.76 | Yes | N/A | N/A | 2024-08-14 | 2024-05-06 | Unknown | Unknown | 2024-05-06 | 2024-08-14 | 101 | 73 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-10-16 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-10-16 | 2024-10-21 | 1900-01-05 | 4 | 2024-10-21 | 2024-10-21 | 1 | 1 | 64 | 46 | 108 | 78 | 172 | 124 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -633 | -453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-05-07 | 2024-05-08 | IOU Designed & Installed | N/A | No | N/A | 1176.31 | 367.35 | Unknown | Unknown | Unknown | 808.96 | 3981 | 738.82 | 1176.31 | -437.49 | Yes | N/A | N/A | 2024-04-15 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-05-07 | 69 | 49 | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-05-08 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2024-05-29 | 1900-01-21 | 16 | 2024-05-29 | 2024-05-29 | 1 | 1 | 2 | 2 | 92 | 66 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | -207 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-05 | 2024-04-18 | IOU Designed & Installed | N/A | No | N/A | -13.49 | -10.95 | Unknown | Unknown | Unknown | -2.54 | 3241 | 896.62 | -13.49 | 910.11 | Yes | N/A | N/A | 2024-01-31 | 2024-01-31 | 1 | 1 | 2024-01-31 | 2024-02-05 | 6 | 4 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-04-18 | 74 | 54 | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-05-06 | 1900-01-18 | 13 | 2024-05-06 | 2024-05-06 | 1 | 1 | 75 | 55 | 26 | 18 | 101 | 73 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 435 | 435 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-22 | -512 | -365 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-26 | 2024-08-14 | IOU Designed & Installed | N/A | No | N/A | 1411.01 | 395.79 | Unknown | 27.69 | Unknown | 987.53 | 3981 | 755.54 | 1411.01 | -655.47 | Yes | N/A | N/A | 2024-04-03 | 2024-03-08 | Unknown | Unknown | 2024-03-08 | 2024-04-26 | 50 | 36 | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2024-08-14 | 111 | 79 | Unknown | 2024-08-09 | Unknown | Unknown | 2024-08-14 | 2024-09-28 | 1900-02-14 | 33 | 2024-09-28 | 2024-09-28 | 1 | 0 | 111 | 79 | 97 | 69 | 208 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 200 | 200 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-02 | 416 | 298 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 597.17 | -51.11 | Unknown | Unknown | Unknown | 648.28 | 15924 | 1085.39 | 597.17 | 488.22 | Yes | N/A | N/A | 2023-12-19 | 2024-01-18 | 31 | 23 | 2024-01-18 | 2024-02-15 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-01-29 | 12 | 8 | 2024-02-15 | 2024-05-16 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | Unknown | Unknown | 2024-05-23 | 2024-05-22 | Unknown | Unknown | 123 | 89 | 41 | 29 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-27 | 112 | 81 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-05-19 | 2023-11-15 | IOU Designed & Installed | N/A | No | N/A | 1827.63 | 657.79 | Unknown | 122.52 | 8.31 | 1039.01 | 3981 | 401.89 | 1827.63 | -1425.74 | Yes | N/A | N/A | 2023-03-22 | 2023-05-22 | 62 | 44 | 2023-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | 2023-11-15 | 178 | 128 | Unknown | 2023-11-14 | Unknown | Unknown | 2023-11-15 | 2023-11-16 | 1900-01-01 | 2 | 2023-11-16 | 2023-11-16 | 1 | 1 | 240 | 172 | 3 | 3 | 243 | 175 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 101.05 | 101.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | -163 | -118 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-15 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 15519.57 | -149.53 | Unknown | Unknown | -460.28 | 16129.38 | 3981 | 2159.22 | 15519.57 | -13360.35 | Yes | N/A | N/A | 2023-09-14 | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-12-06 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-07-19 | 2 | 2 | 2023-12-06 | 2024-10-03 | 303 | 217 | Unknown | 2024-08-05 | Unknown | Unknown | 2024-10-15 | 2024-11-04 | 1900-01-20 | 15 | 2024-11-04 | 2024-10-29 | Unknown | Unknown | 303 | 217 | 123 | 89 | 426 | 306 | Steps 2,3,5,6,7 | 226 | 162 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -635 | -455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-14 | 2024-11-14 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 8.93 | Unknown | Unknown | Unknown | Unknown | 8.93 | 3241 | 1197.21 | 8.93 | 1188.28 | Yes | N/A | N/A | 2024-11-14 | 2024-11-14 | 1 | 1 | 2024-11-14 | 2024-11-14 | 1 | 1 | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-11-15 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-03 | 1900-01-18 | 13 | 2024-12-03 | 2024-12-02 | Unknown | Unknown | 3 | 3 | 20 | 14 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | 41.05 | 41.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | -397 | -284 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-13 | 2025-02-21 | IOU Designed & Installed | N/A | No | N/A | 1956.03 | -8.77 | Unknown | Unknown | 47.18 | 1917.62 | 3981 | 1780.43 | 1956.03 | -175.6 | Yes | N/A | N/A | 2024-06-06 | 2024-06-20 | 15 | 11 | 2024-06-20 | 2024-06-27 | 8 | 6 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2025-02-21 | 240 | 172 | Unknown | 2025-01-08 | Unknown | Unknown | 2025-02-21 | 2025-03-04 | 1900-01-11 | 8 | 2025-03-04 | 2025-03-04 | 1 | 1 | 255 | 183 | 21 | 15 | 276 | 198 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-21 | -593 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-05 | 2024-12-05 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 1335.7 | -55.34 | Unknown | Unknown | 12.32 | 1378.72 | 3981 | 1191.13 | 1335.7 | -144.57 | Yes | N/A | N/A | 2024-12-05 | 2025-01-15 | 42 | 30 | 2025-01-15 | 2025-02-07 | 24 | 18 | 2025-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-03-06 | 28 | 20 | Unknown | 2025-03-05 | Unknown | Unknown | 2025-03-06 | 2025-04-07 | 1900-02-01 | 23 | 2025-04-07 | 2025-04-07 | 1 | 1 | 70 | 50 | 58 | 42 | 128 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 12.05 | 12.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | -420 | -301 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-27 | 2025-06-26 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1127.35 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-24 | 2024-09-12 | Unknown | Unknown | 2024-09-12 | 2024-09-27 | 16 | 12 | 2024-09-27 | Unknown | Unknown | Unknown | 2024-09-30 | 2024-10-15 | 16 | 12 | 2024-09-27 | 2025-06-26 | 273 | 195 | Unknown | Unknown | Unknown | Unknown | 2025-06-26 | 2025-06-27 | 1900-01-01 | 2 | 2025-06-27 | 2025-06-27 | 1 | 1 | 273 | 195 | 35 | 27 | 308 | 222 | Steps 2,3,5,6,7 | 18 | 12 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-25 | -586 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-06-24 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 7.46 | Unknown | Unknown | Unknown | Unknown | 7.46 | 3981 | 1533.09 | 7.46 | 1525.63 | Yes | N/A | N/A | 2024-05-02 | 2024-06-24 | 54 | 38 | 2024-06-24 | 2024-06-24 | 1 | 1 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-07-29 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-16 | 1900-01-18 | 15 | 2024-08-16 | 2024-08-16 | 1 | 1 | 90 | 64 | 21 | 17 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-15 | -699 | -500 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-03 | 2025-03-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 125.34 | Unknown | Unknown | Unknown | Unknown | 125.34 | 3981 | 1716.03 | 125.34 | 1590.69 | Yes | N/A | N/A | 2025-03-03 | 2025-03-03 | 1 | 1 | 2025-03-03 | 2025-03-03 | 1 | 1 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | 2025-03-18 | 2025-03-18 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 142.05 | 142.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-13 | -501 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | 2024-02-05 | IOU Designed & Installed | N/A | No | N/A | 734.24 | -10.92 | Unknown | Unknown | 10.89 | 734.27 | 3961 | 1044.32 | 734.24 | 310.08 | Yes | N/A | N/A | 2023-10-13 | 2023-07-25 | Unknown | Unknown | 2023-07-25 | 2023-11-21 | 120 | 86 | 2023-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-21 | 2024-02-05 | 77 | 55 | Unknown | 2024-01-05 | Unknown | Unknown | 2024-02-05 | 2024-02-28 | 1900-01-23 | 18 | 2024-02-28 | 2024-02-28 | 1 | 1 | 77 | 55 | 145 | 105 | 222 | 160 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 31.05 | 31.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-21 | 16 | 11 | No | 2023-01-12 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-12 | 2023-01-12 | 2024-09-17 | IOU Designed & Installed | N/A | Yes | 635 | 8079.79 | 2089.34 | Unknown | 184.68 | 280.8 | 5524.97 | 3981 | 1971.49 | 8079.79 | -6108.3 | Yes | N/A | N/A | 2023-01-12 | 2024-10-08 | 636 | 454 | 2024-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-25 | 2024-09-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | 2025-08-15 | 1900-11-28 | 239 | 2025-08-15 | 2024-10-07 | Unknown | Unknown | 636 | 454 | 333 | 239 | 969 | 693 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 68.05 | 68.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-13 | -621 | -445 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-07-12 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 2685.41 | 757.17 | Unknown | 19.42 | Unknown | 1908.82 | 3981 | 1462.39 | 2685.41 | -1223.02 | Yes | N/A | N/A | 2024-07-12 | 2024-06-19 | Unknown | Unknown | 2024-06-19 | 2024-07-12 | 24 | 18 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-09-10 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-30 | 1900-01-20 | 15 | 2024-09-30 | 2024-09-30 | 1 | 1 | 61 | 43 | 46 | 34 | 107 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-02 | 359 | 258 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-29 | 2024-11-21 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 37213.94 | Unknown | Unknown | Yes | N/A | N/A | 2024-07-24 | 2023-09-24 | Unknown | Unknown | 2023-09-24 | 2024-09-27 | 370 | 265 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-10-30 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-12-26 | 1900-02-04 | 26 | 2024-12-26 | 2024-12-26 | 1 | 1 | 0 | 0 | 438 | 315 | 438 | 315 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-03 | -586 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-08-21 | 2023-08-24 | IOU Designed & Installed | N/A | No | N/A | -14.83 | -10.75 | Unknown | Unknown | Unknown | -4.08 | Unknown | 480.37 | -14.83 | 495.2 | Yes | N/A | N/A | 2023-08-21 | 2023-05-17 | Unknown | Unknown | 2023-05-17 | 2023-08-21 | 97 | 69 | 2023-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2023-08-24 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | 2023-09-25 | 1900-02-01 | 23 | 2023-09-25 | 2023-09-25 | 1 | 1 | 4 | 4 | 131 | 93 | 135 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | San Dieog | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -990 | -708 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-19 | 2022-10-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1891.79 | -37.09 | Unknown | Unknown | -1829.11 | -25.59 | Unknown | 6117.61 | -1891.79 | 8009.4 | Yes | N/A | N/A | 2022-10-19 | 2023-02-22 | 127 | 91 | 2023-02-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-16 | Unknown | Unknown | 2023-04-16 | 2023-04-16 | 1 | 0 | 127 | 91 | 1 | 0 | 128 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-17 | -493 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2023-11-15 | 2024-01-04 | IOU Designed & Installed | N/A | No | N/A | 1442.61 | -12.06 | Unknown | Unknown | Unknown | 1454.67 | 3981 | 956.41 | 1442.61 | -486.2 | Yes | N/A | N/A | 2023-11-15 | 2023-08-31 | Unknown | Unknown | 2023-08-31 | 2023-11-15 | 77 | 55 | 2023-11-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2024-01-04 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-10 | 1900-01-06 | 5 | 2024-01-10 | 2024-01-10 | 1 | 1 | 51 | 37 | 85 | 61 | 136 | 98 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 144.05 | 144.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-31 | 443 | 318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 1097.96 | Unknown | Unknown | Unknown | 40.18 | 1057.78 | 3981 | 794.8 | 1097.96 | -303.16 | Yes | N/A | N/A | 2023-09-14 | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2023-09-29 | 17 | 13 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-26 | 2024-09-09 | 350 | 250 | Unknown | 2024-08-12 | Unknown | Unknown | 2024-09-09 | 2024-10-16 | 1900-02-06 | 28 | 2024-10-16 | 2024-10-16 | 1 | 1 | 350 | 250 | 56 | 42 | 406 | 292 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-22 | 722 | 517 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-03-21 | 2024-01-31 | IOU Designed & Installed | N/A | No | N/A | 490.14 | -12.81 | Unknown | Unknown | 48.66 | 454.29 | 3981 | 596.18 | 490.14 | 106.04 | Yes | N/A | N/A | 2023-02-21 | 2023-03-21 | 29 | 21 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2024-01-31 | 317 | 227 | Unknown | 2024-01-31 | Unknown | Unknown | 2024-01-31 | 2024-02-15 | 1900-01-15 | 12 | 2024-02-15 | 2024-02-14 | Unknown | Unknown | 346 | 248 | 16 | 12 | 362 | 260 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 107.05 | 107.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-23 | 767 | 548 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-09 | 2023-03-02 | 2025-03-14 | IOU Designed & Installed | N/A | No | N/A | 5286.84 | Unknown | Unknown | Unknown | Unknown | 5286.84 | 3981 | 777.17 | 5286.84 | -4509.67 | Yes | N/A | N/A | 2022-05-09 | 2023-03-02 | 298 | 214 | 2023-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-02 | 2025-03-14 | 744 | 532 | Unknown | Unknown | Unknown | Unknown | 2025-03-14 | 2025-03-31 | 1900-01-17 | 12 | 2025-03-31 | 2025-03-31 | 1 | 1 | 1042 | 746 | 19 | 13 | 1061 | 759 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 112 | 112 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-03 | -241 | -172 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-31 | 2023-06-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.43 | -12.99 | Unknown | Unknown | Unknown | 8.56 | 3981 | 637.18 | -4.43 | 641.61 | Yes | N/A | N/A | 2023-05-31 | 2023-06-15 | 16 | 12 | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-06 | Unknown | Unknown | 2023-07-06 | 2023-07-06 | 1 | 1 | 16 | 12 | 1 | 1 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-17 | -586 | -420 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2024-04-23 | IOU Designed & Installed | N/A | No | N/A | 410.25 | -8.72 | Unknown | Unknown | Unknown | 418.97 | Unknown | 1291.35 | 410.25 | 881.1 | Yes | N/A | N/A | 2024-04-11 | 2024-01-25 | Unknown | Unknown | 2024-01-25 | 2024-04-23 | 90 | 64 | 2024-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-04-23 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | 2024-06-10 | 1900-02-17 | 35 | 2024-06-10 | 2024-06-10 | 1 | 1 | 1 | 1 | 140 | 100 | 141 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | -576 | -411 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | 2024-11-01 | IOU Designed & Installed | N/A | No | N/A | 18.93 | Unknown | Unknown | Unknown | 5.78 | 13.15 | 3981 | 1571.84 | 18.93 | 1552.91 | Yes | N/A | N/A | 2024-09-24 | 2024-09-13 | Unknown | Unknown | 2024-09-13 | 2024-09-24 | 12 | 8 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | 2024-11-01 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2025-02-07 | 1900-04-08 | 71 | 2025-02-07 | 2025-02-07 | 1 | 1 | 39 | 29 | 112 | 80 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | -220 | -159 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-05-30 | IOU Designed & Installed | N/A | No | N/A | 2078.98 | 369.72 | Unknown | 214.17 | Unknown | 1495.09 | Unknown | 1224.91 | 2078.98 | -854.07 | Yes | N/A | N/A | 2023-02-13 | 2023-02-14 | 2 | 2 | 2023-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-14 | 2023-05-30 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2023-05-30 | 2023-06-06 | 1900-01-07 | 6 | 2023-06-06 | 2023-06-06 | 1 | 1 | 108 | 78 | 9 | 7 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 54 | 54 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-28 | -641 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-02 | 2024-08-12 | 2024-09-12 | IOU Designed & Installed | N/A | No | N/A | 343.61 | Unknown | Unknown | Unknown | 2 | 341.61 | 3981 | 1162.95 | 343.61 | 819.34 | Yes | N/A | N/A | 2024-08-02 | 2024-07-09 | Unknown | Unknown | 2024-07-09 | 2024-08-23 | 46 | 34 | 2024-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-09-12 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-09-12 | 2024-09-25 | 1900-01-13 | 10 | 2024-09-25 | 2024-09-25 | 1 | 1 | 21 | 15 | 61 | 45 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-06 | -500 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-05 | 2024-04-26 | 2024-10-14 | IOU Designed & Installed | N/A | No | N/A | 838.11 | 317.29 | Unknown | Unknown | Unknown | 520.82 | 3981 | 2598.46 | 838.11 | 1760.35 | Yes | N/A | N/A | 2024-04-05 | 2024-04-16 | 12 | 8 | 2024-04-16 | 2024-04-26 | 11 | 9 | 2024-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-26 | 2024-10-14 | 172 | 122 | Unknown | 2024-10-08 | Unknown | Unknown | 2024-10-14 | 2024-10-22 | 1900-01-08 | 7 | 2024-10-22 | 2024-10-22 | 1 | 1 | 184 | 130 | 21 | 17 | 205 | 147 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | -530 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | 2023-08-24 | 2023-11-29 | IOU Designed & Installed | N/A | No | N/A | 236.88 | -5.86 | Unknown | Unknown | 2.19 | 240.55 | 3981 | 685.2 | 236.88 | 448.32 | Yes | N/A | N/A | 2023-08-24 | 2023-09-06 | 14 | 10 | 2023-09-06 | 2023-09-06 | 1 | 1 | 2023-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-06 | 2023-11-29 | 85 | 61 | Unknown | 2023-11-20 | Unknown | Unknown | 2023-11-29 | 2023-12-19 | 1900-01-20 | 15 | 2023-12-19 | 2023-12-19 | 1 | 1 | 99 | 71 | 23 | 17 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | 396 | 396 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | 323 | 232 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-07-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 370.74 | -12.29 | Unknown | Unknown | Unknown | 383.03 | Unknown | 233.49 | 370.74 | -137.25 | Yes | N/A | N/A | 2023-05-23 | 2023-05-25 | 3 | 3 | 2023-05-25 | 2023-08-09 | 77 | 55 | 2023-08-23 | 2023-09-15 | 24 | 18 | 2023-07-18 | 2023-09-28 | 53 | 39 | 2023-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | Unknown | Unknown | 2024-03-19 | 2024-03-19 | 1 | 1 | 27 | 21 | 131 | 95 | 158 | 116 | Steps 2,3,5,6,7 | 109 | 79 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-02 | -603 | -431 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-07-12 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 29.57 | Unknown | Unknown | Unknown | Unknown | 29.57 | Unknown | 1444.08 | 29.57 | 1414.51 | Yes | N/A | N/A | 2024-06-12 | 2024-05-10 | Unknown | Unknown | 2024-05-10 | 2024-07-12 | 64 | 46 | 2024-07-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-08-22 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-09-06 | 1900-01-15 | 12 | 2024-09-06 | 2024-09-06 | 1 | 1 | 42 | 30 | 81 | 59 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 102.1 | 102.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-25 | -652 | -467 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-09 | 2025-05-16 | 2025-05-30 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1026.16 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-09 | 2025-05-08 | 30 | 22 | 2025-05-08 | 2025-05-16 | 9 | 7 | 2025-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-05-30 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-11 | 1900-01-12 | 9 | 2025-06-11 | 2025-06-11 | 1 | 1 | 45 | 33 | 23 | 17 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-12 | -250 | -179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-07 | 2023-11-14 | 2023-12-06 | IOU Designed & Installed | N/A | No | N/A | -1360.32 | 441.84 | Unknown | Unknown | -2010 | 207.84 | Unknown | 2010.5 | -1360.32 | 3370.82 | Yes | N/A | N/A | 2023-11-07 | 2023-11-14 | 8 | 6 | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2023-12-06 | 1899-12-31 | 1 | 2023-12-06 | 2023-12-06 | 1 | 1 | 8 | 6 | 2 | 2 | 10 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 180.2 | 180.2 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-05 | -72 | -53 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-19 | 2024-02-27 | IOU Designed & Installed | N/A | No | N/A | 21360.9 | 682.55 | Unknown | Unknown | 12.34 | 20666.01 | Unknown | 11235.71 | 21360.9 | -10125.19 | Yes | N/A | N/A | 2023-09-18 | 2023-09-19 | 2 | 2 | 2023-09-19 | 2024-01-25 | 129 | 93 | Unknown | Unknown | Unknown | Unknown | 2023-12-22 | 2024-01-29 | 11 | 7 | 2024-01-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | 2024-03-25 | 1900-01-27 | 20 | 2024-03-25 | 2024-03-25 | 1 | 1 | 2 | 2 | 169 | 121 | 171 | 123 | Steps 2,3,5,6,7 | 4 | 2 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 66 | 66 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | 27 | 20 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | -8.1 | -7.65 | Unknown | Unknown | Unknown | -0.45 | Unknown | 163.83 | -8.1 | 171.93 | Yes | N/A | N/A | 2023-11-27 | 2024-03-14 | 109 | 79 | 2024-03-14 | 2024-03-19 | 6 | 4 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-06-03 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-06-27 | 1900-01-24 | 19 | 2024-06-27 | 2024-06-27 | 1 | 1 | 186 | 134 | 32 | 24 | 218 | 158 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-14 | 1 | 1 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 338.63 | 1018.48 | Unknown | 471.68 | -1826 | 674.47 | 0 | 1826.36 | 338.63 | 1487.73 | Yes | N/A | N/A | 2023-08-08 | 2023-08-08 | 1 | 1 | 2023-08-08 | 2023-08-29 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 23 | 17 | 24 | 18 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R29/R45 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | 266 | 191 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-17 | 2023-06-09 | 2024-03-08 | IOU Designed & Installed | N/A | No | N/A | 79694.46 | 1055.99 | Unknown | Unknown | 293.1 | 78345.37 | 0 | 54982.32 | 79694.46 | -24712.14 | Yes | N/A | N/A | 2023-02-17 | 2023-06-16 | 120 | 86 | 2023-06-16 | 2023-12-27 | 195 | 139 | 2023-07-27 | 2023-10-10 | 23 | 17 | 2023-08-24 | 2024-01-04 | 14 | 10 | 2023-12-27 | 2024-05-06 | 132 | 94 | 2024-05-02 | 2024-05-03 | 2 | 2 | 2024-03-08 | 2024-05-24 | 1900-03-18 | 56 | 2024-05-24 | 2024-05-24 | 1 | 1 | 275 | 197 | 290 | 208 | 565 | 405 | Steps 2,3,5,6,7 | 268 | 190 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-14 | 45 | 34 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-10 | 2024-05-10 | 2024-05-16 | IOU Designed & Installed | N/A | No | N/A | 392.52 | 232.44 | Unknown | Unknown | Unknown | 160.08 | Unknown | 277.93 | 392.52 | -114.59 | Yes | N/A | N/A | 2024-05-10 | 2024-05-10 | 1 | 1 | 2024-05-10 | 2024-05-10 | 1 | 1 | 2024-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-05-16 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-06-28 | 1900-02-12 | 32 | 2024-06-28 | 2024-06-28 | 1 | 1 | 5 | 5 | 46 | 34 | 51 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-11 | -506 | -363 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-09 | 2024-05-09 | 2024-10-09 | IOU Designed & Installed | N/A | No | N/A | 1045.49 | -20.4 | Unknown | Unknown | Unknown | 1065.89 | Unknown | 2084.06 | 1045.49 | 1038.57 | Yes | N/A | N/A | 2024-05-09 | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-05-09 | 56 | 40 | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-10-09 | 154 | 110 | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-10-21 | 1900-01-12 | 9 | 2024-10-21 | 2024-10-21 | 1 | 1 | 154 | 110 | 70 | 50 | 224 | 160 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | Both | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 38 | 27 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-05 | 2023-06-05 | 2024-03-19 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 2139.58 | 391.6 | Unknown | 374.58 | -12128 | 13501.4 | Unknown | 19192.1 | 2139.58 | 17052.52 | Yes | N/A | N/A | 2023-06-05 | 2023-10-13 | 131 | 95 | 2023-10-13 | 2024-02-02 | 113 | 81 | 2023-10-26 | 2023-11-09 | 15 | 11 | 2024-01-31 | 2024-02-07 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-04-08 | 1900-01-20 | 15 | 2024-04-08 | 2024-04-08 | 1 | 1 | 146 | 106 | 143 | 103 | 289 | 209 | Steps 2,3,5,6,7 | 99 | 71 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | COUNTY OF SAN DIEGO-SOUTH of 56, SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-03 | -30 | -22 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-03-16 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | 2383.07 | 48.11 | Unknown | Unknown | 0.78 | 2334.18 | Unknown | 807.01 | 2383.07 | -1576.06 | Yes | N/A | N/A | 2023-03-14 | 2023-03-16 | 3 | 3 | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2024-01-05 | 10 | 8 | 2023-03-16 | 2023-12-04 | 264 | 188 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2024-01-04 | 1900-01-31 | 24 | 2024-01-04 | 2024-01-04 | 1 | 1 | 267 | 191 | 43 | 33 | 310 | 224 | Steps 2,3,5,6,7 | 295 | 211 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 14.4 | 14.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-07 | -483 | -346 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-02 | 2024-10-02 | 2025-03-25 | IOU Designed & Installed | N/A | No | N/A | 4096.69 | Unknown | Unknown | Unknown | 10.98 | 4085.71 | 3981 | 1222.34 | 4096.69 | -2874.35 | Yes | N/A | N/A | 2024-10-02 | 2024-08-16 | Unknown | Unknown | 2024-08-16 | 2024-10-02 | 48 | 34 | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2025-03-25 | 175 | 125 | Unknown | 2025-03-20 | Unknown | Unknown | 2025-03-25 | 2025-04-11 | 1900-01-17 | 14 | 2025-04-11 | 2025-04-11 | 1 | 1 | 175 | 125 | 67 | 49 | 242 | 174 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 144 | 103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-24 | 2022-05-24 | 2023-10-06 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 538236.35 | 181082.51 | Unknown | Unknown | 9374.04 | 347779.8 | 5738872 | 344287.73 | 538236.35 | -193948.62 | Yes | N/A | N/A | 2022-05-24 | 2023-02-24 | 277 | 199 | 2023-02-24 | 2023-05-11 | 77 | 55 | 2023-03-10 | 2023-05-24 | 11 | 7 | 2023-05-08 | 2023-05-23 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-07-12 | 2023-10-03 | 84 | 60 | 2023-10-06 | 2023-10-23 | 1900-01-17 | 12 | 2023-10-23 | 2023-10-23 | 1 | 1 | 288 | 206 | 196 | 140 | 484 | 346 | Steps 2,3,5,6,7 | 78 | 56 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 69.05 | 69.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-10 | -472 | -338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | 2025-06-04 | IOU Designed & Installed | N/A | No | N/A | 909.46 | Unknown | Unknown | Unknown | 24.94 | 884.52 | 1736 | 1484.41 | 909.46 | 574.95 | Yes | N/A | N/A | 2025-01-22 | 2025-01-07 | Unknown | Unknown | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-06-04 | 121 | 87 | Unknown | 2025-06-03 | Unknown | Unknown | 2025-06-04 | 2025-06-25 | 1900-01-21 | 16 | 2025-06-25 | 2025-06-25 | 1 | 1 | 121 | 87 | 23 | 17 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-15 | -436 | -312 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-04-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 0.54 | -7.85 | Unknown | Unknown | Unknown | 8.39 | 3981 | 922.3 | 0.54 | 921.76 | Yes | N/A | N/A | 2023-03-28 | 2023-04-17 | 21 | 15 | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | 2024-02-07 | 2023-12-07 | Unknown | Unknown | 21 | 15 | 0 | 0 | 21 | 15 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | -553 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-05 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 18.17 | Unknown | Unknown | Unknown | Unknown | 18.17 | Unknown | 1011.52 | 18.17 | 993.35 | Yes | N/A | N/A | 2024-03-27 | 2024-02-22 | Unknown | Unknown | 2024-02-22 | 2024-04-05 | 44 | 32 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-07-29 | 116 | 82 | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-08-08 | 1900-01-10 | 9 | 2024-08-08 | 2024-08-08 | 1 | 1 | 116 | 82 | 56 | 42 | 172 | 124 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Vista | VISTA | 11220180 | 11220180 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-06-12 | 340 | 245 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2024-04-03 | 2024-05-06 | IOU Designed & Installed | N/A | No | N/A | 3402.35 | Unknown | Unknown | Unknown | -2256 | 5658.35 | Unknown | 2255.55 | 3402.35 | -1146.8 | Yes | N/A | N/A | 2023-02-06 | 2024-04-03 | 423 | 303 | 2024-04-03 | 2024-05-03 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-04-09 | 2024-05-02 | 9 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-05-17 | 1900-01-11 | 10 | 2024-05-17 | 2024-05-17 | 1 | 1 | 423 | 303 | 53 | 39 | 476 | 342 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-05 | -223 | -160 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-04-22 | 2024-05-24 | IOU Designed & Installed | N/A | No | N/A | 814.95 | -12.59 | Unknown | Unknown | Unknown | 827.54 | 3981 | 644.84 | 814.95 | -170.11 | Yes | N/A | N/A | 2024-04-22 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-04-22 | 54 | 38 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-05-24 | 33 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-06-27 | 1900-02-03 | 25 | 2024-06-27 | 2024-06-27 | 1 | 1 | 33 | 25 | 90 | 64 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 139.1 | 139.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-02 | 649 | 464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1010.42 | -8.69 | Unknown | Unknown | -1483 | 481.27 | Unknown | 1371.65 | -1010.42 | 2382.07 | Yes | N/A | N/A | 2024-09-05 | 2024-09-05 | 1 | 1 | 2024-09-05 | 2024-09-19 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | 2024-10-04 | 30 | 22 | 2024-09-19 | 2024-09-24 | 6 | 4 | Unknown | 2024-09-26 | Unknown | Unknown | Unknown | 2024-12-11 | Unknown | Unknown | 2024-12-11 | 2024-12-10 | Unknown | Unknown | 7 | 5 | 45 | 33 | 52 | 38 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R29/R45) | UG | IOU Design | Commercial | Underserved Community | SANTEE | SANTEE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-30 | 277 | 198 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-07-26 | 2025-02-19 | IOU Designed & Installed | N/A | No | N/A | 137031.43 | 39556.73 | Unknown | Unknown | 1582.91 | 95891.79 | 304614 | 221528.93 | 137031.43 | 84497.5 | Yes | N/A | N/A | 2024-06-11 | 2024-07-23 | 43 | 31 | 2024-07-23 | 2025-02-10 | 203 | 145 | 2024-11-05 | 2025-02-04 | 3 | 2 | 2024-08-27 | 2025-05-27 | 131 | 95 | 2025-02-10 | 2025-02-25 | 16 | 12 | 2025-02-25 | 2025-04-04 | 39 | 29 | 2025-02-19 | 2025-06-03 | 1900-04-14 | 75 | 2025-06-03 | 2025-06-03 | 1 | 1 | 62 | 45 | 479 | 345 | 541 | 390 | Steps 2,3,5,6,7 | 408 | 292 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Residential | Underserved Community | Valley Center | N/A | 57.05 | 57.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-17 | -387 | -277 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-09 | 2023-03-09 | 2024-04-19 | IOU Designed & Installed | N/A | No | N/A | 24355.01 | 2441.72 | Unknown | Unknown | 408.82 | 21504.47 | 3095.92 | 3437.57 | 24355.01 | -20917.44 | Yes | N/A | N/A | 2023-03-09 | 2023-03-02 | Unknown | Unknown | 2023-03-02 | 2023-06-08 | 99 | 71 | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2023-09-28 | 5 | 3 | 2024-03-18 | Unknown | Unknown | Unknown | 2024-03-18 | 2024-04-15 | 29 | 21 | 2024-04-19 | 2024-04-25 | 1900-01-06 | 5 | 2024-04-25 | 2024-04-25 | 1 | 1 | 0 | 0 | 141 | 101 | 141 | 101 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-13 | -640 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-20 | 2025-04-25 | IOU Designed & Installed | N/A | No | N/A | 582.25 | -11.7 | Unknown | Unknown | Unknown | 593.95 | 3981 | 1630.92 | 582.25 | 1048.67 | Yes | N/A | N/A | 2025-02-20 | 2025-02-18 | Unknown | Unknown | 2025-02-18 | 2025-02-20 | 3 | 3 | 2025-02-20 | Unknown | Unknown | Unknown | 2025-02-20 | 2025-03-10 | 19 | 13 | 2025-02-20 | 2025-04-25 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-14 | 1900-01-19 | 14 | 2025-05-14 | 2025-05-14 | 1 | 1 | 65 | 47 | 43 | 31 | 108 | 78 | Steps 2,3,5,6,7 | 18 | 12 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-29 | -643 | -460 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-29 | 2024-05-29 | 2024-06-21 | IOU Designed & Installed | N/A | No | N/A | 14565.98 | 11314.04 | Unknown | 279.25 | -2367 | 5339.69 | Unknown | 2366.7 | 14565.98 | -12199.28 | Yes | N/A | N/A | 2024-05-29 | 2024-06-11 | 14 | 10 | 2024-06-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-06-24 | 1900-01-03 | 2 | 2024-06-24 | 2024-06-24 | 1 | 1 | 14 | 10 | 5 | 3 | 19 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-20 | -591 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-02 | 2025-01-02 | IOU Designed & Installed | N/A | No | N/A | 357.8 | Unknown | Unknown | Unknown | -1142.49 | 1500.29 | Unknown | 875.88 | 357.8 | 518.08 | Yes | N/A | N/A | 2024-10-01 | 2024-10-18 | 18 | 14 | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | 2024-10-25 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2025-01-02 | 70 | 50 | Unknown | 2024-12-19 | Unknown | Unknown | 2025-01-02 | 2025-01-06 | 1900-01-04 | 3 | 2025-01-06 | 2025-01-06 | 1 | 1 | 96 | 70 | 7 | 5 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 34819.05 | 34819.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-08-22 | -493 | -354 | No | 2023-12-21 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-21 | 2023-12-21 | 2024-04-09 | IOU Designed & Installed | N/A | Yes | 36 | 2340.64 | 403.88 | Unknown | Unknown | 19.33 | 1917.43 | 3981 | 466.4 | 2340.64 | -1874.24 | Yes | N/A | N/A | 2023-12-21 | 2024-01-23 | 34 | 24 | 2024-01-23 | 2024-01-26 | 4 | 4 | 2024-01-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-05 | 2024-04-09 | 96 | 68 | Unknown | 2024-04-08 | Unknown | Unknown | 2024-04-09 | 2024-04-16 | 1900-01-07 | 6 | 2024-04-16 | 2024-04-16 | 1 | 1 | 130 | 92 | 13 | 11 | 143 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-21 | -641 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-25 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1065.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-21 | 2025-04-11 | Unknown | Unknown | 2025-04-11 | 2025-04-25 | 15 | 11 | 2025-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-25 | 2025-05-20 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-05-22 | 1900-01-02 | 3 | 2025-05-22 | 2025-05-21 | Unknown | Unknown | 26 | 18 | 18 | 14 | 44 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | 146.05 | 146.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -485 | -348 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | 2023-09-28 | IOU Designed & Installed | N/A | No | N/A | 3336.81 | 966.72 | Unknown | 638.8 | Unknown | 1731.29 | 3981 | 1776.28 | 3336.81 | -1560.53 | Yes | N/A | N/A | 2023-09-14 | 2023-03-23 | Unknown | Unknown | 2023-03-23 | 2023-09-19 | 181 | 129 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-19 | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | Unknown | Unknown | 2023-09-28 | 2023-10-03 | 1900-01-05 | 4 | 2023-10-03 | 2023-10-03 | 1 | 1 | 0 | 0 | 188 | 134 | 188 | 134 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-26 | -580 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-12 | 2024-02-12 | 2024-02-26 | IOU Designed & Installed | N/A | No | N/A | -5.27 | -4.27 | Unknown | Unknown | Unknown | -1 | Unknown | 163.83 | -5.27 | 169.1 | Yes | N/A | N/A | 2024-01-12 | 2023-11-03 | Unknown | Unknown | 2023-11-03 | 2024-02-12 | 102 | 72 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-02-26 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-03-25 | 1900-01-28 | 21 | 2024-03-25 | 2024-03-25 | 1 | 1 | 15 | 11 | 132 | 94 | 147 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-15 | -208 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 653.38 | -26.45 | Unknown | Unknown | 47.69 | 632.14 | 3981 | 500.87 | 653.38 | -152.51 | Yes | N/A | N/A | 2023-09-21 | 2023-06-28 | Unknown | Unknown | 2023-06-28 | 2023-10-11 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2023-09-26 | 2023-10-03 | 8 | 6 | 2023-10-11 | 2023-10-27 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2023-11-20 | Unknown | Unknown | 17 | 13 | 114 | 82 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-23 | -511 | -366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | -9.59 | -6.94 | Unknown | Unknown | Unknown | -2.65 | Unknown | 95.13 | -9.59 | 104.72 | Yes | N/A | N/A | 2023-02-23 | 2023-03-04 | 10 | 7 | 2023-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | 10 | 7 | 1 | 1 | 11 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-19 | 15 | 11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-03-08 | 2024-12-27 | IOU Designed & Installed | N/A | No | N/A | 31132.27 | 2004.33 | Unknown | Unknown | -1629.72 | 30757.66 | Unknown | 1746.3 | 31132.27 | -29385.97 | Yes | N/A | N/A | 2024-02-29 | 2024-07-12 | 135 | 97 | 2024-07-12 | 2024-08-02 | 22 | 16 | 2024-07-26 | 2024-07-29 | 4 | 2 | 2024-07-29 | 2024-08-28 | 31 | 23 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | Unknown | Unknown | 2024-12-27 | 2025-02-03 | 1900-02-07 | 27 | 2025-02-03 | 2025-02-03 | 1 | 1 | 139 | 99 | 93 | 67 | 232 | 166 | Steps 2,3,5,6,7 | 33 | 23 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-31 | -680 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-08 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 76.08 | -0.94 | Unknown | Unknown | Unknown | 77.02 | 3981 | 1532.76 | 76.08 | 1456.68 | Yes | N/A | N/A | 2024-11-07 | 2024-11-08 | 2 | 2 | 2024-11-08 | 2024-11-08 | 1 | 1 | 2024-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | 2024-11-14 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-12-20 | 1900-02-05 | 27 | 2024-12-20 | 2024-12-20 | 1 | 1 | 9 | 7 | 39 | 29 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-30 | -673 | -482 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 | 2025-05-29 | 2025-06-24 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1016.07 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-29 | 2025-05-05 | Unknown | Unknown | 2025-05-05 | 2025-05-29 | 25 | 19 | 2025-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-06-24 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-06-24 | 2025-06-26 | 1900-01-02 | 3 | 2025-06-26 | 2025-06-26 | 1 | 1 | 27 | 19 | 29 | 23 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | -554 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-24 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 840.07 | Unknown | Unknown | Unknown | Unknown | 840.07 | 3981 | 1076.2 | 840.07 | 236.13 | Yes | N/A | N/A | 2024-07-16 | 2024-08-19 | 35 | 25 | 2024-08-19 | 2024-09-06 | 19 | 15 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-11-15 | 71 | 51 | Unknown | 2024-11-15 | Unknown | Unknown | 2024-11-15 | 2024-11-22 | 1900-01-07 | 6 | 2024-11-22 | 2024-11-21 | Unknown | Unknown | 106 | 76 | 27 | 21 | 133 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | N/A | Rancho Viejo | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 480 | 343 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-06-19 | 2023-09-19 | IOU Designed & Installed | N/A | No | N/A | 22300.87 | 625.18 | Unknown | Unknown | 2834.88 | 18840.81 | 0 | 15923.79 | 22300.87 | -6377.08 | Yes | N/A | N/A | 2023-03-23 | 2023-03-20 | Unknown | Unknown | 2023-03-20 | 2023-05-08 | 50 | 36 | 2023-04-18 | 2023-08-31 | 46 | 34 | 2023-08-18 | 2023-08-30 | 13 | 9 | 2023-05-10 | Unknown | Unknown | Unknown | 2023-05-10 | 2024-07-03 | 421 | 301 | 2023-09-19 | 2024-09-23 | 1901-01-05 | 265 | 2024-09-23 | 2024-09-23 | 1 | 1 | 46 | 34 | 856 | 612 | 902 | 646 | Steps 2,3,5,6,7 | 433 | 309 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | -514 | -369 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-22 | 2025-01-24 | IOU Designed & Installed | N/A | No | N/A | 4215.73 | 1049.26 | Unknown | 120.74 | Unknown | 3045.73 | Unknown | 1408.3 | 4215.73 | -2807.43 | Yes | N/A | N/A | 2024-07-18 | 2024-07-05 | Unknown | Unknown | 2024-07-05 | 2024-07-22 | 18 | 12 | 2024-07-22 | Unknown | Unknown | Unknown | 2024-07-22 | 2024-08-12 | 22 | 16 | 2024-07-22 | 2025-01-24 | 187 | 135 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-01-27 | 1900-01-03 | 2 | 2025-01-27 | 2025-01-27 | 1 | 1 | 187 | 135 | 45 | 31 | 232 | 166 | Steps 2,3,5,6,7 | 21 | 15 | Unknown | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Commercial | N/A | El Cajon | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-04-01 | 1216 | 869 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-08 | 2021-04-08 | 2024-05-30 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 39280.33 | 9663.62 | Unknown | Unknown | -65796.43 | 95413.14 | Unknown | 69709.31 | 39280.33 | 30428.98 | Yes | N/A | N/A | 2021-04-08 | 2023-08-29 | 874 | 624 | 2023-08-29 | 2024-05-10 | 256 | 184 | 2023-10-12 | 2023-12-14 | 64 | 46 | 2024-02-28 | 2024-03-07 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-30 | 2024-07-30 | 1900-03-02 | 44 | 2024-07-30 | 2024-07-30 | 1 | 1 | 938 | 670 | 328 | 236 | 1266 | 906 | Steps 2,3,5,6,7 | 211 | 151 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-03 | -281 | -202 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-11 | 2024-01-29 | IOU Designed & Installed | N/A | No | N/A | 21.16 | -10.44 | Unknown | Unknown | Unknown | 31.6 | 0 | 338.64 | 21.16 | 317.48 | Yes | N/A | N/A | 2023-07-11 | 2023-08-04 | 25 | 19 | 2023-08-04 | 2023-08-04 | 1 | 1 | 2023-08-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | 2024-01-29 | 179 | 127 | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-06-26 | 1900-05-29 | 108 | 2024-06-26 | 2024-06-26 | 1 | 1 | 204 | 146 | 152 | 110 | 356 | 256 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-01 | -71 | -52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-02-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1.68 | -4.98 | Unknown | Unknown | Unknown | 3.3 | 3981 | 667.76 | -1.68 | 669.44 | Yes | N/A | N/A | 2023-02-06 | 2023-02-13 | 8 | 6 | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | Unknown | Unknown | 2023-08-22 | 2023-08-22 | 1 | 1 | 8 | 6 | 1 | 1 | 9 | 7 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 149 | 149 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-12-28 | 743 | 532 | No | 2023-02-06 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-02-06 | 2023-10-19 | IOU Designed & Installed | N/A | Yes | 217 | 696.63 | 244.9 | Unknown | Unknown | Unknown | 451.73 | 3885 | 554.28 | 696.63 | -142.35 | Yes | N/A | N/A | 2023-02-06 | 2023-09-11 | 218 | 156 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | 2023-10-19 | 256 | 184 | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2023-10-20 | 1900-01-01 | 2 | 2023-10-20 | 2024-01-10 | 83 | 59 | 474 | 340 | 85 | 61 | 559 | 401 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Agricultural | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-08-13 | 1041 | 744 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-01 | 2024-06-05 | IOU Designed & Installed | N/A | No | N/A | -53.59 | -5.35 | Unknown | Unknown | -451 | 402.76 | Unknown | 398.35 | -53.59 | 451.94 | Yes | N/A | N/A | 2024-02-01 | 2024-02-01 | 1 | 1 | 2024-02-01 | 2024-04-24 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-04-12 | Unknown | Unknown | Unknown | 2024-06-10 | Unknown | Unknown | 2024-06-05 | 2024-06-20 | 1900-01-15 | 12 | 2024-06-20 | 2024-06-19 | Unknown | Unknown | 1 | 1 | 100 | 72 | 101 | 73 | Steps 2,3,5,6,7 | 5 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | 88.05 | 88.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-17 | 60 | 43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | 2024-06-28 | IOU Designed & Installed | N/A | No | N/A | 1927.58 | -9.16 | Unknown | Unknown | 88.89 | 1847.85 | 3981 | 857.88 | 1927.58 | -1069.7 | Yes | N/A | N/A | 2023-11-21 | 2023-11-01 | Unknown | Unknown | 2023-11-01 | 2023-12-08 | 38 | 28 | 2023-12-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-08 | 2024-06-28 | 204 | 146 | Unknown | 2024-06-25 | Unknown | Unknown | 2024-06-28 | 2024-07-16 | 1900-01-18 | 13 | 2024-07-16 | 2024-07-16 | 1 | 1 | 204 | 146 | 58 | 42 | 262 | 188 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-27 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2025-01-03 | 2025-03-13 | IOU Designed & Installed | N/A | No | N/A | 93.29 | -1.88 | Unknown | Unknown | Unknown | 95.17 | Unknown | 1863.79 | 93.29 | 1770.5 | Yes | N/A | N/A | 2024-12-18 | 2025-01-03 | 17 | 13 | 2025-01-03 | 2025-01-03 | 1 | 1 | 2025-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-03-13 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-05-29 | 1900-03-18 | 56 | 2025-05-29 | 2025-05-29 | 1 | 1 | 87 | 63 | 80 | 58 | 167 | 121 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -407 | -292 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-06-12 | 2023-12-11 | IOU Designed & Installed | N/A | No | N/A | -7.67 | -5.79 | Unknown | Unknown | Unknown | -1.88 | 3981 | 1110.07 | -7.67 | 1117.74 | Yes | N/A | N/A | 2023-04-03 | 2023-06-12 | 71 | 51 | 2023-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-12 | 2023-12-11 | 183 | 131 | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2023-12-20 | 1900-01-09 | 8 | 2023-12-20 | 2023-12-20 | 1 | 1 | 254 | 182 | 11 | 9 | 265 | 191 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-18 | 98 | 71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-03 | 2024-05-06 | IOU Designed & Installed | N/A | No | N/A | 36911.22 | Unknown | Unknown | Unknown | Unknown | 36911.22 | 94730 | Not available | 36911.22 | Unknown | Yes | N/A | N/A | 2024-01-03 | 2024-01-04 | 2 | 2 | 2024-01-04 | 2024-01-09 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2025-07-30 | 569 | 407 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-03-25 | 1 | 1 | 571 | 409 | 7 | 5 | 578 | 414 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-07-17 | 881 | 630 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | 2023-06-27 | 2023-12-01 | IOU Designed & Installed | N/A | No | N/A | 39641.03 | 11906.22 | Unknown | Unknown | Unknown | 27734.81 | Unknown | 16081.75 | 39641.03 | -23559.28 | Yes | N/A | N/A | 2023-06-26 | 2023-07-07 | 12 | 10 | 2023-07-07 | 2023-07-11 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-11 | 2023-11-14 | 127 | 91 | Unknown | 2023-11-30 | Unknown | Unknown | 2023-12-01 | 2023-12-19 | 1900-01-18 | 13 | 2023-12-19 | 2023-12-15 | Unknown | Unknown | 139 | 101 | 24 | 16 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-11 | 77 | 56 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-02-27 | 2024-03-12 | IOU Designed & Installed | N/A | No | N/A | 14501.66 | Unknown | Unknown | Unknown | Unknown | 14501.66 | 32729 | 3196.34 | 14501.66 | -11305.32 | Yes | N/A | N/A | 2023-02-27 | 2023-10-09 | 225 | 161 | 2023-10-09 | Unknown | Unknown | Unknown | 2024-02-16 | 2024-02-16 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-27 | Unknown | Unknown | 2024-03-12 | 2024-03-28 | 1900-01-16 | 13 | 2024-03-28 | 2024-03-28 | 1 | 1 | 226 | 162 | 18 | 14 | 244 | 176 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 13.1 | 13.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-06 | -117 | -84 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 425.22 | -19.13 | Unknown | Unknown | Unknown | 444.35 | 11943 | 1097.26 | 425.22 | 672.04 | Yes | N/A | N/A | 2024-04-25 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-06-13 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-06-25 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-12 | Unknown | Unknown | 13 | 9 | 126 | 90 | 139 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-15 | -299 | -214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-29 | 2023-11-15 | IOU Designed & Installed | N/A | No | N/A | -204.13 | 1862.88 | Unknown | 1415.04 | -4329 | 846.95 | Unknown | 4328.7 | -204.13 | 4532.83 | Yes | N/A | N/A | 2023-09-25 | 2023-09-25 | 1 | 1 | 2023-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2023-11-21 | 1900-01-06 | 5 | 2023-11-21 | 2023-11-21 | 1 | 1 | 1 | 1 | 8 | 6 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-27 | -494 | -355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-09-03 | 2024-11-11 | IOU Designed & Installed | N/A | No | N/A | 2056.04 | 267.92 | Unknown | 131.84 | Unknown | 1656.28 | 3981 | 636.85 | 2056.04 | -1419.19 | Yes | N/A | N/A | 2024-08-29 | 2024-09-03 | 6 | 4 | 2024-09-03 | 2024-09-03 | 1 | 1 | 2024-09-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-03 | 2024-11-11 | 70 | 50 | Unknown | 2024-11-14 | Unknown | Unknown | 2024-11-11 | 2024-11-18 | 1900-01-07 | 6 | 2024-11-18 | 2024-11-18 | 1 | 1 | 76 | 54 | 10 | 8 | 86 | 62 | Steps 2,3,5,6,7 | 3 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-08-26 | 318 | 227 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-19 | 2024-06-27 | IOU Designed & Installed | N/A | No | N/A | 7454.56 | Unknown | Unknown | Unknown | Unknown | 7454.56 | 4830 | 931.23 | 7454.56 | -6523.33 | Yes | N/A | N/A | 2024-03-19 | 2024-03-19 | 1 | 1 | 2024-03-19 | 2024-03-26 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | 2024-07-09 | 106 | 76 | Unknown | 2024-05-23 | Unknown | Unknown | 2024-06-27 | 2024-07-15 | 1900-01-18 | 13 | 2024-07-15 | 2024-07-09 | Unknown | Unknown | 107 | 77 | 27 | 19 | 134 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | CORONADO | 39 | 39 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-16 | -438 | -313 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-27 | 2024-07-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1718.93 | Unknown | Unknown | Unknown | -1754 | 35.07 | Unknown | 1754.31 | -1718.93 | 3473.24 | Yes | N/A | N/A | 2024-06-27 | 2024-07-09 | 13 | 9 | 2024-07-09 | 2024-08-27 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-07-10 | 8 | 6 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | Unknown | Unknown | 2024-10-04 | 2024-10-04 | 1 | 1 | 13 | 9 | 59 | 43 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-15 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | 2024-12-27 | IOU Designed & Installed | N/A | No | N/A | 119.57 | -1.87 | Unknown | Unknown | Unknown | 121.44 | 3981 | 1576.54 | 119.57 | 1456.97 | Yes | N/A | N/A | 2024-11-05 | 2024-11-05 | 1 | 1 | 2024-11-05 | 2024-11-05 | 1 | 1 | 2024-11-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-05 | 2024-12-27 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2024-12-27 | 2025-01-09 | 1900-01-13 | 10 | 2025-01-09 | 2025-01-09 | 1 | 1 | 54 | 40 | 16 | 12 | 70 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | -533 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-30 | 2024-10-17 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | -1371.92 | Unknown | Unknown | Unknown | -1403 | 31.08 | Unknown | 1403.15 | -1371.92 | 2775.07 | Yes | N/A | N/A | 2024-09-30 | 2024-09-30 | 1 | 1 | 2024-09-30 | 2024-10-17 | 18 | 14 | 2024-10-17 | 2025-01-06 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-29 | 22 | 16 | Unknown | 2025-01-29 | Unknown | Unknown | 2025-01-29 | 2025-02-21 | 1900-01-23 | 18 | 2025-02-21 | 2025-02-21 | 1 | 1 | 105 | 75 | 43 | 33 | 148 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-18 | -729 | -522 | No | 2023-05-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | Unknown | 2024-08-16 | IOU Designed & Installed | N/A | Yes | 486 | 140.21 | -1.5 | Unknown | Unknown | Unknown | 141.71 | 3981 | 1008.11 | 140.21 | 867.9 | Yes | N/A | N/A | 2023-05-02 | 2024-08-30 | 487 | 349 | 2024-08-30 | 2024-08-07 | Unknown | Unknown | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | 2024-08-16 | 473 | 339 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-09-19 | 1900-02-03 | 25 | 2024-09-19 | 2024-09-19 | 1 | 1 | 960 | 688 | 36 | 26 | 996 | 714 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 471 | 336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-30 | 2022-06-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 764.19 | Unknown | Unknown | Unknown | 91.81 | 672.38 | 0 | 1643.04 | 764.19 | 878.85 | Yes | N/A | N/A | 2022-06-30 | 2023-03-06 | 250 | 178 | 2023-03-06 | 2023-08-10 | 158 | 114 | Unknown | Unknown | Unknown | Unknown | 2023-02-16 | 2023-02-24 | 9 | 7 | 2023-08-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-29 | Unknown | Unknown | 2024-09-29 | 2024-09-29 | 1 | 0 | 250 | 178 | 168 | 121 | 418 | 299 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-26 | -179 | -130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-03-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.04 | -11.92 | Unknown | Unknown | Unknown | 7.88 | 3981 | 654.55 | -4.04 | 658.59 | Yes | N/A | N/A | 2023-03-20 | 2023-03-31 | 12 | 10 | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | 2023-07-31 | 2023-07-31 | 1 | 1 | 12 | 10 | 1 | 1 | 13 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | -557 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-16 | 2024-08-30 | 2024-11-25 | IOU Designed & Installed | N/A | No | N/A | 1034.43 | Unknown | Unknown | Unknown | Unknown | 1034.43 | 3981 | 1162.16 | 1034.43 | 127.73 | Yes | N/A | N/A | 2024-08-16 | 2024-08-16 | 1 | 1 | 2024-08-16 | 2024-08-30 | 15 | 11 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-11-25 | 88 | 62 | Unknown | 2024-11-13 | Unknown | Unknown | 2024-11-25 | 2024-12-02 | 1900-01-07 | 6 | 2024-12-02 | 2024-12-02 | 1 | 1 | 89 | 63 | 24 | 18 | 113 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 406.05 | 406.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-09 | -90 | -65 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-04 | 2024-03-04 | 2024-09-20 | IOU Designed & Installed | N/A | No | N/A | 8.57 | Unknown | Unknown | Unknown | Unknown | 8.57 | 3241 | 1001.98 | 8.57 | 993.41 | Yes | N/A | N/A | 2024-03-04 | 2024-03-04 | 1 | 1 | 2024-03-04 | 2024-03-04 | 1 | 1 | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-09-20 | 201 | 145 | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | 2024-10-11 | 1900-01-21 | 16 | 2024-10-11 | 2024-10-11 | 1 | 1 | 202 | 146 | 24 | 18 | 226 | 164 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-26 | -348 | -249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-02-29 | 2024-03-08 | IOU Designed & Installed | N/A | No | N/A | -7.98 | -6.47 | Unknown | Unknown | Unknown | -1.51 | Unknown | 534.53 | -7.98 | 542.51 | Yes | N/A | N/A | 2024-02-29 | 2024-02-29 | 1 | 1 | 2024-02-29 | 2024-02-29 | 1 | 1 | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2024-03-08 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | 2024-03-15 | 1900-01-07 | 6 | 2024-03-15 | 2024-03-15 | 1 | 1 | 10 | 8 | 10 | 8 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | 117.05 | 117.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-22 | 232 | 167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | 2023-12-28 | IOU Designed & Installed | N/A | No | N/A | 3744.31 | 928.76 | Unknown | 318.72 | 26.18 | 2470.65 | 3981 | 1049.15 | 3744.31 | -2695.16 | Yes | N/A | N/A | 2023-02-09 | 2023-03-10 | 30 | 22 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | 2023-12-28 | 294 | 210 | Unknown | 2023-12-28 | Unknown | Unknown | 2023-12-28 | 2024-02-08 | 1900-02-11 | 31 | 2024-02-08 | 2024-02-09 | 2 | 2 | 324 | 232 | 45 | 33 | 369 | 265 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-11 | -7 | -6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-16 | 2023-05-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1417.1 | 227.49 | Unknown | 89.36 | 60.33 | 1039.92 | 3981 | 1205.16 | 1417.1 | -211.94 | Yes | N/A | N/A | 2023-05-16 | 2023-06-14 | 30 | 22 | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-03-04 | 1 | 1 | 30 | 22 | 1 | 1 | 31 | 23 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | -523 | -374 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2025-01-15 | 2025-01-31 | IOU Designed & Installed | N/A | No | N/A | 23.29 | Unknown | Unknown | Unknown | Unknown | 23.29 | 3981 | 1636.64 | 23.29 | 1613.35 | Yes | N/A | N/A | 2024-11-18 | 2025-01-15 | 59 | 43 | 2025-01-15 | 2025-01-15 | 1 | 1 | 2025-01-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-01-31 | 17 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | 2025-02-14 | 1900-01-14 | 11 | 2025-02-14 | 2025-02-14 | 1 | 1 | 76 | 56 | 17 | 13 | 93 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | -477 | -342 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-12-17 | 2025-05-23 | IOU Designed & Installed | N/A | No | N/A | 62.21 | -1.25 | Unknown | Unknown | Unknown | 63.46 | 3981 | 1122.18 | 62.21 | 1059.97 | Yes | N/A | N/A | 2024-11-21 | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-12-16 | 35 | 25 | 2024-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-05-23 | 158 | 114 | Unknown | Unknown | Unknown | Unknown | 2025-05-23 | 2025-06-03 | 1900-01-11 | 8 | 2025-06-03 | 2025-06-03 | 1 | 1 | 158 | 114 | 48 | 34 | 206 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 136 | 136 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | 59 | 42 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-22 | 2024-07-26 | IOU Designed & Installed | N/A | No | N/A | -1134.19 | Unknown | Unknown | Unknown | -1183 | 48.81 | 3981 | 2338.94 | -1134.19 | 3473.13 | Yes | N/A | N/A | 2024-01-22 | 2023-12-18 | Unknown | Unknown | 2023-12-18 | 2024-01-22 | 36 | 26 | 2024-01-22 | 2024-05-29 | 129 | 93 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-07-26 | 59 | 43 | Unknown | 2024-06-27 | Unknown | Unknown | 2024-07-26 | 2024-07-30 | 1900-01-04 | 3 | 2024-07-30 | 2024-07-29 | Unknown | Unknown | 188 | 136 | 41 | 29 | 229 | 165 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-18 | -665 | -476 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | 2025-04-14 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1462.23 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-14 | 2025-04-07 | Unknown | Unknown | 2025-04-07 | 2025-04-23 | 17 | 13 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-05-06 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-22 | 1900-01-16 | 13 | 2025-05-22 | 2025-05-22 | 1 | 1 | 14 | 10 | 35 | 27 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 326 | 326 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | -71 | -52 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-27 | 2023-07-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 20.82 | Unknown | Unknown | Unknown | Unknown | 20.82 | 15924 | 613.78 | 20.82 | 592.96 | Yes | N/A | N/A | 2023-07-27 | 2023-07-27 | 1 | 1 | 2023-07-27 | 2023-07-27 | 1 | 1 | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | 2024-09-19 | 2024-09-19 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-02 | 136 | 97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-19 | 2023-03-20 | 2024-01-16 | IOU Designed & Installed | N/A | No | N/A | 170.28 | -12.61 | Unknown | Unknown | 2.46 | 180.43 | 3981 | 524.75 | 170.28 | 354.47 | Yes | N/A | N/A | 2022-10-19 | 2023-03-30 | 163 | 117 | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | 2024-01-16 | 293 | 209 | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-01-16 | 1899-12-31 | 1 | 2024-01-16 | 2024-01-16 | 1 | 1 | 456 | 326 | 2 | 2 | 458 | 328 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Commercial | N/A | RANCHO MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-08 | 203 | 146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2024-03-16 | IOU Designed & Installed | N/A | No | N/A | 42357.42 | 10186.74 | Unknown | 1995.7 | 2203.46 | 27971.52 | 199397.29 | 31895.73 | 42357.42 | -10461.69 | Yes | N/A | N/A | 2023-03-28 | 2023-03-28 | 1 | 1 | 2023-03-28 | 2023-09-20 | 177 | 127 | 2023-06-21 | 2023-09-19 | 6 | 4 | 2023-09-15 | 2023-09-19 | 5 | 3 | 2023-09-20 | 2024-07-02 | 287 | 205 | Unknown | 2024-07-03 | Unknown | Unknown | 2024-03-16 | 2024-09-23 | 1900-07-10 | 136 | 2024-09-23 | 2024-07-29 | Unknown | Unknown | 294 | 210 | 374 | 266 | 668 | 476 | Steps 2,3,5,6,7 | 204 | 144 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-26 | -240 | -173 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | 2023-11-03 | IOU Designed & Installed | N/A | No | N/A | -17.74 | -13.02 | Unknown | Unknown | Unknown | -4.72 | Unknown | 106.79 | -17.74 | 124.53 | Yes | N/A | N/A | 2023-10-13 | 2023-10-13 | 1 | 1 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2023-11-03 | 9 | 7 | Unknown | 2023-11-03 | Unknown | Unknown | 2023-11-03 | 2024-01-30 | 1900-03-29 | 63 | 2024-01-30 | 2024-01-30 | 1 | 1 | 10 | 8 | 90 | 64 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Oceanside | N/A | 226 | 226 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | 571 | 409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-20 | 2024-07-15 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 18567.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-06-20 | 2024-06-20 | 1 | 1 | 2024-06-20 | 2024-07-08 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-06-27 | 4 | 4 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-07-25 | 1900-01-10 | 9 | 2024-07-25 | 2024-07-25 | 1 | 1 | 1 | 1 | 35 | 27 | 36 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-07 | -668 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-11-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3.02 | Unknown | Unknown | Unknown | Unknown | 3.02 | Unknown | 1615.43 | 3.02 | 1612.41 | Yes | N/A | N/A | 2024-11-25 | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-11-26 | 15 | 11 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | Unknown | Unknown | 2025-01-08 | 2025-01-08 | 1 | 1 | 0 | 0 | 16 | 12 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | Dana Point | N/A | 44.4 | 44.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | 120 | 87 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-06 | 2024-11-11 | 2024-12-10 | IOU Designed & Installed | N/A | No | N/A | 1004.12 | 606.24 | Unknown | Unknown | Unknown | 397.88 | Unknown | 6080.57 | 1004.12 | 5076.45 | Yes | N/A | N/A | 2024-11-06 | 2024-11-06 | 1 | 1 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2024-12-13 | 1900-01-03 | 4 | 2024-12-13 | 2024-12-13 | 1 | 1 | 1 | 1 | 5 | 5 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-05 | -185 | -133 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 382.14 | -43.2 | Unknown | Unknown | Unknown | 425.34 | 3981 | 835.78 | 382.14 | 453.64 | Yes | N/A | N/A | 2023-12-19 | 2023-12-08 | Unknown | Unknown | 2023-12-08 | 2023-12-19 | 12 | 8 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | Unknown | Unknown | 2024-04-03 | 2024-04-03 | 1 | 1 | 0 | 0 | 13 | 9 | 13 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-18 | -540 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | 2024-03-18 | IOU Designed & Installed | N/A | No | N/A | 798.62 | -13.48 | Unknown | Unknown | 4.07 | 808.03 | 3981 | 763.78 | 798.62 | -34.84 | Yes | N/A | N/A | 2023-12-19 | 2023-10-10 | Unknown | Unknown | 2023-10-10 | 2024-01-24 | 107 | 77 | 2024-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-03-18 | 55 | 39 | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-18 | 2024-03-28 | 1900-01-10 | 9 | 2024-03-28 | 2024-03-27 | Unknown | Unknown | 55 | 39 | 118 | 86 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 42 | 42 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-21 | 215 | 154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1056.03 | -49.52 | Unknown | Unknown | Unknown | 1105.55 | 25673 | 2357.31 | 1056.03 | 1301.28 | Yes | N/A | N/A | 2024-02-05 | 2024-02-06 | 2 | 2 | 2024-02-06 | 2024-02-20 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-02-21 | 2024-03-12 | 21 | 15 | 2024-02-20 | 2024-04-18 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-04-23 | Unknown | Unknown | 61 | 45 | 36 | 26 | 97 | 71 | Steps 2,3,5,6,7 | 21 | 15 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-07-19 | 811 | 580 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-03 | 2023-11-22 | 2024-12-06 | IOU Designed & Installed | N/A | No | N/A | 591.01 | Unknown | Unknown | Unknown | -354.42 | 945.43 | 0 | 381.75 | 591.01 | -209.26 | Yes | N/A | N/A | 2023-10-03 | 2023-11-20 | 49 | 35 | 2023-11-20 | 2024-01-16 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2025-01-07 | 168 | 120 | 2024-01-16 | 2024-09-19 | 248 | 178 | Unknown | 2024-09-24 | Unknown | Unknown | 2024-12-06 | 2025-04-03 | 1900-04-28 | 85 | 2025-04-03 | 2024-10-07 | Unknown | Unknown | 297 | 213 | 345 | 247 | 642 | 460 | Steps 2,3,5,6,7 | 357 | 255 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-30 | -686 | -491 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-05-12 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | 4431.24 | 1089.55 | Unknown | Unknown | Unknown | 3341.69 | 3981 | 1434.91 | 4431.24 | -2996.33 | Yes | N/A | N/A | 2025-05-12 | 2025-05-09 | Unknown | Unknown | 2025-05-09 | 2025-05-12 | 4 | 2 | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-06-10 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-06-10 | 2025-06-13 | 1900-01-03 | 4 | 2025-06-13 | 2025-06-13 | 1 | 1 | 30 | 22 | 9 | 7 | 39 | 29 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-30 | -68 | -49 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-06 | 2024-08-08 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 1481.3 | Unknown | Unknown | Unknown | -578 | 2059.3 | 0 | 578.34 | 1481.3 | -902.96 | Yes | N/A | N/A | 2023-06-06 | 2023-06-06 | 1 | 1 | 2023-06-06 | 2023-06-26 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-26 | 2024-07-26 | 397 | 285 | Unknown | 2024-07-23 | Unknown | Unknown | 2024-08-08 | 2024-09-04 | 1900-01-27 | 20 | 2024-09-04 | 2024-08-23 | Unknown | Unknown | 398 | 286 | 49 | 35 | 447 | 321 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | JAMUL | N/A | 34.05 | 34.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-05 | 246 | 177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-02 | 2024-11-05 | IOU Designed & Installed | N/A | No | N/A | 7097.65 | 3040.08 | Unknown | Unknown | -1120 | 5177.57 | 3981 | 3401.94 | 7097.65 | -3695.71 | Yes | N/A | N/A | 2024-05-02 | 2024-05-02 | 1 | 1 | 2024-05-02 | 2024-07-09 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-05-29 | Unknown | Unknown | Unknown | 2024-10-30 | Unknown | Unknown | 2024-11-05 | 2024-11-06 | 1900-01-01 | 2 | 2024-11-06 | 2024-11-06 | 1 | 1 | 1 | 1 | 72 | 52 | 73 | 53 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2021-02-03 | 1338 | 957 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-04-21 | 2024-10-03 | IOU Designed & Installed | N/A | No | N/A | 5034.09 | 609.18 | Unknown | 177.16 | -250.33 | 4498.08 | 0 | 376.62 | 5034.09 | -4657.47 | Yes | N/A | N/A | 2023-03-20 | 2023-04-25 | 37 | 27 | 2023-04-25 | 2024-02-28 | 310 | 222 | 2023-05-01 | 2023-05-11 | 11 | 9 | 2023-04-25 | 2024-08-14 | 72 | 52 | 2024-02-28 | 2024-10-02 | 218 | 156 | Unknown | 2024-07-30 | Unknown | Unknown | 2024-10-03 | 2024-10-03 | 1899-12-31 | 1 | 2024-10-03 | 2024-10-03 | 1 | 1 | 266 | 192 | 384 | 276 | 650 | 468 | Steps 2,3,5,6,7 | 487 | 349 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-21 | -359 | -256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-12-09 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1655.06 | Unknown | Unknown | Yes | N/A | N/A | 2024-08-05 | 2024-11-07 | 95 | 69 | 2024-11-07 | 2025-01-28 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-06-25 | 149 | 107 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-06-27 | 1900-05-29 | 108 | 2025-06-27 | 2025-06-27 | 1 | 1 | 244 | 176 | 234 | 168 | 478 | 344 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 280.05 | 280.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -268 | -193 | No | 2023-04-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-27 | 2023-10-07 | 2024-06-04 | IOU Designed & Installed | N/A | Yes | 288 | 1695.17 | 392.09 | Unknown | Unknown | Unknown | 1303.08 | 3981 | 1348.33 | 1695.17 | -346.84 | Yes | N/A | N/A | 2023-04-27 | 2024-02-09 | 289 | 207 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-07 | 2024-06-04 | 242 | 172 | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-06-05 | 1900-01-01 | 2 | 2024-06-05 | 2024-06-05 | 1 | 1 | 531 | 379 | 3 | 3 | 534 | 382 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-10 | -618 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-06-08 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 14.02 | Unknown | Unknown | Unknown | Unknown | 14.02 | Unknown | 1594.02 | 14.02 | 1580 | Yes | N/A | N/A | 2024-05-14 | 2024-04-18 | Unknown | Unknown | 2024-04-18 | 2024-06-08 | 52 | 37 | 2024-06-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-08 | 2024-07-02 | 25 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-31 | 1900-01-29 | 22 | 2024-07-31 | 2024-07-31 | 1 | 1 | 25 | 17 | 83 | 60 | 108 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-24 | -178 | -127 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-07 | 2023-08-23 | IOU Designed & Installed | N/A | No | N/A | -5.86 | -11.47 | Unknown | Unknown | Unknown | 5.61 | Unknown | 748.69 | -5.86 | 754.55 | Yes | N/A | N/A | 2023-06-06 | 2023-06-30 | 25 | 19 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | 2023-08-23 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2023-08-23 | 2023-09-28 | 1900-02-05 | 27 | 2023-09-28 | 2023-09-28 | 1 | 1 | 103 | 75 | 38 | 28 | 141 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-02 | 379 | 272 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2109.58 | -45.88 | Unknown | Unknown | Unknown | 2155.46 | 15924 | 801.56 | 2109.58 | -1308.02 | Yes | N/A | N/A | 2024-05-02 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-05-14 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-05-29 | 23 | 17 | 2024-05-14 | 2024-07-25 | 73 | 53 | Unknown | 2024-07-01 | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | 2024-08-16 | 2024-08-15 | Unknown | Unknown | 73 | 53 | 37 | 27 | 110 | 80 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-16 | -510 | -365 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-07 | 2024-06-07 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 1.78 | Unknown | Unknown | Unknown | Unknown | 1.78 | Unknown | 1050.61 | 1.78 | 1048.83 | Yes | N/A | N/A | 2024-06-07 | 2024-06-07 | 1 | 1 | 2024-06-07 | 2024-06-07 | 1 | 1 | 2024-06-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-11-14 | 161 | 115 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-11-22 | 1900-01-08 | 7 | 2024-11-22 | 2024-11-22 | 1 | 1 | 162 | 116 | 11 | 9 | 173 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | NATIONAL CITY | N/A | 67.05 | 67.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | -478 | -342 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-14 | 2025-03-14 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | -1518.7 | -36.62 | Unknown | Unknown | -2072 | 589.92 | Unknown | 1779.06 | -1518.7 | 3297.76 | Yes | N/A | N/A | 2025-03-14 | 2025-03-14 | 1 | 1 | 2025-03-14 | 2025-03-14 | 1 | 1 | 2025-03-14 | 2025-04-08 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-04-08 | 2025-04-09 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-17 | 1900-01-08 | 7 | 2025-04-17 | 2025-04-17 | 1 | 1 | 29 | 21 | 11 | 9 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-02 | -628 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-06-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | -0.79 | -2.38 | Unknown | Unknown | Unknown | 1.59 | Unknown | 255.53 | -0.79 | 256.32 | Yes | N/A | N/A | 2023-06-02 | 2023-06-02 | 1 | 1 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | Unknown | Unknown | 2023-09-13 | 2023-09-13 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Lakeside | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-05-03 | 1282 | 916 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-02 | 2023-10-02 | 2023-10-25 | IOU Designed & Installed | N/A | No | N/A | -2478.39 | 1559.66 | Unknown | 5.04 | -4696 | 652.91 | Unknown | 4695.83 | -2478.39 | 7174.22 | Yes | N/A | N/A | 2023-10-02 | 2023-10-23 | 22 | 16 | 2023-10-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | 2023-11-06 | 1900-01-12 | 9 | 2023-11-06 | 2023-11-06 | 1 | 1 | 22 | 16 | 14 | 10 | 36 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-26 | -606 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | 2024-08-01 | 2024-08-08 | IOU Designed & Installed | N/A | No | N/A | 164.78 | -3 | Unknown | Unknown | 2.82 | 164.96 | 3981 | 1387.52 | 164.78 | 1222.74 | Yes | N/A | N/A | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-08-08 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-11-27 | 1900-04-21 | 80 | 2024-11-27 | 2024-11-27 | 1 | 1 | 9 | 7 | 114 | 82 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-14 | -208 | -149 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | 2023-12-01 | IOU Designed & Installed | N/A | No | N/A | 309.61 | -18.49 | Unknown | Unknown | Unknown | 328.1 | Unknown | 801.76 | 309.61 | 492.15 | Yes | N/A | N/A | 2023-11-06 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2023-11-06 | 41 | 29 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | 2023-12-01 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2024-01-19 | 1900-02-18 | 36 | 2024-01-19 | 2024-01-19 | 1 | 1 | 26 | 20 | 92 | 66 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-27 | -421 | -302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-07 | 2023-12-07 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 1252.92 | -12.32 | Unknown | Unknown | -758.08 | 2023.32 | Unknown | 772.55 | 1252.92 | -480.37 | Yes | N/A | N/A | 2023-12-07 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2024-02-13 | 140 | 100 | 2024-02-13 | 2024-02-16 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | 2024-04-15 | 50 | 36 | Unknown | 2024-04-12 | Unknown | Unknown | 2024-04-15 | 2024-05-02 | 1900-01-17 | 14 | 2024-05-02 | 2024-05-02 | 1 | 1 | 54 | 40 | 159 | 115 | 213 | 155 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | -604 | -433 | No | 2024-08-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-30 | 2024-10-14 | IOU Designed & Installed | N/A | Yes | 77 | 6.22 | Unknown | Unknown | Unknown | Unknown | 6.22 | 3981 | 985.1 | 6.22 | 978.88 | Yes | N/A | N/A | 2024-08-22 | 2024-10-30 | 70 | 50 | 2024-10-30 | 2024-11-07 | 9 | 7 | 2024-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-10-14 | 46 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2024-12-02 | 1900-02-18 | 36 | 2024-12-02 | 2024-12-02 | 1 | 1 | 116 | 82 | 60 | 44 | 176 | 126 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-09 | -381 | -272 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-20 | 2024-05-07 | IOU Designed & Installed | N/A | No | N/A | 3.93 | -3.46 | Unknown | Unknown | Unknown | 7.39 | 3981 | 741.21 | 3.93 | 737.28 | Yes | N/A | N/A | 2024-03-20 | 2023-06-21 | Unknown | Unknown | 2023-06-21 | 2024-03-20 | 274 | 196 | 2024-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-05-07 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-05-28 | 1900-01-21 | 16 | 2024-05-28 | 2024-05-24 | Unknown | Unknown | 49 | 35 | 296 | 212 | 345 | 247 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-24 | -634 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-14 | 2025-01-17 | IOU Designed & Installed | N/A | No | N/A | 1360.58 | 317.12 | Unknown | 42.73 | Unknown | 1000.73 | Unknown | 1882.99 | 1360.58 | 522.41 | Yes | N/A | N/A | 2024-12-13 | 2024-12-14 | 2 | 1 | 2024-12-14 | 2024-12-19 | 6 | 4 | 2024-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-19 | 2025-01-17 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | 2025-01-28 | 1900-01-11 | 8 | 2025-01-28 | 2025-01-28 | 1 | 1 | 32 | 23 | 19 | 13 | 51 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | -490 | -351 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | 2025-02-21 | IOU Designed & Installed | N/A | No | N/A | 1056.73 | Unknown | Unknown | Unknown | -1143.64 | 2200.37 | Unknown | 1150.97 | 1056.73 | 94.24 | Yes | N/A | N/A | 2024-08-14 | 2024-09-06 | 24 | 18 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-03 | 2025-02-21 | 50 | 36 | Unknown | 2025-02-20 | Unknown | Unknown | 2025-02-21 | 2025-03-07 | 1900-01-14 | 11 | 2025-03-07 | 2025-03-07 | 1 | 1 | 74 | 54 | 16 | 12 | 90 | 66 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | 224 | 161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-05-16 | 2022-05-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2517.16 | Unknown | Unknown | Unknown | 2.26 | 2514.9 | Unknown | 1482.4 | 2517.16 | -1034.76 | Yes | N/A | N/A | 2022-05-16 | 2023-03-21 | 310 | 222 | 2023-03-21 | 2023-08-29 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | Unknown | Unknown | 2023-10-30 | 2023-10-27 | Unknown | Unknown | 310 | 222 | 162 | 116 | 472 | 338 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-27 | -639 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-18 | 2024-12-18 | 2025-01-08 | IOU Designed & Installed | N/A | No | N/A | 36.21 | Unknown | Unknown | Unknown | Unknown | 36.21 | Unknown | 1912.19 | 36.21 | 1875.98 | Yes | N/A | N/A | 2024-12-18 | 2024-12-03 | Unknown | Unknown | 2024-12-03 | 2024-12-18 | 16 | 12 | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-01-08 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-02-26 | 1900-02-18 | 36 | 2025-02-26 | 2025-02-26 | 1 | 1 | 22 | 16 | 67 | 49 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-09 | -11 | -8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-16 | 2023-06-16 | 2023-12-05 | IOU Designed & Installed | N/A | No | N/A | 668.32 | 435.54 | Unknown | Unknown | Unknown | 232.78 | 23991 | 330.53 | 668.32 | -337.79 | Yes | N/A | N/A | 2023-06-16 | 2023-06-16 | 1 | 1 | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-12-05 | 173 | 123 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2023-12-29 | 1900-01-24 | 19 | 2023-12-29 | 2023-12-29 | 1 | 1 | 174 | 124 | 26 | 20 | 200 | 144 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-25 | -118 | -85 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-16 | 2025-01-17 | 2025-05-07 | IOU Designed & Installed | N/A | No | N/A | 4002.04 | 931.1 | Unknown | Unknown | Unknown | 3070.94 | 3981 | 1774.21 | 4002.04 | -2227.83 | Yes | N/A | N/A | 2025-01-16 | 2025-01-16 | 1 | 1 | 2025-01-16 | 2025-01-17 | 2 | 2 | 2025-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-17 | 2025-05-07 | 111 | 79 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-05-30 | 1900-01-23 | 18 | 2025-05-30 | 2025-05-30 | 1 | 1 | 112 | 80 | 27 | 21 | 139 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | Escondido | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-27 | -326 | -233 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | -2458.71 | 1260.78 | Unknown | Unknown | -4472 | 752.51 | Unknown | 4471.94 | -2458.71 | 6930.65 | Yes | N/A | N/A | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2023-12-06 | 1900-01-02 | 3 | 2023-12-06 | 2023-12-06 | 1 | 1 | 1 | 1 | 4 | 4 | 5 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | San Diego | San Diego | 204 | 204 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-31 | 419 | 300 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-01 | 2023-08-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 28197.95 | 14343.58 | Unknown | Unknown | -26528.38 | 40382.75 | 2752 | 28496.39 | 28197.95 | 298.44 | Yes | N/A | N/A | 2022-03-01 | 2023-02-23 | 360 | 258 | 2023-02-23 | 2023-10-06 | 226 | 162 | 2023-05-25 | 2023-11-13 | 3 | 3 | 2023-10-05 | 2023-10-20 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-19 | 16 | 12 | Unknown | 2024-02-23 | Unknown | Unknown | 2024-02-23 | 2024-02-23 | 1 | 1 | 363 | 261 | 259 | 187 | 622 | 448 | Steps 2,3,5,6,7 | 173 | 123 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-10 | -244 | -175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-27 | 2023-11-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 709.02 | -14.57 | Unknown | Unknown | Unknown | 723.59 | 3981 | 903.51 | 709.02 | 194.49 | Yes | N/A | N/A | 2023-10-27 | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-11-06 | 85 | 61 | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2024-10-09 | 1 | 1 | 0 | 0 | 86 | 62 | 86 | 62 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 192 | 192 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-09 | -558 | -399 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-09 | 2023-02-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 631.23 | -5.59 | Unknown | Unknown | 1.96 | 634.86 | 3981 | 1592.58 | 631.23 | 961.35 | Yes | N/A | N/A | 2023-02-09 | 2023-04-06 | 57 | 41 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | Unknown | Unknown | Unknown | 2023-05-31 | Unknown | Unknown | 2023-05-31 | 2023-05-31 | 1 | 1 | 57 | 41 | 1 | 1 | 58 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-16 | -300 | -215 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-12 | 2024-10-09 | IOU Designed & Installed | N/A | No | N/A | 11.85 | Unknown | Unknown | Unknown | Unknown | 11.85 | 0 | 186.4 | 11.85 | 174.55 | Yes | N/A | N/A | 2024-06-12 | 2024-04-12 | Unknown | Unknown | 2024-04-12 | 2024-06-24 | 74 | 52 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-10-09 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2025-04-22 | 1900-07-14 | 140 | 2025-04-22 | 2025-04-22 | 1 | 1 | 108 | 78 | 271 | 193 | 379 | 271 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-09 | -647 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-09 | 2024-09-06 | 2024-09-06 | IOU Designed & Installed | N/A | No | N/A | 8.87 | Unknown | Unknown | Unknown | Unknown | 8.87 | Unknown | 1493.52 | 8.87 | 1484.65 | Yes | N/A | N/A | 2024-08-09 | 2024-07-23 | Unknown | Unknown | 2024-07-23 | 2024-09-06 | 46 | 34 | 2024-09-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-09-06 | 2024-09-30 | 1900-01-24 | 17 | 2024-09-30 | 2024-09-30 | 1 | 1 | 1 | 1 | 72 | 52 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -580 | -415 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 377.09 | -8.24 | Unknown | Unknown | Unknown | 385.33 | Unknown | 216 | 377.09 | -161.09 | Yes | N/A | N/A | 2023-02-24 | 2023-02-27 | 4 | 2 | 2023-02-27 | 2023-03-03 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-30 | Unknown | Unknown | 2023-08-30 | 2023-08-30 | 1 | 1 | 4 | 2 | 6 | 6 | 10 | 8 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-01 | -307 | -220 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-11 | 2024-03-11 | 2024-12-18 | IOU Designed & Installed | N/A | No | N/A | 2024.56 | Unknown | Unknown | Unknown | Unknown | 2024.56 | 0 | 849.12 | 2024.56 | -1175.44 | Yes | N/A | N/A | 2024-03-11 | 2024-03-06 | Unknown | Unknown | 2024-03-06 | 2024-09-19 | 198 | 142 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-01-28 | 1900-02-10 | 30 | 2025-01-28 | 2025-01-28 | 1 | 1 | 0 | 0 | 241 | 173 | 241 | 173 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 367 | 367 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-04 | -15 | -11 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1608.47 | -14.66 | Unknown | Unknown | Unknown | 1623.13 | Unknown | 2572.13 | 1608.47 | 963.66 | Yes | N/A | N/A | 2024-09-10 | 2024-09-25 | 16 | 12 | 2024-09-25 | 2024-11-27 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | 2024-12-20 | 2024-12-20 | 1 | 1 | 16 | 12 | 65 | 47 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-17 | -342 | -245 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-20 | 2023-09-20 | 2023-10-30 | IOU Designed & Installed | N/A | No | N/A | 1144.34 | -44.32 | Unknown | Unknown | Unknown | 1188.66 | Unknown | 1287.33 | 1144.34 | 142.99 | Yes | N/A | N/A | 2023-09-20 | 2023-09-20 | 1 | 1 | 2023-09-20 | 2023-09-21 | 2 | 2 | 2023-09-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-20 | 2023-10-30 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2023-12-11 | 1900-02-11 | 31 | 2023-12-11 | 2023-12-11 | 1 | 1 | 42 | 30 | 46 | 34 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 138 | 138 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-08 | -148 | -107 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-15 | 2024-01-11 | 2024-07-12 | IOU Designed & Installed | N/A | No | N/A | 70.66 | Unknown | Unknown | Unknown | Unknown | 70.66 | 3981 | 818.76 | 70.66 | 748.1 | Yes | N/A | N/A | 2023-11-15 | 2024-01-08 | 55 | 39 | 2024-01-08 | 2024-01-11 | 4 | 4 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-07-12 | 184 | 132 | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-08-13 | 1900-02-01 | 23 | 2024-08-13 | 2024-08-13 | 1 | 1 | 239 | 171 | 38 | 28 | 277 | 199 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-18 | -192 | -139 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-03 | 2024-09-03 | 2024-10-02 | IOU Designed & Installed | N/A | No | N/A | 272.67 | 1937.06 | Unknown | 493.64 | -3052 | 893.97 | Unknown | 3052.18 | 272.67 | 2779.51 | Yes | N/A | N/A | 2024-09-03 | 2024-08-28 | Unknown | Unknown | 2024-08-28 | 2024-10-08 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-08 | Unknown | Unknown | Unknown | 2024-10-08 | 2024-10-08 | 1 | 1 | 2024-10-02 | 2024-10-08 | 1900-01-06 | 5 | 2024-10-08 | 2024-10-08 | 1 | 1 | 0 | 0 | 51 | 37 | 51 | 37 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 29078 | 29078 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-11-22 | 258 | 185 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-08 | 2024-03-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1214.97 | -7.64 | Unknown | Unknown | 43.51 | 1179.1 | 7962 | 265.9 | 1214.97 | -949.07 | Yes | N/A | N/A | 2024-03-08 | 2024-03-13 | 6 | 4 | 2024-03-13 | 2024-03-20 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-08-05 | 139 | 99 | Unknown | 2024-07-08 | Unknown | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | 2024-08-06 | 2024-08-06 | 1 | 1 | 145 | 103 | 9 | 7 | 154 | 110 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-28 | -134 | -97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-29 | 2023-12-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2411.14 | -63.27 | Unknown | Unknown | Unknown | 2474.41 | 11943 | 1027.51 | 2411.14 | -1383.63 | Yes | N/A | N/A | 2023-11-29 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2023-12-27 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2023-12-15 | 11 | 9 | 2023-12-27 | 2024-02-02 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-02-15 | Unknown | Unknown | 38 | 28 | 103 | 75 | 141 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-10 | -121 | -88 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-11-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2864.82 | 2316.36 | Unknown | 1561.6 | -2079 | 1065.86 | Unknown | 2078.54 | 2864.82 | -786.28 | Yes | N/A | N/A | 2023-10-30 | 2023-10-24 | Unknown | Unknown | 2023-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 67 | 67 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-09 | -109 | -78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-18 | 2023-09-18 | 2024-03-11 | IOU Designed & Installed | N/A | No | N/A | 1340.54 | -12.13 | Unknown | Unknown | 16.32 | 1336.35 | 3981 | 1060.11 | 1340.54 | -280.43 | Yes | N/A | N/A | 2023-09-18 | 2023-11-28 | 72 | 52 | 2023-11-28 | 2023-11-29 | 2 | 2 | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2024-03-11 | 104 | 74 | Unknown | 2024-03-18 | Unknown | Unknown | 2024-03-11 | 2024-03-21 | 1900-01-10 | 9 | 2024-03-21 | 2024-03-22 | 2 | 2 | 176 | 126 | 15 | 13 | 191 | 139 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-26 | -87 | -64 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-12 | 2024-01-04 | IOU Designed & Installed | N/A | No | N/A | 725.91 | -12.3 | Unknown | Unknown | 7.63 | 730.58 | 3885 | 1070.35 | 725.91 | 344.44 | Yes | N/A | N/A | 2023-09-07 | 2023-10-06 | 30 | 22 | 2023-10-06 | 2023-10-20 | 15 | 11 | 2023-10-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-20 | 2024-01-04 | 77 | 55 | Unknown | 2024-01-03 | Unknown | Unknown | 2024-01-04 | 2024-01-30 | 1900-01-26 | 19 | 2024-01-30 | 2024-01-30 | 1 | 1 | 107 | 77 | 43 | 31 | 150 | 108 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 30 | 30 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-17 | 174 | 125 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-04 | 2022-08-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 26262.01 | 10798.6 | Unknown | Unknown | 274.22 | 15189.19 | 99121 | 9280.03 | 26262.01 | -16981.98 | Yes | N/A | N/A | 2022-08-04 | 2023-02-03 | 184 | 132 | 2023-02-03 | 2023-02-22 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-25 | Unknown | Unknown | Unknown | 2023-08-17 | Unknown | Unknown | 2023-08-17 | 2023-05-10 | Unknown | Unknown | 184 | 132 | 20 | 14 | 204 | 146 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | -87 | -64 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1812.35 | 1787.26 | Unknown | 298.3 | -1076 | 802.79 | Unknown | 1076.36 | 1812.35 | -735.99 | Yes | N/A | N/A | 2024-04-11 | 2024-04-10 | Unknown | Unknown | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-22 | 401 | 288 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-08-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | 963.33 | -29.1 | Unknown | Unknown | Unknown | 992.43 | 11943 | 1449.53 | 963.33 | 486.2 | Yes | N/A | N/A | 2023-05-18 | 2023-08-22 | 97 | 69 | 2023-08-22 | 2023-08-29 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-06-19 | 28 | 20 | 2023-08-29 | 2024-05-24 | 270 | 194 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | Unknown | Unknown | 2024-07-02 | 2024-06-26 | Unknown | Unknown | 367 | 263 | 36 | 26 | 403 | 289 | Steps 2,3,5,6,7 | 295 | 211 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | -501 | -360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-09-23 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 6.78 | Unknown | Unknown | Unknown | Unknown | 6.78 | Unknown | 1921.6 | 6.78 | 1914.82 | Yes | N/A | N/A | 2024-08-13 | 2024-07-22 | Unknown | Unknown | 2024-07-22 | 2024-09-23 | 64 | 46 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2025-02-03 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-25 | 1900-01-22 | 17 | 2025-02-25 | 2025-02-24 | Unknown | Unknown | 134 | 96 | 87 | 63 | 221 | 159 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 104.05 | 104.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-30 | 318 | 229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-09 | 2023-05-04 | 2025-03-10 | IOU Designed & Installed | N/A | No | N/A | -2442.66 | Unknown | Unknown | Unknown | -2516 | 73.34 | 0 | 2368.31 | -2442.66 | 4810.97 | Yes | N/A | N/A | 2023-01-09 | 2023-05-04 | 116 | 84 | 2023-05-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-04 | 2025-03-10 | 677 | 483 | Unknown | 2025-02-25 | Unknown | Unknown | 2025-03-10 | 2025-03-17 | 1900-01-07 | 6 | 2025-03-17 | 2025-03-14 | Unknown | Unknown | 793 | 567 | 8 | 6 | 801 | 573 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-18 | 524 | 375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-27 | 2023-08-08 | 2025-03-18 | IOU Designed & Installed | N/A | No | N/A | 3340.68 | 1024.24 | Unknown | 874.79 | -821.87 | 2263.52 | 3981 | 2144.11 | 3340.68 | -1196.57 | Yes | N/A | N/A | 2023-07-27 | 2023-08-09 | 14 | 10 | 2023-08-09 | 2023-09-05 | 28 | 20 | 2023-09-05 | 2023-09-11 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2025-03-18 | 555 | 397 | Unknown | 2024-06-20 | Unknown | Unknown | 2025-03-18 | 2025-03-24 | 1900-01-06 | 5 | 2025-03-24 | 2025-03-25 | 2 | 2 | 576 | 412 | 37 | 27 | 613 | 439 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 183.05 | 183.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-13 | -618 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-27 | 2024-09-30 | 2024-11-20 | IOU Designed & Installed | N/A | No | N/A | 3154.94 | 502.72 | Unknown | 254.14 | Unknown | 2398.08 | 3981 | 1385.71 | 3154.94 | -1769.23 | Yes | N/A | N/A | 2024-09-27 | 2024-08-13 | Unknown | Unknown | 2024-08-13 | 2024-09-30 | 49 | 35 | 2024-09-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-11-20 | 52 | 38 | Unknown | 2024-11-14 | Unknown | Unknown | 2024-11-20 | 2024-12-02 | 1900-01-12 | 9 | 2024-12-02 | 2024-12-03 | 2 | 2 | 52 | 38 | 64 | 46 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-15 | -524 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-02 | 2024-02-23 | 2024-04-25 | IOU Designed & Installed | N/A | No | N/A | -14.07 | -11.43 | Unknown | Unknown | Unknown | -2.64 | 3981 | 910.75 | -14.07 | 924.82 | Yes | N/A | N/A | 2024-01-02 | 2023-10-20 | Unknown | Unknown | 2023-10-20 | 2024-02-23 | 127 | 91 | 2024-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-23 | 2024-04-25 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-05-09 | 1900-01-14 | 11 | 2024-05-09 | 2024-05-09 | 1 | 1 | 63 | 45 | 143 | 103 | 206 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ALPINE | N/A | 150.1 | 150.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-31 | 152 | 110 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-28 | 2023-07-28 | 2024-04-10 | IOU Designed & Installed | N/A | No | N/A | 1338.63 | -14.68 | Unknown | Unknown | 14.48 | 1338.83 | 3981 | 926.48 | 1338.63 | -412.15 | Yes | N/A | N/A | 2023-07-28 | 2023-05-12 | Unknown | Unknown | 2023-05-12 | 2023-09-12 | 124 | 88 | 2023-09-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2024-04-10 | 211 | 151 | Unknown | 2024-04-09 | Unknown | Unknown | 2024-04-10 | 2024-04-23 | 1900-01-13 | 10 | 2024-04-23 | 2024-05-31 | 39 | 29 | 211 | 151 | 177 | 127 | 388 | 278 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | N/A | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-17 | 142 | 103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | 2023-05-05 | 2024-01-30 | IOU Designed & Installed | N/A | No | N/A | 1222.97 | 378.69 | Unknown | 36.69 | Unknown | 807.59 | 3981 | 954.77 | 1222.97 | -268.2 | Yes | N/A | N/A | 2023-01-03 | 2023-05-05 | 123 | 89 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | 2024-01-30 | 271 | 193 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-03-07 | 1900-02-06 | 28 | 2024-03-07 | 2024-03-07 | 1 | 1 | 394 | 282 | 39 | 29 | 433 | 311 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 12.1 | 12.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-12 | -403 | -290 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-27 | 2025-02-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 487.83 | -9.81 | Unknown | Unknown | Unknown | 497.64 | 3981 | 1785.4 | 487.83 | 1297.57 | Yes | N/A | N/A | 2024-11-27 | 2025-01-14 | 49 | 35 | 2025-01-14 | 2025-02-05 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-02-25 | 22 | 16 | 2025-02-05 | 2025-04-15 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | Unknown | Unknown | 2025-05-06 | 2025-05-05 | Unknown | Unknown | 119 | 85 | 45 | 33 | 164 | 118 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-09 | 101 | 74 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1642.86 | -31.69 | Unknown | Unknown | 7.72 | 1666.83 | 3981 | 817.72 | 1642.86 | -825.14 | Yes | N/A | N/A | 2023-09-21 | 2023-07-31 | Unknown | Unknown | 2023-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | Unknown | Unknown | 2024-12-20 | 2024-12-19 | Unknown | Unknown | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-30 | -475 | -340 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-08-21 | 2023-12-06 | IOU Designed & Installed | N/A | No | N/A | 410.41 | 257.62 | Unknown | Unknown | Unknown | 152.79 | Unknown | 480.37 | 410.41 | 69.96 | Yes | N/A | N/A | 2023-08-21 | 2023-08-21 | 1 | 1 | 2023-08-21 | 2023-08-21 | 1 | 1 | 2023-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2023-12-06 | 108 | 78 | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2023-12-11 | 1900-01-05 | 4 | 2023-12-11 | 2023-12-11 | 1 | 1 | 109 | 79 | 8 | 6 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-21 | -269 | -194 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-07-26 | 2023-09-20 | IOU Designed & Installed | N/A | No | N/A | 2496.17 | 795.52 | Unknown | 289.38 | Unknown | 1411.27 | 3981 | 945.58 | 2496.17 | -1550.59 | Yes | N/A | N/A | 2023-07-07 | 2023-07-25 | 19 | 13 | 2023-07-25 | 2023-07-26 | 2 | 2 | 2023-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-09-20 | 57 | 41 | Unknown | 2023-08-31 | Unknown | Unknown | 2023-09-20 | 2023-09-26 | 1900-01-06 | 5 | 2023-09-26 | 2023-09-26 | 1 | 1 | 76 | 54 | 10 | 8 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 306 | 306 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | -283 | -204 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-20 | 2023-05-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 10.56 | -9.4 | Unknown | Unknown | Unknown | 19.96 | 3885 | 559.56 | 10.56 | 549 | Yes | N/A | N/A | 2023-04-20 | 2023-05-03 | 14 | 10 | 2023-05-03 | 2023-12-01 | 213 | 153 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | Unknown | Unknown | 2024-04-29 | 2024-04-29 | 1 | 1 | 14 | 10 | 214 | 154 | 228 | 164 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-14 | -701 | -501 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-21 | 2024-11-21 | 2024-11-21 | IOU Designed & Installed | N/A | No | N/A | 647.53 | -12.33 | Unknown | Unknown | Unknown | 659.86 | 3981 | 1565.71 | 647.53 | 918.18 | Yes | N/A | N/A | 2024-11-21 | 2024-11-21 | 1 | 1 | 2024-11-21 | 2024-11-21 | 1 | 1 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-11-21 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-12-13 | 1900-01-22 | 17 | 2024-12-13 | 2024-12-13 | 1 | 1 | 2 | 2 | 25 | 19 | 27 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-31 | -707 | -506 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | 2025-04-14 | 2025-04-18 | IOU Designed & Installed | N/A | No | N/A | 2392.33 | -48.08 | Unknown | Unknown | Unknown | 2440.41 | 3981 | 1605.34 | 2392.33 | -786.99 | Yes | N/A | N/A | 2025-04-14 | 2025-04-14 | 1 | 1 | 2025-04-14 | 2025-04-14 | 1 | 1 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | 2025-04-18 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-04-23 | 1900-01-05 | 4 | 2025-04-23 | 2025-04-23 | 1 | 1 | 6 | 6 | 8 | 6 | 14 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-10-25 | 787 | 564 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2024-02-07 | 2024-12-17 | IOU Designed & Installed | N/A | No | N/A | 5435.32 | 1478.82 | Unknown | 149.24 | Unknown | 3807.26 | 15924 | 1105.84 | 5435.32 | -4329.48 | Yes | N/A | N/A | 2023-02-14 | 2024-08-27 | 561 | 401 | 2024-08-27 | 2024-11-27 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2024-11-26 | 33 | 23 | 2024-11-27 | 2024-12-09 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2024-12-20 | 1900-01-03 | 4 | 2024-12-20 | 2024-12-20 | 1 | 1 | 574 | 410 | 131 | 95 | 705 | 505 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | -474 | -340 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-22 | 2024-04-22 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | -944.75 | -2.5 | Unknown | Unknown | -1120 | 177.75 | 3981 | 2458.84 | -944.75 | 3403.59 | Yes | N/A | N/A | 2024-04-22 | 2024-05-30 | 39 | 29 | 2024-05-30 | 2025-03-06 | 281 | 201 | 2025-03-06 | 2024-06-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-07-16 | 30 | 22 | Unknown | 2025-03-06 | Unknown | Unknown | 2024-07-16 | 2024-07-29 | 1900-01-13 | 10 | 2024-07-29 | 2024-07-29 | 1 | 1 | 69 | 51 | 296 | 212 | 365 | 263 | Steps 2,3,5,6,7 | 233 | 167 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 87.05 | 87.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-19 | -223 | -160 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-29 | 2023-09-29 | 2023-10-06 | IOU Designed & Installed | N/A | No | N/A | -14.21 | -10.41 | Unknown | Unknown | Unknown | -3.8 | Unknown | 500.87 | -14.21 | 515.08 | Yes | N/A | N/A | 2023-08-29 | 2023-09-29 | 32 | 24 | 2023-09-29 | 2023-09-29 | 1 | 1 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-10-06 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | 2023-11-09 | 1900-02-03 | 25 | 2023-11-09 | 2023-11-09 | 1 | 1 | 40 | 30 | 37 | 27 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-15 | 470 | 337 | No | 2023-03-30 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | 2024-01-31 | IOU Designed & Installed | N/A | Yes | 167 | 749.76 | -8.2 | Unknown | Unknown | 34.95 | 723.01 | 3661.75 | 383.74 | 749.76 | -366.02 | Yes | N/A | N/A | 2023-03-30 | 2023-08-20 | 144 | 102 | 2023-08-20 | 2023-09-13 | 25 | 18 | 2023-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-13 | 2024-01-31 | 141 | 101 | Unknown | 2024-01-11 | Unknown | Unknown | 2024-01-31 | 2024-03-14 | 1900-02-12 | 32 | 2024-03-14 | 2024-02-28 | Unknown | Unknown | 285 | 203 | 69 | 50 | 354 | 253 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-30 | -138 | -100 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-07 | 2024-02-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1799.68 | Unknown | Unknown | Yes | N/A | N/A | 2024-02-07 | 2024-02-06 | Unknown | Unknown | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 16850 | 16850 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-01-09 | 828 | 592 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-08 | 2021-03-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -5.25 | -4.26 | Unknown | Unknown | Unknown | -0.99 | 3981 | 994.94 | -5.25 | 1000.19 | Yes | N/A | N/A | 2021-03-08 | 2023-11-13 | 981 | 701 | 2023-11-13 | 2023-11-13 | 1 | 1 | 2023-11-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2024-04-16 | 1 | 1 | 981 | 701 | 2 | 2 | 983 | 703 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-10 | -116 | -83 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-09 | 2024-01-09 | 2024-06-25 | IOU Designed & Installed | N/A | No | N/A | 13.59 | -10.49 | Unknown | Unknown | Unknown | 24.08 | 3941 | 811.07 | 13.59 | 797.48 | Yes | N/A | N/A | 2024-01-09 | 2023-12-05 | Unknown | Unknown | 2023-12-05 | 2024-01-09 | 36 | 26 | 2024-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-09 | 2024-06-25 | 169 | 121 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-11 | 1900-01-16 | 13 | 2024-07-11 | 2024-07-17 | 7 | 5 | 169 | 121 | 60 | 44 | 229 | 165 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-31 | -805 | -576 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-04 | 2024-05-01 | IOU Designed & Installed | N/A | No | N/A | 11.39 | -10.09 | Unknown | Unknown | Unknown | 21.48 | Unknown | 1051.95 | 11.39 | 1040.56 | Yes | N/A | N/A | 2024-04-04 | 2024-04-04 | 1 | 1 | 2024-04-04 | 2024-04-04 | 1 | 1 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-05-01 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-05-17 | 1900-01-16 | 13 | 2024-05-17 | 2024-05-17 | 1 | 1 | 29 | 21 | 19 | 15 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CORONADO | CORONADO | 18.1 | 18.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | -785 | -562 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-19 | Unknown | IOU Designed & Installed | N/A | No | N/A | 489.03 | -9.49 | Unknown | Unknown | Unknown | 498.52 | Unknown | 444.8 | 489.03 | -44.23 | Yes | N/A | N/A | 2024-07-19 | 2024-07-19 | 1 | 1 | 2024-07-19 | 2024-07-24 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-07-24 | 6 | 4 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2024-08-29 | 1 | 1 | 1 | 1 | 13 | 9 | 14 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-12-31 | 1932 | 1381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 15.33 | Unknown | Unknown | Unknown | Unknown | 15.33 | Unknown | 803.04 | 15.33 | 787.71 | Yes | N/A | N/A | 2025-02-10 | 2025-02-20 | 11 | 9 | 2025-02-20 | 2025-02-20 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | Unknown | Unknown | 2025-04-15 | 2025-04-15 | 1 | 1 | 11 | 9 | 2 | 2 | 13 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-28 | -584 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-17 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 36.36 | -0.63 | Unknown | Unknown | Unknown | 36.99 | Unknown | 1722.95 | 36.36 | 1686.59 | Yes | N/A | N/A | 2024-07-17 | 2024-07-17 | 1 | 1 | 2024-07-17 | 2024-07-17 | 1 | 1 | 2024-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-17 | 2024-11-07 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2024-11-21 | 1900-01-14 | 11 | 2024-11-21 | 2024-11-21 | 1 | 1 | 115 | 83 | 17 | 13 | 132 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VALLEY CENTER | COUNTY OF SAN DIEGO-NORTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-21 | -668 | -477 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-06 | 2025-03-06 | 2025-04-17 | IOU Designed & Installed | N/A | No | N/A | 409.69 | -34.2 | Unknown | Unknown | -1293 | 1736.89 | Unknown | 1217.47 | 409.69 | 807.78 | Yes | N/A | N/A | 2025-03-06 | 2025-03-04 | Unknown | Unknown | 2025-03-04 | 2025-03-07 | 4 | 4 | 2025-03-07 | 2025-03-12 | 6 | 4 | 2025-03-07 | 2025-03-14 | 8 | 6 | 2025-03-12 | 2025-04-17 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-04-23 | 1900-01-06 | 5 | 2025-04-23 | 2025-04-24 | 2 | 2 | 43 | 31 | 21 | 17 | 64 | 48 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-23 | -652 | -467 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-04 | 2024-06-21 | 2024-06-25 | IOU Designed & Installed | N/A | No | N/A | 3.75 | -2.9 | Unknown | Unknown | Unknown | 6.65 | Unknown | 443.54 | 3.75 | 439.79 | Yes | N/A | N/A | 2024-06-04 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-06-21 | 52 | 38 | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-06-25 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-07-10 | 1900-01-15 | 12 | 2024-07-10 | 2024-07-10 | 1 | 1 | 5 | 3 | 69 | 51 | 74 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 72.05 | 72.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-31 | 561 | 402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-08 | 2023-08-08 | 2024-11-11 | IOU Designed & Installed | N/A | No | N/A | 24723.74 | 140.46 | Unknown | 58.96 | 18.52 | 24505.8 | 3981 | 2830.61 | 24723.74 | -21893.13 | Yes | N/A | N/A | 2023-08-08 | 2024-01-29 | 175 | 125 | 2024-01-29 | 2024-01-29 | 1 | 1 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2024-11-11 | Unknown | Unknown | Unknown | 2024-10-21 | Unknown | Unknown | 2024-11-11 | 2025-02-18 | 1900-04-09 | 72 | 2025-02-18 | 2025-05-14 | 86 | 62 | 175 | 125 | 187 | 135 | 362 | 260 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-04 | -572 | -409 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-04 | 2023-11-09 | IOU Designed & Installed | N/A | No | N/A | 1903.05 | 611.22 | Unknown | 316.32 | Unknown | 975.51 | Unknown | 4528.01 | 1903.05 | 2624.96 | Yes | N/A | N/A | 2023-10-04 | 2023-10-10 | 7 | 5 | 2023-10-10 | 2023-10-19 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-11-10 | 1900-01-01 | 2 | 2023-11-10 | 2023-11-10 | 1 | 1 | 7 | 5 | 13 | 11 | 20 | 16 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 497.05 | 497.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-13 | -281 | -201 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1237.15 | Unknown | Unknown | Unknown | 17.12 | 1220.03 | 3981 | 1335.11 | 1237.15 | 97.96 | Yes | N/A | N/A | 2024-01-23 | 2023-10-27 | Unknown | Unknown | 2023-10-27 | 2024-02-01 | 98 | 70 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | Unknown | Unknown | Unknown | 2024-12-06 | Unknown | Unknown | 2024-12-06 | 2024-12-06 | 1 | 1 | 0 | 0 | 99 | 71 | 99 | 71 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 261 | 261 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-10-15 | -6531 | -4666 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 600.6 | -26.15 | Unknown | Unknown | 5.27 | 621.48 | 15924 | 635.84 | 600.6 | 35.24 | Yes | N/A | N/A | 2023-03-06 | 2023-02-27 | Unknown | Unknown | 2023-02-27 | 2023-05-25 | 88 | 64 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-25 | 2023-11-08 | 168 | 120 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | Unknown | Unknown | 2024-02-01 | 2003-11-28 | Unknown | Unknown | 168 | 120 | 88 | 64 | 256 | 184 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 264 | 189 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3397.08 | 62.02 | Unknown | Unknown | 64.63 | 3270.43 | Unknown | 1472.71 | 3397.08 | -1924.37 | Yes | N/A | N/A | 2023-07-17 | 2023-08-29 | 44 | 32 | 2023-08-29 | 2023-09-12 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-12 | 2024-01-24 | 135 | 97 | Unknown | 2024-02-20 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-06 | Unknown | Unknown | 179 | 129 | 15 | 11 | 194 | 140 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 63 | 63 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | -92 | -67 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-05 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 21732.61 | 1454.22 | Unknown | Unknown | -5288.46 | 25566.85 | Unknown | 5299.12 | 21732.61 | -16433.49 | Yes | N/A | N/A | 2024-04-04 | 2024-07-02 | 90 | 64 | 2024-07-02 | 2024-08-23 | 53 | 39 | 2024-07-30 | 2024-07-30 | 1 | 1 | 2024-10-18 | 2024-11-13 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-11-06 | 1900-02-11 | 31 | 2024-11-06 | 2024-11-06 | 1 | 1 | 91 | 65 | 124 | 90 | 215 | 155 | Steps 2,3,5,6,7 | 24 | 18 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 75.05 | 75.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-13 | 95 | 68 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2023-12-20 | 2024-06-24 | IOU Designed & Installed | N/A | No | N/A | 10.25 | -7.89 | Unknown | Unknown | Unknown | 18.14 | 3981 | 561.37 | 10.25 | 551.12 | Yes | N/A | N/A | 2023-12-20 | 2023-11-08 | Unknown | Unknown | 2023-11-08 | 2023-12-20 | 43 | 31 | 2023-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2024-06-24 | 188 | 134 | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | 2024-07-12 | 1900-01-18 | 15 | 2024-07-12 | 2024-07-17 | 6 | 4 | 188 | 134 | 68 | 50 | 256 | 184 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BONITA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | -469 | -336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-16 | 2024-05-06 | IOU Designed & Installed | N/A | No | N/A | 12.87 | -11.42 | Unknown | Unknown | Unknown | 24.29 | 3981 | 1049.42 | 12.87 | 1036.55 | Yes | N/A | N/A | 2024-01-11 | 2024-01-16 | 6 | 4 | 2024-01-16 | 2024-01-16 | 1 | 1 | 2024-01-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-16 | 2024-05-06 | 112 | 80 | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | 2024-05-20 | 1900-01-14 | 11 | 2024-05-20 | 2024-05-20 | 1 | 1 | 118 | 84 | 17 | 13 | 135 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-22 | -562 | -403 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-08-21 | 2023-10-16 | IOU Designed & Installed | N/A | No | N/A | 1470.61 | 278.1 | Unknown | 32.54 | 6.77 | 1153.2 | 3981 | 650.91 | 1470.61 | -819.7 | Yes | N/A | N/A | 2023-08-21 | 2023-06-01 | Unknown | Unknown | 2023-06-01 | 2023-08-31 | 92 | 66 | 2023-08-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | 2023-10-16 | 47 | 33 | Unknown | 2023-10-11 | Unknown | Unknown | 2023-10-16 | 2023-11-07 | 1900-01-22 | 17 | 2023-11-07 | 2023-11-07 | 1 | 1 | 47 | 33 | 116 | 84 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-28 | -129 | -93 | No | 2022-01-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-19 | 2022-01-19 | Unknown | IOU Designed & Installed | N/A | Yes | 517 | -2.1 | -6.16 | Unknown | Unknown | Unknown | 4.06 | 3241 | 1294.87 | -2.1 | 1296.97 | Yes | N/A | N/A | 2022-01-19 | 2023-06-20 | 518 | 370 | 2023-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-01-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | Unknown | Unknown | 2023-06-21 | 2023-06-21 | 1 | 1 | 518 | 370 | 1 | 1 | 519 | 371 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-12-31 | 408 | 291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-16 | 2023-11-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 264.48 | -20.01 | Unknown | Unknown | Unknown | 284.49 | Unknown | 770.07 | 264.48 | 505.59 | Yes | N/A | N/A | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-11-16 | 2023-11-22 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | Unknown | Unknown | 2024-02-12 | 2024-02-12 | 1 | 1 | 1 | 1 | 8 | 6 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | -219 | -157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-11-08 | 2025-02-12 | IOU Designed & Installed | N/A | No | N/A | 6415.66 | Unknown | Unknown | Unknown | Unknown | 6415.66 | 3981 | 2453.41 | 6415.66 | -3962.25 | Yes | N/A | N/A | 2024-02-26 | 2024-07-30 | 156 | 112 | 2024-07-30 | 2025-02-05 | 191 | 137 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-01-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-03-03 | 1900-01-19 | 14 | 2025-03-03 | 2025-02-27 | Unknown | Unknown | 156 | 112 | 211 | 151 | 367 | 263 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | La Mesa | N/A | 9 | 9 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-06 | -198 | -142 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | 2023-03-28 | IOU Designed & Installed | N/A | No | N/A | 936.63 | 304.15 | Unknown | 110.13 | 13.01 | 509.34 | Unknown | 1808.91 | 936.63 | 872.28 | Yes | N/A | N/A | 2023-02-23 | 2023-02-23 | 1 | 1 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | 2023-03-28 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | 2023-06-22 | 1900-03-27 | 63 | 2023-06-22 | 2023-06-22 | 1 | 1 | 35 | 25 | 88 | 64 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | -606 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-05-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | -378.2 | -20.22 | Unknown | Unknown | -744 | 386.02 | 3981 | 1539.16 | -378.2 | 1917.36 | Yes | N/A | N/A | 2023-05-15 | 2023-05-15 | 1 | 1 | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-27 | Unknown | Unknown | 2023-06-27 | 2023-06-27 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 70 | 70 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-09 | -332 | -237 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-08 | 2023-03-08 | 2024-02-01 | IOU Designed & Installed | N/A | No | N/A | -519.33 | -11.11 | Unknown | Unknown | -1239.45 | 731.23 | 0 | 1252.13 | -519.33 | 1771.46 | Yes | N/A | N/A | 2023-03-08 | 2023-02-23 | Unknown | Unknown | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2024-02-01 | 172 | 124 | Unknown | 2024-01-25 | Unknown | Unknown | 2024-02-01 | 2024-03-14 | 1900-02-11 | 31 | 2024-03-14 | 2024-03-14 | 1 | 1 | 172 | 124 | 44 | 32 | 216 | 156 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | -632 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-30 | 2024-11-01 | IOU Designed & Installed | N/A | No | N/A | 25.93 | Unknown | Unknown | Unknown | Unknown | 25.93 | Unknown | 1590.34 | 25.93 | 1564.41 | Yes | N/A | N/A | 2024-10-28 | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2024-10-30 | 22 | 16 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2024-11-01 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-11-01 | 2024-11-14 | 1900-01-13 | 10 | 2024-11-14 | 2024-11-14 | 1 | 1 | 3 | 3 | 37 | 27 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-15 | -493 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-03-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 635.94 | -11.13 | Unknown | Unknown | 9.37 | 637.7 | 3981 | 514.73 | 635.94 | -121.21 | Yes | N/A | N/A | 2023-02-24 | 2023-03-03 | 8 | 6 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | 2023-05-24 | Unknown | Unknown | Unknown | 2023-07-11 | Unknown | Unknown | 2023-07-11 | 2023-07-11 | 1 | 1 | 8 | 6 | 1 | 1 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-06 | 13 | 10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-29 | 2023-06-29 | Unknown | IOU Designed & Installed | N/A | No | N/A | 5425.8 | 256.6 | Unknown | 23.84 | Unknown | 5145.36 | 0 | 3054.47 | 5425.8 | -2371.33 | Yes | N/A | N/A | 2023-06-29 | 2023-05-31 | Unknown | Unknown | 2023-05-31 | 2023-07-14 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | Unknown | Unknown | 2024-04-19 | 2024-04-19 | 1 | 1 | 0 | 0 | 46 | 34 | 46 | 34 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-05 | -639 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | 2025-02-24 | IOU Designed & Installed | N/A | No | N/A | 1367.38 | Unknown | Unknown | Unknown | 9.48 | 1357.9 | 3981 | 1219.99 | 1367.38 | -147.39 | Yes | N/A | N/A | 2024-12-19 | 2025-01-28 | 41 | 29 | 2025-01-28 | 2025-01-28 | 1 | 1 | 2025-01-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-02-24 | 28 | 20 | Unknown | 2025-02-21 | Unknown | Unknown | 2025-02-24 | 2025-03-06 | 1900-01-10 | 9 | 2025-03-06 | 2025-03-06 | 1 | 1 | 69 | 49 | 13 | 11 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-13 | -307 | -220 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2602.51 | 276.41 | Unknown | 93.76 | Unknown | 2232.34 | 3981 | 816.91 | 2602.51 | -1785.6 | Yes | N/A | N/A | 2024-03-06 | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-04-01 | 41 | 29 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | Unknown | Unknown | 2024-04-12 | 2024-04-12 | 1 | 1 | 0 | 0 | 42 | 30 | 42 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-20 | -554 | -396 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-12 | 2024-02-12 | IOU Designed & Installed | N/A | No | N/A | 785.06 | -26.46 | Unknown | Unknown | Unknown | 811.52 | 3981 | 855.43 | 785.06 | 70.37 | Yes | N/A | N/A | 2024-01-10 | 2023-09-29 | Unknown | Unknown | 2023-09-29 | 2024-01-12 | 106 | 76 | 2024-01-12 | Unknown | Unknown | Unknown | 2024-01-12 | 2024-01-29 | 18 | 12 | 2024-01-12 | 2024-02-12 | 32 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-03-15 | 1900-02-01 | 25 | 2024-03-15 | 2024-03-15 | 1 | 1 | 32 | 22 | 158 | 114 | 190 | 136 | Steps 2,3,5,6,7 | 17 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | -514 | -369 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | 2024-02-06 | IOU Designed & Installed | N/A | No | N/A | 952.55 | 183.68 | Unknown | Unknown | 39.44 | 729.43 | 3981 | 659.77 | 952.55 | -292.78 | Yes | N/A | N/A | 2023-10-17 | 2023-12-21 | 66 | 48 | 2023-12-21 | 2023-12-21 | 1 | 1 | 2023-12-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-21 | 2024-02-06 | 48 | 34 | Unknown | 2024-02-21 | Unknown | Unknown | 2024-02-06 | 2024-07-03 | 1900-05-28 | 107 | 2024-07-03 | 2024-02-26 | Unknown | Unknown | 114 | 82 | 150 | 108 | 264 | 190 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | -627 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1445.07 | Unknown | Unknown | Unknown | 10.34 | 1434.73 | 3981 | 1182.68 | 1445.07 | -262.39 | Yes | N/A | N/A | 2024-08-27 | 2024-08-28 | 2 | 2 | 2024-08-28 | 2024-09-24 | 28 | 20 | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | Unknown | Unknown | 2024-11-19 | 2024-11-19 | 1 | 1 | 2 | 2 | 29 | 21 | 31 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 37 | 37 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-13 | 133 | 96 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-30 | 2023-08-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 13.97 | -12.39 | Unknown | Unknown | Unknown | 26.36 | 3241 | 1501.15 | 13.97 | 1487.18 | Yes | N/A | N/A | 2023-04-30 | 2023-04-30 | 1 | 0 | 2023-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | Unknown | Unknown | 2024-06-25 | 2024-06-25 | 1 | 1 | 1 | 0 | 1 | 1 | 2 | 1 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-29 | 601 | 430 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-18 | 2025-06-11 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 4992.43 | 1094.53 | Unknown | Unknown | 379.47 | 3518.43 | 124020 | 30895.6 | 4992.43 | 25903.17 | Yes | N/A | N/A | 2023-07-18 | 2023-08-28 | 42 | 30 | 2023-08-28 | 2023-11-29 | 94 | 68 | 2023-09-20 | 2023-09-28 | 9 | 7 | 2023-08-23 | 2025-05-08 | 149 | 108 | 2023-11-29 | 2025-04-11 | 500 | 358 | 2024-02-07 | 2024-12-09 | 307 | 219 | 2025-06-11 | 2025-06-30 | 1900-01-19 | 14 | 2025-06-30 | 2025-05-22 | Unknown | Unknown | 551 | 395 | 570 | 409 | 1121 | 804 | Steps 2,3,5,6,7 | 1061 | 759 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Residential | Underserved Community | SM 1128-J1 NORTH CITY BLK2 WO1 | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-30 | 520 | 371 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2024-11-22 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 97318.87 | 16559.82 | Unknown | Unknown | -40371.63 | 121130.68 | 0 | 42983.15 | 97318.87 | -54335.72 | Yes | N/A | N/A | 2023-02-14 | 2023-02-21 | 8 | 6 | 2023-02-21 | 2023-08-11 | 172 | 124 | 2023-02-24 | 2024-02-27 | 46 | 32 | 2023-02-25 | 2024-08-12 | 48 | 34 | 2023-08-16 | Unknown | Unknown | Unknown | 2023-08-16 | 2024-11-18 | 461 | 329 | 2024-11-22 | 2025-03-03 | 1900-04-11 | 72 | 2025-03-03 | 2025-03-03 | 1 | 1 | 54 | 38 | 784 | 560 | 838 | 598 | Steps 2,3,5,6,7 | 897 | 639 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | -676 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-05 | 2024-06-05 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 811.08 | -15.3 | Unknown | Unknown | Unknown | 826.38 | 3981 | 1378.67 | 811.08 | 567.59 | Yes | N/A | N/A | 2024-06-05 | 2024-06-05 | 1 | 1 | 2024-06-05 | 2024-06-05 | 1 | 1 | 2024-06-05 | Unknown | Unknown | Unknown | 2024-06-06 | 2024-07-03 | 28 | 20 | 2024-06-05 | 2024-07-09 | 35 | 25 | Unknown | Unknown | Unknown | Unknown | 2024-07-09 | 2024-07-22 | 1900-01-13 | 10 | 2024-07-22 | 2024-07-22 | 1 | 1 | 36 | 26 | 44 | 32 | 80 | 58 | Steps 2,3,5,6,7 | 28 | 20 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 19.43 | 19.43 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-25 | -679 | -486 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-04-16 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | 850.65 | 303.12 | Unknown | 314.55 | Unknown | 232.98 | 3981 | 196.38 | 850.65 | -654.27 | Yes | N/A | N/A | 2025-04-16 | 2025-04-18 | 3 | 3 | 2025-04-18 | 2025-04-18 | 1 | 1 | 2025-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2025-05-06 | 19 | 13 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-15 | 1900-01-09 | 8 | 2025-05-15 | 2025-05-15 | 1 | 1 | 22 | 16 | 12 | 10 | 34 | 26 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 71 | 71 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-17 | -69 | -50 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 11.45 | Unknown | Unknown | Unknown | Unknown | 11.45 | 3981 | 2449.09 | 11.45 | 2437.64 | Yes | N/A | N/A | 2024-01-04 | 2023-11-30 | Unknown | Unknown | 2023-11-30 | 2024-01-04 | 36 | 26 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-08-09 | 1 | 1 | 0 | 0 | 37 | 27 | 37 | 27 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | Imperial Beach | IMPERIAL BEACH | 131164 | 131164 | Not Available | >2MW | No | N/A | N/A | N/A | 2022-09-26 | 750 | 537 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-04 | 2023-07-25 | 2024-07-17 | IOU Designed & Installed | N/A | No | N/A | 160424.04 | 11363.99 | Unknown | Unknown | 1722.29 | 147337.76 | 36065 | 52198.36 | 160424.04 | -108225.68 | Yes | N/A | N/A | 2022-10-04 | 2023-05-10 | 219 | 157 | 2023-05-10 | 2023-12-11 | 216 | 154 | 2023-08-24 | 2024-01-02 | 104 | 74 | 2023-11-14 | 2023-12-11 | 28 | 20 | 2023-12-19 | Unknown | Unknown | Unknown | 2023-12-19 | 2024-09-06 | 263 | 189 | 2024-07-17 | 2024-10-15 | 1900-03-31 | 65 | 2024-10-15 | 2024-10-15 | 1 | 1 | 323 | 231 | 599 | 429 | 922 | 660 | Steps 2,3,5,6,7 | 209 | 149 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 106 | 106 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-24 | -627 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-02-20 | 2025-04-07 | IOU Designed & Installed | N/A | No | N/A | 279.7 | -3.66 | Unknown | Unknown | Unknown | 283.36 | 3981 | 1702.29 | 279.7 | 1422.59 | Yes | N/A | N/A | 2025-02-11 | 2025-02-20 | 10 | 8 | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-04-07 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2025-04-07 | 2025-05-07 | 1900-01-30 | 23 | 2025-05-07 | 2025-05-07 | 1 | 1 | 57 | 41 | 33 | 25 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-23 | -632 | -453 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-06-11 | 2024-07-12 | IOU Designed & Installed | N/A | No | N/A | 1225.13 | -24.15 | Unknown | Unknown | Unknown | 1249.28 | Unknown | 1759.53 | 1225.13 | 534.4 | Yes | N/A | N/A | 2024-05-31 | 2024-06-11 | 12 | 8 | 2024-06-11 | 2024-06-11 | 1 | 1 | 2024-06-11 | Unknown | Unknown | Unknown | 2024-06-11 | 2024-07-11 | 31 | 23 | 2024-06-11 | 2024-07-12 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-07-30 | 1900-01-18 | 13 | 2024-07-30 | 2024-07-30 | 1 | 1 | 44 | 32 | 52 | 38 | 96 | 70 | Steps 2,3,5,6,7 | 30 | 22 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | BONITA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -229 | -164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-19 | 2024-05-19 | 2025-04-11 | IOU Designed & Installed | N/A | No | N/A | 11719.14 | 514.16 | Unknown | Unknown | 50 | 11154.98 | 3981 | 1894.07 | 11719.14 | -9825.07 | Yes | N/A | N/A | 2024-05-19 | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-08-30 | 180 | 130 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2025-04-11 | 225 | 161 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-04-15 | 1900-01-04 | 3 | 2025-04-15 | 2025-04-15 | 1 | 1 | 225 | 161 | 186 | 134 | 411 | 295 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | -499 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | 2023-09-11 | IOU Designed & Installed | N/A | No | N/A | 674.3 | -20.93 | Unknown | Unknown | 66.16 | 629.07 | Unknown | 987.33 | 674.3 | 313.03 | Yes | N/A | N/A | 2023-03-24 | 2023-04-14 | 22 | 16 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | 2023-09-11 | 151 | 107 | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2024-10-08 | 1901-01-28 | 282 | 2024-10-08 | 2023-09-20 | Unknown | Unknown | 173 | 123 | 394 | 282 | 567 | 405 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-17 | -209 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 7.03 | Unknown | Unknown | Unknown | Unknown | 7.03 | 0 | 158.79 | 7.03 | 151.76 | Yes | N/A | N/A | 2023-12-13 | 2023-10-03 | Unknown | Unknown | 2023-10-03 | 2024-01-18 | 108 | 78 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-02-20 | 1 | 1 | 0 | 0 | 109 | 79 | 109 | 79 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 139.05 | 139.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-20 | -234 | -169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-19 | 2023-02-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -2.68 | -7.98 | Unknown | Unknown | Unknown | 5.3 | 3981 | 1058.61 | -2.68 | 1061.29 | Yes | N/A | N/A | 2023-01-19 | 2023-02-06 | 19 | 13 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | Unknown | Unknown | 2023-03-07 | 2023-02-28 | Unknown | Unknown | 19 | 13 | 0 | 0 | 19 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-12 | -279 | -200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 91.4 | Unknown | Unknown | Unknown | Unknown | 91.4 | Unknown | 1901.4 | 91.4 | 1810 | Yes | N/A | N/A | 2025-01-07 | 2025-01-09 | 3 | 3 | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | Unknown | Unknown | 2025-02-06 | 2025-02-06 | 1 | 1 | 3 | 3 | 2 | 2 | 5 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-02 | -213 | -154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | Unknown | 2024-07-31 | IOU Designed & Installed | N/A | No | N/A | 60.78 | -0.31 | Unknown | Unknown | 2.74 | 58.35 | 3981 | 1039.36 | 60.78 | 978.58 | Yes | N/A | N/A | 2024-05-13 | 2024-05-13 | 1 | 1 | 2024-05-13 | 2024-05-13 | 1 | 1 | 2024-05-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-07-31 | 80 | 58 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-10-01 | 1900-03-03 | 45 | 2024-10-01 | 2024-10-01 | 1 | 1 | 81 | 59 | 65 | 47 | 146 | 106 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-06 | 351 | 252 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | 2024-06-12 | IOU Designed & Installed | N/A | No | N/A | -344.21 | 2372.67 | Unknown | 533.87 | -4353 | 1102.25 | Unknown | 4353.13 | -344.21 | 4697.34 | Yes | N/A | N/A | 2024-05-20 | 2024-05-16 | Unknown | Unknown | 2024-05-16 | 2024-06-21 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | Unknown | Unknown | Unknown | 2024-06-21 | 2024-06-21 | 1 | 1 | 2024-06-12 | 2024-06-21 | 1900-01-09 | 8 | 2024-06-21 | 2024-06-21 | 1 | 1 | 0 | 0 | 49 | 37 | 49 | 37 | Steps 2,3,5,6,7 | 9 | 7 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | LA MESA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-05-01 | 722 | 516 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-27 | 2024-02-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 619.77 | -32.75 | Unknown | Unknown | Unknown | 652.52 | Unknown | 308.87 | 619.77 | -310.9 | Yes | N/A | N/A | 2024-02-27 | 2024-02-29 | 3 | 3 | 2024-02-29 | 2024-03-28 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-02-28 | 2024-03-26 | 28 | 20 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | Unknown | Unknown | 2024-04-22 | 2024-04-22 | 1 | 1 | 3 | 3 | 58 | 42 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | -513 | -366 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-03 | 2024-02-14 | IOU Designed & Installed | N/A | No | N/A | -232.79 | -16.01 | Unknown | Unknown | -246 | 29.22 | Unknown | 798.77 | -232.79 | 1031.56 | Yes | N/A | N/A | 2024-01-03 | 2024-01-03 | 1 | 1 | 2024-01-03 | 2024-01-03 | 1 | 1 | 2024-01-03 | 2024-02-14 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-02-14 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-02-14 | 2024-03-15 | 1900-01-30 | 23 | 2024-03-15 | 2024-03-15 | 1 | 1 | 80 | 58 | 33 | 25 | 113 | 83 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-28 | 155 | 111 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2023-09-06 | 2024-08-06 | IOU Designed & Installed | N/A | No | N/A | 426.16 | 251.36 | Unknown | Unknown | Unknown | 174.8 | 0 | 1009.05 | 426.16 | 582.89 | Yes | N/A | N/A | 2023-09-06 | 2023-09-06 | 1 | 1 | 2023-09-06 | 2023-09-06 | 1 | 1 | 2023-09-06 | 2024-11-04 | 426 | 304 | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2024-08-06 | 299 | 213 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-12-30 | 1900-05-26 | 105 | 2024-12-30 | 2024-12-30 | 1 | 1 | 726 | 518 | 149 | 107 | 875 | 625 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | Both | IOU Design | Residential | N/A | ENCINITAS | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 224 | 161 | No | 2023-09-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-25 | Unknown | IOU Designed & Installed | N/A | Yes | 101 | 1065.6 | Unknown | Unknown | Unknown | 21.09 | 1044.51 | 3981 | 427.32 | 1065.6 | -638.28 | Yes | N/A | N/A | 2023-09-19 | 2024-01-04 | 108 | 78 | 2024-01-04 | 2023-09-25 | Unknown | Unknown | 2023-09-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-25 | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | Unknown | Unknown | Unknown | 2024-10-11 | Unknown | Unknown | 2024-10-11 | 2024-10-11 | 1 | 1 | 108 | 78 | 1 | 1 | 109 | 79 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 541.05 | 541.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-17 | -586 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-19 | 2024-02-12 | 2024-04-01 | IOU Designed & Installed | N/A | No | N/A | 10.97 | -9.75 | Unknown | Unknown | Unknown | 20.72 | 3981 | 983.09 | 10.97 | 972.12 | Yes | N/A | N/A | 2024-01-19 | 2023-11-17 | Unknown | Unknown | 2023-11-17 | 2024-02-12 | 88 | 62 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-04-01 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-04-11 | 1900-01-10 | 9 | 2024-04-11 | 2024-04-10 | Unknown | Unknown | 50 | 36 | 99 | 71 | 149 | 107 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | LEMON GROVE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-24 | -682 | -488 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2024-11-08 | 2024-11-25 | IOU Designed & Installed | N/A | No | N/A | 648.15 | -11.7 | Unknown | Unknown | Unknown | 659.85 | 3981 | 1475.62 | 648.15 | 827.47 | Yes | N/A | N/A | 2024-11-08 | 2024-11-04 | Unknown | Unknown | 2024-11-04 | 2024-11-08 | 5 | 5 | 2024-11-08 | Unknown | Unknown | Unknown | 2024-11-08 | 2024-11-15 | 8 | 6 | 2024-11-08 | 2024-11-25 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2024-12-11 | 1900-01-16 | 13 | 2024-12-11 | 2024-12-11 | 1 | 1 | 18 | 12 | 31 | 25 | 49 | 37 | Steps 2,3,5,6,7 | 7 | 5 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 84.05 | 84.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | -518 | -371 | No | 2023-09-11 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | 2023-10-23 | IOU Designed & Installed | N/A | Yes | 22 | 1045.6 | 392.28 | Unknown | Unknown | Unknown | 653.32 | Unknown | 878.05 | 1045.6 | -167.55 | Yes | N/A | N/A | 2023-09-11 | 2023-10-03 | 23 | 17 | 2023-10-03 | 2023-09-11 | Unknown | Unknown | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-10-23 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-10-23 | 2023-10-26 | 1900-01-03 | 4 | 2023-10-26 | 2023-10-26 | 1 | 1 | 66 | 48 | 5 | 5 | 71 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 5 | 5 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-19 | -229 | -165 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1378.92 | 121.24 | Unknown | 896.5 | 6.48 | 354.7 | 3981 | 2141.72 | 1378.92 | 762.8 | Yes | N/A | N/A | 2023-11-14 | 2023-11-14 | 1 | 1 | 2023-11-14 | 2023-12-11 | 28 | 20 | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | Unknown | Unknown | 2023-12-26 | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-03-04 | 1 | 1 | 1 | 1 | 29 | 21 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-13 | -442 | -316 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-04 | 2025-01-31 | 2025-03-05 | IOU Designed & Installed | N/A | No | N/A | -1159.48 | 251.36 | Unknown | 40.57 | -2191 | 739.59 | Unknown | 1763.19 | -1159.48 | 2922.67 | Yes | N/A | N/A | 2024-10-04 | 2025-01-20 | 109 | 77 | 2025-01-20 | 2025-01-31 | 12 | 10 | 2025-01-31 | 2025-02-21 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-03-05 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | 2025-03-28 | 1900-01-23 | 18 | 2025-03-28 | 2025-03-28 | 1 | 1 | 144 | 102 | 37 | 29 | 181 | 131 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -499 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | 2025-04-09 | IOU Designed & Installed | N/A | No | N/A | 325.28 | -6.54 | Unknown | Unknown | Unknown | 331.82 | Unknown | 1770.12 | 325.28 | 1444.84 | Yes | N/A | N/A | 2024-12-09 | 2024-12-15 | 7 | 5 | 2024-12-15 | 2024-12-30 | 16 | 11 | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-04-09 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-17 | 1900-01-08 | 7 | 2025-04-17 | 2025-04-17 | 1 | 1 | 93 | 67 | 26 | 19 | 119 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 179.15 | 179.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-12 | -70 | -51 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-24 | 2023-10-24 | 2025-02-07 | IOU Designed & Installed | N/A | No | N/A | -1152.85 | -8.61 | Unknown | Unknown | -1593 | 448.76 | 0 | Not available | -1152.85 | Unknown | Yes | N/A | N/A | 2023-10-24 | 2023-07-27 | Unknown | Unknown | 2023-07-27 | 2024-08-07 | 378 | 270 | 2024-08-07 | 2024-09-19 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2025-02-07 | 142 | 102 | Unknown | Unknown | Unknown | Unknown | 2025-02-07 | 2025-03-04 | 1900-01-25 | 18 | 2025-03-04 | 2025-03-03 | Unknown | Unknown | 186 | 134 | 404 | 288 | 590 | 422 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-02 | 278 | 199 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-05 | 2024-11-02 | IOU Designed & Installed | N/A | No | N/A | 14653.81 | 3826.88 | Unknown | 750.47 | -740.18 | 10816.64 | Unknown | 795.13 | 14653.81 | -13858.68 | Yes | N/A | N/A | 2024-02-02 | 2024-02-05 | 4 | 2 | 2024-02-05 | 2024-03-19 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-07-12 | 32 | 24 | 2024-03-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-02 | 2024-11-06 | 1900-01-04 | 3 | 2024-11-06 | 2024-11-06 | 1 | 1 | 4 | 2 | 82 | 60 | 86 | 62 | Steps 2,3,5,6,7 | 115 | 83 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-22 | -710 | -508 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-30 | 2025-05-30 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 979.24 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-30 | 2025-05-30 | 1 | 1 | 2025-05-30 | 2025-05-30 | 1 | 1 | 2025-05-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-09 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-11 | 1900-01-02 | 3 | 2025-06-11 | 2025-06-11 | 1 | 1 | 12 | 8 | 5 | 5 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 18.1 | 18.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-13 | -171 | -122 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-11-06 | 2024-08-29 | IOU Designed & Installed | N/A | No | N/A | 55688.35 | 2016.41 | Unknown | Unknown | 40.05 | 53631.89 | 0 | 18872.72 | 55688.35 | -36815.63 | Yes | N/A | N/A | 2023-10-30 | 2023-11-02 | 4 | 4 | 2023-11-02 | 2024-06-26 | 238 | 170 | Unknown | Unknown | Unknown | Unknown | 2024-05-04 | 2024-07-08 | 41 | 29 | 2024-06-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-10-24 | 1900-02-25 | 41 | 2024-10-24 | 2024-10-24 | 1 | 1 | 4 | 4 | 337 | 241 | 341 | 245 | Steps 2,3,5,6,7 | 12 | 8 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-01 | -348 | -249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-02-26 | 2024-07-16 | IOU Designed & Installed | N/A | No | N/A | 14.18 | -10.92 | Unknown | Unknown | Unknown | 25.1 | 3981 | 789.82 | 14.18 | 775.64 | Yes | N/A | N/A | 2024-02-26 | 2024-01-24 | Unknown | Unknown | 2024-01-24 | 2024-06-05 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-05 | 2025-04-21 | 321 | 229 | Unknown | Unknown | Unknown | Unknown | 2024-07-16 | 2024-07-19 | 1900-01-03 | 4 | 2024-07-19 | 2024-07-18 | Unknown | Unknown | 321 | 229 | 138 | 100 | 459 | 329 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 916 | 916 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-15 | -464 | -333 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-08 | 2024-01-23 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | -14.9 | -12.11 | Unknown | Unknown | Unknown | -2.79 | 3981 | 1732.66 | -14.9 | 1747.56 | Yes | N/A | N/A | 2023-12-08 | 2023-09-27 | Unknown | Unknown | 2023-09-27 | 2024-01-23 | 119 | 85 | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-04-22 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-05-09 | 1900-01-17 | 14 | 2024-05-09 | 2024-05-08 | Unknown | Unknown | 90 | 64 | 137 | 99 | 227 | 163 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 684 | 684 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -576 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-25 | 2024-10-25 | 2024-11-04 | IOU Designed & Installed | N/A | No | N/A | 1653.46 | 367.51 | Unknown | Unknown | Unknown | 1285.95 | Unknown | 1619.31 | 1653.46 | -34.15 | Yes | N/A | N/A | 2024-10-25 | 2024-08-15 | Unknown | Unknown | 2024-08-15 | 2024-10-25 | 72 | 52 | 2024-10-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-25 | 2024-11-04 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2024-12-02 | 1900-01-28 | 21 | 2024-12-02 | 2024-12-02 | 1 | 1 | 11 | 7 | 102 | 74 | 113 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-24 | -301 | -216 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | -561.73 | 940.68 | Unknown | 44.72 | -2121 | 573.87 | Unknown | 2120.56 | -561.73 | 2682.29 | Yes | N/A | N/A | 2024-08-14 | 2024-08-13 | Unknown | Unknown | 2024-08-13 | 2024-09-20 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-09-26 | 1900-01-03 | 4 | 2024-09-26 | 2024-09-26 | 1 | 1 | 0 | 0 | 44 | 34 | 44 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community,Tribal Community | SANTA YSABEL | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-07 | -293 | -210 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-12-04 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 809.18 | Unknown | Unknown | Yes | N/A | N/A | 2023-11-21 | 2023-12-04 | 14 | 10 | 2023-12-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-09-10 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2025-07-18 | 1900-11-07 | 224 | 2025-07-18 | 2024-09-17 | Unknown | Unknown | 85 | 61 | 312 | 224 | 397 | 285 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-01 | -196 | -141 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-07-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12.53 | Unknown | Unknown | Unknown | Unknown | 12.53 | Unknown | 1029.85 | 12.53 | 1017.32 | Yes | N/A | N/A | 2024-04-04 | 2024-07-30 | 118 | 84 | 2024-07-30 | 2024-08-14 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-17 | Unknown | Unknown | 2024-09-17 | 2024-09-17 | 1 | 1 | 118 | 84 | 17 | 13 | 135 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-10 | -542 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-06 | 2023-01-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -20.15 | -15.48 | Unknown | Unknown | Unknown | -4.67 | 3981 | 98.41 | -20.15 | 118.56 | Yes | N/A | N/A | 2023-01-06 | 2023-02-28 | 54 | 38 | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 54 | 38 | 1 | 1 | 55 | 39 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-11 | -65 | -48 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-19 | 2022-10-20 | Unknown | IOU Designed & Installed | N/A | No | N/A | 866.22 | -12.99 | Unknown | Unknown | 14.19 | 865.02 | 3981 | 528.72 | 866.22 | -337.5 | Yes | N/A | N/A | 2022-10-19 | 2023-02-14 | 119 | 85 | 2023-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-11-01 | Unknown | Unknown | Unknown | Unknown | 2023-05-09 | Unknown | Unknown | Unknown | 2023-06-07 | Unknown | Unknown | 2023-06-07 | 2023-06-07 | 1 | 1 | 119 | 85 | 1 | 1 | 120 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 77.05 | 77.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-14 | -350 | -251 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-11 | 2023-11-11 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | -4.2 | -3.4 | Unknown | Unknown | Unknown | -0.8 | 3981 | 1135.58 | -4.2 | 1139.78 | Yes | N/A | N/A | 2023-11-11 | 2023-11-11 | 1 | 0 | 2023-11-11 | 2023-11-11 | 1 | 0 | 2023-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-11 | 2024-04-17 | 159 | 113 | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-05-02 | 1900-01-15 | 12 | 2024-05-02 | 2024-04-29 | Unknown | Unknown | 160 | 113 | 17 | 12 | 177 | 125 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-30 | -617 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | 2024-10-30 | IOU Designed & Installed | N/A | No | N/A | 1187.55 | Unknown | Unknown | Unknown | 2.45 | 1185.1 | 3981 | 1150.97 | 1187.55 | -36.58 | Yes | N/A | N/A | 2024-09-05 | 2024-10-01 | 27 | 19 | 2024-10-01 | 2024-10-02 | 2 | 2 | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-10-30 | 29 | 21 | Unknown | 2024-10-30 | Unknown | Unknown | 2024-10-30 | 2024-11-20 | 1900-01-21 | 16 | 2024-11-20 | 2024-11-20 | 1 | 1 | 56 | 40 | 25 | 19 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-18 | -331 | -237 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-06-02 | 2023-06-19 | IOU Designed & Installed | N/A | No | N/A | 4071.76 | 1379.55 | Unknown | 323 | Unknown | 2369.21 | 3981 | 960.53 | 4071.76 | -3111.23 | Yes | N/A | N/A | 2023-06-02 | 2023-06-02 | 1 | 1 | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | 2023-06-19 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | 2023-06-22 | 1900-01-03 | 4 | 2023-06-22 | 2023-06-22 | 1 | 1 | 19 | 13 | 5 | 5 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-09 | -226 | -163 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-20 | 2023-05-25 | 2023-06-09 | IOU Designed & Installed | N/A | No | N/A | -3.89 | -11.47 | Unknown | Unknown | Unknown | 7.58 | 3241 | 803.72 | -3.89 | 807.61 | Yes | N/A | N/A | 2023-03-20 | 2023-05-25 | 67 | 49 | 2023-05-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-25 | 2023-06-09 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-06-09 | 2023-06-28 | 1900-01-19 | 14 | 2023-06-28 | 2023-06-28 | 1 | 1 | 83 | 61 | 21 | 15 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-05 | -40 | -30 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-06-20 | 2025-02-11 | IOU Designed & Installed | N/A | No | N/A | -54.92 | Unknown | Unknown | Unknown | -1090.06 | 1035.14 | Unknown | 1096.01 | -54.92 | 1150.93 | Yes | N/A | N/A | 2024-05-14 | 2024-07-08 | 56 | 40 | 2024-07-08 | 2024-07-10 | 3 | 3 | 2024-07-10 | 2024-10-04 | 87 | 63 | 2024-12-27 | 2024-12-30 | 4 | 2 | 2024-10-04 | 2025-02-11 | 131 | 93 | Unknown | 2025-01-02 | Unknown | Unknown | 2025-02-11 | 2025-03-05 | 1900-01-22 | 17 | 2025-03-05 | 2025-02-24 | Unknown | Unknown | 274 | 196 | 30 | 22 | 304 | 218 | Steps 2,3,5,6,7 | 87 | 61 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 98 | 98 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-20 | -578 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-09 | 2025-01-24 | IOU Designed & Installed | N/A | No | N/A | 305.26 | -6.14 | Unknown | Unknown | Unknown | 311.4 | 3981 | 1777.34 | 305.26 | 1472.08 | Yes | N/A | N/A | 2025-01-09 | 2025-01-09 | 1 | 1 | 2025-01-09 | 2025-01-10 | 2 | 2 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-01-24 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-02-19 | 1900-01-26 | 19 | 2025-02-19 | 2025-02-19 | 1 | 1 | 16 | 12 | 30 | 22 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-22 | -197 | -141 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-30 | 2024-05-30 | 2024-08-06 | IOU Designed & Installed | N/A | No | N/A | -2655.87 | 1341.78 | Unknown | 662.55 | -5650 | 989.8 | Unknown | 5650.07 | -2655.87 | 8305.94 | Yes | N/A | N/A | 2024-05-30 | 2024-06-19 | 21 | 15 | 2024-06-19 | 2024-07-22 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-08-08 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-09 | 1900-01-03 | 4 | 2024-08-09 | 2024-08-09 | 1 | 1 | 39 | 29 | 39 | 29 | 78 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-30 | -501 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-03-11 | 2024-04-05 | IOU Designed & Installed | N/A | No | N/A | 125.62 | -4.4 | Unknown | Unknown | Unknown | 130.02 | Unknown | 912.75 | 125.62 | 787.13 | Yes | N/A | N/A | 2024-02-20 | 2024-03-04 | 14 | 10 | 2024-03-04 | 2024-03-11 | 8 | 6 | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | 2024-04-05 | 26 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-04-16 | 1900-01-11 | 8 | 2024-04-16 | 2024-04-16 | 1 | 1 | 40 | 30 | 21 | 15 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | -233 | -168 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | 2023-05-03 | IOU Designed & Installed | N/A | No | N/A | 460.61 | -16.44 | Unknown | Unknown | Unknown | 477.05 | Unknown | 670.81 | 460.61 | 210.2 | Yes | N/A | N/A | 2023-03-21 | 2023-03-21 | 1 | 1 | 2023-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-21 | 2023-05-03 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2023-05-03 | 2023-06-13 | 1900-02-10 | 30 | 2023-06-13 | 2023-06-13 | 1 | 1 | 45 | 33 | 43 | 31 | 88 | 64 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-02 | 5 | 4 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-16 | 2024-03-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 53.1 | Unknown | Unknown | Unknown | Unknown | 53.1 | 3981 | 1046.11 | 53.1 | 993.01 | Yes | N/A | N/A | 2024-02-16 | 2024-03-06 | 20 | 14 | 2024-03-06 | 2024-06-19 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-03-29 | 11 | 9 | 2024-06-19 | 2024-07-31 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-11-07 | Unknown | Unknown | 63 | 45 | 117 | 85 | 180 | 130 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-25 | -172 | -124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-27 | 2023-12-05 | IOU Designed & Installed | N/A | No | N/A | 1003.33 | 352.7 | Unknown | Unknown | Unknown | 650.63 | 3981 | 1049.75 | 1003.33 | 46.42 | Yes | N/A | N/A | 2023-10-12 | 2023-10-27 | 16 | 12 | 2023-10-27 | 2023-10-27 | 1 | 1 | 2023-10-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2023-12-05 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-12-05 | 2023-12-05 | 1899-12-31 | 1 | 2023-12-05 | 2023-12-05 | 1 | 1 | 56 | 40 | 3 | 3 | 59 | 43 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-15 | -395 | -284 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-15 | 2023-08-15 | 2024-03-12 | IOU Designed & Installed | N/A | No | N/A | 322.21 | 189.35 | Unknown | Unknown | Unknown | 132.86 | Unknown | 148.7 | 322.21 | -173.51 | Yes | N/A | N/A | 2023-08-15 | 2023-09-01 | 18 | 14 | 2023-09-01 | 2023-09-01 | 1 | 1 | 2023-09-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-01 | 2024-03-12 | 194 | 138 | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-04-15 | 1900-02-03 | 25 | 2024-04-15 | 2024-04-15 | 1 | 1 | 212 | 152 | 37 | 27 | 249 | 179 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-05 | -592 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-06 | Unknown | 2024-10-10 | IOU Designed & Installed | N/A | No | N/A | 2217.42 | -43.93 | Unknown | Unknown | Unknown | 2261.35 | 3981 | 1834.9 | 2217.42 | -382.52 | Yes | N/A | N/A | 2024-08-06 | 2024-08-06 | 1 | 1 | 2024-08-06 | 2024-08-06 | 1 | 1 | 2024-08-06 | Unknown | Unknown | Unknown | 2024-08-07 | 2024-09-13 | 38 | 28 | 2024-08-06 | 2024-10-10 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-11-20 | 1900-02-10 | 30 | 2024-11-20 | 2024-11-20 | 1 | 1 | 67 | 49 | 82 | 60 | 149 | 109 | Steps 2,3,5,6,7 | 38 | 28 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 107 | 107 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-08-05 | 775 | 554 | No | 2021-12-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-12-06 | 2021-12-07 | 2023-07-17 | IOU Designed & Installed | N/A | Yes | 587 | 1148.23 | -17.33 | Unknown | Unknown | 41.96 | 1123.6 | 6482 | 698.08 | 1148.23 | -450.15 | Yes | N/A | N/A | 2021-12-06 | 2023-07-17 | 589 | 421 | 2023-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-12-07 | 2023-07-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-17 | 2023-09-19 | 1900-03-05 | 47 | 2023-09-19 | 2023-09-19 | 1 | 1 | 589 | 421 | 66 | 48 | 655 | 469 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-05 | -569 | -406 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-20 | 2024-01-17 | 2024-01-31 | IOU Designed & Installed | N/A | No | N/A | 14.42 | -12.86 | Unknown | Unknown | Unknown | 27.28 | Unknown | 1043.73 | 14.42 | 1029.31 | Yes | N/A | N/A | 2023-12-20 | 2024-01-17 | 29 | 21 | 2024-01-17 | 2024-01-17 | 1 | 1 | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | 2024-01-31 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-03-15 | 1900-02-13 | 33 | 2024-03-15 | 2024-03-15 | 1 | 1 | 44 | 32 | 47 | 35 | 91 | 67 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -647 | -464 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-03 | 2024-06-03 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 754.15 | 246.68 | Unknown | Unknown | Unknown | 507.47 | 3981 | 1440.48 | 754.15 | 686.33 | Yes | N/A | N/A | 2024-06-03 | 2024-06-03 | 1 | 1 | 2024-06-03 | 2024-06-03 | 1 | 1 | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-02 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-08-06 | 1900-02-04 | 26 | 2024-08-06 | 2024-08-06 | 1 | 1 | 2 | 2 | 38 | 28 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | La Mesa | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-09 | -57 | -42 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-07 | 2023-02-07 | 2023-03-28 | IOU Designed & Installed | N/A | No | N/A | 5555.55 | 78.56 | Unknown | Unknown | Unknown | 5476.99 | Unknown | 889.13 | 5555.55 | -4666.42 | Yes | N/A | N/A | 2023-02-07 | 2023-03-22 | 44 | 32 | 2023-03-22 | 2023-03-30 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | 2023-03-24 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | 2023-09-13 | 1900-06-18 | 122 | 2023-09-13 | 2023-09-13 | 1 | 1 | 44 | 32 | 181 | 131 | 225 | 163 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | -262 | -189 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-30 | 2023-05-01 | 2023-05-22 | IOU Designed & Installed | N/A | No | N/A | -10.99 | -7.96 | Unknown | Unknown | Unknown | -3.03 | Unknown | 495.75 | -10.99 | 506.74 | Yes | N/A | N/A | 2023-04-30 | 2023-04-30 | 1 | 0 | 2023-04-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | 2023-05-22 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-05-22 | 2023-06-13 | 1900-01-22 | 17 | 2023-06-13 | 2023-06-13 | 1 | 1 | 23 | 16 | 24 | 18 | 47 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | -231 | -166 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 203.53 | -8.05 | Unknown | Unknown | Unknown | 211.58 | Unknown | 154.72 | 203.53 | -48.81 | Yes | N/A | N/A | 2024-02-02 | 2024-02-15 | 14 | 10 | 2024-02-15 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-15 | 1 | 1 | 14 | 10 | 1 | 1 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 252 | 252 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-05 | 732 | 525 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-21 | 2025-05-06 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | 1605.86 | Unknown | Unknown | Unknown | Unknown | 1605.86 | 0 | 1569.16 | 1605.86 | -36.7 | Yes | N/A | N/A | 2025-03-21 | 2024-04-16 | Unknown | Unknown | 2024-04-16 | 2025-06-02 | 413 | 295 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-06-06 | 1900-01-01 | 2 | 2025-06-06 | 2025-06-06 | 1 | 1 | 0 | 0 | 416 | 298 | 416 | 298 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-26 | -301 | -216 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | 2025-05-29 | IOU Designed & Installed | N/A | No | N/A | 269.53 | 1367.06 | Unknown | Unknown | -1646 | 548.47 | Unknown | 1645.6 | 269.53 | 1376.07 | Yes | N/A | N/A | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-29 | 2025-05-29 | 1899-12-31 | 1 | 2025-05-29 | 2025-05-29 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-13 | -611 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-15 | 2024-05-01 | 2024-05-08 | IOU Designed & Installed | N/A | No | N/A | 927.87 | 244.9 | Unknown | 143.08 | Unknown | 539.89 | 3981 | 685.65 | 927.87 | -242.22 | Yes | N/A | N/A | 2024-04-15 | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-05-01 | 63 | 45 | 2024-05-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-01 | 2024-05-08 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2024-06-12 | 1900-02-04 | 26 | 2024-06-12 | 2024-06-12 | 1 | 1 | 8 | 6 | 100 | 72 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-01 | -544 | -389 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-30 | 2023-09-29 | 2023-11-29 | IOU Designed & Installed | N/A | No | N/A | 2154.47 | 757.38 | Unknown | Unknown | Unknown | 1397.09 | 3981 | 900.17 | 2154.47 | -1254.3 | Yes | N/A | N/A | 2023-08-30 | 2023-06-13 | Unknown | Unknown | 2023-06-13 | 2023-09-29 | 109 | 79 | 2023-09-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-29 | 2023-11-29 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2023-11-29 | 2023-12-05 | 1900-01-06 | 5 | 2023-12-05 | 2023-12-05 | 1 | 1 | 62 | 44 | 117 | 85 | 179 | 129 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | El Cajon | El Cajon | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-23 | 40 | 29 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-30 | 2025-01-28 | 2025-04-23 | IOU Designed & Installed | N/A | No | N/A | 37730.61 | 3558.34 | Unknown | Unknown | 35.66 | 34136.61 | Unknown | 41925.09 | 37730.61 | 4194.48 | Yes | N/A | N/A | 2024-12-30 | 2024-12-30 | 1 | 1 | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-04-16 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-06-02 | 1900-02-09 | 29 | 2025-06-02 | 2025-06-02 | 1 | 1 | 1 | 1 | 76 | 54 | 77 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 317 | 317 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-29 | 212 | 153 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-14 | 2024-08-28 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | -687.56 | Unknown | Unknown | Unknown | -746 | 58.44 | 3981 | 2074.82 | -687.56 | 2762.38 | Yes | N/A | N/A | 2023-06-14 | 2023-05-12 | Unknown | Unknown | 2023-05-12 | 2024-12-19 | 588 | 420 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-10 | 5 | 3 | 2024-12-19 | 2025-02-07 | 51 | 37 | Unknown | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-02-27 | 1900-01-07 | 6 | 2025-02-27 | 2025-02-26 | Unknown | Unknown | 51 | 37 | 601 | 429 | 652 | 466 | Steps 2,3,5,6,7 | 53 | 37 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-07 | -295 | -212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-01 | 2023-12-06 | IOU Designed & Installed | N/A | No | N/A | -5.19 | -4.09 | Unknown | Unknown | Unknown | -1.1 | Unknown | 499.18 | -5.19 | 504.37 | Yes | N/A | N/A | 2023-12-01 | 2023-11-21 | Unknown | Unknown | 2023-11-21 | 2023-12-01 | 11 | 9 | 2023-12-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-01 | 2023-12-06 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-12-06 | 2024-01-17 | 1900-02-11 | 31 | 2024-01-17 | 2024-01-17 | 1 | 1 | 6 | 4 | 55 | 41 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-04 | -625 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-27 | 2025-02-27 | 2025-03-06 | IOU Designed & Installed | N/A | No | N/A | 556.98 | -20.29 | Unknown | Unknown | Unknown | 577.27 | Unknown | 1200.26 | 556.98 | 643.28 | Yes | N/A | N/A | 2025-02-27 | 2025-03-04 | 6 | 4 | 2025-03-04 | 2025-03-04 | 1 | 1 | 2025-03-04 | 2025-04-25 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-03-04 | 2025-03-06 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-05-20 | 1900-03-16 | 54 | 2025-05-20 | 2025-05-20 | 1 | 1 | 62 | 46 | 78 | 56 | 140 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-13 | -458 | -329 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-09 | 2023-10-30 | IOU Designed & Installed | N/A | No | N/A | -208.04 | -10.64 | Unknown | Unknown | -889.38 | 691.98 | Unknown | 902.45 | -208.04 | 1110.49 | Yes | N/A | N/A | 2023-06-06 | 2023-04-14 | Unknown | Unknown | 2023-04-14 | 2023-08-14 | 123 | 87 | 2023-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | 2023-10-30 | 13 | 9 | Unknown | 2023-10-18 | Unknown | Unknown | 2023-10-30 | 2023-12-11 | 1900-02-11 | 31 | 2023-12-11 | 2023-12-11 | 1 | 1 | 13 | 9 | 167 | 119 | 180 | 128 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | -499 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-17 | 2023-05-18 | 2023-08-04 | IOU Designed & Installed | N/A | No | N/A | 129.16 | -26.12 | Unknown | Unknown | Unknown | 155.28 | Unknown | 153.75 | 129.16 | 24.59 | Yes | N/A | N/A | 2023-05-17 | 2023-06-16 | 31 | 23 | 2023-06-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-08-04 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | 2023-08-04 | 2023-10-17 | 1900-03-15 | 53 | 2023-10-17 | 2023-10-17 | 1 | 1 | 81 | 59 | 76 | 54 | 157 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-05 | -584 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-03-18 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | 378.33 | -3.41 | Unknown | Unknown | 6.85 | 374.89 | 3981 | 850.88 | 378.33 | 472.55 | Yes | N/A | N/A | 2024-03-18 | 2024-03-19 | 2 | 2 | 2024-03-19 | 2024-03-21 | 3 | 3 | 2024-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-05-17 | 58 | 42 | Unknown | 2024-05-14 | Unknown | Unknown | 2024-05-17 | 2024-06-03 | 1900-01-17 | 12 | 2024-06-03 | 2024-05-31 | Unknown | Unknown | 60 | 44 | 21 | 15 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-19 | -605 | -434 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-19 | 2024-12-19 | 2025-03-12 | IOU Designed & Installed | N/A | No | N/A | 1234.37 | -24.15 | Unknown | Unknown | Unknown | 1258.52 | 3981 | 1628.9 | 1234.37 | 394.53 | Yes | N/A | N/A | 2024-12-19 | 2024-12-18 | Unknown | Unknown | 2024-12-18 | 2024-12-20 | 3 | 3 | 2024-12-20 | Unknown | Unknown | Unknown | 2024-12-26 | 2025-01-30 | 36 | 26 | 2024-12-20 | 2025-03-12 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2025-03-12 | 2025-03-24 | 1900-01-12 | 9 | 2025-03-24 | 2025-03-24 | 1 | 1 | 83 | 59 | 53 | 39 | 136 | 98 | Steps 2,3,5,6,7 | 41 | 29 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-27 | 308 | 221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-04-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 0 | 2596.76 | Unknown | Unknown | Yes | N/A | N/A | 2023-04-26 | 2023-05-03 | 8 | 6 | 2023-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | 2024-09-30 | 2024-09-30 | 1 | 1 | 8 | 6 | 1 | 1 | 9 | 7 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | SAN DIEGO | 20 | 20 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-01 | 672 | 481 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-04-30 | 2024-07-29 | IOU Designed & Installed | N/A | No | N/A | 6059.74 | 454.5 | Unknown | Unknown | 8.68 | 5596.56 | Unknown | 19047.62 | 6059.74 | 12987.88 | Yes | N/A | N/A | 2024-03-19 | 2024-04-10 | 23 | 17 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-07-18 | 40 | 30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-29 | 2024-09-03 | 1900-02-05 | 27 | 2024-09-03 | 2024-09-03 | 1 | 1 | 23 | 17 | 78 | 58 | 101 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-04 | -515 | -368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-30 | 2023-11-14 | 2023-12-19 | IOU Designed & Installed | N/A | No | N/A | 4.4 | -5.54 | Unknown | Unknown | Unknown | 9.94 | 3981 | 909.98 | 4.4 | 905.58 | Yes | N/A | N/A | 2023-10-30 | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-11-14 | 89 | 63 | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2023-12-19 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-03-07 | 1900-03-20 | 58 | 2024-03-07 | 2024-03-07 | 1 | 1 | 36 | 26 | 170 | 122 | 206 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 122.05 | 122.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-28 | -425 | -304 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | 2024-07-09 | IOU Designed & Installed | N/A | No | N/A | 1107.55 | Unknown | Unknown | Unknown | 9.54 | 1098.01 | 3981 | 766.01 | 1107.55 | -341.54 | Yes | N/A | N/A | 2023-12-18 | 2023-10-10 | Unknown | Unknown | 2023-10-10 | 2024-02-29 | 143 | 103 | 2024-02-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | 2024-07-09 | 132 | 94 | Unknown | 2024-06-20 | Unknown | Unknown | 2024-07-09 | 2024-07-30 | 1900-01-21 | 16 | 2024-07-30 | 2024-07-30 | 1 | 1 | 132 | 94 | 166 | 120 | 298 | 214 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | -288 | -207 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-24 | 2023-04-24 | 2023-10-02 | IOU Designed & Installed | N/A | No | N/A | 235.48 | 85.61 | Unknown | Unknown | Unknown | 149.87 | 3981 | 666.84 | 235.48 | 431.36 | Yes | N/A | N/A | 2023-04-24 | 2023-04-24 | 1 | 1 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | 2023-10-02 | 162 | 116 | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2023-10-18 | 1900-01-16 | 13 | 2023-10-18 | 2023-10-18 | 1 | 1 | 163 | 117 | 18 | 14 | 181 | 131 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 204 | 204 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-12-31 | 746 | 533 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | 2023-08-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1547.82 | Unknown | Unknown | Unknown | Unknown | 1547.82 | 3981 | 889.06 | 1547.82 | -658.76 | Yes | N/A | N/A | 2023-08-24 | 2023-03-18 | Unknown | Unknown | 2023-03-18 | 2023-10-06 | 203 | 145 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-06 | 2024-02-23 | 141 | 101 | Unknown | 2025-01-06 | Unknown | Unknown | Unknown | 2025-01-16 | Unknown | Unknown | 2025-01-16 | 2025-01-15 | Unknown | Unknown | 141 | 101 | 203 | 145 | 344 | 246 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 140.05 | 140.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-05 | -77 | -56 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-23 | 2024-05-06 | 2024-11-11 | IOU Designed & Installed | N/A | No | N/A | 660.19 | 254.7 | Unknown | 107.89 | -406 | 703.6 | 3981 | 1138.52 | 660.19 | 478.33 | Yes | N/A | N/A | 2024-04-23 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-05-06 | 41 | 29 | 2024-05-06 | 2024-05-21 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2024-11-11 | 175 | 125 | Unknown | 2024-09-11 | Unknown | Unknown | 2024-11-11 | 2024-11-20 | 1900-01-09 | 8 | 2024-11-20 | 2024-11-20 | 1 | 1 | 191 | 137 | 52 | 38 | 243 | 175 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-26 | -297 | -214 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-23 | 2025-04-23 | 2025-06-02 | IOU Designed & Installed | N/A | No | N/A | 3174.73 | 3430.38 | Unknown | Unknown | -1646 | 1390.35 | Unknown | 1645.6 | 3174.73 | -1529.13 | Yes | N/A | N/A | 2025-04-23 | 2025-04-23 | 1 | 1 | 2025-04-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-06-02 | 1899-12-31 | 1 | 2025-06-02 | 2025-06-02 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-07 | 237 | 170 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | 2023-05-01 | IOU Designed & Installed | N/A | No | N/A | -3.35 | -9.83 | Unknown | Unknown | Unknown | 6.48 | 3981 | 786.58 | -3.35 | 789.93 | Yes | N/A | N/A | 2023-03-23 | 2023-03-23 | 1 | 1 | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | 2023-05-01 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-05-01 | 2023-08-14 | 1900-04-15 | 76 | 2023-08-14 | 2023-05-02 | Unknown | Unknown | 41 | 29 | 106 | 76 | 147 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-31 | -442 | -316 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-09-10 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 949.22 | Unknown | Unknown | Unknown | Unknown | 949.22 | 3981 | 1076.2 | 949.22 | 126.98 | Yes | N/A | N/A | 2024-03-27 | 2024-08-08 | 135 | 97 | 2024-08-08 | 2024-09-10 | 34 | 24 | 2024-09-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-11-07 | 59 | 43 | Unknown | 2024-10-24 | Unknown | Unknown | 2024-11-07 | 2024-11-15 | 1900-01-08 | 7 | 2024-11-15 | 2024-11-15 | 1 | 1 | 194 | 140 | 44 | 32 | 238 | 172 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | 17 | 17 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-03 | -638 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-27 | 2025-05-30 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1700.33 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-25 | 2025-03-10 | Unknown | Unknown | 2025-03-10 | 2025-03-27 | 18 | 14 | 2025-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-27 | 2025-05-30 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-05-30 | 2025-06-03 | 1900-01-04 | 3 | 2025-06-03 | 2025-06-03 | 1 | 1 | 65 | 47 | 24 | 18 | 89 | 65 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | -703 | -504 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-10 | 2024-07-10 | 2024-07-15 | IOU Designed & Installed | N/A | No | N/A | 79.57 | Unknown | Unknown | Unknown | Unknown | 79.57 | 3981 | 1359.92 | 79.57 | 1280.35 | Yes | N/A | N/A | 2024-07-10 | 2024-07-10 | 1 | 1 | 2024-07-10 | 2024-07-10 | 1 | 1 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-07-15 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | 2024-07-22 | 1900-01-07 | 6 | 2024-07-22 | 2024-07-22 | 1 | 1 | 7 | 5 | 10 | 8 | 17 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-04 | -597 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-03-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 196.67 | -13.99 | Unknown | Unknown | 2.03 | 208.63 | 3981 | 594.9 | 196.67 | 398.23 | Yes | N/A | N/A | 2023-03-22 | 2023-03-28 | 7 | 5 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 7 | 5 | 1 | 1 | 8 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-27 | -705 | -504 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | 2025-01-30 | 2025-02-13 | IOU Designed & Installed | N/A | No | N/A | 1384.14 | -26.88 | Unknown | Unknown | Unknown | 1411.02 | 3981 | 946.19 | 1384.14 | -437.95 | Yes | N/A | N/A | 2025-01-27 | 2025-01-27 | 1 | 1 | 2025-01-27 | 2025-01-30 | 4 | 4 | 2025-01-30 | Unknown | Unknown | Unknown | 2025-01-27 | 2025-01-30 | 4 | 4 | 2025-01-30 | 2025-02-13 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-02-21 | 1900-01-08 | 7 | 2025-02-21 | 2025-02-21 | 1 | 1 | 16 | 12 | 18 | 16 | 34 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-20 | -396 | -284 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-19 | 2023-07-01 | 2023-10-09 | IOU Designed & Installed | N/A | No | N/A | 1471.38 | -35.36 | Unknown | Unknown | -943 | 2449.74 | Unknown | 954.01 | 1471.38 | -517.37 | Yes | N/A | N/A | 2023-06-19 | 2023-07-01 | 13 | 10 | 2023-07-01 | 2023-07-01 | 1 | 0 | 2023-07-01 | 2023-10-09 | 101 | 71 | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2023-10-09 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-10-09 | 2024-01-21 | 1900-04-14 | 75 | 2024-01-21 | 2024-01-21 | 1 | 0 | 115 | 82 | 107 | 75 | 222 | 157 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-27 | -681 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-25 | 2024-07-26 | IOU Designed & Installed | N/A | No | N/A | 7.2 | Unknown | Unknown | Unknown | Unknown | 7.2 | Unknown | 186.09 | 7.2 | 178.89 | Yes | N/A | N/A | 2024-07-24 | 2024-07-09 | Unknown | Unknown | 2024-07-09 | 2024-07-24 | 16 | 12 | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-25 | 2024-07-26 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | 2024-08-15 | 1900-01-20 | 15 | 2024-08-15 | 2024-08-15 | 1 | 1 | 2 | 2 | 38 | 28 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 1 | 1 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-28 | -8 | -6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-03 | 2024-01-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1045.43 | -20.4 | Unknown | Unknown | Unknown | 1065.83 | 0 | 839.18 | 1045.43 | -206.25 | Yes | N/A | N/A | 2024-01-03 | 2023-11-02 | Unknown | Unknown | 2023-11-02 | 2024-01-03 | 63 | 45 | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-20 | Unknown | Unknown | 2024-09-20 | 2024-09-20 | 1 | 1 | 0 | 0 | 64 | 46 | 64 | 46 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-05 | -597 | -428 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-09 | 2024-10-09 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | 20.69 | Unknown | Unknown | Unknown | Unknown | 20.69 | 3981 | 1571.57 | 20.69 | 1550.88 | Yes | N/A | N/A | 2024-10-09 | 2024-10-23 | 15 | 11 | 2024-10-23 | 2024-10-29 | 7 | 5 | 2024-10-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-11-15 | 18 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2024-12-16 | 1900-01-31 | 22 | 2024-12-16 | 2024-12-16 | 1 | 1 | 33 | 25 | 40 | 28 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | 33.05 | 33.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-12 | -624 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-05-12 | 2025-06-16 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1104.62 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-12 | 2025-04-22 | Unknown | Unknown | 2025-04-22 | 2025-05-12 | 21 | 15 | 2025-05-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-06-16 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-06-26 | 1900-01-10 | 9 | 2025-06-26 | 2025-06-26 | 1 | 1 | 36 | 26 | 33 | 25 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 19 | 19 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-12-30 | -958 | -685 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-04-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1623.73 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2025-04-11 | 60 | 44 | 2025-04-11 | 2025-04-14 | 4 | 2 | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | Unknown | Unknown | 2025-05-16 | 2025-05-16 | 1 | 1 | 60 | 44 | 5 | 3 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-22 | -568 | -407 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-16 | 2025-01-06 | 2025-02-27 | IOU Designed & Installed | N/A | No | N/A | 972.08 | -38.8 | Unknown | Unknown | 1.72 | 1009.16 | 3981 | 1306.91 | 972.08 | 334.83 | Yes | N/A | N/A | 2024-12-16 | 2025-01-06 | 22 | 16 | 2025-01-06 | 2025-01-06 | 1 | 1 | 2025-01-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | 2025-02-27 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-04-03 | 1900-02-04 | 26 | 2025-04-03 | 2025-04-02 | Unknown | Unknown | 75 | 55 | 37 | 27 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-29 | -37 | -28 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-14 | 2023-02-14 | 2024-10-22 | IOU Designed & Installed | N/A | No | N/A | 2964.86 | 502.72 | Unknown | 35.51 | 18.97 | 2407.66 | 0 | 1566.59 | 2964.86 | -1398.27 | Yes | N/A | N/A | 2023-02-14 | 2023-03-20 | 35 | 25 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-20 | 2024-10-22 | 583 | 417 | Unknown | 2024-10-14 | Unknown | Unknown | 2024-10-22 | 2024-10-23 | 1900-01-01 | 2 | 2024-10-23 | 2024-10-23 | 1 | 1 | 618 | 442 | 3 | 3 | 621 | 445 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 69.05 | 69.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-04 | -543 | -388 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | 2023-10-27 | IOU Designed & Installed | N/A | No | N/A | 0.43 | -12.73 | Unknown | Unknown | Unknown | 13.16 | 3981 | 795.89 | 0.43 | 795.46 | Yes | N/A | N/A | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | 2023-09-11 | 1 | 1 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-11 | 2023-10-27 | 47 | 35 | Unknown | Unknown | Unknown | Unknown | 2023-10-27 | 2023-11-08 | 1900-01-12 | 9 | 2023-11-08 | 2023-11-08 | 1 | 1 | 48 | 36 | 15 | 11 | 63 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-02 | -86 | -63 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | -5.44 | -10.44 | Unknown | Unknown | Unknown | 5 | 3981 | 668.06 | -5.44 | 673.5 | Yes | N/A | N/A | 2023-02-28 | 2023-03-29 | 30 | 22 | 2023-03-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-29 | 2023-07-26 | 120 | 86 | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-08-08 | 1900-01-13 | 10 | 2023-08-08 | 2023-08-08 | 1 | 1 | 150 | 108 | 15 | 11 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 192.05 | 192.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-02 | 156 | 113 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-03 | 2024-05-23 | IOU Designed & Installed | N/A | No | N/A | 18.33 | -16.27 | Unknown | Unknown | Unknown | 34.6 | Unknown | 1039.03 | 18.33 | 1020.7 | Yes | N/A | N/A | 2024-04-30 | 2024-03-21 | Unknown | Unknown | 2024-03-21 | 2024-05-03 | 44 | 32 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-05-23 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-06-07 | 1900-01-15 | 12 | 2024-06-07 | 2024-06-06 | Unknown | Unknown | 21 | 15 | 60 | 44 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-24 | -631 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-08 | 2024-07-08 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 72.77 | Unknown | Unknown | Unknown | Unknown | 72.77 | 3981 | 1447.53 | 72.77 | 1374.76 | Yes | N/A | N/A | 2024-07-08 | 2024-07-08 | 1 | 1 | 2024-07-08 | 2024-07-08 | 1 | 1 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-09-10 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-10-01 | 1900-01-21 | 16 | 2024-10-01 | 2024-10-01 | 1 | 1 | 66 | 48 | 24 | 18 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | -651 | -466 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-20 | 2024-05-20 | 2024-05-29 | IOU Designed & Installed | N/A | No | N/A | 445.21 | -4.61 | Unknown | Unknown | Unknown | 449.82 | 3981 | 496.14 | 445.21 | 50.93 | Yes | N/A | N/A | 2024-05-20 | 2024-05-20 | 1 | 1 | 2024-05-20 | 2024-04-08 | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-05-29 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-05-31 | 1900-01-02 | 3 | 2024-05-31 | 2024-05-31 | 1 | 1 | 11 | 9 | 4 | 4 | 15 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-04-23 | -13 | -10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-30 | 2024-05-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 232.76 | -8.57 | Unknown | Unknown | Unknown | 241.33 | 0 | 468.05 | 232.76 | 235.29 | Yes | N/A | N/A | 2024-04-30 | 2024-05-02 | 3 | 3 | 2024-05-02 | 2024-07-01 | 61 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-06-18 | 28 | 20 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | Unknown | Unknown | 2025-04-10 | 2025-04-10 | 1 | 1 | 3 | 3 | 90 | 64 | 93 | 67 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 44.05 | 44.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-29 | -563 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-15 | 2024-01-23 | 2024-02-09 | IOU Designed & Installed | N/A | No | N/A | 353.46 | -29.01 | Unknown | Unknown | Unknown | 382.47 | Unknown | 1372.61 | 353.46 | 1019.15 | Yes | N/A | N/A | 2023-12-15 | 2023-10-05 | Unknown | Unknown | 2023-10-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-03-15 | 1900-02-04 | 26 | 2024-03-15 | 2024-03-15 | 1 | 1 | 0 | 0 | 37 | 27 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-15 | -525 | -376 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | 2024-04-01 | IOU Designed & Installed | N/A | No | N/A | -6.4 | -7.71 | Unknown | Unknown | Unknown | 1.31 | Unknown | 153.49 | -6.4 | 159.89 | Yes | N/A | N/A | 2024-01-04 | 2024-01-18 | 15 | 11 | 2024-01-18 | 2024-01-18 | 1 | 1 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-04-01 | 75 | 53 | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-04-08 | 1900-01-07 | 6 | 2024-04-08 | 2024-04-08 | 1 | 1 | 90 | 64 | 10 | 8 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-14 | -51 | -38 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-21 | 2023-06-23 | 2023-09-27 | IOU Designed & Installed | N/A | No | N/A | 1.19 | -5.97 | Unknown | Unknown | Unknown | 7.16 | Unknown | 264.34 | 1.19 | 263.15 | Yes | N/A | N/A | 2023-06-21 | 2023-06-21 | 1 | 1 | 2023-06-21 | 2023-06-23 | 3 | 3 | 2023-06-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-09-27 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2023-09-27 | 2024-01-23 | 1900-04-28 | 85 | 2024-01-23 | 2024-01-23 | 1 | 1 | 98 | 70 | 123 | 89 | 221 | 159 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 129.05 | 129.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | -232 | -167 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 3065.18 | 586.7 | Unknown | Unknown | Unknown | 2478.48 | Unknown | 977.6 | 3065.18 | -2087.58 | Yes | N/A | N/A | 2024-04-25 | 2023-11-16 | Unknown | Unknown | 2023-11-16 | 2024-04-25 | 162 | 116 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-09-10 | 139 | 99 | Unknown | Unknown | Unknown | Unknown | 2024-09-10 | 2024-09-12 | 1900-01-02 | 3 | 2024-09-12 | 2024-09-11 | Unknown | Unknown | 139 | 99 | 165 | 119 | 304 | 218 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 16.05 | 16.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | -609 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-17 | 2025-04-03 | 2025-06-05 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1992.26 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-17 | 2025-04-03 | 18 | 14 | 2025-04-03 | 2025-04-04 | 2 | 2 | 2025-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-06-05 | 63 | 45 | Unknown | Unknown | Unknown | Unknown | 2025-06-05 | 2025-06-13 | 1900-01-08 | 7 | 2025-06-13 | 2025-06-13 | 1 | 1 | 81 | 59 | 12 | 10 | 93 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-18 | -621 | -444 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-04 | 2023-06-04 | 2023-07-02 | IOU Designed & Installed | N/A | No | N/A | 4496.53 | 1633.18 | Unknown | 245.75 | Unknown | 2617.6 | 3981 | 1079.39 | 4496.53 | -3417.14 | Yes | N/A | N/A | 2023-06-04 | 2023-06-02 | Unknown | Unknown | 2023-06-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-04 | 2023-07-02 | 29 | 20 | Unknown | Unknown | Unknown | Unknown | 2023-07-02 | 2023-07-06 | 1900-01-04 | 4 | 2023-07-06 | 2023-07-06 | 1 | 1 | 29 | 20 | 6 | 5 | 35 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-05 | -660 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-03 | 2024-04-04 | IOU Designed & Installed | N/A | No | N/A | 55.81 | -9.39 | Unknown | Unknown | Unknown | 65.2 | 3241 | 1027.78 | 55.81 | 971.97 | Yes | N/A | N/A | 2024-04-02 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-04-03 | 49 | 35 | 2024-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-03 | 2024-04-04 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-04-16 | 1900-01-12 | 9 | 2024-04-16 | 2024-04-16 | 1 | 1 | 2 | 2 | 63 | 45 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | Valley Center | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-10 | -243 | -175 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-11 | 2023-10-24 | IOU Designed & Installed | N/A | No | N/A | 1177.96 | 1789.04 | Unknown | 1408.64 | -3249 | 1229.28 | Unknown | 3248.51 | 1177.96 | 2070.55 | Yes | N/A | N/A | 2023-10-10 | 2023-10-09 | Unknown | Unknown | 2023-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2023-12-11 | 1900-02-17 | 35 | 2023-12-11 | 2023-12-11 | 1 | 1 | 0 | 0 | 50 | 36 | 50 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-09 | -467 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-25 | 2024-12-18 | 2025-01-09 | IOU Designed & Installed | N/A | No | N/A | 30.01 | Unknown | Unknown | Unknown | Unknown | 30.01 | Unknown | 1766.16 | 30.01 | 1736.15 | Yes | N/A | N/A | 2024-11-25 | 2024-11-06 | Unknown | Unknown | 2024-11-06 | 2024-12-18 | 43 | 31 | 2024-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-01-09 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-01-27 | 1900-01-18 | 13 | 2025-01-27 | 2025-01-27 | 1 | 1 | 23 | 17 | 63 | 45 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1061 | 1061 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2025-03-23 | -475 | -340 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | 2023-11-15 | IOU Designed & Installed | N/A | No | N/A | -4.7 | -3.57 | Unknown | Unknown | Unknown | -1.13 | Unknown | 514.57 | -4.7 | 519.27 | Yes | N/A | N/A | 2023-10-13 | 2023-10-13 | 1 | 1 | 2023-10-13 | 2023-10-13 | 1 | 1 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-11-15 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2023-11-15 | 2023-12-04 | 1900-01-19 | 14 | 2023-12-04 | 2023-12-04 | 1 | 1 | 35 | 25 | 22 | 16 | 57 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-14 | 178 | 129 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-26 | 2023-05-02 | 2023-08-09 | IOU Designed & Installed | N/A | No | N/A | 4049.18 | 1301.4 | Unknown | 494.82 | Unknown | 2252.96 | 7962 | 924.54 | 4049.18 | -3124.64 | Yes | N/A | N/A | 2023-04-26 | 2023-05-02 | 7 | 5 | 2023-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | 2023-08-09 | 100 | 72 | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | 2023-08-11 | 1900-01-02 | 3 | 2023-08-11 | 2023-08-11 | 1 | 1 | 107 | 77 | 4 | 4 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 96 | 96 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-10-04 | 2024-12-06 | IOU Designed & Installed | N/A | No | N/A | 1195.53 | -22.33 | Unknown | Unknown | 2.54 | 1215.32 | 3981 | 1692.3 | 1195.53 | 496.77 | Yes | N/A | N/A | 2024-09-05 | 2024-10-03 | 29 | 21 | 2024-10-03 | 2024-10-04 | 2 | 2 | 2024-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-04 | 2024-12-06 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-12-06 | 2025-01-02 | 1900-01-27 | 20 | 2025-01-02 | 2024-12-30 | Unknown | Unknown | 93 | 67 | 30 | 22 | 123 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-31 | -520 | -373 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-23 | 2024-10-30 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 729.78 | -14.1 | Unknown | Unknown | Unknown | 743.88 | Unknown | 1752.85 | 729.78 | 1023.07 | Yes | N/A | N/A | 2024-10-23 | 2024-10-30 | 8 | 6 | 2024-10-30 | 2024-10-30 | 1 | 1 | 2024-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | 2025-02-03 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2025-02-03 | 2025-02-26 | 1900-01-23 | 18 | 2025-02-26 | 2025-02-26 | 1 | 1 | 105 | 75 | 26 | 20 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 109.05 | 109.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-08 | -493 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-12 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 14.87 | -13.16 | Unknown | Unknown | Unknown | 28.03 | 3981 | 1313.96 | 14.87 | 1299.09 | Yes | N/A | N/A | 2024-02-12 | 2024-03-04 | 22 | 16 | 2024-03-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-04-15 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-05-03 | 1900-01-18 | 15 | 2024-05-03 | 2024-05-03 | 1 | 1 | 86 | 62 | 20 | 16 | 106 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 676.1 | 676.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-05 | -538 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-04-19 | 2024-08-07 | IOU Designed & Installed | N/A | No | N/A | 26.97 | Unknown | Unknown | Unknown | Unknown | 26.97 | 3981 | 1563.36 | 26.97 | 1536.39 | Yes | N/A | N/A | 2024-03-20 | 2024-04-17 | 29 | 21 | 2024-04-17 | 2024-04-19 | 3 | 3 | 2024-04-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | 2024-08-07 | 111 | 79 | Unknown | Unknown | Unknown | Unknown | 2024-08-07 | 2024-08-16 | 1900-01-09 | 8 | 2024-08-16 | 2024-08-16 | 1 | 1 | 140 | 100 | 14 | 12 | 154 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-23 | -639 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-03 | 2023-04-20 | IOU Designed & Installed | N/A | No | N/A | 1074.38 | 579.33 | Unknown | 132.15 | Unknown | 362.9 | 3981 | 634.93 | 1074.38 | -439.45 | Yes | N/A | N/A | 2023-03-03 | 2023-03-03 | 1 | 1 | 2023-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-03 | 2023-04-20 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | 2023-04-25 | 1900-01-05 | 4 | 2023-04-25 | 2023-04-25 | 1 | 1 | 50 | 36 | 7 | 5 | 57 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-15 | -309 | -222 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | 2024-08-28 | IOU Designed & Installed | N/A | No | N/A | -44.87 | Unknown | Unknown | Unknown | -780.46 | 735.59 | 0 | 794.51 | -44.87 | 839.38 | Yes | N/A | N/A | 2024-02-20 | 2023-11-06 | Unknown | Unknown | 2023-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-07 | 2024-08-28 | 83 | 59 | Unknown | 2024-08-07 | Unknown | Unknown | 2024-08-28 | 2024-10-10 | 1900-02-12 | 32 | 2024-10-10 | 2024-10-10 | 1 | 1 | 83 | 59 | 45 | 33 | 128 | 92 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 1.35 | 1.35 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-05 | -551 | -394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 737.46 | -13.67 | Unknown | Unknown | Unknown | 751.13 | 3981 | 1527.34 | 737.46 | 789.88 | Yes | N/A | N/A | 2024-08-13 | 2024-08-13 | 1 | 1 | 2024-08-13 | 2024-09-19 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-09-19 | 1 | 1 | Unknown | 2024-09-23 | Unknown | Unknown | Unknown | 2024-10-02 | Unknown | Unknown | 2024-10-02 | 2024-10-01 | Unknown | Unknown | 2 | 2 | 38 | 28 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-14 | -351 | -251 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 795.66 | -11.56 | Unknown | Unknown | Unknown | 807.22 | 3981 | 769.25 | 795.66 | -26.41 | Yes | N/A | N/A | 2023-11-08 | 2023-06-23 | Unknown | Unknown | 2023-06-23 | 2024-01-08 | 200 | 142 | 2024-01-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-08 | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | Unknown | Unknown | Unknown | 2024-06-28 | Unknown | Unknown | 2024-06-28 | 2024-06-28 | 1 | 1 | 0 | 0 | 201 | 143 | 201 | 143 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 195 | 195 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-27 | -606 | -433 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | -11.61 | -9.27 | Unknown | Unknown | Unknown | -2.34 | Unknown | 154.79 | -11.61 | 166.4 | Yes | N/A | N/A | 2023-03-24 | 2023-04-06 | 14 | 10 | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-01 | Unknown | Unknown | 2023-06-01 | 2023-06-01 | 1 | 1 | 14 | 10 | 1 | 1 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-30 | -595 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-19 | 2024-12-12 | 2025-03-13 | IOU Designed & Installed | N/A | No | N/A | -569.45 | Unknown | Unknown | Unknown | -1578 | 1008.55 | Unknown | 1433.44 | -569.45 | 2002.89 | Yes | N/A | N/A | 2024-11-19 | 2024-12-11 | 23 | 17 | 2024-12-11 | 2024-12-13 | 3 | 3 | 2024-12-13 | 2024-12-18 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2025-03-13 | 86 | 62 | Unknown | 2025-03-11 | Unknown | Unknown | 2025-03-13 | 2025-03-14 | 1900-01-01 | 2 | 2025-03-14 | 2025-03-14 | 1 | 1 | 115 | 83 | 6 | 6 | 121 | 89 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 525 | 525 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-27 | -563 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-26 | 2024-12-31 | 2025-01-14 | IOU Designed & Installed | N/A | No | N/A | -1877.83 | Unknown | Unknown | Unknown | -1906 | 28.17 | Unknown | 1766.16 | -1877.83 | 3643.99 | Yes | N/A | N/A | 2024-12-26 | 2024-12-31 | 6 | 4 | 2024-12-31 | 2024-12-31 | 1 | 1 | 2024-12-31 | 2025-01-07 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-01-14 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-02-10 | 1900-01-27 | 20 | 2025-02-10 | 2025-02-10 | 1 | 1 | 22 | 16 | 30 | 22 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | COUNTY OF SAN DIEGO-NORTH of 56 | 137.05 | 137.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-29 | -502 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-02-21 | 2024-05-13 | IOU Designed & Installed | N/A | No | N/A | 2321.09 | 748.15 | Unknown | 430.07 | -401 | 1543.87 | 3981 | 1537.6 | 2321.09 | -783.49 | Yes | N/A | N/A | 2024-01-17 | 2024-02-21 | 36 | 26 | 2024-02-21 | 2024-02-21 | 1 | 1 | 2024-02-21 | 2024-04-01 | 7 | 5 | 2024-05-06 | 2024-05-10 | 5 | 5 | 2024-02-26 | 2024-05-13 | 78 | 56 | Unknown | 2024-05-03 | Unknown | Unknown | 2024-05-13 | 2024-05-15 | 1900-01-02 | 3 | 2024-05-15 | 2024-05-15 | 1 | 1 | 121 | 87 | 10 | 10 | 131 | 97 | Steps 2,3,5,6,7 | 74 | 54 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-08 | -156 | -113 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-23 | 2023-01-31 | 2023-02-14 | IOU Designed & Installed | N/A | No | N/A | -1.98 | -5.94 | Unknown | Unknown | Unknown | 3.96 | Unknown | 722.13 | -1.98 | 724.11 | Yes | N/A | N/A | 2023-01-23 | 2023-01-31 | 9 | 7 | 2023-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-01-31 | 2023-02-14 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2023-02-14 | 2023-07-28 | 1900-06-13 | 119 | 2023-07-28 | 2023-04-05 | Unknown | Unknown | 24 | 18 | 165 | 119 | 189 | 137 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-23 | -330 | -237 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-07-31 | 2024-08-23 | IOU Designed & Installed | N/A | No | N/A | 2201.7 | 362.52 | Unknown | Unknown | Unknown | 1839.18 | Unknown | 1220.55 | 2201.7 | -981.15 | Yes | N/A | N/A | 2024-07-31 | 2024-07-31 | 1 | 1 | 2024-07-31 | 2024-07-31 | 1 | 1 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-08-23 | 24 | 18 | Unknown | 2024-08-22 | Unknown | Unknown | 2024-08-23 | 2024-08-27 | 1900-01-04 | 3 | 2024-08-27 | 2024-08-27 | 1 | 1 | 25 | 19 | 7 | 5 | 32 | 24 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | 120.05 | 120.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-15 | 119 | 86 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-26 | 2023-08-11 | 2023-10-04 | IOU Designed & Installed | N/A | No | N/A | -391.28 | -51.65 | Unknown | Unknown | -1109 | 769.37 | 3981 | 2052.09 | -391.28 | 2443.37 | Yes | N/A | N/A | 2023-07-26 | 2023-05-15 | Unknown | Unknown | 2023-05-15 | 2023-08-11 | 89 | 65 | 2023-08-11 | 2023-09-22 | 43 | 31 | 2023-10-20 | Unknown | Unknown | Unknown | 2023-09-22 | 2023-10-04 | 13 | 9 | Unknown | 2023-09-28 | Unknown | Unknown | 2023-10-04 | 2023-11-03 | 1900-01-30 | 23 | 2023-11-03 | 2024-03-13 | 132 | 94 | 56 | 40 | 252 | 182 | 308 | 222 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 900 | 900 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-07 | 188 | 135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 | 2024-09-19 | 2025-02-26 | IOU Designed & Installed | N/A | No | N/A | 17257.49 | 12273.95 | Unknown | 11.9 | -52279 | 57250.64 | 0 | 90990.44 | 17257.49 | 73732.95 | Yes | N/A | N/A | 2024-03-18 | 2024-04-22 | 36 | 26 | 2024-04-22 | 2024-12-23 | 246 | 176 | 2024-10-03 | 2024-10-10 | 8 | 6 | 2024-12-23 | 2025-01-06 | 15 | 11 | 2024-12-23 | 2025-03-11 | 79 | 57 | 2025-01-08 | 2025-02-20 | 44 | 32 | 2025-02-26 | 2025-03-14 | 1900-01-16 | 13 | 2025-03-14 | 2025-03-14 | 1 | 1 | 123 | 89 | 323 | 233 | 446 | 322 | Steps 2,3,5,6,7 | 157 | 111 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 224.3 | 224.3 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-09 | 91 | 66 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-10-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 472.27 | -14.73 | Unknown | Unknown | Unknown | 487 | 21692 | 1999.98 | 472.27 | 1527.71 | Yes | N/A | N/A | 2023-10-19 | 2023-10-26 | 8 | 6 | 2023-10-26 | 2023-12-06 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2023-10-26 | 2023-11-02 | 8 | 6 | 2023-12-06 | 2024-07-26 | 234 | 168 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-08-08 | Unknown | Unknown | 242 | 174 | 50 | 36 | 292 | 210 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-30 | -225 | -162 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-07 | 2023-09-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1460.74 | Unknown | Unknown | Unknown | 27.88 | 1432.86 | 0 | 742.67 | 1460.74 | -718.07 | Yes | N/A | N/A | 2023-09-07 | 2023-10-06 | 30 | 22 | 2023-10-06 | 2023-10-18 | 13 | 9 | 2023-10-18 | Unknown | Unknown | Unknown | 2024-12-23 | 2024-12-23 | 1 | 1 | 2023-10-18 | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | Unknown | Unknown | Unknown | 2025-05-19 | Unknown | Unknown | 2025-05-19 | 2025-05-19 | 1 | 1 | 30 | 22 | 15 | 11 | 45 | 33 | Steps 2,3,5,6,7 | 432 | 308 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-15 | -463 | -332 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-03-28 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | 2569.21 | 403.68 | Unknown | Unknown | Unknown | 2165.53 | 3981 | 750.18 | 2569.21 | -1819.03 | Yes | N/A | N/A | 2024-03-28 | 2024-03-28 | 1 | 1 | 2024-03-28 | 2024-03-28 | 1 | 1 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-04-22 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-05-09 | 1900-01-17 | 14 | 2024-05-09 | 2024-05-09 | 1 | 1 | 27 | 19 | 20 | 16 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-16 | -436 | -313 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-06-18 | 2024-06-20 | IOU Designed & Installed | N/A | No | N/A | 1100.58 | 370.02 | Unknown | Unknown | Unknown | 730.56 | 3981 | 1554.08 | 1100.58 | 453.5 | Yes | N/A | N/A | 2024-05-06 | 2024-06-18 | 44 | 32 | 2024-06-18 | 2024-06-18 | 1 | 1 | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | 2024-06-20 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-08-06 | 1900-02-16 | 34 | 2024-08-06 | 2024-08-06 | 1 | 1 | 47 | 35 | 50 | 36 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | 5 | 4 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 34.45 | Unknown | Unknown | Unknown | Unknown | 34.45 | Unknown | 1287.25 | 34.45 | 1252.8 | Yes | N/A | N/A | 2024-11-11 | 2024-02-21 | Unknown | Unknown | 2024-02-21 | 2024-12-11 | 295 | 211 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-06 | Unknown | Unknown | 2025-01-06 | 2025-01-06 | 1 | 1 | 0 | 0 | 296 | 212 | 296 | 212 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | -603 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | Unknown | 2025-01-14 | IOU Designed & Installed | N/A | No | N/A | 1801.4 | -35.76 | Unknown | Unknown | Unknown | 1837.16 | 3981 | 1747.06 | 1801.4 | -54.34 | Yes | N/A | N/A | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | 2024-10-18 | 1 | 1 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2025-01-14 | 89 | 63 | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-02-06 | 1900-01-23 | 18 | 2025-02-06 | 2025-02-06 | 1 | 1 | 90 | 64 | 26 | 20 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 13.75 | 13.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-23 | -485 | -347 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-25 | 2024-08-08 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 33.54 | Unknown | Unknown | Unknown | 0.94 | 32.6 | Unknown | 1510.56 | 33.54 | 1477.02 | Yes | N/A | N/A | 2024-07-25 | 2024-06-24 | Unknown | Unknown | 2024-06-24 | 2024-08-08 | 46 | 34 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-11-07 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2025-01-23 | 1900-03-18 | 56 | 2025-01-23 | 2025-01-23 | 1 | 1 | 92 | 66 | 125 | 91 | 217 | 157 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 96 | 96 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-14 | -83 | -60 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 | 2024-08-15 | IOU Designed & Installed | N/A | No | N/A | -420.4 | Unknown | Unknown | Unknown | -479 | 58.6 | 3981 | 1284.6 | -420.4 | 1705 | Yes | N/A | N/A | 2024-06-06 | 2024-05-30 | Unknown | Unknown | 2024-05-30 | 2024-06-06 | 8 | 6 | 2024-06-06 | 2024-06-12 | 7 | 5 | 2024-06-11 | 2024-06-11 | 1 | 1 | 2024-06-12 | 2024-08-15 | 65 | 47 | Unknown | 2024-08-05 | Unknown | Unknown | 2024-08-15 | 2024-08-29 | 1900-01-14 | 11 | 2024-08-29 | 2024-08-23 | Unknown | Unknown | 72 | 52 | 24 | 18 | 96 | 70 | Steps 2,3,5,6,7 | 1 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-06 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-03-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -7.2 | -6.25 | Unknown | Unknown | Unknown | -0.95 | Unknown | 98.66 | -7.2 | 105.86 | Yes | N/A | N/A | 2023-03-13 | 2023-03-27 | 15 | 11 | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-27 | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | Unknown | Unknown | Unknown | 2023-06-05 | Unknown | Unknown | 2023-06-05 | 2023-06-05 | 1 | 1 | 15 | 11 | 1 | 1 | 16 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-05 | -653 | -467 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-08 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 8.59 | Unknown | Unknown | Unknown | Unknown | 8.59 | Unknown | 197.01 | 8.59 | 188.42 | Yes | N/A | N/A | 2025-01-07 | 2025-01-09 | 3 | 3 | 2025-01-09 | 2025-02-28 | 51 | 37 | 2025-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-01-27 | 18 | 12 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-02-20 | 1900-01-24 | 19 | 2025-02-20 | 2025-02-20 | 1 | 1 | 21 | 15 | 77 | 57 | 98 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-22 | -333 | -238 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | 2023-08-07 | IOU Designed & Installed | N/A | No | N/A | -412.11 | -19.07 | Unknown | Unknown | -669 | 275.96 | 3981 | 1631.23 | -412.11 | 2043.34 | Yes | N/A | N/A | 2023-06-13 | 2023-06-13 | 1 | 1 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2023-08-07 | 15 | 11 | Unknown | 2023-08-01 | Unknown | Unknown | 2023-08-07 | 2023-08-24 | 1900-01-17 | 14 | 2023-08-24 | 2023-08-24 | 1 | 1 | 16 | 12 | 19 | 15 | 35 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | 248 | 248 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-23 | 248 | 179 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-19 | 2023-06-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 515.28 | -26.26 | Unknown | Unknown | 12.61 | 528.93 | 137987 | 3145.29 | 515.28 | 2630.01 | Yes | N/A | N/A | 2022-08-19 | 2023-06-09 | 295 | 211 | 2023-06-09 | 2024-01-03 | 209 | 149 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-03 | 2023-12-29 | Unknown | Unknown | Unknown | 2024-01-11 | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-01-26 | Unknown | Unknown | 295 | 211 | 209 | 149 | 504 | 360 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-04 | -555 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-21 | 2024-10-21 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 583.78 | 125.68 | Unknown | 89.32 | Unknown | 368.78 | 3981 | 1466.94 | 583.78 | 883.16 | Yes | N/A | N/A | 2024-10-21 | 2024-09-23 | Unknown | Unknown | 2024-09-23 | 2024-10-24 | 32 | 24 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-14 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-12-26 | 1900-02-11 | 31 | 2024-12-26 | 2024-12-26 | 1 | 1 | 22 | 16 | 76 | 56 | 98 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | Applicant Design | Commercial | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | 410 | 293 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-24 | 2022-08-24 | 2024-12-20 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 121900.3 | 31904.94 | Unknown | Unknown | 1697.16 | 88298.2 | 128082.55 | 67768.01 | 121900.3 | -54132.29 | Yes | N/A | N/A | 2022-08-24 | 2023-05-15 | 265 | 189 | 2023-05-15 | 2023-06-27 | 44 | 32 | 2023-05-22 | 2023-08-11 | 18 | 14 | 2023-04-07 | 2024-11-25 | 118 | 86 | Unknown | Unknown | Unknown | Unknown | 2024-08-23 | 2024-12-04 | 104 | 74 | 2024-12-20 | 2025-03-17 | 1900-03-28 | 62 | 2025-03-17 | 2025-03-17 | 1 | 1 | 283 | 203 | 355 | 255 | 638 | 458 | Steps 2,3,5,6,7 | 162 | 116 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 103 | 103 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-24 | -571 | -410 | No | 2024-02-02 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | 2024-03-25 | IOU Designed & Installed | N/A | Yes | 19 | 2212.78 | 358.29 | Unknown | 35.59 | Unknown | 1818.9 | 3981 | 1008.12 | 2212.78 | -1204.66 | Yes | N/A | N/A | 2024-02-02 | 2024-02-21 | 20 | 14 | 2024-02-21 | 2024-02-02 | Unknown | Unknown | 2024-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-03-25 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-04-01 | 1900-01-07 | 6 | 2024-04-01 | 2024-04-01 | 1 | 1 | 73 | 51 | 9 | 7 | 82 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 80 | 80 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-25 | -597 | -426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-25 | 2024-05-03 | 2024-05-17 | IOU Designed & Installed | N/A | No | N/A | 37.15 | -24.84 | Unknown | Unknown | Unknown | 61.99 | Unknown | 859.94 | 37.15 | 822.79 | Yes | N/A | N/A | 2024-03-25 | 2024-05-03 | 40 | 30 | 2024-05-03 | 2024-05-03 | 1 | 1 | 2024-05-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-05-17 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-05-17 | 2024-06-07 | 1900-01-21 | 16 | 2024-06-07 | 2024-06-07 | 1 | 1 | 55 | 41 | 24 | 18 | 79 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 114.05 | 114.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-04 | 27 | 20 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-14 | 2023-06-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2954.57 | 411.21 | Unknown | 268.08 | 6.17 | 2269.11 | 3981 | 715.96 | 2954.57 | -2238.61 | Yes | N/A | N/A | 2023-06-14 | 2023-12-08 | 178 | 128 | 2023-12-08 | 2023-12-12 | 5 | 3 | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-12 | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-05-01 | 1 | 1 | 178 | 128 | 6 | 4 | 184 | 132 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -520 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2023-08-24 | IOU Designed & Installed | N/A | No | N/A | 599.6 | -26.14 | Unknown | Unknown | Unknown | 625.74 | Unknown | 499.96 | 599.6 | -99.64 | Yes | N/A | N/A | 2023-03-28 | 2023-04-24 | 28 | 20 | 2023-04-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-24 | 2023-08-24 | 123 | 89 | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | 2023-09-05 | 1900-01-12 | 9 | 2023-09-05 | 2023-08-31 | Unknown | Unknown | 151 | 109 | 13 | 9 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-08 | 411 | 294 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-16 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 12272.15 | 3575.67 | Unknown | 336.19 | 54.34 | 8305.95 | 56251 | 5767.05 | 12272.15 | -6505.1 | Yes | N/A | N/A | 2023-06-07 | 2023-08-21 | 76 | 54 | 2023-08-21 | 2023-11-14 | 86 | 62 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2024-06-05 | 205 | 147 | Unknown | 2024-07-08 | Unknown | Unknown | 2024-07-23 | 2024-07-24 | 1900-01-01 | 2 | 2024-07-24 | 2024-07-23 | Unknown | Unknown | 281 | 201 | 88 | 64 | 369 | 265 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-06 | -234 | -169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1390.01 | 1439.41 | Unknown | 329.6 | -1076 | 697 | Unknown | 1076.36 | 1390.01 | -313.65 | Yes | N/A | N/A | 2024-04-04 | 2024-04-04 | 1 | 1 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-17 | 70 | 51 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-21 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1631.76 | Unknown | Unknown | Unknown | -1657 | 25.24 | Unknown | 1444.66 | -1631.76 | 3076.42 | Yes | N/A | N/A | 2023-10-21 | 2024-08-16 | 301 | 215 | 2024-08-16 | 2024-09-04 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2023-10-31 | 8 | 6 | 2024-09-04 | 2024-08-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-09-25 | Unknown | Unknown | 301 | 215 | 28 | 20 | 329 | 235 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-16 | -616 | -441 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-12 | 2025-01-31 | IOU Designed & Installed | N/A | No | N/A | -43.55 | Unknown | Unknown | Unknown | -1362.71 | 1319.16 | Unknown | 1364.93 | -43.55 | 1408.48 | Yes | N/A | N/A | 2024-11-12 | 2024-10-25 | Unknown | Unknown | 2024-10-25 | 2024-11-15 | 22 | 16 | 2024-11-15 | 2024-12-20 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-11-15 | 2025-01-31 | 78 | 56 | Unknown | 2025-01-30 | Unknown | Unknown | 2025-01-31 | 2025-02-07 | 1900-01-07 | 6 | 2025-02-07 | 2025-02-07 | 1 | 1 | 114 | 82 | 31 | 23 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | N/A | Coronado | CALTRANS-SOUTH of 56, CORONADO, COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 348 | 249 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-03 | 2022-06-03 | 2024-02-12 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 4422.38 | -42.57 | Unknown | Unknown | -1990 | 6454.95 | Unknown | 1989.98 | 4422.38 | -2432.4 | Yes | N/A | N/A | 2022-06-03 | 2023-04-11 | 313 | 223 | 2023-04-11 | 2023-08-14 | 126 | 90 | 2023-04-26 | 2023-05-05 | 10 | 8 | 2023-07-26 | 2023-11-22 | 66 | 48 | 2023-08-22 | Unknown | Unknown | Unknown | 2023-08-22 | 2023-08-22 | 1 | 1 | 2024-02-12 | 2024-03-14 | 1900-01-31 | 24 | 2024-03-14 | 2024-03-14 | 1 | 1 | 323 | 231 | 226 | 164 | 549 | 395 | Steps 2,3,5,6,7 | 202 | 144 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 72 | 72 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-20 | -640 | -459 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-24 | 2025-01-24 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 1578.31 | 377.04 | Unknown | 89.69 | Unknown | 1111.58 | 3981 | 1829.4 | 1578.31 | 251.09 | Yes | N/A | N/A | 2025-01-24 | 2025-01-15 | Unknown | Unknown | 2025-01-15 | 2025-01-24 | 10 | 8 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-01-27 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-01-27 | 2025-02-18 | 1900-01-22 | 17 | 2025-02-18 | 2025-02-18 | 1 | 1 | 1 | 1 | 34 | 26 | 35 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-02 | -618 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | 2023-12-18 | IOU Designed & Installed | N/A | No | N/A | -13.54 | -10.68 | Unknown | Unknown | Unknown | -2.86 | Unknown | 499.18 | -13.54 | 512.72 | Yes | N/A | N/A | 2023-11-27 | 2023-10-17 | Unknown | Unknown | 2023-10-17 | 2023-11-27 | 42 | 30 | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2023-12-18 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-01-23 | 1900-02-05 | 27 | 2024-01-23 | 2024-01-23 | 1 | 1 | 22 | 16 | 80 | 58 | 102 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | N/A | San Diego | SOLANA BEACH | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-15 | 185 | 133 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-07 | 2023-07-07 | 2024-04-04 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -8611.75 | 675.74 | Unknown | 61.48 | -20518 | 11169.03 | Unknown | 20156.38 | -8611.75 | 28768.13 | Yes | N/A | N/A | 2023-07-07 | 2023-11-07 | 124 | 88 | 2023-11-07 | 2024-02-02 | 88 | 64 | 2023-11-17 | 2023-12-13 | 27 | 19 | 2023-11-27 | 2024-02-23 | 41 | 31 | 2024-02-14 | Unknown | Unknown | Unknown | 2024-02-14 | 2024-03-29 | 45 | 33 | 2024-04-04 | 2024-04-17 | 1900-01-13 | 10 | 2024-04-17 | 2024-04-17 | 1 | 1 | 151 | 107 | 189 | 139 | 340 | 246 | Steps 2,3,5,6,7 | 102 | 74 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Underserved Community | Oceanside | OCEANSIDE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-30 | 444 | 318 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-04 | 2024-01-04 | 2024-09-10 | IOU Designed & Installed | N/A | No | N/A | 34452.86 | 9561.94 | Unknown | Unknown | -2247.01 | 27137.93 | 8076 | 13010.38 | 34452.86 | -21442.48 | Yes | N/A | N/A | 2024-01-04 | 2023-11-03 | Unknown | Unknown | 2023-11-03 | 2024-03-01 | 120 | 86 | 2024-01-05 | 2024-08-06 | 46 | 32 | 2024-01-12 | 2024-09-03 | 47 | 33 | 2024-03-21 | Unknown | Unknown | Unknown | 2024-03-21 | 2024-08-14 | 147 | 105 | 2024-09-10 | 2024-10-16 | 1900-02-05 | 27 | 2024-10-16 | 2024-10-16 | 1 | 1 | 46 | 32 | 352 | 252 | 398 | 284 | Steps 2,3,5,6,7 | 429 | 305 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-17 | -660 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-17 | 2024-07-22 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 24.95 | Unknown | Unknown | Unknown | Unknown | 24.95 | Unknown | 1100.46 | 24.95 | 1075.51 | Yes | N/A | N/A | 2024-07-17 | 2024-06-25 | Unknown | Unknown | 2024-06-25 | 2024-07-22 | 28 | 20 | 2024-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-22 | 2024-07-23 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-07-23 | 2024-08-26 | 1900-02-03 | 25 | 2024-08-26 | 2024-08-26 | 1 | 1 | 2 | 2 | 64 | 46 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-07 | 618 | 443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | 2022-08-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 690.26 | -13.66 | Unknown | Unknown | Unknown | 703.92 | 3981 | 1492.06 | 690.26 | 801.8 | Yes | N/A | N/A | 2022-08-31 | 2024-05-31 | 640 | 458 | 2024-05-31 | 2024-07-26 | 57 | 41 | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-02-14 | 1 | 1 | 640 | 458 | 58 | 42 | 698 | 500 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 202 | 202 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-09 | -127 | -91 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-06 | 2023-06-08 | 2023-10-16 | IOU Designed & Installed | N/A | No | N/A | 682.93 | -12.3 | Unknown | Unknown | 13.96 | 681.27 | 3981 | 1015.43 | 682.93 | 332.5 | Yes | N/A | N/A | 2023-06-06 | 2023-06-30 | 25 | 19 | 2023-06-30 | 2023-06-30 | 1 | 1 | 2023-06-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-30 | 2023-10-16 | 109 | 77 | Unknown | 2023-10-13 | Unknown | Unknown | 2023-10-16 | 2023-11-03 | 1900-01-18 | 15 | 2023-11-03 | 2023-11-03 | 1 | 1 | 134 | 96 | 21 | 17 | 155 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 61.05 | 61.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-30 | -161 | -116 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-10 | 2025-04-10 | 2025-05-22 | IOU Designed & Installed | N/A | No | N/A | -278.39 | 2546.96 | Unknown | 1408.03 | -5530 | 1296.62 | Unknown | 5529.5 | -278.39 | 5807.89 | Yes | N/A | N/A | 2025-04-10 | 2025-04-16 | 7 | 5 | 2025-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-05-22 | 1899-12-31 | 1 | 2025-05-22 | 2025-05-22 | 1 | 1 | 7 | 5 | 2 | 2 | 9 | 7 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 53 | 53 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-04 | -343 | -246 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1139.98 | -19.06 | Unknown | Unknown | Unknown | 1159.04 | 3981 | 681.6 | 1139.98 | -458.38 | Yes | N/A | N/A | 2023-07-11 | 2023-05-30 | Unknown | Unknown | 2023-05-30 | 2023-08-23 | 86 | 62 | 2023-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-22 | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | Unknown | 2024-04-26 | Unknown | Unknown | 2024-04-26 | 2024-04-26 | 1 | 1 | 0 | 0 | 87 | 63 | 87 | 63 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-07 | -600 | -429 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | 2024-11-04 | IOU Designed & Installed | N/A | No | N/A | 996.48 | -19.3 | Unknown | Unknown | 1.16 | 1014.62 | 3981 | 1603.8 | 996.48 | 607.32 | Yes | N/A | N/A | 2024-11-04 | 2024-10-31 | Unknown | Unknown | 2024-10-31 | 2024-11-04 | 5 | 3 | 2024-11-04 | Unknown | Unknown | Unknown | 2024-11-07 | 2024-12-10 | 34 | 24 | 2024-11-04 | 2024-11-04 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | 2025-02-14 | 1900-04-12 | 75 | 2025-02-14 | 2025-02-14 | 1 | 1 | 1 | 1 | 143 | 103 | 144 | 104 | Steps 2,3,5,6,7 | 36 | 26 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-14 | -598 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-19 | 2025-02-19 | 2025-02-28 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1503.22 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-19 | 2025-02-19 | 1 | 1 | 2025-02-19 | 2025-02-19 | 1 | 1 | 2025-02-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-28 | 10 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-06-26 | 1900-04-28 | 85 | 2025-06-26 | 2025-06-26 | 1 | 1 | 11 | 9 | 121 | 87 | 132 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-12 | -320 | -229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-24 | 2023-05-24 | 2023-06-22 | IOU Designed & Installed | N/A | No | N/A | -3079.11 | 862.2 | Unknown | 71 | -4538 | 525.69 | Unknown | 4537.71 | -3079.11 | 7616.82 | Yes | N/A | N/A | 2023-05-24 | 2023-05-24 | 1 | 1 | 2023-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | 2023-06-27 | 1900-01-05 | 4 | 2023-06-27 | 2023-06-27 | 1 | 1 | 1 | 1 | 7 | 5 | 8 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-21 | -501 | -360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-22 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 2166.31 | 567.46 | Unknown | 53.77 | Unknown | 1545.08 | Unknown | 1637.59 | 2166.31 | -528.72 | Yes | N/A | N/A | 2024-11-22 | 2024-09-19 | Unknown | Unknown | 2024-09-19 | 2024-11-22 | 65 | 47 | 2024-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-22 | 2025-02-20 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-04-07 | 1900-02-15 | 33 | 2025-04-07 | 2025-04-07 | 1 | 1 | 91 | 65 | 113 | 81 | 204 | 146 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-21 | -245 | -176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-22 | 2023-11-22 | 2023-12-07 | IOU Designed & Installed | N/A | No | N/A | 10492.31 | Unknown | Unknown | Unknown | Unknown | 10492.31 | 3981 | 1054.08 | 10492.31 | -9438.23 | Yes | N/A | N/A | 2023-11-22 | 2023-11-07 | Unknown | Unknown | 2023-11-07 | 2023-11-22 | 16 | 12 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2023-12-07 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-12-07 | 2023-12-20 | 1900-01-13 | 10 | 2023-12-20 | 2023-12-20 | 1 | 1 | 16 | 12 | 31 | 23 | 47 | 35 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | BONITA | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-23 | -534 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-24 | 2023-03-24 | 2023-08-07 | IOU Designed & Installed | N/A | No | N/A | 773.6 | -11.09 | Unknown | Unknown | -642 | 1426.69 | Unknown | 656.47 | 773.6 | -117.13 | Yes | N/A | N/A | 2023-03-24 | 2023-05-24 | 62 | 44 | 2023-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | 2023-08-07 | 54 | 38 | Unknown | 2023-08-02 | Unknown | Unknown | 2023-08-07 | 2023-08-08 | 1900-01-01 | 2 | 2023-08-08 | 2023-08-08 | 1 | 1 | 116 | 82 | 3 | 3 | 119 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-01 | -313 | -225 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | 2024-03-21 | IOU Designed & Installed | N/A | No | N/A | -1815.57 | 728.65 | Unknown | 75.06 | -3051 | 431.72 | Unknown | 3051.4 | -1815.57 | 4866.97 | Yes | N/A | N/A | 2024-02-06 | 2024-02-06 | 1 | 1 | 2024-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-03-25 | 1900-01-04 | 3 | 2024-03-25 | 2024-03-25 | 1 | 1 | 1 | 1 | 6 | 4 | 7 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-24 | 372 | 266 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2024-12-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | -17085.2 | Unknown | Unknown | Unknown | -36609 | 19523.8 | Unknown | 34593.44 | -17085.2 | 51678.64 | Yes | N/A | N/A | 2024-12-31 | 2024-12-03 | Unknown | Unknown | 2024-12-03 | 2025-01-24 | 53 | 39 | Unknown | Unknown | Unknown | Unknown | 2025-02-19 | 2025-02-19 | 1 | 1 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | Unknown | Unknown | Unknown | 2025-03-31 | Unknown | Unknown | 2025-03-31 | 2025-03-31 | 1 | 1 | 0 | 0 | 55 | 41 | 55 | 41 | Steps 2,3,5,6,7 | 26 | 18 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-13 | -626 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-05-22 | IOU Designed & Installed | N/A | No | N/A | 2074.58 | 655.33 | Unknown | Unknown | Unknown | 1419.25 | 3941 | 1089.95 | 2074.58 | -984.63 | Yes | N/A | N/A | 2024-04-25 | 2024-02-27 | Unknown | Unknown | 2024-02-27 | 2024-04-25 | 59 | 43 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-05-22 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-05-28 | 1900-01-06 | 5 | 2024-05-28 | 2024-05-28 | 1 | 1 | 28 | 20 | 67 | 49 | 95 | 69 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-01 | -672 | -481 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-14 | 2025-04-14 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1273.32 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-14 | 2025-04-14 | 1 | 1 | 2025-04-14 | 2025-05-02 | 19 | 15 | 2025-05-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-16 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-05-16 | 2025-05-29 | 1900-01-13 | 10 | 2025-05-29 | 2025-05-29 | 1 | 1 | 16 | 12 | 34 | 26 | 50 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 306 | 306 | Not Available | <1MW | No | N/A | N/A | N/A | 2021-11-22 | 935 | 670 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-06 | 2024-06-06 | IOU Designed & Installed | N/A | No | N/A | 1894.25 | Unknown | Unknown | Unknown | Unknown | 1894.25 | 3981 | 545.3 | 1894.25 | -1348.95 | Yes | N/A | N/A | 2023-11-06 | 2023-09-15 | Unknown | Unknown | 2023-09-15 | 2023-12-18 | 95 | 67 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-04-25 | 130 | 94 | Unknown | 2024-05-06 | Unknown | Unknown | 2024-06-06 | 2024-06-17 | 1900-01-11 | 8 | 2024-06-17 | 2024-06-14 | Unknown | Unknown | 130 | 94 | 107 | 75 | 237 | 169 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 447 | 447 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-31 | 106 | 77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-12 | 2023-07-12 | 2023-09-11 | IOU Designed & Installed | N/A | No | N/A | 2326.42 | 397.65 | Unknown | 1097.26 | 1.17 | 830.34 | 3981 | 2300.96 | 2326.42 | -25.46 | Yes | N/A | N/A | 2023-07-12 | 2023-08-07 | 27 | 19 | 2023-08-07 | 2023-08-09 | 3 | 3 | 2023-08-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | 2023-09-11 | 34 | 24 | Unknown | 2023-09-05 | Unknown | Unknown | 2023-09-11 | 2023-09-14 | 1900-01-03 | 4 | 2023-09-14 | 2023-09-14 | 1 | 1 | 61 | 43 | 8 | 8 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 240.05 | 240.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-24 | -617 | -442 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-16 | 2023-03-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.09 | -9.03 | Unknown | Unknown | Unknown | 5.94 | 3981 | 830.07 | -3.09 | 833.16 | Yes | N/A | N/A | 2023-03-16 | 2023-03-16 | 1 | 1 | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-31 | -92 | -67 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-11 | 2023-09-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 749.73 | -23.23 | Unknown | Unknown | Unknown | 772.96 | Unknown | 1139.68 | 749.73 | 389.95 | Yes | N/A | N/A | 2023-09-11 | 2023-10-18 | 38 | 28 | 2023-10-18 | 2023-12-13 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2023-11-28 | 2023-12-01 | 4 | 4 | 2023-12-13 | 2023-11-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-29 | Unknown | Unknown | 2024-02-29 | 2024-02-29 | 1 | 1 | 38 | 28 | 62 | 46 | 100 | 74 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-10 | -292 | -209 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | -162.18 | 1254.24 | Unknown | 328.41 | -2627 | 882.17 | Unknown | 2627.03 | -162.18 | 2789.21 | Yes | N/A | N/A | 2024-08-27 | 2024-10-02 | 37 | 27 | 2024-10-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-10-22 | 1900-01-01 | 2 | 2024-10-22 | 2024-10-22 | 1 | 1 | 37 | 27 | 3 | 3 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 112.05 | 112.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | -421 | -302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-10-19 | 2023-12-07 | IOU Designed & Installed | N/A | No | N/A | 0.83 | -12.07 | Unknown | Unknown | Unknown | 12.9 | 3981 | 902.65 | 0.83 | 901.82 | Yes | N/A | N/A | 2023-10-19 | 2023-10-18 | Unknown | Unknown | 2023-10-18 | 2023-10-19 | 2 | 2 | 2023-10-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-19 | 2023-12-07 | 50 | 36 | Unknown | 2023-12-05 | Unknown | Unknown | 2023-12-07 | 2023-12-13 | 1900-01-06 | 5 | 2023-12-13 | 2023-12-13 | 1 | 1 | 50 | 36 | 10 | 8 | 60 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | -629 | -450 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-19 | 2024-08-23 | 2024-10-14 | IOU Designed & Installed | N/A | No | N/A | 605.91 | -11.7 | Unknown | Unknown | Unknown | 617.61 | Unknown | 1512.57 | 605.91 | 906.66 | Yes | N/A | N/A | 2024-08-19 | 2024-07-30 | Unknown | Unknown | 2024-07-30 | 2024-08-23 | 25 | 19 | 2024-08-23 | Unknown | Unknown | Unknown | 2024-09-26 | 2024-10-02 | 7 | 5 | 2024-08-23 | 2024-10-14 | 53 | 37 | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2024-10-31 | 1900-01-17 | 14 | 2024-10-31 | 2024-10-31 | 1 | 1 | 53 | 37 | 51 | 39 | 104 | 76 | Steps 2,3,5,6,7 | 40 | 28 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | 838 | 838 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-21 | -171 | -124 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-06-21 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 284541.87 | 25039.88 | Unknown | Unknown | 1797.92 | 257704.07 | 0 | 150128.87 | 284541.87 | -134413 | Yes | N/A | N/A | 2024-02-12 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | 2024-09-20 | 226 | 162 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-09-25 | 27 | 19 | 2024-09-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2025-03-03 | 1900-05-05 | 90 | 2025-03-03 | 2025-03-03 | 1 | 1 | 0 | 0 | 380 | 272 | 380 | 272 | Steps 2,3,5,6,7 | 5 | 3 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-05 | -612 | -439 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-17 | 2025-05-12 | IOU Designed & Installed | N/A | No | N/A | 600.8 | -12.08 | Unknown | Unknown | Unknown | 612.88 | Unknown | 2145.24 | 600.8 | 1544.44 | Yes | N/A | N/A | 2025-03-12 | 2025-02-14 | Unknown | Unknown | 2025-02-14 | 2025-03-17 | 32 | 22 | 2025-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-17 | 2025-05-12 | 57 | 41 | Unknown | Unknown | Unknown | Unknown | 2025-05-12 | 2025-06-03 | 1900-01-22 | 17 | 2025-06-03 | 2025-06-03 | 1 | 1 | 57 | 41 | 56 | 40 | 113 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | LAGUNA NIGUEL | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-24 | -268 | -193 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-22 | 2023-07-22 | 2023-07-28 | IOU Designed & Installed | N/A | No | N/A | 1131.2 | 603.42 | Unknown | 158.76 | Unknown | 369.02 | Unknown | 1111.27 | 1131.2 | -19.93 | Yes | N/A | N/A | 2023-07-22 | 2023-07-18 | Unknown | Unknown | 2023-07-18 | 2023-07-22 | 5 | 4 | 2023-07-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-22 | 2023-07-28 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2023-07-31 | 1900-01-03 | 2 | 2023-07-31 | 2023-07-31 | 1 | 1 | 7 | 5 | 10 | 7 | 17 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 176 | 176 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-28 | 322 | 231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-12 | 2024-03-25 | 2024-10-30 | IOU Designed & Installed | N/A | No | N/A | 35204.17 | 273.47 | Unknown | Unknown | -974.07 | 35904.77 | 3981 | 2257.82 | 35204.17 | -32946.35 | Yes | N/A | N/A | 2023-06-12 | 2024-02-09 | 243 | 175 | 2024-02-09 | 2024-07-02 | 145 | 103 | Unknown | Unknown | Unknown | Unknown | 2024-10-02 | 2024-10-02 | 1 | 1 | 2024-07-02 | 2024-10-25 | 116 | 84 | Unknown | 2024-10-22 | Unknown | Unknown | 2024-10-30 | 2025-02-05 | 1900-04-08 | 71 | 2025-02-05 | 2025-01-15 | Unknown | Unknown | 359 | 259 | 245 | 175 | 604 | 434 | Steps 2,3,5,6,7 | 92 | 66 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-17 | -509 | -365 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2024-08-05 | IOU Designed & Installed | N/A | No | N/A | 1484.36 | 450.44 | Unknown | Unknown | Unknown | 1033.92 | 3941 | 1154.76 | 1484.36 | -329.6 | Yes | N/A | N/A | 2024-04-11 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-04-11 | 63 | 45 | 2024-04-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | 2024-08-05 | 117 | 83 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-08-27 | 1900-01-22 | 17 | 2024-08-27 | 2024-08-26 | Unknown | Unknown | 117 | 83 | 86 | 62 | 203 | 145 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-02 | -294 | -211 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-09 | 2024-04-10 | 2024-06-09 | IOU Designed & Installed | N/A | No | N/A | -1338.96 | 603 | Unknown | 80.26 | -2441 | 418.78 | Unknown | 2441.31 | -1338.96 | 3780.27 | Yes | N/A | N/A | 2024-04-09 | 2024-04-10 | 2 | 2 | 2024-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-09 | 2024-06-12 | 1900-01-03 | 3 | 2024-06-12 | 2024-06-12 | 1 | 1 | 2 | 2 | 5 | 4 | 7 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CAPISTRANO BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-23 | -126 | -91 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-09-05 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 5966.01 | Unknown | Unknown | Unknown | -1243.41 | 7209.42 | Unknown | 1313.3 | 5966.01 | -4652.71 | Yes | N/A | N/A | 2024-08-20 | 2024-08-20 | 1 | 1 | 2024-08-20 | 2024-10-17 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | 2024-10-29 | 2025-03-19 | 1900-05-21 | 102 | 2025-03-19 | 2025-03-19 | 1 | 1 | 1 | 1 | 202 | 146 | 203 | 147 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 952.05 | 952.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-31 | -544 | -390 | No | 2022-10-14 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-14 | 2022-10-14 | Unknown | IOU Designed & Installed | N/A | Yes | 154 | 744.97 | -11.45 | Unknown | Unknown | Unknown | 756.42 | 3885 | 2088.72 | 744.97 | 1343.75 | Yes | N/A | N/A | 2022-10-14 | 2023-03-17 | 155 | 111 | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-10-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-03-06 | Unknown | Unknown | 155 | 111 | 0 | 0 | 155 | 111 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 44 | 44 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-11 | -561 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-05 | 2023-12-05 | 2024-02-25 | IOU Designed & Installed | N/A | No | N/A | 1637.12 | 189.35 | Unknown | Unknown | 84.38 | 1363.39 | 3981 | 1011.2 | 1637.12 | -625.92 | Yes | N/A | N/A | 2023-12-05 | 2023-09-19 | Unknown | Unknown | 2023-09-19 | 2024-01-18 | 122 | 88 | 2024-01-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-02-25 | 39 | 27 | Unknown | 2024-02-27 | Unknown | Unknown | 2024-02-25 | 2024-07-03 | 1900-05-09 | 93 | 2024-07-03 | 2024-02-28 | Unknown | Unknown | 39 | 27 | 252 | 181 | 291 | 208 | Steps 2,3,5,6,7 | 2 | 1 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-14 | -550 | -394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-12 | 2024-06-17 | 2024-07-31 | IOU Designed & Installed | N/A | No | N/A | 67.2 | -0.94 | Unknown | Unknown | Unknown | 68.14 | Unknown | 1600.62 | 67.2 | 1533.42 | Yes | N/A | N/A | 2024-06-12 | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2025-03-06 | 289 | 207 | 2025-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-17 | 2024-07-31 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-08-13 | 1900-01-13 | 10 | 2024-08-13 | 2024-08-13 | 1 | 1 | 45 | 33 | 304 | 218 | 349 | 251 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 105 | 105 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-05 | -185 | -132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-21 | 2023-08-21 | 2023-10-30 | IOU Designed & Installed | N/A | No | N/A | 2057.18 | 670.89 | Unknown | 133.41 | Unknown | 1252.88 | 3981 | 2074.58 | 2057.18 | 17.4 | Yes | N/A | N/A | 2023-08-21 | 2023-05-31 | Unknown | Unknown | 2023-05-31 | 2023-08-21 | 83 | 59 | 2023-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2023-10-30 | 71 | 51 | Unknown | 2023-10-24 | Unknown | Unknown | 2023-10-30 | 2023-11-02 | 1900-01-03 | 4 | 2023-11-02 | 2023-11-02 | 1 | 1 | 71 | 51 | 88 | 64 | 159 | 115 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 279.05 | 279.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-30 | -577 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-12 | 2024-08-02 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 1143.06 | 306.56 | Unknown | Unknown | Unknown | 836.5 | 3981 | 1060.46 | 1143.06 | -82.6 | Yes | N/A | N/A | 2024-07-12 | 2024-06-28 | Unknown | Unknown | 2024-06-28 | 2024-08-02 | 36 | 26 | 2024-08-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-02 | 2024-10-23 | 83 | 59 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-10-30 | 1900-01-07 | 6 | 2024-10-30 | 2024-10-30 | 1 | 1 | 83 | 59 | 45 | 33 | 128 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | 33.05 | 33.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-01 | 181 | 130 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-09-22 | IOU Designed & Installed | N/A | No | N/A | 839.48 | -15.11 | Unknown | Unknown | 39.47 | 815.12 | 3241 | 387.3 | 839.48 | -452.18 | Yes | N/A | N/A | 2023-04-11 | 2023-05-05 | 25 | 19 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | 2023-09-22 | 148 | 106 | Unknown | 2023-09-21 | Unknown | Unknown | 2023-09-22 | 2023-09-29 | 1900-01-07 | 6 | 2023-09-29 | 2023-09-29 | 1 | 1 | 173 | 125 | 9 | 7 | 182 | 132 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-02 | 188 | 135 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-02 | 2024-07-08 | IOU Designed & Installed | N/A | No | N/A | 63.2 | Unknown | Unknown | Unknown | Unknown | 63.2 | 11943 | 2103.74 | 63.2 | 2040.54 | Yes | N/A | N/A | 2024-05-02 | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-06-13 | 109 | 79 | 2024-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-07-08 | 26 | 18 | Unknown | 2025-03-07 | Unknown | Unknown | 2024-07-08 | 2024-08-08 | 1900-01-31 | 24 | 2024-08-08 | 2024-08-08 | 1 | 1 | 26 | 18 | 142 | 104 | 168 | 122 | Steps 2,3,5,6,7 | 242 | 174 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 5760000 | 5760000 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-05-01 | 194 | 139 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-06 | 2024-02-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1893.77 | -34.03 | Unknown | Unknown | 6.96 | 1920.84 | 51753 | 704.57 | 1893.77 | -1189.2 | Yes | N/A | N/A | 2024-02-06 | 2024-02-06 | 1 | 1 | 2024-02-06 | 2024-03-21 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-02-22 | 16 | 12 | 2024-03-21 | 2024-09-18 | 182 | 130 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | Unknown | Unknown | 2024-11-12 | 2024-11-11 | Unknown | Unknown | 183 | 131 | 61 | 45 | 244 | 176 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-03 | -653 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-22 | 2024-05-22 | 2024-06-13 | IOU Designed & Installed | N/A | No | N/A | -11.56 | -9.38 | Unknown | Unknown | Unknown | -2.18 | Unknown | 1902.1 | -11.56 | 1913.66 | Yes | N/A | N/A | 2024-05-22 | 2024-05-22 | 1 | 1 | 2024-05-22 | 2024-05-23 | 2 | 2 | 2024-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-23 | 2024-06-13 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-06-13 | 2024-06-19 | 1900-01-06 | 5 | 2024-06-19 | 2024-06-19 | 1 | 1 | 23 | 17 | 10 | 8 | 33 | 25 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CORONADO | N/A | 106.05 | 106.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-08 | -698 | -500 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-19 | 2025-05-22 | 2025-06-03 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1052.93 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-19 | 2025-05-22 | 4 | 4 | 2025-05-22 | 2025-05-22 | 1 | 1 | 2025-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-22 | 2025-06-03 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-06-03 | 2025-06-09 | 1900-01-06 | 5 | 2025-06-09 | 2025-06-09 | 1 | 1 | 17 | 13 | 9 | 7 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-02 | -585 | -419 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-19 | 2024-07-19 | 2024-09-04 | IOU Designed & Installed | N/A | No | N/A | 1092 | -21.16 | Unknown | Unknown | 9.78 | 1103.38 | 3981 | 1641.32 | 1092 | 549.32 | Yes | N/A | N/A | 2024-07-19 | 2024-07-19 | 1 | 1 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-09-04 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-09-04 | 2025-02-07 | 1900-06-05 | 113 | 2025-02-07 | 2024-09-24 | Unknown | Unknown | 49 | 35 | 157 | 113 | 206 | 148 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 22.7 | 22.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-05 | -416 | -299 | No | 2024-06-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-24 | 2024-07-03 | 2025-04-15 | IOU Designed & Installed | N/A | Yes | 262 | 2013.81 | 236.93 | Unknown | 113.3 | Unknown | 1663.58 | Unknown | 1832.94 | 2013.81 | -180.87 | Yes | N/A | N/A | 2024-06-24 | 2025-03-13 | 263 | 189 | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | Unknown | Unknown | Unknown | 2025-03-13 | 2025-04-08 | 27 | 19 | 2025-03-13 | 2025-04-15 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-04-15 | 2025-04-15 | 1899-12-31 | 1 | 2025-04-15 | 2025-04-15 | 1 | 1 | 297 | 213 | 30 | 22 | 327 | 235 | Steps 2,3,5,6,7 | 26 | 18 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-22 | -609 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | 2023-08-24 | 2023-09-15 | IOU Designed & Installed | N/A | No | N/A | -6.35 | -4.61 | Unknown | Unknown | Unknown | -1.74 | Unknown | 480.37 | -6.35 | 486.72 | Yes | N/A | N/A | 2023-08-24 | 2023-05-31 | Unknown | Unknown | 2023-05-31 | 2023-08-24 | 86 | 62 | 2023-08-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | 2023-09-15 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2023-09-15 | 2023-09-21 | 1900-01-06 | 5 | 2023-09-21 | 2023-09-21 | 1 | 1 | 23 | 17 | 94 | 68 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-27 | -1 | -2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | 2024-11-20 | IOU Designed & Installed | N/A | No | N/A | 37.84 | Unknown | Unknown | Unknown | Unknown | 37.84 | 3981 | 1123.62 | 37.84 | 1085.78 | Yes | N/A | N/A | 2024-10-30 | 2024-10-30 | 1 | 1 | 2024-10-30 | 2024-11-11 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2024-11-25 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2024-11-26 | 1900-01-06 | 5 | 2024-11-26 | 2024-11-26 | 1 | 1 | 16 | 12 | 21 | 15 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-11 | -592 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-12 | 2024-11-12 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 5663.36 | 1488.87 | Unknown | Unknown | Unknown | 4174.49 | Unknown | 2818.45 | 5663.36 | -2844.91 | Yes | N/A | N/A | 2024-11-12 | 2024-11-14 | 3 | 3 | 2024-11-14 | 2025-01-14 | 62 | 44 | 2025-01-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-14 | 2025-02-20 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-02-26 | 1900-01-06 | 5 | 2025-02-26 | 2025-02-26 | 1 | 1 | 41 | 31 | 70 | 50 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-14 | -655 | -470 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-11 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 27.4 | Unknown | Unknown | Unknown | Unknown | 27.4 | Unknown | 1523.96 | 27.4 | 1496.56 | Yes | N/A | N/A | 2024-10-10 | 2024-10-11 | 2 | 2 | 2024-10-11 | 2024-10-18 | 8 | 6 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-10-15 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-10-28 | 1900-01-13 | 10 | 2024-10-28 | 2024-10-28 | 1 | 1 | 7 | 5 | 23 | 17 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SANTEE | N/A | 6.75 | 6.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-28 | -437 | -313 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | 2024-05-14 | 2024-11-18 | IOU Designed & Installed | N/A | No | N/A | 25.61 | Unknown | Unknown | Unknown | Unknown | 25.61 | Unknown | 963.63 | 25.61 | 938.02 | Yes | N/A | N/A | 2024-05-13 | 2024-04-02 | Unknown | Unknown | 2024-04-02 | 2024-05-14 | 43 | 31 | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-11-18 | 189 | 135 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-12-20 | 1900-02-01 | 25 | 2024-12-20 | 2024-12-18 | Unknown | Unknown | 189 | 135 | 76 | 56 | 265 | 191 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -654 | -468 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-12 | 2024-04-18 | 2024-04-30 | IOU Designed & Installed | N/A | No | N/A | 1185.11 | 370.02 | Unknown | 4.77 | Unknown | 810.32 | Unknown | 997.38 | 1185.11 | -187.73 | Yes | N/A | N/A | 2024-04-12 | 2024-02-27 | Unknown | Unknown | 2024-02-27 | 2024-04-18 | 52 | 38 | 2024-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-04-30 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-04-30 | 2024-05-08 | 1900-01-08 | 7 | 2024-05-08 | 2024-05-08 | 1 | 1 | 13 | 9 | 62 | 46 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 6.05 | 6.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-31 | -538 | -385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-25 | 2024-07-11 | 2024-11-14 | IOU Designed & Installed | N/A | No | N/A | 234.58 | 149.88 | Unknown | Unknown | 8.59 | 76.11 | 3981 | 1347.81 | 234.58 | 1113.23 | Yes | N/A | N/A | 2024-06-25 | 2024-06-05 | Unknown | Unknown | 2024-06-05 | 2024-07-11 | 37 | 27 | 2024-07-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-11 | 2024-11-14 | 127 | 91 | Unknown | Unknown | Unknown | Unknown | 2024-11-14 | 2024-12-09 | 1900-01-25 | 18 | 2024-12-09 | 2024-12-09 | 1 | 1 | 127 | 91 | 64 | 46 | 191 | 137 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 9.75 | 9.75 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -534 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | Unknown | 2024-11-21 | IOU Designed & Installed | N/A | No | N/A | 1799.53 | 373.61 | Unknown | Unknown | Unknown | 1425.92 | Unknown | 1532.2 | 1799.53 | -267.33 | Yes | N/A | N/A | 2024-10-17 | 2024-11-16 | 31 | 22 | 2024-11-16 | 2024-11-18 | 3 | 1 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-16 | 2024-11-21 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2025-01-13 | 1900-02-22 | 38 | 2025-01-13 | 2025-01-13 | 1 | 1 | 37 | 26 | 58 | 40 | 95 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -465 | -332 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-01 | 2024-10-01 | 2024-10-24 | IOU Designed & Installed | N/A | No | N/A | 1461.67 | 412.74 | Unknown | Unknown | Unknown | 1048.93 | 3981 | 1690.58 | 1461.67 | 228.91 | Yes | N/A | N/A | 2024-10-01 | 2024-03-08 | Unknown | Unknown | 2024-03-08 | 2024-10-01 | 208 | 148 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2024-10-24 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | 2024-11-21 | 1900-01-28 | 21 | 2024-11-21 | 2024-11-21 | 1 | 1 | 24 | 18 | 238 | 170 | 262 | 188 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-21 | -524 | -375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-06 | 2023-12-06 | 2024-01-30 | IOU Designed & Installed | N/A | No | N/A | -3.06 | -6.52 | Unknown | Unknown | Unknown | 3.46 | Unknown | 153.49 | -3.06 | 156.55 | Yes | N/A | N/A | 2023-12-06 | 2023-12-18 | 13 | 9 | 2023-12-18 | 2023-12-18 | 1 | 1 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-01-30 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2024-01-30 | 2024-03-15 | 1900-02-14 | 34 | 2024-03-15 | 2024-03-15 | 1 | 1 | 57 | 41 | 48 | 36 | 105 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-25 | -139 | -100 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-06-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -829.19 | -31.92 | Unknown | Unknown | -1798 | 1000.73 | Unknown | 1761.51 | -829.19 | 2590.7 | Yes | N/A | N/A | 2023-04-12 | 2023-05-25 | 44 | 32 | 2023-05-25 | 2023-09-06 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2023-06-27 | 2023-07-05 | 9 | 7 | 2023-09-06 | 2023-12-04 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | 2024-04-08 | 2024-04-08 | 1 | 1 | 134 | 96 | 115 | 83 | 249 | 179 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | ES 1110-F5 DIXON TL PH1 | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-10 | 123 | 88 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-06-01 | 2024-11-11 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 291437.31 | 71304.57 | Unknown | Unknown | 21567.67 | 198565.07 | 0 | 74798.14 | 291437.31 | -216639.17 | Yes | N/A | N/A | 2023-06-01 | 2024-01-13 | 227 | 162 | 2024-01-13 | 2024-04-17 | 96 | 68 | 2024-02-07 | 2024-10-24 | 37 | 27 | 2023-06-08 | 2025-01-27 | 342 | 246 | 2024-07-03 | Unknown | Unknown | Unknown | 2024-07-03 | 2024-11-01 | 122 | 88 | 2024-11-11 | 2025-02-10 | 1900-04-01 | 66 | 2025-02-10 | 2025-02-10 | 1 | 1 | 264 | 189 | 653 | 469 | 917 | 658 | Steps 2,3,5,6,7 | 782 | 558 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 15 | 15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -403 | -290 | No | 2023-06-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-27 | 2024-01-19 | IOU Designed & Installed | N/A | Yes | 198 | 1579.84 | 510.06 | Unknown | Unknown | Unknown | 1069.78 | 3981 | 1084.9 | 1579.84 | -494.94 | Yes | N/A | N/A | 2023-06-27 | 2024-01-11 | 199 | 143 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-27 | 2024-01-19 | 207 | 149 | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-01-22 | 1900-01-03 | 2 | 2024-01-22 | 2024-01-22 | 1 | 1 | 406 | 292 | 5 | 3 | 411 | 295 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | -661 | -474 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-17 | 2024-06-20 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 921.73 | 546.56 | Unknown | Unknown | Unknown | 375.17 | Unknown | 1457.03 | 921.73 | 535.3 | Yes | N/A | N/A | 2024-06-17 | 2024-05-15 | Unknown | Unknown | 2024-05-15 | 2024-06-20 | 37 | 27 | 2024-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-07-02 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-07-16 | 1900-01-14 | 11 | 2024-07-16 | 2024-07-16 | 1 | 1 | 13 | 9 | 53 | 39 | 66 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | Imperial Beach | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-07-05 | 303 | 218 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 16.84 | -14.94 | Unknown | Unknown | Unknown | 31.78 | 11943 | Not available | 16.84 | Unknown | Yes | N/A | N/A | 2023-11-28 | 2023-06-30 | Unknown | Unknown | 2023-06-30 | 2024-03-21 | 266 | 190 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-04-25 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-06 | Unknown | Unknown | 2024-05-06 | 2024-05-03 | Unknown | Unknown | 36 | 26 | 266 | 190 | 302 | 216 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-06-01 | 306 | 219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-04 | 2025-03-14 | IOU Designed & Installed | N/A | No | N/A | 1618.36 | -13.19 | Unknown | Unknown | -426 | 2057.55 | 0 | 371.59 | 1618.36 | -1246.77 | Yes | N/A | N/A | 2023-12-04 | 2023-12-04 | 1 | 1 | 2023-12-04 | 2025-01-02 | 396 | 284 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-02 | 2025-03-04 | 62 | 44 | Unknown | 2025-04-03 | Unknown | Unknown | 2025-03-14 | 2025-04-04 | 1900-01-21 | 16 | 2025-04-04 | 2025-04-03 | Unknown | Unknown | 63 | 45 | 418 | 300 | 481 | 345 | Steps 2,3,5,6,7 | 20 | 14 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-12-15 | -209 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-19 | 2024-04-29 | IOU Designed & Installed | N/A | No | N/A | 769.16 | -11.26 | Unknown | Unknown | Unknown | 780.42 | 3981 | 497.46 | 769.16 | -271.7 | Yes | N/A | N/A | 2024-03-19 | 2024-03-15 | Unknown | Unknown | 2024-03-15 | 2024-03-28 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | 2024-04-29 | Unknown | Unknown | 2024-04-29 | 2024-05-20 | 1900-01-21 | 16 | 2024-05-20 | 2024-05-20 | 1 | 1 | 0 | 0 | 37 | 27 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | 57.05 | 57.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-17 | -338 | -242 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-03 | 2023-03-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6.62 | -5.1 | Unknown | Unknown | Unknown | 11.72 | 3981 | 622.1 | 6.62 | 615.48 | Yes | N/A | N/A | 2023-03-03 | 2023-03-20 | 18 | 12 | 2023-03-20 | 2023-06-08 | 81 | 59 | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-09-28 | 1 | 1 | 2023-06-08 | 2024-05-22 | 350 | 250 | Unknown | 2024-04-15 | Unknown | Unknown | Unknown | 2024-06-14 | Unknown | Unknown | 2024-06-14 | 2024-06-13 | Unknown | Unknown | 368 | 262 | 82 | 60 | 450 | 322 | Steps 2,3,5,6,7 | 112 | 80 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN YSIDRO | N/A | 61 | 61 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-26 | -312 | -224 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-06 | 2023-02-06 | 2023-12-16 | IOU Designed & Installed | N/A | No | N/A | 8303.85 | 1081.88 | Unknown | Unknown | -424.72 | 7646.69 | Unknown | 665.24 | 8303.85 | -7638.61 | Yes | N/A | N/A | 2023-02-06 | 2023-05-10 | 94 | 68 | 2023-05-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-27 | 2023-12-16 | 173 | 124 | Unknown | 2023-12-16 | Unknown | Unknown | 2023-12-16 | 2023-12-19 | 1900-01-03 | 2 | 2023-12-19 | 2023-12-19 | 1 | 1 | 267 | 192 | 5 | 3 | 272 | 195 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | POWAY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-30 | 25 | 18 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | 2023-06-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 239.71 | -10.76 | Unknown | Unknown | Unknown | 250.47 | 3981 | 790.13 | 239.71 | 550.42 | Yes | N/A | N/A | 2023-06-26 | 2023-12-12 | 170 | 122 | 2023-12-12 | 2024-01-30 | 50 | 36 | 2024-01-30 | Unknown | Unknown | Unknown | 2024-04-15 | 2024-04-17 | 3 | 3 | 2024-01-30 | Unknown | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | Unknown | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-04-24 | 1 | 1 | 170 | 122 | 54 | 40 | 224 | 162 | Steps 2,3,5,6,7 | 78 | 56 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN YSIDRO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-30 | -394 | -281 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-11 | 2024-02-08 | IOU Designed & Installed | N/A | No | N/A | 985.95 | -10.57 | Unknown | Unknown | 38.26 | 958.26 | 3981 | 671.58 | 985.95 | -314.37 | Yes | N/A | N/A | 2023-07-11 | 2023-08-13 | 34 | 24 | 2023-08-13 | 2023-08-13 | 1 | 0 | 2023-08-13 | 2023-08-13 | 1 | 0 | Unknown | Unknown | Unknown | Unknown | 2023-08-13 | 2024-02-08 | 180 | 129 | Unknown | 2024-02-26 | Unknown | Unknown | 2024-02-08 | 2024-03-14 | 1900-02-04 | 26 | 2024-03-14 | 2024-03-01 | Unknown | Unknown | 215 | 153 | 37 | 26 | 252 | 179 | Steps 2,3,5,6,7 | 18 | 12 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 60.05 | 60.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-16 | -482 | -345 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-14 | 2025-01-14 | 2025-04-29 | IOU Designed & Installed | N/A | No | N/A | 5504.63 | 604.66 | Unknown | 29.42 | 29.77 | 4840.78 | 3981 | 1496.48 | 5504.63 | -4008.15 | Yes | N/A | N/A | 2025-01-14 | 2025-02-04 | 22 | 16 | 2025-02-04 | 2025-02-05 | 2 | 2 | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-04-29 | 84 | 60 | Unknown | 2025-04-09 | Unknown | Unknown | 2025-04-29 | 2025-05-22 | 1900-01-23 | 18 | 2025-05-22 | 2025-05-22 | 1 | 1 | 106 | 76 | 27 | 21 | 133 | 97 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-10 | -495 | -354 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-04-11 | 2023-07-26 | IOU Designed & Installed | N/A | No | N/A | 402.58 | 241.68 | Unknown | Unknown | Unknown | 160.9 | 3981 | 153.75 | 402.58 | -248.83 | Yes | N/A | N/A | 2023-04-11 | 2023-05-19 | 39 | 29 | 2023-05-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-19 | 2023-07-26 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2023-07-26 | 2023-10-04 | 1900-03-11 | 51 | 2023-10-04 | 2023-10-04 | 1 | 1 | 108 | 78 | 72 | 52 | 180 | 130 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-04 | 18 | 15 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-02-23 | 2024-03-19 | IOU Designed & Installed | N/A | No | N/A | 52.22 | -4.52 | Unknown | Unknown | Unknown | 56.74 | Unknown | 308.87 | 52.22 | 256.65 | Yes | N/A | N/A | 2024-02-23 | 2024-02-24 | 2 | 1 | 2024-02-24 | 2024-02-26 | 3 | 1 | 2024-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-03-19 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-03-19 | 2024-03-22 | 1900-01-03 | 4 | 2024-03-22 | 2024-03-22 | 1 | 1 | 10 | 7 | 8 | 6 | 18 | 13 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-24 | -690 | -493 | No | 2024-09-19 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-19 | 2024-09-19 | 2024-09-30 | IOU Designed & Installed | N/A | Yes | 189 | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1269.39 | Unknown | Unknown | Yes | N/A | N/A | 2024-09-19 | 2024-09-19 | 1 | 1 | 2024-09-19 | 2024-09-19 | 1 | 1 | 2024-09-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-19 | 2024-09-30 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | 2024-10-03 | 1900-01-03 | 4 | 2024-10-03 | 2024-10-03 | 1 | 1 | 13 | 9 | 6 | 6 | 19 | 15 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-06 | -431 | -308 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-14 | 2023-08-21 | 2024-01-19 | IOU Designed & Installed | N/A | No | N/A | -15.75 | -12.56 | Unknown | Unknown | Unknown | -3.19 | 3981 | 465.36 | -15.75 | 481.11 | Yes | N/A | N/A | 2023-07-14 | 2023-08-21 | 39 | 27 | 2023-08-21 | 2023-08-21 | 1 | 1 | 2023-08-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-21 | 2024-01-19 | 152 | 110 | Unknown | Unknown | Unknown | Unknown | 2024-01-19 | 2024-01-31 | 1900-01-12 | 9 | 2024-01-31 | 2024-01-31 | 1 | 1 | 191 | 137 | 15 | 11 | 206 | 148 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-05 | -343 | -246 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-06 | 2024-03-06 | 2024-03-07 | IOU Designed & Installed | N/A | No | N/A | 4.78 | -4.26 | Unknown | Unknown | Unknown | 9.04 | Unknown | 788.77 | 4.78 | 783.99 | Yes | N/A | N/A | 2024-03-06 | 2024-03-06 | 1 | 1 | 2024-03-06 | 2024-03-06 | 1 | 1 | 2024-03-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | 2024-03-07 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-03-27 | 1900-01-20 | 15 | 2024-03-27 | 2024-03-27 | 1 | 1 | 3 | 3 | 23 | 17 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 96.1 | 96.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-23 | -534 | -381 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-31 | 2023-08-04 | 2023-08-31 | IOU Designed & Installed | N/A | No | N/A | -1044.3 | -16.29 | Unknown | Unknown | -1036 | 7.99 | Unknown | 937.43 | -1044.3 | 1981.73 | Yes | N/A | N/A | 2023-07-31 | 2023-08-04 | 5 | 5 | 2023-08-04 | 2023-08-04 | 1 | 1 | 2023-08-04 | 2023-08-09 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | 2023-08-31 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | 2023-09-08 | 1900-01-08 | 7 | 2023-09-08 | 2023-09-08 | 1 | 1 | 35 | 27 | 11 | 9 | 46 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | CHULA VISTA | 157.05 | 157.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-19 | -308 | -221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-12 | 2024-03-12 | 2024-11-25 | IOU Designed & Installed | N/A | No | N/A | 497.76 | -46.71 | Unknown | Unknown | -1862 | 2406.47 | 0 | 1746.64 | 497.76 | 1248.88 | Yes | N/A | N/A | 2024-03-12 | 2023-12-04 | Unknown | Unknown | 2023-12-04 | 2024-09-03 | 275 | 197 | 2024-09-03 | 2024-09-19 | 17 | 13 | 2024-09-03 | 2024-09-23 | 21 | 15 | 2024-09-19 | 2024-11-25 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-01-16 | 1900-02-21 | 39 | 2025-01-16 | 2025-01-15 | Unknown | Unknown | 85 | 61 | 349 | 251 | 434 | 312 | Steps 2,3,5,6,7 | 20 | 14 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-17 | -109 | -78 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-26 | 2023-06-26 | 2023-11-27 | IOU Designed & Installed | N/A | No | N/A | 2177.64 | 529.05 | Unknown | Unknown | 3.57 | 1645.02 | 3981 | 1991.59 | 2177.64 | -186.05 | Yes | N/A | N/A | 2023-06-26 | 2023-07-07 | 12 | 10 | 2023-07-07 | 2023-07-10 | 4 | 2 | 2023-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-10 | 2023-11-27 | 141 | 101 | Unknown | 2023-10-17 | Unknown | Unknown | 2023-11-27 | 2023-11-29 | 1900-01-02 | 3 | 2023-11-29 | 2023-11-29 | 1 | 1 | 153 | 111 | 8 | 6 | 161 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-11 | -224 | -161 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | 2023-11-30 | 2023-11-30 | IOU Designed & Installed | N/A | No | N/A | -11.3 | -8.54 | Unknown | Unknown | Unknown | -2.76 | Unknown | 499.18 | -11.3 | 510.48 | Yes | N/A | N/A | 2023-11-30 | 2023-10-26 | Unknown | Unknown | 2023-10-26 | 2023-11-30 | 36 | 26 | 2023-11-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2023-11-30 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2023-11-30 | 2024-03-01 | 1900-04-02 | 67 | 2024-03-01 | 2024-03-01 | 1 | 1 | 1 | 1 | 130 | 94 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 144.05 | 144.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-03 | 480 | 343 | No | 2022-10-25 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-10-25 | 2022-12-05 | Unknown | IOU Designed & Installed | N/A | Yes | 549 | 37.79 | Unknown | Unknown | Unknown | Unknown | 37.79 | 3981 | 1374.31 | 37.79 | 1336.52 | Yes | N/A | N/A | 2022-10-25 | 2024-04-29 | 553 | 395 | 2024-04-29 | 2024-04-30 | 2 | 2 | 2023-05-17 | 2023-05-18 | 2 | 2 | 2023-05-16 | 2023-06-06 | 18 | 10 | 2022-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | Unknown | Unknown | 2024-11-25 | 2024-11-25 | 1 | 1 | 555 | 397 | 21 | 13 | 576 | 410 | Steps 2,3,5,6,7 | 351 | 251 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-22 | -556 | -398 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-10 | 2023-04-10 | 2023-08-30 | IOU Designed & Installed | N/A | No | N/A | -187.59 | 261.56 | Unknown | 159.7 | -1868.73 | 1259.88 | Unknown | 1944.86 | -187.59 | 2132.45 | Yes | N/A | N/A | 2023-04-10 | 2023-04-26 | 17 | 13 | 2023-04-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-05 | 2023-08-30 | 87 | 63 | Unknown | 2023-08-29 | Unknown | Unknown | 2023-08-30 | 2023-09-13 | 1900-01-14 | 11 | 2023-09-13 | 2023-09-13 | 1 | 1 | 104 | 76 | 16 | 12 | 120 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-16 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-11 | 2023-05-11 | 2023-07-31 | IOU Designed & Installed | N/A | No | N/A | -14.27 | -10.34 | Unknown | Unknown | Unknown | -3.93 | Unknown | 985.07 | -14.27 | 999.34 | Yes | N/A | N/A | 2023-05-11 | 2023-05-11 | 1 | 1 | 2023-05-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-11 | 2023-07-31 | 82 | 58 | Unknown | Unknown | Unknown | Unknown | 2023-07-31 | 2023-09-11 | 1900-02-11 | 31 | 2023-09-11 | 2023-09-11 | 1 | 1 | 83 | 59 | 44 | 32 | 127 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-01 | -368 | -263 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-28 | 2024-02-06 | IOU Designed & Installed | N/A | No | N/A | 3005.99 | 455.57 | Unknown | 89.74 | Unknown | 2460.68 | 3981 | 951.6 | 3005.99 | -2054.39 | Yes | N/A | N/A | 2023-12-13 | 2023-12-28 | 16 | 12 | 2023-12-28 | 2023-12-28 | 1 | 1 | 2023-12-28 | Unknown | Unknown | Unknown | 2024-07-08 | 2024-08-09 | 33 | 25 | 2023-12-28 | 2024-02-06 | 41 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-02-06 | 2024-08-29 | 1900-07-24 | 148 | 2024-08-29 | 2024-08-29 | 1 | 1 | 57 | 41 | 241 | 175 | 298 | 216 | Steps 2,3,5,6,7 | 225 | 161 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-12 | -499 | -358 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-11 | 2023-10-17 | IOU Designed & Installed | N/A | No | N/A | 0.13 | -3.07 | Unknown | Unknown | Unknown | 3.2 | Unknown | 284.12 | 0.13 | 283.99 | Yes | N/A | N/A | 2023-10-10 | 2023-06-21 | Unknown | Unknown | 2023-06-21 | 2023-10-11 | 113 | 81 | 2023-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-11 | 2023-10-17 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-10-17 | 2024-01-30 | 1900-04-15 | 76 | 2024-01-30 | 2024-01-30 | 1 | 1 | 7 | 5 | 220 | 158 | 227 | 163 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-16 | -241 | -174 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-17 | 2025-04-17 | IOU Designed & Installed | N/A | No | N/A | 866.58 | Unknown | Unknown | Unknown | 51.38 | 815.2 | 1029 | 391.02 | 866.58 | -475.56 | Yes | N/A | N/A | 2024-05-17 | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2024-05-17 | 99 | 71 | 2024-05-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-16 | 2025-04-17 | 92 | 66 | Unknown | 2025-04-15 | Unknown | Unknown | 2025-04-17 | 2025-05-20 | 1900-02-02 | 24 | 2025-05-20 | 2025-05-20 | 1 | 1 | 92 | 66 | 134 | 96 | 226 | 162 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | 129 | 129 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-01 | -584 | -417 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-09 | 2024-06-11 | IOU Designed & Installed | N/A | No | N/A | 91.97 | -14.44 | Unknown | Unknown | Unknown | 106.41 | Unknown | 998.32 | 91.97 | 906.35 | Yes | N/A | N/A | 2024-05-03 | 2024-04-10 | Unknown | Unknown | 2024-04-10 | 2024-05-09 | 30 | 22 | 2024-05-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-09 | 2024-06-11 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2024-06-11 | 2024-06-27 | 1900-01-16 | 13 | 2024-06-27 | 2024-06-27 | 1 | 1 | 34 | 24 | 48 | 36 | 82 | 60 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-04 | -417 | -298 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-19 | 2024-06-19 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 21.36 | Unknown | Unknown | Unknown | Unknown | 21.36 | 3981 | 1442.97 | 21.36 | 1421.61 | Yes | N/A | N/A | 2024-06-19 | 2024-03-24 | Unknown | Unknown | 2024-03-24 | 2024-06-19 | 88 | 63 | 2024-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-08-26 | 68 | 48 | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-09-13 | 1900-01-18 | 15 | 2024-09-13 | 2024-09-13 | 1 | 1 | 68 | 48 | 108 | 79 | 176 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-26 | -613 | -438 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-01 | Unknown | 2024-09-23 | IOU Designed & Installed | N/A | No | N/A | 57.29 | Unknown | Unknown | Unknown | 2.56 | 54.73 | 3981 | 1510.5 | 57.29 | 1453.21 | Yes | N/A | N/A | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | 2024-08-01 | 1 | 1 | 2024-08-01 | 2024-11-05 | 97 | 69 | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-09-23 | 54 | 38 | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2024-11-20 | 1900-02-27 | 43 | 2024-11-20 | 2024-11-20 | 1 | 1 | 152 | 108 | 61 | 45 | 213 | 153 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | VISTA | VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | 359 | 258 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-29 | 2023-06-05 | 2024-04-19 | IOU Designed & Installed | N/A | No | N/A | 14105.15 | 803.15 | Unknown | Unknown | 36.37 | 13265.63 | 248356 | 19492.87 | 14105.15 | 5387.72 | Yes | N/A | N/A | 2023-03-29 | 2023-03-28 | Unknown | Unknown | 2023-03-28 | 2023-12-04 | 252 | 180 | 2023-04-21 | 2023-05-30 | 40 | 28 | 2023-06-14 | 2024-03-29 | -57 | -45 | 2023-12-04 | 2024-04-04 | 123 | 89 | 2023-12-14 | 2024-04-16 | 125 | 89 | 2024-04-19 | 2024-04-26 | 1900-01-07 | 6 | 2024-04-26 | 2024-04-24 | Unknown | Unknown | 163 | 117 | 328 | 230 | 491 | 347 | Steps 2,3,5,6,7 | 455 | 325 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | Carlsbad | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-21 | -177 | -126 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-06-21 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 2361.73 | Unknown | Unknown | Yes | N/A | N/A | 2023-05-09 | 2023-06-14 | 37 | 27 | 2023-06-14 | Unknown | Unknown | Unknown | 2023-06-14 | 2023-06-14 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-21 | 2023-10-27 | 1900-05-08 | 93 | 2023-10-27 | 2023-10-27 | 1 | 1 | 38 | 28 | 130 | 94 | 168 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-03 | -144 | -103 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-17 | 2023-04-17 | 2023-08-30 | IOU Designed & Installed | N/A | No | N/A | 2247.72 | 390.13 | Unknown | 1083.28 | -1147.35 | 1921.66 | Unknown | 989.59 | 2247.72 | -1258.13 | Yes | N/A | N/A | 2023-04-17 | 2023-04-28 | 12 | 10 | 2023-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-07 | 2023-08-30 | 85 | 61 | Unknown | 2023-08-28 | Unknown | Unknown | 2023-08-30 | 2023-10-11 | 1900-02-11 | 31 | 2023-10-11 | 2023-10-11 | 1 | 1 | 97 | 71 | 44 | 32 | 141 | 103 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | 2382 | 2382 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-11-15 | -199 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-10 | 2023-04-28 | 2024-04-25 | IOU Designed & Installed | N/A | No | N/A | 6467.36 | 678.52 | Unknown | Unknown | 2.78 | 5786.06 | 3981 | 597.5 | 6467.36 | -5869.86 | Yes | N/A | N/A | 2022-03-10 | 2023-03-24 | 380 | 272 | 2023-03-24 | 2023-07-10 | 109 | 77 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-23 | Unknown | Unknown | 2024-04-25 | 2024-05-01 | 1900-01-06 | 5 | 2024-05-01 | 2024-04-30 | Unknown | Unknown | 380 | 272 | 116 | 82 | 496 | 354 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 769.05 | 769.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-21 | -192 | -139 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-07-23 | 2025-05-06 | IOU Designed & Installed | N/A | No | N/A | -1051.42 | -10.2 | Unknown | Unknown | -1559 | 517.78 | Unknown | 1445.3 | -1051.42 | 2496.72 | Yes | N/A | N/A | 2024-04-25 | 2024-07-17 | 84 | 60 | 2024-07-17 | 2024-07-23 | 7 | 5 | 2024-07-23 | 2025-05-06 | 288 | 206 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-14 | 1900-01-08 | 7 | 2025-05-14 | 2025-05-13 | Unknown | Unknown | 373 | 267 | 16 | 12 | 389 | 279 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | COTO DE CAZA | N/A | 120 | 120 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-29 | 98 | 71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-04-04 | 2024-05-21 | IOU Designed & Installed | N/A | No | N/A | 12.05 | -10.69 | Unknown | Unknown | Unknown | 22.74 | 2875.23 | 335.46 | 12.05 | 323.41 | Yes | N/A | N/A | 2023-03-14 | 2023-04-04 | 22 | 16 | 2023-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | Unknown | Unknown | 2024-05-21 | 2024-05-22 | 1900-01-01 | 2 | 2024-05-22 | 2024-04-05 | Unknown | Unknown | 22 | 16 | 2 | 2 | 24 | 18 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 59 | 59 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-10 | 386 | 277 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-08 | 2023-03-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12.09 | -14.61 | Unknown | Unknown | Unknown | 26.7 | 3981 | 592.54 | 12.09 | 580.45 | Yes | N/A | N/A | 2022-11-08 | 2023-03-23 | 136 | 98 | 2023-03-23 | 2023-12-18 | 271 | 193 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | Unknown | Unknown | 2024-01-31 | 2024-01-31 | 1 | 1 | 136 | 98 | 272 | 194 | 408 | 292 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-30 | 544 | 389 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2025-02-27 | 2025-05-07 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 7962 | 1558.1 | Unknown | Unknown | Yes | N/A | N/A | 2024-10-22 | 2024-11-12 | 22 | 16 | 2024-11-12 | 2025-05-02 | 172 | 124 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | 2025-06-10 | 1900-02-03 | 25 | 2025-06-10 | 2025-05-27 | Unknown | Unknown | 22 | 16 | 207 | 149 | 229 | 165 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-19 | -218 | -157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-26 | 2023-09-11 | IOU Designed & Installed | N/A | No | N/A | 1838.75 | 261.56 | Unknown | 998.38 | Unknown | 578.81 | 3885 | 1930.85 | 1838.75 | 92.1 | Yes | N/A | N/A | 2023-05-23 | 2023-05-26 | 4 | 4 | 2023-05-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-26 | 2023-09-11 | 109 | 77 | Unknown | 2023-09-07 | Unknown | Unknown | 2023-09-11 | 2023-09-14 | 1900-01-03 | 4 | 2023-09-14 | 2023-09-14 | 1 | 1 | 113 | 81 | 5 | 5 | 118 | 86 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-20 | 174 | 125 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-10 | 2023-03-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 27.03 | -21.31 | Unknown | Unknown | Unknown | 48.34 | 3981 | 1034.43 | 27.03 | 1007.4 | Yes | N/A | N/A | 2023-03-10 | 2023-03-10 | 1 | 1 | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-10 | Unknown | Unknown | Unknown | Unknown | 2024-04-10 | Unknown | Unknown | Unknown | 2024-07-16 | Unknown | Unknown | 2024-07-16 | 2024-07-12 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-26 | -626 | -448 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-16 | 2023-10-30 | 2023-11-02 | IOU Designed & Installed | N/A | No | N/A | 3600.69 | 593.23 | Unknown | 97.61 | Unknown | 2909.85 | Unknown | 940.09 | 3600.69 | -2660.6 | Yes | N/A | N/A | 2023-10-16 | 2023-08-04 | Unknown | Unknown | 2023-08-04 | 2023-10-30 | 88 | 62 | 2023-10-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-30 | 2023-11-02 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-11-02 | 2023-11-08 | 1900-01-06 | 5 | 2023-11-08 | 2023-11-08 | 1 | 1 | 4 | 4 | 96 | 68 | 100 | 72 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-04 | -630 | -451 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-18 | 2024-07-18 | 2024-08-01 | IOU Designed & Installed | N/A | No | N/A | 668.31 | 218.6 | Unknown | Unknown | Unknown | 449.71 | 3981 | 1485.06 | 668.31 | 816.75 | Yes | N/A | N/A | 2024-07-18 | 2024-05-21 | Unknown | Unknown | 2024-05-21 | 2024-07-18 | 59 | 43 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-08-01 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-08-01 | 2024-08-12 | 1900-01-11 | 8 | 2024-08-12 | 2024-08-12 | 1 | 1 | 15 | 11 | 72 | 52 | 87 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 57.05 | 57.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-31 | -282 | -203 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-02 | 2024-04-02 | 2024-04-22 | IOU Designed & Installed | N/A | No | N/A | 1703.13 | 421.14 | Unknown | Unknown | Unknown | 1281.99 | 3941 | 1756.93 | 1703.13 | 53.8 | Yes | N/A | N/A | 2024-04-02 | 2024-02-08 | Unknown | Unknown | 2024-02-08 | 2024-04-02 | 55 | 39 | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-04-22 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-04-22 | 2024-04-24 | 1900-01-02 | 3 | 2024-04-24 | 2024-04-24 | 1 | 1 | 21 | 15 | 59 | 43 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-01-13 | 1012 | 723 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-09-13 | 2023-10-17 | IOU Designed & Installed | N/A | No | N/A | 18391.89 | 2222.74 | Unknown | 352.74 | Unknown | 15816.41 | Unknown | 4380.06 | 18391.89 | -14011.83 | Yes | N/A | N/A | 2023-09-13 | 2023-08-29 | Unknown | Unknown | 2023-08-29 | 2023-09-26 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-26 | 2023-10-13 | 18 | 14 | Unknown | 2023-10-12 | Unknown | Unknown | 2023-10-17 | 2023-10-24 | 1900-01-07 | 6 | 2023-10-24 | 2023-10-22 | Unknown | Unknown | 18 | 14 | 37 | 27 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 100.7 | 100.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-01 | -332 | -237 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-17 | 2024-05-17 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 1435.01 | 189.45 | Unknown | Unknown | -1167.79 | 2413.35 | 0 | 1205.98 | 1435.01 | -229.03 | Yes | N/A | N/A | 2024-05-17 | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2025-03-07 | 359 | 257 | 2025-03-07 | 2025-04-02 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-11-07 | 2025-04-01 | 146 | 104 | Unknown | 2025-02-28 | Unknown | Unknown | 2025-04-01 | 2025-04-03 | 1900-01-02 | 3 | 2025-04-03 | 2025-04-03 | 1 | 1 | 173 | 123 | 363 | 261 | 536 | 384 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 69 | 69 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-30 | -421 | -302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-05-31 | 2023-11-27 | IOU Designed & Installed | N/A | No | N/A | 0.41 | -4.85 | Unknown | Unknown | Unknown | 5.26 | Unknown | 1179.97 | 0.41 | 1179.56 | Yes | N/A | N/A | 2023-03-17 | 2023-05-31 | 76 | 54 | 2023-05-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-31 | 2023-11-08 | 59 | 43 | 2023-05-31 | 2023-11-27 | 181 | 129 | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2023-12-06 | 1900-01-09 | 8 | 2023-12-06 | 2023-12-06 | 1 | 1 | 257 | 183 | 70 | 52 | 327 | 235 | Steps 2,3,5,6,7 | 161 | 115 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | BOULEVARD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-15 | -197 | -142 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-18 | 2023-12-18 | 2024-01-14 | IOU Designed & Installed | N/A | No | N/A | 912.1 | 483.36 | Unknown | 83.56 | Unknown | 345.18 | Unknown | 499.18 | 912.1 | -412.92 | Yes | N/A | N/A | 2023-12-18 | 2023-08-31 | Unknown | Unknown | 2023-08-31 | 2023-12-18 | 110 | 78 | 2023-12-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-18 | 2024-01-14 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2024-01-14 | 2024-01-31 | 1900-01-17 | 13 | 2024-01-31 | 2024-01-31 | 1 | 1 | 28 | 20 | 129 | 92 | 157 | 112 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 38.05 | 38.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-22 | -598 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-07-15 | IOU Designed & Installed | N/A | No | N/A | 5.15 | Unknown | Unknown | Unknown | Unknown | 5.15 | 3961 | 192.51 | 5.15 | 187.36 | Yes | N/A | N/A | 2024-04-25 | 2024-06-13 | 50 | 36 | 2024-06-13 | 2024-07-01 | 19 | 13 | 2024-07-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-07-15 | 15 | 11 | Unknown | 2024-07-11 | Unknown | Unknown | 2024-07-15 | 2024-08-01 | 1900-01-17 | 14 | 2024-08-01 | 2024-08-01 | 1 | 1 | 65 | 47 | 38 | 28 | 103 | 75 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-12 | -49 | -36 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-04 | 2023-03-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 47.46 | Unknown | Unknown | Unknown | Unknown | 47.46 | 3981 | 529.39 | 47.46 | 481.93 | Yes | N/A | N/A | 2023-03-04 | 2023-03-07 | 4 | 2 | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-24 | Unknown | Unknown | 2024-10-24 | 2024-10-24 | 1 | 1 | 4 | 2 | 1 | 1 | 5 | 3 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | San Marcos | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | -217 | -156 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-10 | 2023-06-06 | IOU Designed & Installed | N/A | No | N/A | 4793.1 | 2100.4 | Unknown | 1306.8 | Unknown | 1385.9 | Unknown | 4537.71 | 4793.1 | -255.39 | Yes | N/A | N/A | 2023-05-10 | 2023-05-15 | 6 | 4 | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-06 | 2023-06-09 | 1900-01-03 | 4 | 2023-06-09 | 2023-06-09 | 1 | 1 | 6 | 4 | 5 | 5 | 11 | 9 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 77.05 | 77.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-27 | -320 | -229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-03-30 | 2023-04-12 | IOU Designed & Installed | N/A | No | N/A | 1108.29 | 364.98 | Unknown | 132.15 | Unknown | 611.16 | 3885 | 673.17 | 1108.29 | -435.12 | Yes | N/A | N/A | 2023-03-30 | 2023-03-30 | 1 | 1 | 2023-03-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-30 | 2023-04-12 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-04-12 | 2023-04-13 | 1900-01-01 | 2 | 2023-04-13 | 2023-04-13 | 1 | 1 | 15 | 11 | 3 | 3 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-09 | -406 | -291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-19 | 2023-10-19 | 2024-01-26 | IOU Designed & Installed | N/A | No | N/A | -5.26 | -5.22 | Unknown | Unknown | Unknown | -0.04 | Unknown | 158.14 | -5.26 | 163.4 | Yes | N/A | N/A | 2023-10-19 | 2023-11-16 | 29 | 21 | 2023-11-16 | 2023-11-16 | 1 | 1 | 2023-11-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-16 | 2024-01-26 | 72 | 52 | Unknown | Unknown | Unknown | Unknown | 2024-01-26 | 2024-02-28 | 1900-02-02 | 24 | 2024-02-28 | 2024-02-28 | 1 | 1 | 101 | 73 | 36 | 26 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-24 | -694 | -497 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 119.14 | Unknown | Unknown | Unknown | Unknown | 119.14 | 3981 | 1623.29 | 119.14 | 1504.15 | Yes | N/A | N/A | 2024-10-17 | 2024-10-15 | Unknown | Unknown | 2024-10-15 | 2024-10-18 | 4 | 4 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-30 | Unknown | Unknown | 2024-10-30 | 2024-10-30 | 1 | 1 | 0 | 0 | 5 | 5 | 5 | 5 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-11 | -594 | -425 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-18 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 43.81 | Unknown | Unknown | Unknown | Unknown | 43.81 | Unknown | 3246.39 | 43.81 | 3202.58 | Yes | N/A | N/A | 2024-07-16 | 2024-06-26 | Unknown | Unknown | 2024-06-26 | 2024-07-18 | 23 | 17 | 2024-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-18 | 2024-10-15 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-10-25 | 1900-01-10 | 9 | 2024-10-25 | 2024-10-25 | 1 | 1 | 90 | 64 | 35 | 27 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 53.05 | 53.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | -160 | -115 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-13 | 2024-06-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 347.53 | Unknown | Unknown | Unknown | 4.02 | 343.51 | 3981 | 2373.57 | 347.53 | 2026.04 | Yes | N/A | N/A | 2024-06-13 | 2024-07-23 | 41 | 29 | 2024-07-23 | 2024-07-30 | 8 | 6 | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | Unknown | Unknown | Unknown | 2024-10-18 | Unknown | Unknown | 2024-10-18 | 2024-10-18 | 1 | 1 | 41 | 29 | 9 | 7 | 50 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-08 | -90 | -65 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | 2024-06-04 | IOU Designed & Installed | N/A | No | N/A | 1654.87 | 516.8 | Unknown | Unknown | Unknown | 1138.07 | Unknown | 307.58 | 1654.87 | -1347.29 | Yes | N/A | N/A | 2024-05-14 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-05-14 | 49 | 35 | 2024-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-14 | 2024-06-04 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2024-06-04 | 2024-06-10 | 1900-01-06 | 5 | 2024-06-10 | 2024-06-10 | 1 | 1 | 22 | 16 | 57 | 41 | 79 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-13 | -109 | -80 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-14 | 2023-06-20 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 1076.27 | 254.7 | Unknown | 69.81 | Unknown | 751.76 | 0 | 2037.02 | 1076.27 | 960.75 | Yes | N/A | N/A | 2023-06-14 | 2023-06-20 | 7 | 5 | 2023-06-20 | 2023-06-20 | 1 | 1 | 2023-06-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | 2025-02-20 | 612 | 438 | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-02-24 | 1900-01-04 | 3 | 2025-02-24 | 2025-02-24 | 1 | 1 | 619 | 443 | 7 | 5 | 626 | 448 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-13 | -60 | -45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-23 | 2023-10-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1835.02 | 3043.41 | Unknown | 1827.76 | -4454 | 1417.85 | Unknown | 4454.15 | 1835.02 | 2619.13 | Yes | N/A | N/A | 2023-10-23 | 2023-10-21 | Unknown | Unknown | 2023-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 56.05 | 56.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | -353 | -253 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 656.88 | -12.3 | Unknown | Unknown | Unknown | 669.18 | 3981 | 2040.56 | 656.88 | 1383.68 | Yes | N/A | N/A | 2024-02-15 | 2023-10-18 | Unknown | Unknown | 2023-10-18 | 2024-06-20 | 247 | 177 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-20 | 2024-10-16 | 119 | 85 | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | 2024-10-17 | 2024-10-16 | Unknown | Unknown | 119 | 85 | 247 | 177 | 366 | 262 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-12 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-29 | 2024-04-04 | 2024-04-15 | IOU Designed & Installed | N/A | No | N/A | 1056.44 | -42.23 | Unknown | Unknown | Unknown | 1098.67 | Unknown | 947.93 | 1056.44 | -108.51 | Yes | N/A | N/A | 2024-02-29 | 2024-02-27 | Unknown | Unknown | 2024-02-27 | 2024-04-04 | 38 | 28 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-04-15 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-05-09 | 1900-01-24 | 19 | 2024-05-09 | 2024-05-09 | 1 | 1 | 12 | 8 | 64 | 48 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-16 | -459 | -328 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2024-02-12 | 2024-06-25 | IOU Designed & Installed | N/A | No | N/A | 1213.88 | -17.15 | Unknown | Unknown | Unknown | 1231.03 | 3281 | 671.43 | 1213.88 | -542.45 | Yes | N/A | N/A | 2023-12-19 | 2024-02-12 | 56 | 40 | 2024-02-12 | 2024-02-12 | 1 | 1 | 2024-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-12 | 2024-06-25 | 135 | 97 | Unknown | Unknown | Unknown | Unknown | 2024-06-25 | 2024-08-06 | 1900-02-11 | 31 | 2024-08-06 | 2024-08-14 | 9 | 7 | 191 | 137 | 53 | 39 | 244 | 176 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | DEL MAR | N/A | 108 | 108 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-11 | -516 | -370 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-03-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | 230.13 | -8.75 | Unknown | Unknown | Unknown | 238.88 | 3981 | 865.06 | 230.13 | 634.93 | Yes | N/A | N/A | 2023-03-13 | 2023-03-24 | 12 | 10 | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1 | 1 | 12 | 10 | 1 | 1 | 13 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | 16 | 16 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | 87 | 62 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-12-13 | 2025-01-07 | IOU Designed & Installed | N/A | No | N/A | 2455.37 | 580.44 | Unknown | 166.3 | Unknown | 1708.63 | 3981 | 1300.49 | 2455.37 | -1154.88 | Yes | N/A | N/A | 2023-09-21 | 2023-12-13 | 84 | 60 | 2023-12-13 | 2024-07-15 | 216 | 154 | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2023-12-15 | 3 | 3 | 2024-07-15 | 2024-10-31 | 109 | 79 | Unknown | 2024-12-19 | Unknown | Unknown | 2025-01-07 | 2025-01-27 | 1900-01-20 | 15 | 2025-01-27 | 2025-01-27 | 1 | 1 | 193 | 139 | 241 | 173 | 434 | 312 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 112 | 112 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-18 | -274 | -196 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-02-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -359.86 | -17.18 | Unknown | Unknown | -354 | 11.32 | 3981 | 759.7 | -359.86 | 1119.56 | Yes | N/A | N/A | 2023-02-21 | 2023-02-21 | 1 | 1 | 2023-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | 2023-05-02 | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-08 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-08 | 2024-12-09 | 2025-01-09 | IOU Designed & Installed | N/A | No | N/A | 9070.63 | 2293.81 | Unknown | 235.55 | 14.27 | 6527 | Unknown | 1740.94 | 9070.63 | -7329.69 | Yes | N/A | N/A | 2024-11-08 | 2024-12-09 | 32 | 22 | 2024-12-09 | 2024-12-17 | 9 | 7 | 2024-12-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-01-09 | 24 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | 2025-04-09 | 1900-03-31 | 65 | 2025-04-09 | 2025-04-09 | 1 | 1 | 56 | 40 | 101 | 73 | 157 | 113 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-16 | -575 | -411 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2024-08-29 | IOU Designed & Installed | N/A | No | N/A | 116.27 | Unknown | Unknown | Unknown | Unknown | 116.27 | 3885 | 1606.03 | 116.27 | 1489.76 | Yes | N/A | N/A | 2024-08-22 | 2024-05-24 | Unknown | Unknown | 2024-05-24 | 2024-08-22 | 91 | 65 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-08-29 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-10-18 | 1900-02-19 | 37 | 2024-10-18 | 2024-10-18 | 1 | 1 | 8 | 6 | 143 | 103 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-13 | -678 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-24 | 2025-04-24 | 2025-05-21 | IOU Designed & Installed | N/A | No | N/A | 846.77 | -17.02 | Unknown | Unknown | Unknown | 863.79 | 3981 | 1434.91 | 846.77 | 588.14 | Yes | N/A | N/A | 2025-04-24 | 2025-04-22 | Unknown | Unknown | 2025-04-22 | 2025-04-24 | 3 | 3 | 2025-04-24 | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-02 | 9 | 7 | 2025-04-24 | 2025-05-21 | 28 | 20 | Unknown | Unknown | Unknown | Unknown | 2025-05-21 | 2025-06-04 | 1900-01-14 | 11 | 2025-06-04 | 2025-06-04 | 1 | 1 | 28 | 20 | 28 | 22 | 56 | 42 | Steps 2,3,5,6,7 | 8 | 6 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VALLEY CENTER | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-20 | 407 | 291 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-14 | 2023-11-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 39.49 | Unknown | Unknown | Unknown | Unknown | 39.49 | 3981 | 850.99 | 39.49 | 811.5 | Yes | N/A | N/A | 2023-11-14 | 2023-11-14 | 1 | 1 | 2023-11-14 | 2023-11-14 | 1 | 1 | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-30 | Unknown | Unknown | 2024-09-30 | 2024-09-30 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-07 | -631 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-14 | 2024-05-14 | 2024-06-28 | IOU Designed & Installed | N/A | No | N/A | 10.38 | Unknown | Unknown | Unknown | Unknown | 10.38 | 3981 | 1009.78 | 10.38 | 999.4 | Yes | N/A | N/A | 2024-05-14 | 2024-05-14 | 1 | 1 | 2024-05-14 | 2024-05-14 | 1 | 1 | 2024-05-14 | Unknown | Unknown | Unknown | 2024-05-14 | 2024-07-02 | 50 | 36 | 2024-05-14 | 2024-06-28 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-08-14 | 1900-02-16 | 34 | 2024-08-14 | 2024-08-14 | 1 | 1 | 47 | 35 | 100 | 72 | 147 | 107 | Steps 2,3,5,6,7 | 49 | 35 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-16 | -548 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-13 | 2024-02-16 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | 343 | -9.36 | Unknown | Unknown | Unknown | 352.36 | Unknown | 1128.84 | 343 | 785.84 | Yes | N/A | N/A | 2024-02-13 | 2023-12-04 | Unknown | Unknown | 2023-12-04 | 2024-02-16 | 75 | 55 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-04-17 | 62 | 44 | Unknown | Unknown | Unknown | Unknown | 2024-04-17 | 2024-05-17 | 1900-01-30 | 23 | 2024-05-17 | 2024-05-17 | 1 | 1 | 62 | 44 | 107 | 79 | 169 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-01 | -358 | -256 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-11 | 2024-03-21 | IOU Designed & Installed | N/A | No | N/A | 24.82 | -10.09 | Unknown | Unknown | 13.43 | 21.48 | Unknown | 1053.79 | 24.82 | 1028.97 | Yes | N/A | N/A | 2024-01-10 | 2024-04-16 | 98 | 70 | 2024-04-16 | 2024-04-16 | 1 | 1 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-03-21 | 42 | 30 | Unknown | Unknown | Unknown | Unknown | 2024-03-21 | 2024-11-08 | 1900-08-20 | 167 | 2024-11-08 | 2024-11-08 | 1 | 1 | 140 | 100 | 235 | 169 | 375 | 269 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-25 | -510 | -365 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-31 | 2024-06-13 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 1497.68 | Unknown | Unknown | Unknown | 6.82 | 1490.86 | 3981 | 1225.78 | 1497.68 | -271.9 | Yes | N/A | N/A | 2024-05-31 | 2024-06-18 | 19 | 13 | 2024-06-18 | 2024-07-10 | 23 | 17 | 2024-07-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-10 | 2024-10-15 | 98 | 70 | Unknown | 2024-10-09 | Unknown | Unknown | 2024-10-15 | 2024-10-31 | 1900-01-16 | 13 | 2024-10-31 | 2024-10-31 | 1 | 1 | 117 | 83 | 41 | 31 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 19 | 19 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-22 | -534 | -383 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-02 | 2024-07-18 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 354.37 | Unknown | Unknown | Unknown | 9.3 | 345.07 | 3981 | 1114.43 | 354.37 | 760.06 | Yes | N/A | N/A | 2024-07-02 | 2024-07-24 | 23 | 17 | 2024-07-24 | 2024-07-31 | 8 | 6 | 2024-07-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-31 | 2024-11-07 | 100 | 72 | Unknown | 2024-11-01 | Unknown | Unknown | 2024-11-07 | 2024-12-04 | 1900-01-27 | 20 | 2024-12-04 | 2024-12-04 | 1 | 1 | 123 | 89 | 37 | 27 | 160 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-07-06 | 1034 | 739 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-21 | 2025-04-21 | 2025-04-28 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1032.09 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-21 | 2025-04-21 | 1 | 1 | 2025-04-21 | 2025-04-28 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | 2025-05-05 | 1900-01-07 | 6 | 2025-05-05 | 2025-05-05 | 1 | 1 | 1 | 1 | 17 | 13 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-02 | -461 | -330 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-25 | 2024-01-25 | 2024-06-26 | IOU Designed & Installed | N/A | No | N/A | 653.18 | Unknown | Unknown | Unknown | Unknown | 653.18 | Unknown | 437.38 | 653.18 | -215.8 | Yes | N/A | N/A | 2024-01-25 | 2023-10-13 | Unknown | Unknown | 2023-10-13 | 2024-02-16 | 127 | 91 | 2024-02-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-16 | 2024-06-26 | 132 | 94 | Unknown | Unknown | Unknown | Unknown | 2024-06-26 | 2024-06-28 | 1900-01-02 | 3 | 2024-06-28 | 2024-06-28 | 1 | 1 | 132 | 94 | 131 | 95 | 263 | 189 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-27 | -433 | -310 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-03-28 | 2024-08-05 | IOU Designed & Installed | N/A | No | N/A | 11.83 | Unknown | Unknown | Unknown | Unknown | 11.83 | Unknown | 192.83 | 11.83 | 181 | Yes | N/A | N/A | 2024-03-20 | 2024-05-07 | 49 | 35 | 2024-05-07 | 2024-06-03 | 28 | 20 | 2024-06-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-03 | 2024-08-05 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-08-05 | 2024-09-20 | 1900-02-15 | 35 | 2024-09-20 | 2024-09-20 | 1 | 1 | 113 | 81 | 76 | 56 | 189 | 137 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | EL CAJON | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-23 | -699 | -500 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-28 | 2024-12-28 | 2025-01-07 | IOU Designed & Installed | N/A | No | N/A | 604.28 | -11.7 | Unknown | Unknown | Unknown | 615.98 | 3981 | 1595.27 | 604.28 | 990.99 | Yes | N/A | N/A | 2024-12-28 | 2024-12-27 | Unknown | Unknown | 2024-12-27 | 2024-12-28 | 2 | 1 | 2024-12-28 | Unknown | Unknown | Unknown | 2024-12-28 | 2025-02-12 | 47 | 33 | 2024-12-28 | 2025-01-07 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-01-23 | 1900-01-16 | 13 | 2025-01-23 | 2025-01-23 | 1 | 1 | 11 | 7 | 67 | 48 | 78 | 55 | Steps 2,3,5,6,7 | 46 | 32 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | 639 | 639 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-22 | -652 | -467 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-20 | 2024-08-21 | 2024-09-16 | IOU Designed & Installed | N/A | No | N/A | 1193.27 | -23.4 | Unknown | Unknown | Unknown | 1216.67 | 3981 | 1533.12 | 1193.27 | 339.85 | Yes | N/A | N/A | 2024-08-20 | 2024-08-21 | 2 | 2 | 2024-08-21 | 2024-08-21 | 1 | 1 | 2024-08-21 | 2024-09-05 | 11 | 9 | 2024-08-23 | 2024-09-10 | 10 | 6 | 2024-08-21 | 2024-09-16 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2024-09-16 | 2024-10-08 | 1900-01-22 | 17 | 2024-10-08 | 2024-10-08 | 1 | 1 | 40 | 30 | 35 | 25 | 75 | 55 | Steps 2,3,5,6,7 | 33 | 23 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DESCANSO | N/A | 98.05 | 98.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-22 | -201 | -144 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-23 | 2023-05-23 | 2023-09-08 | IOU Designed & Installed | N/A | No | N/A | 636.42 | 406.47 | Unknown | Unknown | -461 | 690.95 | 3981 | 2304.93 | 636.42 | 1668.51 | Yes | N/A | N/A | 2023-05-23 | 2023-05-23 | 1 | 1 | 2023-05-23 | 2023-06-23 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-23 | 2023-07-12 | 20 | 14 | Unknown | 2023-08-25 | Unknown | Unknown | 2023-09-08 | 2023-10-09 | 1900-01-31 | 22 | 2023-10-09 | 2023-11-03 | 26 | 20 | 21 | 15 | 90 | 66 | 111 | 81 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 136.05 | 136.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-03 | -454 | -325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | 2023-04-25 | 2023-10-31 | IOU Designed & Installed | N/A | No | N/A | 0.25 | -6.69 | Unknown | Unknown | Unknown | 6.94 | 3981 | 677.74 | 0.25 | 677.49 | Yes | N/A | N/A | 2023-03-30 | 2023-04-25 | 27 | 19 | 2023-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-25 | 2023-10-31 | 190 | 136 | Unknown | 2023-09-21 | Unknown | Unknown | 2023-10-31 | 2023-11-07 | 1900-01-07 | 6 | 2023-11-07 | 2023-11-07 | 1 | 1 | 217 | 155 | 9 | 7 | 226 | 162 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 49.05 | 49.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-28 | -390 | -279 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-07 | 2023-08-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 276.15 | -7.4 | Unknown | Unknown | 1.73 | 281.82 | 3981 | 870.98 | 276.15 | 594.83 | Yes | N/A | N/A | 2023-08-07 | 2024-02-13 | 191 | 137 | 2024-02-13 | 2024-02-14 | 2 | 2 | 2024-02-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | Unknown | Unknown | Unknown | Unknown | 2024-02-26 | Unknown | Unknown | Unknown | 2024-04-08 | Unknown | Unknown | 2024-04-08 | 2024-04-03 | Unknown | Unknown | 191 | 137 | 2 | 2 | 193 | 139 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-17 | -571 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-22 | 2024-01-29 | 2024-03-14 | IOU Designed & Installed | N/A | No | N/A | 5.48 | -4.85 | Unknown | Unknown | Unknown | 10.33 | Unknown | 980.69 | 5.48 | 975.21 | Yes | N/A | N/A | 2024-01-22 | 2023-11-08 | Unknown | Unknown | 2023-11-08 | 2024-01-29 | 83 | 59 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-03-14 | 46 | 34 | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | 2024-03-25 | 1900-01-11 | 8 | 2024-03-25 | 2024-03-25 | 1 | 1 | 46 | 34 | 96 | 68 | 142 | 102 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-31 | -16 | -13 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-08 | 2023-11-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 371.73 | 1145.55 | Unknown | Unknown | -1299 | 525.18 | Unknown | 1299.08 | 371.73 | 927.35 | Yes | N/A | N/A | 2023-11-08 | 2023-11-07 | Unknown | Unknown | 2023-11-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-04 | 753 | 538 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-14 | 2024-08-14 | 2024-11-07 | IOU Designed & Installed | N/A | No | N/A | 4547.19 | Unknown | Unknown | Unknown | -4414.6 | 8961.79 | Unknown | 2932.89 | 4547.19 | -1614.3 | Yes | N/A | N/A | 2024-08-14 | 2024-08-14 | 1 | 1 | 2024-08-14 | 2024-09-27 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-27 | 2024-10-15 | 19 | 13 | Unknown | 2024-11-01 | Unknown | Unknown | 2024-11-07 | 2025-04-28 | 1900-06-21 | 123 | 2025-04-28 | 2024-11-26 | Unknown | Unknown | 20 | 14 | 218 | 156 | 238 | 170 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | DESCANSO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-29 | -62 | -45 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-12 | 2023-06-12 | 2023-09-25 | IOU Designed & Installed | N/A | No | N/A | 5812.27 | 1302.57 | Unknown | 646.45 | -1086 | 4949.25 | 3885 | 1680.79 | 5812.27 | -4131.48 | Yes | N/A | N/A | 2023-06-12 | 2023-06-12 | 1 | 1 | 2023-06-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-20 | 2023-09-25 | 98 | 70 | Unknown | 2023-09-07 | Unknown | Unknown | 2023-09-25 | 2023-09-28 | 1900-01-03 | 4 | 2023-09-28 | 2023-09-28 | 1 | 1 | 99 | 71 | 5 | 5 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-28 | -296 | -213 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-16 | 2024-09-16 | 2025-01-24 | IOU Designed & Installed | N/A | No | N/A | 1242.05 | Unknown | Unknown | Unknown | 16.12 | 1225.93 | 3981 | 1413.98 | 1242.05 | 171.93 | Yes | N/A | N/A | 2024-09-16 | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2024-10-01 | 34 | 24 | 2024-10-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-01 | 2025-01-24 | 116 | 84 | Unknown | 2024-12-26 | Unknown | Unknown | 2025-01-24 | 2025-02-05 | 1900-01-12 | 9 | 2025-02-05 | 2025-02-05 | 1 | 1 | 116 | 84 | 48 | 34 | 164 | 118 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 13 | 13 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-18 | 515 | 368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-06 | 2023-03-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1415.49 | -9.47 | Unknown | Unknown | 6.2 | 1418.76 | 151013.2 | 11934.96 | 1415.49 | 10519.47 | Yes | N/A | N/A | 2023-03-06 | 2023-03-26 | 21 | 15 | 2023-03-26 | 2024-08-09 | 503 | 360 | Unknown | Unknown | Unknown | Unknown | 2024-08-29 | 2024-09-30 | 33 | 23 | 2024-08-09 | 2024-09-30 | 53 | 37 | Unknown | 2024-08-27 | Unknown | Unknown | Unknown | 2024-10-15 | Unknown | Unknown | 2024-10-15 | 2024-10-14 | Unknown | Unknown | 74 | 52 | 536 | 383 | 610 | 435 | Steps 2,3,5,6,7 | 52 | 36 | Unknown | Unknown | Not Available | Unknown
| Combo (R15 & R16) | OH | IOU Design | Commercial | N/A | Santee | SANTEE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2020-11-19 | 1450 | 1037 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-30 | 2022-02-09 | 2025-05-23 | IOU Designed & Installed | N/A | No | N/A | 711051.28 | 211219.6 | Unknown | Unknown | -173394.75 | 673226.43 | 25363448 | Not available | 711051.28 | Unknown | Yes | N/A | N/A | 2021-09-30 | 2023-03-06 | 523 | 373 | 2023-03-06 | 2024-06-24 | 477 | 341 | 2024-06-18 | 2024-06-18 | 1 | 1 | 2024-01-10 | 2024-06-19 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-07-03 | 2024-07-10 | 8 | 6 | 2025-05-23 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-11-08 | 1 | 1 | 524 | 374 | 505 | 363 | 1029 | 737 | Steps 2,3,5,6,7 | 166 | 118 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-08 | -624 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-11 | 2024-01-11 | 2024-04-16 | IOU Designed & Installed | N/A | No | N/A | 1283.75 | 739.08 | Unknown | 282.62 | -1059 | 1321.05 | Unknown | 1003.97 | 1283.75 | -279.78 | Yes | N/A | N/A | 2024-01-11 | 2024-01-11 | 1 | 1 | 2024-01-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-11 | 2024-04-16 | 97 | 69 | Unknown | 2024-03-15 | Unknown | Unknown | 2024-04-16 | 2024-04-24 | 1900-01-08 | 7 | 2024-04-24 | 2024-04-24 | 1 | 1 | 98 | 70 | 10 | 8 | 108 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 2044 | 2044 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-01-19 | 97 | 70 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-02-14 | 2023-08-17 | 2024-04-17 | IOU Designed & Installed | N/A | No | N/A | 14957.77 | 544.05 | Unknown | Unknown | -2658.28 | 17072 | 10946.44 | 16568.51 | 14957.77 | 1610.74 | Yes | N/A | N/A | 2022-02-14 | 2023-05-08 | 449 | 321 | 2023-05-08 | 2023-11-13 | 190 | 136 | 2023-08-21 | 2024-04-11 | 38 | 26 | 2023-09-29 | 2023-12-21 | 31 | 23 | 2023-11-13 | Unknown | Unknown | Unknown | 2023-11-30 | 2024-04-11 | 134 | 96 | 2024-04-17 | 2024-04-25 | 1900-01-08 | 7 | 2024-04-25 | 2024-04-25 | 1 | 1 | 487 | 347 | 365 | 263 | 852 | 610 | Steps 2,3,5,6,7 | 317 | 227 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | Underserved Community | Mission Viejo | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-04 | 12 | 10 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-02-18 | 2025-04-23 | IOU Designed & Installed | N/A | No | N/A | -8774.43 | 111.46 | Unknown | Unknown | -12203 | 3317.11 | Unknown | 11273.8 | -8774.43 | 20048.23 | Yes | N/A | N/A | 2025-02-12 | 2025-02-12 | 1 | 1 | 2025-02-12 | Unknown | Unknown | Unknown | 2025-02-20 | 2025-02-24 | 5 | 3 | 2025-04-10 | 2025-04-15 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-23 | 2025-05-16 | 1900-01-23 | 18 | 2025-05-16 | 2025-05-16 | 1 | 1 | 6 | 4 | 31 | 23 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 9.05 | 9.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-15 | 2024-10-17 | 2024-12-18 | IOU Designed & Installed | N/A | No | N/A | 2205.98 | 519.44 | Unknown | 15.45 | -131 | 1802.09 | Unknown | 1497.88 | 2205.98 | -708.1 | Yes | N/A | N/A | 2024-10-15 | 2024-10-16 | 2 | 2 | 2024-10-16 | 2024-10-16 | 1 | 1 | 2024-10-16 | 2024-10-22 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-10-22 | 2024-12-18 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2024-12-18 | 2024-12-20 | 1900-01-02 | 3 | 2024-12-20 | 2024-12-20 | 1 | 1 | 67 | 49 | 5 | 5 | 72 | 54 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-01-21 | -618 | -443 | No | 2025-02-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-03 | 2025-02-05 | 2025-05-06 | IOU Designed & Installed | N/A | Yes | 88 | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1581.95 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-03 | 2025-05-02 | 89 | 65 | 2025-05-02 | 2025-02-05 | Unknown | Unknown | 2025-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-05 | 2025-05-06 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2025-05-06 | 2025-05-14 | 1900-01-08 | 7 | 2025-05-14 | 2025-05-13 | Unknown | Unknown | 180 | 130 | 9 | 7 | 189 | 137 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 118.05 | 118.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-28 | -226 | -163 | No | 2024-02-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | 2024-07-14 | IOU Designed & Installed | N/A | Yes | 60 | 415.94 | -12 | Unknown | Unknown | Unknown | 427.94 | 3941 | 827.16 | 415.94 | 411.22 | Yes | N/A | N/A | 2024-02-15 | 2024-04-15 | 61 | 43 | 2024-04-15 | 2024-02-15 | Unknown | Unknown | 2024-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | 2024-07-14 | 151 | 107 | Unknown | Unknown | Unknown | Unknown | 2024-07-14 | 2024-07-18 | 1900-01-04 | 4 | 2024-07-18 | 2024-07-17 | Unknown | Unknown | 212 | 150 | 5 | 4 | 217 | 154 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-17 | -711 | -509 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-29 | 2025-04-29 | 2025-04-29 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 976.53 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-29 | 2025-04-27 | Unknown | Unknown | 2025-04-27 | 2025-04-29 | 3 | 2 | 2025-04-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-04-29 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-05-06 | 1900-01-07 | 6 | 2025-05-06 | 2025-05-06 | 1 | 1 | 1 | 1 | 12 | 9 | 13 | 10 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-08 | -501 | -359 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-09 | 2024-11-09 | 2025-02-18 | IOU Designed & Installed | N/A | No | N/A | 2928.16 | 624.86 | Unknown | Unknown | Unknown | 2303.3 | Unknown | 1790.14 | 2928.16 | -1138.02 | Yes | N/A | N/A | 2024-11-09 | 2024-11-11 | 3 | 1 | 2024-11-11 | 2024-11-11 | 1 | 1 | 2024-11-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-09 | 2025-02-18 | 102 | 72 | Unknown | Unknown | Unknown | Unknown | 2025-02-18 | 2025-03-25 | 1900-02-04 | 26 | 2025-03-25 | 2025-03-25 | 1 | 1 | 105 | 73 | 38 | 28 | 143 | 101 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-21 | -588 | -421 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-30 | 2024-10-30 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | 937.87 | Unknown | Unknown | Unknown | Unknown | 937.87 | 3981 | 1189.69 | 937.87 | 251.82 | Yes | N/A | N/A | 2024-10-30 | 2024-10-10 | Unknown | Unknown | 2024-10-10 | 2024-11-19 | 41 | 29 | 2024-11-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-19 | 2025-01-29 | 72 | 52 | Unknown | 2025-01-15 | Unknown | Unknown | 2025-01-29 | 2025-02-10 | 1900-01-12 | 9 | 2025-02-10 | 2025-02-10 | 1 | 1 | 72 | 52 | 55 | 39 | 127 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 230.15 | 230.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-04 | -198 | -143 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-24 | 2023-02-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 26.05 | Unknown | Unknown | Unknown | Unknown | 26.05 | 3981 | 572.32 | 26.05 | 546.27 | Yes | N/A | N/A | 2023-02-24 | 2023-02-24 | 1 | 1 | 2023-02-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-27 | Unknown | Unknown | Unknown | Unknown | 2024-12-31 | Unknown | Unknown | Unknown | 2025-01-21 | Unknown | Unknown | 2025-01-21 | 2025-05-20 | 120 | 86 | 1 | 1 | 120 | 86 | 121 | 87 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-02 | 127 | 92 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1019.91 | -9.26 | Unknown | Unknown | Unknown | 1029.17 | 3885 | 695.07 | 1019.91 | -324.84 | Yes | N/A | N/A | 2023-02-08 | 2023-02-08 | 1 | 1 | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | Unknown | Unknown | 2023-03-31 | 2023-03-09 | Unknown | Unknown | 1 | 1 | 0 | 0 | 1 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-14 | -493 | -353 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-03-13 | 2023-04-19 | IOU Designed & Installed | N/A | No | N/A | -7.94 | -5.75 | Unknown | Unknown | Unknown | -2.19 | 3981 | 341 | -7.94 | 348.94 | Yes | N/A | N/A | 2023-03-13 | 2023-03-13 | 1 | 1 | 2023-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-13 | 2023-04-19 | 38 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-04-19 | 2023-08-09 | 1900-04-22 | 81 | 2023-08-09 | 2023-08-09 | 1 | 1 | 39 | 29 | 114 | 82 | 153 | 111 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SANTA YSABEL | N/A | 71364 | 71364 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-02-15 | 89 | 64 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-02 | 2024-05-11 | IOU Designed & Installed | N/A | No | N/A | 13031.05 | 3712.27 | Unknown | 1146.84 | -673 | 8844.94 | 6308 | 3986.83 | 13031.05 | -9044.22 | Yes | N/A | N/A | 2024-02-02 | 2024-01-22 | Unknown | Unknown | 2024-01-22 | 2024-02-20 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-03-07 | 2024-04-23 | 48 | 34 | 2024-02-20 | 2024-05-02 | 73 | 53 | Unknown | 2024-04-16 | Unknown | Unknown | 2024-05-11 | 2024-05-14 | 1900-01-03 | 2 | 2024-05-14 | 2024-05-14 | 1 | 1 | 73 | 53 | 83 | 59 | 156 | 112 | Steps 2,3,5,6,7 | 63 | 45 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-29 | 118 | 85 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-08-16 | Unknown | IOU Designed & Installed | N/A | No | N/A | 269.7 | -5.42 | Unknown | Unknown | Unknown | 275.12 | 3981 | 664.85 | 269.7 | 395.15 | Yes | N/A | N/A | 2024-03-14 | 2024-08-16 | 156 | 112 | 2024-08-16 | 2024-08-16 | 1 | 1 | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | Unknown | Unknown | Unknown | Unknown | 2025-05-07 | Unknown | Unknown | Unknown | 2025-05-27 | Unknown | Unknown | 2025-05-27 | 2025-05-27 | 1 | 1 | 156 | 112 | 2 | 2 | 158 | 114 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-20 | -681 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-03 | 2025-04-29 | IOU Designed & Installed | N/A | No | N/A | 873.36 | -17.55 | Unknown | Unknown | Unknown | 890.91 | 3981 | 1820.28 | 873.36 | 946.92 | Yes | N/A | N/A | 2025-04-03 | 2025-04-03 | 1 | 1 | 2025-04-03 | 2025-04-03 | 1 | 1 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-03 | 2025-04-29 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-05-08 | 1900-01-09 | 8 | 2025-05-08 | 2025-05-08 | 1 | 1 | 28 | 20 | 12 | 10 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | POWAY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-10 | -573 | -410 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-10 | 2025-02-11 | 2025-02-28 | IOU Designed & Installed | N/A | No | N/A | 964.69 | -19.38 | Unknown | Unknown | Unknown | 984.07 | 3981 | 1700.3 | 964.69 | 735.61 | Yes | N/A | N/A | 2025-02-10 | 2025-01-27 | Unknown | Unknown | 2025-01-27 | 2025-02-11 | 16 | 12 | 2025-02-11 | Unknown | Unknown | Unknown | 2025-02-11 | 2025-02-21 | 11 | 9 | 2025-02-27 | 2025-02-28 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-04-16 | 1900-02-16 | 34 | 2025-04-16 | 2025-04-16 | 1 | 1 | 2 | 2 | 76 | 56 | 78 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 90 | 90 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-11 | -557 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-22 | 2024-10-22 | 2025-02-25 | IOU Designed & Installed | N/A | No | N/A | 448.12 | Unknown | Unknown | Unknown | 13.98 | 434.14 | 3981 | 298.35 | 448.12 | -149.77 | Yes | N/A | N/A | 2024-10-22 | 2024-11-12 | 22 | 16 | 2024-11-12 | 2024-11-12 | 1 | 1 | 2024-11-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2025-02-25 | 106 | 76 | Unknown | 2025-01-17 | Unknown | Unknown | 2025-02-25 | 2025-03-04 | 1900-01-07 | 6 | 2025-03-04 | 2025-03-03 | Unknown | Unknown | 128 | 92 | 9 | 7 | 137 | 99 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-02 | 586 | 419 | No | 2023-02-23 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-15 | 2023-02-23 | Unknown | IOU Designed & Installed | N/A | Yes | 669 | 29.47 | Unknown | Unknown | Unknown | Unknown | 29.47 | 3991 | 337.66 | 29.47 | 308.19 | Yes | N/A | N/A | 2022-09-15 | 2024-12-23 | 831 | 593 | 2024-12-23 | 2024-12-23 | 1 | 1 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | 2025-01-09 | 2025-01-08 | Unknown | Unknown | 831 | 593 | 1 | 1 | 832 | 594 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-10 | -295 | -212 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-27 | 2025-03-27 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | 449.02 | Unknown | Unknown | Unknown | -220 | 669.02 | Unknown | 1260.12 | 449.02 | 811.1 | Yes | N/A | N/A | 2025-03-27 | 2025-03-14 | Unknown | Unknown | 2025-03-14 | 2025-03-27 | 14 | 10 | 2025-03-27 | 2025-04-10 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-04-10 | 2025-05-02 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-20 | 1900-01-18 | 13 | 2025-05-20 | 2025-05-19 | Unknown | Unknown | 38 | 28 | 33 | 23 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 22 | 22 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | -498 | -357 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-18 | 2025-02-07 | 2025-05-16 | IOU Designed & Installed | N/A | No | N/A | 1517.13 | -0.94 | Unknown | Unknown | 20 | 1498.07 | 3981 | 1390.98 | 1517.13 | -126.15 | Yes | N/A | N/A | 2024-11-18 | 2025-02-20 | 95 | 69 | 2025-02-20 | 2025-02-21 | 2 | 2 | 2025-02-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-05-16 | 85 | 61 | Unknown | 2025-05-07 | Unknown | Unknown | 2025-05-16 | 2025-06-12 | 1900-01-27 | 20 | 2025-06-12 | 2025-06-12 | 1 | 1 | 180 | 130 | 31 | 23 | 211 | 153 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | SM 1128-H1 N.CITY PA7 (E) | SAN MARCOS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-01 | 344 | 247 | No | 2022-12-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-07 | 2022-12-07 | 2025-05-16 | Customer elected Applicant Design | Step 2 Engineering & Design | Yes | 680 | 55171.3 | 10987.92 | Unknown | Unknown | 4695.96 | 39487.42 | 213709 | 69252.8 | 55171.3 | 14081.5 | Yes | N/A | N/A | 2022-12-07 | 2024-11-26 | 721 | 515 | 2024-11-26 | 2024-11-27 | 2 | 2 | 2024-04-09 | 2025-02-19 | 23 | 15 | 2024-04-09 | 2025-06-26 | 117 | 85 | 2024-12-11 | Unknown | Unknown | Unknown | 2024-12-11 | 2025-05-07 | 148 | 106 | 2025-05-16 | 2025-06-10 | 1900-01-25 | 18 | 2025-06-10 | 2025-06-10 | 1 | 1 | 744 | 530 | 294 | 212 | 1038 | 742 | Steps 2,3,5,6,7 | 745 | 533 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-06 | -271 | -195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-01 | 2023-12-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1156.86 | Unknown | Unknown | Unknown | 3.1 | 1153.76 | 3981 | 1282.03 | 1156.86 | 125.17 | Yes | N/A | N/A | 2023-12-01 | 2024-06-11 | 194 | 138 | 2024-06-11 | 2024-06-24 | 14 | 10 | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-24 | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | Unknown | Unknown | Unknown | 2024-12-09 | Unknown | Unknown | 2024-12-09 | 2024-12-09 | 1 | 1 | 194 | 138 | 15 | 11 | 209 | 149 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-05 | -174 | -125 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-12 | 2024-02-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6358.36 | 2429.36 | Unknown | Unknown | 43.03 | 3885.97 | 3981 | 2350.63 | 6358.36 | -4007.73 | Yes | N/A | N/A | 2024-02-12 | 2024-01-22 | Unknown | Unknown | 2024-01-22 | 2024-03-08 | 47 | 35 | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-08 | Unknown | Unknown | Unknown | Unknown | 2024-04-11 | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 0 | 0 | 48 | 36 | 48 | 36 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-12 | -472 | -339 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-22 | 2024-08-22 | 2024-11-20 | IOU Designed & Installed | N/A | No | N/A | 866.29 | -16.32 | Unknown | Unknown | Unknown | 882.61 | 3981 | 1589.96 | 866.29 | 723.67 | Yes | N/A | N/A | 2024-08-22 | 2024-07-18 | Unknown | Unknown | 2024-07-18 | 2024-08-22 | 36 | 26 | 2024-08-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-11-20 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2024-11-26 | 1900-01-06 | 5 | 2024-11-26 | 2024-11-25 | Unknown | Unknown | 91 | 65 | 43 | 31 | 134 | 96 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-17 | -540 | -387 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-13 | 2025-03-13 | 2025-06-04 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1824.2 | Unknown | Unknown | Yes | N/A | N/A | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | 2025-03-13 | 1 | 1 | 2025-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-13 | 2025-06-04 | 84 | 60 | Unknown | Unknown | Unknown | Unknown | 2025-06-04 | 2025-06-25 | 1900-01-21 | 16 | 2025-06-25 | 2025-06-25 | 1 | 1 | 85 | 61 | 24 | 18 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | EL CAJON | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-21 | -660 | -471 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-05 | 2024-08-08 | 2024-08-22 | IOU Designed & Installed | N/A | No | N/A | 62.25 | Unknown | Unknown | Unknown | Unknown | 62.25 | Unknown | 1493.33 | 62.25 | 1431.08 | Yes | N/A | N/A | 2024-08-05 | 2024-07-17 | Unknown | Unknown | 2024-07-17 | 2024-08-08 | 23 | 17 | 2024-08-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-08-22 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2024-08-22 | 2024-08-30 | 1900-01-08 | 7 | 2024-08-30 | 2024-08-30 | 1 | 1 | 15 | 11 | 33 | 25 | 48 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 43.05 | 43.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-21 | -356 | -255 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | 2025-06-25 | IOU Designed & Installed | N/A | No | N/A | -345.71 | Unknown | Unknown | Unknown | -912.93 | 567.22 | 0 | 956.34 | -345.71 | 1302.05 | Yes | N/A | N/A | 2024-09-10 | 2024-06-18 | Unknown | Unknown | 2024-06-18 | 2024-10-10 | 115 | 83 | 2024-10-10 | 2025-06-18 | 252 | 180 | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2025-06-25 | 259 | 185 | Unknown | 2025-06-19 | Unknown | Unknown | 2025-06-25 | 2025-06-30 | 1900-01-05 | 4 | 2025-06-30 | 2025-06-30 | 1 | 1 | 511 | 365 | 122 | 88 | 633 | 453 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-26 | -158 | -114 | No | 2024-09-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 | 2024-09-24 | 2025-01-30 | IOU Designed & Installed | N/A | Yes | 27 | 427.46 | 253.74 | Unknown | Unknown | Unknown | 173.72 | Unknown | 190.44 | 427.46 | -237.02 | Yes | N/A | N/A | 2024-09-24 | 2024-10-21 | 28 | 20 | 2024-10-21 | 2024-10-11 | Unknown | Unknown | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2025-01-30 | 112 | 80 | Unknown | 2025-01-27 | Unknown | Unknown | 2025-01-30 | 2025-02-18 | 1900-01-19 | 14 | 2025-02-18 | 2025-02-18 | 1 | 1 | 140 | 100 | 21 | 15 | 161 | 115 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -686 | -491 | No | 2024-07-24 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-24 | 2024-07-24 | 2024-07-30 | IOU Designed & Installed | N/A | Yes | 5 | 4.93 | Unknown | Unknown | Unknown | Unknown | 4.93 | Unknown | 186.52 | 4.93 | 181.59 | Yes | N/A | N/A | 2024-07-24 | 2024-07-29 | 6 | 4 | 2024-07-29 | 2024-07-24 | Unknown | Unknown | 2024-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-24 | 2024-07-30 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-07-30 | 2024-08-14 | 1900-01-15 | 12 | 2024-08-14 | 2024-08-14 | 1 | 1 | 13 | 9 | 17 | 13 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 30.05 | 30.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-15 | -550 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-20 | 2024-12-20 | 2025-06-12 | IOU Designed & Installed | N/A | No | N/A | 774.94 | Unknown | Unknown | Unknown | 51.22 | 723.72 | Unknown | 1522.88 | 774.94 | 747.94 | Yes | N/A | N/A | 2024-12-20 | 2024-12-19 | Unknown | Unknown | 2024-12-19 | 2025-01-13 | 26 | 18 | 2025-01-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-06-12 | 151 | 109 | Unknown | 2025-06-02 | Unknown | Unknown | 2025-06-12 | 2025-06-13 | 1900-01-01 | 2 | 2025-06-13 | 2025-06-13 | 1 | 1 | 151 | 109 | 29 | 21 | 180 | 130 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | 48.05 | 48.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-28 | -335 | -240 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-29 | 2024-01-29 | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 1419.78 | Unknown | Unknown | Unknown | 4.49 | 1415.29 | 3981 | 2445.62 | 1419.78 | 1025.84 | Yes | N/A | N/A | 2024-01-29 | 2024-06-26 | 150 | 108 | 2024-06-26 | 2024-06-28 | 3 | 3 | 2024-06-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-28 | 2024-09-09 | 74 | 52 | Unknown | 2024-09-04 | Unknown | Unknown | 2024-09-09 | 2024-09-30 | 1900-01-21 | 16 | 2024-09-30 | 2024-09-27 | Unknown | Unknown | 224 | 160 | 25 | 19 | 249 | 179 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-07 | 538 | 385 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-15 | 2024-05-08 | Unknown | IOU Designed & Installed | N/A | No | N/A | 6412.5 | 6144.72 | Unknown | 21.84 | -2738 | 2983.94 | Unknown | 2737.53 | 6412.5 | -3674.97 | Yes | N/A | N/A | 2022-04-15 | 2024-05-17 | 764 | 546 | 2024-05-17 | 2024-07-05 | 50 | 36 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | Unknown | Unknown | 2024-09-26 | 2024-09-26 | 1 | 1 | 764 | 546 | 51 | 37 | 815 | 583 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-27 | -468 | -335 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-16 | 2023-07-16 | 2023-11-10 | IOU Designed & Installed | N/A | No | N/A | 0.82 | -11.64 | Unknown | Unknown | Unknown | 12.46 | 3981 | 869.81 | 0.82 | 868.99 | Yes | N/A | N/A | 2023-07-16 | 2023-07-16 | 1 | 0 | 2023-07-16 | 2023-07-16 | 1 | 0 | 2023-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-16 | 2023-11-10 | 118 | 85 | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2023-11-20 | 1900-01-10 | 7 | 2023-11-20 | 2023-11-17 | Unknown | Unknown | 119 | 85 | 12 | 7 | 131 | 92 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | IMPERIAL BEACH | 115 | 115 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-06 | -421 | -302 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-13 | 2023-12-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 971.16 | -25.96 | Unknown | Unknown | Unknown | 997.12 | 3981 | 925.47 | 971.16 | -45.69 | Yes | N/A | N/A | 2023-12-13 | 2023-09-07 | Unknown | Unknown | 2023-09-07 | 2024-04-01 | 208 | 148 | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-01-12 | 31 | 23 | 2024-04-01 | 2024-03-13 | Unknown | Unknown | Unknown | 2024-04-01 | Unknown | Unknown | Unknown | 2024-04-12 | Unknown | Unknown | 2024-04-12 | 2024-04-11 | Unknown | Unknown | 0 | 0 | 239 | 171 | 239 | 171 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | OCEANSIDE | 47 | 47 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-18 | 183 | 132 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-21 | 2023-09-25 | 2023-11-10 | IOU Designed & Installed | N/A | No | N/A | 611.8 | -18.77 | Unknown | Unknown | Unknown | 630.57 | 3981 | 810.31 | 611.8 | 198.51 | Yes | N/A | N/A | 2023-09-21 | 2023-04-19 | Unknown | Unknown | 2023-04-19 | 2023-09-25 | 160 | 114 | 2023-09-25 | Unknown | Unknown | Unknown | 2023-09-25 | 2023-10-11 | 17 | 13 | 2023-09-25 | 2023-11-10 | 47 | 35 | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2023-11-20 | 1900-01-10 | 7 | 2023-11-20 | 2023-11-17 | Unknown | Unknown | 47 | 35 | 188 | 134 | 235 | 169 | Steps 2,3,5,6,7 | 16 | 12 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN JUAN CAPISTRANO | N/A | 130 | 130 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-01-01 | 806 | 576 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-03 | 2023-09-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | 9169.72 | Unknown | Unknown | Unknown | Unknown | 9169.72 | 3981 | 833.33 | 9169.72 | -8336.39 | Yes | N/A | N/A | 2023-01-03 | 2023-08-22 | 232 | 166 | 2023-08-22 | 2023-09-11 | 21 | 15 | 2023-09-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-09 | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | Unknown | 2025-03-18 | Unknown | Unknown | 2025-03-18 | 2025-03-17 | Unknown | Unknown | 232 | 166 | 21 | 15 | 253 | 181 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2019-12-31 | 1269 | 908 | No | 2019-07-22 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2019-06-11 | 2019-06-11 | Unknown | IOU Designed & Installed | N/A | Yes | 1366 | 889.77 | -8.86 | Unknown | Unknown | 4.64 | 893.99 | 13818 | 93.77 | 889.77 | -796 | Yes | N/A | N/A | 2019-06-11 | 2023-04-18 | 1408 | 1006 | 2023-04-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2019-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-22 | Unknown | Unknown | 2023-06-22 | 2023-06-22 | 1 | 1 | 1408 | 1006 | 1 | 1 | 1409 | 1007 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-14 | -432 | -309 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 621.31 | -7.03 | Unknown | Unknown | Unknown | 628.34 | Unknown | 363.72 | 621.31 | -257.59 | Yes | N/A | N/A | 2023-02-01 | 2023-02-02 | 2 | 2 | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-09 | Unknown | Unknown | 2023-08-09 | 2023-08-09 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Commercial | Disadvantaged Community,Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2022-09-16 | 576 | 411 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-09-16 | 2022-02-24 | 2024-03-18 | IOU Designed & Installed | N/A | No | N/A | 42425.14 | 4950.17 | Unknown | 229.48 | 146.9 | 37098.59 | 2616445 | 68896.93 | 42425.14 | 26471.79 | Yes | N/A | N/A | 2021-09-16 | 2023-03-03 | 534 | 382 | 2023-03-03 | 2023-08-04 | 155 | 111 | 2023-05-19 | 2023-08-31 | 45 | 31 | 2023-07-12 | 2023-10-20 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-04-01 | 89 | 63 | 2024-03-18 | 2024-04-17 | 1900-01-30 | 23 | 2024-04-17 | 2024-04-14 | Unknown | Unknown | 579 | 413 | 366 | 262 | 945 | 675 | Steps 2,3,5,6,7 | 141 | 101 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-27 | -309 | -221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-23 | 2024-03-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 23.3 | Unknown | Unknown | Unknown | Unknown | 23.3 | 3981 | 753.64 | 23.3 | 730.34 | Yes | N/A | N/A | 2024-02-23 | 2024-02-28 | 6 | 4 | 2024-02-28 | 2024-03-02 | 4 | 3 | 2024-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | Unknown | Unknown | 2025-02-21 | 2025-02-21 | 1 | 1 | 6 | 4 | 5 | 4 | 11 | 8 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | Applicant Design | Commercial | N/A | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-01 | 843 | 603 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | 2025-03-01 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 92689.63 | 31676.63 | Unknown | 1427.09 | 1846.31 | 57739.6 | 11077484 | 74742.2 | 92689.63 | -17947.43 | Yes | N/A | N/A | 2023-10-12 | 2024-05-15 | 217 | 155 | 2024-05-15 | 2024-11-27 | 197 | 141 | 2024-06-13 | 2024-11-26 | 99 | 71 | 2024-11-26 | 2024-12-06 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-01 | 2025-06-21 | 1900-04-22 | 80 | 2025-06-21 | 2025-06-21 | 1 | 0 | 316 | 226 | 322 | 230 | 638 | 456 | Steps 2,3,5,6,7 | 167 | 119 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 103 | 103 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-16 | -543 | -390 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-01 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | -2299.47 | Unknown | Unknown | Unknown | -2939 | 639.53 | Unknown | 2966.95 | -2299.47 | 5266.42 | Yes | N/A | N/A | 2024-11-01 | 2024-12-05 | 35 | 25 | 2024-12-05 | 2024-12-18 | 14 | 10 | 2024-12-18 | 2025-02-28 | 73 | 53 | Unknown | Unknown | Unknown | Unknown | 2025-03-06 | 2025-03-31 | 26 | 18 | Unknown | 2025-03-28 | Unknown | Unknown | 2025-03-31 | 2025-04-21 | 1900-01-21 | 16 | 2025-04-21 | 2025-04-21 | 1 | 1 | 134 | 96 | 37 | 27 | 171 | 123 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-12 | -32 | -25 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-25 | 2023-04-26 | 2023-06-15 | IOU Designed & Installed | N/A | No | N/A | -564.5 | 1632.12 | Unknown | 358.79 | -3313 | 757.59 | Unknown | 2992.35 | -564.5 | 3556.85 | Yes | N/A | N/A | 2023-04-25 | 2023-06-06 | 43 | 31 | 2023-06-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-15 | 2023-12-11 | 1900-06-28 | 128 | 2023-12-11 | 2023-12-11 | 1 | 1 | 43 | 31 | 181 | 129 | 224 | 160 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 33 | 33 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-13 | -619 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | 2024-09-11 | IOU Designed & Installed | N/A | No | N/A | 770.01 | Unknown | Unknown | Unknown | 8.02 | 761.99 | 3981 | 278.35 | 770.01 | -491.66 | Yes | N/A | N/A | 2024-08-13 | 2024-08-30 | 18 | 14 | 2024-08-30 | 2024-08-30 | 1 | 1 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-09-11 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-09-11 | 2024-10-02 | 1900-01-21 | 16 | 2024-10-02 | 2024-10-02 | 1 | 1 | 31 | 23 | 24 | 18 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 292.1 | 292.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-02 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-07 | 2024-11-07 | 2025-02-06 | IOU Designed & Installed | N/A | No | N/A | 2008.81 | 541.28 | Unknown | Unknown | Unknown | 1467.53 | 3981 | 1991.52 | 2008.81 | -17.29 | Yes | N/A | N/A | 2024-11-07 | 2024-11-25 | 19 | 13 | 2024-11-25 | 2024-12-30 | 36 | 26 | 2024-12-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-06 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-02-28 | 1900-01-22 | 17 | 2025-02-28 | 2025-02-28 | 1 | 1 | 20 | 14 | 60 | 44 | 80 | 58 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community,Tribal Community | PALA | N/A | 41.03 | 41.03 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-19 | -242 | -174 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-19 | 2023-12-19 | 2024-03-04 | IOU Designed & Installed | N/A | No | N/A | -1692.32 | 2168.96 | Unknown | 1072.12 | -6510 | 1576.6 | Unknown | 3254.8 | -1692.32 | 4947.12 | Yes | N/A | N/A | 2023-12-19 | 2024-01-23 | 36 | 26 | 2024-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | 2024-02-20 | Unknown | Unknown | 2024-02-20 | 2024-02-20 | 1 | 1 | 36 | 26 | 1 | 1 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 486 | 486 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | 595 | 426 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-22 | 2024-02-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2418.36 | -30.63 | Unknown | Unknown | Unknown | 2448.99 | 73445 | 6554.67 | 2418.36 | 4136.31 | Yes | N/A | N/A | 2024-02-22 | 2023-10-17 | Unknown | Unknown | 2023-10-17 | 2024-08-09 | 298 | 214 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-09 | 2025-05-27 | 292 | 208 | Unknown | 2025-04-10 | Unknown | Unknown | Unknown | 2025-04-21 | Unknown | Unknown | 2025-04-21 | 2025-04-18 | Unknown | Unknown | 292 | 208 | 298 | 214 | 590 | 422 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-03 | -473 | -339 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-03-01 | 2024-09-09 | IOU Designed & Installed | N/A | No | N/A | 1010.22 | Unknown | Unknown | Unknown | 11.1 | 999.12 | 3981 | 790.36 | 1010.22 | -219.86 | Yes | N/A | N/A | 2024-02-15 | 2024-01-18 | Unknown | Unknown | 2024-01-18 | 2024-03-02 | 45 | 32 | 2024-03-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-02 | 2024-09-09 | 192 | 136 | Unknown | 2025-02-27 | Unknown | Unknown | 2024-09-09 | 2024-09-17 | 1900-01-08 | 7 | 2024-09-17 | 2024-09-17 | 1 | 1 | 192 | 136 | 55 | 40 | 247 | 176 | Steps 2,3,5,6,7 | 171 | 123 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | N/A | CARDIFF | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-28 | -662 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-28 | 2025-05-08 | 2025-05-19 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1315.61 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-28 | 2025-05-08 | 11 | 9 | 2025-05-08 | 2025-05-08 | 1 | 1 | 2025-05-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-08 | 2025-05-19 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-05-19 | 2025-06-04 | 1900-01-16 | 13 | 2025-06-04 | 2025-06-04 | 1 | 1 | 23 | 17 | 19 | 15 | 42 | 32 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO MISSION VIEJO | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-01 | 218 | 157 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | 2023-11-03 | 2024-01-04 | IOU Designed & Installed | N/A | No | N/A | 965.97 | 326.96 | Unknown | Unknown | Unknown | 639.01 | 7158 | 1736.15 | 965.97 | 770.18 | Yes | N/A | N/A | 2023-11-03 | 2023-11-03 | 1 | 1 | 2023-11-03 | 2023-12-20 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-20 | 2023-12-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | 2024-01-05 | 1900-01-01 | 2 | 2024-01-05 | 2024-01-05 | 1 | 1 | 1 | 1 | 51 | 37 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 48 | 48 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-29 | -563 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2023-12-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3.67 | -4.45 | Unknown | Unknown | Unknown | 8.12 | 3981 | 786.93 | 3.67 | 783.26 | Yes | N/A | N/A | 2023-12-27 | 2023-09-11 | Unknown | Unknown | 2023-09-11 | 2023-12-27 | 108 | 78 | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-02-13 | 1 | 1 | 0 | 0 | 109 | 79 | 109 | 79 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-23 | 63 | 46 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-23 | 2024-01-23 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1194.51 | -43.8 | Unknown | Unknown | -119 | 1357.31 | Unknown | 17.01 | 1194.51 | -1177.5 | Yes | N/A | N/A | 2024-01-23 | 2024-01-23 | 1 | 1 | 2024-01-23 | 2024-03-13 | 51 | 37 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-03-06 | Unknown | Unknown | Unknown | 2024-03-13 | Unknown | Unknown | Unknown | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-03-26 | Unknown | Unknown | 1 | 1 | 51 | 37 | 52 | 38 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 2.7 | 2.7 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-11 | -69 | -50 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-04 | 2023-12-19 | 2024-04-01 | IOU Designed & Installed | N/A | No | N/A | 12.53 | -11.13 | Unknown | Unknown | Unknown | 23.66 | 3981 | 872.5 | 12.53 | 859.97 | Yes | N/A | N/A | 2023-12-04 | 2023-12-19 | 16 | 12 | 2023-12-19 | 2023-12-19 | 1 | 1 | 2023-12-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-04-01 | 105 | 75 | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-05-06 | 1900-02-04 | 26 | 2024-05-06 | 2025-05-03 | 363 | 260 | 121 | 87 | 400 | 287 | 521 | 374 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | DANA POINT | N/A | 27 | 27 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-18 | -544 | -389 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-05 | 2024-09-05 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3614.58 | 165.46 | Unknown | Unknown | 35.83 | 3413.29 | 3981 | 2512.86 | 3614.58 | -1101.72 | Yes | N/A | N/A | 2024-09-05 | 2024-10-09 | 35 | 25 | 2024-10-09 | 2024-10-17 | 9 | 7 | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-17 | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | Unknown | Unknown | Unknown | 2025-02-20 | Unknown | Unknown | 2025-02-20 | 2025-02-20 | 1 | 1 | 35 | 25 | 10 | 8 | 45 | 33 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-11 | -610 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-20 | 2025-02-20 | 2025-04-04 | IOU Designed & Installed | N/A | No | N/A | 684.06 | -11.86 | Unknown | Unknown | Unknown | 695.92 | Unknown | 2074.67 | 684.06 | 1390.61 | Yes | N/A | N/A | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | 2025-02-20 | 1 | 1 | 2025-02-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-04-04 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-10 | 1900-01-06 | 5 | 2025-04-10 | 2025-04-10 | 1 | 1 | 45 | 33 | 9 | 7 | 54 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | DANA POINT | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-06 | -647 | -462 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-10 | 2025-01-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 33.42 | Unknown | Unknown | Unknown | Unknown | 33.42 | 3981 | 1716.42 | 33.42 | 1683 | Yes | N/A | N/A | 2025-01-10 | 2025-01-10 | 1 | 1 | 2025-01-10 | 2025-01-10 | 1 | 1 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | Unknown | Unknown | 2025-02-27 | 2025-02-27 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-07 | -142 | -102 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-14 | 2023-08-29 | 2024-12-13 | IOU Designed & Installed | N/A | No | N/A | 3054.36 | 390.24 | Unknown | 117.73 | 10.29 | 2536.1 | 3981 | 2644.02 | 3054.36 | -410.34 | Yes | N/A | N/A | 2023-08-14 | 2023-11-08 | 87 | 63 | 2023-11-08 | 2023-11-08 | 1 | 1 | 2023-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2024-12-13 | 401 | 287 | Unknown | 2024-12-13 | Unknown | Unknown | 2024-12-13 | 2025-01-16 | 1900-02-03 | 25 | 2025-01-16 | 2025-01-16 | 1 | 1 | 488 | 350 | 37 | 27 | 525 | 377 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 51 | 51 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-03 | -301 | -216 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-14 | 2023-09-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 28.58 | Unknown | Unknown | Unknown | Unknown | 28.58 | 3981 | 1415.62 | 28.58 | 1387.04 | Yes | N/A | N/A | 2023-09-14 | 2023-06-26 | Unknown | Unknown | 2023-06-26 | 2024-06-17 | 358 | 256 | 2024-06-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | Unknown | Unknown | 2024-08-06 | 2024-08-06 | 1 | 1 | 0 | 0 | 359 | 257 | 359 | 257 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-25 | -519 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-10-07 | 2025-01-07 | IOU Designed & Installed | N/A | No | N/A | 5.88 | Unknown | Unknown | Unknown | Unknown | 5.88 | 3981 | 999.88 | 5.88 | 994 | Yes | N/A | N/A | 2024-08-08 | 2024-09-17 | 41 | 29 | 2024-09-17 | 2024-10-07 | 21 | 15 | 2024-10-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-07 | 2025-01-07 | 93 | 67 | Unknown | Unknown | Unknown | Unknown | 2025-01-07 | 2025-01-23 | 1900-01-16 | 13 | 2025-01-23 | 2025-01-22 | Unknown | Unknown | 134 | 96 | 38 | 28 | 172 | 124 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-15 | -265 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-21 | 2024-06-21 | 2024-07-19 | IOU Designed & Installed | N/A | No | N/A | 16.09 | Unknown | Unknown | Unknown | Unknown | 16.09 | 3941 | 1035.85 | 16.09 | 1019.76 | Yes | N/A | N/A | 2024-06-21 | 2024-05-08 | Unknown | Unknown | 2024-05-08 | 2024-06-21 | 45 | 33 | 2024-06-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-21 | 2024-07-19 | 29 | 21 | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-07-25 | 1900-01-06 | 5 | 2024-07-25 | 2024-07-24 | Unknown | Unknown | 29 | 21 | 52 | 38 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-01 | -535 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-11 | 2025-03-25 | 2025-04-14 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1777.92 | Unknown | Unknown | Yes | N/A | N/A | 2025-02-11 | 2025-01-27 | Unknown | Unknown | 2025-01-27 | 2025-03-25 | 58 | 42 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-04-14 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-04-14 | 2025-05-15 | 1900-01-31 | 24 | 2025-05-15 | 2025-05-15 | 1 | 1 | 21 | 15 | 91 | 67 | 112 | 82 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-08-26 | 324 | 231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-19 | 2024-03-19 | 2024-06-27 | IOU Designed & Installed | N/A | No | N/A | 7225.09 | Unknown | Unknown | Unknown | Unknown | 7225.09 | Unknown | Not available | 7225.09 | Unknown | Yes | N/A | N/A | 2024-03-19 | 2024-03-19 | 1 | 1 | 2024-03-19 | 2024-03-26 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-07-15 | 1900-01-18 | 13 | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 28 | 20 | 29 | 21 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-05 | -547 | -391 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-21 | 2023-02-23 | 2023-04-06 | IOU Designed & Installed | N/A | No | N/A | 815.37 | 243.32 | Unknown | 155.78 | Unknown | 416.27 | 3981 | 596.01 | 815.37 | -219.36 | Yes | N/A | N/A | 2023-02-21 | 2023-02-23 | 3 | 3 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | 2023-04-06 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2023-04-06 | 2023-04-07 | 1900-01-01 | 2 | 2023-04-07 | 2023-04-07 | 1 | 1 | 46 | 34 | 3 | 3 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-01 | -533 | -382 | No | 2023-02-15 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | 2023-02-21 | IOU Designed & Installed | N/A | Yes | 33 | -13.83 | -10.02 | Unknown | Unknown | Unknown | -3.81 | 3981 | 341 | -13.83 | 354.83 | Yes | N/A | N/A | 2023-02-15 | 2023-03-20 | 34 | 24 | 2023-03-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | 2023-02-21 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-02-21 | 2023-05-18 | 1900-03-27 | 63 | 2023-05-18 | 2023-05-18 | 1 | 1 | 41 | 29 | 88 | 64 | 129 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LA JOLLA | N/A | 17 | 17 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-25 | -322 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-05 | 2023-06-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -95.19 | -6.02 | Unknown | Unknown | -642.51 | 553.34 | Unknown | 646.79 | -95.19 | 741.98 | Yes | N/A | N/A | 2023-04-05 | 2023-06-09 | 66 | 48 | 2023-06-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-17 | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | Unknown | Unknown | Unknown | 2024-04-09 | Unknown | Unknown | 2024-04-09 | 2024-04-09 | 1 | 1 | 66 | 48 | 1 | 1 | 67 | 49 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-19 | -519 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-05-02 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | 1393.79 | -20.17 | Unknown | Unknown | 4.49 | 1409.47 | 3981 | 771.74 | 1393.79 | -622.05 | Yes | N/A | N/A | 2024-02-15 | 2024-01-02 | Unknown | Unknown | 2024-01-02 | 2024-05-07 | 127 | 91 | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | 2024-07-02 | 57 | 41 | Unknown | 2024-06-28 | Unknown | Unknown | 2024-07-02 | 2024-07-18 | 1900-01-16 | 13 | 2024-07-18 | 2024-07-18 | 1 | 1 | 57 | 41 | 145 | 105 | 202 | 146 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Commercial | N/A | CB 1107-G7 | CARLSBAD | 3874 | 3874 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-02-15 | 39 | 28 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-02 | 2022-12-02 | 2025-01-03 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 366784.34 | 101357.93 | Unknown | 158.65 | 3793.32 | 261474.44 | 1911125 | 184585.57 | 366784.34 | -182198.77 | Yes | N/A | N/A | 2022-12-02 | 2023-04-11 | 131 | 93 | 2023-04-11 | 2023-08-21 | 133 | 95 | 2023-05-22 | 2023-08-17 | 25 | 15 | 2023-04-12 | 2024-12-13 | 183 | 132 | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | 2024-12-06 | 450 | 322 | 2025-01-03 | 2025-03-26 | 1900-03-23 | 59 | 2025-03-26 | 2025-03-26 | 1 | 1 | 156 | 108 | 850 | 609 | 1006 | 717 | Steps 2,3,5,6,7 | 218 | 156 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-28 | -442 | -316 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-05-05 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | 900.68 | -8.23 | Unknown | Unknown | 19.25 | 889.66 | 3885 | 702.88 | 900.68 | -197.8 | Yes | N/A | N/A | 2023-03-17 | 2023-05-05 | 50 | 36 | 2023-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-05 | 2023-10-11 | 160 | 114 | Unknown | 2023-10-10 | Unknown | Unknown | 2023-10-11 | 2023-10-13 | 1900-01-02 | 3 | 2023-10-13 | 2023-10-13 | 1 | 1 | 210 | 150 | 4 | 4 | 214 | 154 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-20 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-07 | 2023-04-10 | Unknown | IOU Designed & Installed | N/A | No | N/A | 198.67 | -2.23 | Unknown | Unknown | Unknown | 200.9 | Unknown | 273.56 | 198.67 | 74.89 | Yes | N/A | N/A | 2023-04-07 | 2023-04-20 | 14 | 10 | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-18 | 1 | 1 | 14 | 10 | 1 | 1 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-25 | -593 | -424 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-13 | 2023-06-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | -16.36 | -11.86 | Unknown | Unknown | Unknown | -4.5 | 3981 | 464.78 | -16.36 | 481.14 | Yes | N/A | N/A | 2023-06-13 | 2023-06-13 | 1 | 1 | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-13 | Unknown | Unknown | 2023-07-13 | 2023-07-13 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-10 | -638 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-31 | 2024-08-08 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 1644.01 | -32.62 | Unknown | Unknown | Unknown | 1676.63 | Unknown | 1909.39 | 1644.01 | 265.38 | Yes | N/A | N/A | 2024-07-31 | 2024-06-27 | Unknown | Unknown | 2024-06-27 | 2024-08-15 | 50 | 36 | 2024-08-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-15 | 2024-08-26 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-09-10 | 1900-01-15 | 12 | 2024-09-10 | 2024-09-10 | 1 | 1 | 12 | 8 | 67 | 49 | 79 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-02-23 | -279 | -200 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-26 | 2024-04-04 | 2024-05-14 | IOU Designed & Installed | N/A | No | N/A | 241.75 | -8.48 | Unknown | Unknown | Unknown | 250.23 | 3981 | 819.22 | 241.75 | 577.47 | Yes | N/A | N/A | 2024-02-26 | 2024-02-29 | 4 | 4 | 2024-02-29 | 2024-04-12 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-05-01 | 20 | 14 | Unknown | 2024-05-14 | Unknown | Unknown | 2024-05-14 | 2024-05-22 | 1900-01-08 | 7 | 2024-05-22 | 2024-05-20 | Unknown | Unknown | 24 | 18 | 53 | 39 | 77 | 57 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 132.05 | 132.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-06 | -559 | -400 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-04 | 2023-07-18 | IOU Designed & Installed | N/A | No | N/A | -19.31 | -7.14 | Unknown | Unknown | 1.48 | -13.65 | 3981 | 657.09 | -19.31 | 676.4 | Yes | N/A | N/A | 2023-04-04 | 2023-04-20 | 17 | 13 | 2023-04-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-20 | 2023-07-18 | 90 | 64 | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-07-28 | 1900-01-10 | 9 | 2023-07-28 | 2023-07-28 | 1 | 1 | 107 | 77 | 12 | 10 | 119 | 87 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARDIFF | ENCINITAS | 149.05 | 149.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-02 | 471 | 338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-25 | 2023-10-25 | Unknown | IOU Designed & Installed | N/A | No | N/A | 643.13 | -12.92 | Unknown | Unknown | Unknown | 656.05 | 3981 | 1131.38 | 643.13 | 488.25 | Yes | N/A | N/A | 2023-10-25 | 2023-09-28 | Unknown | Unknown | 2023-09-28 | 2023-10-25 | 28 | 20 | 2023-10-25 | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-11 | 8 | 6 | 2023-10-25 | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | Unknown | Unknown | Unknown | 2025-04-17 | Unknown | Unknown | 2025-04-17 | 2025-04-17 | 1 | 1 | 0 | 0 | 37 | 27 | 37 | 27 | Steps 2,3,5,6,7 | 534 | 382 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-27 | -527 | -378 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2024-06-19 | IOU Designed & Installed | N/A | No | N/A | 37.08 | -28.58 | Unknown | Unknown | Unknown | 65.66 | 3981 | 813.06 | 37.08 | 775.98 | Yes | N/A | N/A | 2024-04-25 | 2024-03-28 | Unknown | Unknown | 2024-03-28 | 2024-04-25 | 29 | 21 | 2024-04-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-25 | 2024-06-19 | 56 | 40 | Unknown | Unknown | Unknown | Unknown | 2024-06-19 | 2024-07-08 | 1900-01-19 | 14 | 2024-07-08 | 2024-10-16 | 101 | 73 | 56 | 40 | 150 | 108 | 206 | 148 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 76 | 76 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-09 | -469 | -336 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-27 | 2023-12-27 | 2024-06-11 | IOU Designed & Installed | N/A | No | N/A | 874.02 | -7.86 | Unknown | Unknown | 7.87 | 874.01 | 3981 | 1181.8 | 874.02 | 307.78 | Yes | N/A | N/A | 2023-12-27 | 2024-01-02 | 7 | 5 | 2024-01-02 | 2024-03-18 | 77 | 55 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | 2024-06-11 | 86 | 62 | Unknown | 2024-05-28 | Unknown | Unknown | 2024-06-11 | 2024-06-27 | 1900-01-16 | 13 | 2024-06-27 | 2024-06-27 | 1 | 1 | 93 | 67 | 95 | 69 | 188 | 136 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 68 | 68 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-25 | -318 | -228 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-06 | 2023-04-14 | 2024-03-12 | IOU Designed & Installed | N/A | No | N/A | 1736.69 | 589.92 | Unknown | 55.15 | Unknown | 1091.62 | 3885 | 892.34 | 1736.69 | -844.35 | Yes | N/A | N/A | 2023-04-06 | 2023-04-14 | 9 | 7 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | 2024-03-12 | 334 | 238 | Unknown | Unknown | Unknown | Unknown | 2024-03-12 | 2024-03-13 | 1900-01-01 | 2 | 2024-03-13 | 2024-03-13 | 1 | 1 | 343 | 245 | 3 | 3 | 346 | 248 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-08 | -476 | -341 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-10 | 2024-05-16 | 2024-12-02 | IOU Designed & Installed | N/A | No | N/A | 1223.62 | Unknown | Unknown | Unknown | 12.6 | 1211.02 | 3981 | 1078.83 | 1223.62 | -144.79 | Yes | N/A | N/A | 2024-05-10 | 2024-05-22 | 13 | 9 | 2024-05-22 | 2024-05-22 | 1 | 1 | 2024-05-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-22 | 2024-12-02 | 195 | 139 | Unknown | 2024-11-22 | Unknown | Unknown | 2024-12-02 | 2024-12-18 | 1900-01-16 | 13 | 2024-12-18 | 2024-12-18 | 1 | 1 | 208 | 148 | 19 | 15 | 227 | 163 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 11 | 11 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-15 | -99 | -72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | 2023-06-27 | 2023-09-26 | IOU Designed & Installed | N/A | No | N/A | -24.11 | -17.99 | Unknown | Unknown | Unknown | -6.12 | Unknown | 495.75 | -24.11 | 519.86 | Yes | N/A | N/A | 2023-06-27 | 2023-06-27 | 1 | 1 | 2023-06-27 | 2023-06-27 | 1 | 1 | 2023-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-27 | 2023-09-26 | 92 | 66 | Unknown | Unknown | Unknown | Unknown | 2023-09-26 | 2023-12-07 | 1900-03-13 | 53 | 2023-12-07 | 2023-12-07 | 1 | 1 | 93 | 67 | 75 | 55 | 168 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONITA | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-23 | -631 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-11 | 2024-11-11 | 2024-12-13 | IOU Designed & Installed | N/A | No | N/A | 479.26 | Unknown | Unknown | Unknown | 8.63 | 470.63 | 3981 | 298.35 | 479.26 | -180.91 | Yes | N/A | N/A | 2024-11-11 | 2024-11-21 | 11 | 9 | 2024-11-21 | 2024-11-21 | 1 | 1 | 2024-11-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-12-13 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-01-30 | 1900-02-17 | 35 | 2025-01-30 | 2025-01-30 | 1 | 1 | 34 | 26 | 51 | 37 | 85 | 63 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | EL CAJON | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-30 | 235 | 169 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-01 | 2023-08-18 | 2024-04-18 | IOU Designed & Installed | N/A | No | N/A | 35429.93 | 6123.17 | Unknown | Unknown | 1100.62 | 28206.14 | 216998.85 | 69427.23 | 35429.93 | 33997.3 | Yes | N/A | N/A | 2023-05-01 | 2023-04-18 | Unknown | Unknown | 2023-04-18 | 2024-04-12 | 361 | 259 | 2024-02-06 | 2024-02-06 | 1 | 1 | 2023-11-11 | 2024-04-10 | 5 | 3 | 2024-04-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-09-21 | 1900-06-05 | 112 | 2024-09-21 | 2024-09-21 | 1 | 0 | 1 | 1 | 524 | 374 | 525 | 375 | Steps 2,3,5,6,7 | 153 | 109 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | FALLBROOK | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-22 | -631 | -452 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-09 | 2024-12-09 | 2024-12-11 | IOU Designed & Installed | N/A | No | N/A | 27.79 | Unknown | Unknown | Unknown | Unknown | 27.79 | 3981 | 1597.33 | 27.79 | 1569.54 | Yes | N/A | N/A | 2024-12-09 | 2024-12-02 | Unknown | Unknown | 2024-12-02 | 2024-12-09 | 8 | 6 | 2024-12-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2024-12-11 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-12-11 | 2025-01-29 | 1900-02-18 | 36 | 2025-01-29 | 2025-01-29 | 1 | 1 | 3 | 3 | 59 | 43 | 62 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 71.05 | 71.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-06 | -624 | -447 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-20 | 2024-04-01 | 2024-05-13 | IOU Designed & Installed | N/A | No | N/A | 129.77 | -7.93 | Unknown | Unknown | Unknown | 137.7 | 3981 | 983.39 | 129.77 | 853.62 | Yes | N/A | N/A | 2024-03-20 | 2024-03-28 | 9 | 7 | 2024-03-28 | 2024-04-01 | 5 | 3 | 2024-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-01 | 2024-05-13 | 43 | 31 | Unknown | Unknown | Unknown | Unknown | 2024-05-13 | 2024-05-23 | 1900-01-10 | 9 | 2024-05-23 | 2024-05-23 | 1 | 1 | 52 | 38 | 17 | 13 | 69 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | Dana Point | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-19 | 86 | 63 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-23 | 2023-06-02 | IOU Designed & Installed | N/A | No | N/A | -1779.9 | 1633.17 | Unknown | Unknown | -4119 | 705.93 | Unknown | 7335.13 | -1779.9 | 9115.03 | Yes | N/A | N/A | 2023-03-23 | 2023-04-03 | 12 | 8 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-02 | 2023-07-14 | 1900-02-11 | 31 | 2023-07-14 | 2023-07-14 | 1 | 1 | 12 | 8 | 44 | 32 | 56 | 40 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-28 | -364 | -261 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-28 | 2024-10-28 | 2024-10-29 | IOU Designed & Installed | N/A | No | N/A | 1943.54 | 470.45 | Unknown | 48.3 | Unknown | 1424.79 | Unknown | 1620.31 | 1943.54 | -323.23 | Yes | N/A | N/A | 2024-10-28 | 2024-10-28 | 1 | 1 | 2024-10-28 | 2024-10-28 | 1 | 1 | 2024-10-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-28 | 2024-10-29 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2024-10-29 | 1899-12-31 | 1 | 2024-10-29 | 2024-10-29 | 1 | 1 | 3 | 3 | 3 | 3 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 14 | 14 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-09 | -270 | -195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-02-13 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 1964.33 | -38.78 | Unknown | Unknown | Unknown | 2003.11 | 3981 | 2035.16 | 1964.33 | 70.83 | Yes | N/A | N/A | 2025-01-23 | 2025-01-22 | Unknown | Unknown | 2025-01-22 | 2025-02-13 | 23 | 17 | 2025-02-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-13 | 2025-04-01 | 48 | 34 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-14 | 1900-01-13 | 10 | 2025-04-14 | 2025-04-14 | 1 | 1 | 48 | 34 | 38 | 28 | 86 | 62 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-18 | -329 | -236 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | 2024-12-20 | IOU Designed & Installed | N/A | No | N/A | 389.1 | Unknown | Unknown | Unknown | 7.9 | 381.2 | Unknown | 1164.26 | 389.1 | 775.16 | Yes | N/A | N/A | 2024-08-13 | 2024-08-29 | 17 | 13 | 2024-08-29 | 2024-10-11 | 44 | 32 | 2024-10-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-11 | 2024-12-20 | 71 | 51 | Unknown | 2024-12-13 | Unknown | Unknown | 2024-12-20 | 2025-01-23 | 1900-02-03 | 25 | 2025-01-23 | 2025-01-23 | 1 | 1 | 88 | 64 | 80 | 58 | 168 | 122 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-15 | -718 | -514 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-21 | 2023-11-21 | 2023-11-27 | IOU Designed & Installed | N/A | No | N/A | 66.43 | -6.31 | Unknown | Unknown | Unknown | 72.74 | 3661 | 598.28 | 66.43 | 531.85 | Yes | N/A | N/A | 2023-11-21 | 2023-11-21 | 1 | 1 | 2023-11-21 | 2023-11-21 | 1 | 1 | 2023-11-21 | 2023-12-01 | 4 | 4 | 2023-11-21 | 2023-11-28 | 8 | 6 | 2023-11-21 | 2023-11-27 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2023-11-27 | 2024-02-01 | 1900-03-07 | 49 | 2024-02-01 | 2023-11-28 | Unknown | Unknown | 12 | 10 | 76 | 56 | 88 | 66 | Steps 2,3,5,6,7 | 17 | 13 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 6 | 6 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-04 | -264 | -190 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2023-08-01 | 2023-08-14 | IOU Designed & Installed | N/A | No | N/A | 1196.91 | 401.98 | Unknown | 135.61 | Unknown | 659.32 | 3981 | 1039.97 | 1196.91 | -156.94 | Yes | N/A | N/A | 2023-08-01 | 2023-08-01 | 1 | 1 | 2023-08-01 | 2023-08-01 | 1 | 1 | 2023-08-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-01 | 2023-08-14 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-08-14 | 2023-08-14 | 1899-12-31 | 1 | 2023-08-14 | 2023-08-14 | 1 | 1 | 15 | 11 | 3 | 3 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-14 | 190 | 137 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-27 | 2024-05-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2793.23 | Unknown | Unknown | Unknown | 9.02 | 2784.21 | 541772 | 16690.82 | 2793.23 | 13897.59 | Yes | N/A | N/A | 2023-04-27 | 2023-04-17 | Unknown | Unknown | 2023-04-17 | 2024-05-10 | 390 | 280 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-10 | 2024-08-26 | 109 | 77 | Unknown | 2024-08-27 | Unknown | Unknown | Unknown | 2024-09-16 | Unknown | Unknown | 2024-09-16 | 2024-09-20 | 5 | 5 | 109 | 77 | 395 | 285 | 504 | 362 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | ALPINE | ALPINE | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-12 | -329 | -236 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-13 | 2024-12-19 | 2025-01-02 | IOU Designed & Installed | N/A | No | N/A | 478.2 | -4.5 | Unknown | Unknown | 3.58 | 479.12 | Unknown | 2635.69 | 478.2 | 2157.49 | Yes | N/A | N/A | 2024-12-13 | 2024-12-23 | 11 | 7 | 2024-12-23 | 2024-12-23 | 1 | 1 | 2024-12-23 | Unknown | Unknown | Unknown | 2025-01-13 | 2025-01-16 | 4 | 4 | 2024-12-27 | 2025-01-02 | 7 | 5 | Unknown | 2025-01-14 | Unknown | Unknown | 2025-01-02 | 2025-01-27 | 1900-01-25 | 18 | 2025-01-27 | 2025-01-17 | Unknown | Unknown | 18 | 12 | 31 | 23 | 49 | 35 | Steps 2,3,5,6,7 | 32 | 22 | Meeting | Meeting | Not Available | N/A
| R16 | OH | Applicant Design | Residential | Underserved Community | SAN DIEGO | N/A | 51.05 | 51.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-20 | -69 | -50 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-11 | 2024-12-11 | 2025-06-11 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 456.57 | 95.01 | Unknown | Unknown | -94 | 455.56 | Unknown | 94.02 | 456.57 | -362.55 | Yes | N/A | N/A | 2024-12-11 | 2024-12-11 | 1 | 1 | 2024-12-11 | 2025-01-09 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-11 | 2025-06-12 | 1900-01-01 | 2 | 2025-06-12 | 2025-06-12 | 1 | 1 | 1 | 1 | 33 | 25 | 34 | 26 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-01 | -581 | -416 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-22 | 2024-08-08 | 2024-11-21 | IOU Designed & Installed | N/A | No | N/A | -1317.34 | Unknown | Unknown | Unknown | -1359 | 41.66 | Unknown | 1358.71 | -1317.34 | 2676.05 | Yes | N/A | N/A | 2024-07-22 | 2024-08-08 | 18 | 14 | 2024-08-08 | 2024-08-08 | 1 | 1 | 2024-08-08 | 2024-11-21 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-11-21 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-12-02 | 1900-01-11 | 8 | 2024-12-02 | 2024-11-27 | Unknown | Unknown | 125 | 91 | 13 | 9 | 138 | 100 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | POWAY | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-23 | -560 | -401 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-04-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 749.77 | -8.54 | Unknown | Unknown | 75.5 | 682.81 | 3981 | 596.67 | 749.77 | -153.1 | Yes | N/A | N/A | 2023-03-22 | 2023-04-07 | 17 | 13 | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-07 | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | 2024-03-14 | 2024-03-12 | Unknown | Unknown | 17 | 13 | 0 | 0 | 17 | 13 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-08 | 155 | 112 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2024-01-18 | 2025-02-20 | IOU Designed & Installed | N/A | No | N/A | 13960.91 | 1802.33 | Unknown | Unknown | -14244.54 | 26403.12 | 0 | 14248.23 | 13960.91 | 287.32 | Yes | N/A | N/A | 2023-11-27 | 2023-11-22 | Unknown | Unknown | 2023-11-22 | 2025-01-09 | 415 | 297 | 2024-03-05 | 2024-03-07 | 3 | 3 | 2024-02-02 | 2025-01-31 | 89 | 62 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-20 | 2025-03-12 | 1900-01-20 | 15 | 2025-03-12 | 2025-03-12 | 1 | 1 | 3 | 3 | 526 | 375 | 529 | 378 | Steps 2,3,5,6,7 | 344 | 246 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 105 | 105 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-12 | 131 | 95 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2023-07-24 | 2024-07-19 | IOU Designed & Installed | N/A | No | N/A | 907.12 | Unknown | Unknown | Unknown | 42.12 | 865 | 3981 | 1099.94 | 907.12 | 192.82 | Yes | N/A | N/A | 2023-07-24 | 2023-05-22 | Unknown | Unknown | 2023-05-22 | 2023-07-28 | 68 | 50 | 2023-07-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-28 | 2024-07-19 | 358 | 256 | Unknown | 2024-07-05 | Unknown | Unknown | 2024-07-19 | 2024-09-20 | 1900-03-04 | 46 | 2024-09-20 | 2024-09-20 | 1 | 1 | 358 | 256 | 133 | 97 | 491 | 353 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-10 | -342 | -245 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-17 | 2024-12-17 | 2024-12-30 | IOU Designed & Installed | N/A | No | N/A | 864.34 | 465.14 | Unknown | 75.69 | Unknown | 323.51 | Unknown | 52.54 | 864.34 | -811.8 | Yes | N/A | N/A | 2024-12-17 | 2024-12-18 | 2 | 2 | 2024-12-18 | 2024-12-20 | 3 | 3 | 2024-12-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-20 | 2024-12-30 | 11 | 7 | Unknown | Unknown | Unknown | Unknown | 2024-12-30 | 2025-01-02 | 1900-01-03 | 4 | 2025-01-02 | 2025-01-02 | 1 | 1 | 13 | 9 | 8 | 8 | 21 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 91.4 | 91.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-06 | -554 | -397 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-11 | 2024-06-12 | 2024-10-21 | IOU Designed & Installed | N/A | No | N/A | -680.32 | -6.04 | Unknown | Unknown | -1120 | 445.72 | 3981 | 2251 | -680.32 | 2931.32 | Yes | N/A | N/A | 2024-06-11 | 2024-06-12 | 2 | 2 | 2024-06-12 | 2025-03-06 | 268 | 192 | 2025-03-06 | 2024-07-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-08 | 2024-10-21 | 106 | 76 | Unknown | 2024-10-18 | Unknown | Unknown | 2024-10-21 | 2024-11-05 | 1900-01-15 | 12 | 2024-11-05 | 2024-10-29 | Unknown | Unknown | 108 | 78 | 284 | 204 | 392 | 282 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | Applicant Design | Residential | Underserved Community | Oceanside | OCEANSIDE | 84190 | 84190 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-01-01 | 124 | 89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-03 | 2023-11-03 | 2025-03-13 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 126753.45 | 29543.6 | Unknown | Unknown | 2716.63 | 94493.22 | 391241 | 48435.22 | 126753.45 | -78318.23 | Yes | N/A | N/A | 2023-11-03 | 2024-03-14 | 133 | 95 | 2024-03-14 | 2024-06-20 | 99 | 71 | 2024-04-18 | 2025-04-22 | 364 | 260 | 2024-04-23 | 2025-04-18 | 277 | 197 | 2024-06-20 | Unknown | Unknown | Unknown | 2024-06-27 | 2025-04-02 | 280 | 200 | 2025-03-13 | 2025-05-05 | 1900-02-22 | 38 | 2025-05-05 | 2025-05-05 | 1 | 1 | 497 | 355 | 711 | 507 | 1208 | 862 | Steps 2,3,5,6,7 | 749 | 535 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-30 | -34 | -25 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-10 | 2024-09-11 | IOU Designed & Installed | N/A | No | N/A | 1029.86 | Unknown | Unknown | Unknown | 3.93 | 1025.93 | 3981 | 1237.65 | 1029.86 | 207.79 | Yes | N/A | N/A | 2024-01-10 | 2023-11-16 | Unknown | Unknown | 2023-11-16 | 2024-06-27 | 225 | 161 | 2024-06-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-27 | 2024-09-11 | 77 | 55 | Unknown | 2024-09-10 | Unknown | Unknown | 2024-09-11 | 2024-09-19 | 1900-01-08 | 7 | 2024-09-19 | 2024-09-26 | 8 | 6 | 77 | 55 | 242 | 174 | 319 | 229 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | SPRING VALLEY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-05-30 | -730 | -521 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-24 | 2025-06-24 | Unknown | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1623.02 | Unknown | Unknown | Yes | N/A | N/A | 2025-06-24 | 2025-06-03 | Unknown | Unknown | 2025-06-03 | 2025-06-24 | 22 | 16 | 2025-06-24 | 2025-07-30 | 37 | 27 | 2025-06-24 | 2025-06-27 | 4 | 4 | 2025-06-24 | 2025-07-08 | 15 | 11 | Unknown | Unknown | Unknown | Unknown | 2025-07-08 | 2025-07-11 | 1900-01-03 | 4 | 2025-07-11 | 2025-05-30 | Unknown | Unknown | 52 | 38 | 30 | 24 | 82 | 62 | Steps 2,3,5,6,7 | 39 | 29 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-26 | -246 | -177 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-28 | 2023-03-28 | 2024-01-23 | IOU Designed & Installed | N/A | No | N/A | 677.19 | 438.84 | Unknown | Unknown | Unknown | 238.35 | Unknown | 98.95 | 677.19 | -578.24 | Yes | N/A | N/A | 2023-03-28 | 2023-04-04 | 8 | 6 | 2023-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-04 | 2024-01-23 | 295 | 211 | Unknown | Unknown | Unknown | Unknown | 2024-01-23 | 2024-01-24 | 1900-01-01 | 2 | 2024-01-24 | 2024-01-24 | 1 | 1 | 303 | 217 | 3 | 3 | 306 | 220 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | Chula Vista | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-14 | 636 | 455 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-20 | 2024-06-20 | 2025-06-10 | IOU Designed & Installed | N/A | No | N/A | 10850.44 | 4848.91 | Unknown | Unknown | 25.44 | 5976.09 | 335293 | Not available | 10850.44 | Unknown | Yes | N/A | N/A | 2024-06-20 | 2024-06-12 | Unknown | Unknown | 2024-06-12 | 2024-10-29 | 140 | 100 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-29 | 2025-08-08 | 284 | 204 | Unknown | 2025-04-24 | Unknown | Unknown | 2025-06-10 | 2025-06-11 | 1900-01-01 | 2 | 2025-06-11 | 2025-06-11 | 1 | 1 | 284 | 204 | 143 | 103 | 427 | 307 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 8 | 8 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-03-23 | 358 | 257 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-22 | 2022-04-22 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | 2455.31 | 206.11 | Unknown | Unknown | 92.78 | 2156.42 | 3281 | 646.79 | 2455.31 | -1808.52 | Yes | N/A | N/A | 2022-04-22 | 2023-05-18 | 392 | 280 | 2023-05-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-18 | 2024-01-22 | 250 | 178 | Unknown | 2024-01-19 | Unknown | Unknown | 2024-01-22 | 2024-03-15 | 1900-02-22 | 40 | 2024-03-15 | 2024-03-15 | 1 | 1 | 642 | 458 | 55 | 41 | 697 | 499 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-30 | -530 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-26 | 2023-02-26 | Unknown | IOU Designed & Installed | N/A | No | N/A | -0.76 | -2.23 | Unknown | Unknown | Unknown | 1.47 | Unknown | 231.38 | -0.76 | 232.14 | Yes | N/A | N/A | 2023-02-26 | 2023-02-26 | 1 | 0 | 2023-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-19 | Unknown | Unknown | 2023-06-19 | 2023-06-19 | 1 | 1 | 1 | 0 | 1 | 1 | 2 | 1 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | RAMONA | N/A | 97.05 | 97.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-23 | -296 | -213 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-09 | 2024-03-09 | 2025-03-28 | IOU Designed & Installed | N/A | No | N/A | 4438.5 | 1212.48 | Unknown | Unknown | Unknown | 3226.02 | 3981 | 805.01 | 4438.5 | -3633.49 | Yes | N/A | N/A | 2024-03-09 | 2024-01-23 | Unknown | Unknown | 2024-01-23 | 2024-03-11 | 49 | 35 | 2024-03-11 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-11 | 2025-03-28 | 383 | 275 | Unknown | Unknown | Unknown | Unknown | 2025-03-28 | 2025-04-02 | 1900-01-05 | 4 | 2025-04-02 | 2025-04-02 | 1 | 1 | 383 | 275 | 56 | 40 | 439 | 315 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | OCEANSIDE | N/A | 77 | 77 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-05-16 | 22 | 17 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-05 | 2024-05-20 | IOU Designed & Installed | N/A | No | N/A | 43.62 | -11.86 | Unknown | Unknown | Unknown | 55.48 | Unknown | 1259.97 | 43.62 | 1216.35 | Yes | N/A | N/A | 2024-02-05 | 2024-02-05 | 1 | 1 | 2024-02-05 | 2024-02-05 | 1 | 1 | 2024-02-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-05 | 2024-05-20 | 106 | 76 | Unknown | Unknown | Unknown | Unknown | 2024-05-20 | 2024-06-07 | 1900-01-18 | 15 | 2024-06-07 | 2024-06-07 | 1 | 1 | 107 | 77 | 21 | 17 | 128 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 115.15 | 115.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-07-21 | -101 | -72 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-17 | 2024-01-17 | 2024-04-08 | IOU Designed & Installed | N/A | No | N/A | 5867.82 | Unknown | Unknown | Unknown | Unknown | 5867.82 | 3981 | 1092.82 | 5867.82 | -4775 | Yes | N/A | N/A | 2024-01-17 | 2023-12-12 | Unknown | Unknown | 2023-12-12 | 2024-02-08 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-02-16 | 9 | 7 | Unknown | 2024-04-01 | Unknown | Unknown | 2024-04-08 | 2024-04-15 | 1900-01-07 | 6 | 2024-04-15 | 2024-04-11 | Unknown | Unknown | 9 | 7 | 67 | 49 | 76 | 56 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LADERA RANCH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-12 | -306 | -219 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | -16.58 | -13.47 | Unknown | Unknown | Unknown | -3.11 | 3981 | 85.4 | -16.58 | 101.98 | Yes | N/A | N/A | 2024-03-14 | 2024-03-14 | 1 | 1 | 2024-03-14 | 2024-03-14 | 1 | 1 | 2024-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | Unknown | Unknown | 2024-04-12 | 2024-04-12 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | Both | IOU Design | Residential | Underserved Community | LA JOLLA | N/A | 3134.05 | 3134.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-02-22 | -73 | -54 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-11 | 2023-10-09 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1144.03 | -12.9 | Unknown | Unknown | -1145 | 13.87 | 7235 | 1893.95 | -1144.03 | 3037.98 | Yes | N/A | N/A | 2023-04-11 | 2023-10-09 | 182 | 130 | 2023-10-09 | 2023-11-09 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2023-12-01 | 23 | 17 | Unknown | 2023-11-20 | Unknown | Unknown | Unknown | 2024-02-09 | Unknown | Unknown | 2024-02-09 | 2023-12-11 | Unknown | Unknown | 205 | 147 | 32 | 24 | 237 | 171 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-23 | -513 | -368 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-10 | 2024-10-18 | 2025-04-17 | IOU Designed & Installed | N/A | No | N/A | 3287.8 | 254.7 | Unknown | Unknown | -1186 | 4219.1 | Unknown | 1180.79 | 3287.8 | -2107.01 | Yes | N/A | N/A | 2024-10-10 | 2025-01-03 | 86 | 62 | 2025-01-03 | 2025-01-10 | 8 | 6 | 2025-01-10 | 2025-02-01 | 23 | 16 | Unknown | Unknown | Unknown | Unknown | 2025-02-01 | 2025-04-17 | 76 | 54 | Unknown | 2025-04-17 | Unknown | Unknown | 2025-04-17 | 2025-04-28 | 1900-01-11 | 8 | 2025-04-28 | 2025-04-28 | 1 | 1 | 185 | 132 | 21 | 15 | 206 | 147 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-08 | 358 | 257 | No | 2022-08-26 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-26 | 2022-08-26 | 2024-03-28 | IOU Designed & Installed | N/A | Yes | 550 | 178.46 | -10.83 | Unknown | Unknown | Unknown | 189.29 | 7770 | 1018.32 | 178.46 | 839.86 | Yes | N/A | N/A | 2022-08-26 | 2024-02-27 | 551 | 393 | 2024-02-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-08-26 | 2024-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-28 | 2024-04-15 | 1900-01-18 | 13 | 2024-04-15 | 2024-05-31 | 47 | 35 | 551 | 393 | 66 | 48 | 617 | 441 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | LA JOLLA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-01 | 136 | 97 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-01 | 2023-03-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -553.79 | 1667.48 | Unknown | 299.75 | -3302 | 780.98 | 0 | 3301.74 | -553.79 | 3855.53 | Yes | N/A | N/A | 2023-03-01 | 2023-03-01 | 1 | 1 | 2023-03-01 | 2023-03-09 | 9 | 7 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 10 | 8 | 11 | 9 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 121.05 | 121.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-31 | -118 | -85 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-12 | 2023-04-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 610.63 | -17.64 | Unknown | Unknown | Unknown | 628.27 | 3981 | 725.86 | 610.63 | 115.23 | Yes | N/A | N/A | 2023-04-12 | 2023-04-14 | 3 | 3 | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-05 | Unknown | Unknown | 2023-07-05 | 2023-07-05 | 1 | 1 | 3 | 3 | 1 | 1 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-28 | -552 | -395 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-16 | 2023-12-16 | 2023-12-28 | IOU Designed & Installed | N/A | No | N/A | 695.08 | 424.15 | Unknown | Unknown | Unknown | 270.93 | Unknown | 515.81 | 695.08 | -179.27 | Yes | N/A | N/A | 2023-12-16 | 2023-12-16 | 1 | 0 | 2023-12-16 | 2023-12-16 | 1 | 0 | 2023-12-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-16 | 2023-12-28 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2023-12-28 | 2024-02-23 | 1900-02-26 | 42 | 2024-02-23 | 2024-02-23 | 1 | 1 | 14 | 9 | 60 | 43 | 74 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-30 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | Unknown | 2024-09-26 | IOU Designed & Installed | N/A | No | N/A | 30.17 | Unknown | Unknown | Unknown | Unknown | 30.17 | 3981 | 881 | 30.17 | 850.83 | Yes | N/A | N/A | 2024-05-16 | 2024-05-16 | 1 | 1 | 2024-05-16 | 2024-05-16 | 1 | 1 | 2024-05-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-16 | 2024-09-26 | 134 | 96 | Unknown | Unknown | Unknown | Unknown | 2024-09-26 | 2024-10-02 | 1900-01-06 | 5 | 2024-10-02 | 2024-10-02 | 1 | 1 | 135 | 97 | 9 | 7 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | RANCHO SANTA FE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-08 | -540 | -386 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-04 | 2023-04-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3.68 | -10.8 | Unknown | Unknown | Unknown | 7.12 | 3981 | 957.46 | -3.68 | 961.14 | Yes | N/A | N/A | 2023-04-04 | 2023-04-10 | 7 | 5 | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | Unknown | Unknown | 2023-08-18 | 2023-08-18 | 1 | 1 | 7 | 5 | 1 | 1 | 8 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | 7527 | 7527 | Not Available | >2MW | No | N/A | N/A | N/A | 2025-07-03 | -416 | -299 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-13 | 2023-12-27 | 2024-04-24 | IOU Designed & Installed | N/A | No | N/A | 309.7 | -11.77 | Unknown | Unknown | Unknown | 321.47 | 3981 | 792.71 | 309.7 | 483.01 | Yes | N/A | N/A | 2023-11-13 | 2023-12-27 | 45 | 33 | 2023-12-27 | 2023-12-27 | 1 | 1 | 2023-12-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2024-04-24 | 120 | 86 | Unknown | 2024-04-24 | Unknown | Unknown | 2024-04-24 | 2024-05-13 | 1900-01-19 | 14 | 2024-05-13 | 2024-05-13 | 1 | 1 | 165 | 119 | 22 | 16 | 187 | 135 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-22 | -642 | -460 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-07 | 2024-10-09 | 2024-10-23 | IOU Designed & Installed | N/A | No | N/A | 850.52 | 234.86 | Unknown | Unknown | Unknown | 615.66 | Unknown | 1684.12 | 850.52 | 833.6 | Yes | N/A | N/A | 2024-10-07 | 2024-10-02 | Unknown | Unknown | 2024-10-02 | 2024-10-09 | 8 | 6 | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-10 | 2024-10-23 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2024-11-18 | 1900-01-26 | 19 | 2024-11-18 | 2024-11-18 | 1 | 1 | 14 | 10 | 36 | 26 | 50 | 36 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | IMPERIAL BEACH | N/A | 45.05 | 45.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-09-15 | -340 | -243 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 | 2024-02-15 | 2024-04-12 | IOU Designed & Installed | N/A | No | N/A | 1131.56 | 183.68 | Unknown | Unknown | 10.09 | 937.79 | 3941 | 239.33 | 1131.56 | -892.23 | Yes | N/A | N/A | 2024-02-15 | 2024-03-13 | 28 | 20 | 2024-03-13 | 2024-03-13 | 1 | 1 | 2024-03-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | 2024-04-12 | 31 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-04-12 | 2024-05-08 | 1900-01-26 | 19 | 2024-05-08 | 2024-10-10 | 156 | 112 | 59 | 43 | 184 | 132 | 243 | 175 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 448.05 | 448.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-20 | 336 | 241 | No | 2023-04-27 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-27 | 2023-04-27 | 2024-11-20 | IOU Designed & Installed | N/A | Yes | 344 | 1684.87 | 350.47 | Unknown | Unknown | Unknown | 1334.4 | 3981 | 1777.67 | 1684.87 | 92.8 | Yes | N/A | N/A | 2023-04-27 | 2024-04-05 | 345 | 247 | 2024-04-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-27 | 2024-11-20 | 574 | 410 | Unknown | Unknown | Unknown | Unknown | 2024-11-20 | 2024-11-20 | 1899-12-31 | 1 | 2024-11-20 | 2024-11-20 | 1 | 1 | 919 | 657 | 2 | 2 | 921 | 659 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | 102.05 | 102.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-16 | -465 | -332 | No | 2023-01-18 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-18 | 2023-02-07 | Unknown | IOU Designed & Installed | N/A | Yes | 125 | 415.86 | -14.76 | Unknown | Unknown | 16.09 | 414.53 | 3981 | 716.41 | 415.86 | 300.55 | Yes | N/A | N/A | 2023-01-18 | 2023-05-23 | 126 | 90 | 2023-05-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | 2023-06-08 | Unknown | Unknown | Unknown | 2023-07-11 | Unknown | Unknown | 2023-07-11 | 2023-06-09 | Unknown | Unknown | 126 | 90 | 0 | 0 | 126 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | Lakeside | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-08-04 | 5 | 4 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-01 | 2023-08-01 | 2023-08-07 | IOU Designed & Installed | N/A | No | N/A | -436.09 | 581.2 | Unknown | 321.6 | -1725 | 386.11 | Unknown | 1725.09 | -436.09 | 2161.18 | Yes | N/A | N/A | 2023-08-01 | 2023-08-01 | 1 | 1 | 2023-08-01 | 2023-08-03 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-07 | 2023-08-09 | 1900-01-02 | 3 | 2023-08-09 | 2023-08-09 | 1 | 1 | 1 | 1 | 7 | 7 | 8 | 8 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | -403 | -289 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-01 | 2024-02-01 | 2024-07-12 | IOU Designed & Installed | N/A | No | N/A | 742.19 | 225.22 | Unknown | Unknown | Unknown | 516.97 | Unknown | 861.68 | 742.19 | 119.49 | Yes | N/A | N/A | 2024-02-01 | 2023-10-19 | Unknown | Unknown | 2023-10-19 | 2024-02-01 | 106 | 76 | 2024-02-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-01 | 2024-07-12 | 163 | 117 | Unknown | Unknown | Unknown | Unknown | 2024-07-12 | 2024-08-27 | 1900-02-15 | 33 | 2024-08-27 | 2024-08-27 | 1 | 1 | 163 | 117 | 154 | 110 | 317 | 227 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 40 | 40 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-04 | -590 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-16 | 2024-01-16 | 2024-02-02 | IOU Designed & Installed | N/A | No | N/A | -30.16 | -25.71 | Unknown | Unknown | Unknown | -4.45 | Unknown | 163.83 | -30.16 | 193.99 | Yes | N/A | N/A | 2024-01-16 | 2023-10-24 | Unknown | Unknown | 2023-10-24 | 2024-01-29 | 98 | 70 | 2024-01-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-29 | 2024-02-02 | 5 | 5 | Unknown | Unknown | Unknown | Unknown | 2024-02-02 | 2024-02-22 | 1900-01-20 | 15 | 2024-02-22 | 2024-02-22 | 1 | 1 | 5 | 5 | 120 | 86 | 125 | 91 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | 34 | 34 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-24 | -194 | -139 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2023-07-25 | 2023-08-18 | IOU Designed & Installed | N/A | No | N/A | -10.19 | -20 | Unknown | Unknown | Unknown | 9.81 | 3885 | 833.62 | -10.19 | 843.81 | Yes | N/A | N/A | 2023-07-18 | 2023-07-25 | 8 | 6 | 2023-07-25 | 2023-07-25 | 1 | 1 | 2023-07-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2023-08-18 | 25 | 19 | Unknown | Unknown | Unknown | Unknown | 2023-08-18 | 2023-09-12 | 1900-01-25 | 18 | 2023-09-12 | 2023-09-12 | 1 | 1 | 33 | 25 | 28 | 20 | 61 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-24 | -597 | -427 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-22 | 2024-11-22 | 2025-01-27 | IOU Designed & Installed | N/A | No | N/A | 451.14 | Unknown | Unknown | Unknown | 7.67 | 443.47 | 3981 | 3762.27 | 451.14 | 3311.13 | Yes | N/A | N/A | 2024-11-22 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-12-23 | 46 | 32 | 2024-12-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-23 | 2025-01-27 | 36 | 26 | Unknown | 2025-01-23 | Unknown | Unknown | 2025-01-27 | 2025-03-06 | 1900-02-07 | 29 | 2025-03-06 | 2025-03-06 | 1 | 1 | 36 | 26 | 86 | 62 | 122 | 88 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-27 | 30 | 23 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-06 | 2024-03-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2.61 | -2.31 | Unknown | Unknown | Unknown | 4.92 | 3981 | 506.52 | 2.61 | 503.91 | Yes | N/A | N/A | 2023-09-06 | 2024-03-15 | 192 | 138 | 2024-03-15 | 2024-03-15 | 1 | 1 | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-15 | Unknown | Unknown | Unknown | Unknown | 2024-04-19 | Unknown | Unknown | Unknown | 2024-05-22 | Unknown | Unknown | 2024-05-22 | 2024-04-26 | Unknown | Unknown | 192 | 138 | 1 | 1 | 193 | 139 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | ESCONDIDO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-19 | -639 | -457 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-27 | 2025-01-27 | 2025-02-27 | IOU Designed & Installed | N/A | No | N/A | 3457.68 | 1364.81 | Unknown | 322.45 | Unknown | 1770.42 | 3981 | 1627.32 | 3457.68 | -1830.36 | Yes | N/A | N/A | 2025-01-27 | 2025-01-27 | 1 | 1 | 2025-01-27 | 2025-01-27 | 1 | 1 | 2025-01-27 | Unknown | Unknown | Unknown | 2025-01-27 | 2025-02-21 | 26 | 20 | 2025-01-27 | 2025-02-27 | 32 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-03-20 | 1900-01-21 | 16 | 2025-03-20 | 2025-03-20 | 1 | 1 | 33 | 25 | 50 | 38 | 83 | 63 | Steps 2,3,5,6,7 | 25 | 19 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-04-28 | -186 | -133 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-25 | 2023-09-25 | 2023-10-13 | IOU Designed & Installed | N/A | No | N/A | 159.3 | -8.56 | Unknown | Unknown | Unknown | 167.86 | Unknown | 469.58 | 159.3 | 310.28 | Yes | N/A | N/A | 2023-09-25 | 2023-05-05 | Unknown | Unknown | 2023-05-05 | 2023-09-28 | 147 | 105 | 2023-09-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-28 | 2023-10-13 | 16 | 12 | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2023-10-25 | 1900-01-12 | 9 | 2023-10-25 | 2023-10-25 | 1 | 1 | 16 | 12 | 161 | 115 | 177 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 46.1 | 46.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-15 | -473 | -338 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-09 | 2023-11-09 | 2024-01-24 | IOU Designed & Installed | N/A | No | N/A | 14.85 | -5.5 | Unknown | Unknown | Unknown | 20.35 | 3241 | 496.75 | 14.85 | 481.9 | Yes | N/A | N/A | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | 2023-11-09 | 1 | 1 | 2023-11-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-09 | 2024-01-24 | 77 | 55 | Unknown | Unknown | Unknown | Unknown | 2024-01-24 | 2024-03-14 | 1900-02-19 | 37 | 2024-03-14 | 2024-02-28 | Unknown | Unknown | 78 | 56 | 52 | 38 | 130 | 94 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | Underserved Community | Ramona | COUNTY OF SAN DIEGO-NORTH of 56 | 476 | 476 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-31 | -592 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-14 | 2023-06-23 | 2023-12-28 | IOU Designed & Installed | N/A | No | N/A | 43364.9 | 12242.34 | Unknown | Unknown | -9651.26 | 40773.82 | 3308 | 26993.89 | 43364.9 | -16371.01 | Yes | N/A | N/A | 2023-03-14 | 2023-06-20 | 99 | 71 | 2023-06-20 | 2023-11-20 | 154 | 110 | 2023-10-19 | 2023-11-13 | 26 | 18 | 2023-10-05 | 2023-11-16 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-28 | 2024-01-17 | 1900-01-20 | 15 | 2024-01-17 | 2024-01-17 | 1 | 1 | 125 | 89 | 179 | 129 | 304 | 218 | Steps 2,3,5,6,7 | 71 | 49 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-21 | 88 | 63 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-30 | 2025-04-17 | IOU Designed & Installed | N/A | No | N/A | 28242.65 | 12063.45 | Unknown | Unknown | 122.74 | 16056.46 | 0 | 11288.91 | 28242.65 | -16953.74 | Yes | N/A | N/A | 2024-05-03 | 2024-05-01 | Unknown | Unknown | 2024-05-01 | 2024-10-21 | 174 | 124 | Unknown | Unknown | Unknown | Unknown | 2024-08-17 | 2024-10-23 | 40 | 28 | 2024-10-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-17 | 2025-05-20 | 1900-02-02 | 24 | 2025-05-20 | 2025-05-20 | 1 | 1 | 0 | 0 | 249 | 177 | 249 | 177 | Steps 2,3,5,6,7 | 2 | 2 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-16 | 178 | 127 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-08-31 | 2022-08-31 | Unknown | IOU Designed & Installed | N/A | No | N/A | 585.69 | 2103.39 | Unknown | 208.62 | -2753 | 1026.68 | Unknown | Not available | 585.69 | Unknown | Yes | N/A | N/A | 2022-08-31 | 2023-09-20 | 386 | 276 | 2023-09-20 | 2023-09-27 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 386 | 276 | 9 | 7 | 395 | 283 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-11-09 | 570 | 408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-05-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 9263.7 | 3058.21 | Unknown | Unknown | Unknown | 6205.49 | 2417600 | 31038.21 | 9263.7 | 21774.51 | Yes | N/A | N/A | 2023-05-10 | 2024-03-19 | 315 | 225 | 2024-03-19 | 2024-03-20 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-20 | 2024-05-16 | 58 | 42 | Unknown | 2024-05-31 | Unknown | Unknown | Unknown | 2024-06-03 | Unknown | Unknown | 2024-06-03 | 2024-06-01 | Unknown | Unknown | 373 | 267 | 2 | 2 | 375 | 269 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | 26 | 26 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-31 | 7 | 6 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-02 | 2023-02-21 | 2023-11-03 | IOU Designed & Installed | N/A | No | N/A | 1719.63 | 868.38 | Unknown | 288.42 | Unknown | 562.83 | Unknown | 153.87 | 1719.63 | -1565.76 | Yes | N/A | N/A | 2023-02-02 | 2023-07-05 | 154 | 110 | 2023-07-05 | 2023-07-18 | 14 | 10 | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-11-03 | 109 | 79 | Unknown | Unknown | Unknown | Unknown | 2023-11-03 | 2023-11-06 | 1900-01-03 | 2 | 2023-11-06 | 2023-11-07 | 2 | 2 | 263 | 189 | 20 | 14 | 283 | 203 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-14 | -699 | -500 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-05 | 2024-11-05 | 2024-11-11 | IOU Designed & Installed | N/A | No | N/A | 2551.97 | 414.43 | Unknown | Unknown | Unknown | 2137.54 | Unknown | 1752.03 | 2551.97 | -799.94 | Yes | N/A | N/A | 2024-11-05 | 2024-11-05 | 1 | 1 | 2024-11-05 | 2024-11-06 | 2 | 2 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2024-11-11 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-11-11 | 2024-11-14 | 1900-01-03 | 4 | 2024-11-14 | 2024-11-14 | 1 | 1 | 7 | 5 | 7 | 7 | 14 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | 140.05 | 140.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-16 | 76 | 55 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-12 | 2023-10-12 | Unknown | IOU Designed & Installed | N/A | No | N/A | 769.36 | -4.62 | Unknown | Unknown | Unknown | 773.98 | 3981 | 699.79 | 769.36 | -69.57 | Yes | N/A | N/A | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | 2023-10-12 | 1 | 1 | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-12 | Unknown | Unknown | Unknown | Unknown | 2024-03-13 | Unknown | Unknown | Unknown | 2024-05-31 | Unknown | Unknown | 2024-05-31 | 2024-05-31 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-01 | 404 | 289 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-22 | 2024-02-21 | Unknown | IOU Designed & Installed | N/A | No | N/A | -691.24 | -14.02 | Unknown | Unknown | -1470 | 792.78 | 0 | 1469.76 | -691.24 | 2161 | Yes | N/A | N/A | 2023-05-22 | 2024-02-21 | 276 | 198 | 2024-02-21 | 2024-11-18 | 272 | 194 | Unknown | Unknown | Unknown | Unknown | 2024-02-22 | 2024-03-14 | 22 | 16 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | Unknown | Unknown | 2025-03-11 | 2025-03-11 | 1 | 1 | 276 | 198 | 295 | 211 | 571 | 409 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DEL MAR | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-14 | -575 | -412 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-29 | 2024-07-29 | 2024-12-09 | IOU Designed & Installed | N/A | No | N/A | 2492.34 | 303.12 | Unknown | 41.78 | 3.46 | 2143.98 | 3981 | 2399.12 | 2492.34 | -93.22 | Yes | N/A | N/A | 2024-07-29 | 2024-08-09 | 12 | 10 | 2024-08-09 | 2024-08-14 | 6 | 4 | 2024-08-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-14 | 2024-12-09 | 118 | 84 | Unknown | 2024-11-21 | Unknown | Unknown | 2024-12-09 | 2024-12-16 | 1900-01-07 | 6 | 2024-12-16 | 2024-12-16 | 1 | 1 | 130 | 94 | 15 | 11 | 145 | 105 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-22 | -576 | -413 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-24 | 2023-08-24 | 2024-01-18 | IOU Designed & Installed | N/A | No | N/A | 737.28 | -25.64 | Unknown | Unknown | Unknown | 762.92 | Unknown | 1496.16 | 737.28 | 758.88 | Yes | N/A | N/A | 2023-08-24 | 2023-08-24 | 1 | 1 | 2023-08-24 | 2023-08-24 | 1 | 1 | 2023-08-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-24 | 2024-01-18 | 148 | 106 | Unknown | Unknown | Unknown | Unknown | 2024-01-18 | 2024-01-24 | 1900-01-06 | 5 | 2024-01-24 | 2024-01-24 | 1 | 1 | 149 | 107 | 9 | 7 | 158 | 114 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | OH | IOU Design | Residential | N/A | ALPINE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-23 | -58 | -43 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-13 | 2024-08-13 | 2025-02-21 | IOU Designed & Installed | N/A | No | N/A | 5315.12 | 824.43 | Unknown | 388.93 | 0.02 | 4101.74 | Unknown | 2783.51 | 5315.12 | -2531.61 | Yes | N/A | N/A | 2024-08-13 | 2024-12-27 | 137 | 99 | 2024-12-27 | 2025-01-08 | 13 | 9 | Unknown | Unknown | Unknown | Unknown | 2025-01-08 | 2025-01-15 | 8 | 6 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-21 | 2025-02-24 | 1900-01-03 | 2 | 2025-02-24 | 2025-02-24 | 1 | 1 | 137 | 99 | 26 | 18 | 163 | 117 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RAMONA | N/A | 93.05 | 93.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-31 | -252 | -181 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-13 | 2023-07-16 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | 2942.62 | 712.24 | Unknown | 237.49 | Unknown | 1992.89 | 3981 | 856.66 | 2942.62 | -2085.96 | Yes | N/A | N/A | 2023-07-13 | 2023-07-16 | 4 | 2 | 2023-07-16 | 2023-07-16 | 1 | 0 | 2023-07-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-02 | 2025-04-24 | 571 | 409 | Unknown | 2025-01-31 | Unknown | Unknown | 2025-04-24 | 2025-04-24 | 1899-12-31 | 1 | 2025-04-24 | 2025-04-23 | Unknown | Unknown | 575 | 411 | 2 | 1 | 577 | 412 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | Rancho Santa Fe | N/A | 66.05 | 66.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-09-30 | 920 | 657 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-18 | 2024-09-18 | 2025-02-28 | IOU Designed & Installed | N/A | No | N/A | 7397.71 | Unknown | Unknown | Unknown | Unknown | 7397.71 | 0 | 1502.89 | 7397.71 | -5894.82 | Yes | N/A | N/A | 2024-09-18 | 2023-11-21 | Unknown | Unknown | 2023-11-21 | 2024-10-09 | 324 | 232 | Unknown | Unknown | Unknown | Unknown | 2024-10-03 | 2024-10-09 | 7 | 5 | 2024-10-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-28 | 2025-04-07 | 1900-02-07 | 27 | 2025-04-07 | 2025-04-07 | 1 | 1 | 0 | 0 | 371 | 265 | 371 | 265 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R15 | OH | IOU Design | Commercial | Underserved Community | National city | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-18 | 1 | 2 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-03 | 2024-04-03 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | 62198.02 | 5071.21 | Unknown | 214.76 | 93.99 | 56818.06 | 26792 | 36633.58 | 62198.02 | -25564.44 | Yes | N/A | N/A | 2024-04-03 | 2024-04-03 | 1 | 1 | 2024-04-03 | 2024-11-19 | 231 | 165 | 2024-08-09 | 2024-11-13 | 6 | 4 | 2024-07-05 | 2025-01-06 | 150 | 108 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-03-19 | 1900-02-18 | 36 | 2025-03-19 | 2025-03-19 | 1 | 1 | 7 | 5 | 432 | 310 | 439 | 315 | Steps 2,3,5,6,7 | 233 | 165 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-22 | -260 | -187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-08-13 | Unknown | IOU Designed & Installed | N/A | No | N/A | 565.16 | -0.31 | Unknown | Unknown | Unknown | 565.47 | Unknown | 449.58 | 565.16 | -115.58 | Yes | N/A | N/A | 2024-08-08 | 2024-08-27 | 20 | 14 | 2024-08-27 | 2024-10-24 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | 2024-08-16 | 2024-09-20 | 36 | 26 | 2024-10-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-04 | Unknown | Unknown | 2024-11-04 | 2024-11-04 | 1 | 1 | 20 | 14 | 96 | 70 | 116 | 84 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | Chula Vista | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-02-01 | 738 | 529 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-01 | 2022-09-01 | 2024-01-11 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 85692.95 | 24616.19 | Unknown | Unknown | 233.87 | 60842.89 | 181927 | 45312.88 | 85692.95 | -40380.07 | Yes | N/A | N/A | 2022-09-01 | 2023-04-04 | 216 | 154 | 2023-04-04 | 2023-06-08 | 66 | 48 | 2023-03-06 | 2023-07-21 | 32 | 24 | 2023-04-10 | 2023-06-26 | 26 | 18 | 2023-06-13 | Unknown | Unknown | Unknown | 2023-06-13 | 2024-01-08 | 210 | 150 | 2024-01-11 | 2024-02-09 | 1900-01-29 | 22 | 2024-02-09 | 2024-02-09 | 1 | 1 | 248 | 178 | 333 | 239 | 581 | 417 | Steps 2,3,5,6,7 | 209 | 151 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-21 | -620 | -443 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | 2025-02-04 | IOU Designed & Installed | N/A | No | N/A | 65.47 | Unknown | Unknown | Unknown | Unknown | 65.47 | 3981 | 1956 | 65.47 | 1890.53 | Yes | N/A | N/A | 2025-01-22 | 2025-01-16 | Unknown | Unknown | 2025-01-16 | 2025-01-22 | 7 | 5 | 2025-01-22 | Unknown | Unknown | Unknown | 2025-01-22 | 2025-02-11 | 21 | 15 | 2025-01-22 | 2025-02-04 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-04-10 | 1900-03-06 | 48 | 2025-04-10 | 2025-04-10 | 1 | 1 | 14 | 10 | 95 | 69 | 109 | 79 | Steps 2,3,5,6,7 | 20 | 14 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Residential | N/A | SAN DIEGO | SAN DIEGO | 486 | 486 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-09-01 | 551 | 394 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | 2023-07-24 | 2024-12-06 | IOU Designed & Installed | N/A | No | N/A | 254487.51 | 35858.82 | Unknown | 146.21 | -12835.7 | 231318.18 | 109122.71 | 102188.55 | 254487.51 | -152298.96 | Yes | N/A | N/A | 2023-01-10 | 2023-06-28 | 170 | 122 | 2023-06-28 | 2024-08-15 | 415 | 297 | 2023-10-17 | 2024-08-05 | 13 | 7 | 2024-06-11 | 2024-08-15 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2024-10-21 | 2024-11-18 | 29 | 21 | 2024-12-06 | 2025-03-05 | 1900-03-30 | 64 | 2025-03-05 | 2025-03-05 | 1 | 1 | 183 | 129 | 574 | 412 | 757 | 541 | Steps 2,3,5,6,7 | 358 | 256 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -375 | -269 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-28 | 2024-12-06 | 2025-02-04 | IOU Designed & Installed | N/A | No | N/A | 4.66 | Unknown | Unknown | Unknown | Unknown | 4.66 | Unknown | 1677.82 | 4.66 | 1673.16 | Yes | N/A | N/A | 2024-03-28 | 2024-11-20 | 238 | 170 | 2024-11-20 | 2024-12-06 | 17 | 13 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-09 | 2025-02-04 | 58 | 42 | Unknown | Unknown | Unknown | Unknown | 2025-02-04 | 2025-02-14 | 1900-01-10 | 9 | 2025-02-14 | 2025-02-11 | Unknown | Unknown | 296 | 212 | 28 | 22 | 324 | 234 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 88.05 | 88.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-22 | -664 | -475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-09 | 2025-01-10 | 2025-01-21 | IOU Designed & Installed | N/A | No | N/A | 6.25 | Unknown | Unknown | Unknown | Unknown | 6.25 | 3981 | 1103.34 | 6.25 | 1097.09 | Yes | N/A | N/A | 2025-01-09 | 2024-12-16 | Unknown | Unknown | 2024-12-16 | 2025-01-10 | 26 | 20 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-01-21 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | 2025-01-21 | 2025-01-27 | 1900-01-06 | 5 | 2025-01-27 | 2025-01-27 | 1 | 1 | 12 | 8 | 34 | 26 | 46 | 34 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-27 | -507 | -364 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-27 | 2023-02-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.92 | -4.43 | Unknown | Unknown | Unknown | -0.49 | Unknown | 98.66 | -4.92 | 103.58 | Yes | N/A | N/A | 2023-02-27 | 2023-03-28 | 30 | 22 | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-08 | Unknown | Unknown | 2023-08-08 | 2023-08-08 | 1 | 1 | 30 | 22 | 1 | 1 | 31 | 23 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | LAGUNA HILLS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-22 | -146 | -105 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-02 | 2023-07-18 | 2023-09-21 | IOU Designed & Installed | N/A | No | N/A | 10780.1 | Unknown | Unknown | Unknown | Unknown | 10780.1 | 3981 | 2353 | 10780.1 | -8427.1 | Yes | N/A | N/A | 2023-06-02 | 2023-07-18 | 47 | 33 | 2023-07-18 | 2023-07-18 | 1 | 1 | 2023-07-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-18 | 2023-09-21 | 66 | 48 | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2023-09-29 | 1900-01-08 | 7 | 2023-09-29 | 2023-09-29 | 1 | 1 | 113 | 81 | 11 | 9 | 124 | 90 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ENCINITAS | ENCINITAS | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-16 | -255 | -182 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-08-03 | 2023-08-08 | 2023-12-27 | IOU Designed & Installed | N/A | No | N/A | 622.43 | -22.28 | Unknown | Unknown | Unknown | 644.71 | 3981 | 774.52 | 622.43 | 152.09 | Yes | N/A | N/A | 2023-08-03 | 2023-08-08 | 6 | 4 | 2023-08-08 | 2023-08-08 | 1 | 1 | 2023-08-08 | Unknown | Unknown | Unknown | 2023-08-08 | 2023-08-23 | 16 | 12 | 2023-08-08 | 2023-12-27 | 142 | 102 | Unknown | Unknown | Unknown | Unknown | 2023-12-27 | 2024-01-08 | 1900-01-12 | 9 | 2024-01-08 | 2024-01-05 | Unknown | Unknown | 148 | 106 | 30 | 22 | 178 | 128 | Steps 2,3,5,6,7 | 15 | 11 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-27 | -262 | -189 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-13 | 2023-10-13 | 2024-06-03 | IOU Designed & Installed | N/A | No | N/A | 5909.71 | 1315.03 | Unknown | Unknown | 58.53 | 4536.15 | 3981 | 1246.41 | 5909.71 | -4663.3 | Yes | N/A | N/A | 2023-10-13 | 2023-08-23 | Unknown | Unknown | 2023-08-23 | 2023-10-13 | 52 | 38 | 2023-10-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-13 | 2024-06-03 | 235 | 167 | Unknown | 2025-03-17 | Unknown | Unknown | 2024-06-03 | 2024-07-08 | 1900-02-04 | 26 | 2024-07-08 | 2024-07-08 | 1 | 1 | 235 | 167 | 89 | 65 | 324 | 232 | Steps 2,3,5,6,7 | 287 | 205 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | 4.05 | 4.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-08 | 78 | 57 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-20 | 2023-01-23 | 2024-01-22 | IOU Designed & Installed | N/A | No | N/A | 999.68 | 483.36 | Unknown | 162.32 | Unknown | 354 | 0 | 341 | 999.68 | -658.68 | Yes | N/A | N/A | 2023-01-20 | 2023-02-06 | 18 | 12 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | 2024-01-22 | 351 | 251 | Unknown | Unknown | Unknown | Unknown | 2024-01-22 | 2024-01-25 | 1900-01-03 | 4 | 2024-01-25 | 2024-01-25 | 1 | 1 | 369 | 263 | 5 | 5 | 374 | 268 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-03 | -424 | -305 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | 2024-09-09 | 2025-01-15 | IOU Designed & Installed | N/A | No | N/A | -2511.66 | -0.94 | Unknown | Unknown | -2595 | 84.28 | Unknown | 2595.14 | -2511.66 | 5106.8 | Yes | N/A | N/A | 2024-08-08 | 2024-09-09 | 33 | 23 | 2024-09-09 | 2024-09-09 | 1 | 1 | 2024-09-09 | 2025-01-15 | 129 | 93 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-01-15 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-01-15 | 2025-02-03 | 1900-01-19 | 14 | 2025-02-03 | 2025-02-03 | 1 | 1 | 163 | 117 | 22 | 16 | 185 | 133 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | LA JOLLA | N/A | 52 | 52 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-23 | -547 | -392 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-02 | 2025-01-10 | 2025-06-16 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 1809.73 | Unknown | Unknown | Yes | N/A | N/A | 2025-01-02 | 2024-12-27 | Unknown | Unknown | 2024-12-27 | 2025-01-10 | 15 | 11 | 2025-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-10 | 2025-06-16 | 158 | 112 | Unknown | Unknown | Unknown | Unknown | 2025-06-16 | 2025-06-24 | 1900-01-08 | 7 | 2025-06-24 | 2025-06-24 | 1 | 1 | 158 | 112 | 25 | 19 | 183 | 131 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2025-12-31 | -255 | -183 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-06 | 2022-09-06 | 2025-03-19 | IOU Designed & Installed | N/A | No | N/A | 9488.99 | 2068.96 | Unknown | 102.56 | 59.35 | 7258.12 | 0 | Not available | 9488.99 | Unknown | Yes | N/A | N/A | 2022-09-06 | 2023-08-07 | 336 | 240 | 2023-08-07 | 2023-11-28 | 114 | 82 | Unknown | Unknown | Unknown | Unknown | 2023-09-08 | 2024-10-08 | 98 | 70 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-19 | 2025-04-20 | 1900-02-01 | 23 | 2025-04-20 | 2025-04-20 | 1 | 0 | 336 | 240 | 246 | 175 | 582 | 415 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | 18 | 18 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-04-05 | 407 | 292 | No | 2021-04-30 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-30 | 2021-05-05 | Unknown | IOU Designed & Installed | N/A | Yes | 678 | -3.15 | -9.19 | Unknown | Unknown | Unknown | 6.04 | 3885 | 760.07 | -3.15 | 763.22 | Yes | N/A | N/A | 2021-04-30 | 2023-03-09 | 679 | 485 | 2023-03-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2021-05-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-17 | Unknown | Unknown | 2023-05-17 | 2023-05-17 | 1 | 1 | 679 | 485 | 1 | 1 | 680 | 486 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-13 | 79 | 58 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 117.45 | -6.45 | Unknown | Unknown | Unknown | 123.9 | Unknown | 710.4 | 117.45 | 592.95 | Yes | N/A | N/A | 2023-02-15 | 2023-02-15 | 1 | 1 | 2023-02-15 | 2023-03-31 | 45 | 33 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-31 | Unknown | Unknown | 2023-08-31 | 2023-08-31 | 1 | 1 | 1 | 1 | 46 | 34 | 47 | 35 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-14 | -429 | -308 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-10 | 2023-10-10 | 2023-11-17 | IOU Designed & Installed | N/A | No | N/A | 600.5 | -13.37 | Unknown | Unknown | Unknown | 613.87 | Unknown | 885.44 | 600.5 | 284.94 | Yes | N/A | N/A | 2023-10-10 | 2023-10-10 | 1 | 1 | 2023-10-10 | 2023-10-10 | 1 | 1 | 2023-10-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-10 | 2023-11-17 | 39 | 29 | Unknown | Unknown | Unknown | Unknown | 2023-11-17 | 2024-01-10 | 1900-02-23 | 39 | 2024-01-10 | 2024-01-10 | 1 | 1 | 40 | 30 | 57 | 41 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-19 | -492 | -352 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-08 | 2023-10-08 | 2023-12-04 | IOU Designed & Installed | N/A | No | N/A | -8516.1 | -3790.59 | Unknown | Unknown | Unknown | -4725.51 | Unknown | 932.82 | -8516.1 | 9448.92 | Yes | N/A | N/A | 2023-10-08 | 2023-10-08 | 1 | 0 | 2023-10-08 | 2023-10-08 | 1 | 0 | 2023-10-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-08 | 2023-12-04 | 58 | 41 | Unknown | Unknown | Unknown | Unknown | 2023-12-04 | 2024-03-14 | 1900-04-11 | 74 | 2024-03-14 | 2024-03-14 | 1 | 1 | 59 | 41 | 104 | 75 | 163 | 116 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-08 | 428 | 307 | No | 2023-02-03 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | 2024-08-06 | IOU Designed & Installed | N/A | Yes | 549 | 33.76 | Unknown | Unknown | Unknown | Unknown | 33.76 | 3981 | 1009.87 | 33.76 | 976.11 | Yes | N/A | N/A | 2023-02-03 | 2024-08-05 | 550 | 392 | 2024-08-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | 2024-08-06 | 551 | 393 | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-08-12 | 1900-01-06 | 5 | 2024-08-12 | 2024-08-09 | Unknown | Unknown | 1101 | 785 | 7 | 5 | 1108 | 790 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-06-19 | -430 | -309 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-08 | Unknown | 2024-08-12 | IOU Designed & Installed | N/A | No | N/A | 213.59 | -3 | Unknown | Unknown | 11.63 | 204.96 | 3981 | 1660.65 | 213.59 | 1447.06 | Yes | N/A | N/A | 2024-08-08 | 2024-08-08 | 1 | 1 | 2024-08-08 | 2025-03-21 | 226 | 162 | 2025-03-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-08 | 2024-08-12 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | 2024-08-12 | 2025-04-15 | 1900-09-03 | 177 | 2025-04-15 | 2025-04-15 | 1 | 1 | 6 | 4 | 474 | 340 | 480 | 344 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | CHULA VISTA | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-08 | -569 | -408 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-13 | Unknown | 2024-10-09 | IOU Designed & Installed | N/A | No | N/A | 456.4 | -8.06 | Unknown | Unknown | Unknown | 464.46 | 3981 | 1106.13 | 456.4 | 649.73 | Yes | N/A | N/A | 2024-05-13 | 2024-05-13 | 1 | 1 | 2024-05-13 | 2024-05-13 | 1 | 1 | 2024-05-13 | Unknown | Unknown | Unknown | 2024-05-13 | 2024-07-05 | 54 | 40 | 2024-05-13 | 2024-10-09 | 150 | 108 | Unknown | Unknown | Unknown | Unknown | 2024-10-09 | 2024-10-16 | 1900-01-07 | 6 | 2024-10-16 | 2024-10-16 | 1 | 1 | 151 | 109 | 64 | 48 | 215 | 157 | Steps 2,3,5,6,7 | 53 | 39 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | 26703 | 26703 | Not Available | >2MW | No | N/A | N/A | N/A | 2024-12-31 | 177 | 128 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-03 | 2024-05-03 | 2025-06-25 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1084.87 | Unknown | Unknown | Yes | N/A | N/A | 2024-05-03 | 2024-05-03 | 1 | 1 | 2024-05-03 | 2024-06-04 | 33 | 23 | Unknown | Unknown | Unknown | Unknown | 2024-05-03 | 2024-06-03 | 32 | 22 | 2024-06-04 | 2025-06-26 | 388 | 278 | Unknown | Unknown | Unknown | Unknown | 2025-06-25 | 2025-06-26 | 1900-01-01 | 2 | 2025-06-26 | 2025-06-26 | 1 | 1 | 389 | 279 | 68 | 48 | 457 | 327 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-15 | -563 | -404 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-10-14 | IOU Designed & Installed | N/A | No | N/A | 80.42 | -1.5 | Unknown | Unknown | Unknown | 81.92 | 3981 | 1352.96 | 80.42 | 1272.54 | Yes | N/A | N/A | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | 2024-08-27 | 1 | 1 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-10-14 | 49 | 35 | Unknown | Unknown | Unknown | Unknown | 2024-10-14 | 2024-10-29 | 1900-01-15 | 12 | 2024-10-29 | 2024-10-29 | 1 | 1 | 50 | 36 | 18 | 14 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | LA MESA | 312 | 312 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-03-02 | 464 | 331 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-03-06 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | 673.94 | -13.55 | Unknown | Unknown | Unknown | 687.49 | Unknown | 2222.22 | 673.94 | 1548.28 | Yes | N/A | N/A | 2025-01-22 | 2025-03-06 | 44 | 32 | 2025-03-06 | 2025-03-07 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-02-07 | 16 | 12 | 2025-03-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-09 | 1899-12-31 | 1 | 2025-06-09 | 2025-06-09 | 1 | 1 | 44 | 32 | 20 | 16 | 64 | 48 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-24 | -521 | -372 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-17 | 2023-07-24 | 2023-10-18 | IOU Designed & Installed | N/A | No | N/A | 0.3 | -8.89 | Unknown | Unknown | Unknown | 9.19 | 7962 | 656.63 | 0.3 | 656.33 | Yes | N/A | N/A | 2023-07-17 | 2023-07-24 | 8 | 6 | 2023-07-24 | 2023-07-24 | 1 | 1 | 2023-07-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-24 | 2023-10-18 | 87 | 63 | Unknown | Unknown | Unknown | Unknown | 2023-10-18 | 2023-11-21 | 1900-02-03 | 25 | 2023-11-21 | 2023-10-20 | Unknown | Unknown | 95 | 69 | 36 | 26 | 131 | 95 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | 71 | 71 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-14 | -229 | -164 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-27 | 2023-09-27 | 2024-08-26 | IOU Designed & Installed | N/A | No | N/A | 4053.97 | 886.88 | Unknown | Unknown | 35.61 | 3131.48 | 3981 | 689.03 | 4053.97 | -3364.94 | Yes | N/A | N/A | 2023-09-27 | 2023-07-11 | Unknown | Unknown | 2023-07-11 | 2023-11-08 | 121 | 87 | 2023-11-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-08 | 2024-08-26 | 293 | 209 | Unknown | Unknown | Unknown | Unknown | 2024-08-26 | 2024-09-03 | 1900-01-08 | 7 | 2024-09-03 | 2024-08-28 | Unknown | Unknown | 293 | 209 | 130 | 94 | 423 | 303 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-03 | -628 | -449 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-05 | 2024-02-09 | IOU Designed & Installed | N/A | No | N/A | 39.87 | -5.37 | Unknown | Unknown | Unknown | 45.24 | Unknown | 501.14 | 39.87 | 461.27 | Yes | N/A | N/A | 2024-02-05 | 2023-12-06 | Unknown | Unknown | 2023-12-06 | 2024-02-08 | 65 | 47 | 2024-02-08 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-08 | 2024-02-09 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-03-15 | 1900-02-04 | 26 | 2024-03-15 | 2024-03-15 | 1 | 1 | 2 | 2 | 102 | 74 | 104 | 76 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Commercial | Underserved Community | Escondido | Escondido | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-20 | -216 | -155 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2023-12-26 | 2025-06-02 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | -7406.69 | Unknown | Unknown | Unknown | -11006 | 3599.31 | 0 | 10298.99 | -7406.69 | 17705.68 | Yes | N/A | N/A | 2023-12-26 | 2024-07-02 | 190 | 136 | 2024-07-02 | 2025-04-08 | 281 | 201 | 2024-07-11 | 2024-11-04 | 117 | 83 | 2025-03-27 | 2025-04-07 | 12 | 8 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-06-02 | 2025-06-18 | 1900-01-16 | 13 | 2025-06-18 | 2025-06-18 | 1 | 1 | 307 | 219 | 311 | 223 | 618 | 442 | Steps 2,3,5,6,7 | 271 | 193 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-11 | -322 | -231 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-13 | 2023-09-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 55.8 | -11.17 | Unknown | Unknown | Unknown | 66.97 | 3981 | 791.39 | 55.8 | 735.59 | Yes | N/A | N/A | 2023-09-13 | 2023-09-11 | Unknown | Unknown | 2023-09-11 | 2023-09-13 | 3 | 3 | 2023-09-13 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-25 | Unknown | Unknown | 2023-10-25 | 2023-10-25 | 1 | 1 | 0 | 0 | 4 | 4 | 4 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 58.05 | 58.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-12-16 | 80 | 59 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-11 | 2024-11-14 | 2025-02-27 | IOU Designed & Installed | N/A | No | N/A | 9408.22 | Unknown | Unknown | Unknown | Unknown | 9408.22 | 11943 | 1124.16 | 9408.22 | -8284.06 | Yes | N/A | N/A | 2024-07-11 | 2024-12-10 | 153 | 109 | 2024-12-10 | 2024-12-13 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-13 | 2025-02-10 | 60 | 42 | Unknown | Unknown | Unknown | Unknown | 2025-02-27 | 2025-03-10 | 1900-01-11 | 8 | 2025-03-10 | 2025-03-06 | Unknown | Unknown | 213 | 151 | 16 | 12 | 229 | 163 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-29 | -644 | -461 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | 2024-10-15 | IOU Designed & Installed | N/A | No | N/A | 660.28 | -13.2 | Unknown | Unknown | Unknown | 673.48 | 3981 | 1889.24 | 660.28 | 1228.96 | Yes | N/A | N/A | 2024-08-29 | 2024-08-07 | Unknown | Unknown | 2024-08-07 | 2024-08-30 | 24 | 18 | 2024-08-30 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-30 | 2024-10-15 | 47 | 33 | Unknown | Unknown | Unknown | Unknown | 2024-10-15 | 2024-10-23 | 1900-01-08 | 7 | 2024-10-23 | 2024-10-23 | 1 | 1 | 47 | 33 | 34 | 26 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-10-08 | 130 | 94 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-11 | 2023-10-18 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1112.3 | -7.15 | Unknown | Unknown | 30.99 | 1088.46 | 2875 | 772.82 | 1112.3 | -339.48 | Yes | N/A | N/A | 2023-10-11 | 2023-10-18 | 8 | 6 | 2023-10-18 | 2023-12-15 | 59 | 43 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-15 | 2024-01-10 | 27 | 19 | Unknown | 2024-01-24 | Unknown | Unknown | Unknown | 2024-04-01 | Unknown | Unknown | 2024-04-01 | 2024-02-15 | Unknown | Unknown | 35 | 25 | 59 | 43 | 94 | 68 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 4 | 4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-17 | -204 | -146 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-19 | 2024-10-11 | IOU Designed & Installed | N/A | No | N/A | 732.67 | Unknown | Unknown | Unknown | 6.02 | 726.65 | 3981 | 1055.45 | 732.67 | 322.78 | Yes | N/A | N/A | 2024-07-16 | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-19 | 5 | 5 | 2024-07-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-19 | 2024-10-11 | 85 | 61 | Unknown | 2024-10-03 | Unknown | Unknown | 2024-10-11 | 2024-10-25 | 1900-01-14 | 11 | 2024-10-25 | 2024-10-25 | 1 | 1 | 85 | 61 | 21 | 17 | 106 | 78 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-27 | -704 | -505 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-16 | 2024-04-16 | 2024-04-16 | IOU Designed & Installed | N/A | No | N/A | 4.05 | -3.59 | Unknown | Unknown | Unknown | 7.64 | Unknown | 609.47 | 4.05 | 605.42 | Yes | N/A | N/A | 2024-04-16 | 2024-03-27 | Unknown | Unknown | 2024-03-27 | 2024-04-16 | 21 | 15 | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-04-16 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-04-22 | 1900-01-06 | 5 | 2024-04-22 | 2024-04-22 | 1 | 1 | 1 | 1 | 29 | 21 | 30 | 22 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-06-23 | 276 | 197 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-28 | 2022-11-28 | 2024-03-25 | IOU Designed & Installed | N/A | No | N/A | -2959.54 | 2755.02 | Unknown | 169.37 | -7146 | 1262.07 | 0 | 2845.69 | -2959.54 | 5805.23 | Yes | N/A | N/A | 2022-11-28 | 2023-04-27 | 151 | 109 | 2023-04-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-25 | 2024-03-25 | 1899-12-31 | 1 | 2024-03-25 | 2024-03-25 | 1 | 1 | 151 | 109 | 2 | 2 | 153 | 111 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LEMON GROVE | N/A | 21 | 21 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-28 | 124 | 89 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-22 | 2023-11-22 | 2023-12-13 | IOU Designed & Installed | N/A | No | N/A | 1357.78 | -29.54 | Unknown | Unknown | Unknown | 1387.32 | 3941 | 840.7 | 1357.78 | -517.08 | Yes | N/A | N/A | 2023-11-22 | 2023-10-16 | Unknown | Unknown | 2023-10-16 | 2023-11-22 | 38 | 28 | 2023-11-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2023-12-13 | 22 | 16 | Unknown | Unknown | Unknown | Unknown | 2023-12-13 | 2024-03-14 | 1900-04-02 | 67 | 2024-03-14 | 2025-01-30 | 323 | 231 | 22 | 16 | 454 | 326 | 476 | 342 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | DANA POINT | N/A | 102 | 102 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-05 | -147 | -106 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-04 | 2023-10-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1833.62 | 610.26 | Unknown | Unknown | 41.26 | 1182.1 | 3981 | 1164.61 | 1833.62 | -669.01 | Yes | N/A | N/A | 2023-10-04 | 2023-12-05 | 63 | 45 | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-27 | Unknown | Unknown | Unknown | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-04-11 | 1 | 1 | 63 | 45 | 1 | 1 | 64 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | COTO DE CAZA | N/A | 151 | 151 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-11-06 | -209 | -150 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | Unknown | IOU Designed & Installed | N/A | No | N/A | 927.95 | 308.36 | Unknown | Unknown | 16.84 | 602.75 | 3981 | 1445.82 | 927.95 | 517.87 | Yes | N/A | N/A | 2023-12-14 | 2024-01-02 | 20 | 14 | 2024-01-02 | 2024-01-04 | 3 | 3 | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-04 | Unknown | Unknown | Unknown | Unknown | 2024-03-06 | Unknown | Unknown | Unknown | 2024-04-11 | Unknown | Unknown | 2024-04-11 | 2024-04-11 | 1 | 1 | 20 | 14 | 4 | 4 | 24 | 18 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | BONSALL | N/A | 124.1 | 124.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-10-07 | -725 | -518 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | 2023-10-11 | IOU Designed & Installed | N/A | No | N/A | 914.34 | -14 | Unknown | Unknown | 16.16 | 912.18 | 3981 | 665.69 | 914.34 | -248.65 | Yes | N/A | N/A | 2023-06-07 | 2023-06-05 | Unknown | Unknown | 2023-06-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-09-21 | 2023-10-11 | 21 | 15 | Unknown | 2023-10-10 | Unknown | Unknown | 2023-10-11 | 2023-10-13 | 1900-01-02 | 3 | 2023-10-13 | 2023-10-13 | 1 | 1 | 21 | 15 | 4 | 4 | 25 | 19 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-05 | 445 | 320 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-15 | 2023-02-15 | 2023-08-25 | IOU Designed & Installed | N/A | No | N/A | 20324.95 | 4062.86 | Unknown | 808.56 | 213.69 | 15239.84 | 3981 | 1336.33 | 20324.95 | -18988.62 | Yes | N/A | N/A | 2023-02-15 | 2023-02-15 | 1 | 1 | 2023-02-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-15 | 2023-08-25 | 192 | 138 | Unknown | 2025-03-05 | Unknown | Unknown | 2023-08-25 | 2025-04-25 | 1901-09-01 | 436 | 2025-04-25 | 2025-04-25 | 1 | 1 | 193 | 139 | 611 | 437 | 804 | 576 | Steps 2,3,5,6,7 | 558 | 398 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SANTEE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-15 | -247 | -178 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-03 | 2023-04-03 | 2023-04-14 | IOU Designed & Installed | N/A | No | N/A | -8.75 | -6.34 | Unknown | Unknown | Unknown | -2.41 | Unknown | 352.77 | -8.75 | 361.52 | Yes | N/A | N/A | 2023-04-03 | 2023-04-03 | 1 | 1 | 2023-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-03 | 2023-04-14 | 12 | 10 | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | 2023-06-13 | 1900-03-01 | 43 | 2023-06-13 | 2023-06-13 | 1 | 1 | 13 | 11 | 62 | 44 | 75 | 55 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | POWAY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-25 | -678 | -485 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-15 | 2025-05-15 | 2025-05-20 | IOU Designed & Installed | N/A | No | N/A | 94.62 | Unknown | Unknown | Unknown | Unknown | 94.62 | 3981 | 1020.04 | 94.62 | 925.42 | Yes | N/A | N/A | 2025-05-15 | 2025-05-15 | 1 | 1 | 2025-05-15 | 2025-05-15 | 1 | 1 | 2025-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-15 | 2025-05-20 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-06-16 | 1900-01-27 | 20 | 2025-06-16 | 2025-06-16 | 1 | 1 | 7 | 5 | 30 | 22 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2027-04-14 | -660 | -473 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-12 | 2025-05-14 | 2025-06-12 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | Unknown | 450.11 | Unknown | Unknown | Yes | N/A | N/A | 2025-05-12 | 2025-04-17 | Unknown | Unknown | 2025-04-17 | 2025-05-14 | 28 | 20 | 2025-05-14 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-14 | 2025-06-12 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2025-06-12 | 2025-06-23 | 1900-01-11 | 8 | 2025-06-23 | 2025-06-23 | 1 | 1 | 30 | 22 | 41 | 29 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-02-22 | 11 | 8 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-28 | 2023-02-28 | Unknown | IOU Designed & Installed | N/A | No | N/A | 158.03 | 2502.75 | Unknown | 361.66 | -3773 | 1066.62 | 0 | 3773.45 | 158.03 | 3615.42 | Yes | N/A | N/A | 2023-02-28 | 2023-02-28 | 1 | 1 | 2023-02-28 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-04 | Unknown | Unknown | 2024-03-04 | 2024-03-04 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | 60 | 60 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-03 | -98 | -71 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-10 | 2023-02-10 | 2023-06-13 | IOU Designed & Installed | N/A | No | N/A | 806.6 | -29.82 | Unknown | Unknown | 5.69 | 830.73 | 3981 | 657.46 | 806.6 | -149.14 | Yes | N/A | N/A | 2023-02-10 | 2023-02-10 | 1 | 1 | 2023-02-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-10 | 2023-06-13 | 124 | 88 | Unknown | Unknown | Unknown | Unknown | 2023-06-13 | 2023-09-27 | 1900-04-16 | 77 | 2023-09-27 | 2023-09-27 | 1 | 1 | 125 | 89 | 108 | 78 | 233 | 167 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-12-31 | 107 | 77 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-06 | 2023-11-15 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1325.36 | 71.61 | Unknown | Unknown | 29.27 | 1224.48 | 25032 | 1362.36 | 1325.36 | 37 | Yes | N/A | N/A | 2023-11-06 | 2023-11-13 | 8 | 6 | 2023-11-13 | 2023-12-19 | 37 | 27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-02-28 | 72 | 52 | Unknown | 2024-04-12 | Unknown | Unknown | Unknown | 2024-04-17 | Unknown | Unknown | 2024-04-17 | 2024-04-16 | Unknown | Unknown | 80 | 58 | 37 | 27 | 117 | 85 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | 58 | 58 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-21 | -635 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-22 | 2025-01-22 | 2025-03-11 | IOU Designed & Installed | N/A | No | N/A | 5.38 | Unknown | Unknown | Unknown | 2.68 | 2.7 | 3981 | 1545.24 | 5.38 | 1539.86 | Yes | N/A | N/A | 2025-01-22 | 2025-02-03 | 13 | 9 | 2025-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-06 | 2025-03-11 | 34 | 24 | Unknown | Unknown | Unknown | Unknown | 2025-03-11 | 2025-03-26 | 1900-01-15 | 12 | 2025-03-26 | 2025-03-26 | 1 | 1 | 47 | 33 | 17 | 13 | 64 | 46 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | RAMONA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-16 | -592 | -423 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-30 | 2023-11-30 | 2024-03-21 | IOU Designed & Installed | N/A | No | N/A | 12828.47 | 4097.62 | Unknown | 1174.27 | Unknown | 7556.58 | 3981 | 1438.78 | 12828.47 | -11389.69 | Yes | N/A | N/A | 2023-11-30 | 2023-12-05 | 6 | 4 | 2023-12-05 | 2023-12-05 | 1 | 1 | 2023-12-05 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | 2024-03-21 | 102 | 74 | Unknown | 2025-03-18 | Unknown | Unknown | 2024-03-21 | 2024-04-03 | 1900-01-13 | 10 | 2024-04-03 | 2024-04-03 | 1 | 1 | 108 | 78 | 16 | 12 | 124 | 90 | Steps 2,3,5,6,7 | 362 | 258 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | OH | Applicant Design | Residential | Disadvantaged Community,Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-01 | 189 | 136 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-20 | 2023-10-20 | 2024-12-17 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 92190.31 | 4438.32 | Unknown | Unknown | 722.55 | 87029.44 | 778901 | 28868.45 | 92190.31 | -63321.86 | Yes | N/A | N/A | 2023-10-20 | 2024-07-09 | 264 | 188 | 2024-07-09 | 2024-12-06 | 151 | 109 | 2024-07-23 | 2024-10-25 | 42 | 32 | 2024-10-08 | 2024-11-21 | 45 | 31 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-17 | 2025-02-06 | 1900-02-20 | 38 | 2025-02-06 | 2025-02-06 | 1 | 1 | 306 | 220 | 249 | 179 | 555 | 399 | Steps 2,3,5,6,7 | 153 | 111 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO LA COSTA | N/A | 154 | 154 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-02 | -296 | -211 | No | 2022-11-08 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-08 | 2022-11-11 | Unknown | IOU Designed & Installed | N/A | Yes | 93 | 1040.52 | -14.29 | Unknown | Unknown | 25.99 | 1028.82 | 3981 | 768.91 | 1040.52 | -271.61 | Yes | N/A | N/A | 2022-11-08 | 2023-02-09 | 94 | 68 | 2023-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-12-02 | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | Unknown | Unknown | Unknown | 2023-06-26 | Unknown | Unknown | 2023-06-26 | 2023-08-11 | 47 | 35 | 94 | 68 | 47 | 35 | 141 | 103 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-28 | -689 | -492 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-25 | 2025-03-25 | 2025-03-26 | IOU Designed & Installed | N/A | No | N/A | 4474.77 | 1050.24 | Unknown | 322.61 | Unknown | 3101.92 | Unknown | 2246.45 | 4474.77 | -2228.32 | Yes | N/A | N/A | 2025-03-25 | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-25 | 21 | 15 | 2025-03-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-25 | 2025-03-26 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | 2025-03-26 | 2025-04-10 | 1900-01-15 | 12 | 2025-04-10 | 2025-04-10 | 1 | 1 | 2 | 2 | 38 | 28 | 40 | 30 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-29 | -653 | -467 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-16 | 2024-10-18 | 2024-11-12 | IOU Designed & Installed | N/A | No | N/A | 1445.64 | 392.34 | Unknown | Unknown | Unknown | 1053.3 | Unknown | 1667.18 | 1445.64 | 221.54 | Yes | N/A | N/A | 2024-10-16 | 2024-08-29 | Unknown | Unknown | 2024-08-29 | 2024-10-18 | 51 | 37 | 2024-10-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-18 | 2024-11-12 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2024-11-12 | 2024-11-14 | 1900-01-02 | 3 | 2024-11-14 | 2024-11-14 | 1 | 1 | 26 | 18 | 55 | 41 | 81 | 59 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-17 | -155 | -111 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-14 | 2023-12-14 | 2023-12-19 | IOU Designed & Installed | N/A | No | N/A | 1540.38 | -41.85 | Unknown | Unknown | 8 | 1574.23 | Unknown | 799.66 | 1540.38 | -740.72 | Yes | N/A | N/A | 2023-12-14 | 2023-12-14 | 1 | 1 | 2023-12-14 | 2023-12-14 | 1 | 1 | 2023-12-14 | Unknown | Unknown | Unknown | 2023-12-15 | 2023-12-19 | 5 | 3 | 2023-12-14 | 2023-12-19 | 6 | 4 | Unknown | Unknown | Unknown | Unknown | 2023-12-19 | 2024-03-15 | 1900-03-28 | 64 | 2024-03-15 | 2024-03-15 | 1 | 1 | 7 | 5 | 95 | 69 | 102 | 74 | Steps 2,3,5,6,7 | 5 | 3 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-26 | -688 | -493 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-03 | 2025-04-03 | 2025-04-29 | IOU Designed & Installed | N/A | No | N/A | 1311.03 | -26.35 | Unknown | Unknown | Unknown | 1337.38 | 3981 | 1935.12 | 1311.03 | 624.09 | Yes | N/A | N/A | 2025-04-03 | 2025-04-03 | 1 | 1 | 2025-04-03 | 2025-04-03 | 1 | 1 | 2025-04-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-04 | 2025-04-29 | 26 | 18 | Unknown | Unknown | Unknown | Unknown | 2025-04-29 | 2025-05-07 | 1900-01-08 | 7 | 2025-05-07 | 2025-05-07 | 1 | 1 | 27 | 19 | 11 | 9 | 38 | 28 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN CLEMENTE | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-10-31 | 731 | 523 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-09-19 | 2023-09-19 | 2023-10-23 | IOU Designed & Installed | N/A | No | N/A | 18195.75 | 5504.26 | Unknown | 2281.09 | -863 | 11273.4 | Unknown | 863.25 | 18195.75 | -17332.5 | Yes | N/A | N/A | 2023-09-19 | 2023-10-02 | 14 | 10 | 2023-10-02 | 2023-10-24 | 23 | 17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-10-24 | 2023-10-30 | 7 | 5 | Unknown | 2023-10-19 | Unknown | Unknown | 2023-10-23 | 2023-10-26 | 1900-01-03 | 4 | 2023-10-26 | 2023-11-01 | 7 | 5 | 21 | 15 | 34 | 26 | 55 | 41 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | OCEANSIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-06 | -604 | -432 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-20 | 2024-02-20 | 2024-04-05 | IOU Designed & Installed | N/A | No | N/A | -11.84 | -5.83 | Unknown | Unknown | Unknown | -6.01 | Unknown | 163.83 | -11.84 | 175.67 | Yes | N/A | N/A | 2024-02-20 | 2024-03-06 | 16 | 12 | 2024-03-06 | 2024-03-18 | 13 | 9 | 2024-03-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-03-18 | 2024-04-05 | 19 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-04-05 | 2024-04-11 | 1900-01-06 | 5 | 2024-04-11 | 2024-04-11 | 1 | 1 | 35 | 27 | 21 | 15 | 56 | 42 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-09-21 | -46 | -34 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-28 | 2023-11-28 | 2024-07-02 | IOU Designed & Installed | N/A | No | N/A | -1032.54 | -5.91 | Unknown | Unknown | -1075 | 48.37 | Unknown | 1075.26 | -1032.54 | 2107.8 | Yes | N/A | N/A | 2023-11-28 | 2023-10-04 | Unknown | Unknown | 2023-10-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | 2024-07-02 | 78 | 56 | Unknown | Unknown | Unknown | Unknown | 2024-07-02 | 2024-08-06 | 1900-02-04 | 26 | 2024-08-06 | 2024-08-06 | 1 | 1 | 78 | 56 | 37 | 27 | 115 | 83 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | ENCINITAS | N/A | 76.05 | 76.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-17 | -589 | -422 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-13 | 2023-03-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 428.25 | -6.36 | Unknown | Unknown | Unknown | 434.61 | 3981 | 733.88 | 428.25 | 305.63 | Yes | N/A | N/A | 2023-03-13 | 2023-03-17 | 5 | 5 | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-03-17 | Unknown | Unknown | Unknown | Unknown | 2023-05-24 | Unknown | Unknown | Unknown | 2023-06-08 | Unknown | Unknown | 2023-06-08 | 2023-06-08 | 1 | 1 | 5 | 5 | 1 | 1 | 6 | 6 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-08-22 | 172 | 123 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-17 | 2024-10-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | -3026.57 | -11.24 | Unknown | Unknown | -3687 | 671.67 | Unknown | 3686.95 | -3026.57 | 6713.52 | Yes | N/A | N/A | 2024-10-17 | 2024-10-10 | Unknown | Unknown | 2024-10-10 | 2024-11-14 | 36 | 26 | Unknown | Unknown | Unknown | Unknown | 2024-10-31 | 2025-01-29 | 36 | 26 | 2024-11-14 | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | Unknown | 2025-02-10 | Unknown | Unknown | 2025-02-10 | 2025-02-10 | 1 | 1 | 0 | 0 | 73 | 53 | 73 | 53 | Steps 2,3,5,6,7 | 76 | 54 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 84.4 | 84.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-04-10 | -420 | -301 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-12-26 | 2023-12-26 | 2024-02-09 | IOU Designed & Installed | N/A | No | N/A | 782.64 | -4.79 | Unknown | Unknown | 3.19 | 784.24 | 3981 | 1044.29 | 782.64 | 261.65 | Yes | N/A | N/A | 2023-12-26 | 2023-09-07 | Unknown | Unknown | 2023-09-07 | 2024-01-10 | 126 | 90 | 2024-01-10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-01-10 | 2024-02-09 | 31 | 23 | Unknown | 2024-02-01 | Unknown | Unknown | 2024-02-09 | 2024-02-16 | 1900-01-07 | 6 | 2024-02-16 | 2024-02-15 | Unknown | Unknown | 31 | 23 | 134 | 96 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | 110.05 | 110.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-01-01 | 5 | 4 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-18 | 2023-06-01 | Unknown | IOU Designed & Installed | N/A | No | N/A | -1893.48 | Unknown | Unknown | Unknown | -1941 | 47.52 | 0 | 1304.18 | -1893.48 | 3197.66 | Yes | N/A | N/A | 2023-05-18 | 2023-05-24 | 7 | 5 | 2023-05-24 | 2023-07-27 | 65 | 47 | 2023-07-27 | 2024-11-18 | 481 | 343 | Unknown | Unknown | Unknown | Unknown | 2024-09-05 | Unknown | Unknown | Unknown | Unknown | 2024-12-05 | Unknown | Unknown | Unknown | 2025-01-06 | Unknown | Unknown | 2025-01-06 | 2025-01-06 | 1 | 1 | 488 | 348 | 66 | 48 | 554 | 396 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 193.1 | 193.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-08-03 | -339 | -242 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-27 | 2024-04-02 | 2024-07-01 | IOU Designed & Installed | N/A | No | N/A | 108.46 | Unknown | Unknown | Unknown | Unknown | 108.46 | 3885 | 947.93 | 108.46 | 839.47 | Yes | N/A | N/A | 2024-03-27 | 2024-03-25 | Unknown | Unknown | 2024-03-25 | 2024-04-02 | 9 | 7 | 2024-04-02 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-02 | 2024-07-01 | 91 | 65 | Unknown | Unknown | Unknown | Unknown | 2024-07-01 | 2024-09-03 | 1900-03-05 | 47 | 2024-09-03 | 2024-08-29 | Unknown | Unknown | 91 | 65 | 74 | 54 | 165 | 119 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 73.05 | 73.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-06 | -514 | -367 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-29 | 2024-10-29 | 2025-03-28 | IOU Designed & Installed | N/A | No | N/A | 1339.12 | Unknown | Unknown | Unknown | 11.14 | 1327.98 | 3981 | 1692.58 | 1339.12 | 353.46 | Yes | N/A | N/A | 2024-10-29 | 2024-11-13 | 16 | 12 | 2024-11-13 | 2024-12-06 | 24 | 18 | 2024-12-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-12-10 | 2025-03-28 | 109 | 79 | Unknown | 2025-03-11 | Unknown | Unknown | 2025-03-28 | 2025-04-11 | 1900-01-14 | 11 | 2025-04-11 | 2025-04-10 | Unknown | Unknown | 125 | 91 | 39 | 29 | 164 | 120 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 47.05 | 47.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-04-03 | 220 | 159 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-22 | 2023-04-14 | 2023-11-06 | IOU Designed & Installed | N/A | No | N/A | 2756.39 | 834.72 | Unknown | 350.04 | Unknown | 1571.63 | 3981 | 1982.72 | 2756.39 | -773.67 | Yes | N/A | N/A | 2023-03-22 | 2023-08-23 | 155 | 111 | 2023-08-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-04-14 | 2023-11-06 | 207 | 147 | Unknown | 2023-09-01 | Unknown | Unknown | 2023-11-06 | 2023-11-09 | 1900-01-03 | 4 | 2023-11-09 | 2023-11-09 | 1 | 1 | 362 | 258 | 5 | 5 | 367 | 263 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | 689.15 | 689.15 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-11-30 | -202 | -145 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-10 | 2023-11-10 | 2025-05-01 | IOU Designed & Installed | N/A | No | N/A | 52258.18 | 12202.79 | Unknown | Unknown | Unknown | 40055.39 | 91701 | 19536.6 | 52258.18 | -32721.58 | Yes | N/A | N/A | 2023-05-10 | 2023-06-30 | 52 | 38 | 2023-06-30 | 2023-11-14 | 138 | 98 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-11-14 | 2025-04-17 | 521 | 373 | Unknown | 2025-04-07 | Unknown | Unknown | 2025-05-01 | 2025-05-20 | 1900-01-19 | 14 | 2025-05-20 | 2025-05-12 | Unknown | Unknown | 573 | 411 | 158 | 112 | 731 | 523 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 5.4 | 5.4 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-21 | -634 | -454 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-10 | 2024-05-09 | IOU Designed & Installed | N/A | No | N/A | 4.88 | -4.33 | Unknown | Unknown | Unknown | 9.21 | Unknown | 396.88 | 4.88 | 392 | Yes | N/A | N/A | 2024-04-10 | 2024-03-11 | Unknown | Unknown | 2024-03-11 | 2024-04-15 | 36 | 26 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-05-09 | 25 | 19 | Unknown | 2025-04-16 | Unknown | Unknown | 2024-05-09 | 2024-05-28 | 1900-01-19 | 14 | 2024-05-28 | 2024-05-28 | 1 | 1 | 25 | 19 | 57 | 41 | 82 | 60 | Steps 2,3,5,6,7 | 342 | 244 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 54.45 | 54.45 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-04 | -530 | -379 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-29 | 2024-08-29 | 2025-02-03 | IOU Designed & Installed | N/A | No | N/A | 1109.02 | Unknown | Unknown | Unknown | 25.48 | 1083.54 | 3981 | 1121.78 | 1109.02 | 12.76 | Yes | N/A | N/A | 2024-08-29 | 2024-08-09 | Unknown | Unknown | 2024-08-09 | 2024-09-23 | 46 | 32 | 2024-09-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-09-23 | 2025-02-03 | 134 | 96 | Unknown | 2025-01-31 | Unknown | Unknown | 2025-02-03 | 2025-03-05 | 1900-01-30 | 23 | 2025-03-05 | 2025-02-20 | Unknown | Unknown | 134 | 96 | 77 | 55 | 211 | 151 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R15 | UG | Applicant Design | Residential | Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 503 | 360 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-07 | 2024-03-07 | 2025-03-07 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 2336.37 | 429.47 | Unknown | Unknown | -21146.68 | 23053.58 | 0 | 20892.89 | 2336.37 | 18556.52 | Yes | N/A | N/A | 2024-03-07 | 2024-04-22 | 47 | 33 | 2024-04-22 | 2024-08-29 | 130 | 94 | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-12-05 | 18 | 14 | 2025-01-17 | Unknown | Unknown | Unknown | 2025-01-17 | 2025-02-27 | 42 | 30 | 2025-03-07 | 2025-04-17 | 1900-02-10 | 30 | 2025-04-17 | 2025-04-17 | 1 | 1 | 47 | 33 | 233 | 169 | 280 | 202 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-12 | -639 | -458 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-12 | 2025-03-12 | 2025-05-02 | IOU Designed & Installed | N/A | No | N/A | 1997.4 | -40.14 | Unknown | Unknown | Unknown | 2037.54 | 3981 | 1618.58 | 1997.4 | -378.82 | Yes | N/A | N/A | 2025-03-12 | 2025-03-11 | Unknown | Unknown | 2025-03-11 | 2025-03-12 | 2 | 2 | 2025-03-12 | Unknown | Unknown | Unknown | 2025-03-12 | 2025-03-26 | 15 | 11 | 2025-03-12 | 2025-05-02 | 52 | 38 | Unknown | Unknown | Unknown | Unknown | 2025-05-02 | 2025-05-14 | 1900-01-12 | 9 | 2025-05-14 | 2025-05-14 | 1 | 1 | 52 | 38 | 31 | 23 | 83 | 61 | Steps 2,3,5,6,7 | 14 | 10 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-11-05 | -496 | -355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-04 | 2025-02-04 | 2025-06-27 | IOU Designed & Installed | N/A | No | N/A | 1700.71 | Unknown | Unknown | Unknown | -1624.12 | 3324.83 | Unknown | 1502.36 | 1700.71 | -198.35 | Yes | N/A | N/A | 2025-02-04 | 2025-03-27 | 52 | 38 | 2025-03-27 | 2025-04-02 | 7 | 5 | 2025-04-02 | 2025-04-28 | 27 | 19 | Unknown | Unknown | Unknown | Unknown | 2025-04-28 | 2025-06-27 | 61 | 45 | Unknown | 2025-06-24 | Unknown | Unknown | 2025-06-27 | 2025-06-27 | 1899-12-31 | 1 | 2025-06-27 | 2025-06-27 | 1 | 1 | 140 | 102 | 9 | 7 | 149 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | NATIONAL CITY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-17 | -785 | -562 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-17 | 2023-11-17 | 2024-05-21 | IOU Designed & Installed | N/A | No | N/A | -3.22 | -9.66 | Unknown | Unknown | Unknown | 6.44 | 28804 | 494.63 | -3.22 | 497.85 | Yes | N/A | N/A | 2023-11-17 | 2024-01-22 | 67 | 47 | 2024-01-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2024-05-21 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2024-05-21 | 2024-05-23 | 1900-01-02 | 3 | 2024-05-23 | 2024-05-23 | 1 | 1 | 68 | 48 | 4 | 4 | 72 | 52 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | EL CAJON | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-05 | -259 | -186 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-04 | 2024-04-24 | IOU Designed & Installed | N/A | No | N/A | 19.43 | -17.23 | Unknown | Unknown | Unknown | 36.66 | Unknown | 868.12 | 19.43 | 848.69 | Yes | N/A | N/A | 2024-04-04 | 2024-02-26 | Unknown | Unknown | 2024-02-26 | 2024-04-04 | 39 | 29 | 2024-04-04 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-04 | 2024-04-24 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2024-04-24 | 2024-05-22 | 1900-01-28 | 21 | 2024-05-22 | 2024-05-22 | 1 | 1 | 21 | 15 | 69 | 51 | 90 | 66 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | MISSION VIEJO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-02-08 | 25 | 18 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-03-02 | 2025-03-02 | Unknown | IOU Designed & Installed | N/A | No | N/A | 12.5 | Unknown | Unknown | Unknown | Unknown | 12.5 | Unknown | 768.95 | 12.5 | 756.45 | Yes | N/A | N/A | 2025-03-02 | 2025-03-03 | 2 | 1 | 2025-03-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-03-05 | Unknown | Unknown | 2025-03-05 | 2025-03-05 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 2 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-31 | -413 | -296 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-30 | 2023-06-30 | 2023-11-22 | IOU Designed & Installed | N/A | No | N/A | 1162.63 | -12.13 | Unknown | Unknown | -645.25 | 1820.01 | Unknown | 645.55 | 1162.63 | -517.08 | Yes | N/A | N/A | 2023-06-30 | 2023-07-20 | 21 | 15 | 2023-07-20 | 2023-07-20 | 1 | 1 | 2023-07-20 | 2023-10-23 | 96 | 68 | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | 2023-11-22 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | 2023-11-22 | 2024-02-12 | 1900-03-23 | 59 | 2024-02-12 | 2024-02-12 | 1 | 1 | 243 | 173 | 85 | 61 | 328 | 234 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-01 | 380 | 273 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-18 | 2024-02-06 | Unknown | IOU Designed & Installed | N/A | No | N/A | 11336.89 | Unknown | Unknown | Unknown | Unknown | 11336.89 | 325677 | 15764.34 | 11336.89 | 4427.45 | Yes | N/A | N/A | 2023-07-18 | 2023-10-13 | 88 | 64 | 2023-10-13 | 2024-08-06 | 299 | 213 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-06 | 2024-10-25 | 81 | 59 | Unknown | 2025-01-07 | Unknown | Unknown | Unknown | 2025-01-30 | Unknown | Unknown | 2025-01-30 | 2025-01-15 | Unknown | Unknown | 169 | 123 | 299 | 213 | 468 | 336 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | 14.1 | 14.1 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-29 | -480 | -345 | No | 2024-09-10 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-10 | 2024-09-10 | 2025-01-24 | IOU Designed & Installed | N/A | Yes | 77 | 1251.87 | 248.54 | Unknown | Unknown | Unknown | 1003.33 | 3981 | 1821.39 | 1251.87 | 569.52 | Yes | N/A | N/A | 2024-09-10 | 2024-11-19 | 71 | 51 | 2024-11-19 | 2024-11-26 | 8 | 6 | 2024-11-26 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-26 | 2025-01-24 | 60 | 44 | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-02-03 | 1900-01-10 | 7 | 2025-02-03 | 2025-02-03 | 1 | 1 | 131 | 95 | 20 | 14 | 151 | 109 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| Combo (R15 & R16) | UG | IOU Design | Commercial | Underserved Community | JAMUL | COUNTY OF SAN DIEGO-SOUTH of 56 | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-31 | 664 | 475 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 79078.87 | 18360.88 | Unknown | 2096.59 | 4678.08 | 53943.32 | 19859 | 43922.94 | 79078.87 | -35155.93 | Yes | N/A | N/A | 2023-10-17 | 2023-10-10 | Unknown | Unknown | 2023-10-10 | 2024-07-10 | 275 | 197 | 2024-01-09 | 2024-01-10 | 2 | 2 | 2024-01-18 | 2025-01-10 | 218 | 155 | 2024-07-10 | 2025-02-24 | 230 | 164 | 2024-07-17 | 2025-02-24 | 223 | 159 | Unknown | 2025-03-27 | Unknown | Unknown | 2025-03-27 | 2025-03-25 | Unknown | Unknown | 232 | 166 | 716 | 511 | 948 | 677 | Steps 2,3,5,6,7 | 589 | 421 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-27 | -716 | -512 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-01 | 2025-04-01 | 2025-04-01 | IOU Designed & Installed | N/A | No | N/A | 49.71 | Unknown | Unknown | Unknown | Unknown | 49.71 | 3981 | 1672.51 | 49.71 | 1622.8 | Yes | N/A | N/A | 2025-04-01 | 2025-04-01 | 1 | 1 | 2025-04-01 | 2025-04-01 | 1 | 1 | 2025-04-01 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-01 | 1 | 1 | Unknown | Unknown | Unknown | Unknown | 2025-04-01 | 2025-04-10 | 1900-01-09 | 8 | 2025-04-10 | 2025-04-10 | 1 | 1 | 2 | 2 | 12 | 10 | 14 | 12 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-03-18 | -703 | -504 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-04 | 2025-04-09 | 2025-04-11 | IOU Designed & Installed | N/A | No | N/A | 782.8 | -14.93 | Unknown | Unknown | Unknown | 797.73 | Unknown | 2025.32 | 782.8 | 1242.52 | Yes | N/A | N/A | 2025-04-04 | 2025-03-31 | Unknown | Unknown | 2025-03-31 | 2025-04-09 | 10 | 8 | 2025-04-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-09 | 2025-04-11 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-04-11 | 2025-04-14 | 1900-01-03 | 2 | 2025-04-14 | 2025-04-14 | 1 | 1 | 3 | 3 | 15 | 11 | 18 | 14 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SPRING VALLEY | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2027-02-08 | -705 | -504 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-02-12 | 2025-02-12 | 2025-02-14 | IOU Designed & Installed | N/A | No | N/A | 149.74 | -1.5 | Unknown | Unknown | Unknown | 151.24 | 3981 | 1616.42 | 149.74 | 1466.68 | Yes | N/A | N/A | 2025-02-12 | 2025-02-11 | Unknown | Unknown | 2025-02-11 | 2025-02-12 | 2 | 2 | 2025-02-12 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-02-12 | 2025-02-14 | 3 | 3 | Unknown | Unknown | Unknown | Unknown | 2025-02-14 | 2025-03-05 | 1900-01-19 | 14 | 2025-03-05 | 2025-03-05 | 1 | 1 | 3 | 3 | 23 | 17 | 26 | 20 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | SAN DIEGO | 36 | 36 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-06-04 | 681 | 487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-03 | 2025-01-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 510.46 | -10.26 | Unknown | Unknown | Unknown | 520.72 | 15924 | 1726.56 | 510.46 | 1216.1 | Yes | N/A | N/A | 2024-12-03 | 2024-12-03 | 1 | 1 | 2024-12-03 | 2025-02-04 | 64 | 46 | Unknown | Unknown | Unknown | Unknown | 2024-12-04 | 2025-01-17 | 45 | 33 | 2025-02-04 | 2025-04-15 | 71 | 51 | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-16 | Unknown | Unknown | 2025-04-16 | 2025-04-15 | Unknown | Unknown | 72 | 52 | 109 | 79 | 181 | 131 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 113.05 | 113.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-15 | -449 | -322 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-02 | 2024-02-05 | 2024-04-18 | IOU Designed & Installed | N/A | No | N/A | 103.39 | -11.45 | Unknown | Unknown | Unknown | 114.84 | 3981 | 919.85 | 103.39 | 816.46 | Yes | N/A | N/A | 2024-02-02 | 2024-02-09 | 8 | 6 | 2024-02-09 | 2024-02-09 | 1 | 1 | 2024-02-09 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-09 | 2024-04-18 | 70 | 50 | Unknown | Unknown | Unknown | Unknown | 2024-04-18 | 2024-04-23 | 1900-01-05 | 4 | 2024-04-23 | 2024-04-22 | Unknown | Unknown | 78 | 56 | 7 | 5 | 85 | 61 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN MARCOS | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-08-15 | -681 | -487 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-08-27 | 2024-08-27 | 2024-09-25 | IOU Designed & Installed | N/A | No | N/A | 20.28 | Unknown | Unknown | Unknown | Unknown | 20.28 | 3891 | 1459.84 | 20.28 | 1439.56 | Yes | N/A | N/A | 2024-08-27 | 2024-08-19 | Unknown | Unknown | 2024-08-19 | 2024-08-27 | 9 | 7 | 2024-08-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-08-27 | 2024-09-25 | 30 | 22 | Unknown | Unknown | Unknown | Unknown | 2024-09-25 | 2024-10-03 | 1900-01-08 | 7 | 2024-10-03 | 2024-10-03 | 1 | 1 | 30 | 22 | 19 | 15 | 49 | 37 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-05 | -647 | -463 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-15 | 2024-11-18 | 2024-11-21 | IOU Designed & Installed | N/A | No | N/A | 27.4 | Unknown | Unknown | Unknown | Unknown | 27.4 | 3981 | 1588.31 | 27.4 | 1560.91 | Yes | N/A | N/A | 2024-11-15 | 2024-11-08 | Unknown | Unknown | 2024-11-08 | 2024-11-18 | 11 | 7 | 2024-11-18 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-18 | 2024-11-21 | 4 | 4 | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | 2024-11-27 | 1900-01-06 | 5 | 2024-11-27 | 2024-11-27 | 1 | 1 | 4 | 4 | 19 | 13 | 23 | 17 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SD 1189-H1 JUNIPERS PH7 (E) | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-08-22 | 496 | 355 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-24 | 2024-04-24 | 2025-04-18 | IOU Designed & Installed | N/A | No | N/A | 5166.08 | Unknown | Unknown | Unknown | Unknown | 5166.08 | 3981 | Not available | 5166.08 | Unknown | Yes | N/A | N/A | 2024-04-24 | 2024-01-03 | Unknown | Unknown | 2024-01-03 | 2024-05-07 | 126 | 90 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-18 | 2024-12-30 | Unknown | Unknown | 2024-12-30 | 2024-12-30 | 1 | 1 | 0 | 0 | 127 | 91 | 127 | 91 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Residential | N/A | SOUTH LAGUNA | N/A | 1033 | 1033 | Not Available | 1MW to 2MW | No | N/A | N/A | N/A | 2023-12-26 | 79 | 58 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-13 | 2023-01-13 | 2023-04-10 | IOU Designed & Installed | N/A | No | N/A | 5.99 | -3.79 | Unknown | Unknown | 8.16 | 1.62 | 3981 | 507.98 | 5.99 | 501.99 | Yes | N/A | N/A | 2023-01-13 | 2023-02-06 | 25 | 17 | 2023-02-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-06 | 2023-04-10 | 64 | 46 | Unknown | 2023-04-05 | Unknown | Unknown | 2023-04-10 | 2024-03-14 | 1900-12-05 | 244 | 2024-03-14 | 2024-03-14 | 1 | 1 | 89 | 63 | 341 | 245 | 430 | 308 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | OH | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2021-07-27 | 1416 | 1013 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-09 | 2024-09-09 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | -1351.83 | -2.29 | Unknown | Unknown | -1466 | 116.46 | Unknown | 1466.11 | -1351.83 | 2817.94 | Yes | N/A | N/A | 2024-09-09 | 2024-09-10 | 2 | 2 | 2024-09-10 | 2024-10-23 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-10-23 | 2025-04-09 | 169 | 121 | Unknown | 2025-06-10 | Unknown | Unknown | 2025-06-11 | 2025-06-12 | 1900-01-01 | 2 | 2025-06-12 | 2025-06-12 | 1 | 1 | 171 | 123 | 47 | 35 | 218 | 158 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-17 | -215 | -154 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-13 | 2023-02-23 | 2023-04-28 | IOU Designed & Installed | N/A | No | N/A | -3.41 | -10.16 | Unknown | Unknown | Unknown | 6.75 | Unknown | 707.65 | -3.41 | 711.06 | Yes | N/A | N/A | 2023-02-13 | 2023-02-23 | 11 | 9 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-23 | 2023-04-28 | 65 | 47 | Unknown | Unknown | Unknown | Unknown | 2023-04-28 | 2023-06-16 | 1900-02-18 | 36 | 2023-06-16 | 2023-06-16 | 1 | 1 | 76 | 56 | 51 | 37 | 127 | 93 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN JUAN CAPISTRANO | N/A | 38 | 38 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-11-15 | -245 | -176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-12-30 | 2022-12-30 | Unknown | IOU Designed & Installed | N/A | No | N/A | -4.12 | -12.06 | Unknown | Unknown | Unknown | 7.94 | 3981 | 1570.25 | -4.12 | 1574.37 | Yes | N/A | N/A | 2022-12-30 | 2023-02-03 | 36 | 26 | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-03 | Unknown | Unknown | Unknown | Unknown | 2023-03-08 | Unknown | Unknown | Unknown | 2023-03-15 | Unknown | Unknown | 2023-03-15 | 2023-03-15 | 1 | 1 | 36 | 26 | 1 | 1 | 37 | 27 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-10-24 | -101 | -74 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-27 | 2023-11-27 | Unknown | IOU Designed & Installed | N/A | No | N/A | -323.44 | 1275.92 | Unknown | 462.7 | -2606 | 543.94 | Unknown | 2606.42 | -323.44 | 2929.86 | Yes | N/A | N/A | 2023-11-27 | 2023-11-27 | 1 | 1 | 2023-11-27 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-07-15 | Unknown | Unknown | 2024-07-15 | 2024-07-15 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-05-01 | -318 | -229 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-21 | 2024-05-21 | 2024-06-14 | IOU Designed & Installed | N/A | No | N/A | -1961.24 | 437.19 | Unknown | 87.28 | -2792 | 306.29 | Unknown | 2791.91 | -1961.24 | 4753.15 | Yes | N/A | N/A | 2024-05-21 | 2024-05-21 | 1 | 1 | 2024-05-21 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-06-14 | 2024-06-17 | 1900-01-03 | 2 | 2024-06-17 | 2024-06-17 | 1 | 1 | 1 | 1 | 5 | 3 | 6 | 4 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | RANCHO SANTA FE | COUNTY OF SAN DIEGO-NORTH of 56 | 15107.05 | 15107.05 | Not Available | >2MW | No | N/A | N/A | N/A | 2023-11-15 | -104 | -75 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-01 | 2023-02-02 | 2023-07-28 | IOU Designed & Installed | N/A | No | N/A | 1585.63 | -30.59 | Unknown | Unknown | 20.14 | 1596.08 | 3981 | 546.86 | 1585.63 | -1038.77 | Yes | N/A | N/A | 2023-02-01 | 2023-02-07 | 7 | 5 | 2023-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-02-07 | 2023-02-08 | 2 | 2 | 2023-02-07 | 2023-07-28 | 172 | 124 | Unknown | 2023-07-12 | Unknown | Unknown | 2023-07-28 | 2023-08-03 | 1900-01-06 | 5 | 2023-08-03 | 2023-08-03 | 1 | 1 | 179 | 129 | 10 | 8 | 189 | 137 | Steps 2,3,5,6,7 | 1 | 1 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-07-09 | -230 | -165 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-10-18 | 2024-10-18 | 2024-11-15 | IOU Designed & Installed | N/A | No | N/A | -804.62 | 1758.68 | Unknown | 384.01 | -3760 | 812.69 | Unknown | 3759.82 | -804.62 | 4564.44 | Yes | N/A | N/A | 2024-10-18 | 2024-10-09 | Unknown | Unknown | 2024-10-09 | 2024-11-21 | 44 | 32 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-21 | Unknown | Unknown | Unknown | 2024-11-21 | 2024-11-21 | 1 | 1 | 2024-11-15 | 2024-11-21 | 1900-01-06 | 5 | 2024-11-21 | 2024-11-21 | 1 | 1 | 0 | 0 | 53 | 39 | 53 | 39 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | VISTA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-01-01 | 1220 | 871 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-15 | 2025-01-15 | 2025-04-24 | IOU Designed & Installed | N/A | No | N/A | 510.66 | Unknown | Unknown | Unknown | 6.38 | 504.28 | Unknown | 1379.75 | 510.66 | 869.09 | Yes | N/A | N/A | 2025-01-15 | 2025-01-15 | 1 | 1 | 2025-01-15 | 2025-01-28 | 14 | 10 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-28 | 2025-03-11 | 43 | 31 | Unknown | 2025-04-15 | Unknown | Unknown | 2025-04-24 | 2025-05-06 | 1900-01-12 | 9 | 2025-05-06 | 2025-05-05 | Unknown | Unknown | 44 | 32 | 27 | 19 | 71 | 51 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | VISTA | VISTA | 10 | 10 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-12-05 | -308 | -221 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-17 | 2024-04-22 | Unknown | IOU Designed & Installed | N/A | No | N/A | 1615.59 | -31.46 | Unknown | Unknown | Unknown | 1647.05 | 0 | 1239.67 | 1615.59 | -375.92 | Yes | N/A | N/A | 2024-04-17 | 2024-03-05 | Unknown | Unknown | 2024-03-05 | 2024-04-22 | 49 | 35 | 2024-04-22 | Unknown | Unknown | Unknown | 2024-06-11 | 2025-01-24 | 30 | 22 | 2024-04-22 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-31 | Unknown | Unknown | 2025-01-31 | 2025-01-31 | 1 | 1 | 0 | 0 | 80 | 58 | 80 | 58 | Steps 2,3,5,6,7 | 277 | 199 | Unknown | Unknown | Not Available | Unknown
| R15 | UG | IOU Design | Commercial | N/A | Carlsbad | N/A | 12 | 12 | Not Available | <1MW | No | N/A | N/A | N/A | 2023-02-28 | 204 | 147 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-07-11 | 2023-07-11 | Unknown | IOU Designed & Installed | N/A | No | N/A | 3122.86 | Unknown | Unknown | Unknown | Unknown | 3122.86 | 46943 | 1933.5 | 3122.86 | -1189.36 | Yes | N/A | N/A | 2023-07-11 | 2023-08-03 | 24 | 18 | 2023-08-03 | 2023-08-14 | 12 | 8 | 2023-08-08 | 2023-08-09 | 2 | 2 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-08-25 | Unknown | Unknown | Unknown | 2023-09-20 | Unknown | Unknown | 2023-09-20 | 2023-09-20 | 1 | 1 | 26 | 20 | 13 | 9 | 39 | 29 | Steps 2,3,5,6,7 | 6 | 4 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-02 | -610 | -437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-23 | 2025-01-23 | 2025-01-29 | IOU Designed & Installed | N/A | No | N/A | 8046.69 | 1930.55 | Unknown | 591.87 | Unknown | 5524.27 | Unknown | 2234.01 | 8046.69 | -5812.68 | Yes | N/A | N/A | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | 2025-01-23 | 1 | 1 | 2025-01-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-23 | 2025-01-29 | 7 | 5 | Unknown | Unknown | Unknown | Unknown | 2025-01-29 | 2025-04-01 | 1900-03-03 | 45 | 2025-04-01 | 2025-04-01 | 1 | 1 | 8 | 6 | 65 | 47 | 73 | 53 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LAKESIDE | N/A | 146.05 | 146.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-12-09 | -609 | -436 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-01-07 | 2025-01-07 | 2025-03-31 | IOU Designed & Installed | N/A | No | N/A | 40.07 | Unknown | Unknown | Unknown | Unknown | 40.07 | 3981 | 2170.9 | 40.07 | 2130.83 | Yes | N/A | N/A | 2025-01-07 | 2025-01-07 | 1 | 1 | 2025-01-07 | 2025-01-24 | 18 | 14 | 2025-01-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-01-24 | 2025-03-31 | 67 | 47 | Unknown | Unknown | Unknown | Unknown | 2025-03-31 | 2025-04-09 | 1900-01-09 | 8 | 2025-04-09 | 2025-04-09 | 1 | 1 | 68 | 48 | 29 | 23 | 97 | 71 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Underserved Community | SAN DIEGO | N/A | 39.05 | 39.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-02-23 | -563 | -402 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-06 | 2024-05-06 | 2024-07-10 | IOU Designed & Installed | N/A | No | N/A | 2812.65 | 241.68 | Unknown | 18.01 | 48.72 | 2504.24 | 3981 | 1360.9 | 2812.65 | -1451.75 | Yes | N/A | N/A | 2024-05-06 | 2024-05-15 | 10 | 8 | 2024-05-15 | 2024-05-15 | 1 | 1 | 2024-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-15 | 2024-07-10 | 57 | 41 | Unknown | 2024-07-05 | Unknown | Unknown | 2024-07-10 | 2024-08-15 | 1900-02-05 | 27 | 2024-08-15 | 2024-08-09 | Unknown | Unknown | 67 | 49 | 38 | 28 | 105 | 77 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-03-17 | 269 | 192 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-04-29 | 2022-05-03 | Unknown | IOU Designed & Installed | N/A | No | N/A | 2613.73 | 2910.08 | Unknown | 1864.2 | -3483 | 1322.45 | Unknown | 3482.79 | 2613.73 | 869.06 | Yes | N/A | N/A | 2022-04-29 | 2023-06-29 | 427 | 305 | 2023-06-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-12-11 | Unknown | Unknown | 2023-12-11 | 2023-12-11 | 1 | 1 | 427 | 305 | 1 | 1 | 428 | 306 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 57 | 57 | Not Available | <1MW | No | N/A | N/A | N/A | 2025-06-20 | -422 | -303 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-05 | 2024-02-07 | 2024-04-18 | IOU Designed & Installed | N/A | No | N/A | 776.7 | -15.25 | Unknown | Unknown | Unknown | 791.95 | 3981 | 790.13 | 776.7 | 13.43 | Yes | N/A | N/A | 2024-02-05 | 2023-08-11 | Unknown | Unknown | 2023-08-11 | 2024-02-07 | 181 | 129 | 2024-02-07 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-07 | 2024-04-18 | 72 | 52 | Unknown | 2024-04-17 | Unknown | Unknown | 2024-04-18 | 2024-04-24 | 1900-01-06 | 5 | 2024-04-24 | 2024-04-24 | 1 | 1 | 72 | 52 | 189 | 135 | 261 | 187 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2022-08-31 | 610 | 437 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-04 | 2024-04-04 | Unknown | IOU Designed & Installed | N/A | No | N/A | 645.72 | -11.79 | Unknown | Unknown | Unknown | 657.51 | Unknown | 222.67 | 645.72 | -423.05 | Yes | N/A | N/A | 2024-04-04 | 2024-04-12 | 9 | 7 | 2024-04-12 | 2024-04-16 | 5 | 3 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-16 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-02 | Unknown | Unknown | 2024-05-02 | 2024-05-02 | 1 | 1 | 9 | 7 | 6 | 4 | 15 | 11 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | CHULA VISTA | N/A | 118 | 118 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-07-10 | -387 | -278 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2025-04-16 | 2025-05-19 | 2025-06-09 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 7962 | 1801.97 | Unknown | Unknown | Yes | N/A | N/A | 2025-04-16 | 2025-05-19 | 34 | 24 | 2025-05-19 | 2025-05-20 | 2 | 2 | 2025-05-20 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-05-20 | 2025-06-09 | 21 | 15 | Unknown | Unknown | Unknown | Unknown | 2025-06-09 | 2025-06-18 | 1900-01-09 | 8 | 2025-06-18 | 2025-06-18 | 1 | 1 | 55 | 39 | 13 | 11 | 68 | 50 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-04-02 | -533 | -382 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-29 | 2024-04-29 | 2024-09-30 | IOU Designed & Installed | N/A | No | N/A | 844.03 | Unknown | Unknown | Unknown | 13.06 | 830.97 | 3981 | 1120.95 | 844.03 | 276.92 | Yes | N/A | N/A | 2024-04-29 | 2024-05-28 | 30 | 22 | 2024-05-28 | 2024-05-29 | 2 | 2 | 2024-05-29 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-29 | 2024-09-30 | 125 | 89 | Unknown | 2024-08-09 | Unknown | Unknown | 2024-09-30 | 2024-10-16 | 1900-01-16 | 13 | 2024-10-16 | 2024-10-16 | 1 | 1 | 155 | 111 | 20 | 16 | 175 | 127 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | Underserved Community | OCEANSIDE | OCEANSIDE | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2024-09-28 | 247 | 176 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-10-17 | 2023-10-17 | 2025-05-19 | IOU Designed & Installed | N/A | No | N/A | 1133.2 | 124.03 | Unknown | Unknown | 49.87 | 959.3 | Unknown | 3625.11 | 1133.2 | 2491.91 | Yes | N/A | N/A | 2023-10-17 | 2025-01-09 | 451 | 323 | 2025-01-09 | 2025-02-04 | 27 | 19 | 2024-10-22 | 2024-12-13 | 39 | 29 | 2024-08-15 | 2024-12-31 | 104 | 74 | 2025-02-04 | 2025-05-15 | 101 | 73 | Unknown | 2025-04-11 | Unknown | Unknown | 2025-05-19 | 2025-06-02 | 1900-01-14 | 11 | 2025-06-02 | 2025-06-02 | 1 | 1 | 591 | 425 | 147 | 105 | 738 | 530 | Steps 2,3,5,6,7 | 225 | 161 | Meeting | Meeting | Not Available | N/A
| R15 | OH | Applicant Design | Commercial | Disadvantaged Community,Underserved Community | National City | NATIONAL CITY | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-12 | 524 | 375 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-07-16 | 2024-07-16 | 2025-04-24 | Customer elected Applicant Design | Step 2 Engineering & Design | No | N/A | 43174.25 | 10816.14 | Unknown | Unknown | 39.38 | 32318.73 | 522244.96 | 39149.78 | 43174.25 | -4024.47 | Yes | N/A | N/A | 2024-07-16 | 2024-10-23 | 100 | 72 | 2024-10-23 | 2025-02-27 | 128 | 92 | 2024-10-31 | 2025-02-26 | 27 | 19 | 2024-08-19 | 2025-07-10 | 123 | 90 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2025-04-24 | 2025-05-19 | 1900-01-25 | 18 | 2025-05-19 | 2025-05-19 | 1 | 1 | 127 | 91 | 278 | 201 | 405 | 292 | Steps 2,3,5,6,7 | 310 | 222 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 156 | 156 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-03-13 | -270 | -195 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-25 | 2024-04-25 | 2025-06-11 | IOU Designed & Installed | N/A | No | N/A | Unknown |  | Unknown | Unknown | Unknown | Unknown | 3981 | 1709.69 | Unknown | Unknown | Yes | N/A | N/A | 2024-04-25 | 2024-10-29 | 188 | 134 | 2024-10-29 | 2024-11-06 | 9 | 7 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2025-06-11 | 218 | 156 | Unknown | 2025-05-22 | Unknown | Unknown | 2025-06-11 | 2025-06-16 | 1900-01-05 | 4 | 2025-06-16 | 2025-06-16 | 1 | 1 | 406 | 290 | 16 | 12 | 422 | 302 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | MISSION VIEJO | N/A | 7 | 7 | Not Available | <1MW | No | N/A | N/A | N/A | 2024-01-25 | -182 | -131 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-01 | 2023-06-01 | 2023-07-25 | IOU Designed & Installed | N/A | No | N/A | 2224.12 | 469.72 | Unknown | 167.45 | 0.54 | 1586.41 | 3981 | 1963.96 | 2224.12 | -260.16 | Yes | N/A | N/A | 2023-06-01 | 2023-06-19 | 19 | 13 | 2023-06-19 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-06-16 | 2023-07-25 | 40 | 28 | Unknown | Unknown | Unknown | Unknown | 2023-07-25 | 2023-07-27 | 1900-01-02 | 3 | 2023-07-27 | 2023-07-27 | 1 | 1 | 59 | 41 | 4 | 4 | 63 | 45 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Commercial | Disadvantaged Community,Underserved Community | San Diego | N/A | Unknown | Unknown | Not Available | Unknown | No | N/A | N/A | N/A | 2023-05-10 | 309 | 222 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-10 | 2024-01-25 | 2024-02-26 | IOU Designed & Installed | N/A | No | N/A | 9892.55 | Unknown | Unknown | Unknown | Unknown | 9892.55 | Unknown | 4128.42 | 9892.55 | -5764.13 | Yes | N/A | N/A | 2024-01-10 | 2024-01-30 | 21 | 15 | 2024-01-30 | 2024-02-09 | 11 | 9 | Unknown | Unknown | Unknown | Unknown | 2024-01-31 | 2024-02-13 | 14 | 10 | 2024-02-13 | Unknown | Unknown | Unknown | 2024-02-13 | Unknown | Unknown | Unknown | 2024-02-26 | 2024-03-14 | 1900-01-17 | 14 | 2024-03-14 | 2024-03-14 | 1 | 1 | 21 | 15 | 44 | 34 | 65 | 49 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | 310.05 | 310.05 | Not Available | <1MW | No | N/A | N/A | N/A | 2026-01-24 | -530 | -380 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-14 | 2024-03-22 | 2024-07-23 | IOU Designed & Installed | N/A | No | N/A | 4.84 | Unknown | Unknown | Unknown | Unknown | 4.84 | Unknown | 163.83 | 4.84 | 158.99 | Yes | N/A | N/A | 2024-03-14 | 2024-02-13 | Unknown | Unknown | 2024-02-13 | 2024-04-15 | 63 | 45 | 2024-04-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-04-15 | 2024-07-23 | 100 | 72 | Unknown | 2024-06-26 | Unknown | Unknown | 2024-07-23 | 2024-08-12 | 1900-01-20 | 15 | 2024-08-12 | 2024-08-12 | 1 | 1 | 100 | 72 | 85 | 61 | 185 | 133 | N/A | 0 | 0 | Unknown | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | Underserved Community | LA MESA | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-05-20 | -667 | -478 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-23 | 2024-05-24 | 2024-06-12 | IOU Designed & Installed | N/A | No | N/A | 1280.42 | -31.08 | Unknown | Unknown | Unknown | 1311.5 | 3981 | 1406.91 | 1280.42 | 126.49 | Yes | N/A | N/A | 2024-05-23 | 2024-05-24 | 2 | 2 | 2024-05-24 | 2024-05-24 | 1 | 1 | 2024-05-24 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-05-24 | 2024-06-12 | 20 | 14 | Unknown | Unknown | Unknown | Unknown | 2024-06-12 | 2024-07-22 | 1900-02-09 | 29 | 2024-07-22 | 2024-07-22 | 1 | 1 | 22 | 16 | 43 | 31 | 65 | 47 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | ESCONDIDO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2025-03-14 | 4 | 3 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-15 | 2023-05-25 | 2023-08-17 | IOU Designed & Installed | N/A | No | N/A | 48.42 | -12.52 | Unknown | Unknown | 54.86 | 6.08 | 3981 | 737.39 | 48.42 | 688.97 | Yes | N/A | N/A | 2023-05-15 | 2023-05-25 | 11 | 9 | 2023-05-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-25 | 2023-08-17 | 85 | 61 | Unknown | Unknown | Unknown | Unknown | 2023-08-17 | 2025-03-18 | 1901-08-02 | 414 | 2025-03-18 | 2025-03-18 | 1 | 1 | 96 | 70 | 581 | 415 | 677 | 485 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown
| R16 | UG | IOU Design | Commercial | N/A | CARLSBAD | CARLSBAD | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-31 | 260 | 187 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-07 | 2023-06-07 | Unknown | IOU Designed & Installed | N/A | No | N/A | 13214.38 | Unknown | Unknown | Unknown | -196 | 13410.38 | Unknown | 215.6 | 13214.38 | -12998.78 | Yes | N/A | N/A | 2023-06-07 | 2024-01-16 | 224 | 160 | 2024-01-16 | 2024-01-31 | 16 | 12 | 2023-08-23 | 2023-10-16 | 55 | 39 | 2023-08-11 | 2023-11-15 | 38 | 19 | 2024-01-31 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-02-15 | Unknown | Unknown | 2024-02-15 | 2024-02-15 | 1 | 1 | 279 | 199 | 55 | 32 | 334 | 231 | Steps 2,3,5,6,7 | 227 | 161 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | CARLSBAD | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-10-04 | -493 | -352 | No | 2024-11-04 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-04 | 2024-11-04 | 2025-05-21 | IOU Designed & Installed | N/A | Yes | 65 | 5827.3 | 1018.8 | Unknown | Unknown | 28.4 | 4780.1 | 3981 | 1570.98 | 5827.3 | -4256.32 | Yes | N/A | N/A | 2024-11-04 | 2025-01-08 | 66 | 48 | 2025-01-08 | 2024-11-25 | Unknown | Unknown | 2024-11-25 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-25 | 2025-05-21 | 178 | 128 | Unknown | 2025-04-29 | Unknown | Unknown | 2025-05-21 | 2025-05-29 | 1900-01-08 | 7 | 2025-05-29 | 2025-05-29 | 1 | 1 | 244 | 176 | 10 | 8 | 254 | 184 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | Disadvantaged Community,Underserved Community | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-05-01 | 80 | 59 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-17 | 2023-03-17 | Unknown | IOU Designed & Installed | N/A | No | N/A | 609.69 | -17.72 | Unknown | Unknown | Unknown | 627.41 | Unknown | 432 | 609.69 | -177.69 | Yes | N/A | N/A | 2023-03-17 | 2023-03-17 | 1 | 1 | 2023-03-17 | 2023-05-15 | 60 | 42 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-05-15 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2023-07-20 | Unknown | Unknown | 2023-07-20 | 2023-07-20 | 1 | 1 | 1 | 1 | 61 | 43 | 62 | 44 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | OH | IOU Design | Residential | N/A | SOLANA BEACH | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2026-09-17 | -548 | -393 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-11-01 | 2024-11-06 | 2025-01-13 | IOU Designed & Installed | N/A | No | N/A | -3.01 | -12.53 | Unknown | Unknown | Unknown | 9.52 | 3981 | 1853.67 | -3.01 | 1856.68 | Yes | N/A | N/A | 2024-11-01 | 2024-10-29 | Unknown | Unknown | 2024-10-29 | 2024-11-06 | 9 | 7 | 2024-11-06 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2024-11-06 | 2025-01-13 | 69 | 49 | Unknown | Unknown | Unknown | Unknown | 2025-01-13 | 2025-03-18 | 1900-03-05 | 47 | 2025-03-18 | 2025-03-18 | 1 | 1 | 69 | 49 | 75 | 55 | 144 | 104 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R15 | UG | IOU Design | Residential | Underserved Community | San Diego | SAN DIEGO | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2023-12-01 | 454 | 325 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-10 | 2024-04-10 | 2025-01-03 | IOU Designed & Installed | N/A | No | N/A | 10440.94 | 101.73 | Unknown | Unknown | -10549.61 | 20888.82 | Unknown | 10550.23 | 10440.94 | 109.29 | Yes | N/A | N/A | 2024-04-10 | 2024-04-23 | 14 | 10 | 2024-04-23 | 2024-09-04 | 135 | 97 | 2024-06-12 | 2024-10-09 | 11 | 9 | 2024-09-03 | 2024-12-05 | 60 | 42 | 2024-12-03 | Unknown | Unknown | Unknown | 2024-12-03 | 2024-12-03 | 1 | 1 | 2025-01-03 | 2025-02-27 | 1900-02-24 | 40 | 2025-02-27 | 2025-02-27 | 1 | 1 | 25 | 19 | 253 | 181 | 278 | 200 | Steps 2,3,5,6,7 | 122 | 88 | Unknown | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Commercial | N/A | SOLANA BEACH | N/A | 132 | 132 | Not Available | <1MW | No | N/A | N/A | N/A | 2022-07-17 | 309 | 221 | No | 2022-09-07 | Step 2 Engineering & Design | Yes | No | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-07 | 2022-09-08 | 2023-05-18 | IOU Designed & Installed | N/A | Yes | 169 | 1717.67 | 335.6 | Unknown | 100.24 | Unknown | 1281.83 | Unknown | 284.26 | 1717.67 | -1433.41 | Yes | N/A | N/A | 2022-09-07 | 2023-02-23 | 170 | 122 | 2023-02-23 | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | 2022-09-08 | 2023-05-18 | Unknown | Unknown | Unknown | 2023-05-18 | Unknown | Unknown | 2023-05-18 | 2023-05-22 | 1900-01-04 | 3 | 2023-05-22 | 2023-05-22 | 1 | 1 | 170 | 122 | 6 | 4 | 176 | 126 | N/A | 0 | 0 | Meeting | Meeting | Not Available | N/A
| R16 | UG | IOU Design | Residential | N/A | SAN DIEGO | N/A | Unknown | Unknown | Not Available | <1MW | No | N/A | N/A | N/A | 2024-06-08 | -18 | -14 | No | N/A | N/A | No | No | N/A | N/A | N/A | N/A | N/A | N/A | 2023-11-01 | 2023-11-01 | 2024-05-08 | IOU Designed & Installed | N/A | No | N/A | 823.58 | 432.4 | Unknown | 110.16 | Unknown | 281.02 | 0 | 158.14 | 823.58 | -665.44 | Yes | N/A | N/A | 2023-11-01 | 2023-06-19 | Unknown | Unknown | 2023-06-19 | 2023-11-10 | 145 | 105 | 2023-11-10 | 2024-05-08 | 181 | 129 | Unknown | Unknown | Unknown | Unknown | 2023-11-10 | 2024-05-08 | 181 | 129 | Unknown | Unknown | Unknown | Unknown | 2024-05-08 | 2024-05-21 | 1900-01-13 | 10 | 2024-05-21 | 2024-05-21 | 1 | 1 | 362 | 258 | 160 | 116 | 522 | 374 | N/A | 0 | 0 | Unknown | Unknown | Not Available | Unknown