## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | WMP CATEGORY | WMP INITIATIVE | WMP ACTIVITY NAME | TARGET ID (IF MULTIPLE) | UTILITY MITIGATION ACTIVITY TRACKING ID (UMAT) | ACTIVITY CLASSIFICATION | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP SECTION | RISK COMPONENT TARGETED | QUANT / QUAL | QUANT TARGET UNITS | MIDYEAR TARGET (YES / NO) | COMMENTS | BLANK MEANING | REPORTING YEAR | REPORTING QUARTER | QUANT YTD VALUE | QUAL YTD VALUE | STATUS | CORRECTIVE ACTIONS IF DELAYED
1010000000 | SDG&E | 2026-08-01 | Risk Methodology and Assessment | Risk Methodology and Assessment | Risk Methodology and Assessment |  | WMP.0442 | Program | A summarized risk map that shows the overall ignition probability and estimated wildfire consequence along the electric lines and equipment (WiNGS) | Enhance WiNGS Visualization Platform | 05.07.01 | Wildfire spread Wildfire hazard Wildfire exposure potential Wildfire vulnerability PSPS likelihood PSPS exposure potential PSPS vulnerability | Qualitative |  | No | WMP.0442-Risk Methodology and Assessment |  | 2026 | 2 |  | In Q2, the team continued enhancing risk visualization and analysis capabilities to improve access to reliable risk information and support operational and mitigation investment planning decisions. Efforts focused on improving data usability, application performance, and analytical capabilities to enable faster and more efficient evaluation of investment planning scenarios. Progress included further integrating asset, risk, and financial information within a centralized visualization environment, improving data accessibility, geospatial analysis, and visibility into assets, investment alternatives, and projected outcomes. The team also strengthened data consistency and accessibility by consolidating information into standardized, trusted data sources, reducing the effort required to access and analyze information across planning activities. In parallel, analytical process enhancements improved model performance and scalability through parallel computing, reducing processing times and supporting increasingly complex risk assessments. Feedback from planning and operations users informed enhancements to improve access to critical asset and risk information, expand visibility into asset characteristics and relationships, strengthen segment-level geospatial analysis capabilities, and increase the usability and configurability of visualizations. Improvements included more configurable and persistent user views, enhanced commenting and map interactions, expanded visibility into circuit segments and asset details, and refined dashboard labels, legends, tooltips, and data access features to help users more quickly understand wildfire risk, PSPS risk, customer impacts, and asset relationships. These efforts continue to improve platform usability, stability, and decision-making effectiveness. | In Progress
1010000001 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Covered conductor installation |  | WMP.0455 | Project | Covered conductor utilizes conductors manufactured with an internal semiconducting layer and external insulating ultraviolet-resistant layer to provide incidental contact protection. The Covered Conductor program has the potential to raise the threshold for PSPS events to higher wind speeds compared to bare conductor. | Covered conductor utilizes conductors manufactured with an internal semiconducting layer and external insulating ultraviolet-resistant layer to provide incidental contact protection. The Covered Conductor program has the potential to raise the threshold for PSPS events to higher wind speeds compared to bare conductor. | 08.02.01 | Contact from vegetation ignition likelihood Contact by object ignition likelihood | Quantitative | Miles | No | WMP.0455-Combined Covered Conductor |  | 2026 | 2 | 8.36 |  | In Progress
1010000002 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Undergrounding of electric lines and/or equipment |  | WMP.0473 | Project | Strategic undergrounding converts overhead systems to underground, providing the dual benefits of nearly eliminating the risk of utility-caused wildfire and the need for PSPS events in these areas. | Strategic undergrounding converts overhead systems to underground, providing the dual benefits of nearly eliminating the risk of utility-caused wildfire and the need for PSPS events in these areas. | 08.02.02 | Equipment ignition likelihood Contact from vegetation ignition likelihood Contact by object ignition | Quantitative | Miles | No | WMP.0473-Strategic Undergrounding |  | 2026 | 2 | 1.38 |  | Completed
1010000003 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Traditional overhead hardening |  | WMP.0475 | Project | Bare Conductor Hardening includes the replacement of wood poles with steel, replacement of conductor with high-strength bare conductor, and in some cases permanent removal of overhead facilities. | Bare Conductor Hardening includes the replacement of wood poles with steel, replacement of conductor with high-strength bare conductor, and in some cases permanent removal of overhead facilities. | 08.02.05 | Equipment ignition likelihood | Quantitative | Miles | No | WMP.0475-Distribution Overhead System Hardening |  | 2026 | 2 | 2.52 |  | In Progress
1010000004 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Traditional overhead hardening |  | WMP.0543 | Project | The Transmission System Hardening Program is a program that utilizes enhanced design criteria to replace wood poles with steel poles, replace aging conductors with high strength conductors, and increase conductor spacing in the HFTD to reduce the chance of risk events and ignitions. | The Transmission System Hardening Program is a program that utilizes enhanced design criteria to replace wood poles with steel poles, replace aging conductors with high strength conductors, and increase conductor spacing in the HFTD to reduce the chance of risk events and ignitions. | 08.02.05 | Equipment ignition likelihood | Quantitative | Miles | No | WMP.0543-Transmission Overhead Hardening |  | 2026 | 2 | 5.79 |  | In Progress
1010000005 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Traditional overhead hardening |  | WMP.0545 | Project | The Transmission System Hardening Program is a program that utilizes enhanced design criteria to replace wood poles with steel poles, replace aging conductors with high strength conductors, and increase conductor spacing in the HFTD to reduce the chance of risk events and ignitions. | The Transmission System Hardening Program is a program that utilizes enhanced design criteria to replace wood poles with steel poles, replace aging conductors with high strength conductors, and increase conductor spacing in the HFTD to reduce the chance of risk events and ignitions. | 08.02.05 | Equipment ignition likelihood | Quantitative | Miles | No | WMP.0545-Transmission Overhead Hardening (Distribution Underbuild) |  | 2026 | 2 | 0.16 |  | In Progress
1010000006 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Microgrids |  | WMP.0462 | Project | Microgrid backup generation and battery storage to reduce the impact of PSPS. | Microgrid backup generation and battery storage to reduce the impact of PSPS. | 08.02.07 | PSPS vulnerability | Quantitative | Microgrids | No | WMP.0462-Microgrids |  | 2026 | 2 | 0 |  | Completed
1010000007 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Installation of system automation equipment |  | WMP.0463 | Project | Advanced Protection creates higher visibility and situational awareness in fire-prone areas, and allow for the implementation of new relay and automation standards in locations where protection coordination is difficult due to lower fault currents attributed to high impedance faults. | Advanced Protection creates higher visibility and situational awareness in fire-prone areas, and allow for the implementation of new relay and automation standards in locations where protection coordination is difficult due to lower fault currents attributed to high impedance faults. | 08.02.08 | Equipment ignition likelihood | Quantitative | Nodes | No | WMP.0463-Advanced Protection |  | 2026 | 2 | 5 |  | In Progress
1010000008 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to minimize risk of ignitions |  | WMP.1189 | Project | Strategic Pole Remediation targets high-risk poles located throughout the service territory that are gas treated (also known as Cellon treatment) and are set in concrete and steel reinforced, steel reinforced and set in soil, or set in soil, and are not being address by other programs such as Covered Conductor Hardening or Strategic Undergrounding. | Strategic Pole Remediation targets high-risk poles located throughout the service territory that are gas treated (also known as Cellon treatment) and are set in concrete and steel reinforced, steel reinforced and set in soil, or set in soil, and are not being address by other programs such as Covered Conductor Hardening or Strategic Undergrounding. | 08.02.10 | Equipment ignition likelihood | Quantitative | Poles | No | WMP.1189-Strategic Pole Remediation |  | 2026 | 2 | 69 |  | In Progress
1010000009 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to mitigate or reduce PSPS events |  | WMP.0467 | Project | Provide rebates on backup power solutions for eligible customers in the high fire threat district. | Provide rebates on backup power solutions for eligible customers in the high fire threat district. | 08.02.11 | PSPS vulnerability | Qualitative |  | No | WMP.0467-Generator Assistance Program |  | 2026 | 2 |  | Program invitation letter and email campaigns were completed in April, followed by a targeted marketing campaign for customers who reserved coupons but did not yet redeem them. An additional outreach email campaign targeting customers with unredeemed coupons began in June for the current program year. The GAP program was promoted at Wildfire Safety Fairs. The qualified product list continued to be monitored to ensure rebate amounts remained aligned with product pricing. Rebate processing activities began in April. | In Progress
1010000010 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to mitigate or reduce PSPS events |  | WMP.0468 | Project | Assess and enable resiliency and backup power solutions for eligible non-residential customers in the high fire threat district. | Assess and enable resiliency and backup power solutions for eligible non-residential customers in the high fire threat district. | 08.02.11 | PSPS vulnerability | Qualitative |  | No | WMP.0468-Standby Power Program (Fixed Backup Power Commercial) |  | 2026 | 2 |  | Additional testing at the Fallbrook Library CRC site was conducted in the form of two outage simulations to evaluate backup power capacity capabilities in preparation for PSPS scenarios. Installation work has continued at the Whispering Winds CRC site in Julian. That project is etimated to be completed in Q3 of 2026. Q2 also included continued design and feasibility activities focused on backup power solution offerings for K12 schools in the high fire threat district that experience PSPS outages. In addition, the team has begun customer engagement efforts to better understand school needs, gather input on solution requirements, and support the development of the program offering. | In Progress
1010000011 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to mitigate or reduce PSPS events |  | WMP.0461 | Project | PSPS Sectionalizing Enhancement Program installs switches in strategic locations, improving the ability to isolate high-risk areas for potential de energization. For example, switches are installed on circuits that have significant sections undergrounded, allowing customers with this lower-risk infrastructure to remain energized during weather events. | PSPS Sectionalizing Enhancement Program installs switches in strategic locations, improving the ability to isolate high-risk areas for potential de energization. For example, switches are installed on circuits that have significant sections undergrounded, allowing customers with this lower-risk infrastructure to remain energized during weather events. | 08.02.11 | PSPS exposure potential PSPS vulnerability | Quantitative | Switches | No | WMP.0461-PSPS Sectionalizing Enhancements |  | 2026 | 2 | 0 |  | Planned
1010000012 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Other grid topology improvements to mitigate or reduce PSPS events |  | WMP.1432 | Project | Assess and enable resiliency and backup power solutions for eligible residential customers in the high fire threat district. | Assess and enable resiliency and backup power solutions for eligible residential customers in the high fire threat district. | 08.02.11 | PSPS vulnerability | Qualitative |  | No | WMP.1432-Customized Resiliancy Assessments |  | 2026 | 2 |  | In Q2 of 2026, efforts for the Customized Resiliency Assessments (CRA) Program continued to advance toward finalization and operational readiness. Key activities focused on completing contract execution with the implementation partner, refining operational workflows for customer intake, assessments, referrals, and coordinated service delivery, and preparing for program launch activities. Transition planning for the Generator Grant Program (GGP) also continued to progress, supporting a seamless shift to the CRA Program. Throughout the transition period, eligible customers continued to receive resiliency assessments and backup power delivery services to ensure uninterrupted access to resiliency support while program implementation activities moved toward completion. | In Progress
1010000013 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Distribution Overhead Detailed Inspections |  | WMP.0478 | Program | Perform overhead detailed inspections, as scheduled, to reduce the risk of equipment failure. | Perform overhead detailed inspections, as scheduled, to reduce the risk of equipment failure. | 08.03 | Equipment ignition likelihood | Quantitative | Inspections | Yes | WMP.0478-Distribution Overhead Detailed Inspections |  | 2026 | 2 | 18425 |  | In Progress
1010000014 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Distribution Overhead Patrol Inspections |  | WMP.0488 | Program | Perform overhead patrol inspections, as scheduled, to reduce the risk of equipment failure | Perform overhead patrol inspections, as scheduled, to reduce the risk of equipment failure | 08.03 | Equipment ignition likelihood | Quantitative | Inspections | Yes | WMP.0488-Distribution Overhead Patrol Inspections |  | 2026 | 2 | 61481 |  | In Progress
1010000015 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Distribution Wood Pole Intrusive Inspections |  | WMP.0483 | Program | Perform intrusive inspections, as scheduled, to reduce the risk of equipment failure | Perform intrusive inspections, as scheduled, to reduce the risk of equipment failure | 08.03 | Equipment ignition likelihood | Quantitative | Inspections | Yes | WMP.0483-Distribution Wood Pole Intrusive Inspections |  | 2026 | 2 | 1186 |  | In Progress
1010000016 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Risk-Informed Drone Inspections |  | WMP.0552 | Program | Perform drone inspections on highest risk structures in the HFTD and WUI areas. | Perform drone inspections on highest risk structures in the HFTD and WUI areas. | 08.03 | Equipment ignition likelihood | Quantitative | Inspections | Yes | WMP.0552-Risk-Informed Drone Inspections |  | 2026 | 2 | 0 |  | Planned
1010000017 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Substation Patrol Inspections |  | WMP.0492 | Program | Perform substation patrols, as scheduled, to reduce the risk of equipment failure and to manage vegetation hazards within the substation. | Perform substation patrols, as scheduled, to reduce the risk of equipment failure and to manage vegetation hazards within the substation. | 08.03 | Equipment ignition likelihood | Quantitative | Inspections | Yes | WMP.0492-Substation Patrol Inspections |  | 2026 | 2 | 191 |  | In Progress
1010000018 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Transmission Infrared Inspections |  | WMP.0482 | Program | Perform infrared inspections, as scheduled, to reduce the risk of equipment failure. | Perform infrared inspections, as scheduled, to reduce the risk of equipment failure. | 08.03 | Equipment ignition likelihood | Quantitative | Inspections | Yes | WMP.0482-Transmission Infrared Inspections |  | 2026 | 2 | 0 |  | Planned
1010000019 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Transmission Overhead Patrol Inspections |  | WMP.0489 | Program | Perform overhead patrol inspections, as scheduled, to reduce the risk of equipment failure | Perform overhead patrol inspections, as scheduled, to reduce the risk of equipment failure | 08.03 | Equipment ignition likelihood | Quantitative | Inspections | Yes | WMP.0489-Transmission Overhead Patrol Inspections |  | 2026 | 2 | 6983 |  | In Progress
1010000020 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Transmission Wood Pole Intrusive Inspections |  | WMP.1190 | Program | Perform intrusive inspections, as scheduled, to reduce the risk of equipment failure | Perform intrusive inspections, as scheduled, to reduce the risk of equipment failure | 08.03 | Equipment ignition likelihood | Quantitative | Inspections | Yes | WMP.1190-Transmission Wood Pole Intrusive Inspections |  | 2026 | 2 | 3 |  | In Progress
1010000021 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Transmisson Overhead Detailed Inspections |  | WMP.0479 | Program | Perform overhead detailed inspections, as scheduled, to reduce the risk of equipment failure. | Perform overhead detailed inspections, as scheduled, to reduce the risk of equipment failure. | 08.03 | Equipment ignition likelihood | Quantitative | Inspections | Yes | WMP.0479-Transmisson Overhead Detailed Inspections |  | 2026 | 2 | 1313 |  | In Progress
1010000022 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Asset Inspections | Transmission Switch Inspections |  | WMP.1509 | Program | Evaluate transmission switches in the HFTD to verify functionality, identify potential issues, and determine if repair or replacement is needed | Evaluate transmission switches in the HFTD to verify functionality, identify potential issues, and determine if repair or replacement is needed | 08.03 | Equipment ignition likelihood | Quantitative | Inspections | Yes | WMP.1509-Transmission Switch Inspection |  | 2026 | 2 | 0 |  | Planned
1010000023 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Equipment Maintenance and Repair | Transmission Asset Health |  | WMP.1458 | Program | Analyze asset heath for transmission shield wire, insulators, and hardware; explore proactive replacement strategies | Analyze asset heath for transmission shield wire, insulators, and hardware; explore proactive replacement strategies | 08.04 | Equipment ignition likelihood | Qualitative |  | No | WMP.1458-Transmission Asset Health |  | 2026 | 2 |  | SDG&E continues development of its asset health evaluation system for shield wires and has begun development for insulators on transmission structures. This includes intake of asset data from initial design packages to validate age, material type, and physical locations as well as historical data including outage and compliance conditions identified. Full system data is in the process of being validated and asset health analysis is being further developed to automate job package intake after construction. | In Progress
1010000024 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Quality Assurance / Quality Control of Transmission Inspections |  | WMP.1191 | Program | Ensure inspections are following SDG&E’s procedures for inspections | Ensure inspections are following SDG&E’s procedures for inspections | 08.05 | Equipment ignition likelihood | Quantitative | Findings | No | WMP.1191-Quality Assurance / Quality Control of Transmission Inspections |  | 2026 | 2 | 100% |  | In Progress
1010000025 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Quality Assurance / Quality Control of Corrective Maintenance Program |  | WMP.1434 | Program | Ensure SDG&E repair procedures are being adhered to | Ensure SDG&E repair procedures are being adhered to | 08.05 | Equipment ignition likelihood | Quantitative | OH Fire or Safety Related Corrective Actions | No | WMP.1434-Quality Assurance / Quality Control of Corrective Maintenance Program |  | 2026 | 2 | 2.713% |  | In Progress
1010000026 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Quality Assurance / Quality Control of Distribution Detailed Inspections |  | WMP.0491 | Program | Ensure SDG&E inspection procedures are being adhered to | Ensure SDG&E inspection procedures are being adhered to | 08.05 | Equipment ignition likelihood | Quantitative | Findings | No | WMP.0491-Quality Assurance / Quality Control of Distribution Detailed Inspections |  | 2026 | 2 | 44.52% |  | In Progress
1010000027 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Quality assurance/quality control of PSPS Sectionalizing Enhancement Program |  | WMP.1435 | Program | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | 08.05 | Equipment ignition likelihood | Quantitative | Switches | No | WMP.1435-Quality assurance/quality control of PSPS Sectionalizing Enhancement Program |  | 2026 | 2 | 0% |  | Planned
1010000028 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Quality assurance/quality control of Advanced Protection Program |  | WMP.1496 | Program | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | 08.05 | Equipment ignition likelihood | Quantitative | Nodes | No | WMP.1496-Quality assurance/quality control of Advanced Protection Program |  | 2026 | 2 | 0% |  | Planned
1010000029 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Quality assurance/quality control of Strategic Undergrounding Program |  | WMP.1497 | Program | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | 08.05 | Equipment ignition likelihood | Quantitative | Miles | No | WMP.1497-Quality assurance/quality control of Strategic Undergrounding Program |  | 2026 | 2 | 16.6% |  | In Progress
1010000030 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Quality assurance/quality control of Distribution Overhead System Hardening Program |  | WMP.1498 | Program | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | 08.05 | Equipment ignition likelihood | Quantitative | Miles | No | WMP.1498-Quality assurance/quality control of Distribution Overhead System Hardening Program |  | 2026 | 2 | 24% |  | In Progress
1010000031 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Quality assurance/quality control of Transmission Overhead Hardening |  | WMP.1499 | Program | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | 08.05 | Equipment ignition likelihood | Quantitative | Miles | No | WMP.1499-Quality assurance/quality control of Transmission Overhead Hardening |  | 2026 | 2 | 0% |  | Planned
1010000032 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Quality assurance/quality control of Transmission Overhead Hardening (Distribution Underbuild) |  | WMP.1500 | Program | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | 08.05 | Equipment ignition likelihood | Quantitative | Miles | No | WMP.1500-Quality assurance/quality control of Transmission Overhead Hardening (Distribution Underbuild) |  | 2026 | 2 | 0% |  | Planned
1010000033 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Quality assurance/ quality control of Combined Covered Conductor |  | WMP.1508 | Program | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | Validate work is performed in accordance with project documents, standards, specifications, and codes, as applicable | 08.05 | Equipment ignition likelihood | Quantitative | Miles | No | WMP.1508-Quality assurance/ quality control of Combined Covered Conductor |  | 2026 | 2 | 50.7% |  | In Progress
1010000034 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Quality Assurance / Quality Control of Risk Informed Drone Inspections |  | WMP.1192 | Program | Ensure SDG&E inspection procedures are being adhered to | Ensure SDG&E inspection procedures are being adhered to | 08.05 | Equipment ignition likelihood | Quantitative | Drone Inspections | No | WMP.1192-Quality Assurance / Quality Control of Risk Informed Drone Inspections |  | 2026 | 2 | 0% |  | Planned
1010000035 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Quality Assurance / Quality Control of Substation Inspections |  | WMP.1194 | Program | Ensure SDG&E substation inspection procedures and checklists are being adhered to | Ensure SDG&E substation inspection procedures and checklists are being adhered to | 08.05 | Equipment ignition likelihood | Quantitative | Findings | No | WMP.1194-Quality Assurance / Quality Control of Substation Inspections |  | 2026 | 2 | 9 |  | In Progress
1010000036 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Quality Assurance / Quality Control of Wood Pole Intrusive (Transmission and Distribution) |  | WMP.1193 | Program | Ensure SDG&E inspection procedures are being adhered to | Ensure SDG&E inspection procedures are being adhered to | 08.05 | Equipment ignition likelihood | Quantitative | Intrusive Inspections | No | WMP.1193-Quality Assurance / Quality Control of Wood Pole Intrusive (Transmission and Distribution) |  | 2026 | 2 | 7.233% |  | In Progress
1010000037 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Quality Assurance / Quality Control of Transmission Switch Inspections |  | WMP.1510 | Program | Ensure inspections are following SDG&E’s procedures for inspections | Ensure inspections are following SDG&E’s procedures for inspections | 08.05 | Equipment ignition likelihood | Quantitative | Switch Function Inspections | No | WMP.1510-Quality Assurance / Quality Control of Transmission Switch Inspections |  | 2026 | 2 | 0% |  | Planned
1010000038 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) | Corrective Maintenance Program |  | WMP.1433 | Program | Repair wildfire-related conditions within established timeframes | Repair wildfire-related conditions within established timeframes | 08.06 | Equipment ignition likelihood | Qualitative |  | No | WMP.1433-Corrective Maintenance Program |  | 2026 | 2 |  | SDG&E continues to implement our Electric Distribution Corrective Maintenance Program to remediate any conditions identified and due in accordance with the risk and severity of the condition and GO 95 Rule 18. | In Progress
1010000039 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Personnel Work Procedures and Training in Conditions of Elevated Fire Risk |  | WMP.1452 | Program | Examine electric line crew training and incorporate updates annually | Examine electric line crew training and incorporate updates annually | 08.07.03 | Equipment ignition likelihood | Qualitative |  | No | WMP.1452-Personnel Training |  | 2026 | 2 |  | Electric line crew training review and updates will be completed in Q3 of 2026. | Planned
1010000040 | SDG&E | 2026-08-01 | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) | Workforce Planning (Asset Management) |  | WMP.1453 | Program | Consult with subject matter experts update the Storm and PSPS curriculum. | Consult with subject matter experts update the Storm and PSPS curriculum. | 08.08 | Equipment ignition likelihood | Qualitative |  | No | WMP.1453-Workforce Planning (Asset Management) |  | 2026 | 2 |  | A Storm Drill and PSPS Drill are schedule for the end of July, with a full end-to-end training environment being used for the first time. The training materials have been reviewed, updated, and are ready for deployment during both of those exercises. | In Progress
1010000041 | SDG&E | 2026-08-01 | Vegetation Management and Inspections | Vegetation Management Inspections | Detailed Inspections |  | WMP.1502 | Program | Vegetation management operations are driven by regulatory requirements and follow an annual, schedule that includes inspection, tree trimming, and auditing. During the annually scheduled routine inspection activity, all inventory trees are inspected to determine whether they require pruning to maintain mandated clearances from electrical lines. | Vegetation management operations are driven by regulatory requirements and follow an annual, schedule that includes inspection, tree trimming, and auditing. During the annually scheduled routine inspection activity, all inventory trees are inspected to determine whether they require pruning to maintain mandated clearances from electrical lines. | 09.02 | Wildfire hazard;Contact from vegetation ignition likelihood | Quantitative | Circuit Miles | No | WMP.1502-Detailed Inspections |  | 2026 | 2 | 4270.5 |  | In Progress
1010000042 | SDG&E | 2026-08-01 | Vegetation Management and Inspections | Vegetation Management Inspections | Detailed Inspections |  | WMP.0494 | Program | Vegetation management operations are driven by regulatory requirements and follow an annual, schedule that includes inspection, tree trimming, and auditing. During the annually scheduled routine inspection activity, all inventory trees are inspected to determine whether they require pruning to maintain mandated clearances from electrical lines. | Vegetation management operations are driven by regulatory requirements and follow an annual, schedule that includes inspection, tree trimming, and auditing. During the annually scheduled routine inspection activity, all inventory trees are inspected to determine whether they require pruning to maintain mandated clearances from electrical lines. | 09.02 | Wildfire hazard;Contact from vegetation ignition likelihood | Quantitative | Trees | No | WMP.0494-Detailed Inspections |  | 2026 | 2 | 288304 |  | In Progress
1010000043 | SDG&E | 2026-08-01 | Vegetation Management and Inspections | Vegetation Management Inspections | Off-Cycle Patrols |  | WMP.1503 | Program | Vegetation management operations are driven by regulatory requirements and follow an annual, schedule that includes inspection, tree trimming, and auditing. During the annually scheduled routine inspection activity, all inventory trees are inspected to determine whether they require pruning to maintain mandated clearances from electrical lines. | Vegetation management operations are driven by regulatory requirements and follow an annual, schedule that includes inspection, tree trimming, and auditing. During the annually scheduled routine inspection activity, all inventory trees are inspected to determine whether they require pruning to maintain mandated clearances from electrical lines. | 09.02 | Contact from vegetation ignition likelihood | Quantitative | Circuit Miles | No | WMP.1503-Off-Cycle Patrols |  | 2026 | 2 | 3349.08 |  | In Progress
1010000044 | SDG&E | 2026-08-01 | Vegetation Management and Inspections | Vegetation Management Inspections | Off-Cycle Patrols |  | WMP.0508 | Program | Vegetation management operations are driven by regulatory requirements and follow an annual, schedule that includes inspection, tree trimming, and auditing. During the annually scheduled routine inspection activity, all inventory trees are inspected to determine whether they require pruning to maintain mandated clearances from electrical lines. | Vegetation management operations are driven by regulatory requirements and follow an annual, schedule that includes inspection, tree trimming, and auditing. During the annually scheduled routine inspection activity, all inventory trees are inspected to determine whether they require pruning to maintain mandated clearances from electrical lines. | 09.02 | Contact from vegetation ignition likelihood | Quantitative | VMAs | No | WMP.0508-Off-Cycle Patrols |  | 2026 | 2 | 72 |  | In Progress
1010000045 | SDG&E | 2026-08-01 | Vegetation Management and Inspections | Pole Clearing | Pole Clearing |  | WMP.1504 | Program | Pole brushing is a fire prevention measure involving the removal of vegetation at the base of poles that carry specific types of electrical hardware that could cause sparking or molten material to fall to the ground. | Pole brushing is a fire prevention measure involving the removal of vegetation at the base of poles that carry specific types of electrical hardware that could cause sparking or molten material to fall to the ground. | 09.04 | Wildfire hazard;Contact from vegetation ignition likelihood | Quantitative | Circuit Miles | No | WMP.1504-Pole Clearing |  | 2026 | 2 | 1346.62 |  | In Progress
1010000046 | SDG&E | 2026-08-01 | Vegetation Management and Inspections | Pole Clearing | Pole Clearing |  | WMP.0512 | Program | Pole brushing is a fire prevention measure involving the removal of vegetation at the base of poles that carry specific types of electrical hardware that could cause sparking or molten material to fall to the ground. | Pole brushing is a fire prevention measure involving the removal of vegetation at the base of poles that carry specific types of electrical hardware that could cause sparking or molten material to fall to the ground. | 09.04 | Wildfire hazard;Contact from vegetation ignition likelihood | Quantitative | Poles Cleared | No | WMP.0512-Pole Clearing |  | 2026 | 2 | 19246 |  | In Progress
1010000047 | SDG&E | 2026-08-01 | Vegetation Management and Inspections | Wood and Slash Management | Sustainability |  | WMP.1460 | Project | As part of the company sustainability goal, SDG&E will explore additional options of diverting green waste from landfills to recycling facilities. | As part of the company sustainability goal, SDG&E will explore additional options of diverting green waste from landfills to recycling facilities. | 09.05 | Contact from vegetation ignition likelihood | Qualitative |  | No | WMP.1460-Sustainability |  | 2026 | 2 |  | Vegetation Management validated with all recycling and landfill vendors that 100% of all green waste material associated with tree trimming operations are converted to reusable material such as composting, mulch, landscaping, etc. SDG&E tracks and records the green waste material tonnage and percentages by each vendor, and tracks and records the tonnage of chipped material left on customer's property for reuse. In Q2, SDG&E also created a new Smartsheet form for the tree vendor to document and record all dump slips provided by landfill/recycling vendors. This information is provided by the tree contractor during invoicing to corroborate tonnage delivered to facilities. | In Progress
1010000048 | SDG&E | 2026-08-01 | Vegetation Management and Inspections | Integrated Vegetation Management | Fuels Management |  | WMP.0497 | Program | Wildland fuel reduction involves the thinning, pruning, and in some cases, removal of vegetation for the purpose of minimizing source material that could ignite and propagate a wildfire. | Wildland fuel reduction involves the thinning, pruning, and in some cases, removal of vegetation for the purpose of minimizing source material that could ignite and propagate a wildfire. | 09.07 | Contact from vegetation ignition likelihood | Quantitative | Poles Cleared | No | WMP.0497-Fuels Management |  | 2026 | 2 | 377 |  | In Progress
1010000049 | SDG&E | 2026-08-01 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | Quality Assurance / Quality Control of Vegetation Management |  | WMP.1493 | Program | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | 09.11 | Contact from vegetation ignition likelihood | Quantitative | Circuit Miles | No | WMP.1493-Quality Assurance / Quality Control of Vegetation Management |  | 2026 | 2 | 1692.05 |  | In Progress
1010000050 | SDG&E | 2026-08-01 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | Quality Assurance / Quality Control of Vegetation Management |  | WMP.1505 | Program | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | 09.11 | Contact from vegetation ignition likelihood | Quantitative | Inspections | No | WMP.1505-Quality assurance/quality control of Vegetation Management |  | 2026 | 2 | 36886 |  | In Progress
1010000051 | SDG&E | 2026-08-01 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | Quality assurance/quality control of Prune and Removal |  | WMP.1494 | Program | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | 09.11 | Contact from vegetation ignition likelihood | Quantitative | Circuit Miles | No | WMP.1494-Quality assurance/quality control of Prune and Removal |  | 2026 | 2 | 18.57% |  | In Progress
1010000052 | SDG&E | 2026-08-01 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | Quality assurance/quality control of Prune and Removal |  | WMP.1506 | Program | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | 09.11 | Contact from vegetation ignition likelihood | Quantitative | Trees trimmed/removed | No | WMP.1506-Quality assurance/quality control of Prune and Removal |  | 2026 | 2 | 18.57% |  | In Progress
1010000053 | SDG&E | 2026-08-01 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | Quality assurance/quality control of Pole Clearing |  | WMP.1495 | Program | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | 09.11 | Contact from vegetation ignition likelihood | Quantitative | Circuit Miles | No | WMP.1495-Quality assurance/quality control of Pole Clearing |  | 2026 | 2 | 249.78 |  | In Progress
1010000054 | SDG&E | 2026-08-01 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | Quality assurance/quality control of Pole Clearing |  | WMP.1507 | Program | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | SDG&E uses statistical sampling methodology in its audits of all Vegetation Management-related activities including pre-inspection, clearance (tree trimming), and pole clearing. Audit results are tracked, documented, and reported as a core component of contractor performance. | 09.11 | Contact from vegetation ignition likelihood | Quantitative | Poles Cleared | No | WMP.1507-Quality assurance/quality control of Pole Clearing |  | 2026 | 2 | 1778 |  | In Progress
1010000055 | SDG&E | 2026-08-01 | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) | Workforce Planning (Vegetation Management) |  | WMP.0506 | Program | Manage vegetation management workforce through qualification and certification requirements. | Manage vegetation management workforce through qualification and certification requirements. | 09.13 | Contact from vegetation ignition likelihood | Qualitative |  | No | WMP.0506-Workforce Planning (Vegetation Management) |  | 2026 | 2 |  | Annual training initiative is still in progress and on track to be completed by year end. Veg Mgmt contractors have completed most of the required four training modules (Wildfire Prevention, Hazard Tree Assessment, Customer Relations, Environmental). Internal VM staff are scheduled to complete all annual required ESCMP (Environmental, Safety, & Compliance) training. | In Progress
1010000056 | SDG&E | 2026-08-01 | Situational Awareness and Forecasting | Environmental Monitoring Systems | Air Quality Station Maintenance |  | WMP.1431 | Program | Air Quality Maintenance of the particulate sensors will include a scheduled monthly, quarterly, and annual inspection. Each visit will include a rigorous preventative maintenance to ensure accurate functioning of the sensors. | Air Quality Maintenance of the particulate sensors will include a scheduled monthly, quarterly, and annual inspection. Each visit will include a rigorous preventative maintenance to ensure accurate functioning of the sensors. | 10.02 | Wildfire exposure potential | Quantitative | Sensors | No | WMP.1431-Air Quality Station Maintenance |  | 2026 | 2 | 95 |  | In Progress
1010000057 | SDG&E | 2026-08-01 | Situational Awareness and Forecasting | Environmental Monitoring Systems | Weather Station Data |  | WMP.1461 | Program | Update 95th, 99th and max wind gust annually utilizing prior years weather station data. | Update 95th, 99th and max wind gust annually utilizing prior years weather station data. | 10.02 | Wildfire exposure potential | Qualitative |  | No | WMP.1461-Weather Station Data |  | 2026 | 2 |  | Adjustments completed on 7/09/2026. | Completed
1010000058 | SDG&E | 2026-08-01 | Situational Awareness and Forecasting | Grid Monitoring Systems | Grid Monitoring Systems Data Integration |  | WMP.1444 | Program | Integrate power quality, fault data and smoke detection to enhance situational awareness and support grid reliability. | Integrate power quality, fault data and smoke detection to enhance situational awareness and support grid reliability. | 10.03 | Equipment ignition likelihood | Qualitative |  | No | WMP.1444-Grid Monitoring Systems Data Integration |  | 2026 | 2 |  | During Q2 2026, additional next-generation RIVA meters were installed at customer main panels across circits 222 and 445. Furthermore, problems involving data from "Fischer Block" devices were resolved, providing another source of waveform data captures for inclusion on the Cascadence UI. | In Progress
1010000059 | SDG&E | 2026-08-01 | Situational Awareness and Forecasting | Grid Monitoring Systems | Early Fault Detection |  | WMP.1195 | Project | Early fault detection employs technologies such as Advance Radio Frequency Sensors (ARFS) and Power Quality (PQ) Meters to detect and prevent significant equipment failures before they occur. | Early fault detection employs technologies such as Advance Radio Frequency Sensors (ARFS) and Power Quality (PQ) Meters to detect and prevent significant equipment failures before they occur. | 10.03 | Equipment ignition likelihood | Quantitative | Nodes | No | WMP.1195-Early Fault Detection |  | 2026 | 2 | 21 |  | In Progress
1010000060 | SDG&E | 2026-08-01 | Situational Awareness and Forecasting | Ignition Detection Systems | Ignition Detection Systems - Cameras |  | WMP.1343 | Program | Ongoing review to identify camera communication network single points of failure to avoid interruption of camera imagery | Ongoing review to identify camera communication network single points of failure to avoid interruption of camera imagery | 10.04 | Wildfire vulnerability Wildfire exposure potential | Qualitative |  | No | WMP.1343-Ignition Detection Systems - Cameras |  | 2026 | 2 |  | Regular monitoring continues. Bi-weekly meetings are ongoing with UCSD to discuss required maintenance and future upgrades. | In Progress
1010000061 | SDG&E | 2026-08-01 | Situational Awareness and Forecasting | Ignition Detection Systems | Quarterly validation of weekly uptime for Ignition Detection Cameras |  | WMP.1467 | Program | Quarterly validation of weekly uptime for Ignition Detection Cameras | Quarterly validation of weekly uptime for Ignition Detection Cameras | 10.04 | Wildfire vulnerability Wildfire exposure potential | Quantitative | Quarterly Validations | No | WMP.1467-Quarterly validation of weekly uptime for Ignition Detection Cameras |  | 2026 | 2 | 2 |  | In Progress
1010000062 | SDG&E | 2026-08-01 | Situational Awareness and Forecasting | Weather Forecasting | Post-processing success rate - WRF simulations |  | WMP.1465 | Program | Post-processing success rate - WRF simulations | Post-processing success rate - WRF simulations | 10.05 | Wildfire vulnerability Wildfire exposure potential | Quantitative | Success rate | No | WMP.1465- Post-processing success rate - WRF simulations |  | 2026 | 2 | 99.65% |  | In Progress
1010000063 | SDG&E | 2026-08-01 | Situational Awareness and Forecasting | Weather Forecasting | Weather Station Maintenance and Calibration |  | WMP.1466 | Program | Monitoring of communication success rate of weather stations | Monitoring of communication success rate of weather stations | 10.05.05 | Wildfire vulnerability Wildfire exposure potential | Qualitative |  | No | WMP.1466-Communication success rate of weather stations |  | 2026 | 2 |  | 97.7% for Q2 by examining weekly communciation metrics from April through June. | In Progress
1010000064 | SDG&E | 2026-08-01 | Situational Awareness and Forecasting | Weather Forecasting | Weather Station Maintenance and Calibration |  | WMP.1430 | Program | Weather Station Maintenance and Calibration is dedicated to the maintenance and calibration of weather stations. The Weather Station Network strategically positions weather stations to transmit data on sustained wind speed, wind gust, wind direction, temperature, and humidity every 10 minutes using cellular and spread spectrum communications. | Weather Station Maintenance and Calibration is dedicated to the maintenance and calibration of weather stations. The Weather Station Network strategically positions weather stations to transmit data on sustained wind speed, wind gust, wind direction, temperature, and humidity every 10 minutes using cellular and spread spectrum communications. | 10.05.05 | Wildfire vulnerability Wildfire exposure potential | Quantitative | Weather Stations | No | WMP.1430-Weather Station Maintenance and Calibration |  | 2026 | 2 | 217 |  | In Progress
1010000065 | SDG&E | 2026-08-01 | Situational Awareness and Forecasting | Fire Potential Index | Fire potential index |  | WMP.0450 | Program | Ongoing analysis of FPI predictions versus observations to potentially improve FPI | Ongoing analysis of FPI predictions versus observations to potentially improve FPI | 10.06 | Wildfire vulnerability Wildfire exposure potential | Qualitative |  | No | WMP.0450-Fire potential index |  | 2026 | 2 |  | Forecasted values of the FPI continue to be validated against daily observations. Annual analysis will be completed on time by 12/31. | In Progress
1010000066 | SDG&E | 2026-08-01 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan | Emergency Preparedness and Recovery Plan |  | WMP.1008 | Program | Augment the CEADPP by incorporating detailed plans, concepts of operations (conops), and annexes tailored to specific identified risks. | Augment the CEADPP by incorporating detailed plans, concepts of operations (conops), and annexes tailored to specific identified risks. | 11.02 | PSPS exposure potential PSPS vulnerability Wildfire vulnerability Wildfire exposure potential | Qualitative |  | No | WMP.1008-Emergency Preparedness and Recovery Plan |  | 2026 | 2 |  | CDEAPP has been approved and finialized for 2026- April 2026 | Completed
1010000067 | SDG&E | 2026-08-01 | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination | External Collaboration and Coordination |  | WMP.1454 | Program | Enhance current collaborations and establish new ones with CBOs, public safety agencies, and government entities that deliver emergency preparedness education, response, and support services | Enhance current collaborations and establish new ones with CBOs, public safety agencies, and government entities that deliver emergency preparedness education, response, and support services | 11.03 | PSPS exposure potential PSPS vulnerability Wildfire vulnerability Wildfire exposure potential | Qualitative |  | No | WMP.1454-External Collaboration and Coordination |  | 2026 | 2 |  | The CBO network has been expanded to 58 CBOs, achieving the 2026 target as of July 2026. | Completed
1010000068 | SDG&E | 2026-08-01 | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness | Public Outreach and Education Awareness |  | WMP.0527 | Program | Public Communication, Outreach, and Education - Focus on creating more meaningful and interactive engagements including proactive preparedness through community collaboration, Tribal feedback sessions, and a combination of Outreach and AFN engagement. Organize a series of Wildfire Safety Fairs and mini-Wildfire Safety Fairs aimed at educating, engaging, and preparing customers in rural communities for wildfires. Implement Wildfire/PSPS Public Education campaign leading up to when RFW are the highest. Solicit customer feedback on communications and messaging and use results to improve communications and notifications for the following year. | Public Communication, Outreach, and Education - Focus on creating more meaningful and interactive engagements including proactive preparedness through community collaboration, Tribal feedback sessions, and a combination of Outreach and AFN engagement. Organize a series of Wildfire Safety Fairs and mini-Wildfire Safety Fairs aimed at educating, engaging, and preparing customers in rural communities for wildfires. Implement Wildfire/PSPS Public Education campaign leading up to when RFW are the highest. Solicit customer feedback on communications and messaging and use results to improve communications and notifications for the following year. | 11.04 | PSPS exposure potential PSPS vulnerability Wildfire vulnerability Wildfire exposure potential | Qualitative |  | No | WMP.0527-Public Outreach and Education Awareness |  | 2026 | 2 |  | During Q2 2026, there were no PSPS de‑energization events; therefore, PSPS‑specific post‑event activities and post‑PSPS Tribal Nation learning sessions were not applicable during this period. Following any future PSPS events, these efforts will be implemented to gather customer and Tribal Nation feedback related to communications and resiliency, with insights incorporated as appropriate. Public Wildfire Safety and emergency preparedness education occurs year‑round along with coordination with Community‑Based Organizations (CBOs) and engagement with the AFN Collaborative Council to help amplify preparedness messaging. During Q2 2026, the Outreach team participated in over 150 community events and presentations which included 46 mini-Wildfire Safety Fairs. At these outreach events, topics discussed include PSPS, Wildfire Safety, customer assistance programs, resources, and emergency preparedness. SDG&E hosted two Wildfire Safety Fairs in Q2 in the following locations: May 2, 2026 421 Aqua Ln Ramona, CA 92065 and June 27, 2026 Joan MacQueen Middle School 2001 Tavern Rd Alpine, CA 91901. Planning and coordination for two additional Wildfire Safety Fairs will take place on July 18, 2026 Antique Gas and Steam Engine Museum 2040 N Santa Fe Ave Vista, CA 92083 and August 29, 2026 Bate’s Nut Farm 15954 Woods Valley Rd Valley Center, CA 92082. Campaign activities remain on track for completion by December 31, 2026. Customer feedback will be collected and used to inform program enhancements for 2027. | In Progress
1010000069 | SDG&E | 2026-08-01 | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies | Customer Support in Wildfire and PSPS Emergencies |  | WMP.1455 | Program | Enhance support and resources provided to impacted customers at Community Resource Centers. | Enhance support and resources provided to impacted customers at Community Resource Centers. | 11.05 | PSPS exposure potential PSPS vulnerability | Qualitative |  | No | WMP.1455-Customer Support in Wildfire and PSPS Emergencies |  | 2026 | 2 |  | During the second quarter of 2026, SDG&E did not implement any PSPS de-energizations. As a result, Community Resource Centers were not activated during this period, and there are no updates to report. | Planned
1010000070 | SDG&E | 2026-08-01 | Enterprise Systems | Enterprise Systems Development | Asset Management and Inspection Enterprise System |  | WMP.1457 | Program | Utilize advanced technology and analytics - including integrating Asset 360 and IIP data - to develop, enhance, expand risk-informed strategies, and enhance transparency for asset management | Utilize advanced technology and analytics - including integrating Asset 360 and IIP data - to develop, enhance, expand risk-informed strategies, and enhance transparency for asset management | 12.01.01 | Equipment ignition likelihood | Qualitative |  | No | WMP.1457-Asset Management and Inspection Enterprise System |  | 2026 | 2 |  | SDG&E utilized the Q1 2026 data analysis to develop the scope for risk-informed drone inspection (RIDI) in 2026, including removal of any poles recently or soon to be repaired, replaced, inspected (detailed), or otherwise modified in order to reduce redundancy or duplication across programs. | In Progress
1010000071 | SDG&E | 2026-08-01 | Enterprise Systems | Enterprise Systems Development | Enterprise Data Foundation |  | WMP.0519 | Program | Migrate data from on-premise to the AWS Cloud | Migrate data from on-premise to the AWS Cloud | 12.01.01 | Wildfire hazard | Qualitative |  | No | WMP.0519-Enterprise Data Foundation |  | 2026 | 2 |  | Ready to use the full data Products in AWS: • Weather Patterns • Asset Inspections • Asset Point • Asset Line • Partial PSPS Ready to use the intermediate data Products in AWS: • Grid Hardening WCS will be able to start using the data products in AWS for the upcoming QDR. They will start by using it in parallel with the current process to validate. We are still on track to be off of Hana by end of the year. | In Progress
1010000072 | SDG&E | 2026-08-01 | Enterprise Systems | Enterprise Systems Development | Vegetation Management Enterprise System |  | WMP.0511 | Program | Enhance asset tracking, data analytics, and scheduling capabilities to more effectively manage and support Vegetation Management activities. | Enhance asset tracking, data analytics, and scheduling capabilities to more effectively manage and support Vegetation Management activities. | 12.01.01 | Contact from vegetation ignition likelihood | Qualitative |  | No | WMP.0511-Vegetation Management Enterprise System |  | 2026 | 2 |  | Q2, 2026: New work order enhancement in Epoch put into production allowing visualization of the progress of the pre-inspection activity. This application enables electronic map documentation of pre-inspection, and avoiding the creation of hard-copy maps for field personnel. Additionally, new Epoch enhancement designs begun including the creation of new condition codes for tree removal/stump grind, and new process to electronically track and record "cycle breaker" palms. | In Progress
1010000073 | SDG&E | 2026-08-01 | Enterprise Systems | Enterprise Systems Development | Vegetation Management Enterprise System - Advanced Analytics |  | WMP.1464 | Program | Advanced Analytics-Advanced analytics for proactive vegetation inspection | Advanced Analytics-Advanced analytics for proactive vegetation inspection | 12.01.01 | Contact from vegetation ignition likelihood | Qualitative |  | No | WMP.1464-Vegetation Management Enterprise System - Advanced Analytics |  | 2026 | 2 |  | Q2 ongoing developments included the following work on models: Probability of Failure (PoF) PoF provides daily/hourly, weather-responsive predictions of vegetation-related equipment failures at span-level granularity. It flags spans most vulnerable to outage-causing interactions by integrating environmental drivers, including wind-gust forecasts and local station data, vegetation structure (species, height, tree counts), trim history, outage history, and conductor-vegetation interaction factors. PoF strengthens reliability and Public Safety Power Shutoff (PSPS) readiness by aligning predictions with observed outage behavior. Vegetation Priority Score (VPS): VPS is a composite span-level score developed by Logic 20/20 to rank where to inspect. It combines the likelihood models (PoH, PoVC, PoF, and PoI) with a consequence estimate based on the WiNGS methodology (safety, reliability, and financial attributes) into a single risk index per span. VPS separates high-likelihood, high-consequence spans from the broader population and supports condition-based inspection and mitigation scheduling, refreshed on a recurring cadence to reflect current field conditions. Future Development: Integrate the likelihood models (Including PoH) into the Vegetation Priority Score (VPS) to support condition-based inspection prioritization. Ongoing data migration from PowerWorkz/Oracle to AWS expected to be completed Q3, 2026. | In Progress

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1020000000 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000001 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000002 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000003 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 37
1020000004 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000005 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000006 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000007 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 21
1020000008 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000009 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000010 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000011 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 121
1020000012 | Risk Events | Number of wires down | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000013 | Risk Events | Number of wires down | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000014 | Risk Events | Number of wires down | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000015 | Risk Events | Number of wires down | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 5
1020000016 | Risk Events | Number of wires down | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000017 | Risk Events | Number of wires down | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000018 | Risk Events | Number of wires down | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000019 | Risk Events | Number of wires down | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 2
1020000020 | Risk Events | Number of wires down | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000021 | Risk Events | Number of wires down | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000022 | Risk Events | Number of wires down | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000023 | Risk Events | Number of wires down | Neither | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 11
1020000024 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000025 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000026 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000027 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 37
1020000028 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000029 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000030 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000031 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 21
1020000032 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000033 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000034 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000035 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 114
1020000036 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000037 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000038 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000039 | Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000040 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000041 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000042 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000043 | Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000044 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000045 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000046 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000047 | Risk Events | Number of outage events caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 7
1020000048 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000049 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000050 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000051 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000052 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000053 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000054 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000055 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000056 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000057 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000058 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000059 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | Non-HFTD |  |  |  | Number of events |  |  | SDG&E | 2026 | 2 | 0
1020000060 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | SDG&E | 2026 | 2 | 120
1020000061 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | SDG&E | 2026 | 2 | 167
1020000062 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | SDG&E | 2026 | 2 | 130
1020000063 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | SDG&E | 2026 | 2 | 171
1020000064 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Distribution |  |  | days |  |  | SDG&E | 2026 | 2 | 138
1020000065 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | days |  |  | SDG&E | 2026 | 2 | 182
1020000066 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Transmission |  |  | days |  |  | SDG&E | 2026 | 2 | 139
1020000067 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | days |  |  | SDG&E | 2026 | 2 | 165
1020000068 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Transmission |  |  | days |  |  | SDG&E | 2026 | 2 | 119
1020000069 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | days |  |  | SDG&E | 2026 | 2 | 197
1020000070 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Transmission |  |  | days |  |  | SDG&E | 2026 | 2 | 119
1020000071 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | days |  |  | SDG&E | 2026 | 2 | 170
1020000072 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 4.5
1020000073 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 13.75
1020000074 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 0
1020000075 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 1.8
1020000076 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 1
1020000077 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 21
1020000078 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 0
1020000079 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 0
1020000080 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 0
1020000081 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 0
1020000082 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 0
1020000083 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 0
1020000084 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 221.5
1020000085 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 531.9
1020000086 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 200
1020000087 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 277
1020000088 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 357
1020000089 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 748
1020000090 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 207
1020000091 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 909.7
1020000092 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 242
1020000093 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 286.5
1020000094 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 115
1020000095 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 369
1020000096 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 57.5
1020000097 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 109.4
1020000098 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 19
1020000099 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 80.95
1020000100 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 6
1020000101 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 139.6
1020000102 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 0
1020000103 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 0
1020000104 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 0
1020000105 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 0
1020000106 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 0
1020000107 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours | SDG&E uses days as unit |  | SDG&E | 2026 | 2 | 0
1020000108 | Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders |  |  | SDG&E | 2026 | 2 | 25515
1020000109 | Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders |  |  | SDG&E | 2026 | 2 | 2988
1020000110 | Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  |  | SDG&E | 2026 | 2 | 2539
1020000111 | Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  |  | SDG&E | 2026 | 2 | 64
1020000112 | Response Time | Response time to locked open circuit breaker | [5 empty] | Hours |  |  | SDG&E | 2026 | 2 | 1.15
1020000113 | Fatalities and injuries due to utility-related ignitions | Fatalities due to utility-related ignitions (total) | [5 empty] | Number of fatalities |  |  | SDG&E | 2026 | 2 | 0
1020000114 | Fatalities and injuries due to utility-related ignitions | Injuries due to utility-related ignitions (total) | [5 empty] | Number of injuries |  |  | SDG&E | 2026 | 2 | 0
1020000115 | Value of assets destroyed by utility-related ignitions, listed by asset type | Value of assets destroyed by utility-related ignitions (total) | [5 empty] | Dollars |  |  | SDG&E | 2026 | 2 | 0
1020000116 | Structures damaged or destroyed by utility-related ignitions | Number of structures destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | SDG&E | 2026 | 2 | 0
1020000117 | Structures damaged or destroyed by utility-related ignitions | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | [5 empty] | Number of structures |  |  | SDG&E | 2026 | 2 | 0
1020000118 | Acreage burned by utility-ignited wildfires | Acreage burned by utility-ignited wildfires | [5 empty] | Acres |  |  | SDG&E | 2026 | 2 | 4.7403
1020000119 | Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SDG&E | 2026 | 2 | 0
1020000120 | Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SDG&E | 2026 | 2 | 0
1020000121 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SDG&E | 2026 | 2 | 0
1020000122 | Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 2 |  |  |  | Number of ignitions |  |  | SDG&E | 2026 | 2 | 3
1020000123 | Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SDG&E | 2026 | 2 | 0
1020000124 | Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SDG&E | 2026 | 2 | 0
1020000125 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SDG&E | 2026 | 2 | 0
1020000126 | Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 3 |  |  |  | Number of ignitions |  |  | SDG&E | 2026 | 2 | 2
1020000127 | Number of utility-related ignitions | Number of ignitions | RFW only | Non-HFTD |  |  |  | Number of ignitions |  |  | SDG&E | 2026 | 2 | 0
1020000128 | Number of utility-related ignitions | Number of ignitions | HWW only | Non-HFTD |  |  |  | Number of ignitions |  |  | SDG&E | 2026 | 2 | 0
1020000129 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | Non-HFTD |  |  |  | Number of ignitions |  |  | SDG&E | 2026 | 2 | 0
1020000130 | Number of utility-related ignitions | Number of ignitions | Neither | Non-HFTD |  |  |  | Number of ignitions |  |  | SDG&E | 2026 | 2 | 2
1020000131 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000132 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000133 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000134 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 16231
1020000135 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000136 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000137 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000138 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 5469
1020000139 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000140 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000141 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000142 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 509
1020000143 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000144 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000145 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000146 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 600.1259
1020000147 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000148 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000149 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000150 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 195.1987
1020000151 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000152 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000153 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000154 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000155 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000156 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000157 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000158 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 2
1020000159 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000160 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000161 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000162 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 8
1020000163 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000164 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000165 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000166 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000167 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000168 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000169 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000170 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 25
1020000171 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000172 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000173 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000174 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 213
1020000175 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000176 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000177 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000178 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 3
1020000179 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000180 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000181 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000182 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 10
1020000183 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000184 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000185 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000186 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 1284
1020000187 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000188 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000189 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000190 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000191 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000192 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000193 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000194 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 16935
1020000195 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000196 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000197 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000198 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 3970
1020000199 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000200 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000201 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000202 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 150
1020000203 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000204 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000205 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000206 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 699.9316
1020000207 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000208 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000209 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000210 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 165.5557
1020000211 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000212 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000213 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000214 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000215 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000216 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000217 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000218 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 2
1020000219 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000220 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000221 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000222 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 2
1020000223 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000224 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000225 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000226 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000227 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000228 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000229 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000230 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 10
1020000231 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000232 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000233 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000234 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 116
1020000235 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000236 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000237 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000238 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 1
1020000239 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000240 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000241 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000242 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 5
1020000243 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000244 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000245 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000246 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 908
1020000247 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000248 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000249 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000250 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000251 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000252 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000253 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000254 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 36076
1020000255 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000256 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000257 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000258 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 7399
1020000259 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000260 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000261 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000262 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 3632
1020000263 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000264 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000265 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000266 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 806.193
1020000267 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000268 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000269 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000270 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 134.5657
1020000271 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000272 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000273 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000274 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000275 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000276 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000277 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000278 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 6
1020000279 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000280 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000281 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000282 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 29
1020000283 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000284 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000285 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000286 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000287 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000288 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000289 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000290 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 63
1020000291 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000292 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000293 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000294 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 678
1020000295 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000296 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000297 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000298 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 32
1020000299 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000300 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000301 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000302 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 25
1020000303 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000304 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000305 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000306 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 2878
1020000307 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000308 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000309 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000310 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000311 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000312 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000313 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000314 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000315 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000316 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000317 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000318 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 307
1020000319 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000320 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000321 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000322 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 1
1020000323 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000324 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000325 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000326 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000327 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000328 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000329 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000330 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 58.0406
1020000331 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000332 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000333 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000334 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000335 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000336 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000337 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000338 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000339 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000340 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000341 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000342 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000343 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000344 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000345 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000346 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000347 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000348 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000349 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000350 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000351 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000352 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000353 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000354 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 29
1020000355 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000356 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000357 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000358 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000359 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000360 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000361 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000362 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000363 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000364 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000365 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000366 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000367 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000368 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000369 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000370 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000371 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000372 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000373 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000374 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000375 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000376 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000377 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000378 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 509
1020000379 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000380 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000381 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000382 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 1
1020000383 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000384 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000385 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000386 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000387 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000388 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000389 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000390 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 34.0635
1020000391 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000392 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000393 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000394 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000395 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000396 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000397 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000398 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000399 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000400 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000401 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000402 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000403 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000404 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000405 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000406 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000407 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000408 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000409 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000410 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000411 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000412 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000413 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000414 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 16
1020000415 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000416 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000417 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000418 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000419 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000420 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000421 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000422 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000423 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000424 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000425 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000426 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000427 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000428 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000429 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000430 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000431 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000432 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000433 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000434 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000435 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000436 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000437 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000438 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 1004
1020000439 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000440 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000441 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000442 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | SDG&E | 2026 | 2 | 9
1020000443 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000444 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000445 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000446 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000447 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000448 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000449 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000450 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 134.448
1020000451 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000452 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  |  | SDG&E | 2026 | 2 | 0
1020000453 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000454 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | Not Applicable | SDG&E | 2026 | 2
1020000455 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000456 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000457 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000458 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000459 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000460 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000461 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000462 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000463 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000464 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000465 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000466 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000467 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000468 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000469 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000470 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000471 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000472 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000473 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000474 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 244
1020000475 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000476 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000477 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000478 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000479 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000480 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000481 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000482 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000483 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000484 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000485 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000486 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000487 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000488 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000489 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | Not Applicable | SDG&E | 2026 | 2
1020000490 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | SDG&E | 2026 | 2 | 0
1020000491 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000492 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000493 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000494 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 2
1020000495 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000496 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000497 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000498 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 4
1020000499 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000500 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000501 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000502 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000503 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000504 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000505 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000506 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 36
1020000507 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000508 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000509 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000510 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 31
1020000511 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 89
1020000512 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000513 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000514 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000515 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000516 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000517 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000518 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 1
1020000519 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000520 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000521 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000522 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 83
1020000523 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000524 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000525 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000526 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000527 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000528 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000529 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000530 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 1
1020000531 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000532 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000533 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000534 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 2
1020000535 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000536 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000537 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000538 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000539 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000540 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000541 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000542 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 12
1020000543 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000544 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000545 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000546 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 14
1020000547 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 279
1020000548 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000549 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000550 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000551 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000552 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000553 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000554 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 2
1020000555 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000556 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000557 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000558 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 26
1020000559 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000560 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000561 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000562 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000563 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000564 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000565 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000566 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 6
1020000567 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000568 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000569 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000570 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 22
1020000571 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000572 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000573 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000574 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000575 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000576 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000577 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000578 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 61
1020000579 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000580 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000581 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000582 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 178
1020000583 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000584 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000585 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000586 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 18
1020000587 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000588 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000589 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000590 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 1
1020000591 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000592 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000593 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000594 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 68
1020000595 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000596 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000597 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000598 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000599 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000600 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000601 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000602 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000603 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000604 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000605 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000606 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000607 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000608 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000609 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000610 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000611 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000612 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000613 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000614 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000615 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000616 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000617 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000618 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 23
1020000619 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000620 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000621 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000622 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000623 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000624 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000625 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000626 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000627 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000628 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000629 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000630 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000631 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000632 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000633 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000634 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000635 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000636 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000637 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000638 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000639 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000640 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000641 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000642 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000643 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000644 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000645 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000646 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000647 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000648 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000649 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000650 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000651 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000652 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000653 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000654 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 7
1020000655 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000656 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000657 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000658 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000659 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000660 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000661 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000662 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000663 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000664 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000665 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000666 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000667 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000668 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000669 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000670 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000671 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000672 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000673 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000674 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000675 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000676 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000677 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000678 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000679 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000680 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000681 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000682 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000683 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000684 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000685 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000686 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000687 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000688 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000689 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000690 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 111
1020000691 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000692 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000693 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000694 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000695 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000696 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000697 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000698 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000699 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000700 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000701 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000702 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000703 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000704 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000705 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | Not Applicable | SDG&E | 2026 | 2
1020000706 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | SDG&E | 2026 | 2 | 0
1020000707 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000708 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000709 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000710 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 46617
1020000711 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000712 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000713 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000714 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2026 | 2 | 47183
1020000715 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2026 | 2 | 0
1020000716 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000717 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000718 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000719 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000720 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000721 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000722 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 395
1020000723 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2 | 0
1020000724 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 0
1020000725 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 0
1020000726 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 20081
1020000727 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000728 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000729 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000730 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2026 | 2 | 23734
1020000731 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2026 | 2 | 0
1020000732 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000733 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000734 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000735 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000736 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000737 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000738 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 127
1020000739 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2 | 0
1020000740 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 0
1020000741 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 0
1020000742 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 54161
1020000743 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000744 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000745 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000746 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2026 | 2 | 51687
1020000747 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2026 | 2 | 0
1020000748 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000749 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000750 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000751 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000752 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000753 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000754 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 480
1020000755 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2 | 0
1020000756 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 117
1020000757 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 0
1020000758 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 1755
1020000759 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000760 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000761 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000762 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2026 | 2 | 2865
1020000763 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000764 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000765 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000766 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000767 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000768 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000769 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000770 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 0
1020000771 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2 | 0
1020000772 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 2
1020000773 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 0
1020000774 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 625
1020000775 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000776 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000777 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000778 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2026 | 2 | 509
1020000779 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000780 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000781 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000782 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000783 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000784 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000785 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000786 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 0
1020000787 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2 | 0
1020000788 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 47
1020000789 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 0
1020000790 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 3616
1020000791 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000792 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000793 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000794 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | SDG&E | 2026 | 2 | 2345
1020000795 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000796 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000797 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000798 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000799 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000800 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000801 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | Not Applicable | SDG&E | 2026 | 2
1020000802 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | SDG&E | 2026 | 2 | 2
1020000803 | Community outreach metrics | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | [5 empty] | Percentage of customers notified of evacuation |  | Not Applicable | SDG&E | 2026 | 2

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1030000000 | Vegetation caused ignitions in the HFTD during FPI ratings of Elevated or higher | Vegetation caused ignitons in HFTD with elevated or higher FPI | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2026 | 2 | 0
1030000001 | Vegetation caused ignitions in the HFTD during an RFW | Vegetation caused ignitons in HFTD with RFW | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2026 | 2 | 0
1030000002 | Equipment caused ignitions in the HFTD during FPI ratings of Elevated or higher | Equipment caused ignitions in HFTD with elevated or higher FPI | To evaluate the performance of risk reduction from asset inspection and grid hardening during fire-prone conditions | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2026 | 2 | 0
1030000003 | Equipment caused ignitions in the HFTD during an RFW | Equipment caused ignitions in HFTD with RFW | To evaluate the performance of risk reduction from asset inspection and grid hardening during fire-prone conditions | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions |  |  | SDG&E | 2026 | 2 | 0
1030000004 | Equipment caused ignition rate in the HFTD during a High FPI rating | Equipment caused ignition rate in HFTD during high FPI | To evaluate the performance of risk reduction from asset inspection and grid hardening during fire-prone conditions | To evaluate the performance of risk reduction during fire prone weather conditions | No | Ignitions per high FPI day |  |  | SDG&E | 2026 | 2 | 0
1030000005 | Vegetation caused outages in the HFTD during an Elevated FPI | Vegetation caused outages in HFTD with Elevated FPI | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions | No | Outages |  |  | SDG&E | 2026 | 2 | 0
1030000006 | Vegetation caused outages in the HFTD during an RFW | Vegetation caused outages in HFTD with RFW | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions | To evaluate the performance of risk reduction from vegetation mitigations during fire prone weather conditions | No | Outages |  |  | SDG&E | 2026 | 2 | 0
1030000007 | Overhead faults on circuits in the HFTD during an Elevated FPI | Overhead faults on circuits in HFTD with Elevated or higher FPI | To evaluate the performance of risk reduction from overall mitigations during fire-prone conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Outages |  |  | SDG&E | 2026 | 2 | 13
1030000008 | Overhead faults on circuits in the HFTD during an RFW | Overhead faults on circuits in HFTD with RFW | To evaluate the performance of risk reduction from overall mitigations during fire-prone conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Outages |  |  | SDG&E | 2026 | 2 | 0
1030000009 | Energized wire down events in the HFTD during an FPI of Elevated or higher | Energized wire down events in HFTD with Elevated or higher FPI | To evaluate the performance of risk reduction from grid hardening related mitigations during fire-prone conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Outages |  |  | SDG&E | 2026 | 2 | 2
1030000010 | Energized wire down events in the HFTD during an RFW | Energized wire down events in HFTD with RFW | To evaluate the performance of risk reduction from grid hardening related mitigations during fire-prone conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Outages |  |  | SDG&E | 2026 | 2 | 0
1030000011 | Overhead fault rate in the HFTD during a High FPI | Overhead fault rate in HFTD during High FPI | To evaluate the performance of risk reduction from overall mitigations during fire-prone conditions | To evaluate the performance of risk reduction from mitigations that have impacts on the drivers during fire prone weather conditions | No | Overhead faults per high FPI day |  |  | SDG&E | 2026 | 2 | 0.27

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1040000000 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000001 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000002 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | Non-HFTD | Red flag warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000003 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000004 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000005 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | Non-HFTD | Red flag warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000006 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000007 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000008 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000009 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000010 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000011 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000012 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000013 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000014 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000015 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000016 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000017 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 0
1040000018 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 59564.53
1040000019 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 68182.67
1040000020 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 42181.1
1040000021 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 15073
1040000022 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 11979.45
1040000023 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | SDG&E | 2026 | 2 | 6484.82

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1050000000 | Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2
1050000001 | Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2
1050000002 | Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2
1050000003 | Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2
1050000004 | Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2
1050000005 | Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2
1050000006 | Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000007 | Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000008 | Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000009 | Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000010 | Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000011 | Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000012 | Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000013 | Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000014 | Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000015 | Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000016 | Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000017 | Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000018 | Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 3
1050000019 | Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 4
1050000020 | Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000021 | Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000022 | Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000023 | Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000024 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000025 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000026 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000027 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000028 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000029 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000030 | Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000031 | Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000032 | Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000033 | Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000034 | Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000035 | Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000036 | Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000037 | Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000038 | Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000039 | Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000040 | Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000041 | Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000042 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000043 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000044 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000045 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000046 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000047 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events | SDG&E doesn't currently track this driver as contact from object. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000048 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000049 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000050 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000051 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000052 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000053 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000054 | Vegetation contact | Wire down event | Grow-in | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000055 | Vegetation contact | Wire down event | Grow-in | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000056 | Vegetation contact | Wire down event | Grow-in | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000057 | Vegetation contact | Wire down event | Grow-in | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000058 | Vegetation contact | Wire down event | Grow-in | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000059 | Vegetation contact | Wire down event | Grow-in | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000060 | Vegetation contact | Wire down event | Blow-in | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000061 | Vegetation contact | Wire down event | Blow-in | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000062 | Vegetation contact | Wire down event | Blow-in | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000063 | Vegetation contact | Wire down event | Blow-in | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000064 | Vegetation contact | Wire down event | Blow-in | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000065 | Vegetation contact | Wire down event | Blow-in | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000066 | Vegetation contact | Wire down event | Trunk failure | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 4
1050000067 | Vegetation contact | Wire down event | Trunk failure | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000068 | Vegetation contact | Wire down event | Trunk failure | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000069 | Vegetation contact | Wire down event | Trunk failure | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000070 | Vegetation contact | Wire down event | Trunk failure | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000071 | Vegetation contact | Wire down event | Trunk failure | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000072 | Vegetation contact | Wire down event | Root failure | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000073 | Vegetation contact | Wire down event | Root failure | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000074 | Vegetation contact | Wire down event | Root failure | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000075 | Vegetation contact | Wire down event | Root failure | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000076 | Vegetation contact | Wire down event | Root failure | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000077 | Vegetation contact | Wire down event | Root failure | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000078 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000079 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000080 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000081 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000082 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000083 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000084 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000085 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000086 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000087 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000088 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000089 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000090 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000091 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000092 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000093 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000094 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000095 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000096 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 2
1050000097 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000098 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000099 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000100 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000101 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000102 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 2
1050000103 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000104 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000105 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000106 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000107 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000108 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000109 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000110 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000111 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000112 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000113 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000114 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000115 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000116 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000117 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000118 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000119 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000120 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000121 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000122 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000123 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000124 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000125 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000126 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000127 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000128 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000129 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000130 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000131 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000132 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000133 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000134 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000135 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000136 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000137 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000138 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000139 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000140 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000141 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000142 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000143 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000144 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000145 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000146 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000147 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000148 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000149 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000150 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2
1050000151 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2
1050000152 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2
1050000153 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000154 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000155 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000156 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000157 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000158 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000159 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000160 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000161 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000162 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000163 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000164 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000165 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000166 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000167 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000168 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000169 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000170 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000171 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000172 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000173 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000174 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2
1050000175 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2
1050000176 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2
1050000177 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000178 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000179 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000180 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2
1050000181 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2
1050000182 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events | SDG&E does not track this driver for distribution wire-down events | not applicable | SDG&E | 2026 | 2
1050000183 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000184 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000185 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000186 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000187 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000188 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000189 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000190 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000191 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000192 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000193 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000194 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000195 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000196 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000197 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000198 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000199 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000200 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000201 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000202 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000203 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track unkown wire-down events in the equipment failure category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000204 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 2
1050000205 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000206 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000207 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000208 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000209 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000210 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000211 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000212 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000213 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000214 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000215 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000216 | Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000217 | Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000218 | Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000219 | Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000220 | Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000221 | Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000222 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000223 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000224 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000225 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000226 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000227 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000228 | Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000229 | Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000230 | Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000231 | Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000232 | Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000233 | Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000234 | Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000235 | Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000236 | Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000237 | Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000238 | Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000239 | Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000240 | Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000241 | Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000242 | Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000243 | Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000244 | Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000245 | Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track this driver for transmission wire-down events | not applicable | SDG&E | 2026 | 2
1050000246 | Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000247 | Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000248 | Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000249 | Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000250 | Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000251 | Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000252 | Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000253 | Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000254 | Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000255 | Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000256 | Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000257 | Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000258 | Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 8
1050000259 | Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000260 | Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 3
1050000261 | Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000262 | Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000263 | Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000264 | Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 15
1050000265 | Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000266 | Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000267 | Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 3
1050000268 | Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 2
1050000269 | Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000270 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 12
1050000271 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 10
1050000272 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 3
1050000273 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000274 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000275 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000276 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000277 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000278 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000279 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000280 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000281 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000282 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000283 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000284 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000285 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000286 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000287 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000288 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 8
1050000289 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 3
1050000290 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000291 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000292 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000293 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000294 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000295 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000296 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000297 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000298 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000299 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track unkown risk events in the contact from object category. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000300 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000301 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000302 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000303 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000304 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000305 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000306 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000307 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000308 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000309 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000310 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000311 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000312 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000313 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000314 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000315 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000316 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000317 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000318 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 5
1050000319 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000320 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000321 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000322 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000323 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000324 | Vegetation contact | Unplanned Outage | Root failure | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000325 | Vegetation contact | Unplanned Outage | Root failure | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000326 | Vegetation contact | Unplanned Outage | Root failure | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000327 | Vegetation contact | Unplanned Outage | Root failure | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000328 | Vegetation contact | Unplanned Outage | Root failure | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000329 | Vegetation contact | Unplanned Outage | Root failure | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000330 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 12
1050000331 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000332 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000333 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000334 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000335 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000336 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 2
1050000337 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000338 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000339 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000340 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000341 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000342 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000343 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000344 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000345 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000346 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000347 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000348 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 4
1050000349 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000350 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000351 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000352 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000353 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000354 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 9
1050000355 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 2
1050000356 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 4
1050000357 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000358 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000359 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000360 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 4
1050000361 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000362 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 4
1050000363 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000364 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000365 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000366 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 3
1050000367 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000368 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000369 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000370 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000371 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000372 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 5
1050000373 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000374 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000375 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000376 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000377 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000378 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000379 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000380 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000381 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000382 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000383 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000384 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000385 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 2
1050000386 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 2
1050000387 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000388 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000389 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000390 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 6
1050000391 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 2
1050000392 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 3
1050000393 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000394 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000395 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000396 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000397 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000398 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000399 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000400 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000401 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000402 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events | SDG&E does not currently track this driver - relays are located within other pieces of equipment (sectionalizers/reclosers/etc.) | not applicable | SDG&E | 2026 | 2
1050000403 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events | SDG&E does not currently track this driver - relays are located within other pieces of equipment (sectionalizers/reclosers/etc.) | not applicable | SDG&E | 2026 | 2
1050000404 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events | SDG&E does not currently track this driver - relays are located within other pieces of equipment (sectionalizers/reclosers/etc.) | not applicable | SDG&E | 2026 | 2
1050000405 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000406 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000407 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000408 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000409 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000410 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000411 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000412 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000413 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000414 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000415 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000416 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000417 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000418 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000419 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000420 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 4
1050000421 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000422 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000423 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000424 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000425 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000426 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000427 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000428 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000429 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000430 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000431 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000432 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000433 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000434 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000435 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000436 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000437 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1050000438 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 6
1050000439 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 2
1050000440 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000441 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000442 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000443 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000444 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000445 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000446 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000447 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000448 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000449 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events | SDG&E's transmission lines do not contain this equipment | not applicable | SDG&E | 2026 | 2
1050000450 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000451 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000452 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000453 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000454 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000455 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events | SDG&E does not track unkown risk events within equipment failure. If no damage is found the risk event is categorized as "Unknown" | not applicable | SDG&E | 2026 | 2
1050000456 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 2
1050000457 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000458 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000459 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000460 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000461 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000462 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000463 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000464 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000465 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000466 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000467 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000468 | Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000469 | Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000470 | Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000471 | Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000472 | Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000473 | Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000474 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000475 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000476 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000477 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000478 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000479 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000480 | Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 2
1050000481 | Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000482 | Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000483 | Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000484 | Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000485 | Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000486 | Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000487 | Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000488 | Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000489 | Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000490 | Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000491 | Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000492 | Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000493 | Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000494 | Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000495 | Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000496 | Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000497 | Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000498 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000499 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000500 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000501 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000502 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000503 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events | SDG&E does not consider this driver as a risk event - see comments in QDR cover letter | not applicable | SDG&E | 2026 | 2
1050000504 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 30
1050000505 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 10
1050000506 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 7
1050000507 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 2
1050000508 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000509 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000510 | Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 1
1050000511 | Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000512 | Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000513 | Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000514 | Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events |  |  | SDG&E | 2026 | 2 | 0
1050000515 | Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events |  |  | SDG&E | 2026 | 2 | 0

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1060000000 | Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2
1060000001 | Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2
1060000002 | Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2
1060000003 | Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2
1060000004 | Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2
1060000005 | Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions | SDG&E does not consider this driver as a risk event | not applicable | SDG&E | 2026 | 2
1060000006 | Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000007 | Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000008 | Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000009 | Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000010 | Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000011 | Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000012 | Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 1
1060000013 | Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000014 | Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 1
1060000015 | Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000016 | Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000017 | Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000018 | Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000019 | Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 1
1060000020 | Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 1
1060000021 | Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000022 | Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000023 | Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000024 | Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000025 | Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000026 | Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000027 | Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000028 | Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000029 | Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000030 | Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2026 | 2
1060000031 | Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2026 | 2
1060000032 | Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2026 | 2
1060000033 | Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2026 | 2
1060000034 | Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2026 | 2
1060000035 | Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions | SDGE includes this metric in #11 "Other" | not applicable | SDG&E | 2026 | 2
1060000036 | Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000037 | Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 1
1060000038 | Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000039 | Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000040 | Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000041 | Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000042 | Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000043 | Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000044 | Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000045 | Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000046 | Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 1
1060000047 | Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000048 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000049 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000050 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000051 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000052 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000053 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000054 | Vegetation contact | Grow-in | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000055 | Vegetation contact | Grow-in | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000056 | Vegetation contact | Grow-in | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000057 | Vegetation contact | Grow-in | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000058 | Vegetation contact | Grow-in | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000059 | Vegetation contact | Grow-in | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000060 | Vegetation contact | Blow-in | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000061 | Vegetation contact | Blow-in | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000062 | Vegetation contact | Blow-in | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000063 | Vegetation contact | Blow-in | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000064 | Vegetation contact | Blow-in | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000065 | Vegetation contact | Blow-in | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000066 | Vegetation contact | Trunk failure | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000067 | Vegetation contact | Trunk failure | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000068 | Vegetation contact | Trunk failure | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000069 | Vegetation contact | Trunk failure | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000070 | Vegetation contact | Trunk failure | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000071 | Vegetation contact | Trunk failure | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000072 | Vegetation contact | Root failure | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000073 | Vegetation contact | Root failure | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000074 | Vegetation contact | Root failure | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000075 | Vegetation contact | Root failure | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000076 | Vegetation contact | Root failure | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000077 | Vegetation contact | Root failure | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000078 | Vegetation contact | Detached frond / limb / bark | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000079 | Vegetation contact | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000080 | Vegetation contact | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000081 | Vegetation contact | Detached frond / limb / bark | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000082 | Vegetation contact | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000083 | Vegetation contact | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000084 | Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000085 | Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000086 | Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000087 | Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000088 | Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000089 | Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000090 | Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000091 | Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000092 | Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000093 | Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000094 | Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000095 | Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000096 | Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000097 | Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000098 | Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000099 | Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000100 | Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000101 | Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000102 | Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000103 | Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000104 | Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000105 | Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000106 | Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000107 | Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000108 | Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000109 | Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000110 | Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000111 | Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000112 | Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000113 | Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000114 | Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000115 | Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000116 | Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000117 | Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000118 | Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000119 | Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000120 | Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000121 | Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000122 | Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000123 | Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000124 | Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000125 | Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000126 | Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000127 | Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000128 | Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000129 | Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000130 | Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000131 | Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000132 | Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000133 | Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000134 | Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000135 | Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000136 | Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000137 | Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000138 | Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000139 | Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000140 | Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000141 | Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000142 | Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000143 | Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000144 | Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000145 | Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000146 | Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000147 | Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000148 | Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000149 | Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000150 | Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000151 | Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000152 | Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000153 | Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000154 | Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000155 | Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000156 | Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000157 | Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000158 | Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000159 | Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000160 | Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000161 | Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000162 | Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2026 | 2
1060000163 | Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2026 | 2
1060000164 | Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2026 | 2
1060000165 | Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2026 | 2
1060000166 | Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2026 | 2
1060000167 | Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions | SDG&E tracks splice failure/damage under connection device | not applicable | SDG&E | 2026 | 2
1060000168 | Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000169 | Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000170 | Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000171 | Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000172 | Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000173 | Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000174 | Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000175 | Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000176 | Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000177 | Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000178 | Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000179 | Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000180 | Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000181 | Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000182 | Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000183 | Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000184 | Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000185 | Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000186 | Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000187 | Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000188 | Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000189 | Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000190 | Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000191 | Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000192 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000193 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000194 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000195 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000196 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000197 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000198 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2 | 0
1060000199 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2 | 0
1060000200 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2 | 0
1060000201 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2 | 0
1060000202 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2 | 0
1060000203 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2 | 0
1060000204 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000205 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000206 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000207 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000208 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000209 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000210 | Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000211 | Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000212 | Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000213 | Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000214 | Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000215 | Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000216 | Contamination | Contamination | Distribution | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000217 | Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000218 | Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000219 | Contamination | Contamination | Transmission | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000220 | Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000221 | Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000222 | Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000223 | Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000224 | Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000225 | Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000226 | Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000227 | Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions | SDG&E does not currently track this driver | not applicable | SDG&E | 2026 | 2
1060000228 | Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 1
1060000229 | Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000230 | Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000231 | Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000232 | Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000233 | Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000234 | Lightning | Lightning | Distribution | Non-HFTD | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000235 | Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000236 | Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000237 | Lightning | Lightning | Transmission | Non-HFTD | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000238 | Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000239 | Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions | SDG&E did not track this driver historically but can implement for future ignitions | not applicable | SDG&E | 2026 | 2
1060000240 | Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000241 | Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000242 | Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000243 | Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000244 | Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000245 | Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000246 | Other | Other (other) | Distribution | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000247 | Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000248 | Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000249 | Other | Other (other) | Transmission | Non-HFTD | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000250 | Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions |  |  | SDG&E | 2026 | 2 | 0
1060000251 | Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions |  |  | SDG&E | 2026 | 2 | 0

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1070000000 | Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 368.4922
1070000001 | Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 2161.8843
1070000002 | Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 121.9297
1070000003 | Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 146.8783
1070000004 | Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 26.0936
1070000005 | Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 117.7533
1070000006 | Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 87.3648
1070000007 | Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 96.2159
1070000008 | Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 732.8635
1070000009 | Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 676.4311
1070000010 | Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 14.3597
1070000011 | Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 155.3749
1070000012 | Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 4.9743
1070000013 | Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.37957
1070000014 | Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 542.5722
1070000015 | Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 886.5615
1070000016 | Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 7.7471
1070000017 | Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 110.2178
1070000018 | Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 99.735
1070000019 | Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 452.6864
1070000020 | Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 25.1634
1070000021 | Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 123.8697
1070000022 | Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1070000023 | Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 22.832
1070000024 | Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 27.103
1070000025 | Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 110.344
1070000026 | Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 67.1126
1070000027 | Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 514.0921
1070000028 | Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1070000029 | Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 23.4247
1070000030 | Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.66539
1070000031 | Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.56946
1070000032 | Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 16.0867
1070000033 | Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 246.6958
1070000034 | Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.20107
1070000035 | Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 11.8547
1070000036 | Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 1741.236
1070000037 | Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 5253.0642
1070000038 | Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 373.4017
1070000039 | Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 767.105
1070000040 | Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 11.8623
1070000041 | Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 39.6565
1070000042 | Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 846.3237
1070000043 | Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 284.094
1070000044 | Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 732.4495
1070000045 | Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 421.0506
1070000046 | Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 4.7447
1070000047 | Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 9.7207
1070000048 | Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 5.6537
1070000049 | Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 1.6613
1070000050 | Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 318.9784
1070000051 | Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 265.3431
1070000052 | Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 4.8673
1070000053 | Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 29.8363
1070000054 | Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 14.3482
1070000055 | Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 87.6308
1070000056 | Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 5.3869
1070000057 | Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 22.7862
1070000058 | Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1070000059 | Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.092242
1070000060 | Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 10.6718
1070000061 | Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 4.961
1070000062 | Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 8.641
1070000063 | Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 16.9785
1070000064 | Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1070000065 | Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1070000066 | Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 1.7332
1070000067 | Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.65012
1070000068 | Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 3.5361
1070000069 | Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 3.4685
1070000070 | Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1070000071 | Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1070000072 | Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 3256
1070000073 | Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 15158
1070000074 | Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 518
1070000075 | Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 1995
1070000076 | Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 3
1070000077 | Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 61
1070000078 | Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 965
1070000079 | Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 386
1070000080 | Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 842
1070000081 | Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 878
1070000082 | Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 12
1070000083 | Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 85
1070000084 | Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 2
1070000085 | Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 0
1070000086 | Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 459
1070000087 | Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 792
1070000088 | Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 6
1070000089 | Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities |  |  | SDG&E | 2026 | 2 | 67
1070000090 | Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 219536
1070000091 | Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 926572
1070000092 | Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 23379
1070000093 | Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 22209
1070000094 | Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 1347
1070000095 | Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 1326
1070000096 | Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 80421
1070000097 | Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 24615
1070000098 | Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 46959
1070000099 | Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 17021
1070000100 | Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 256
1070000101 | Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 493
1070000102 | Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 102
1070000103 | Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 3
1070000104 | Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 18994
1070000105 | Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 8588
1070000106 | Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 157
1070000107 | Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers |  |  | SDG&E | 2026 | 2 | 545
1070000108 | Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 16087
1070000109 | Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 95811
1070000110 | Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 2695
1070000111 | Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 19825
1070000112 | Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 104
1070000113 | Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 376
1070000114 | Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 4739
1070000115 | Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 2667
1070000116 | Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 4163
1070000117 | Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 3862
1070000118 | Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 32
1070000119 | Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 215
1070000120 | Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 14
1070000121 | Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 0
1070000122 | Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 2139
1070000123 | Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 2579
1070000124 | Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 41
1070000125 | Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers |  |  | SDG&E | 2026 | 2 | 240
1070000126 | AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 47162
1070000127 | AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 297331
1070000128 | AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 4457
1070000129 | AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 4140
1070000130 | AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 404
1070000131 | AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 321
1070000132 | AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 16183
1070000133 | AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 6785
1070000134 | AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 9750
1070000135 | AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 3564
1070000136 | AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 97
1070000137 | AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 152
1070000138 | AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 29
1070000139 | AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 1
1070000140 | AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 5628
1070000141 | AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 2244
1070000142 | AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 39
1070000143 | AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | SDG&E | 2026 | 2 | 163
1070000144 | Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 12
1070000145 | Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 72
1070000146 | Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 4
1070000147 | Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 23
1070000148 | Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1070000149 | Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 3
1070000150 | Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 2
1070000151 | Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 7
1070000152 | Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 4
1070000153 | Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 18
1070000154 | Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1070000155 | Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 1
1070000156 | Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1070000157 | Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1070000158 | Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1070000159 | Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 11
1070000160 | Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1070000161 | Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 1
1070000162 | Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 3
1070000163 | Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 14
1070000164 | Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1070000165 | Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 3
1070000166 | Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1070000167 | Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 2
1070000168 | Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 3
1070000169 | Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 6
1070000170 | Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 16
1070000171 | Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 51
1070000172 | Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 1
1070000173 | Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 7
1070000174 | Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1070000175 | Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1070000176 | Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 13
1070000177 | Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 93
1070000178 | Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 3
1070000179 | Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 7

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1080000000 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.42656
1080000001 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 2.7033
1080000002 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.28594
1080000003 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.17181
1080000004 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.019994
1080000005 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.0023296
1080000006 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.10168
1080000007 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.11424
1080000008 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 3.4716
1080000009 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 6.2656
1080000010 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 1.7875
1080000011 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 7.8186
1080000012 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | -0.0048202
1080000013 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000014 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 10.6701
1080000015 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 9.4635
1080000016 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.0036519
1080000017 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.10309
1080000018 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.039813
1080000019 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.032368
1080000020 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000021 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | -4.7e-06
1080000022 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000023 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000024 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000025 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000026 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000027 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | -0.0043474
1080000028 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000029 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000030 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000031 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000032 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 8.57e-05
1080000033 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.0027056
1080000034 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000035 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000036 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 5.6367
1080000037 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 30.3462
1080000038 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 1.4932
1080000039 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 3.2417
1080000040 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | -0.00023263
1080000041 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.032754
1080000042 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 1.0428
1080000043 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.43369
1080000044 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 1.6612
1080000045 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 8.3099
1080000046 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.022556
1080000047 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.22755
1080000048 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.065646
1080000049 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000050 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 2.999
1080000051 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 13.3013
1080000052 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.025728
1080000053 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.15413
1080000054 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000055 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.0033832
1080000056 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | -1.3e-05
1080000057 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | -0.0018297
1080000058 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000059 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000060 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000061 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000062 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000063 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000064 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000065 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000066 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | -0.027845
1080000067 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000068 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.028809
1080000069 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000070 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000071 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1080000072 | Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000073 | Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000074 | Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000075 | Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000076 | Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000077 | Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000078 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000079 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000080 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000081 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000082 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000083 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000084 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000085 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000086 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000087 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000088 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000089 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations | Substation removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000090 | Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000091 | Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000092 | Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000093 | Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000094 | Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000095 | Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000096 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000097 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000098 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000099 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000100 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000101 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000102 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000103 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000104 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000105 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000106 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0
1080000107 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations | Weather station removals or addtions are sourced from businesses, table 7 is sourced from GIS database. A small difference could be observed due to data digitizing processes. |  | SDG&E | 2026 | 2 | 0

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1090000000 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.017736
1090000001 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000002 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000003 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000004 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000005 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000006 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000007 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000008 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.6708
1090000009 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 1.0625
1090000010 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.48957
1090000011 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 1.1019
1090000012 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000013 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000014 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 2.3095
1090000015 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.91726
1090000016 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000017 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000018 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000019 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000020 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000021 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000022 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000023 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000024 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000025 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0.12465
1090000026 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000027 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 1.1483
1090000028 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000029 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000030 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000031 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000032 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000033 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000034 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000035 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | SDG&E | 2026 | 2 | 0
1090000036 | Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 1
1090000037 | Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000038 | Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000039 | Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000040 | Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000041 | Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000042 | Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000043 | Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000044 | Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000045 | Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000046 | Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000047 | Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000048 | Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000049 | Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000050 | Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000051 | Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000052 | Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000053 | Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | SDG&E | 2026 | 2 | 0
1090000054 | Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000055 | Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000056 | Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000057 | Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000058 | Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000059 | Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000060 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000061 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000062 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000063 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000064 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000065 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000066 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000067 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000068 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000069 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000070 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0
1090000071 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | SDG&E | 2026 | 2 | 0

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1100000000 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | RFW only | Number of events |  |  | SDG&E | 2026 | 2 | 0
1100000001 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW only | Number of events |  |  | SDG&E | 2026 | 2 | 0
1100000002 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW & RFW | Number of events |  |  | SDG&E | 2026 | 2 | 0
1100000003 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | Neither | Number of events |  |  | SDG&E | 2026 | 2 | 0
1100000004 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | RFW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000005 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000006 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW & RFW | Circuit-events, measured in number of events multiplied by number of circuits de-energized | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000007 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | Neither | Circuit-events, measured in number of events multiplied by number of circuits de-energized | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000008 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | RFW only | Customer hours | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000009 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW only | Customer hours | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000010 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW & RFW | Customer hours | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000011 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | Neither | Customer hours | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000012 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | RFW only | Number of events |  |  | SDG&E | 2026 | 2 | 0
1100000013 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW only | Number of events |  |  | SDG&E | 2026 | 2 | 0
1100000014 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW & RFW | Number of events |  |  | SDG&E | 2026 | 2 | 0
1100000015 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | Neither | Number of events |  |  | SDG&E | 2026 | 2 | 0
1100000016 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | RFW only | Circuit mile days | No fast-trip events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000017 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW only | Circuit mile days | No fast-trip events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000018 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW & RFW | Circuit mile days | No fast-trip events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000019 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | Neither | Circuit mile days | No fast-trip events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000020 | Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours |  |  | SDG&E | 2026 | 2 | 252905.75
1100000021 | Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  |  | SDG&E | 2026 | 2 | 240256.1
1100000022 | Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours |  |  | SDG&E | 2026 | 2 | 0
1100000023 | Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | SDG&E | 2026 | 2 | 8.94
1100000024 | Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served |  |  | SDG&E | 2026 | 2 | 8.94
1100000025 | Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | SDG&E | 2026 | 2 | 0.07699
1100000026 | Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | SDG&E | 2026 | 2 | 0.07699
1100000027 | Critical infrastructure impacted by PSPS | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000028 | Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000029 | Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000030 | Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000031 | Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000032 | Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000033 | Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000034 | Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000035 | Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000036 | Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000037 | Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000038 | Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000039 | Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000040 | Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000041 | Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours | No fast-trip events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000042 | Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours | No fast-trip events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2
1100000043 | Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events | No PSPS events in 2026 Q2 | Not Applicable | SDG&E | 2026 | 2

## Table 12
METRIC NUMBER | WORK ORDER NUMBER | EQUIPMENT TYPE | HFTD TIER | LINE TYPE | DATE OPENED | DUE DATE | GO 95 RULE 18 PRIORITY | UTILITY SPECIFIC REPAIR PRIORITY | DATE REINSPECTED | DATE MODIFIED | DUE DATE AFTER REINSPECTED OR MODIFIED | GO 95 RULE 18 PRIORITY AFTER REINSPECTED OR MODIFIED | REASON FOR REINSPECTION | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER
1120000000 | 139200 | Guy Wire - OH | Non-HFTD | Transmission | 2025-12-08 | 2026-12-08 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000001 | 140287 | Anchor Rod Ground Wire | Non-HFTD | Transmission | 2025-12-02 | 2026-12-02 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000002 | 136600 | Pole Butt | HFTD Tier 2 | Transmission | 2025-08-01 | 2026-08-01 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000003 | 141595 | Complete Tower | HFTD Tier 2 | Transmission | 2026-04-25 | 2026-08-29 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000004 | 141970 | Shoe Nut(s) | HFTD Tier 2 | Transmission | 2026-04-09 | 2027-04-08 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000005 | 141971 | Shoe Nut(s) | HFTD Tier 2 | Transmission | 2026-04-09 | 2027-04-08 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000006 | 141972 | Bolted Spacer | HFTD Tier 2 | Transmission | 2026-04-09 | 2027-04-08 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000007 | 142058 | Complete Tower | HFTD Tier 2 | Transmission | 2026-04-25 | 2026-08-29 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000008 | 139178 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000009 | 141475 | Shield Wire (Complete) | HFTD Tier 2 | Transmission | 2026-04-13 | 2027-04-12 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000010 | 140264 | Anchor Rod Ground Wire | HFTD Tier 2 | Transmission | 2026-02-28 | 2027-02-27 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000011 | 140263 | Anchor Rods | HFTD Tier 2 | Transmission | 2026-02-28 | 2027-02-27 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000012 | 140284 | Pole Top | Non-HFTD | Transmission | 2025-12-02 | 2026-12-02 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000013 | 140285 | Pole Top | Non-HFTD | Transmission | 2025-12-02 | 2026-12-02 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000014 | 141802 | Stub Pole - Wood | HFTD Tier 2 | Transmission | 2026-03-11 | 2027-03-11 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000015 | 141962 | Complete Tower | HFTD Tier 2 | Transmission | 2026-04-25 | 2026-08-29 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000016 | 137810 | Area Around Structure | HFTD Tier 3 | Transmission | 2025-06-25 | 2027-06-25 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000017 | 139753 | Pole Butt | HFTD Tier 2 | Transmission | 2026-01-16 | 2027-01-16 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000018 | 141986 | Conductor Strand(s) | HFTD Tier 2 | Transmission | 2026-04-09 | 2027-04-08 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000019 | 139148 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-16 | 2026-12-16 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000020 | 140608 | Footings (Complete) | HFTD Tier 2 | Transmission | 2025-05-28 | 2026-11-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000021 | 141825 | Bolt(s) | HFTD Tier 2 | Transmission | 2026-06-10 | 2027-06-10 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000022 | 137576 | FAA Light(s) | HFTD Tier 2 | Transmission | 2025-02-04 | 2026-08-02 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000023 | 139369 | Insulators-Post NCI 69kv Long | Non-HFTD | Transmission | 2026-01-05 | 2027-01-05 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000024 | 141728 | Complete Wood Pole | Non-HFTD | Transmission | 2026-03-12 | 2027-03-12 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000025 | 139532 | Hot End Cotter Key(s) | HFTD Tier 2 | Transmission | 2026-05-06 | 2027-05-05 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000026 | 142770 | Complete Wood Pole | Non-HFTD | Transmission | 2025-12-27 | 2026-12-27 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000027 | 142195 | Bolt(s) | HFTD Tier 2 | Transmission | 2026-04-24 | 2027-04-23 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000028 | 142062 | Ground Grid Taps | HFTD Tier 2 | Transmission | 2026-04-24 | 2027-04-23 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000029 | 140393 | Cross Arms | Non-HFTD | Transmission | 2026-04-02 | 2027-04-02 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000030 | 139841 | Footings (Complete) | HFTD Tier 2 | Transmission | 2026-03-12 | 2027-03-12 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000031 | 141997 | Damper (Complete) | HFTD Tier 2 | Transmission | 2026-05-06 | 2027-05-06 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000032 | 141823 | Footings (Complete) | HFTD Tier 2 | Transmission | 2026-03-18 | 2027-03-18 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000033 | 137941 | Anchor Rod Ground Wire | Non-HFTD | Transmission | 2025-08-02 | 2026-08-01 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000034 | 139198 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-08 | 2026-12-08 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000035 | 139854 | Pole Butt | HFTD Tier 2 | Transmission | 2026-01-16 | 2027-01-16 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000036 | 142733 | Pole Ground (Wire) | Non-HFTD | Transmission | 2026-06-06 | 2027-06-06 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000037 | 138452 | Hardware | HFTD Tier 2 | Transmission | 2026-04-11 | 2027-04-11 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000038 | 141605 | Shieldwire Attachment Point | HFTD Tier 2 | Transmission | 2026-05-06 | 2027-05-06 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000039 | 141606 | Shieldwire Attachment Point | HFTD Tier 2 | Transmission | 2026-05-06 | 2027-05-06 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000040 | 142869 | Complete Steel Pole | HFTD Tier 2 | Transmission | 2026-06-17 | 2027-06-17 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000041 | 138867 | Hardware | HFTD Tier 2 | Transmission | 2025-10-31 | 2026-10-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000042 | 139203 | Insulators-Ceramic Standard 30K | Non-HFTD | Transmission | 2025-12-08 | 2026-12-08 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000043 | 139201 | Pole Top | Non-HFTD | Transmission | 2025-12-08 | 2026-12-08 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000044 | 139205 | Shoe (Complete) | Non-HFTD | Transmission | 2025-12-08 | 2026-12-08 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000045 | 139206 | Guy Wire - OH | Non-HFTD | Transmission | 2025-12-08 | 2026-12-08 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000046 | 140120 | Insulators-Ceramic Standard 40K | HFTD Tier 2 | Transmission | 2025-11-24 | 2026-11-24 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000047 | 139179 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000048 | 142196 | Bolt(s) | HFTD Tier 2 | Transmission | 2026-04-24 | 2027-04-23 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000049 | 140256 | Footings (Complete) | HFTD Tier 2 | Transmission | 2026-03-16 | 2027-03-16 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000050 | 142751 | Pole Butt | HFTD Tier 2 | Transmission | 2025-08-13 | 2026-08-13 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000051 | 138612 | Hardware | HFTD Tier 2 | Transmission | 2026-02-27 | 2027-02-26 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000052 | 141141 | Complete Tower | HFTD Tier 2 | Transmission | 2026-04-09 | 2027-04-08 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000053 | 142756 | Complete Wood Pole | Non-HFTD | Transmission | 2026-03-01 | 2027-03-01 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000054 | 139182 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000055 | 139150 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000056 | 139752 | Pole Butt | HFTD Tier 2 | Transmission | 2026-01-16 | 2027-01-16 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000057 | 142060 | Cold End Clevis-Shackle | HFTD Tier 2 | Transmission | 2026-04-24 | 2027-04-23 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000058 | 141413 | Complete Wood Pole | Non-HFTD | Transmission | 2025-12-14 | 2026-12-14 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000059 | 139721 | Insulators-Ceramic Standard 40K | HFTD Tier 2 | Transmission | 2026-01-20 | 2027-01-19 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000060 | 139181 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000061 | 141590 | Hot End Cotter Key(s) | HFTD Tier 2 | Transmission | 2026-04-03 | 2027-04-02 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000062 | 141112 | Complete Wood Pole | Non-HFTD | Transmission | 2025-04-17 | 2026-07-17 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000063 | 141111 | Pole Butt | Non-HFTD | Transmission | 2025-04-17 | 2026-07-17 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000064 | 141250 | Hardware | Non-HFTD | Transmission | 2026-04-09 | 2027-04-09 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000065 | 142156 | Complete Wood Pole | Non-HFTD | Transmission | 2026-04-09 | 2027-04-09 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000066 | 139175 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000067 | 140578 | Shoe Nut(s) | HFTD Tier 2 | Transmission | 2026-03-17 | 2027-03-16 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000068 | 138419 | Bond Wire | Non-HFTD | Transmission | 2026-04-11 | 2027-04-11 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000069 | 139855 | Pole Butt | HFTD Tier 2 | Transmission | 2026-01-16 | 2027-01-16 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000070 | 142426 | Conduit | HFTD Tier 2 | Transmission | 2025-07-29 | 2026-07-29 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000071 | 140388 | Guy Wire - OH | HFTD Tier 2 | Transmission | 2026-03-11 | 2027-03-11 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000072 | 139367 | Bolt(s) | Non-HFTD | Transmission | 2025-10-13 | 2026-10-12 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000073 | 139368 | Insulators-Post NCI 69kv Long | Non-HFTD | Transmission | 2025-10-13 | 2026-10-12 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000074 | 141960 | Hardware | HFTD Tier 2 | Transmission | 2026-04-09 | 2027-04-08 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000075 | 141959 | Hot End Cotter Key(s) | HFTD Tier 2 | Transmission | 2026-04-09 | 2027-04-08 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000076 | 141690 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2026-03-04 | 2027-03-04 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000077 | 142044 | Cold End Cotter Key(s) | HFTD Tier 2 | Transmission | 2026-05-06 | 2027-05-05 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000078 | 139149 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-16 | 2026-12-16 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000079 | 140661 | Anchor Rods | Non-HFTD | Transmission | 2026-02-09 | 2027-02-09 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000080 | 142792 | Complete Steel Pole | HFTD Tier 2 | Transmission | 2026-06-17 | 2027-06-17 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000081 | 142039 | Bolt(s) | HFTD Tier 2 | Transmission | 2026-05-06 | 2027-05-05 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000082 | 141836 | Complete Tower | HFTD Tier 2 | Transmission | 2026-03-17 | 2027-03-18 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000083 | 142073 | Cold End Cotter Key(s) | HFTD Tier 2 | Transmission | 2026-04-24 | 2027-04-23 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000084 | 141182 | Damper (Complete) | HFTD Tier 2 | Transmission | 2026-02-13 | 2027-02-13 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000085 | 140863 | Footings (Complete) | HFTD Tier 3 | Transmission | 2025-04-16 | 2026-10-15 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000086 | 143341 | Guy Wire - Anchor | Non-HFTD | Transmission | 2026-05-01 | 2027-05-01 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000087 | 141534 | Lightening Arrestors | Non-HFTD | Transmission | 2026-03-14 | 2027-03-13 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000088 | 132855 | Jumper (Complete) | HFTD Tier 3 | Transmission | 2023-12-18 | 2026-12-15 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000089 | 137811 | Pole Top | HFTD Tier 3 | Transmission | 2025-12-23 | 2026-12-23 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000090 | 140075 | Insulators-Post NCI 69kv Long | HFTD Tier 2 | Transmission | 2026-02-28 | 2027-02-27 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000091 | 139815 | Pole Butt | HFTD Tier 2 | Transmission | 2026-01-16 | 2027-01-16 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000092 | 141259 | Complete Tower | HFTD Tier 2 | Transmission | 2026-04-09 | 2027-04-08 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000093 | 139099 | Ground Rod Bond Wire | Non-HFTD | Transmission | 2026-05-26 | 2027-05-26 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000094 | 141584 | Complete Tower | HFTD Tier 2 | Transmission | 2026-04-25 | 2026-08-29 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000095 | 141511 | Guy Wire - OH | Non-HFTD | Transmission | 2026-04-21 | 2027-04-21 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000096 | 141510 | Cross Arms | Non-HFTD | Transmission | 2026-04-21 | 2027-04-21 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000097 | 142263 | Ground Grid Taps | Non-HFTD | Transmission | 2026-05-01 | 2027-05-01 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000098 | 142264 | Ground Grid Taps | Non-HFTD | Transmission | 2026-05-01 | 2027-05-01 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000099 | 130991 | Bolted Spacer | HFTD Tier 2 | Transmission | 2023-10-08 | 2026-10-07 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000100 | 142025 | Complete Tower | HFTD Tier 2 | Transmission | 2026-04-25 | 2027-04-24 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000101 | 142034 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2026-03-11 | 2027-03-11 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000102 | 140449 | Anchor Rod Ground Wire | HFTD Tier 2 | Transmission | 2026-03-11 | 2027-03-11 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000103 | 140448 | Anchor Rods | HFTD Tier 2 | Transmission | 2026-03-11 | 2027-03-11 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000104 | 138614 | Shieldwire Attachment Point | HFTD Tier 2 | Transmission | 2025-11-08 | 2026-11-07 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000105 | 141868 | Shieldwire Attachment Point | HFTD Tier 2 | Transmission | 2026-04-24 | 2027-04-24 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000106 | 142530 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2025-07-29 | 2026-07-29 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000107 | 141946 | Stub Angles | HFTD Tier 3 | Transmission | 2025-08-21 | 2026-12-19 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000108 | 139751 | Pole Butt | HFTD Tier 2 | Transmission | 2026-01-16 | 2027-01-16 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000109 | 140989 | Complete Wood Pole | Non-HFTD | Transmission | 2025-12-16 | 2026-12-16 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000110 | 140864 | Footings (Complete) | HFTD Tier 3 | Transmission | 2025-04-15 | 2026-10-14 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000111 | 139819 | Pole Butt | HFTD Tier 2 | Transmission | 2026-01-16 | 2027-01-16 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000112 | 141691 | Stub Pole - Wood | HFTD Tier 2 | Transmission | 2026-02-28 | 2027-02-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000113 | 134403 | Complete Steel Pole | HFTD Tier 2 | Transmission | 2024-07-09 | 2027-07-09 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000114 | 141588 | Footings (Complete) | HFTD Tier 2 | Transmission | 2026-03-30 | 2027-03-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000115 | 141585 | Shieldwire Attachment Point | HFTD Tier 2 | Transmission | 2026-04-03 | 2026-08-29 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000116 | 139956 | Insulators-Post NCI 69kv Long | HFTD Tier 3 | Transmission | 2026-03-11 | 2027-03-11 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000117 | 139177 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000118 | 139818 | Pole Butt | HFTD Tier 2 | Transmission | 2026-01-16 | 2027-01-16 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000119 | 139151 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000120 | 142061 | Ground Grid Taps | HFTD Tier 2 | Transmission | 2026-04-24 | 2027-04-23 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000121 | 142242 | Pole Butt | Non-HFTD | Transmission | 2026-05-26 | 2027-05-26 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000122 | 138348 | Cold End Cotter Key(s) | HFTD Tier 3 | Transmission | 2025-08-23 | 2026-08-20 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000123 | 141775 | Bolt(s) | HFTD Tier 2 | Transmission | 2026-05-06 | 2027-05-05 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000124 | 125650 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2021-09-01 | 2027-08-25 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000125 | 139174 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000126 | 142802 | Hardware | Non-HFTD | Transmission | 2026-05-26 | 2027-05-26 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000127 | 142803 | Cross Arms | Non-HFTD | Transmission | 2026-05-26 | 2027-05-26 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000128 | 141591 | Footings (Complete) | HFTD Tier 2 | Transmission | 2026-05-08 | 2027-05-08 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000129 | 139194 | Complete Wood Pole | Non-HFTD | Transmission | 2025-12-02 | 2026-12-02 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000130 | 139192 | Anchor Rod Ground Wire | Non-HFTD | Transmission | 2026-05-03 | 2027-05-03 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000131 | 139193 | Guy Wire - OH | Non-HFTD | Transmission | 2025-12-02 | 2026-12-02 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000132 | 142024 | Complete Tower | HFTD Tier 2 | Transmission | 2026-04-25 | 2027-04-24 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000133 | 141985 | Conductor Strand(s) | HFTD Tier 2 | Transmission | 2026-04-09 | 2027-04-09 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000134 | 138416 | Pole Butt | Non-HFTD | Transmission | 2026-04-11 | 2027-04-11 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000135 | 139800 | Shoe Pin-Bolt | HFTD Tier 2 | Transmission | 2026-01-24 | 2027-01-23 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000136 | 140259 | Insulators-NCI 69kv | HFTD Tier 2 | Transmission | 2026-03-11 | 2027-03-10 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000137 | 140865 | Footings (Complete) | HFTD Tier 3 | Transmission | 2025-04-15 | 2026-10-14 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000138 | 137216 | Ground Grid Taps | HFTD Tier 2 | Transmission | 2025-10-08 | 2026-10-07 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000139 | 138868 | Anchor Rods | HFTD Tier 2 | Transmission | 2025-10-31 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000140 | 138870 | Anchor Rod Ground Wire | HFTD Tier 2 | Transmission | 2025-10-31 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000141 | 141391 | Bolt(s) | HFTD Tier 2 | Transmission | 2026-05-06 | 2027-05-05 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000142 | 139183 | Pole Butt | HFTD Tier 2 | Transmission | 2025-12-17 | 2026-12-17 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000143 | 139860 | Pole Butt | HFTD Tier 2 | Transmission | 2026-01-16 | 2027-01-16 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000144 | 141569 | Hardware | Non-HFTD | Transmission | 2026-05-03 | 2027-05-03 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000145 | 141097 | Cold End Cotter Key(s) | HFTD Tier 2 | Transmission | 2026-05-06 | 2027-05-05 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000146 | 141903 | Complete Tower | HFTD Tier 2 | Transmission | 2026-03-19 | 2027-03-18 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000147 | 140790 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2025-11-29 | 2026-11-29 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000148 | 140003 | Shoe Nut(s) | Non-HFTD | Transmission | 2026-03-01 | 2027-03-01 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000149 | 140980 | Complete Wood Pole | Non-HFTD | Transmission | 2025-12-27 | 2026-12-27 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000150 | 140972 | Complete Wood Pole | HFTD Tier 2 | Transmission | 2025-12-27 | 2026-12-27 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000151 | 141840 | Complete Wood Pole | Non-HFTD | Transmission | 2026-03-18 | 2027-03-18 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000152 | 138087 | Anchor Rod Ground Wire | Non-HFTD | Transmission | 2025-08-13 | 2026-08-13 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000153 | 138088 | Guy Wire - OH | Non-HFTD | Transmission | 2025-08-13 | 2026-08-13 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000154 | 143342 | Complete Wood Pole | Non-HFTD | Transmission | 2026-05-13 | 2027-05-13 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000155 | 140773 | Bond Wire | Non-HFTD | Transmission | 2026-05-13 | 2027-05-13 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000156 | 140772 | Cross Arms | Non-HFTD | Transmission | 2026-05-13 | 2027-05-13 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000157 | 139231 | Corona Ring(s) | HFTD Tier 2 | Transmission | 2026-05-06 | 2027-05-05 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000158 | 139152 | Insulators-NCI 69kv | Non-HFTD | Transmission | 2025-12-02 | 2026-12-02 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000159 | 139801 | Fiberglass Rod | HFTD Tier 2 | Transmission | 2026-01-24 | 2027-01-23 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000160 | 100028485562 | Other | HFTD Tier 2 | Distribution | 2026-01-02 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000161 | 100028485564 | Other | HFTD Tier 2 | Distribution | 2026-01-02 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000162 | 100028485604 | Other | HFTD Tier 2 | Distribution | 2026-01-02 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000163 | 100028485605 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-01-02 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000164 | 100028485606 | Conductor | HFTD Tier 2 | Distribution | 2026-01-02 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000165 | 100028485674 | Pole | HFTD Tier 2 | Distribution | 2026-01-02 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000166 | 100028488106 | Sign | HFTD Tier 2 | Distribution | 2026-01-05 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000167 | 100028489372 | Other | HFTD Tier 2 | Distribution | 2026-01-05 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000168 | 100028491817 | Other | HFTD Tier 3 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000169 | 100028491818 | Other | HFTD Tier 3 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000170 | 100028491819 | Other | HFTD Tier 3 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000171 | 100028491885 | Other | HFTD Tier 2 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000172 | 100028491886 | Other | HFTD Tier 2 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000173 | 100028491907 | Other | HFTD Tier 3 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000174 | 100028491908 | Other | HFTD Tier 3 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000175 | 100028491909 | Other | HFTD Tier 3 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000176 | 100028491929 | Sign | HFTD Tier 2 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000177 | 100028491971 | Other | HFTD Tier 3 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000178 | 100028491972 | Other | HFTD Tier 3 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000179 | 100028491973 | Other | HFTD Tier 3 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000180 | 100028491974 | Other | HFTD Tier 3 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000181 | 100028491975 | Other | HFTD Tier 3 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000182 | 100028492030 | Other | HFTD Tier 3 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000183 | 100028492031 | Other | HFTD Tier 3 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000184 | 100028492032 | Other | HFTD Tier 3 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000185 | 100028492033 | Other | HFTD Tier 3 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000186 | 100028492110 | Ground Wire | HFTD Tier 2 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000187 | 100028492293 | Other | HFTD Tier 2 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000188 | 100028492525 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000189 | 100028492526 | Conductor | HFTD Tier 2 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000190 | 100028492528 | Other | HFTD Tier 2 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000191 | 100028492672 | Other | HFTD Tier 2 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000192 | 100028492938 | Conductor | HFTD Tier 2 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000193 | 100028492939 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000194 | 100028492950 | Ground Wire | HFTD Tier 2 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000195 | 100028492951 | Pole | HFTD Tier 2 | Distribution | 2026-01-06 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000196 | 100028493706 | Avian Protection | HFTD Tier 2 | Distribution | 2026-01-07 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000197 | 100028493707 | Avian Protection | HFTD Tier 2 | Distribution | 2026-01-07 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000198 | 100028493981 | Other | HFTD Tier 3 | Distribution | 2026-01-07 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000199 | 100028494101 | Other | HFTD Tier 3 | Distribution | 2026-01-07 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000200 | 100028494418 | Avian Protection | HFTD Tier 2 | Distribution | 2026-01-07 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000201 | 100028494551 | Conduit | HFTD Tier 2 | Distribution | 2026-01-07 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000202 | 100028494568 | Sign | HFTD Tier 2 | Distribution | 2026-01-07 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000203 | 100028494634 | Sign | HFTD Tier 3 | Distribution | 2026-01-07 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000204 | 100028494680 | Pole | HFTD Tier 2 | Distribution | 2026-01-07 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000205 | 100028494681 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-07 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000206 | 100028494688 | Other | HFTD Tier 2 | Distribution | 2026-01-07 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000207 | 100028494750 | Sign | HFTD Tier 2 | Distribution | 2026-01-07 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000208 | 100028494751 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-01-07 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000209 | 100028495154 | Sign | HFTD Tier 2 | Distribution | 2026-01-07 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000210 | 100028495155 | Other | HFTD Tier 2 | Distribution | 2026-01-07 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000211 | 100028496455 | Avian Protection | HFTD Tier 3 | Distribution | 2026-01-08 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000212 | 100028496456 | Other | HFTD Tier 3 | Distribution | 2026-01-08 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000213 | 100028496583 | Pole | HFTD Tier 2 | Distribution | 2026-01-08 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000214 | 100028496584 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-08 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000215 | 100028497081 | Other | HFTD Tier 3 | Distribution | 2026-01-08 | 2026-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000216 | 100028497955 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-01-08 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000217 | 100028497957 | Other | HFTD Tier 2 | Distribution | 2026-01-08 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000218 | 100028497958 | Other | HFTD Tier 2 | Distribution | 2026-01-08 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000219 | 100028497962 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-01-08 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000220 | 100028497963 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-01-08 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000221 | 100028497966 | Sign | HFTD Tier 2 | Distribution | 2026-01-08 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000222 | 100028498073 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-08 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000223 | 100028498074 | Other | HFTD Tier 2 | Distribution | 2026-01-08 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000224 | 100028498736 | Avian Protection | HFTD Tier 2 | Distribution | 2026-01-09 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000225 | 100028498937 | Pole | HFTD Tier 3 | Distribution | 2026-01-09 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000226 | 100028499586 | Cross Arm | HFTD Tier 3 | Distribution | 2026-01-09 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000227 | 100028499587 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-01-09 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000228 | 100028499588 | Pole | HFTD Tier 2 | Distribution | 2026-01-09 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000229 | 100028499873 | Cross Arm | HFTD Tier 3 | Distribution | 2026-01-09 | 2026-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000230 | 100028500100 | Pole | HFTD Tier 3 | Distribution | 2026-01-09 | 2026-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000231 | 100028500337 | Other | HFTD Tier 3 | Distribution | 2026-01-09 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000232 | 100028501011 | Anchor/Guy - Veg | HFTD Tier 3 | Distribution | 2026-01-09 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000233 | 100028501012 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-01-09 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000234 | 100028501013 | Pole | HFTD Tier 3 | Distribution | 2026-01-09 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000235 | 100028501014 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-01-09 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000236 | 100028502152 | Other | HFTD Tier 3 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000237 | 100028502239 | Other | HFTD Tier 3 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000238 | 100028502311 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000239 | 100028502482 | Pole | HFTD Tier 3 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000240 | 100028502483 | Cross Arm | HFTD Tier 3 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000241 | 100028502526 | Other | HFTD Tier 3 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000242 | 100028502527 | Other | HFTD Tier 3 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000243 | 100028502614 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000244 | 100028502711 | Other | HFTD Tier 3 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000245 | 100028502712 | Other | HFTD Tier 3 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000246 | 100028502713 | Other | HFTD Tier 3 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000247 | 100028502717 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000248 | 100028502772 | Conductor - Veg | HFTD Tier 3 | Distribution | 2026-01-12 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000249 | 100028502773 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000250 | 100028502774 | Conductor - Veg | HFTD Tier 3 | Distribution | 2026-01-12 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000251 | 100028502972 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000252 | 100028503081 | Conductor | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000253 | 100028503082 | Pole | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000254 | 100028503083 | Ground Wire | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000255 | 100028503084 | Pole | HFTD Tier 2 | Distribution | 2026-01-12 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000256 | 100028503262 | Pole | HFTD Tier 3 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000257 | 100028503341 | Anchor/Guy - Veg | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000258 | 100028503342 | Other | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000259 | 100028503343 | Anchor/Guy - Veg | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000260 | 100028503344 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000261 | 100028503480 | Other | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000262 | 100028503481 | Ground Wire | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000263 | 100028503484 | Other | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000264 | 100028503486 | Ground Wire | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000265 | 100028503487 | Other | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000266 | 100028503489 | Other | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000267 | 100028503565 | Pole | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000268 | 100028503569 | Ground Wire | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000269 | 100028503610 | Pole | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000270 | 100028503612 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000271 | 100028503773 | Pole | HFTD Tier 3 | Distribution | 2026-01-12 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000272 | 100028506839 | Other | HFTD Tier 3 | Distribution | 2026-01-13 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000273 | 100028508331 | Other | HFTD Tier 2 | Distribution | 2026-01-13 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000274 | 100028508783 | Other | HFTD Tier 2 | Distribution | 2026-01-13 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000275 | 100028508784 | Ground Wire | HFTD Tier 2 | Distribution | 2026-01-13 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000276 | 100028508785 | Pole | HFTD Tier 2 | Distribution | 2026-01-13 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000277 | 100028508788 | Other | HFTD Tier 2 | Distribution | 2026-01-13 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000278 | 100028508800 | Other | HFTD Tier 2 | Distribution | 2026-01-13 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000279 | 100028508803 | Pole | HFTD Tier 2 | Distribution | 2026-01-13 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000280 | 100028509486 | Pole | HFTD Tier 2 | Distribution | 2026-01-14 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000281 | 100028509587 | Transformer | HFTD Tier 2 | Distribution | 2026-01-14 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000282 | 100028509746 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-14 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000283 | 100028509801 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000284 | 100028509802 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-14 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000285 | 100028509877 | Other | HFTD Tier 2 | Distribution | 2026-01-14 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000286 | 100028509878 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-01-14 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000287 | 100028510210 | Guy | HFTD Tier 3 | Distribution | 2026-01-14 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000288 | 100028510211 | Ground Wire | HFTD Tier 3 | Distribution | 2026-01-14 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000289 | 100028510441 | Other | HFTD Tier 2 | Distribution | 2026-01-14 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000290 | 100028510442 | Conductor | HFTD Tier 2 | Distribution | 2026-01-14 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000291 | 100028510443 | Other | HFTD Tier 2 | Distribution | 2026-01-14 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000292 | 100028510497 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-14 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000293 | 100028510499 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-14 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000294 | 100028510885 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-01-14 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000295 | 100028510887 | Pole | HFTD Tier 2 | Distribution | 2026-01-14 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000296 | 100028510888 | Conductor | HFTD Tier 2 | Distribution | 2026-01-14 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000297 | 100028510961 | Avian Protection | HFTD Tier 2 | Distribution | 2026-01-14 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000298 | 100028510963 | Pole | HFTD Tier 2 | Distribution | 2026-01-14 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000299 | 100028511649 | Anchor/Guy | HFTD Tier 3 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000300 | 100028511657 | Other | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000301 | 100028512529 | Pole | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000302 | 100028512690 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000303 | 100028512691 | Guy | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000304 | 100028513120 | Conductor | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000305 | 100028513431 | Pole | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000306 | 100028513432 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000307 | 100028513903 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000308 | 100028514900 | Sign | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000309 | 100028514901 | Other | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000310 | 100028514906 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000311 | 100028514907 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000312 | 100028514908 | Conductor | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000313 | 100028514909 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000314 | 100028515088 | Other | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000315 | 100028515089 | Other | HFTD Tier 2 | Distribution | 2026-01-15 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000316 | 100028516917 | Pole | HFTD Tier 2 | Distribution | 2026-01-16 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000317 | 100028516919 | Conductor | HFTD Tier 2 | Distribution | 2026-01-16 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000318 | 100028516970 | Conductor | HFTD Tier 2 | Distribution | 2026-01-16 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000319 | 100028517387 | Pole | HFTD Tier 2 | Distribution | 2026-01-16 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000320 | 100028517388 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-01-16 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000321 | 100028517966 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-16 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000322 | 100028518126 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-16 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000323 | 100028518127 | Conductor | HFTD Tier 2 | Distribution | 2026-01-16 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000324 | 100028518128 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-01-16 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000325 | 100028518361 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-01-16 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000326 | 100028518399 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-01-16 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000327 | 100028521055 | Pole | HFTD Tier 2 | Distribution | 2026-01-20 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000328 | 100028521158 | Pole | HFTD Tier 3 | Distribution | 2026-01-20 | 2026-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000329 | 100028521250 | Cross Arm | HFTD Tier 3 | Distribution | 2026-01-20 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000330 | 100028521389 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-01-20 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000331 | 100028521712 | Pole | HFTD Tier 2 | Distribution | 2026-01-20 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000332 | 100028521713 | Avian Protection | HFTD Tier 2 | Distribution | 2026-01-20 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000333 | 100028522076 | Pole | HFTD Tier 2 | Distribution | 2026-01-20 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000334 | 100028522665 | Other | HFTD Tier 2 | Distribution | 2026-01-20 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000335 | 100028522666 | Pole | HFTD Tier 2 | Distribution | 2026-01-20 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000336 | 100028522667 | Anchor/Guy - Veg | HFTD Tier 2 | Distribution | 2026-01-20 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000337 | 100028522668 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-01-20 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000338 | 100028522669 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-20 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000339 | 100028522680 | Other | HFTD Tier 2 | Distribution | 2026-01-20 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000340 | 100028522681 | Pole | HFTD Tier 2 | Distribution | 2026-01-20 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000341 | 100028523225 | Pole | HFTD Tier 2 | Distribution | 2026-01-20 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000342 | 100028523228 | Pole | HFTD Tier 2 | Distribution | 2026-01-20 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000343 | 100028523240 | Other | HFTD Tier 2 | Distribution | 2026-01-20 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000344 | 100028523793 | Pole | HFTD Tier 2 | Distribution | 2026-01-20 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000345 | 100028523794 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-20 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000346 | 100028523993 | Pole | HFTD Tier 2 | Distribution | 2026-01-20 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000347 | 100028524041 | Pole | HFTD Tier 2 | Distribution | 2026-01-20 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000348 | 100028525158 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000349 | 100028525159 | Pole | HFTD Tier 2 | Distribution | 2026-01-21 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000350 | 100028525420 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000351 | 100028525421 | Sign | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000352 | 100028525423 | Pole | HFTD Tier 2 | Distribution | 2026-01-21 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000353 | 100028525424 | Conductor | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000354 | 100028525726 | Pole | HFTD Tier 2 | Distribution | 2026-01-21 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000355 | 100028525980 | Sign | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000356 | 100028525981 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000357 | 100028526326 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000358 | 100028526327 | Conductor | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000359 | 100028526331 | Pole | HFTD Tier 2 | Distribution | 2026-01-21 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000360 | 100028526332 | Conductor | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000361 | 100028526333 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000362 | 100028526334 | Pole | HFTD Tier 2 | Distribution | 2026-01-21 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000363 | 100028526336 | Sign | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000364 | 100028526337 | Sign | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000365 | 100028526752 | Other | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000366 | 100028526753 | Other | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000367 | 100028526754 | Other | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000368 | 100028526755 | Other | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000369 | 100028526756 | Other | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000370 | 100028526902 | Other | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000371 | 100028526903 | Other | HFTD Tier 2 | Distribution | 2026-01-21 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000372 | 100028527768 | Pole | HFTD Tier 2 | Distribution | 2026-01-22 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000373 | 100028527778 | Pole | HFTD Tier 2 | Distribution | 2026-01-22 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000374 | 100028527779 | Pole | HFTD Tier 2 | Distribution | 2026-01-22 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000375 | 100028527920 | Other | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000376 | 100028527921 | Other | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000377 | 100028527923 | Other | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000378 | 100028527924 | Other | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000379 | 100028527925 | Other | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000380 | 100028528066 | Other | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000381 | 100028528067 | Other | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000382 | 100028528165 | Sign | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000383 | 100028528166 | Sign | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000384 | 100028528167 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000385 | 100028528478 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000386 | 100028528500 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000387 | 100028528501 | Other | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000388 | 100028528815 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000389 | 100028528816 | Pole | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000390 | 100028528851 | Other | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000391 | 100028529160 | Conductor | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000392 | 100028529358 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000393 | 100028529359 | Pole | HFTD Tier 2 | Distribution | 2026-01-22 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000394 | 100028564339 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000395 | 100028564350 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000396 | 100028564668 | Ground Wire | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000397 | 100028564794 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000398 | 100028564795 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000399 | 100028564796 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000400 | 100028564797 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000401 | 100028564798 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000402 | 100028564799 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000403 | 100028564800 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000404 | 100028565015 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000405 | 100028565726 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000406 | 100028565727 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000407 | 100028565728 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000408 | 100028565729 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000409 | 100028565730 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000410 | 100028565731 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000411 | 100028565732 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000412 | 100028566102 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000413 | 100028566103 | Sign | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000414 | 100028566105 | Other | HFTD Tier 2 | Distribution | 2026-01-26 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000415 | 100028566108 | Ground Wire | HFTD Tier 2 | Distribution | 2026-01-26 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000416 | 100028568118 | Sign | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000417 | 100028568212 | Conductor | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000418 | 100028568385 | Other | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000419 | 100028568387 | Conductor | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000420 | 100028569615 | Sign | HFTD Tier 2 | Distribution | 2026-01-27 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000421 | 100028570188 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000422 | 100028570189 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000423 | 100028570230 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000424 | 100028570231 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000425 | 100028570232 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000426 | 100028570233 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000427 | 100028570316 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000428 | 100028570317 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000429 | 100028570318 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000430 | 100028570319 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000431 | 100028570330 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000432 | 100028570331 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000433 | 100028570332 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000434 | 100028570538 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000435 | 100028570539 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000436 | 100028570598 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000437 | 100028570599 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000438 | 100028570632 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000439 | 100028570670 | Other | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000440 | 100028571380 | Ground Wire | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000441 | 100028571382 | Cross Arm | HFTD Tier 2 | Distribution | 2026-01-28 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000442 | 100028571383 | Pole | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000443 | 100028571843 | Sign | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000444 | 100028571844 | Sign | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000445 | 100028571845 | Sign | HFTD Tier 2 | Distribution | 2026-01-28 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000446 | 100028572585 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-01-29 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000447 | 100028573677 | Pole | HFTD Tier 2 | Distribution | 2026-01-29 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000448 | 100028573678 | Other | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000449 | 100028573865 | Other | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000450 | 100028573866 | Other | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000451 | 100028573895 | Pole | HFTD Tier 3 | Distribution | 2026-01-29 | 2026-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000452 | 100028573896 | Pole | HFTD Tier 3 | Distribution | 2026-01-29 | 2026-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000453 | 100028574347 | Anchor/Guy - Veg | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000454 | 100028574348 | Other | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000455 | 100028574553 | Transformer | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000456 | 100028574566 | Conduit | HFTD Tier 2 | Distribution | 2026-01-29 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000457 | 100028578940 | Pole | HFTD Tier 2 | Distribution | 2026-01-30 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000458 | 100028578941 | Pole | HFTD Tier 2 | Distribution | 2026-01-30 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000459 | 100028578946 | Pole | HFTD Tier 2 | Distribution | 2026-01-30 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000460 | 100028579299 | Conductor | HFTD Tier 2 | Distribution | 2026-01-30 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000461 | 100028580096 | Pole | HFTD Tier 2 | Distribution | 2026-01-30 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000462 | 100028580099 | Sign | HFTD Tier 2 | Distribution | 2026-01-30 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000463 | 100028580832 | Other | HFTD Tier 2 | Distribution | 2026-01-30 | 2031-03-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000464 | 100028581983 | Other | HFTD Tier 2 | Distribution | 2026-01-30 | 2027-03-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000465 | 100028597243 | Cross Arm | HFTD Tier 3 | Distribution | 2026-02-02 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000466 | 100028597883 | Other | HFTD Tier 3 | Distribution | 2026-02-02 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000467 | 100028597884 | Anchor/Guy | HFTD Tier 3 | Distribution | 2026-02-02 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000468 | 100028597885 | Pole | HFTD Tier 2 | Distribution | 2026-02-02 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000469 | 100028598036 | Other | HFTD Tier 3 | Distribution | 2026-02-02 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000470 | 100028598206 | Pole | HFTD Tier 2 | Distribution | 2026-02-02 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000471 | 100028598595 | Other | HFTD Tier 2 | Distribution | 2026-02-02 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000472 | 100028600508 | Avian Protection | HFTD Tier 3 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000473 | 100028600509 | Other | HFTD Tier 3 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000474 | 100028600630 | Other | HFTD Tier 3 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000475 | 100028600631 | Other | HFTD Tier 3 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000476 | 100028600686 | Other | HFTD Tier 3 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000477 | 100028600894 | Ground Wire | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000478 | 100028601779 | Sign | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000479 | 100028601845 | Guy | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000480 | 100028601847 | Ground Wire | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000481 | 100028601849 | Avian Protection | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000482 | 100028602015 | Other | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000483 | 100028602018 | Other | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000484 | 100028602081 | Other | HFTD Tier 3 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000485 | 100028602106 | Pole | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000486 | 100028602107 | Ground Wire | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000487 | 100028602284 | Pole | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000488 | 100028602288 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000489 | 100028602818 | Sign | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000490 | 100028602826 | Sign | HFTD Tier 2 | Distribution | 2026-02-03 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000491 | 100028602945 | Other | HFTD Tier 3 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000492 | 100028602946 | Ground Wire | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000493 | 100028602947 | Other | HFTD Tier 3 | Distribution | 2026-01-13 | 2026-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000494 | 100028603014 | Sign | HFTD Tier 3 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000495 | 100028603017 | Conduit | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000496 | 100028603018 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000497 | 100028603019 | Avian Protection | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000498 | 100028603023 | Pole | HFTD Tier 3 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000499 | 100028603231 | Avian Protection | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000500 | 100028603232 | Avian Protection | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000501 | 100028603233 | Avian Protection | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000502 | 100028603849 | Cross Arm | HFTD Tier 2 | Distribution | 2026-02-04 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000503 | 100028603991 | Avian Protection | HFTD Tier 3 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000504 | 100028604078 | Avian Protection | HFTD Tier 3 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000505 | 100028604079 | Avian Protection | HFTD Tier 3 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000506 | 100028604176 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000507 | 100028604178 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000508 | 100028604613 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000509 | 100028604614 | Pole | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000510 | 100028606075 | Conductor | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000511 | 100028606077 | Other | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000512 | 100028606078 | Sign | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000513 | 100028606370 | Sign | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000514 | 100028606371 | Sign | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000515 | 100028606372 | Sign | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000516 | 100028606373 | Other | HFTD Tier 2 | Distribution | 2026-02-04 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000517 | 100028608321 | Guy | HFTD Tier 3 | Distribution | 2026-02-05 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000518 | 100028609529 | Pole | HFTD Tier 2 | Distribution | 2026-02-05 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000519 | 100028610160 | Anchor/Guy - Veg | HFTD Tier 2 | Distribution | 2026-02-05 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000520 | 100028610164 | Other | HFTD Tier 2 | Distribution | 2026-02-05 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000521 | 100028611373 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-02-05 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000522 | 100028611608 | Pole | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000523 | 100028611609 | Pole | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000524 | 100028611793 | Pole | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000525 | 100028611794 | Conductor | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000526 | 100028611795 | Other | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000527 | 100028612394 | Pole | HFTD Tier 2 | Distribution | 2026-02-06 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000528 | 100028612395 | Conductor | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000529 | 100028612396 | Conductor | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000530 | 100028612397 | Pole | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000531 | 100028612459 | Conductor | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000532 | 100028612500 | Pole | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000533 | 100028612501 | Cross Arm | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000534 | 100028612502 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000535 | 100028612504 | Pole | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000536 | 100028612505 | Conductor | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000537 | 100028612575 | Pole | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000538 | 100028612635 | Conductor | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000539 | 100028612636 | Conductor | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000540 | 100028612637 | Cross Arm | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000541 | 100028612638 | Cross Arm | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000542 | 100028612896 | Cross Arm | HFTD Tier 2 | Distribution | 2026-02-06 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000543 | 100028613182 | Cross Arm | HFTD Tier 2 | Distribution | 2026-02-06 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000544 | 100028615647 | Other | HFTD Tier 2 | Distribution | 2026-02-09 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000545 | 100028616616 | Other | HFTD Tier 2 | Distribution | 2026-02-09 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000546 | 100028616617 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-02-09 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000547 | 100028617079 | Sign | HFTD Tier 2 | Distribution | 2026-02-09 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000548 | 100028617080 | Pole | HFTD Tier 2 | Distribution | 2026-02-09 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000549 | 100028617082 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-02-09 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000550 | 100028617083 | Pole | HFTD Tier 2 | Distribution | 2026-02-09 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000551 | 100028617852 | Other | HFTD Tier 2 | Distribution | 2026-02-10 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000552 | 100028618736 | Cross Arm | HFTD Tier 2 | Distribution | 2026-02-10 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000553 | 100028618737 | Other | HFTD Tier 2 | Distribution | 2026-02-10 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000554 | 100028618738 | Other | HFTD Tier 2 | Distribution | 2026-02-10 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000555 | 100028619269 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-02-10 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000556 | 100028619303 | Other | HFTD Tier 2 | Distribution | 2026-02-10 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000557 | 100028619640 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-02-10 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000558 | 100028620918 | Pole | HFTD Tier 2 | Distribution | 2026-02-10 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000559 | 100028622487 | Pole | HFTD Tier 2 | Distribution | 2026-02-11 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000560 | 100028622510 | Pole | HFTD Tier 2 | Distribution | 2026-02-11 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000561 | 100028623056 | Pole | HFTD Tier 2 | Distribution | 2026-02-11 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000562 | 100028623057 | Pole | HFTD Tier 2 | Distribution | 2026-02-11 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000563 | 100028623059 | Pole | HFTD Tier 2 | Distribution | 2026-02-11 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000564 | 100028623438 | Pole | HFTD Tier 2 | Distribution | 2026-02-11 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000565 | 100028624275 | Other | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000566 | 100028624532 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000567 | 100028625840 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000568 | 100028625842 | Pole | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000569 | 100028625843 | Cross Arm | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000570 | 100028626179 | Ground Wire | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000571 | 100028626260 | Cross Arm | HFTD Tier 2 | Distribution | 2026-02-12 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000572 | 100028626261 | Pole | HFTD Tier 2 | Distribution | 2026-02-12 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000573 | 100028626426 | Other | HFTD Tier 2 | Distribution | 2026-02-12 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000574 | 100028628319 | Sign | HFTD Tier 3 | Distribution | 2026-02-13 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000575 | 100028629014 | Pole | HFTD Tier 3 | Distribution | 2026-02-13 | 2026-08-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000576 | 100028629017 | Other | HFTD Tier 2 | Distribution | 2026-02-13 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000577 | 100028633461 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000578 | 100028633941 | Other | HFTD Tier 2 | Distribution | 2026-02-17 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000579 | 100028637891 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000580 | 100028637892 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000581 | 100028637893 | Other | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000582 | 100028638033 | Other | HFTD Tier 2 | Distribution | 2026-02-18 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000583 | 100028639656 | Other | HFTD Tier 3 | Distribution | 2026-02-19 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000584 | 100028639781 | Other | HFTD Tier 2 | Distribution | 2026-02-19 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000585 | 100028640546 | Other | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000586 | 100028640549 | Other | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000587 | 100028640590 | Other | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000588 | 100028640591 | Other | HFTD Tier 2 | Distribution | 2026-02-19 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000589 | 100028641478 | Pole | HFTD Tier 3 | Distribution | 2026-02-20 | 2026-08-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000590 | 100028641591 | Other | HFTD Tier 3 | Distribution | 2026-02-20 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000591 | 100028641592 | Other | HFTD Tier 3 | Distribution | 2026-02-20 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000592 | 100028641593 | Other | HFTD Tier 3 | Distribution | 2026-02-20 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000593 | 100028642526 | Pole | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000594 | 100028642527 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000595 | 100028643071 | Other | HFTD Tier 2 | Distribution | 2026-02-20 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000596 | 100028662696 | Pole | HFTD Tier 3 | Distribution | 2026-02-23 | 2026-08-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000597 | 100028663116 | Pole | HFTD Tier 2 | Distribution | 2026-02-23 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000598 | 100028663225 | Sign | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000599 | 100028663226 | Conduit | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000600 | 100028663288 | Avian Protection | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000601 | 100028663472 | Cross Arm | HFTD Tier 2 | Distribution | 2026-02-23 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000602 | 100028665059 | Pole | HFTD Tier 2 | Distribution | 2026-02-23 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000603 | 100028665330 | Sign | HFTD Tier 2 | Distribution | 2026-02-23 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000604 | 100028665331 | Pole | HFTD Tier 2 | Distribution | 2026-02-23 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000605 | 100028676216 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-02-24 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000606 | 100028677407 | Pole | HFTD Tier 2 | Distribution | 2026-02-24 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000607 | 100028677951 | Other | HFTD Tier 3 | Distribution | 2026-02-24 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000608 | 100028677956 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-02-24 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000609 | 100028681600 | Pole | HFTD Tier 3 | Distribution | 2026-02-25 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000610 | 100028681656 | Pole | HFTD Tier 3 | Distribution | 2026-02-25 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000611 | 100028683154 | Other | HFTD Tier 2 | Distribution | 2026-02-25 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000612 | 100028683155 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000613 | 100028683156 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000614 | 100028684012 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000615 | 100028684155 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000616 | 100028684156 | Other | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000617 | 100028685256 | Pole | HFTD Tier 2 | Distribution | 2026-02-25 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000618 | 100028686892 | Avian Protection | HFTD Tier 2 | Distribution | 2026-02-26 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000619 | 100028686894 | Other | HFTD Tier 2 | Distribution | 2026-02-26 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000620 | 100028687794 | Pole | HFTD Tier 2 | Distribution | 2026-02-26 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000621 | 100028688283 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-02-26 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000622 | 100028688284 | Other | HFTD Tier 2 | Distribution | 2026-02-26 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000623 | 100028689887 | Avian Protection | HFTD Tier 3 | Distribution | 2026-02-27 | 2031-04-28 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000624 | 100028690531 | Pole | HFTD Tier 3 | Distribution | 2026-02-27 | 2026-08-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000625 | 100028690826 | Pole | HFTD Tier 2 | Distribution | 2026-02-27 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000626 | 100028691272 | Pole | HFTD Tier 2 | Distribution | 2026-02-27 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000627 | 100028691274 | Pole | HFTD Tier 2 | Distribution | 2026-02-27 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000628 | 100028707173 | Pole | HFTD Tier 3 | Distribution | 2026-02-27 | 2026-08-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000629 | 100028707298 | Avian Protection | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000630 | 100028707533 | Pole | HFTD Tier 2 | Distribution | 2026-03-02 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000631 | 100028707534 | Avian Protection | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000632 | 100028707535 | Avian Protection | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000633 | 100028707537 | Other | HFTD Tier 3 | Distribution | 2026-03-02 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000634 | 100028707666 | Pole | HFTD Tier 2 | Distribution | 2026-03-02 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000635 | 100028708132 | Ground Wire | HFTD Tier 3 | Distribution | 2026-03-02 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000636 | 100028708133 | Pole | HFTD Tier 3 | Distribution | 2026-03-02 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000637 | 100028708134 | Conduit | HFTD Tier 3 | Distribution | 2026-03-02 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000638 | 100028708135 | Sign | HFTD Tier 3 | Distribution | 2026-03-02 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000639 | 100028708136 | Avian Protection | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000640 | 100028708191 | Avian Protection | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000641 | 100028708731 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-03-02 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000642 | 100028710229 | Avian Protection | HFTD Tier 2 | Distribution | 2026-03-02 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000643 | 100028710271 | Pole | HFTD Tier 3 | Distribution | 2026-03-02 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000644 | 100028710272 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-03-02 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000645 | 100028711207 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000646 | 100028711216 | Pole | HFTD Tier 2 | Distribution | 2026-03-03 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000647 | 100028711289 | Other | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000648 | 100028711308 | Other | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000649 | 100028711309 | Other | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000650 | 100028711312 | Sign | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000651 | 100028711384 | Other | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000652 | 100028711437 | Other | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000653 | 100028712913 | Other | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000654 | 100028712914 | Other | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000655 | 100028712915 | Other | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000656 | 100028713026 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000657 | 100028713027 | Other | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000658 | 100028713028 | Other | HFTD Tier 2 | Distribution | 2026-03-03 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000659 | 100028714379 | Other | HFTD Tier 2 | Distribution | 2026-03-04 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000660 | 100028714401 | Pole | HFTD Tier 2 | Distribution | 2026-03-04 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000661 | 100028714504 | Cross Arm | HFTD Tier 2 | Distribution | 2026-03-04 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000662 | 100028715534 | Other | HFTD Tier 2 | Distribution | 2026-03-04 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000663 | 100028715798 | Ground Wire | HFTD Tier 2 | Distribution | 2026-03-04 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000664 | 100028716632 | Other | HFTD Tier 2 | Distribution | 2026-03-04 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000665 | 100028716633 | Pole | HFTD Tier 2 | Distribution | 2026-03-04 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000666 | 100028717319 | Pole | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000667 | 100028717360 | Cross Arm | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000668 | 100028717644 | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000669 | 100028717645 | Pole | HFTD Tier 3 | Distribution | 2026-03-05 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000670 | 100028718018 | Cross Arm | HFTD Tier 3 | Distribution | 2026-03-05 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000671 | 100028719302 | Other | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000672 | 100028719303 | Other | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000673 | 100028719304 | Other | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000674 | 100028719322 | Sign | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000675 | 100028719323 | Pole | HFTD Tier 2 | Distribution | 2026-03-05 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000676 | 100028719329 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000677 | 100028719462 | Other | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000678 | 100028719708 | Pole | HFTD Tier 2 | Distribution | 2026-03-05 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000679 | 100028719757 | Pole | HFTD Tier 2 | Distribution | 2026-03-05 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000680 | 100028719875 | Ground Wire | HFTD Tier 2 | Distribution | 2026-03-05 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000681 | 100028720559 | Other | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000682 | 100028720564 | Other | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000683 | 100028720582 | Other | HFTD Tier 3 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000684 | 100028720583 | Sign | HFTD Tier 3 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000685 | 100028720584 | Pole | HFTD Tier 3 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000686 | 100028720732 | Pole | HFTD Tier 2 | Distribution | 2026-03-06 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000687 | 100028720770 | Pole | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000688 | 100028720771 | Other | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000689 | 100028720892 | Ground Wire | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000690 | 100028720893 | Sign | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000691 | 100028720969 | Other | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000692 | 100028721136 | Cross Arm | HFTD Tier 2 | Distribution | 2026-03-06 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000693 | 100028721313 | Other | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000694 | 100028721717 | Sign | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000695 | 100028722286 | Sign | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000696 | 100028722287 | Other | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000697 | 100028722288 | Bolt | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000698 | 100028722289 | Other | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000699 | 100028722390 | Other | HFTD Tier 2 | Distribution | 2026-03-06 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000700 | 100028722394 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-03-06 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000701 | 100028723548 | Other | HFTD Tier 3 | Distribution | 2026-03-09 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000702 | 100028723719 | Transformer | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000703 | 100028723746 | Sign | HFTD Tier 3 | Distribution | 2026-03-09 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000704 | 100028723747 | Sign | HFTD Tier 3 | Distribution | 2026-03-09 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000705 | 100028723748 | Conduit | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000706 | 100028723965 | Anchor/Guy | HFTD Tier 3 | Distribution | 2026-03-09 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000707 | 100028723966 | Sign | HFTD Tier 3 | Distribution | 2026-03-09 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000708 | 100028723967 | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000709 | 100028724057 | Ground Wire | HFTD Tier 3 | Distribution | 2026-03-09 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000710 | 100028724096 | Cross Arm | HFTD Tier 3 | Distribution | 2026-03-09 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000711 | 100028724296 | Sign | HFTD Tier 3 | Distribution | 2026-03-09 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000712 | 100028725436 | Pole | HFTD Tier 2 | Distribution | 2026-03-09 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000713 | 100028725876 | Other | HFTD Tier 2 | Distribution | 2026-03-09 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000714 | 100028727507 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-03-09 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000715 | 100028727508 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-03-09 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000716 | 100028727509 | Pole | HFTD Tier 3 | Distribution | 2026-03-09 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000717 | 100028727600 | Sign | HFTD Tier 3 | Distribution | 2026-03-09 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000718 | 100028728676 | Sign | HFTD Tier 3 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000719 | 100028728728 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000720 | 100028728729 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000721 | 100028728740 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000722 | 100028728741 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000723 | 100028728742 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000724 | 100028728743 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000725 | 100028728744 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000726 | 100028728745 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000727 | 100028728746 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000728 | 100028728747 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000729 | 100028728748 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000730 | 100028728749 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000731 | 100028728750 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000732 | 100028728751 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000733 | 100028729836 | Cross Arm | HFTD Tier 2 | Distribution | 2026-03-10 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000734 | 100028730671 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000735 | 100028730672 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000736 | 100028730943 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000737 | 100028730990 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000738 | 100028730991 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000739 | 100028730992 | Pole | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000740 | 100028732418 | Pole | HFTD Tier 3 | Distribution | 2026-03-11 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000741 | 100028732550 | Other | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000742 | 100028732551 | Other | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000743 | 100028732552 | Other | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000744 | 100028732807 | Other | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000745 | 100028732808 | Other | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000746 | 100028732809 | Other | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000747 | 100028732850 | Other | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000748 | 100028732855 | Pole | HFTD Tier 2 | Distribution | 2026-03-11 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000749 | 100028733516 | Ground Wire | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000750 | 100028733518 | Pole | HFTD Tier 2 | Distribution | 2026-03-11 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000751 | 100028733519 | Ground Wire | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000752 | 100028733531 | Pole | HFTD Tier 2 | Distribution | 2026-03-11 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000753 | 100028733706 | Pole | HFTD Tier 2 | Distribution | 2026-03-11 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000754 | 100028733710 | Pole | HFTD Tier 2 | Distribution | 2026-03-11 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000755 | 100028733711 | Cross Arm | HFTD Tier 2 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000756 | 100028733713 | Other | HFTD Tier 3 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000757 | 100028733714 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000758 | 100028733715 | Pole | HFTD Tier 3 | Distribution | 2026-03-11 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000759 | 100028733716 | Sign | HFTD Tier 3 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000760 | 100028733717 | Other | HFTD Tier 3 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000761 | 100028733718 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000762 | 100028733720 | Other | HFTD Tier 3 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000763 | 100028733723 | Sign | HFTD Tier 3 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000764 | 100028733724 | Sign | HFTD Tier 3 | Distribution | 2026-03-11 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000765 | 100028735415 | Cross Arm | HFTD Tier 3 | Distribution | 2026-03-12 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000766 | 100028735685 | Pole | HFTD Tier 3 | Distribution | 2026-03-12 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000767 | 100028736203 | Sign | HFTD Tier 3 | Distribution | 2026-03-12 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000768 | 100028736322 | Pole | HFTD Tier 2 | Distribution | 2026-03-12 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000769 | 100028743714 | Pole | HFTD Tier 3 | Distribution | 2026-03-12 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000770 | 100028743715 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-03-12 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000771 | 100028743716 | Sign | HFTD Tier 3 | Distribution | 2026-03-12 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000772 | 100028743718 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-03-12 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000773 | 100028745439 | Pole | HFTD Tier 2 | Distribution | 2026-03-13 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000774 | 100028748244 | Other | HFTD Tier 3 | Distribution | 2026-03-16 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000775 | 100028748245 | Cross Arm | HFTD Tier 3 | Distribution | 2026-03-16 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000776 | 100028748695 | Other | HFTD Tier 3 | Distribution | 2026-03-16 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000777 | 100028748696 | Other | HFTD Tier 3 | Distribution | 2026-03-16 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000778 | 100028749010 | Other | HFTD Tier 3 | Distribution | 2026-03-16 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000779 | 100028749871 | Cross Arm | HFTD Tier 3 | Distribution | 2026-03-16 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000780 | 100028751091 | Cross Arm | HFTD Tier 3 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000781 | 100028751092 | Pole | HFTD Tier 3 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000782 | 100028751093 | Pole | HFTD Tier 3 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000783 | 100028751095 | Pole | HFTD Tier 3 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000784 | 100028751096 | Cross Arm | HFTD Tier 3 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000785 | 100028751097 | Pole | HFTD Tier 3 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000786 | 100028751098 | Other | HFTD Tier 3 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000787 | 100028751225 | Pole | HFTD Tier 3 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000788 | 100028751318 | Pole | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000789 | 100028751419 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000790 | 100028751420 | Ground Wire | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000791 | 100028751421 | Sign | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000792 | 100028751614 | Pole | HFTD Tier 2 | Distribution | 2026-03-17 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000793 | 100028752073 | Pole | HFTD Tier 2 | Distribution | 2026-03-17 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000794 | 100028752076 | Ground Wire | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000795 | 100028752078 | Pole | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000796 | 100028752446 | Pole | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000797 | 100028752447 | Conductor | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000798 | 100028752872 | Other | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000799 | 100028752874 | Conduit | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000800 | 100028753180 | Other | HFTD Tier 3 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000801 | 100028753181 | Pole | HFTD Tier 3 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000802 | 100028753182 | Ground Wire | HFTD Tier 3 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000803 | 100028753183 | Cross Arm | HFTD Tier 3 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000804 | 100028753511 | Other | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000805 | 100028753513 | Other | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000806 | 100028753516 | Other | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000807 | 100028753519 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000808 | 100028753520 | Other | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000809 | 100028754064 | Ground Wire | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000810 | 100028754065 | Conduit | HFTD Tier 2 | Distribution | 2026-03-17 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000811 | 100028754066 | Ground Wire | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000812 | 100028754067 | Sign | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000813 | 100028754068 | Anchor/Guy - Veg | HFTD Tier 2 | Distribution | 2026-03-17 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000814 | 100028754069 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000815 | 100028754150 | Ground Wire | HFTD Tier 2 | Distribution | 2026-03-17 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000816 | 100028754154 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2026-03-17 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000817 | 100028754155 | Pole | HFTD Tier 2 | Distribution | 2026-03-17 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000818 | 100028754794 | Pole | HFTD Tier 3 | Distribution | 2026-03-18 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000819 | 100028754795 | Pole | HFTD Tier 3 | Distribution | 2026-03-18 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000820 | 100028755107 | Cross Arm | HFTD Tier 2 | Distribution | 2026-03-18 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000821 | 100028755160 | Cross Arm | HFTD Tier 3 | Distribution | 2026-03-18 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000822 | 100028755161 | Avian Protection | HFTD Tier 3 | Distribution | 2026-03-18 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000823 | 100028755594 | Pole | HFTD Tier 2 | Distribution | 2026-03-18 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000824 | 100028755595 | Cross Arm | HFTD Tier 2 | Distribution | 2026-03-18 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000825 | 100028756013 | Other | HFTD Tier 2 | Distribution | 2026-03-18 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000826 | 100028756014 | Pole | HFTD Tier 2 | Distribution | 2026-03-18 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000827 | 100028756551 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-03-18 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000828 | 100028756657 | Transformer | HFTD Tier 2 | Distribution | 2026-03-18 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000829 | 100028756658 | Pole | HFTD Tier 3 | Distribution | 2026-03-18 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000830 | 100028756659 | Other | HFTD Tier 2 | Distribution | 2026-03-18 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000831 | 100028756894 | Pole | HFTD Tier 2 | Distribution | 2026-03-18 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000832 | 100028756895 | Conductor | HFTD Tier 2 | Distribution | 2026-03-18 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000833 | 100028756897 | Conductor | HFTD Tier 2 | Distribution | 2026-03-18 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000834 | 100028756898 | Pole | HFTD Tier 2 | Distribution | 2026-03-18 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000835 | 100028757502 | Pole | HFTD Tier 3 | Distribution | 2026-03-19 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000836 | 100028759094 | Pole | HFTD Tier 2 | Distribution | 2026-03-19 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000837 | 100028759095 | Cross Arm | HFTD Tier 2 | Distribution | 2026-03-19 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000838 | 100028759097 | Pole | HFTD Tier 2 | Distribution | 2026-03-19 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000839 | 100028759326 | Pole | HFTD Tier 2 | Distribution | 2026-03-19 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000840 | 100028759327 | Cross Arm | HFTD Tier 2 | Distribution | 2026-03-19 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000841 | 100028759329 | Ground Wire | HFTD Tier 2 | Distribution | 2026-03-19 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000842 | 100028759460 | Conductor | HFTD Tier 2 | Distribution | 2026-03-19 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000843 | 100028759461 | Other | HFTD Tier 2 | Distribution | 2026-03-19 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000844 | 100028759462 | Other | HFTD Tier 2 | Distribution | 2026-03-19 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000845 | 100028759463 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-03-19 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000846 | 100028759648 | Pole | HFTD Tier 2 | Distribution | 2026-03-19 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000847 | 100028759649 | Other | HFTD Tier 2 | Distribution | 2026-03-19 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000848 | 100028759790 | Cross Arm | HFTD Tier 2 | Distribution | 2026-03-19 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000849 | 100028759791 | Pole | HFTD Tier 2 | Distribution | 2026-03-19 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000850 | 100028759859 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-03-19 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000851 | 100028759936 | Sign | HFTD Tier 3 | Distribution | 2026-03-19 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000852 | 100028759962 | Sign | HFTD Tier 3 | Distribution | 2026-03-19 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000853 | 100028762709 | Other | HFTD Tier 2 | Distribution | 2026-03-20 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000854 | 100028762710 | Pole | HFTD Tier 2 | Distribution | 2026-03-20 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000855 | 100028763099 | Anchor/Guy - Veg | HFTD Tier 2 | Distribution | 2026-03-20 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000856 | 100028763111 | Conductor | HFTD Tier 2 | Distribution | 2026-03-20 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000857 | 100028763447 | Pole | HFTD Tier 2 | Distribution | 2026-03-20 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000858 | 100028764089 | Other | HFTD Tier 2 | Distribution | 2026-03-20 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000859 | 100028764280 | Other | HFTD Tier 2 | Distribution | 2026-03-20 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000860 | 100028764281 | Other | HFTD Tier 2 | Distribution | 2026-03-20 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000861 | 100028765550 | Sign | HFTD Tier 3 | Distribution | 2026-03-23 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000862 | 100028765551 | Sign | HFTD Tier 3 | Distribution | 2026-03-23 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000863 | 100028765587 | Pole | HFTD Tier 3 | Distribution | 2026-03-23 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000864 | 100028765599 | Sign | HFTD Tier 3 | Distribution | 2026-03-23 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000865 | 100028766923 | Other | HFTD Tier 2 | Distribution | 2026-03-23 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000866 | 100028766924 | Pole | HFTD Tier 2 | Distribution | 2026-03-23 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000867 | 100028766944 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-03-23 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000868 | 100028766945 | Other | HFTD Tier 2 | Distribution | 2026-03-23 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000869 | 100028767076 | Ground Wire | HFTD Tier 3 | Distribution | 2026-03-23 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000870 | 100028767078 | Pole | HFTD Tier 3 | Distribution | 2026-03-23 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000871 | 100028767079 | Conductor | HFTD Tier 3 | Distribution | 2026-03-23 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000872 | 100028767130 | Pole | HFTD Tier 3 | Distribution | 2026-03-23 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000873 | 100028767131 | Pole | HFTD Tier 3 | Distribution | 2026-03-23 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000874 | 100028767134 | Pole | HFTD Tier 3 | Distribution | 2026-03-23 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000875 | 100028767136 | Guy | HFTD Tier 3 | Distribution | 2026-03-23 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000876 | 100028770449 | Sign | HFTD Tier 3 | Distribution | 2026-03-24 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000877 | 100028770470 | Pole | HFTD Tier 3 | Distribution | 2026-03-24 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000878 | 100028771610 | Sign | HFTD Tier 2 | Distribution | 2026-03-24 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000879 | 100028771614 | Conductor | HFTD Tier 2 | Distribution | 2026-03-24 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000880 | 100028772969 | Ground Wire | HFTD Tier 2 | Distribution | 2026-03-24 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000881 | 100028773572 | Other | HFTD Tier 2 | Distribution | 2026-03-24 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000882 | 100028773573 | Pole | HFTD Tier 2 | Distribution | 2026-03-24 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000883 | 100028773574 | Sign | HFTD Tier 2 | Distribution | 2026-03-24 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000884 | 100028773575 | Pole | HFTD Tier 2 | Distribution | 2026-03-24 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000885 | 100028773576 | Conductor | HFTD Tier 2 | Distribution | 2026-03-24 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000886 | 100028773577 | Pole | HFTD Tier 2 | Distribution | 2026-03-24 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000887 | 100028773578 | Cross Arm | HFTD Tier 2 | Distribution | 2026-03-24 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000888 | 100028773761 | Guy | HFTD Tier 2 | Distribution | 2026-03-24 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000889 | 100028773967 | Pole | HFTD Tier 3 | Distribution | 2026-03-24 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000890 | 100028773968 | Pole | HFTD Tier 3 | Distribution | 2026-03-24 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000891 | 100028774440 | Other | HFTD Tier 2 | Distribution | 2026-03-24 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000892 | 100028774443 | Pole | HFTD Tier 2 | Distribution | 2026-03-24 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000893 | 100028774446 | Other | HFTD Tier 2 | Distribution | 2026-03-24 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000894 | 100028793294 | Other | HFTD Tier 3 | Distribution | 2026-03-25 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000895 | 100028793295 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-03-25 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000896 | 100028794040 | Pole | HFTD Tier 2 | Distribution | 2026-03-25 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000897 | 100028794423 | Pole | HFTD Tier 2 | Distribution | 2026-03-25 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000898 | 100028794424 | Other | HFTD Tier 2 | Distribution | 2026-03-25 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000899 | 100028794425 | Other | HFTD Tier 2 | Distribution | 2026-03-25 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000900 | 100028794426 | Other | HFTD Tier 2 | Distribution | 2026-03-25 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000901 | 100028794460 | Other | HFTD Tier 2 | Distribution | 2026-03-25 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000902 | 100028794757 | Pole | HFTD Tier 2 | Distribution | 2026-03-25 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000903 | 100028794758 | Sign | HFTD Tier 2 | Distribution | 2026-03-25 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000904 | 100028794759 | Sign | HFTD Tier 2 | Distribution | 2026-03-25 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000905 | 100028795095 | Pole | HFTD Tier 2 | Distribution | 2026-03-25 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000906 | 100028795096 | Ground Wire | HFTD Tier 2 | Distribution | 2026-03-25 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000907 | 100028795345 | Pole | HFTD Tier 2 | Distribution | 2026-03-25 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000908 | 100028795347 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-03-25 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000909 | 100028795444 | Cross Arm | HFTD Tier 2 | Distribution | 2026-03-25 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000910 | 100028795445 | Sign | HFTD Tier 2 | Distribution | 2026-03-25 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000911 | 100028806345 | Pole | HFTD Tier 2 | Distribution | 2026-03-26 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000912 | 100028806346 | Ground Wire | HFTD Tier 2 | Distribution | 2026-03-26 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000913 | 100028806347 | Pole | HFTD Tier 2 | Distribution | 2026-03-26 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000914 | 100028807419 | Pole | HFTD Tier 2 | Distribution | 2026-03-26 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000915 | 100028807476 | Ground Wire | HFTD Tier 2 | Distribution | 2026-03-26 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000916 | 100028807500 | Other | HFTD Tier 2 | Distribution | 2026-03-26 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000917 | 100028807501 | Other | HFTD Tier 2 | Distribution | 2026-03-26 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000918 | 100028807504 | Pole | HFTD Tier 2 | Distribution | 2026-03-26 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000919 | 100028807505 | Sign | HFTD Tier 2 | Distribution | 2026-03-26 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000920 | 100028807506 | Pole | HFTD Tier 2 | Distribution | 2026-03-26 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000921 | 100028807508 | Sign | HFTD Tier 2 | Distribution | 2026-03-26 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000922 | 100028807540 | Sign | HFTD Tier 2 | Distribution | 2026-03-26 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000923 | 100028808091 | Sign | HFTD Tier 2 | Distribution | 2026-03-25 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000924 | 100028808095 | Cross Arm | HFTD Tier 2 | Distribution | 2026-03-25 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000925 | 100028808253 | Other | HFTD Tier 2 | Distribution | 2026-03-27 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000926 | 100028808255 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-03-27 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000927 | 100028808312 | Other | HFTD Tier 2 | Distribution | 2026-03-27 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000928 | 100028808313 | Other | HFTD Tier 2 | Distribution | 2026-03-27 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000929 | 100028808727 | Other | HFTD Tier 3 | Distribution | 2026-03-27 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000930 | 100028809661 | Pole | HFTD Tier 2 | Distribution | 2026-03-26 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000931 | 100028810288 | Ground Wire | HFTD Tier 3 | Distribution | 2026-03-27 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000932 | 100028810289 | Sign | HFTD Tier 3 | Distribution | 2026-03-27 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000933 | 100028810386 | Pole | HFTD Tier 2 | Distribution | 2026-03-27 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000934 | 100028810387 | Sign | HFTD Tier 3 | Distribution | 2026-03-27 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000935 | 100028810388 | Sign | HFTD Tier 3 | Distribution | 2026-03-27 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000936 | 100028810553 | Sign | HFTD Tier 2 | Distribution | 2026-03-27 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000937 | 100028810554 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-03-27 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000938 | 100028810555 | Transformer | HFTD Tier 2 | Distribution | 2026-03-27 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000939 | 100028810584 | Other | HFTD Tier 2 | Distribution | 2026-03-27 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000940 | 100028810997 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-03-27 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000941 | 100028810999 | Sign | HFTD Tier 2 | Distribution | 2026-03-27 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000942 | 100028817071 | Pole | HFTD Tier 2 | Distribution | 2026-03-31 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000943 | 100028817072 | Pole | HFTD Tier 2 | Distribution | 2026-03-31 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000944 | 100028817073 | Pole | HFTD Tier 2 | Distribution | 2026-03-31 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000945 | 100028817670 | Cross Arm | HFTD Tier 3 | Distribution | 2026-03-20 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000946 | 100028818269 | Other | HFTD Tier 3 | Distribution | 2026-03-31 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000947 | 100028818330 | Sign | HFTD Tier 3 | Distribution | 2026-03-31 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000948 | 100028818401 | Pole | HFTD Tier 2 | Distribution | 2026-03-31 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000949 | 100028831521 | Pole | HFTD Tier 3 | Distribution | 2026-03-31 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000950 | 100028831522 | Pole | HFTD Tier 3 | Distribution | 2026-03-31 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000951 | 100028831702 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000952 | 100028831703 | Pole | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000953 | 100028831704 | Cross Arm | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000954 | 100028831705 | Sign | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000955 | 100028831706 | Sign | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000956 | 100028831707 | Transformer | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000957 | 100028831841 | Transformer | HFTD Tier 2 | Distribution | 2026-04-01 | 2027-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000958 | 100028831972 | Pole | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000959 | 100028831973 | Sign | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000960 | 100028832444 | Sign | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000961 | 100028832445 | Sign | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000962 | 100028832446 | Guy | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000963 | 100028832510 | Other | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000964 | 100028832511 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-04-01 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000965 | 100028832512 | Other | HFTD Tier 3 | Distribution | 2026-04-01 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000966 | 100028832534 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-04-01 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000967 | 100028833133 | Pole | HFTD Tier 2 | Distribution | 2026-04-02 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000968 | 100028833134 | Other | HFTD Tier 2 | Distribution | 2026-04-02 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000969 | 100028833136 | Pole | HFTD Tier 2 | Distribution | 2026-04-02 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000970 | 100028833512 | Pole | HFTD Tier 3 | Distribution | 2026-04-01 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000971 | 100028833513 | Pole | HFTD Tier 2 | Distribution | 2026-04-02 | 2027-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000972 | 100028833536 | Other | HFTD Tier 2 | Distribution | 2026-04-02 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000973 | 100028833576 | Other | HFTD Tier 2 | Distribution | 2026-04-02 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000974 | 100028833887 | Cross Arm | HFTD Tier 3 | Distribution | 2026-04-02 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000975 | 100028833888 | Other | HFTD Tier 3 | Distribution | 2026-04-02 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000976 | 100028833889 | Other | HFTD Tier 3 | Distribution | 2026-04-02 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000977 | 100028834483 | Other | HFTD Tier 2 | Distribution | 2026-04-02 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000978 | 100028834764 | Cross Arm | HFTD Tier 3 | Distribution | 2026-04-02 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000979 | 100028834765 | Pole | HFTD Tier 3 | Distribution | 2026-04-02 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000980 | 100028834766 | Sign | HFTD Tier 3 | Distribution | 2026-04-02 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000981 | 100028834767 | Pole | HFTD Tier 3 | Distribution | 2026-04-02 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000982 | 100028834768 | Conductor | HFTD Tier 3 | Distribution | 2026-04-02 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000983 | 100028834801 | Sign | HFTD Tier 3 | Distribution | 2026-04-02 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000984 | 100028835473 | Other | HFTD Tier 2 | Distribution | 2026-04-03 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000985 | 100028836414 | Anchor/Guy - Veg | HFTD Tier 3 | Distribution | 2026-04-03 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000986 | 100028836415 | Pole | HFTD Tier 3 | Distribution | 2026-04-03 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000987 | 100028836416 | Cross Arm | HFTD Tier 3 | Distribution | 2026-04-03 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000988 | 100028836417 | Pole | HFTD Tier 3 | Distribution | 2026-04-03 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000989 | 100028836657 | Pole | HFTD Tier 3 | Distribution | 2026-04-03 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000990 | 100028836660 | Pole | HFTD Tier 3 | Distribution | 2026-04-03 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000991 | 100028836974 | Sign | HFTD Tier 3 | Distribution | 2026-04-03 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000992 | 100028836978 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-04-03 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000993 | 100028836981 | Pole | HFTD Tier 3 | Distribution | 2026-04-03 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000994 | 100028836982 | Cross Arm | HFTD Tier 3 | Distribution | 2026-04-03 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000995 | 100028838446 | Cross Arm | HFTD Tier 2 | Distribution | 2026-04-06 | 2027-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120000996 | 100028838504 | Other | HFTD Tier 2 | Distribution | 2026-04-06 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000997 | 100028838505 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-04-06 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000998 | 100028838506 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-04-06 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120000999 | 100028838817 | Conductor | HFTD Tier 3 | Distribution | 2026-04-06 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001000 | 100028839684 | Sign | HFTD Tier 2 | Distribution | 2026-04-06 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001001 | 100028839685 | Sign | HFTD Tier 2 | Distribution | 2026-04-06 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001002 | 100028839686 | Sign | HFTD Tier 2 | Distribution | 2026-04-06 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001003 | 100028840062 | Other | HFTD Tier 3 | Distribution | 2026-04-06 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001004 | 100028840063 | Sign | HFTD Tier 3 | Distribution | 2026-04-06 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001005 | 100028842074 | Pole | HFTD Tier 3 | Distribution | 2026-04-07 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001006 | 100028842075 | Pole | HFTD Tier 3 | Distribution | 2026-04-07 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001007 | 100028842076 | Cross Arm | HFTD Tier 3 | Distribution | 2026-04-07 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001008 | 100028842813 | Pole | HFTD Tier 2 | Distribution | 2026-04-07 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001009 | 100028842819 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001010 | 100028842920 | Sign | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001011 | 100028842924 | Other | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001012 | 100028842925 | Other | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001013 | 100028842926 | Other | HFTD Tier 2 | Distribution | 2026-04-07 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001014 | 100028842972 | Guy | HFTD Tier 3 | Distribution | 2026-04-07 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001015 | 100028842974 | Pole | HFTD Tier 3 | Distribution | 2026-04-07 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001016 | 100028843238 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001017 | 100028843239 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2031-05-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001018 | 100028843451 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001019 | 100028843452 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001020 | 100028843453 | Other | HFTD Tier 2 | Distribution | 2026-03-10 | 2027-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001021 | 100028843975 | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2027-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001022 | 100028844413 | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001023 | 100028844880 | Sign | HFTD Tier 3 | Distribution | 2026-04-08 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001024 | 100028845293 | Other | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001025 | 100028845459 | Other | HFTD Tier 2 | Distribution | 2026-04-08 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001026 | 100028845563 | Pole | HFTD Tier 3 | Distribution | 2026-04-08 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001027 | 100028845564 | Cross Arm | HFTD Tier 3 | Distribution | 2026-04-08 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001028 | 100028845568 | Pole | HFTD Tier 3 | Distribution | 2026-04-08 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001029 | 100028847930 | Other | HFTD Tier 3 | Distribution | 2026-04-09 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001030 | 100028847931 | Other | HFTD Tier 3 | Distribution | 2026-04-09 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001031 | 100028847933 | Other | HFTD Tier 3 | Distribution | 2026-04-09 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001032 | 100028847934 | Other | HFTD Tier 3 | Distribution | 2026-04-09 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001033 | 100028847937 | Other | HFTD Tier 3 | Distribution | 2026-04-09 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001034 | 100028847938 | Other | HFTD Tier 3 | Distribution | 2026-04-09 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001035 | 100028848958 | Other | HFTD Tier 2 | Distribution | 2026-04-10 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001036 | 100028849064 | Pole | HFTD Tier 2 | Distribution | 2026-04-08 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001037 | 100028849915 | Ground Wire | HFTD Tier 3 | Distribution | 2026-04-10 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001038 | 100028849916 | Pole | HFTD Tier 3 | Distribution | 2026-04-10 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001039 | 100028849919 | Sign | HFTD Tier 3 | Distribution | 2026-04-10 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001040 | 100028849920 | Sign | HFTD Tier 3 | Distribution | 2026-04-10 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001041 | 100028849921 | Sign | HFTD Tier 3 | Distribution | 2026-04-10 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001042 | 100028850710 | Pole | HFTD Tier 3 | Distribution | 2026-04-10 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001043 | 100028850711 | Pole | HFTD Tier 3 | Distribution | 2026-04-10 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001044 | 100028850872 | Sign | HFTD Tier 3 | Distribution | 2026-04-10 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001045 | 100028850873 | Pole | HFTD Tier 3 | Distribution | 2026-04-10 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001046 | 100028850875 | Other | HFTD Tier 3 | Distribution | 2026-04-10 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001047 | 100028850914 | Sign | HFTD Tier 3 | Distribution | 2026-04-10 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001048 | 100028850915 | Sign | HFTD Tier 3 | Distribution | 2026-04-10 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001049 | 100028850917 | Sign | HFTD Tier 3 | Distribution | 2026-04-10 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001050 | 100028851004 | Cross Arm | HFTD Tier 3 | Distribution | 2026-04-10 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001051 | 100028851116 | Pole | HFTD Tier 3 | Distribution | 2026-04-10 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001052 | 100028852370 | Pole | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001053 | 100028852371 | Other | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001054 | 100028852373 | Other | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001055 | 100028852920 | Conductor | HFTD Tier 3 | Distribution | 2026-04-13 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001056 | 100028853523 | Cross Arm | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001057 | 100028853524 | Pole | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001058 | 100028853525 | Pole | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001059 | 100028853527 | Pole | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001060 | 100028853996 | Pole | HFTD Tier 3 | Distribution | 2026-04-13 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001061 | 100028853997 | Pole | HFTD Tier 3 | Distribution | 2026-04-13 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001062 | 100028853998 | Pole | HFTD Tier 3 | Distribution | 2026-04-13 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001063 | 100028853999 | Pole | HFTD Tier 3 | Distribution | 2026-04-13 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001064 | 100028854795 | Other | HFTD Tier 2 | Distribution | 2026-04-13 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001065 | 100028854888 | Pole | HFTD Tier 3 | Distribution | 2026-04-13 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001066 | 100028854889 | Sign | HFTD Tier 3 | Distribution | 2026-04-13 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001067 | 100028854910 | Pole | HFTD Tier 3 | Distribution | 2026-04-13 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001068 | 100028854911 | Pole | HFTD Tier 3 | Distribution | 2026-04-13 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001069 | 100028857922 | Conductor | HFTD Tier 3 | Distribution | 2026-04-14 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001070 | 100028857923 | Pole | HFTD Tier 3 | Distribution | 2026-04-14 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001071 | 100028857924 | Pole | HFTD Tier 3 | Distribution | 2026-04-14 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001072 | 100028857925 | Pole | HFTD Tier 3 | Distribution | 2026-04-14 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001073 | 100028857926 | Anchor/Guy | HFTD Tier 3 | Distribution | 2026-04-14 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001074 | 100028857927 | Pole | HFTD Tier 3 | Distribution | 2026-04-14 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001075 | 100028861785 | Other | HFTD Tier 2 | Distribution | 2026-04-15 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001076 | 100028861787 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001077 | 100028861790 | Other | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001078 | 100028862217 | Pole | HFTD Tier 3 | Distribution | 2026-04-15 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001079 | 100028862218 | Sign | HFTD Tier 3 | Distribution | 2026-04-15 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001080 | 100028862458 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-04-15 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001081 | 100028864572 | Other | HFTD Tier 2 | Distribution | 2026-04-16 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001082 | 100028864574 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-04-16 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001083 | 100028864579 | Pole | HFTD Tier 3 | Distribution | 2026-04-16 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001084 | 100028864581 | Sign | HFTD Tier 3 | Distribution | 2026-04-16 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001085 | 100028865311 | Sign | HFTD Tier 3 | Distribution | 2026-04-16 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001086 | 100028865840 | Pole | HFTD Tier 3 | Distribution | 2026-04-16 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001087 | 100028866132 | Other | HFTD Tier 3 | Distribution | 2026-04-16 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001088 | 100028866134 | Sign | HFTD Tier 3 | Distribution | 2026-04-16 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001089 | 100028866135 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-04-16 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001090 | 100028868014 | Cross Arm | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001091 | 100028869383 | Other | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001092 | 100028869706 | Sign | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001093 | 100028869707 | Sign | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001094 | 100028869708 | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001095 | 100028869709 | Cross Arm | HFTD Tier 2 | Distribution | 2026-04-17 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001096 | 100028869710 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001097 | 100028869711 | Cross Arm | HFTD Tier 2 | Distribution | 2026-04-17 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001098 | 100028870159 | Pole | HFTD Tier 2 | Distribution | 2026-04-17 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001099 | 100028874769 | Other | HFTD Tier 2 | Distribution | 2026-04-20 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001100 | 100028875711 | Sign | HFTD Tier 3 | Distribution | 2026-04-20 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001101 | 100028875713 | Sign | HFTD Tier 3 | Distribution | 2026-04-20 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001102 | 100028875714 | Other | HFTD Tier 3 | Distribution | 2026-04-20 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001103 | 100028875716 | Other | HFTD Tier 3 | Distribution | 2026-04-20 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001104 | 100028875717 | Sign | HFTD Tier 3 | Distribution | 2026-04-20 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001105 | 100028875730 | Sign | HFTD Tier 3 | Distribution | 2026-04-20 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001106 | 100028875731 | Sign | HFTD Tier 3 | Distribution | 2026-04-20 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001107 | 100028875732 | Anchor/Guy | HFTD Tier 3 | Distribution | 2026-04-20 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001108 | 100028875775 | Other | HFTD Tier 3 | Distribution | 2026-04-20 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001109 | 100028875776 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-04-20 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001110 | 100028875777 | Anchor/Guy | HFTD Tier 3 | Distribution | 2026-04-20 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001111 | 100028875778 | Other | HFTD Tier 3 | Distribution | 2026-04-20 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001112 | 100028875779 | Cross Arm | HFTD Tier 3 | Distribution | 2026-04-20 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001113 | 100028876930 | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001114 | 100028876931 | Pole | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001115 | 100028876932 | Other | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001116 | 100028878073 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001117 | 100028878074 | Other | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001118 | 100028878075 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001119 | 100028878077 | Other | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001120 | 100028878079 | Other | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001121 | 100028878082 | Ground Wire | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001122 | 100028878724 | Cross Arm | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001123 | 100028878726 | Ground Wire | HFTD Tier 2 | Distribution | 2026-04-21 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001124 | 100028879126 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-04-21 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001125 | 100028880699 | Cross Arm | HFTD Tier 2 | Distribution | 2026-04-22 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001126 | 100028881026 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001127 | 100028881109 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001128 | 100028881160 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001129 | 100028881161 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001130 | 100028881162 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001131 | 100028881163 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001132 | 100028881320 | Pole | HFTD Tier 3 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001133 | 100028881323 | Sign | HFTD Tier 3 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001134 | 100028881394 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001135 | 100028881395 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001136 | 100028881396 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001137 | 100028881397 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001138 | 100028881398 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001139 | 100028881401 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001140 | 100028881406 | Pole | HFTD Tier 2 | Distribution | 2026-04-22 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001141 | 100028881410 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001142 | 100028881411 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001143 | 100028881448 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001144 | 100028881449 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001145 | 100028881610 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001146 | 100028881611 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001147 | 100028881612 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001148 | 100028881613 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001149 | 100028881615 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001150 | 100028881616 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001151 | 100028881715 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001152 | 100028881717 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001153 | 100028881718 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001154 | 100028881719 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001155 | 100028881720 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001156 | 100028881721 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001157 | 100028881723 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001158 | 100028881725 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001159 | 100028881822 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001160 | 100028881823 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001161 | 100028881824 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001162 | 100028881825 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001163 | 100028881827 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001164 | 100028881828 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001165 | 100028881829 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001166 | 100028881830 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001167 | 100028881831 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001168 | 100028881832 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001169 | 100028881887 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001170 | 100028881888 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001171 | 100028881889 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001172 | 100028881898 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001173 | 100028881900 | Other | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001174 | 100028881905 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001175 | 100028881906 | Avian Protection | HFTD Tier 2 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001176 | 100028882042 | Conductor - Veg | HFTD Tier 3 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001177 | 100028882043 | Pole | HFTD Tier 3 | Distribution | 2026-04-22 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001178 | 100028882047 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-04-22 | 2027-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001179 | 100028882537 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-04-22 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001180 | 100028884106 | Other | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001181 | 100028884293 | Sign | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001182 | 100028884367 | Sign | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001183 | 100028884467 | Other | HFTD Tier 3 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001184 | 100028884693 | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001185 | 100028884694 | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001186 | 100028884848 | Ground Wire | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001187 | 100028885423 | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001188 | 100028885424 | Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001189 | 100028885425 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001190 | 100028885429 | Other | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001191 | 100028885430 | Guy | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001192 | 100028885431 | Ground Wire | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001193 | 100028885981 | Pole | HFTD Tier 3 | Distribution | 2026-04-23 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001194 | 100028885983 | Sign | HFTD Tier 3 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001195 | 100028885984 | Pole | HFTD Tier 3 | Distribution | 2026-04-23 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001196 | 100028885988 | Guy | HFTD Tier 3 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001197 | 100028885989 | Sign | HFTD Tier 3 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001198 | 100028886030 | Ground Wire | HFTD Tier 3 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001199 | 100028886031 | Sign | HFTD Tier 3 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001200 | 100028886032 | Sign | HFTD Tier 3 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001201 | 100028886191 | Ground Wire | HFTD Tier 2 | Distribution | 2026-04-23 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001202 | 100028889638 | Other | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001203 | 100028889727 | Other | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001204 | 100028889788 | Other | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001205 | 100028890129 | Other | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001206 | 100028890182 | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001207 | 100028890183 | Other | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001208 | 100028890744 | Other | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001209 | 100028890745 | Ground Wire | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001210 | 100028890746 | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2027-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001211 | 100028890747 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001212 | 100028890748 | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2027-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001213 | 100028891935 | Guy | HFTD Tier 3 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001214 | 100028891936 | Guy | HFTD Tier 3 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001215 | 100028891937 | Ground Wire | HFTD Tier 3 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001216 | 100028891938 | Other | HFTD Tier 3 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001217 | 100028891966 | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001218 | 100028891967 | Cross Arm | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001219 | 100028891969 | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001220 | 100028891990 | Pole | HFTD Tier 3 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001221 | 100028891991 | Anchor/Guy | HFTD Tier 3 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001222 | 100028891992 | Sign | HFTD Tier 3 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001223 | 100028892050 | Other | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001224 | 100028892051 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-04-24 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001225 | 100028892052 | Pole | HFTD Tier 2 | Distribution | 2026-04-24 | 2027-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001226 | 100028911978 | Sign | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001227 | 100028912342 | Other | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001228 | 100028912343 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001229 | 100028912344 | Other | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001230 | 100028912752 | Pole | HFTD Tier 3 | Distribution | 2026-04-27 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001231 | 100028912925 | Conduit | HFTD Tier 3 | Distribution | 2026-04-27 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001232 | 100028912927 | Other | HFTD Tier 3 | Distribution | 2026-04-27 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001233 | 100028913170 | Other | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001234 | 100028913171 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-04-27 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001235 | 100028915274 | Conductor | HFTD Tier 3 | Distribution | 2026-04-28 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001236 | 100028915463 | Other | HFTD Tier 2 | Distribution | 2026-04-14 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001237 | 100028915657 | Cross Arm | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001238 | 100028915659 | Ground Wire | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001239 | 100028916758 | Other | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001240 | 100028917302 | Pole | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001241 | 100028917304 | Conductor | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001242 | 100028917305 | Conductor | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001243 | 100028917748 | Pole | HFTD Tier 2 | Distribution | 2026-04-28 | 2027-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001244 | 100028917749 | Pole | HFTD Tier 2 | Distribution | 2026-04-28 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001245 | 100028919308 | Other | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001246 | 100028919574 | Other | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001247 | 100028920679 | Other | HFTD Tier 3 | Distribution | 2026-04-29 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001248 | 100028920770 | Other | HFTD Tier 3 | Distribution | 2026-04-29 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001249 | 100028920771 | Other | HFTD Tier 3 | Distribution | 2026-04-29 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001250 | 100028920772 | Other | HFTD Tier 3 | Distribution | 2026-04-29 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001251 | 100028921795 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-04-29 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001252 | 100028921797 | Other | HFTD Tier 3 | Distribution | 2026-04-29 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001253 | 100028921811 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001254 | 100028924310 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2026-04-29 | 2027-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001255 | 100028924311 | Pole | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001256 | 100028924472 | Other | HFTD Tier 3 | Distribution | 2026-04-30 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001257 | 100028924473 | Sign | HFTD Tier 3 | Distribution | 2026-04-30 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001258 | 100028924552 | Other | HFTD Tier 2 | Distribution | 2026-04-30 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001259 | 100028924553 | Other | HFTD Tier 2 | Distribution | 2026-04-30 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001260 | 100028924637 | Other | HFTD Tier 3 | Distribution | 2026-04-30 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001261 | 100028925120 | Other | HFTD Tier 3 | Distribution | 2026-04-30 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001262 | 100028925661 | Sign | HFTD Tier 3 | Distribution | 2026-04-30 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001263 | 100028940130 | Other | HFTD Tier 2 | Distribution | 2026-04-29 | 2031-06-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001264 | 100028940724 | Pole | HFTD Tier 3 | Distribution | 2026-05-01 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001265 | 100028940729 | Conductor - Veg | HFTD Tier 3 | Distribution | 2026-05-01 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001266 | 100028940751 | Other | HFTD Tier 3 | Distribution | 2026-05-01 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001267 | 100028942034 | Other | HFTD Tier 2 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001268 | 100028942035 | Other | HFTD Tier 2 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001269 | 100028942217 | Other | HFTD Tier 2 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001270 | 100028942218 | Other | HFTD Tier 2 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001271 | 100028942688 | Sign | HFTD Tier 2 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001272 | 100028942689 | Connector | HFTD Tier 2 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001273 | 100028942710 | Other | HFTD Tier 2 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001274 | 100028944674 | Pole | HFTD Tier 3 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001275 | 100028944678 | Pole | HFTD Tier 3 | Distribution | 2026-05-04 | 2026-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001276 | 100028944679 | Other | HFTD Tier 3 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001277 | 100028944711 | Cross Arm | HFTD Tier 3 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001278 | 100028944713 | Pole | HFTD Tier 3 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001279 | 100028944714 | Cross Arm | HFTD Tier 3 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001280 | 100028944715 | Other | HFTD Tier 3 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001281 | 100028944716 | Other | HFTD Tier 3 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001282 | 100028944717 | Other | HFTD Tier 3 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001283 | 100028944718 | Pole | HFTD Tier 3 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001284 | 100028944720 | Pole | HFTD Tier 3 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001285 | 100028944721 | Cross Arm | HFTD Tier 3 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001286 | 100028944722 | Anchor/Guy | HFTD Tier 3 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001287 | 100028945300 | Sign | HFTD Tier 3 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001288 | 100028945301 | Sign | HFTD Tier 3 | Distribution | 2026-05-04 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001289 | 100028945886 | Pole | HFTD Tier 2 | Distribution | 2026-05-05 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001290 | 100028947367 | Pole | HFTD Tier 2 | Distribution | 2026-05-05 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001291 | 100028947368 | Ground Wire | HFTD Tier 2 | Distribution | 2026-05-05 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001292 | 100028947370 | Cross Arm | HFTD Tier 2 | Distribution | 2026-05-05 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001293 | 100028949260 | Avian Protection | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001294 | 100028949305 | Other | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001295 | 100028949306 | Other | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001296 | 100028950236 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001297 | 100028950272 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001298 | 100028950273 | Conduit | HFTD Tier 3 | Distribution | 2026-05-06 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001299 | 100028950274 | Other | HFTD Tier 3 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001300 | 100028950750 | Other | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001301 | 100028950751 | Pole | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001302 | 100028950752 | Cross Arm | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001303 | 100028950753 | Conductor | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001304 | 100028950755 | Pole | HFTD Tier 2 | Distribution | 2026-05-06 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001305 | 100028950756 | Other | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001306 | 100028950757 | Conductor | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001307 | 100028950760 | Other | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001308 | 100028950761 | Pole | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001309 | 100028950764 | Other | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001310 | 100028950765 | Other | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001311 | 100028950766 | Other | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001312 | 100028950767 | Other | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001313 | 100028950769 | Other | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001314 | 100028950771 | Pole | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001315 | 100028950773 | Anchor/Guy - Veg | HFTD Tier 2 | Distribution | 2026-05-06 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001316 | 100028954681 | Conductor | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001317 | 100028954914 | Pole | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001318 | 100028954915 | Cross Arm | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001319 | 100028955059 | Pole | HFTD Tier 2 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001320 | 100028955256 | Other | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001321 | 100028955257 | Other | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001322 | 100028955258 | Other | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001323 | 100028955259 | Other | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001324 | 100028955280 | Other | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001325 | 100028955281 | Other | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001326 | 100028955743 | Pole | HFTD Tier 2 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001327 | 100028957125 | Other | HFTD Tier 2 | Distribution | 2026-05-08 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001328 | 100028957324 | Conductor | HFTD Tier 2 | Distribution | 2026-05-08 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001329 | 100028957703 | Other | HFTD Tier 2 | Distribution | 2026-05-08 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001330 | 100028958143 | Other | HFTD Tier 2 | Distribution | 2026-05-08 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001331 | 100028958146 | Pole | HFTD Tier 2 | Distribution | 2026-05-08 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001332 | 100028958436 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-05-08 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001333 | 100028958437 | Conductor - Veg | HFTD Tier 3 | Distribution | 2026-05-08 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001334 | 100028958523 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-05-08 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001335 | 100028958524 | Pole | HFTD Tier 3 | Distribution | 2026-05-08 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001336 | 100028958525 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-05-08 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001337 | 100028958527 | Other | HFTD Tier 3 | Distribution | 2026-05-08 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001338 | 100028958528 | Other | HFTD Tier 3 | Distribution | 2026-05-08 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001339 | 100028958529 | Other | HFTD Tier 3 | Distribution | 2026-05-08 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001340 | 100028958531 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-05-08 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001341 | 100028958533 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-05-08 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001342 | 100028958682 | Bolt | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001343 | 100028958684 | Sign | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001344 | 100028958685 | Cross Arm | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001345 | 100028958687 | Pole | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001346 | 100028958688 | Pole | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001347 | 100028958689 | Conduit | HFTD Tier 3 | Distribution | 2026-05-07 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001348 | 100028959238 | Cross Arm | HFTD Tier 2 | Distribution | 2026-05-09 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001349 | 100028959239 | Sign | HFTD Tier 2 | Distribution | 2026-05-09 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001350 | 100028959240 | Pole | HFTD Tier 2 | Distribution | 2026-05-09 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001351 | 100028959241 | Pole | HFTD Tier 2 | Distribution | 2026-05-09 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001352 | 100028959242 | Cross Arm | HFTD Tier 2 | Distribution | 2026-05-09 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001353 | 100028959243 | Cross Arm | HFTD Tier 2 | Distribution | 2026-05-09 | 2027-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001354 | 100028959244 | Pole | HFTD Tier 2 | Distribution | 2026-05-09 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001355 | 100028959803 | Other | HFTD Tier 3 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001356 | 100028960157 | Pole | HFTD Tier 3 | Distribution | 2026-05-11 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001357 | 100028960287 | Pole | HFTD Tier 3 | Distribution | 2026-05-11 | 2026-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001358 | 100028960288 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001359 | 100028960289 | Other | HFTD Tier 3 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001360 | 100028960326 | Pole | HFTD Tier 3 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001361 | 100028960328 | Pole | HFTD Tier 3 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001362 | 100028960329 | Pole | HFTD Tier 3 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001363 | 100028960330 | Conductor | HFTD Tier 3 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001364 | 100028960331 | Anchor/Guy | HFTD Tier 3 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001365 | 100028960332 | Other | HFTD Tier 3 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001366 | 100028960333 | Pole | HFTD Tier 3 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001367 | 100028960414 | Other | HFTD Tier 3 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001368 | 100028961783 | Ground Wire | HFTD Tier 2 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001369 | 100028961784 | Pole | HFTD Tier 2 | Distribution | 2026-05-11 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001370 | 100028961785 | Cross Arm | HFTD Tier 2 | Distribution | 2026-05-11 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001371 | 100028961786 | Ground Wire | HFTD Tier 2 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001372 | 100028961787 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001373 | 100028961840 | Pole | HFTD Tier 2 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001374 | 100028961841 | Sign | HFTD Tier 2 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001375 | 100028961842 | Pole | HFTD Tier 2 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001376 | 100028961843 | Cross Arm | HFTD Tier 2 | Distribution | 2026-05-11 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001377 | 100028961848 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001378 | 100028961851 | Other | HFTD Tier 3 | Distribution | 2026-05-11 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001379 | 100028964166 | Other | HFTD Tier 2 | Distribution | 2026-05-12 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001380 | 100028964258 | Pole | HFTD Tier 3 | Distribution | 2026-05-12 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001381 | 100028964479 | Pole | HFTD Tier 3 | Distribution | 2026-05-12 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001382 | 100028964570 | Ground Wire | HFTD Tier 2 | Distribution | 2026-05-12 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001383 | 100028964572 | Pole | HFTD Tier 3 | Distribution | 2026-05-12 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001384 | 100028964573 | Other | HFTD Tier 3 | Distribution | 2026-05-12 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001385 | 100028964574 | Pole | HFTD Tier 3 | Distribution | 2026-05-12 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001386 | 100028964631 | Other | HFTD Tier 2 | Distribution | 2026-05-12 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001387 | 100028964721 | Pole | HFTD Tier 3 | Distribution | 2026-05-12 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001388 | 100028964775 | Pole | HFTD Tier 3 | Distribution | 2026-05-12 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001389 | 100028964776 | Pole | HFTD Tier 3 | Distribution | 2026-05-12 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001390 | 100028964778 | Other | HFTD Tier 2 | Distribution | 2026-05-12 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001391 | 100028964779 | Other | HFTD Tier 2 | Distribution | 2026-05-12 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001392 | 100028964857 | Other | HFTD Tier 2 | Distribution | 2026-05-12 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001393 | 100028964858 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-05-12 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001394 | 100028965060 | Pole | HFTD Tier 3 | Distribution | 2026-05-12 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001395 | 100028965061 | Other | HFTD Tier 3 | Distribution | 2026-05-12 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001396 | 100028965207 | Other | HFTD Tier 2 | Distribution | 2026-05-12 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001397 | 100028965208 | Pole | HFTD Tier 2 | Distribution | 2026-05-12 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001398 | 100028965209 | Other | HFTD Tier 2 | Distribution | 2026-05-12 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001399 | 100028965260 | Pole | HFTD Tier 2 | Distribution | 2026-05-12 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001400 | 100028965261 | Pole | HFTD Tier 2 | Distribution | 2026-05-12 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001401 | 100028965262 | Pole | HFTD Tier 2 | Distribution | 2026-05-12 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001402 | 100028966215 | Ground Wire | HFTD Tier 3 | Distribution | 2026-05-12 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001403 | 100028966219 | Sign | HFTD Tier 3 | Distribution | 2026-05-12 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001404 | 100028966310 | Cross Arm | HFTD Tier 3 | Distribution | 2026-05-12 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001405 | 100028968365 | Pole | HFTD Tier 2 | Distribution | 2026-05-13 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001406 | 100028969435 | Pole | HFTD Tier 2 | Distribution | 2026-05-13 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001407 | 100028969436 | Pole | HFTD Tier 2 | Distribution | 2026-05-13 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001408 | 100028969437 | Cross Arm | HFTD Tier 2 | Distribution | 2026-05-13 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001409 | 100028969585 | Sign | HFTD Tier 2 | Distribution | 2026-05-13 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001410 | 100028969589 | Sign | HFTD Tier 2 | Distribution | 2026-05-13 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001411 | 100028969893 | Pole | HFTD Tier 2 | Distribution | 2026-05-13 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001412 | 100028970024 | Other | HFTD Tier 2 | Distribution | 2026-05-13 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001413 | 100028970168 | Sign | HFTD Tier 3 | Distribution | 2026-05-13 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001414 | 100028970169 | Pole | HFTD Tier 3 | Distribution | 2026-05-13 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001415 | 100028970291 | Pole | HFTD Tier 3 | Distribution | 2026-05-13 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001416 | 100028970293 | Anchor/Guy | HFTD Tier 3 | Distribution | 2026-05-13 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001417 | 100028970294 | Cross Arm | HFTD Tier 3 | Distribution | 2026-05-13 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001418 | 100028970295 | Pole | HFTD Tier 3 | Distribution | 2026-05-13 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001419 | 100028973440 | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001420 | 100028973629 | Other | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001421 | 100028973871 | Fuse | HFTD Tier 3 | Distribution | 2026-05-14 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001422 | 100028974083 | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001423 | 100028974344 | Other | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001424 | 100028974345 | Other | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001425 | 100028974614 | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001426 | 100028974617 | Conductor | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001427 | 100028975057 | Sign | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001428 | 100028975153 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001429 | 100028975155 | Cross Arm | HFTD Tier 2 | Distribution | 2026-05-14 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001430 | 100028975629 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001431 | 100028975630 | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001432 | 100028975634 | Cross Arm | HFTD Tier 2 | Distribution | 2026-05-14 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001433 | 100028975635 | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001434 | 100028975636 | Pole | HFTD Tier 2 | Distribution | 2026-05-14 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001435 | 100028975640 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-05-14 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001436 | 100028975643 | Other | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001437 | 100028975645 | Other | HFTD Tier 2 | Distribution | 2026-05-14 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001438 | 100028975709 | Pole | HFTD Tier 3 | Distribution | 2026-05-06 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001439 | 100028976937 | Cross Arm | HFTD Tier 2 | Distribution | 2026-05-15 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001440 | 100028977016 | Other | HFTD Tier 3 | Distribution | 2026-05-15 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001441 | 100028977360 | Other | HFTD Tier 3 | Distribution | 2026-05-15 | 2026-08-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001442 | 100028977361 | Other | HFTD Tier 3 | Distribution | 2026-05-15 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001443 | 100028979891 | Pole | HFTD Tier 2 | Distribution | 2026-05-15 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001444 | 100028979893 | Other | HFTD Tier 2 | Distribution | 2026-05-15 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001445 | 100028980215 | Sign | HFTD Tier 3 | Distribution | 2026-05-15 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001446 | 100028980216 | Cross Arm | HFTD Tier 3 | Distribution | 2026-05-15 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001447 | 100028983213 | Other | HFTD Tier 2 | Distribution | 2026-05-18 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001448 | 100028983215 | Pole | HFTD Tier 3 | Distribution | 2026-05-18 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001449 | 100028983370 | Ground Wire | HFTD Tier 3 | Distribution | 2026-05-18 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001450 | 100028983588 | Sign | HFTD Tier 2 | Distribution | 2026-05-18 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001451 | 100028983589 | Sign | HFTD Tier 2 | Distribution | 2026-05-18 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001452 | 100028983700 | Pole | HFTD Tier 2 | Distribution | 2026-05-18 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001453 | 100028983985 | Pole | HFTD Tier 3 | Distribution | 2026-05-18 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001454 | 100028984404 | Ground Wire | HFTD Tier 3 | Distribution | 2026-05-18 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001455 | 100028984405 | Sign | HFTD Tier 3 | Distribution | 2026-05-18 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001456 | 100028984406 | Pole | HFTD Tier 2 | Distribution | 2026-05-18 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001457 | 100028984408 | Conductor - Veg | HFTD Tier 3 | Distribution | 2026-05-18 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001458 | 100028985734 | Sign | HFTD Tier 3 | Distribution | 2026-05-19 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001459 | 100028985735 | Sign | HFTD Tier 3 | Distribution | 2026-05-19 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001460 | 100028985895 | Anchor/Guy | HFTD Tier 3 | Distribution | 2026-05-19 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001461 | 100028986214 | Pole | HFTD Tier 3 | Distribution | 2026-05-19 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001462 | 100028986215 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-05-19 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001463 | 100028986216 | Sign | HFTD Tier 3 | Distribution | 2026-05-19 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001464 | 100028986217 | Pole | HFTD Tier 3 | Distribution | 2026-05-19 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001465 | 100028986218 | Pole | HFTD Tier 3 | Distribution | 2026-05-19 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001466 | 100028986220 | Pole | HFTD Tier 3 | Distribution | 2026-05-19 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001467 | 100028987798 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-05-19 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001468 | 100028987799 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-05-19 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001469 | 100028988008 | Pole | HFTD Tier 3 | Distribution | 2026-05-19 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001470 | 100028988009 | Pole | HFTD Tier 3 | Distribution | 2026-05-19 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001471 | 100028988020 | Conductor | HFTD Tier 3 | Distribution | 2026-05-19 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001472 | 100028988557 | Pole | HFTD Tier 2 | Distribution | 2026-05-19 | 2027-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001473 | 100028990047 | Other | HFTD Tier 3 | Distribution | 2026-05-20 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001474 | 100028990203 | Other | HFTD Tier 3 | Distribution | 2026-05-20 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001475 | 100028990474 | Sign | HFTD Tier 2 | Distribution | 2026-05-20 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001476 | 100028990477 | Pole | HFTD Tier 3 | Distribution | 2026-05-20 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001477 | 100028990479 | Sign | HFTD Tier 3 | Distribution | 2026-05-20 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001478 | 100028990500 | Sign | HFTD Tier 3 | Distribution | 2026-05-20 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001479 | 100028990821 | Other | HFTD Tier 3 | Distribution | 2026-05-20 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001480 | 100028990822 | Anchor/Guy | HFTD Tier 3 | Distribution | 2026-05-20 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001481 | 100028990823 | Anchor/Guy | HFTD Tier 3 | Distribution | 2026-05-20 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001482 | 100028990890 | Other | HFTD Tier 2 | Distribution | 2026-05-20 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001483 | 100028990891 | Cross Arm | HFTD Tier 2 | Distribution | 2026-05-20 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001484 | 100028990892 | Pole | HFTD Tier 2 | Distribution | 2026-05-20 | 2027-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001485 | 100028990894 | Avian Protection | HFTD Tier 2 | Distribution | 2026-05-20 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001486 | 100028990896 | Pole | HFTD Tier 2 | Distribution | 2026-05-20 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001487 | 100028990897 | Other | HFTD Tier 2 | Distribution | 2026-05-20 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001488 | 100028990898 | Other | HFTD Tier 2 | Distribution | 2026-05-20 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001489 | 100028991194 | Pole | HFTD Tier 3 | Distribution | 2026-05-20 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001490 | 100028991195 | Pole | HFTD Tier 3 | Distribution | 2026-05-20 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001491 | 100028991196 | Conductor - Veg | HFTD Tier 3 | Distribution | 2026-05-20 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001492 | 100028991596 | Sign | HFTD Tier 2 | Distribution | 2026-05-20 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001493 | 100028991597 | Sign | HFTD Tier 2 | Distribution | 2026-05-20 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001494 | 100028991599 | Pole | HFTD Tier 3 | Distribution | 2026-05-20 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001495 | 100028992532 | Ground Wire | HFTD Tier 2 | Distribution | 2026-05-21 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001496 | 100028992533 | Ground Wire | HFTD Tier 2 | Distribution | 2026-05-21 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001497 | 100028992534 | Other | HFTD Tier 2 | Distribution | 2026-05-21 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001498 | 100028992535 | Pole | HFTD Tier 2 | Distribution | 2026-05-21 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001499 | 100028993733 | Other | HFTD Tier 3 | Distribution | 2026-05-21 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001500 | 100028993734 | Other | HFTD Tier 2 | Distribution | 2026-05-21 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001501 | 100028994157 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-05-21 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001502 | 100028994158 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-05-21 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001503 | 100028994159 | Ground Wire | HFTD Tier 2 | Distribution | 2026-05-21 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001504 | 100028994160 | Pole | HFTD Tier 2 | Distribution | 2026-05-21 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001505 | 100028994315 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-05-21 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001506 | 100028994316 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-05-21 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001507 | 100028994317 | Ground Wire | HFTD Tier 2 | Distribution | 2026-05-21 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001508 | 100028994318 | Pole | HFTD Tier 2 | Distribution | 2026-05-21 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001509 | 100028995162 | Pole | HFTD Tier 2 | Distribution | 2026-05-21 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001510 | 100028995522 | Pole | HFTD Tier 2 | Distribution | 2026-05-21 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001511 | 100028995527 | Sign | HFTD Tier 2 | Distribution | 2026-05-21 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001512 | 100028995528 | Pole | HFTD Tier 2 | Distribution | 2026-05-21 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001513 | 100028995830 | Cross Arm | HFTD Tier 2 | Distribution | 2026-05-21 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001514 | 100028995831 | Ground Wire | HFTD Tier 2 | Distribution | 2026-05-21 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001515 | 100028997037 | Other | HFTD Tier 2 | Distribution | 2026-05-22 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001516 | 100028997217 | Other | HFTD Tier 2 | Distribution | 2026-05-22 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001517 | 100028997322 | Pole | HFTD Tier 2 | Distribution | 2026-05-22 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001518 | 100028998241 | Sign | HFTD Tier 3 | Distribution | 2026-05-22 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001519 | 100028998242 | Pole | HFTD Tier 3 | Distribution | 2026-05-22 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001520 | 100029027167 | Ground Wire | HFTD Tier 3 | Distribution | 2026-05-26 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001521 | 100029027611 | Other | HFTD Tier 3 | Distribution | 2026-05-26 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001522 | 100029027612 | Other | HFTD Tier 3 | Distribution | 2026-05-26 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001523 | 100029027613 | Other | HFTD Tier 3 | Distribution | 2026-05-26 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001524 | 100029027650 | Other | HFTD Tier 3 | Distribution | 2026-05-26 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001525 | 100029027838 | Pole | HFTD Tier 2 | Distribution | 2026-05-26 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001526 | 100029027912 | Other | HFTD Tier 3 | Distribution | 2026-05-26 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001527 | 100029028109 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-05-26 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001528 | 100029028300 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-05-26 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001529 | 100029028302 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-05-26 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001530 | 100029028306 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-05-26 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001531 | 100029028307 | Pole | HFTD Tier 2 | Distribution | 2026-05-26 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001532 | 100029028308 | Other | HFTD Tier 2 | Distribution | 2026-05-26 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001533 | 100029028740 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-05-26 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001534 | 100029028748 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-05-26 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001535 | 100029028858 | Pole | HFTD Tier 2 | Distribution | 2026-05-26 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001536 | 100029029122 | Pole | HFTD Tier 2 | Distribution | 2026-05-26 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001537 | 100029029123 | Pole | HFTD Tier 2 | Distribution | 2026-05-26 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001538 | 100029030619 | Other | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001539 | 100029030620 | Other | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001540 | 100029030621 | Other | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001541 | 100029030622 | Other | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001542 | 100029030769 | Ground Wire | HFTD Tier 2 | Distribution | 2026-05-27 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001543 | 100029030910 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001544 | 100029030912 | Ground Wire | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001545 | 100029030914 | Pole | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001546 | 100029030915 | Anchor/Guy - Veg | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001547 | 100029030916 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001548 | 100029030917 | Sign | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001549 | 100029030918 | Pole | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001550 | 100029030982 | Other | HFTD Tier 3 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001551 | 100029031063 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001552 | 100029031106 | Other | HFTD Tier 3 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001553 | 100029031167 | Other | HFTD Tier 3 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001554 | 100029031634 | Ground Wire | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001555 | 100029031635 | Pole | HFTD Tier 2 | Distribution | 2026-05-27 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001556 | 100029031637 | Other | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001557 | 100029031670 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001558 | 100029031671 | Pole | HFTD Tier 2 | Distribution | 2026-05-27 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001559 | 100029031672 | Pole | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001560 | 100029031673 | Other | HFTD Tier 2 | Distribution | 2026-05-27 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001561 | 100029033482 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001562 | 100029033483 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001563 | 100029033484 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001564 | 100029033485 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001565 | 100029033486 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001566 | 100029033493 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001567 | 100029033494 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001568 | 100029033495 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001569 | 100029033496 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001570 | 100029033497 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001571 | 100029033498 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001572 | 100029033499 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001573 | 100029033500 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001574 | 100029033501 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001575 | 100029033502 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001576 | 100029033503 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001577 | 100029033588 | Sign | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001578 | 100029033589 | Pole | HFTD Tier 2 | Distribution | 2026-05-28 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001579 | 100029033650 | Ground Wire | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001580 | 100029033651 | Sign | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001581 | 100029033652 | Ground Wire | HFTD Tier 2 | Distribution | 2026-05-28 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001582 | 100029033721 | Other | HFTD Tier 3 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001583 | 100029033722 | Other | HFTD Tier 3 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001584 | 100029033723 | Pole | HFTD Tier 3 | Distribution | 2026-05-28 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001585 | 100029033724 | Pole | HFTD Tier 3 | Distribution | 2026-05-28 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001586 | 100029034006 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001587 | 100029034007 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001588 | 100029034082 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001589 | 100029034083 | Pole | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001590 | 100029034179 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001591 | 100029034306 | Pole | HFTD Tier 3 | Distribution | 2026-05-28 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001592 | 100029034307 | Other | HFTD Tier 3 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001593 | 100029034400 | Pole | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001594 | 100029034401 | Other | HFTD Tier 3 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001595 | 100029034555 | Other | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001596 | 100029034876 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001597 | 100029035010 | Pole | HFTD Tier 2 | Distribution | 2026-05-28 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001598 | 100029035011 | Ground Wire | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001599 | 100029035012 | Pole | HFTD Tier 2 | Distribution | 2026-05-28 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001600 | 100029036789 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001601 | 100029037020 | Pole | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001602 | 100029037021 | Sign | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001603 | 100029037022 | Pole | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001604 | 100029037023 | Other | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001605 | 100029037024 | Other | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001606 | 100029037746 | Ground Wire | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001607 | 100029037748 | Cross Arm | HFTD Tier 2 | Distribution | 2026-05-29 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001608 | 100029037749 | Pole | HFTD Tier 2 | Distribution | 2026-05-29 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001609 | 100029037770 | Cross Arm | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001610 | 100029037771 | Pole | HFTD Tier 2 | Distribution | 2026-05-29 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001611 | 100029037772 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-05-29 | 2031-07-31 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001612 | 100029050116 | Sign | HFTD Tier 3 | Distribution | 2026-06-01 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001613 | 100029050117 | Sign | HFTD Tier 3 | Distribution | 2026-06-01 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001614 | 100029050118 | Sign | HFTD Tier 3 | Distribution | 2026-06-01 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001615 | 100029050217 | Pole | HFTD Tier 2 | Distribution | 2026-06-01 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001616 | 100029050220 | Sign | HFTD Tier 3 | Distribution | 2026-06-01 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001617 | 100029050316 | Sign | HFTD Tier 3 | Distribution | 2026-06-01 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001618 | 100029050430 | Other | HFTD Tier 2 | Distribution | 2026-06-01 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001619 | 100029050435 | Ground Wire | HFTD Tier 2 | Distribution | 2026-06-01 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001620 | 100029050436 | Other | HFTD Tier 2 | Distribution | 2026-06-01 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001621 | 100029050555 | Cross Arm | HFTD Tier 3 | Distribution | 2026-06-01 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001622 | 100029050793 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-01 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001623 | 100029050864 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-01 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001624 | 100029052112 | Other | HFTD Tier 3 | Distribution | 2026-06-01 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001625 | 100029052113 | Other | HFTD Tier 3 | Distribution | 2026-06-01 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001626 | 100029052114 | Other | HFTD Tier 3 | Distribution | 2026-06-01 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001627 | 100029052115 | Other | HFTD Tier 3 | Distribution | 2026-06-01 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001628 | 100029052116 | Other | HFTD Tier 3 | Distribution | 2026-06-01 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001629 | 100029052117 | Other | HFTD Tier 3 | Distribution | 2026-06-01 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001630 | 100029052118 | Other | HFTD Tier 3 | Distribution | 2026-06-01 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001631 | 100029053144 | Cross Arm | HFTD Tier 2 | Distribution | 2026-06-01 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001632 | 100029053585 | Conductor | HFTD Tier 2 | Distribution | 2026-06-02 | 2027-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001633 | 100029053586 | Other | HFTD Tier 2 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001634 | 100029053587 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001635 | 100029053588 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001636 | 100029053685 | Other | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001637 | 100029053686 | Sign | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001638 | 100029053688 | Other | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001639 | 100029053863 | Other | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001640 | 100029053864 | Other | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001641 | 100029053865 | Pole | HFTD Tier 3 | Distribution | 2026-06-02 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001642 | 100029053866 | Transformer | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001643 | 100029053867 | Transformer | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001644 | 100029054034 | Other | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001645 | 100029054194 | Pole | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001646 | 100029054195 | Conductor - Veg | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001647 | 100029054197 | Pole | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001648 | 100029054198 | Pole | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001649 | 100029054240 | Pole | HFTD Tier 3 | Distribution | 2026-06-02 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001650 | 100029055314 | Pole | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001651 | 100029055315 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001652 | 100029055316 | Pole | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001653 | 100029055317 | Ground Wire | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001654 | 100029055318 | Ground Wire | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001655 | 100029055319 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001656 | 100029055320 | Conductor - Veg | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001657 | 100029055321 | Anchor/Guy | HFTD Tier 2 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001658 | 100029055322 | Sign | HFTD Tier 2 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001659 | 100029055393 | Pole | HFTD Tier 3 | Distribution | 2026-06-02 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001660 | 100029055394 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001661 | 100029055395 | Other | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001662 | 100029055396 | Conductor - Veg | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001663 | 100029055397 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001664 | 100029055398 | Conductor - Veg | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001665 | 100029055399 | Pole | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001666 | 100029055400 | Other | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001667 | 100029055401 | Other | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001668 | 100029055402 | Pole | HFTD Tier 3 | Distribution | 2026-06-02 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001669 | 100029055869 | Pole | HFTD Tier 2 | Distribution | 2026-06-02 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001670 | 100029056634 | Pole | HFTD Tier 2 | Distribution | 2026-06-03 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001671 | 100029056635 | Pole | HFTD Tier 2 | Distribution | 2026-06-03 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001672 | 100029056714 | Pole | HFTD Tier 2 | Distribution | 2026-06-03 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001673 | 100029056715 | Pole | HFTD Tier 2 | Distribution | 2026-06-03 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001674 | 100029056716 | Pole | HFTD Tier 2 | Distribution | 2026-06-03 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001675 | 100029056717 | Transformer | HFTD Tier 2 | Distribution | 2026-06-03 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001676 | 100029056726 | Pole | HFTD Tier 3 | Distribution | 2026-06-03 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001677 | 100029056749 | Conductor | HFTD Tier 2 | Distribution | 2026-06-03 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001678 | 100029056751 | Pole | HFTD Tier 2 | Distribution | 2026-06-03 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001679 | 100029056754 | Other | HFTD Tier 3 | Distribution | 2026-06-03 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001680 | 100029056755 | Sign | HFTD Tier 3 | Distribution | 2026-06-03 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001681 | 100029057101 | Pole | HFTD Tier 2 | Distribution | 2026-06-03 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001682 | 100029057126 | Other | HFTD Tier 3 | Distribution | 2026-06-03 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001683 | 100029057259 | Pole | HFTD Tier 2 | Distribution | 2026-06-03 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001684 | 100029057357 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-03 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001685 | 100029057358 | Conduit | HFTD Tier 2 | Distribution | 2026-06-03 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001686 | 100029057359 | Ground Wire | HFTD Tier 2 | Distribution | 2026-06-03 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001687 | 100029057522 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-03 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001688 | 100029057523 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-03 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001689 | 100029057525 | Pole | HFTD Tier 2 | Distribution | 2026-06-03 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001690 | 100029057928 | Pole | HFTD Tier 2 | Distribution | 2026-06-03 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001691 | 100029057980 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-03 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001692 | 100029058161 | Pole | HFTD Tier 3 | Distribution | 2026-06-03 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001693 | 100029059167 | Other | HFTD Tier 3 | Distribution | 2026-06-04 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001694 | 100029059323 | Ground Wire | HFTD Tier 3 | Distribution | 2026-06-04 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001695 | 100029059487 | Pole | HFTD Tier 2 | Distribution | 2026-06-04 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001696 | 100029059488 | Other | HFTD Tier 2 | Distribution | 2026-06-04 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001697 | 100029059489 | Conductor | HFTD Tier 2 | Distribution | 2026-06-04 | 2027-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001698 | 100029059563 | Other | HFTD Tier 2 | Distribution | 2026-06-04 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001699 | 100029059860 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-04 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001700 | 100029059861 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-06-04 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001701 | 100029059862 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-06-04 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001702 | 100029059863 | Ground Wire | HFTD Tier 2 | Distribution | 2026-06-04 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001703 | 100029059864 | Other | HFTD Tier 2 | Distribution | 2026-06-04 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001704 | 100029059865 | Ground Wire | HFTD Tier 2 | Distribution | 2026-06-04 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001705 | 100029059910 | Other | HFTD Tier 3 | Distribution | 2026-06-04 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001706 | 100029059952 | Guy | HFTD Tier 2 | Distribution | 2026-06-04 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001707 | 100029059960 | Other | HFTD Tier 3 | Distribution | 2026-06-04 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001708 | 100029060093 | Conductor | HFTD Tier 2 | Distribution | 2026-06-04 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001709 | 100029062709 | Ground Wire | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001710 | 100029062731 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001711 | 100029062732 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001712 | 100029062733 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001713 | 100029062734 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001714 | 100029063111 | Conductor | HFTD Tier 3 | Distribution | 2026-06-05 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001715 | 100029063410 | Ground Wire | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001716 | 100029063801 | Other | HFTD Tier 2 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001717 | 100029064281 | Other | HFTD Tier 2 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001718 | 100029064942 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001719 | 100029064943 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001720 | 100029064944 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001721 | 100029064945 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001722 | 100029064946 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001723 | 100029064947 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001724 | 100029064948 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001725 | 100029064949 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001726 | 100029064950 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001727 | 100029064951 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001728 | 100029064952 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001729 | 100029064953 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001730 | 100029064954 | Other | HFTD Tier 3 | Distribution | 2026-06-05 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001731 | 100029066640 | Ground Wire | HFTD Tier 3 | Distribution | 2026-06-08 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001732 | 100029066973 | Other | HFTD Tier 2 | Distribution | 2026-06-08 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001733 | 100029066974 | Pole | HFTD Tier 2 | Distribution | 2026-06-08 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001734 | 100029066975 | Pole | HFTD Tier 2 | Distribution | 2026-06-08 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001735 | 100029066976 | Transformer | HFTD Tier 2 | Distribution | 2026-06-08 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001736 | 100029067167 | Pole | HFTD Tier 2 | Distribution | 2026-06-08 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001737 | 100029067168 | Pole | HFTD Tier 2 | Distribution | 2026-06-08 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001738 | 100029067169 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-08 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001739 | 100029067201 | Other | HFTD Tier 2 | Distribution | 2026-06-08 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001740 | 100029067202 | Other | HFTD Tier 2 | Distribution | 2026-06-08 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001741 | 100029067203 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-08 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001742 | 100029067204 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-08 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001743 | 100029067542 | Sign | HFTD Tier 3 | Distribution | 2026-06-08 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001744 | 100029067643 | Other | HFTD Tier 2 | Distribution | 2026-06-08 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001745 | 100029068543 | Other | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001746 | 100029068612 | Other | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001747 | 100029068627 | Ground Wire | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001748 | 100029068811 | Ground Wire | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001749 | 100029068812 | Other | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001750 | 100029068903 | Ground Wire | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001751 | 100029068924 | Ground Wire | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001752 | 100029068925 | Ground Wire | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001753 | 100029069179 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001754 | 100029069220 | Pole | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001755 | 100029069596 | Pole | HFTD Tier 2 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001756 | 100029069597 | Conduit | HFTD Tier 2 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001757 | 100029069598 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001758 | 100029069599 | Ground Wire | HFTD Tier 2 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001759 | 100029069650 | Pole | HFTD Tier 2 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001760 | 100029069652 | Other | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001761 | 100029069654 | Ground Wire | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001762 | 100029069655 | Other | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001763 | 100029069656 | Conductor | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001764 | 100029069658 | Other | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001765 | 100029069815 | Cross Arm | HFTD Tier 3 | Distribution | 2026-06-09 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001766 | 100029070037 | Pole | HFTD Tier 2 | Distribution | 2026-06-09 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001767 | 100029070038 | Cross Arm | HFTD Tier 2 | Distribution | 2026-06-09 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001768 | 100029070039 | Pole | HFTD Tier 3 | Distribution | 2026-06-09 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001769 | 100029070061 | Sign | HFTD Tier 2 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001770 | 100029070068 | Other | HFTD Tier 2 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001771 | 100029070069 | Other | HFTD Tier 2 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001772 | 100029070070 | Other | HFTD Tier 2 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001773 | 100029070071 | Other | HFTD Tier 2 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001774 | 100029070072 | Other | HFTD Tier 2 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001775 | 100029070073 | Conductor - Veg | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001776 | 100029070074 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001777 | 100029070075 | Anchor/Guy - Veg | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001778 | 100029070076 | Pole | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001779 | 100029070077 | Anchor/Guy - Veg | HFTD Tier 3 | Distribution | 2026-06-09 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001780 | 100029072081 | Other | HFTD Tier 3 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001781 | 100029072109 | Other | HFTD Tier 3 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001782 | 100029072309 | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001783 | 100029072345 | Cross Arm | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001784 | 100029072346 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001785 | 100029072347 | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001786 | 100029072348 | Transformer | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001787 | 100029073271 | Other | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001788 | 100029073272 | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001789 | 100029073274 | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001790 | 100029073275 | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001791 | 100029073288 | Sign | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001792 | 100029073289 | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001793 | 100029074148 | Pole | HFTD Tier 3 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001794 | 100029074149 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001795 | 100029074170 | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001796 | 100029074192 | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001797 | 100029074193 | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001798 | 100029074195 | Transformer | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001799 | 100029074240 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001800 | 100029074241 | Other | HFTD Tier 3 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001801 | 100029074242 | Pole | HFTD Tier 3 | Distribution | 2026-06-10 | 2026-12-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001802 | 100029075110 | Other | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001803 | 100029075111 | Sign | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001804 | 100029075112 | Ground Wire | HFTD Tier 2 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001805 | 100029075113 | Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001806 | 100029075114 | Ground Wire | HFTD Tier 3 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001807 | 100029075115 | Sign | HFTD Tier 3 | Distribution | 2026-06-10 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001808 | 100029076488 | Pole | HFTD Tier 2 | Distribution | 2026-06-11 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001809 | 100029076723 | Conductor - Veg | HFTD Tier 3 | Distribution | 2026-06-11 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001810 | 100029076934 | Other | HFTD Tier 3 | Distribution | 2026-06-11 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001811 | 100029077376 | Sign | HFTD Tier 2 | Distribution | 2026-06-11 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001812 | 100029077379 | Sign | HFTD Tier 2 | Distribution | 2026-06-11 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001813 | 100029077403 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-11 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001814 | 100029077404 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-11 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001815 | 100029077553 | Other | HFTD Tier 3 | Distribution | 2026-06-11 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001816 | 100029077932 | Conduit | HFTD Tier 3 | Distribution | 2026-06-11 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001817 | 100029077933 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-11 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001818 | 100029077934 | Other | HFTD Tier 3 | Distribution | 2026-06-11 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001819 | 100029077936 | Other | HFTD Tier 3 | Distribution | 2026-06-11 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001820 | 100029078897 | Ground Wire | HFTD Tier 2 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001821 | 100029078898 | Ground Wire | HFTD Tier 2 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001822 | 100029078899 | Cross Arm | HFTD Tier 2 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001823 | 100029079040 | Ground Wire | HFTD Tier 2 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001824 | 100029079041 | Transformer | HFTD Tier 2 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001825 | 100029079461 | Pole | HFTD Tier 3 | Distribution | 2026-06-12 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001826 | 100029079464 | Other | HFTD Tier 3 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001827 | 100029079479 | Other | HFTD Tier 3 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001828 | 100029079490 | Other | HFTD Tier 3 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001829 | 100029079491 | Other | HFTD Tier 3 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001830 | 100029079509 | Other | HFTD Tier 2 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001831 | 100029079545 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001832 | 100029079785 | Pole | HFTD Tier 3 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001833 | 100029079786 | Ground Wire | HFTD Tier 3 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001834 | 100029080209 | Sign | HFTD Tier 2 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001835 | 100029080295 | Pole | HFTD Tier 2 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001836 | 100029080296 | Pole | HFTD Tier 2 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001837 | 100029080298 | Other | HFTD Tier 3 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001838 | 100029080299 | Other | HFTD Tier 3 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001839 | 100029080317 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001840 | 100029080318 | Cross Arm | HFTD Tier 3 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001841 | 100029080350 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001842 | 100029080351 | Other | HFTD Tier 3 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001843 | 100029080352 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001844 | 100029080510 | Other | HFTD Tier 3 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001845 | 100029080620 | Pole | HFTD Tier 3 | Distribution | 2026-06-12 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001846 | 100029080626 | Pole | HFTD Tier 2 | Distribution | 2026-06-12 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001847 | 100029082193 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-06-15 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001848 | 100029083348 | Sign | HFTD Tier 2 | Distribution | 2026-06-15 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001849 | 100029083349 | Pole | HFTD Tier 2 | Distribution | 2026-06-15 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001850 | 100029087176 | Conductor | HFTD Tier 3 | Distribution | 2026-06-16 | 2027-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001851 | 100029087177 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-16 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001852 | 100029087178 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-16 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001853 | 100029087179 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-16 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001854 | 100029087183 | Cross Arm | HFTD Tier 2 | Distribution | 2026-06-16 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001855 | 100029087184 | Pole | HFTD Tier 2 | Distribution | 2026-06-16 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001856 | 100029087185 | Cross Arm | HFTD Tier 2 | Distribution | 2026-06-16 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001857 | 100029087320 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-16 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001858 | 100029087506 | Pole | HFTD Tier 3 | Distribution | 2026-06-16 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001859 | 100029087507 | Pole | HFTD Tier 3 | Distribution | 2026-06-16 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001860 | 100029088165 | Sign | HFTD Tier 2 | Distribution | 2026-06-16 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001861 | 100029088166 | Ground Wire | HFTD Tier 2 | Distribution | 2026-06-16 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001862 | 100029090021 | Cross Arm | HFTD Tier 2 | Distribution | 2026-06-17 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001863 | 100029090022 | Pole | HFTD Tier 2 | Distribution | 2026-06-17 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001864 | 100029090251 | Conductor | HFTD Tier 2 | Distribution | 2026-06-17 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001865 | 100029090252 | Other | HFTD Tier 2 | Distribution | 2026-06-17 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001866 | 100029090253 | Anchor/Guy - Veg | HFTD Tier 2 | Distribution | 2026-06-17 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001867 | 100029090254 | Pole | HFTD Tier 2 | Distribution | 2026-06-17 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001868 | 100029090285 | Pole | HFTD Tier 2 | Distribution | 2026-06-17 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001869 | 100029090286 | Cross Arm | HFTD Tier 2 | Distribution | 2026-06-17 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001870 | 100029090316 | Other | HFTD Tier 2 | Distribution | 2026-06-17 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001871 | 100029090433 | Pole | HFTD Tier 2 | Distribution | 2026-06-17 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001872 | 100029090700 | Pole | HFTD Tier 2 | Distribution | 2026-06-17 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001873 | 100029090701 | Pole | HFTD Tier 2 | Distribution | 2026-06-17 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001874 | 100029090702 | Pole | HFTD Tier 2 | Distribution | 2026-06-17 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001875 | 100029092888 | Other | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001876 | 100029093682 | Other | HFTD Tier 3 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001877 | 100029093718 | Pole | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001878 | 100029093822 | Pole | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001879 | 100029093823 | Pole | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001880 | 100029093825 | Pole | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001881 | 100029093827 | Ground Wire | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001882 | 100029093828 | Pole | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001883 | 100029093829 | Other | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001884 | 100029093911 | Pole | HFTD Tier 3 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001885 | 100029093912 | Pole | HFTD Tier 3 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001886 | 100029093913 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001887 | 100029093914 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001888 | 100029093915 | Pole | HFTD Tier 3 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001889 | 100029094040 | Conduit | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001890 | 100029094042 | Other | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001891 | 100029094043 | Ground Wire | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001892 | 100029094044 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001893 | 100029094045 | Pole | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001894 | 100029094046 | Other | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001895 | 100029094047 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001896 | 100029094048 | Anchor/Guy - Veg | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001897 | 100029094049 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001898 | 100029094050 | Other | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001899 | 100029094051 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001900 | 100029094783 | Sign | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001901 | 100029094802 | Pole | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001902 | 100029094804 | Sign | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001903 | 100029094805 | Sign | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001904 | 100029094806 | Pole | HFTD Tier 2 | Distribution | 2026-06-18 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001905 | 100029097150 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-19 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001906 | 100029097152 | Pole | HFTD Tier 2 | Distribution | 2026-06-19 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001907 | 100029097371 | Other | HFTD Tier 2 | Distribution | 2026-06-19 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001908 | 100029097372 | Other | HFTD Tier 2 | Distribution | 2026-06-19 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001909 | 100029097375 | Ground Wire | HFTD Tier 2 | Distribution | 2026-06-19 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001910 | 100029097808 | Pole | HFTD Tier 2 | Distribution | 2026-06-19 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001911 | 100029097809 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-19 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001912 | 100029097843 | Pole | HFTD Tier 2 | Distribution | 2026-06-19 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001913 | 100029097844 | Cross Arm | HFTD Tier 2 | Distribution | 2026-06-19 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001914 | 100029098010 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-19 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001915 | 100029098011 | Pole | HFTD Tier 2 | Distribution | 2026-06-19 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001916 | 100029098012 | Pole | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001917 | 100029098013 | Pole | HFTD Tier 2 | Distribution | 2026-06-19 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001918 | 100029098069 | Sign | HFTD Tier 2 | Distribution | 2026-06-19 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001919 | 100029098100 | Ground Wire | HFTD Tier 2 | Distribution | 2026-06-19 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001920 | 100029098101 | Sign | HFTD Tier 2 | Distribution | 2026-06-19 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001921 | 100029101675 | Pole | HFTD Tier 2 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001922 | 100029101676 | Ground Wire | HFTD Tier 2 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001923 | 100029101677 | Sign | HFTD Tier 2 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001924 | 100029104197 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001925 | 100029104198 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001926 | 100029104261 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001927 | 100029104262 | Other | HFTD Tier 2 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001928 | 100029104264 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001929 | 100029104265 | Anchor/Guy - Veg | HFTD Tier 2 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001930 | 100029104267 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001931 | 100029104269 | Other | HFTD Tier 3 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001932 | 100029104281 | Other | HFTD Tier 3 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001933 | 100029104282 | Other | HFTD Tier 3 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001934 | 100029104283 | Pole - Veg | HFTD Tier 3 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001935 | 100029104284 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001936 | 100029104286 | Other | HFTD Tier 2 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001937 | 100029104287 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-22 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001938 | 100029106265 | Sign | HFTD Tier 2 | Distribution | 2026-06-23 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001939 | 100029106523 | Pole | HFTD Tier 2 | Distribution | 2026-06-23 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001940 | 100029106526 | Pole | HFTD Tier 2 | Distribution | 2026-06-23 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001941 | 100029106585 | Conductor - Veg | HFTD Tier 2 | Distribution | 2026-06-23 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001942 | 100029106586 | Other | HFTD Tier 2 | Distribution | 2026-06-23 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001943 | 100029106587 | Cross Arm | HFTD Tier 2 | Distribution | 2026-06-23 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001944 | 100029106740 | Pole | HFTD Tier 2 | Distribution | 2026-06-23 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001945 | 100029106869 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-23 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001946 | 100029107360 | Conduit | HFTD Tier 2 | Distribution | 2026-06-23 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001947 | 100029107361 | Conduit | HFTD Tier 2 | Distribution | 2026-06-23 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001948 | 100029107362 | Pole | HFTD Tier 2 | Distribution | 2026-06-23 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001949 | 100029107670 | Pole | HFTD Tier 2 | Distribution | 2026-06-23 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001950 | 100029107671 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-23 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001951 | 100029107672 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-23 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001952 | 100029113169 | Conductor | HFTD Tier 2 | Distribution | 2026-06-24 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001953 | 100029113226 | Other | HFTD Tier 2 | Distribution | 2026-06-24 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001954 | 100029113460 | Pole - Veg | HFTD Tier 2 | Distribution | 2026-06-24 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001955 | 100029113461 | Other | HFTD Tier 2 | Distribution | 2026-06-24 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001956 | 100029113697 | Pole | HFTD Tier 3 | Distribution | 2026-06-24 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001957 | 100029114115 | Other | HFTD Tier 2 | Distribution | 2026-06-24 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001958 | 100029117341 | Other | HFTD Tier 3 | Distribution | 2026-06-19 | 2026-12-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001959 | 100029126367 | Other | HFTD Tier 2 | Distribution | 2026-06-24 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001960 | 100029128806 | Conduit | HFTD Tier 2 | Distribution | 2026-06-25 | 2031-08-30 | Level 3 | [8 empty] | SDG&E | 2026 | 2
1120001961 | 100029140588 | Pole | HFTD Tier 2 | Distribution | 2026-06-26 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001962 | 100029178194 | Wood Pole | Non-HFTD | Distribution | 2026-06-24 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001963 | 100028527637 | Pole | Non-HFTD | Distribution | 2026-01-09 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001964 | 100029106501 | Wood Pole | Non-HFTD | Distribution | 2026-06-08 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001965 | 100028948855 | Wood Pole | Non-HFTD | Distribution | 2026-04-07 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001966 | 100028596999 | Pole | Non-HFTD | Distribution | 2026-01-15 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001967 | 100028584651 | Pole | Non-HFTD | Distribution | 2026-01-13 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001968 | 100028717039 | Pole | Non-HFTD | Distribution | 2026-01-26 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001969 | 100028707845 | Wood Pole | HFTD Tier 2 | Distribution | 2026-02-24 | 2027-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001970 | 100029085873 | Wood Pole | Non-HFTD | Distribution | 2026-06-01 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001971 | 100029106506 | Wood Pole | Non-HFTD | Distribution | 2026-06-09 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001972 | 100028729475 | Wood Pole | HFTD Tier 2 | Distribution | 2026-03-05 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001973 | 100029178195 | Wood Pole | Non-HFTD | Distribution | 2026-06-24 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001974 | 100029106503 | Wood Pole | Non-HFTD | Distribution | 2026-06-10 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001975 | 100029160690 | Wood Pole | Non-HFTD | Distribution | 2026-06-16 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001976 | 100028597011 | Pole | Non-HFTD | Distribution | 2026-01-26 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001977 | 100028527636 | Pole | Non-HFTD | Distribution | 2026-01-08 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001978 | 100029106508 | Wood Pole | HFTD Tier 2 | Distribution | 2026-06-10 | 2027-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001979 | 100028584650 | Pole | Non-HFTD | Distribution | 2026-01-16 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001980 | 100029193789 | Wood Pole | Non-HFTD | Distribution | 2026-07-02 | 2029-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001981 | 100028747324 | Wood Pole | Non-HFTD | Distribution | 2026-03-03 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001982 | 100028948854 | Wood Pole | HFTD Tier 2 | Distribution | 2026-04-20 | 2027-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001983 | 100029106504 | Wood Pole | Non-HFTD | Distribution | 2026-06-08 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001984 | 100028969076 | Wood Pole | Non-HFTD | Distribution | 2026-04-27 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001985 | 100029106507 | Wood Pole | Non-HFTD | Distribution | 2026-06-11 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001986 | 100028877086 | Wood Pole | Non-HFTD | Distribution | 2026-04-08 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001987 | 100028707844 | Wood Pole | Non-HFTD | Distribution | 2026-02-18 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001988 | 100029029569 | Wood Pole | Non-HFTD | Distribution | 2026-05-15 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001989 | 100028992347 | Wood Pole | Non-HFTD | Distribution | 2026-05-08 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001990 | 100028948808 | Wood Pole | HFTD Tier 2 | Distribution | 2026-04-23 | 2027-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001991 | 100028965721 | Wood Pole | Non-HFTD | Distribution | 2026-04-30 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001992 | 100029068900 | Wood Pole | Non-HFTD | Distribution | 2026-05-27 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001993 | 100028747323 | Wood Pole | Non-HFTD | Distribution | 2026-03-03 | 2029-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001994 | 100029178154 | Wood Pole | Non-HFTD | Distribution | 2026-06-24 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001995 | 100028527638 | Pole | Non-HFTD | Distribution | 2026-01-09 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001996 | 100029056089 | Wood Pole | Non-HFTD | Distribution | 2026-05-18 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001997 | 100028951912 | Wood Pole | Non-HFTD | Distribution | 2026-05-06 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001998 | 100028527635 | Pole | Non-HFTD | Distribution | 2026-01-07 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120001999 | 100028584653 | Pole | Non-HFTD | Distribution | 2026-01-13 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002000 | 100028969320 | Wood Pole | Non-HFTD | Distribution | 2026-04-21 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002001 | 100028880231 | Wood Pole | Non-HFTD | Distribution | 2026-04-15 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002002 | 100029159875 | Wood Pole | Non-HFTD | Distribution | 2026-06-17 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002003 | 100029029568 | Wood Pole | Non-HFTD | Distribution | 2026-05-11 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002004 | 100029055947 | Wood Pole | Non-HFTD | Distribution | 2026-05-19 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002005 | 100028877085 | Wood Pole | Non-HFTD | Distribution | 2026-04-09 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002006 | 100028597010 | Pole | Non-HFTD | Distribution | 2026-01-20 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002007 | 100028992271 | Wood Pole | Non-HFTD | Distribution | 2026-05-05 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002008 | 100029029250 | Wood Pole | Non-HFTD | Distribution | 2026-05-22 | 2029-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002009 | 100028717040 | Pole | Non-HFTD | Distribution | 2026-02-05 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002010 | 100029106416 | Wood Pole | Non-HFTD | Distribution | 2026-06-17 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002011 | 100029106502 | Wood Pole | Non-HFTD | Distribution | 2026-06-10 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002012 | 100029178153 | Wood Pole | Non-HFTD | Distribution | 2026-06-24 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002013 | 100029085874 | Wood Pole | Non-HFTD | Distribution | 2026-06-03 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002014 | 100028969189 | Wood Pole | Non-HFTD | Distribution | 2026-04-23 | 2029-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002015 | 100029106505 | Wood Pole | Non-HFTD | Distribution | 2026-06-12 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002016 | 100028729474 | Wood Pole | HFTD Tier 2 | Distribution | 2026-03-05 | 2027-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002017 | 100029075903 | Wood Pole | Non-HFTD | Distribution | 2026-06-04 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002018 | 100029064547 | Wood Pole | HFTD Tier 3 | Distribution | 2026-06-01 | 2026-12-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002019 | 100029200016 | Wood Pole | Non-HFTD | Distribution | 2026-07-01 | 2029-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002020 | 100028744085 | Wood Pole | Non-HFTD | Distribution | 2026-02-24 | 2029-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002021 | 100029192465 | Wood Pole | Non-HFTD | Distribution | 2026-06-24 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002022 | 100028584652 | Pole | Non-HFTD | Distribution | 2026-01-16 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002023 | 100028527634 | Pole | Non-HFTD | Distribution | 2026-01-08 | 2029-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002024 | 100029085982 | Wood Pole | Non-HFTD | Distribution | 2026-06-01 | 2029-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002025 | 100028166013 | Other | HFTD Tier 3 | Distribution | 2025-10-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002026 | 100028176606 | Other | HFTD Tier 2 | Distribution | 2025-10-30 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002027 | 100028166010 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002028 | 100028033917 | Pole | HFTD Tier 3 | Distribution | 2025-09-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002029 | 100028098465 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-10-06 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002030 | 100028158974 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002031 | 100028125908 | Cross Arm | HFTD Tier 2 | Distribution | 2025-08-11 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002032 | 100028166007 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002033 | 100028176607 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-30 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002034 | 100028146095 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-22 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002035 | 100028166008 | Pole | HFTD Tier 3 | Distribution | 2025-10-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002036 | 100028166006 | Other | HFTD Tier 3 | Distribution | 2025-10-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002037 | 100028138532 | Other | HFTD Tier 2 | Distribution | 2025-10-16 | 2026-12-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002038 | 100028053616 | Pole | HFTD Tier 3 | Distribution | 2025-09-23 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002039 | 100028176593 | Pole | HFTD Tier 3 | Distribution | 2025-10-30 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002040 | 100028138190 | Pole | HFTD Tier 3 | Distribution | 2025-10-20 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002041 | 100028188486 | Pole | HFTD Tier 3 | Distribution | 2025-11-03 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002042 | 100028213277 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-11 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002043 | 100028333210 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-12-08 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002044 | 100028333209 | Other | HFTD Tier 3 | Distribution | 2025-12-08 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002045 | 100028096584 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-06 | 2026-04-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002046 | 100028259098 | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002047 | 100028021209 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-09-10 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002048 | 100028220307 | Pole | HFTD Tier 3 | Distribution | 2025-11-14 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002049 | 100028095624 | Pole | HFTD Tier 3 | Distribution | 2025-10-06 | 2026-04-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002050 | 100028138191 | Pole | HFTD Tier 3 | Distribution | 2025-10-20 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002051 | 100027802659 | Cross Arm | HFTD Tier 2 | Distribution | 2025-05-13 | 2026-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002052 | 100028018512 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002053 | 100028208053 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002054 | 100028220306 | Pole | HFTD Tier 3 | Distribution | 2025-11-14 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002055 | 100028216073 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-12 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002056 | 100028096583 | Wood Pole | HFTD Tier 3 | Distribution | 2025-10-06 | 2030-12-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002057 | 100027733628 | Pole | HFTD Tier 2 | Distribution | 2025-06-17 | 2026-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002058 | 100028187874 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | 2027-01-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002059 | 100028018486 | Pole | HFTD Tier 3 | Distribution | 2025-09-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002060 | 100028021201 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-10 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002061 | 100028037691 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-16 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002062 | 100028123788 | Other | HFTD Tier 3 | Distribution | 2025-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002063 | 100027983794 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002064 | 100028234418 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-19 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002065 | 100026766313 | Cross Arm | Non-HFTD | Distribution | 2024-09-05 | 2028-01-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002066 | 100026267796 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002067 | 100027983251 | Pole | HFTD Tier 2 | Distribution | 2025-08-01 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002068 | 100025664760 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-13 | 2025-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002069 | 100028125720 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2026-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002070 | 100025979544 | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2025-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002071 | 100027101588 | Avian Protection | HFTD Tier 2 | Distribution | 2025-01-10 | 2026-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002072 | 100028029621 | Other | HFTD Tier 2 | Distribution | 2025-09-12 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002073 | 100028033915 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002074 | 100028289585 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-25 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002075 | 100028041030 | Switch | Non-HFTD | Distribution | 2025-09-12 | 2028-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002076 | 100028208041 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002077 | 100028138198 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-20 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002078 | 100028221002 | Ground Wire | HFTD Tier 2 | Distribution | 2025-11-14 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002079 | 100028208051 | Pole | HFTD Tier 3 | Distribution | 2025-11-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002080 | 100028289566 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-25 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002081 | 100028228999 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002082 | 100028018508 | Pole | HFTD Tier 3 | Distribution | 2025-09-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002083 | 100028338534 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002084 | 100028117870 | Cross Arm | Non-HFTD | Distribution | 2025-10-13 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002085 | 100027983217 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002086 | 100027505506 | Pole | HFTD Tier 2 | Distribution | 2025-04-16 | 2026-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002087 | 100028201508 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002088 | 100027980878 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002089 | 100028220304 | Pole | HFTD Tier 3 | Distribution | 2025-11-14 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002090 | 100028074817 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-29 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002091 | 100028098478 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-10-06 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002092 | 100028131487 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-17 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002093 | 100026701250 | Cross Arm | Non-HFTD | Distribution | 2024-10-11 | 2027-12-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002094 | 100027519390 | Pole | HFTD Tier 2 | Distribution | 2025-04-21 | 2026-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002095 | 100027705673 | Other | HFTD Tier 2 | Distribution | 2025-06-04 | 2026-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002096 | 100025905418 | Other | HFTD Tier 2 | Distribution | 2024-04-25 | 2025-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002097 | 100028053788 | Other | Non-HFTD | Distribution | 2025-09-23 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002098 | 100028201763 | Other | HFTD Tier 3 | Distribution | 2025-11-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002099 | 100028338544 | Other | HFTD Tier 2 | Distribution | 2025-12-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002100 | 100028053786 | Other | Non-HFTD | Distribution | 2025-09-23 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002101 | 100028053787 | Other | Non-HFTD | Distribution | 2025-09-23 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002102 | 100028018515 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002103 | 100028234415 | Pole | HFTD Tier 3 | Distribution | 2025-11-19 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002104 | 100028160371 | Pole | HFTD Tier 3 | Distribution | 2025-10-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002105 | 100028131483 | Pole | HFTD Tier 3 | Distribution | 2025-10-17 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002106 | 100027983215 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002107 | 100028096522 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-06 | 2026-04-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002108 | 100026403049 | Pole | Non-HFTD | Distribution | 2024-07-23 | 2027-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002109 | 100027643133 | Pole | HFTD Tier 3 | Distribution | 2025-05-21 | 2025-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002110 | 100027616866 | Pole | HFTD Tier 3 | Distribution | 2025-05-13 | 2025-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002111 | 100026267799 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002112 | 100028239600 | Transformer | HFTD Tier 2 | Distribution | 2025-11-21 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002113 | 100028184324 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002114 | 100028021208 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-10 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002115 | 100028021197 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-10 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002116 | 100028015760 | Pole | HFTD Tier 3 | Distribution | 2025-09-08 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002117 | 100028021222 | Transformer | HFTD Tier 2 | Distribution | 2025-09-10 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002118 | 100028104927 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-08 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002119 | 100028201754 | Pole | HFTD Tier 3 | Distribution | 2025-11-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002120 | 100028037711 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-09-16 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002121 | 100028128662 | Other | HFTD Tier 2 | Distribution | 2025-10-16 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002122 | 100028333215 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-08 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002123 | 100028149231 | Pole | HFTD Tier 2 | Distribution | 2025-10-23 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002124 | 100028333213 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-08 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002125 | 100027607201 | Wood Pole | HFTD Tier 2 | Distribution | 2025-05-08 | 2028-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002126 | 100026132564 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-03 | 2025-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002127 | 100028017937 | Pole | HFTD Tier 3 | Distribution | 2025-09-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002128 | 100028012991 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-05 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002129 | 100028104925 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-08 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002130 | 100028117872 | Insulator and Bushing | Non-HFTD | Distribution | 2025-10-13 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002131 | 100028146091 | Pole | HFTD Tier 3 | Distribution | 2025-10-22 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002132 | 100027983218 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002133 | 100027983216 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002134 | 100026683215 | Pole | HFTD Tier 3 | Distribution | 2024-10-11 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002135 | 100027101581 | Avian Protection | HFTD Tier 2 | Distribution | 2025-01-10 | 2026-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002136 | 100028085954 | Cross Arm | Non-HFTD | Distribution | 2025-09-30 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002137 | 100028018510 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002138 | 100028040328 | Pole | HFTD Tier 3 | Distribution | 2025-09-17 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002139 | 100028239587 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-21 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002140 | 100027815785 | Other | Non-HFTD | Distribution | 2025-07-09 | 2028-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002141 | 100028201764 | Pole | HFTD Tier 3 | Distribution | 2025-11-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002142 | 100028338545 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002143 | 100028131493 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-17 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002144 | 100025979542 | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2025-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002145 | 100028122511 | Pole | HFTD Tier 2 | Distribution | 2025-10-15 | 2026-12-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002146 | 100027101580 | Avian Protection | HFTD Tier 2 | Distribution | 2025-01-10 | 2026-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002147 | 100028009643 | Switch | Non-HFTD | Distribution | 2025-09-04 | 2028-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002148 | 100028329477 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-05 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002149 | 100028329455 | Pole | HFTD Tier 3 | Distribution | 2025-12-05 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002150 | 100028128668 | Pole | HFTD Tier 3 | Distribution | 2025-10-16 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002151 | 100028071598 | Other | HFTD Tier 2 | Distribution | 2025-09-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002152 | 100028404846 | Pole | HFTD Tier 2 | Distribution | 2025-12-19 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002153 | 100028075108 | Cross Arm | Non-HFTD | Distribution | 2025-09-29 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002154 | 100028098480 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-06 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002155 | 100028071599 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-09-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002156 | 100028234410 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-11-19 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002157 | 100025979543 | Anchor/Guy | HFTD Tier 2 | Distribution | 2024-05-10 | 2025-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002158 | 100028293743 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-26 | 2027-01-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002159 | 100025684401 | Pole | HFTD Tier 2 | Distribution | 2024-03-18 | 2025-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002160 | 100025911585 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-04-26 | 2025-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002161 | 100028021219 | Pole | HFTD Tier 3 | Distribution | 2025-09-10 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002162 | 100028040972 | Switch | Non-HFTD | Distribution | 2025-09-05 | 2028-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002163 | 100028128670 | Pole | HFTD Tier 3 | Distribution | 2025-10-16 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002164 | 100028037704 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-16 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002165 | 100028002795 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-09-02 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002166 | 100028074818 | Pole | HFTD Tier 3 | Distribution | 2025-09-29 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002167 | 100028345848 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-11 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002168 | 100028043100 | Pole | HFTD Tier 2 | Distribution | 2025-09-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002169 | 100028316784 | Pole | HFTD Tier 3 | Distribution | 2025-12-01 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002170 | 100028233168 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-19 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002171 | 100028278013 | Other | HFTD Tier 2 | Distribution | 2025-07-30 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002172 | 100028229000 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002173 | 100028021203 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-10 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002174 | 100028329473 | Pole | HFTD Tier 3 | Distribution | 2025-12-05 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002175 | 100028172120 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-29 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002176 | 100027983799 | Other | HFTD Tier 3 | Distribution | 2025-08-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002177 | 100027983240 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2026-02-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002178 | 100027936988 | Pole | HFTD Tier 2 | Distribution | 2025-08-18 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002179 | 100023598897 | Other | HFTD Tier 2 | Distribution | 2023-03-28 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002180 | 100024607587 | Cross Arm | HFTD Tier 2 | Distribution | 2023-10-03 | 2024-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002181 | 100025664762 | Pole | HFTD Tier 2 | Distribution | 2024-03-13 | 2025-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002182 | 100025996630 | Cross Arm | HFTD Tier 2 | Distribution | 2024-05-14 | 2025-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002183 | 100027803029 | Insulator and Bushing | Non-HFTD | Distribution | 2025-05-30 | 2028-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002184 | 100028029623 | Pole | HFTD Tier 2 | Distribution | 2025-09-12 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002185 | 100028338551 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002186 | 100028188689 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002187 | 100027990110 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-29 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002188 | 100025926874 | Pole | HFTD Tier 2 | Distribution | 2024-04-30 | 2025-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002189 | 100027907991 | Wood Pole | HFTD Tier 2 | Distribution | 2025-08-05 | 2030-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002190 | 100024226061 | Pole | HFTD Tier 2 | Distribution | 2023-07-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002191 | 100028123798 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002192 | 100028289597 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-25 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002193 | 100028228991 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002194 | 100028060356 | Cross Arm | Non-HFTD | Distribution | 2025-09-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002195 | 100028333212 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-08 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002196 | 100028015757 | Anchor/Guy | HFTD Tier 3 | Distribution | 2025-09-08 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002197 | 100028098479 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-06 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002198 | 100028197468 | Transformer | HFTD Tier 2 | Distribution | 2025-11-05 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002199 | 100028029126 | Pole | HFTD Tier 2 | Distribution | 2025-09-12 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002200 | 100028125082 | Other | HFTD Tier 2 | Distribution | 2025-09-02 | 2026-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002201 | 100027077528 | Pole | HFTD Tier 2 | Distribution | 2025-01-02 | 2026-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002202 | 100028123795 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002203 | 100028040336 | Pole | HFTD Tier 3 | Distribution | 2025-09-17 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002204 | 100028034460 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002205 | 100028029632 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-12 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002206 | 100028008019 | Insulator and Bushing | Non-HFTD | Distribution | 2025-09-04 | 2028-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002207 | 100028229004 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002208 | 100028050960 | Pole | Non-HFTD | Distribution | 2025-09-22 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002209 | 100027983792 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002210 | 100028010207 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-09-04 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002211 | 100028122510 | Other | HFTD Tier 2 | Distribution | 2025-10-15 | 2026-12-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002212 | 100026683217 | Pole | HFTD Tier 3 | Distribution | 2024-10-11 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002213 | 100026935312 | Pole | HFTD Tier 2 | Distribution | 2024-12-10 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002214 | 100026267781 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002215 | 100028037705 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-16 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002216 | 100028053789 | Other | Non-HFTD | Distribution | 2025-09-23 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002217 | 100028128650 | Pole | HFTD Tier 2 | Distribution | 2025-10-16 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002218 | 100028228996 | Pole | HFTD Tier 2 | Distribution | 2025-11-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002219 | 100025656507 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-12 | 2025-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002220 | 100028077661 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-30 | 2026-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002221 | 100026267786 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002222 | 100028184325 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002223 | 100028176591 | Pole | HFTD Tier 3 | Distribution | 2025-10-30 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002224 | 100028188686 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-11-03 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002225 | 100028068723 | Cross Arm | Non-HFTD | Distribution | 2025-09-25 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002226 | 100028193080 | Other | HFTD Tier 2 | Distribution | 2025-11-04 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002227 | 100028071920 | Pole | HFTD Tier 2 | Distribution | 2025-09-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002228 | 100028293798 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002229 | 100027712864 | Cross Arm | HFTD Tier 2 | Distribution | 2025-06-06 | 2026-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002230 | 100025964998 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2024-05-07 | 2024-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002231 | 100025664759 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-03-13 | 2025-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002232 | 100028029634 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-12 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002233 | 100028201753 | Other | HFTD Tier 2 | Distribution | 2025-11-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002234 | 100028201758 | Pole | HFTD Tier 3 | Distribution | 2025-11-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002235 | 100028116948 | Other | HFTD Tier 2 | Distribution | 2025-10-13 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002236 | 100028098477 | Pole | HFTD Tier 3 | Distribution | 2025-10-06 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002237 | 100028237014 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-20 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002238 | 100026672795 | Switch | Non-HFTD | Distribution | 2024-09-30 | 2027-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002239 | 100028021218 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-09-10 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002240 | 100028228995 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002241 | 100028018499 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002242 | 100028012990 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-05 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002243 | 100028218874 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-13 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002244 | 100028123790 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002245 | 100028166000 | Pole | HFTD Tier 2 | Distribution | 2025-10-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002246 | 100027981055 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002247 | 100028345844 | Pole | HFTD Tier 3 | Distribution | 2025-12-11 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002248 | 100028075112 | Pole | Non-HFTD | Distribution | 2025-09-29 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002249 | 100028188681 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-03 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002250 | 100028108573 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002251 | 100027983214 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2025-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002252 | 100028077662 | Pole | HFTD Tier 2 | Distribution | 2025-09-30 | 2026-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002253 | 100028338541 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002254 | 100028128659 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-16 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002255 | 100028053785 | Other | Non-HFTD | Distribution | 2025-09-23 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002256 | 100028201759 | Pole | HFTD Tier 3 | Distribution | 2025-11-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002257 | 100028176590 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-30 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002258 | 100028218890 | Ground Wire | HFTD Tier 2 | Distribution | 2025-11-13 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002259 | 100027981058 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002260 | 100028220305 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-14 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002261 | 100028098476 | Pole | HFTD Tier 3 | Distribution | 2025-10-06 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002262 | 100027963438 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-25 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002263 | 100028233169 | Pole | HFTD Tier 2 | Distribution | 2025-11-19 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002264 | 100028043107 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002265 | 100027980876 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002266 | 100025656501 | Cross Arm | HFTD Tier 2 | Distribution | 2024-03-12 | 2025-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002267 | 100028096210 | Wood Pole | HFTD Tier 3 | Distribution | 2025-10-06 | 2030-12-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002268 | 100028117867 | Pole | Non-HFTD | Distribution | 2025-10-13 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002269 | 100028034461 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002270 | 100028338549 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002271 | 100028029635 | Pole | HFTD Tier 3 | Distribution | 2025-09-12 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002272 | 100028228997 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002273 | 100028338539 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002274 | 100028068716 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-09-25 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002275 | 100028075111 | Anchor/Guy | Non-HFTD | Distribution | 2025-09-29 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002276 | 100028050957 | Capacitor Bank | Non-HFTD | Distribution | 2025-09-22 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002277 | 100028188692 | Pole | HFTD Tier 2 | Distribution | 2025-11-03 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002278 | 100025596658 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2024-02-29 | 2025-02-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002279 | 100028101301 | Other | HFTD Tier 3 | Distribution | 2025-10-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002280 | 100028103011 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-03 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002281 | 100028184317 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002282 | 100028021199 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-10 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002283 | 100028123588 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002284 | 100028037701 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-16 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002285 | 100028332853 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-12-08 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002286 | 100026726329 | Cross Arm | HFTD Tier 2 | Distribution | 2024-10-23 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002287 | 100028239586 | Pole | HFTD Tier 2 | Distribution | 2025-11-21 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002288 | 100028208040 | Pole | HFTD Tier 3 | Distribution | 2025-11-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002289 | 100028338550 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-12-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002290 | 100027981056 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002291 | 100028237031 | Other | HFTD Tier 3 | Distribution | 2025-11-20 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002292 | 100028085957 | Conductor - Veg | Non-HFTD | Distribution | 2025-09-30 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002293 | 100028188693 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-03 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002294 | 100026267708 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002295 | 100026683216 | Other | HFTD Tier 3 | Distribution | 2024-10-11 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002296 | 100028218879 | Transformer | HFTD Tier 2 | Distribution | 2025-11-13 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002297 | 100028329135 | Other | HFTD Tier 2 | Distribution | 2025-12-05 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002298 | 100028034457 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002299 | 100028034464 | Other | HFTD Tier 3 | Distribution | 2025-09-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002300 | 100028329480 | Pole | HFTD Tier 3 | Distribution | 2025-12-05 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002301 | 100028123794 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002302 | 100028029128 | Other | HFTD Tier 2 | Distribution | 2025-09-12 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002303 | 100028075110 | Anchor/Guy | Non-HFTD | Distribution | 2025-09-29 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002304 | 100028234416 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-19 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002305 | 100027983791 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002306 | 100023644150 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2023-04-06 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002307 | 100027101579 | Avian Protection | HFTD Tier 2 | Distribution | 2025-01-10 | 2026-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002308 | 100028338547 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002309 | 100028025665 | Other | HFTD Tier 3 | Distribution | 2025-09-11 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002310 | 100028208050 | Pole | HFTD Tier 3 | Distribution | 2025-11-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002311 | 100028226276 | Pole | HFTD Tier 3 | Distribution | 2025-11-17 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002312 | 100028316787 | Other | HFTD Tier 3 | Distribution | 2025-12-01 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002313 | 100028068724 | Pole | Non-HFTD | Distribution | 2025-09-25 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002314 | 100027016345 | Cross Arm | Non-HFTD | Distribution | 2024-12-16 | 2028-02-29 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002315 | 100027053944 | Cross Arm | HFTD Tier 2 | Distribution | 2024-12-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002316 | 100025979546 | Pole | HFTD Tier 2 | Distribution | 2024-05-10 | 2025-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002317 | 100027918059 | Pole | HFTD Tier 3 | Distribution | 2025-08-08 | 2028-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002318 | 100028009642 | Insulator and Bushing | Non-HFTD | Distribution | 2025-09-04 | 2028-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002319 | 100028029651 | Pole | HFTD Tier 3 | Distribution | 2025-09-12 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002320 | 100028108572 | Pole | HFTD Tier 3 | Distribution | 2025-10-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002321 | 100028149218 | Pole | HFTD Tier 2 | Distribution | 2025-10-23 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002322 | 100028316783 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-01 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002323 | 100028193065 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-04 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002324 | 100028094846 | Pole | HFTD Tier 3 | Distribution | 2025-10-03 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002325 | 100028122369 | Conductor | HFTD Tier 2 | Distribution | 2025-10-15 | 2026-12-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002326 | 100027643132 | Pole | HFTD Tier 3 | Distribution | 2025-05-21 | 2025-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002327 | 100028126206 | Conductor | HFTD Tier 2 | Distribution | 2025-06-04 | 2026-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002328 | 100028338542 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002329 | 100028128660 | Other | HFTD Tier 2 | Distribution | 2025-10-16 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002330 | 100028034456 | Pole | HFTD Tier 3 | Distribution | 2025-09-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002331 | 100028123787 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002332 | 100027805654 | Other | Non-HFTD | Distribution | 2025-05-30 | 2028-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002333 | 100028108577 | Pole | HFTD Tier 2 | Distribution | 2025-10-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002334 | 100028220997 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-14 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002335 | 100024607585 | Pole | HFTD Tier 2 | Distribution | 2023-10-03 | 2024-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002336 | 100028119816 | Other | Non-HFTD | Distribution | 2025-10-14 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002337 | 100027981053 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002338 | 100025905419 | Transformer | HFTD Tier 2 | Distribution | 2024-04-25 | 2025-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002339 | 100028184323 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002340 | 100028228698 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002341 | 100028060351 | Pole | HFTD Tier 3 | Distribution | 2025-09-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002342 | 100028037680 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-16 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002343 | 100028239604 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-21 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002344 | 100028021202 | Pole | HFTD Tier 3 | Distribution | 2025-09-10 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002345 | 100028123786 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002346 | 100028345849 | Pole | HFTD Tier 3 | Distribution | 2025-12-11 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002347 | 100028050958 | Insulator and Bushing | Non-HFTD | Distribution | 2025-09-22 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002348 | 100028216069 | Pole | HFTD Tier 2 | Distribution | 2025-11-12 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002349 | 100027983564 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002350 | 100028131488 | Other | HFTD Tier 2 | Distribution | 2025-10-17 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002351 | 100028239583 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-11-21 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002352 | 100028166001 | Pole | HFTD Tier 2 | Distribution | 2025-10-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002353 | 100028015773 | Pole | HFTD Tier 3 | Distribution | 2025-09-08 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002354 | 100028037426 | Pole | HFTD Tier 3 | Distribution | 2025-09-16 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002355 | 100028104928 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-08 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002356 | 100027963439 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-25 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002357 | 100028117871 | Other | Non-HFTD | Distribution | 2025-10-13 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002358 | 100028234422 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-11-19 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002359 | 100027060310 | Cross Arm | HFTD Tier 2 | Distribution | 2024-11-13 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002360 | 100027157833 | Switch | HFTD Tier 2 | Distribution | 2025-01-23 | 2026-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002361 | 100025911586 | Conductor | HFTD Tier 2 | Distribution | 2024-04-26 | 2025-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002362 | 100027078212 | Pole | HFTD Tier 2 | Distribution | 2025-01-02 | 2026-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002363 | 100028239588 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-21 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002364 | 100028123780 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002365 | 100028218887 | Pole | HFTD Tier 2 | Distribution | 2025-11-13 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002366 | 100028123784 | Other | HFTD Tier 3 | Distribution | 2025-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002367 | 100028085956 | Cross Arm | Non-HFTD | Distribution | 2025-09-30 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002368 | 100027983795 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002369 | 100028138200 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-20 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002370 | 100027983797 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002371 | 100028029622 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-12 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002372 | 100028259099 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002373 | 100028123791 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002374 | 100028208043 | Pole | HFTD Tier 3 | Distribution | 2025-11-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002375 | 100028071926 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002376 | 100028146105 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-22 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002377 | 100028071595 | Pole | HFTD Tier 2 | Distribution | 2025-09-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002378 | 100028316780 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-01 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002379 | 100027504716 | Pole | HFTD Tier 2 | Distribution | 2025-04-16 | 2026-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002380 | 100028073627 | Pole | HFTD Tier 2 | Distribution | 2025-09-29 | 2026-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002381 | 100027914798 | Cross Arm | HFTD Tier 2 | Distribution | 2025-08-07 | 2026-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002382 | 100028046660 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-09-19 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002383 | 100028289568 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002384 | 100028029633 | Other | HFTD Tier 3 | Distribution | 2025-09-12 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002385 | 100028025672 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-11 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002386 | 100028259092 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002387 | 100028123797 | Other | HFTD Tier 3 | Distribution | 2025-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002388 | 100028018485 | Pole | HFTD Tier 3 | Distribution | 2025-09-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002389 | 100028131484 | Pole | HFTD Tier 3 | Distribution | 2025-10-17 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002390 | 100028193068 | Pole | HFTD Tier 2 | Distribution | 2025-11-04 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002391 | 100028333216 | Other | HFTD Tier 2 | Distribution | 2025-12-08 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002392 | 100028184319 | Pole | HFTD Tier 3 | Distribution | 2025-10-31 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002393 | 100028034442 | Other | HFTD Tier 3 | Distribution | 2025-09-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002394 | 100028021215 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-10 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002395 | 100028149215 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-23 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002396 | 100028040324 | Pole | HFTD Tier 3 | Distribution | 2025-09-17 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002397 | 100028289580 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-25 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002398 | 100028149232 | Transformer | HFTD Tier 2 | Distribution | 2025-10-23 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002399 | 100027980879 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002400 | 100028077292 | Conductor | HFTD Tier 2 | Distribution | 2025-09-30 | 2026-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002401 | 100027617034 | Pole | HFTD Tier 3 | Distribution | 2025-05-13 | 2025-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002402 | 100026132409 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-03 | 2025-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002403 | 100028075101 | Other | HFTD Tier 2 | Distribution | 2025-09-29 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002404 | 100028289567 | Pole | HFTD Tier 2 | Distribution | 2025-11-25 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002405 | 100028329472 | Pole | HFTD Tier 3 | Distribution | 2025-12-05 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002406 | 100028123586 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002407 | 100028012971 | Pole | HFTD Tier 3 | Distribution | 2025-09-05 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002408 | 100028021220 | Other | HFTD Tier 3 | Distribution | 2025-09-10 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002409 | 100028123589 | Ground Wire | HFTD Tier 3 | Distribution | 2025-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002410 | 100027978120 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-25 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002411 | 100028188685 | Pole | HFTD Tier 3 | Distribution | 2025-11-03 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002412 | 100027981054 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002413 | 100028043101 | Pole | HFTD Tier 2 | Distribution | 2025-09-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002414 | 100028396836 | Other | HFTD Tier 2 | Distribution | 2025-12-17 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002415 | 100025656487 | Pole | HFTD Tier 2 | Distribution | 2024-03-12 | 2025-03-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002416 | 100023644152 | Other | HFTD Tier 2 | Distribution | 2023-04-06 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002417 | 100024226059 | Pole | HFTD Tier 2 | Distribution | 2023-07-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002418 | 100028228992 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002419 | 100028239599 | Pole | HFTD Tier 2 | Distribution | 2025-11-21 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002420 | 100028021214 | Other | HFTD Tier 3 | Distribution | 2025-09-10 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002421 | 100028228699 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002422 | 100028021221 | Other | HFTD Tier 3 | Distribution | 2025-09-10 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002423 | 100028220303 | Pole | HFTD Tier 3 | Distribution | 2025-11-14 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002424 | 100028396835 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-12-17 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002425 | 100028075107 | Cross Arm | Non-HFTD | Distribution | 2025-09-29 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002426 | 100026768782 | Cross Arm | Non-HFTD | Distribution | 2024-11-01 | 2028-01-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002427 | 100026768781 | Cross Arm | Non-HFTD | Distribution | 2024-11-01 | 2028-01-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002428 | 100026267784 | Cross Arm | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002429 | 100028228994 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002430 | 100028040332 | Pole | HFTD Tier 3 | Distribution | 2025-09-17 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002431 | 100028218873 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-13 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002432 | 100028029637 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-12 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002433 | 100028053612 | Other | HFTD Tier 3 | Distribution | 2025-09-23 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002434 | 100028332854 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-08 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002435 | 100027981052 | Cross Arm | HFTD Tier 3 | Distribution | 2025-08-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002436 | 100028278014 | Other | HFTD Tier 2 | Distribution | 2025-07-30 | 2026-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002437 | 100028218880 | Pole | HFTD Tier 2 | Distribution | 2025-11-13 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002438 | 100028329478 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-05 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002439 | 100027743744 | Switch | Non-HFTD | Distribution | 2025-06-13 | 2028-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002440 | 100028029638 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-12 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002441 | 100028042488 | Cross Arm | HFTD Tier 3 | Distribution | 2025-09-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002442 | 100028236779 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002443 | 100027983567 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002444 | 100028316781 | Pole | HFTD Tier 3 | Distribution | 2025-12-01 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002445 | 100028149214 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-23 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002446 | 100026788858 | Cross Arm | Non-HFTD | Distribution | 2024-11-05 | 2028-01-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002447 | 100026437414 | Cross Arm | HFTD Tier 2 | Distribution | 2024-08-05 | 2025-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002448 | 100026585051 | Transformer | HFTD Tier 2 | Distribution | 2024-09-13 | 2025-11-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002449 | 100023693412 | Pole | HFTD Tier 2 | Distribution | 2023-04-17 | 2024-04-29 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002450 | 100028259102 | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002451 | 100028239603 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-21 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002452 | 100028338543 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002453 | 100028259103 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002454 | 100028025673 | Pole | HFTD Tier 2 | Distribution | 2025-09-11 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002455 | 100028060358 | Cross Arm | Non-HFTD | Distribution | 2025-09-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002456 | 100028025698 | Pole | HFTD Tier 3 | Distribution | 2025-09-11 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002457 | 100028225838 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-17 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002458 | 100028138192 | Pole | HFTD Tier 3 | Distribution | 2025-10-20 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002459 | 100028333214 | Other | HFTD Tier 2 | Distribution | 2025-12-08 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002460 | 100028119705 | Other | Non-HFTD | Distribution | 2025-10-14 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002461 | 100027224636 | Anchor/Guy | HFTD Tier 2 | Distribution | 2025-02-03 | 2026-04-28 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002462 | 100028034443 | Pole | HFTD Tier 3 | Distribution | 2025-09-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002463 | 100028259104 | Pole | HFTD Tier 2 | Distribution | 2025-11-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002464 | 100028158973 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002465 | 100028138193 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-20 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002466 | 100028220999 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-14 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002467 | 100028316790 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-01 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002468 | 100028169593 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-28 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002469 | 100027505825 | Pole | HFTD Tier 2 | Distribution | 2025-04-16 | 2026-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002470 | 100028228998 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002471 | 100028037706 | Cross Arm | HFTD Tier 2 | Distribution | 2025-09-16 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002472 | 100027805436 | Insulator and Bushing | Non-HFTD | Distribution | 2025-05-30 | 2028-07-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002473 | 100028237018 | Pole | HFTD Tier 2 | Distribution | 2025-11-20 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002474 | 100028111735 | Cross Arm | HFTD Tier 3 | Distribution | 2025-10-10 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002475 | 100028316619 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-01 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002476 | 100028316788 | Cross Arm | HFTD Tier 3 | Distribution | 2025-12-01 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002477 | 100027983796 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002478 | 100028332855 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-12-08 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002479 | 100028188690 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-03 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002480 | 100028117869 | Pole | Non-HFTD | Distribution | 2025-10-13 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002481 | 100027989609 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-29 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002482 | 100025883031 | Avian Protection | HFTD Tier 2 | Distribution | 2024-04-24 | 2025-06-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002483 | 100028029125 | Pole | HFTD Tier 2 | Distribution | 2025-09-12 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002484 | 100028146098 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-22 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002485 | 100027397850 | Pole | HFTD Tier 2 | Distribution | 2025-03-20 | 2026-05-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002486 | 100028012976 | Pole | HFTD Tier 3 | Distribution | 2025-09-05 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002487 | 100028289598 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-11-25 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002488 | 100028234414 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-19 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002489 | 100028046397 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-09-19 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002490 | 100027983800 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-08-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002491 | 100028146108 | Pole | HFTD Tier 2 | Distribution | 2025-10-22 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002492 | 100028396834 | Cross Arm | HFTD Tier 2 | Distribution | 2025-12-17 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002493 | 100026729769 | Pole | HFTD Tier 2 | Distribution | 2024-10-24 | 2025-12-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002494 | 100026374171 | Wood Pole | HFTD Tier 2 | Distribution | 2024-07-23 | 2027-09-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002495 | 100026267790 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002496 | 100028259095 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002497 | 100028029650 | Other | HFTD Tier 3 | Distribution | 2025-09-12 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002498 | 100028034469 | Insulator and Bushing | HFTD Tier 3 | Distribution | 2025-09-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002499 | 100028139098 | Other | HFTD Tier 2 | Distribution | 2025-10-20 | 2026-12-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002500 | 100028229005 | Pole | HFTD Tier 3 | Distribution | 2025-11-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002501 | 100028123785 | Pole | HFTD Tier 3 | Distribution | 2025-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002502 | 100028149225 | Cross Arm | HFTD Tier 2 | Distribution | 2025-10-23 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002503 | 100028188691 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-03 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002504 | 100028221001 | Cross Arm | HFTD Tier 3 | Distribution | 2025-11-14 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002505 | 100027722978 | Pole | HFTD Tier 2 | Distribution | 2025-06-11 | 2026-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002506 | 100026267793 | Pole | HFTD Tier 2 | Distribution | 2024-06-28 | 2025-08-30 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002507 | 100024607586 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2023-10-03 | 2024-10-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002508 | 100028259091 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002509 | 100028037710 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2025-09-16 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002510 | 100028338540 | Pole | HFTD Tier 2 | Distribution | 2025-12-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002511 | 100028228993 | Cross Arm | HFTD Tier 2 | Distribution | 2025-11-18 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002512 | 100028050959 | Cross Arm | Non-HFTD | Distribution | 2025-09-22 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002513 | 100028234423 | Other | HFTD Tier 2 | Distribution | 2025-11-19 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002514 | 100028116494 | Avian Protection | HFTD Tier 2 | Distribution | 2025-10-13 | 2026-12-31 | Level 2 | [8 empty] | SDG&E | 2026 | 2
1120002515 | P280407_2022-01-04_I241 | Cross Arm | HFTD Tier 2 | Distribution | 2022-01-04 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002516 | P576675_2022-09-27_I246 | Pole | HFTD Tier 2 | Distribution | 2022-09-27 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002517 | P86056_2021-11-13_I206 | Other | HFTD Tier 2 | Distribution | 2021-11-13 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002518 | P86042_2022-01-09_I246 | Pole | HFTD Tier 2 | Distribution | 2022-01-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002519 | P42270_2021-11-24_I246 | Pole | HFTD Tier 2 | Distribution | 2021-11-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002520 | P714994_2022-04-14_I241 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-14 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002521 | P371204_2021-11-19_I241 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-19 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002522 | P819071_2021-10-15_I246 | Pole | HFTD Tier 2 | Distribution | 2021-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002523 | P217016_2021-11-02_I235 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-11-02 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002524 | P42269_2021-11-24_I235 | Insulator and Bushing | HFTD Tier 2 | Distribution | 2021-11-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002525 | P471899_2021-12-20_I246 | Pole | HFTD Tier 3 | Distribution | 2021-12-20 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002526 | P214757_2021-11-24_I241 | Cross Arm | HFTD Tier 2 | Distribution | 2021-11-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002527 | P819071_2021-10-15_I206 | Other | HFTD Tier 2 | Distribution | 2021-10-15 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002528 | P811934_2022-04-19_I241 | Cross Arm | HFTD Tier 2 | Distribution | 2022-04-19 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002529 | P117588_2021-10-04_I241 | Cross Arm | HFTD Tier 2 | Distribution | 2021-10-04 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002530 | P86045_2022-01-09_I246 | Pole | HFTD Tier 2 | Distribution | 2022-01-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002531 | P42272_2021-11-24_I246 | Pole | HFTD Tier 2 | Distribution | 2021-11-24 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002532 | P86051_2022-01-09_I246 | Pole | HFTD Tier 2 | Distribution | 2022-01-09 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002533 | P42268_2022-07-21_I246 | Pole | HFTD Tier 2 | Distribution | 2022-07-21 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002534 | P42265_2023-01-16_I246 | Pole | HFTD Tier 2 | Distribution | 2023-01-16 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002535 | P42266_2022-12-07-I246 | Pole | HFTD Tier 2 | Distribution | 2022-12-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002536 | P42267_2022-12-07_I246 | Pole | HFTD Tier 2 | Distribution | 2022-12-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002537 | P42273_2022-12-07_I246 | Pole | HFTD Tier 2 | Distribution | 2022-12-07 | [9 empty] | Not Applicable | SDG&E | 2026 | 2
1120002538 | P86055_2026-02-26_I246 | Pole | HFTD Tier 2 | Distribution | 2026-02-26 | [9 empty] | Not Applicable | SDG&E | 2026 | 2